Title: Infrastructure and Cities for Economic Development (ICED)
Programme Value £ (full life): £33,500,000 (of which £8m ICF)		Review date: 24th July 2020
Programme Code: 204250	AMP start date: March 2015 (with varying dates for implementing partners)	AMP end date: September 2020 (implementation period 5 years, / with shorter periods for individual components and partners, including ICED Facility)

Summary of Programme Performance
Year	2015/16	2016/17	2017/18	2018/19	2019/2020
Overall Output Score	A	A	A	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204250 / Specific link to BC http://iati.dfid.gov.uk/iati_documents/4961485.odt
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-1-204250

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme

DFID is providing £33.5 million to the Infrastructure and Cities for Economic Development (ICED) programme over five years, from March 2015 to September 2020.

This annual review covers the reporting period from March 2019 to July 2020. The Covid-19 pandemic has impacted the programme, preventing partners from providing technical assistance to government ministries and delaying the launch of key policy reports. Partners have responded to such constraints, adapting their support to reflect and the new challenges facing governments, cities and local communities. Overall, partners were able to adapt sufficiently to avoid any significant impact on delivery against targets.

This project supports DFID and our development partners through:
- Improving the enabling environment for sustainable, inclusive growth-enhancing infrastructure service delivery in DFID focus countries; and,
- Harnessing the benefits of cities for sustainable economic growth and poverty reduction in DFID focus countries.

Some of this work is delivered by assisting DFID Country Offices to scale up bilateral programming; other work is focused on international influencing and delivery of global public goods, in addition to cross Whitehall working to strengthen the UK offer on infrastructure.

The expected impact is: An improved enabling environment for infrastructure service delivery and better managed and governed cities as drivers of inclusive economic growth in DFID focus countries.

The expected outcome is: DFID scales up, enhances coordination and improves the quality of its country/regional/central-level support for an improved enabling environment for infrastructure and planning for cities (including in our most fragile and conflict-affected states). This is achieved through the following outputs and partners:

At the country level, and to support DFID’s policy globally:
Outputs 1, 2 and 3 - The ICED Facility includes PWC, Adam Smith International, Engineers Against Poverty, the International Institute for Environment & Development, Social Development Direct, MDY Legal and ARUP. The Facility provides support to DFID Country Offices and central/regional departments to enhance existing urban and infrastructure programmes and identify opportunities for new programming. These components closed four months after the start of the reporting year as planned.

At the global level:
- Output 4 - Scale up and enhance the impact of CoST activities to reduce corruption and increase value for money in public sector funded construction projects.
- Output 5 - World Bank: Improved analytics and diagnostics, planning of economic reforms and institutional and skills development in cities. This component was completed before this reporting year and is therefore not assessed.
- Output 6 - Shape the strategic priorities of the Cities Alliance and develop and implement its economic growth programming.
- Output 7 - support the Coalition for Urban Transitions, which seeks to build the case for national level support to urban development in developing countries. This component was established in April 2017.
- Output 8 - Strategic Opportunities Fund (SOF) - to enable additional high priority activities that support this programme’s objectives.

Summary supporting narrative for the overall score in this review

The overall programme score is A+.

The ICED Facility’s strong performance since last year continued. High demand for its services, from country offices and other government departments (OGDs), continued and meant the budget was fully accounted for before the end of the programme. The achievements of the Facility are outlined in section C: overall, it succeeded in scaling up urban and infrastructure programming across country offices and OGDs and seeded the development of a new, more ambitious programme, the Centre for Resilient Cities and Infrastructure.

CoST and the Cities Alliance continued to deliver against their expected outcome indicators. The Coalition for Urban Transition (CUT) produced a flagship report (Climate Emergency, Urban Opportunity) which was launched at the UN Climate Change Summit. CoST continued to expand its membership and its work yielded significant cost savings for governments in Uganda, Afghanistan and Thailand.

The Strategic Opportunities Fund (SOF) was effectively deployed to support key initiatives including the International Development Infrastructure Commission, an Independent Review of CoST and the World Resources Report which will focus on the conditions required for promoting the development of equitable cities in the Global South.

The relative weight of different outputs has been changed to reflect the level of effort and spend across the various components. The ICED Facility, for example, was operational for only four months of the reporting year but nevertheless produced substantive deliverables and accounted for a significant amount of programme spend.

Overall progress and major lessons

The programme’s strong performance, underpinned by the success of the ICED Facility, continued to deliver high quality outputs in year five. Cities Alliance and the Coalition for Urban Transitions continued to perform well, meeting and/or exceeding their targets not least by producing high quality policy reports that have informed debates related to the development of local economic growth in secondary cities and the opportunities for city governments to respond to the impacts of the climate change. CoST is on track to meet most of its output indicators. Importantly, it succeeded in meeting its target to secure additional funding for its new business plan and expanded its membership in key DFID geographies (Mozambique and Ghana). Ensuring successful closure of the programme by supporting the completion of partners’ work in the final phase will be important. In practice, this means being responsive to CoST’s and WRI’s needs over the next three months and ensuring that the project completion review is executed to a high standard such that it provides a framework for the successful inception of the new programme.

Recommendations for the year ahead
As the programme enters its final phase, the recommendations are focused on ensuring a successful transition (to a new programme) and supporting partners to continue to deliver amidst the uncertainty caused by the COVID public health crisis. The recommendations below are also relevant to the project completion review.
Build on the successful features of ICED by designing a new programme that responds to the opportunities and challenges of the post-COVID recovery. The demand for and uptake of ICED services, the successful delivery of outputs and the progress towards the impact underpin the case for a follow up programme. Effective urban planning and infrastructure will play a key role in the recovery from the COVID pandemic, and ambitions to build back better and greener. Assessing the case for this should be a focus of the project completion report.

Apply the insights of partners work to relevant FCDO policies and strategies. Since its inception, the ICED programme has funded a number of key policy deliverables delivered by a range of partners including the Coalition for Urban Transitions, World Resources Institute (WRI) and Cities Alliance. Deploying the policy insights, including those below, from these deliverables will be relevant to:
  - COP 26: aligning national economic policies behind compact and connected cities by developing policies that enable cities to effectively manage density and shifting national transport budgets from road building to public and active transport.
  - New urban programmes: supporting the development of cities’ informal economy by integrating informal businesses and activities into priority (formal) value chains, a measure that will be even more important due to the impact of the public health crisis on local economies.

Consider extending the time horizon of the new (ICED) programme. Many of the DFID programmes that the Facility supported are in design phase and hence assessing their full impact at this point in time is not possible. The project completion review should take account the need for a longer time horizon for DFID infrastructure programmes to reflect the life cycle of infrastructure projects – a point that the Independent Commission for Aid Impact (ICAI) review (October 2018) of DFID’s transport and urban infrastructure investments highlighted.

Use the project completion report to provide an assessment of the uptake and impact of knowledge and learning products/events among internal and external partners. Expertise in-house will be at least as important in the FCDO as it is currently in DFID and FCO. The learning outputs delivered by the Facility will be important for supporting advisers to design programmes that enable UKG partner governments to build back better and greener. In the aftermath of the pandemic, urban planning and infrastructure delivery will be essential in enhancing the resilience of the health and economic sectors across FCDO geographies.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

There were no changes to the programme’s theory of change as its main parameters remain relevant to the process of building back better and greener. However, it is important to note that DFID urban and infrastructure programmes supported by the ICED facility will be recasting their theories of change in response to the crisis.

The programme continues to work at two broad levels of action (the national and the global) and its sustained progress across all components means that it continues to make a substantive contribution to the development of a better enabling environment for infrastructure and urban planning and to inclusive economic growth in DFID focus countries.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track. A no cost extension (to September 2020) was agreed to ensure all programme partners (CoST, Cities Alliance, World Resources Institute) and strategic research activities (funded by the SOF) can be completed to a high standard despite the disruption created by the Covid-19 pandemic.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme will end in September 2020. Its strong performance has seeded the design of a new programme, the Centre for Resilient Cities and Infrastructure, which will build on the success of the ICED programme.

Progress towards outcomes

All components have performed well, meeting or exceeding their output targets. In doing so, they have supported the creation of a stronger enabling environment such that the programme is on track to deliver against its impact statement. The Project Completion Review will provide an opportunity to assess the programme’s impact in terms of the specific programmes that the Facility has supported, some of which will be in early implementation.

At an outcome level, the Facility continued to support the expansion of DFID’s capability to design and deliver high quality infrastructure programmes - evidenced by the design of two new flagship programmes (Developing Markets for Infrastructure and Gateway for Growth), the Prosperity Fund China Future Cities programme and the delivery of key learning products such as the urban handbook.

## C. DETAILED OUTPUT SCORING

Output Title	ICED Facility - High quality technical assistance (TA) provided by ICED Facility to DFID teams (country office, regional and central) to facilitate the delivery of new and improved existing programmes, initiatives and partnerships
Output number:		1	Output Score:		A+
Impact weighting (%):		20	Weighting revised since last AR?		Y
Indicator(s)				Milestones		Progress
1.1a Number of active TA substantive interventions (SI) supporting DFID or OGD teams to scope or strengthen new or redesign existing, programmes, initiatives, partnerships, approved by the DFID or OGD client.				Year 5: 3		Substantially exceeded: 10
1.1b Number of Business Cases (BC) supported and/or strengthened by ICED, approved by the DFID or OGD client.				Year 5: 2		Exceeded: 3
1.2 Number of DFID or OGD programmes that have adopted ICED developed tools and/or programme approaches.				Year 5: 2		Exceeded: 4
1.3 Number of successfully delivered short term engagements and advice, for example through call-down requests (not including large scoping studies).				Year 5: 3		Substantially / exceeded: 12

Briefly describe the output’s activities and provide supporting narrative for the score.

The ICED Facility, which came to an end in July 2020, was a demand-led, flexible facility which supported DFID country offices, central teams and ODA-spending Other Government Departments (OGDs) to deliver DFID’s Economic Development Strategy by scaling up programming and investment in infrastructure and cities. In year five, the Facility continued its strong performance, seeing high demand from Country Offices (including, Caribbean, China, India, Kenya, Lebanon, Nigeria, Pakistan and Sierra Leone)and OGDs and delivering a number of key deliverables including:

- the development of three business cases including the: Developing Markets for Infrastructure Programme, focused on how to better support sovereign sponsored infrastructure; Gateway for Growth, a service to help Africa, UK and other international businesses trade with and invest in Africa or export to the UK; China Future Cities programme focused on bolstering urban resilience to the impacts of climate change.
- the Multilateral Cooperation Center for Development Finance (MCDF) review and country assessments and a review of the World Bank Multilateral Investment Guarantee Agency
- Pakistan Economic Corridors Programme (PECP) support, African Development Bank (AfDB) and DFID Infrastructure Partnerships Scoping Study.
- urban and infrastructure handbooks, important resources for supporting the professional development of the advisory cadre.
- a Legacy Compendium, categorising 200+ relevant ICED deliverables for use by DFID cadres and development advisors.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output has now closed. The success of the ICED facility in generating demand for its services, across DFID country offices and other government departments, meant that its budget was fully accounted four months into the reporting year. A closure event was held on 17 July where the ICED Facility consortium and DFID advisers discussed the benefits yielded from the Facility’s work and its key achievements over a five-year period (between 1 February 2016 and 31 July 2019). The impact of these results will be captured in the ICED Project Completion Review.

Recommendations for the year ahead

N/A. The Facility closed in July 2019.

Output Title	ICED Facility - High quality TA provided by ICED to DFID teams (country/regional/central) to facilitate increased access to ICF funding
Output number:		2	Output Score:		A
Impact weighting (%):		5	Weighting revised since last AR?		Y
Indicator(s)				Milestones		Progress
2.1 % of ICED-supported business cases that are ICF compliant				Year 5: 100%		Met: 100%
2.2 % of ICED-supported programmes that are ICF compliant having ICF KPIs				Year 5: 100%		Met: 100%
2.3 % of £ value of DFID approved Business Cases in infrastructure/urban development supported by ICED classed as ICF eligible				Year 5: 25%		Exceeded: 33%

Briefly describe the output’s activities and provide supporting narrative for the score.

The ICED Facility continued to mainstream climate an environment (C&E) into urban and infrastructure programming in year five, building upon the development of an ICED C&E strategy and mainstreaming approaches in year three. With regards to indicator 2.3, the China Future Cities business case (75%) and the Gateway for Growth programme (20%) were both eligible for ICF funding. In terms of programme design, the Facility enhanced log-frames for both programmes including outcomes relevant to greenhouse gas mitigations, energy and water resource efficiency.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output has now closed (as per output one).

Output Title	ICED Facility: Knowledge management, research and policy influencing mechanisms in place to improve the basis for international dialogue and action on the infrastructure enabling environment and cities that drive sustainable, inclusive growth
Output number:		3		Output Score:		A+
Impact weighting (%):		5		Weighting revised since last AR?		Y
Indicator(s)			Milestones		Progress
3.1 Number of peer reviewed knowledge products delivered by ICED			Year 5: 4		Substantially exceeded: 15
3.2 Number of active learning sessions led by ICED (i.e. Events, Roundtables etc.)			Year 5: 3		Substantially exceeded: 16

Briefly describe the output’s activities and provide supporting narrative for the score

With 15 knowledge products delivered in year five, the facility has exceeded its annual target. In this closing year, ICED focused on its legacy by producing tools, approaches, guidance, and evidence to inform better urban and infrastructure programming. Most of these were derived from ICED work packages; dissemination was delivered through digital channels such as the ICED website.

ICED has exceeded its annual target for active learning sessions, delivering 16 sessions on topics related to resilience, infrastructure finance, water finance, safeguarding, disability, and estimating primary and secondary benefits. This reflected the range of technical needs from various DFID teams and advisers and a higher demand for ICED Facility supported learning events in the final four months.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This output has now closed.

Output Title	CoST: CoST creates a more transparent enabling environment for publicly procured infrastructure by establishing effective government systems to publish project information through the implementation of a scaled-up business plan
Output number:		4	Output Score:			A
Impact weighting (%):		25	Weighting revised since last AR?			Y
Indicator(s)				Milestone(s) for this review (numerical targets are cumulative)	Progress
4.1 CoST develops and publishes: The Infrastructure Transparency Index (ITI) methodology that measure transparency within public infrastructure and that will be implemented at a national level by stakeholders is developed and published				Year 5 / ITI published	Not met. Following successful testing of ITI in Guatemala and Honduras, CoST Board requested in-depth peer review process prior to publication. This identified several technical issues that are currently being resolved. Publication now expected Autumn 2020.
4.2 Training on implementing CoST is delivered in member countries: a) Number of Government staff trained; b) Number of civil society or media representatives trained; c) Number of private sector representatives trained.				Year 5 / (a) 5,000 / (b) 1,800 / (c) 500	Met: (a) 5268 (b) 3682 (c)467 / Training of government officials took place in Afghanistan, El Salvador, Guatemala, Panama and Uganda. Malawi trained nearly 900 CS activists whilst Uganda, Afghanistan, Honduras and Ukraine also engaged with CS. Guatemala/ Uganda led in training private sector.
4.3 (a) Number of international and regional organisations recommend or incorporate CoST tools and standards as part of their approach to improving infrastructure governance; (b) Number of invitations to participate at international and regional events to promote CoST tools and standards				Year 5 / (a) 8 (b) 22	Exceeded (a) 12 (b) 36 / During reporting period four organisations endorsed or adopted elements of CoST approach including IADB as part of regional information platform; World Roads Congress (PIARC); G20 as part of compendium on infrastructure integrity; and C20 Infrastructure Working Group.
4.4 Number of knowledge products (KP) that capture activities/results/lessons from implementing CoST that are disseminated				Year 5: 20	Exceeded - 22 / Six knowledge products published this period including paper on assurance published by Civil Engineer Journal, CoST Annual Report 2019, Added value of CoST in high income countries and case studies on Honduras, Uganda and Afghanistan
4.5 2.5m in additional funding is secured to fully fund the new business plan				Year 5: £2.5m	Exceeded - £2,746,313 / CoST members raised over £1m to enable them to scale-up programmes. Included £80k grant from DFID Business Integrity Initiative for CoST Uganda; £589k for CoST Malawi in partnership with Partnership Transparency Fund from EU; £310k CoST Panama from the Open Government Partnership Multi-Donor Trust Fund and; £11k from British Embassy.

Briefly describe the output’s activities and provide supporting narrative for the score.

Since the beginning of 2019, CoST has grown from 12 to 19 members and affiliates. CoST either exceeded or achieved all but one milestone target - whilst the number of individuals from private sector trained increased, it did not quite meet the expected target. However, a new innovative tool which identifies ‘red flags’ regarding infrastructure investment has been developed by CoST Ukraine and is attracting considerable interest from the private sector including investors.

CoST’s profile continues to grow as evidenced by exceeding the targets for output 4.3 with the notable endorsements of the G20 as part of their Compendium on Infrastructure Integrity, the Federation of International Consulting Engineers (FIDIC) and the World Roads Congress (PIARC). CoST has also demonstrated its impact by publishing new case studies (output 4.4) focused on Honduras, Uganda, and Afghanistan.

By disclosing data, CoST’s deterrent effect is estimated to have delivered cost savings of circa US$360m to the Thai Government. By disclosing data on infrastructure projects, CoST has changed procurement practices, strengthened competitive and contributed to lower contract prices. CoST’s work in Afghanistan identified major problems in the preparation stage of the project cycle, particularly relating to inaccurate surveys and inconsistent designs, which led to time and cost overruns. In response, the National Road Authority created a Design Review Unit which, after reviewing over 100 infrastructure projects (and recalculating quantities and costs) is estimated to delivered savings of circa $8m in 2018-19.

The only output that is delayed is 4.1. However, the testing process of the Infrastructure Transparency Index (ITI) in Guatemala and Honduras was successful and provided some interesting results. The independent review (to assess CoST progress against the objectives of its 2017-20 Business Plan) highlighted the potential of the ITI as an important tool that will help to raise the domestic and international profile of CoST.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to the targets during the year. The CoST monitoring, evaluation and learning framework is currently under review. Feedback from a consultation process is being used to update the theory of change and develop new indicators for publication in September 2020.

CoST has responded to the impact of the pandemic in various way. For example, CoST Uganda has adapted its activities by using a dashboard system connected to the government e-procurement portal that has been adjusted to track projects implemented during the crisis. In Honduras, the President highlighted the potential value of CoST in the country’s new health infrastructure plans which includes the construction of more than 90 new health facilities. CoST will continue to work to support the recovery phase: with reduced fiscal headroom, governments seeking to maximise the efficiency of public investment in infrastructure stand to benefit from CoST’s approach.

Recommendations for the year ahead

CoST should continue to engage with the World Bank and bilateral donors as it pivots towards supporting the response to the public health crisis. CoST remains over reliant on DFID funding and has yet been unable to diversify its funding base. However, it is making considerable effort to engage with donors and foundations with the consultative version of the new business plan used to initiate the conversation. The World Bank has also agreed to develop a proposal for a multi-donor trust fund that would be used to support CoST and mainstream the CoST approach in Bank operations.

Output Title	World Bank: Improved analytics and diagnostics, planning of economic reforms and institutional and skills development in cities.
Output number:		5	Output Score	N/A
Impact weighting (%):		N/A	Weighting revised since last AR?	N/A

This component closed in 2018 and is therefore not subject to assessment as part of this review.

Output Title	Cities Alliance: Knowledge management, research and policy influencing mechanisms to improve the basis for international dialogue and action on the infrastructure enabling environment and cities
Output number:		6	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	Y
Indicator(s)		Milestone(s) for this review	Progress
6.1 Number of global advocacy events on Equitable Economic Growth in cities has raised awareness on the relationship between public goods and equitable economic growth.		Year 5: 1	Exceeded: 2 Joint Work Programme (JWP) organised its main annual policy dialogue at European Development Days 2019 Brussels. Session well attended and addressed ‘equitable growth challenge’, based on insights derived from JWP. JWP facilitated dialogue/networking event at World Urban Forum (WUF 10) on Ghanaian Campaign Cities initiative.
6.2 Number of peer reviewed global knowledge products are being produced per year addressing the relationship between urbanisation, inequality and growth in cities		Year 5: 3	Exceeded: 4 JWP produced 4 publications during review period to advance understanding on key urban economic development issues. Topics covered included secondary cities, pricing municipal services, smart technologies for more equitable city economies and a ‘synthesis report’ to summarise knowledge gained and lessons learned from five years of JWP.
6.3 Number of completed, peer reviewed Institutional Enabling Environment Reports (IEER) for JWP Countries-Cities (Bangladesh, Uganda, Ghana and Kenya)		Year 5: N/A	Met: (8) The cumulative target of eight peer reviewed Institutional Enabling Environment Reports (IEER) was met in year four.
6.4 Number of peer reviewed city level assessment reports and policy briefs on how to foster equitable economic growth in JWP cities delivered		Year 5: 8	Met: 8 JWP produced two Local Assessment Reports and two Policy Briefs for Ghanaian cities of Agona Swedru West and Cape Coast. Reports investigated topics of agro-processing, the tourism sector, water and sanitation and waste management. In Kenya, two Local Assessment Reports and two Policy Briefs produced, focusing on land use management and markets management in Nyandarua and Kadiajo counties. Policy Briefs produced for Nyandarua fully endorsed for implementation by county government.
6.5 Cities Alliance membership increases by 2 members per year (annual)		Year 5: 2	Met: 2 UNICEF and Reall joined the Cities Alliance membership in 2019.

Briefly describe the output’s activities and provide supporting narrative for the score.

This Joint Work Programme (JWP) effectively met and exceeded the log frame’s delivery targets for Year five, as well as end-of-programme cumulative targets. The output is nearly complete.

The JWP’s global knowledge products received strong uptake and much attention. For example, Connecting Systems of Secondary Cities presented at national forums was well cited in the research field. The work was adopted by the World Bank and implemented in a US$100 million programme in Uzbekistan involving rethinking the role of, and supporting, development of secondary cities. The publication also received an award for ‘Cutting Edge Research’ from the Planning Institute of Australia.

The Campaign Cities initiative built on the positive results of previous years and remains a defining feature of the JWP. The city partnership methodology offers several important advantages for the promotion of economic development and beneficial impacts are generated beyond the life of the campaign process. The programmes have concluded in Bangladesh, Uganda and Ghana, where local authorities and central government ministries are developing action plans to implement policy recommendations generated in the initiative. The programme in Kenya is in final stages, with recent presentations of policy briefs delivered to governments.

Outputs from the JWP are well received and highly rated by beneficiaries, which is evident in quality assurance and feedback mechanisms of the JWP. Average levels of satisfaction consistently high across four stakeholder feedback parameters in the Campaign Cities initiative; usefulness, quality, accuracy and likelihood to achieve follow-up action by local governments.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to targets, indicators or any other parameters of the logframe during the past year. The JWP has had to respond to the impact of COVID-19 and has done so by adapting the delivery schedules for some outputs. This has not caused any deviations that would jeopardise the overall success of the programme.

Recommendations for the year ahead

Cities Alliance should expand on the work of the JWP to inform the design and delivery of its country programmes, particularly with regards to enhancing the resilience of the informal economy.
The role of the informal sector was a key focus of the JWP. Cites Alliance should ensure it continues to be so in the context of its long-term technical assistance to cities in the context of the COVID-19 response. Strengthening the informal sector can be facilitated by integrating informal activities into priority value chains, specifically those associated with agro-industrial processing, light manufacturing, business services and tourism.

Output Title		Coalition for Urban Transitions (CUT)
Output number per LF	8		Output score		A+
Impact weighting (%):	20		Weighting revised since last AR?		Y
Indicator(s)		Milestones		Progress
8.1 - Number of flagship country urban roadmaps developed in low income countries (Tanzania and Ghana)		2		Met: 2 / Two urban roadmaps were published, outlining challenges and opportunities relevant to the development of national urban policies in Tanzania and Ghana.
8.2 - Number of major high impact, high quality, peer reviewed working papers - supported by relevant regional and country case studies -		6		Significantly exceeded: 11 / Published and disseminated 11 papers, which have enriched the global evidence base on why and how national governments can support more prosperous and sustainable cities.
8.3 - Number of published flagship global synthesis reports capturing the findings of various projects and communicated by the coalition’s leadership council.		1		Met:1 / Launched global flagship report, Climate Emergency, Urban Opportunity at the UNSG Climate Action Summit in September 2019 in New York City.
8.4 - Number of National Media Assessments completed to lay foundation for successful release of national urban roadmaps		2		Met: 2 / The assessments informed the outreach and engagement activities of CUT in Tanzania and Ghana.
8.5 - Number of publications in global outlets, national newspapers or leading sector media by senior Coalition spokespeople and champions (op-eds, blogs etc).		3		Significantly exceeded: 10 / A range of communications were published and/or syndicated in key media outlets.
8.6 – No. of meeting proceedings from successfully completed bilateral meetings with Heads of State / Ministerial / CEO / IFI Head /Senior decision-maker/official level at which Coalition findings and analysis is discussed.		13		Exceeded: 18 High level bilateral meetings were held with a range of leaders and officials who are relevant to CUT’s objectives including: Global Covenant of Mayors, Global Environment Facility, World Bank, UN and Slum Dwellers International.
8.7 - National groups of relevant key policy makers and other important champions facilitated by the Coalition are set up and operational in each focus country.		2		Met: 2 / Two local think tanks - TULab in Tanzania and the Ghana Urbanisation Think Tank – have been created to advance the urban agenda with CUT’s support.

Briefly describe the output’s activities, and provide supporting narrative for the score.

The Coalitions for Urban Transitions (CUT) programme is building the economic case for why urban development is critical to a country’s national development. The programme is seeking to influence national governments in DFID partner countries about the role urbanisation can play in furthering economic growth. DFID is funding the CUT to produce robust research and evidence on urban development and develop national level urban plans in Tanzania and Ghana. In the last year, across its Country and Global Programmes, CUT published 11 policy/research papers that deepened the global evidence base on why and how national governments can support more prosperous and sustainable cities.

Global Programme

The Coalition launched its flagship global report Climate Emergency, Urban Opportunity at the UNSG Climate Action Summit in New York City in September 2019. The report was a call to action for national governments to prioritise compact, connected and clean cities. The report showed that cutting 90% of emissions in cities is possible using proven technologies, accounting for over half of the global abatement needed and generating returns worth almost US$24 trillion by 2050. It showed that these measures would also support 87 million jobs by 2030 in sectors such as clean energy and public transport. The launch, on 22 September 2019 was, held at the UNSG Climate Action Summit. Christiana Figueres and Lord Nicholas Stern, both Senior Ambassadors for the report, outlined the report’s key findings and presented it to the UN Deputy Secretary-General.

The Coalition’s work in Tanzania culminated in the launch of a flagship policy publication – Harnessing Urbanisation for Development: Roadmap for Tanzania’s Urban Development Policy – which was launched on 21 August 2019 in Dodoma. The launch was hosted by three key ministries responsible for urbanisation – the President’s Office Regional Administration and Local Government, Ministry of Lands and Human Settlement, and Ministry of Finance and Planning. Upon its launch, the Government of Tanzania endorsed the report and called for its full implementation.

The TULab, originally created to deliver this programme, successfully implanted the urban agenda and urban opportunity in Tanzanian public policy discourse. The TULab continues its work and is currently being supported by UNICEF to facilitate a programme focused on children and cities. The Coalition’s work in Ghana culminated in the launch of a flagship policy publication (Cities as a Strategic Resource: Guidelines for Ghana’s National Urban Policy Revision) which was launched in January 2020 at the Ghana Urban Forum.

CUT’s engagement and outreach focused on key global events including the World Urban Forum in Abu Dhabi where the Coalitions work on Ghana’s national urban policy was presented at an event organized by the Ghanaian Ministry of Local Government and Rural Affairs (MLGRA). The Coalition continued to influence other key urban networks through the C40 Mayors Summit in Copenhagen where it presented the Urban Opportunity report at an event opened by UN-Habitat Executive Director. CUT’s outreach activities were complimented by a number of op-eds – by Lord Nicholas Stern, Christina Figueres and the Mayor of Accra, highlighting the role of cities in addressing climate change and acceleration low carbon growth.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to targets, indicators or any other parameters of the logframe during the past year.

Recommendations for the year ahead

CUT has evolved into an important programme that is shaping the urban policy agenda. Yet it has the potential to go further in understanding how its policy work influences the decisions of senior decision makers and in doing so affects the allocation of public investment to cities and urban infrastructure. Allied to this, determining whether the political dynamics of a given country are conducive to reform will be crucial: without a nuanced understanding of the (sub)national political landscape, CUT’s efforts to develop national urban policies may not bear fruit. The Coalition has now grown to over 50 members – it is not clear if continued expansion is necessary or desirable as it may risk dilution of its key policy aims.

Output Title		Strategic Opportunities Fund (SOF): Support the utilisation of the SOF
Output number:	8		Output score		A
Impact weighting (%):	5		Weighting revised since last AR?		Y
Indicator(s)		Milestones		Progress
7.1 £ value and number of sub-sector projects approved by SOF		Year 5: 0		As per the 2018 Annual Review it was agreed not to initiate any new projects for funding under the SOF in Year four, but to focus on successful completion of existing projects
7.2 £ value and number of projects approved by SOF that have achieved their intended outcome as defined by DFID (on a case by case basis)		Year 5: 0		As above

The Strategic Opportunities Fund was set up to support emerging opportunities across the urban, energy and infrastructure sectors. After a pause in allocating funding from the SOF, to concentrate on the delivery of existing projects under this component, the following strategic opportunities were funded in year five.

The SOF provided £330K to support the World Resources Institute to deliver the Synthesis of the World Resources Report, Towards a More Equal City. The WRR Synthesis Report aims to help cities become more equitable, environmentally sustainable, and economically prosperous by providing evidence-driven, actionable recommendations for decision makers at all levels.
The Synthesis Report identifies high priority solutions for cities in the global South that foster equitable access to core services and opportunities focusing on a range of urban sectors (housing, water, sanitation, transportation, energy, informal economy, and urban expansion).The case studies capture in-depth stories of how seven cities have implemented actions in one or more of these sectors towards citywide transformative change, identifying the key triggers, enabling and inhibiting conditions for each, and coalitions that came together, allowing other cities to learn from these experiences. Our engagement activities have served the triple benefits of drawing inputs on how to make the Synthesis Report most useful, disseminating and discussing the WRR findings with the target audience, and working together to understand how specific solutions may be advanced in specific regions.
- A small amount of SOF resources were deployed to support:
  - The running costs of the International Development Infrastructure Commission. In August 2019, the International Development Secretary Alok Sharma convened the Commission bringing together leading experts to explore opportunities and challenges for financing quality infrastructure projects in developing countries. The Commission’s work, summarised in a report, led to the development of a new DFID infrastructure programme focused on structuring and financing new infrastructure projects.
  - An externally commissioned research project focused on utility management in South Asia and sub-Saharan Africa. The report provided a basis for a better understanding of the relationship between utility ownership models and sovereign debt levels yet deep dives into (other) countries were not required to complete the project.
  - An independent review of CoST, the purpose of which was to appraise CoST’s relevance, effectiveness, efficiency and impact on infrastructure governance and provide an assessment of CoST’s progress against the objectives of its 2017-20

D: RISK

Overview of risk management

The overall implementation of ICED continues to be moderate. Due to the uncertainty caused by the Covid-19 pandemic on future ODA programming, the programme was extended by three months (to end of September 2020) to ensure partners and SOF activities can be fully delivered. Now that the ICED Facility has closed, the focus in year five was mainly on managing the risks of CoST and Cities Alliance and their downstream partners.

CoST

Over the last twelve months CoST has continued to develop its risk register and better understand its risk appetite. This has raised four critical risk areas.

- A continued overreliance on DFID funding especially as we draw towards the end of the current agreement. A new business plan is being used to engage a range of bilateral, multilateral donors and foundations that it is anticipated will lead to a broader funding base. The World Bank is also developing a proposal for a CoST multi-donor trust fund that if approved would be operational in 2021.
- Developing a better understanding of the governments that CoST would not work with. The competitive process that led to five new national and sub-national programmes has helped to crystallise the importance of high-level government commitment plus ensuring that there is space for civil society participation.
- The safeguarding policy has been published with training provided to CoST member managers. The safeguarding risks have grown with an increase in community meetings where local citizens may meet local officials. However, we have been greatly encouraged by multi-stakeholder groups appointing an MSG member to be responsible for safeguarding and in one or two cases ensuring citizens are aware of the safeguarding policy and procedure. This will be rolled out as standard good practice as part of a new guidance note on social accountability.
- As well as tightening our grant agreements with CoST members we have undertaken governance reviews in Tanzania and currently in Uganda to better understand how each programme is being managed with the lessons also being used to inform the development of new guidance and standards for CoST member programmes.

Cities Alliance

The Cities Alliance continues to programme and operational risks as described below.

- The JWP maintains an ongoing Risk Management Framework and Risk Log, which is reported to the CA Director and Management Team on a bimonthly basis. The JWP has been able to deliver its programmatic work comfortably within risk appetite.
- The risks that have been identified include operational and reputational risks, as well as both internal and external risks. The JWP has proactively mitigated these risks through measures implemented by CA’s Project Management Team (PMT) and the CA Director. These include for example, increased reporting of grant recipients; further clarification of the functions and responsibilities of Members and the PMT; and strengthening of quality assurance mechanisms through the establishment of Sounding Board Groups and a Global Consultant Roster.
- The COVID-19 pandemic has brought about some risk to the finalisation of programmatic work. This has been mitigated by the efforts of PMT to re-plan tasks where necessary, to ensure all outputs are completed.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

The ICED programme is currently on track for all deliverables against agreed work plan and log frame. The project completion report will include a full review of the ICED programme’s VfM performance. Key aspects related to programme management and all aspects of VfM (economy, efficiency, effectiveness and equity) are summarised below.

ICED Facility

The Facility’s effectiveness continued to be demonstrated through the design of three new business cases, unlocking more than £564m of new ODA programming. The ICED Facility has sought synergies at the work package and facility level. For example, the Kenya Infrastructure Finance CDF and the Developing Markets for Infrastructure Programme business cases were delivered together to support DFID Kenya, UKEF and DFID. The Facility delivered savings from the use of PwC infrastructure and succeeded in streamlining technical inputs in order to minimise the time spent on deliverables through transfer of knowledge and expertise between work packages. The Facility also sought to maximise its use of local consultants, doing so in Cote d’Ivoire, Kyrgyzstan, Zimbabwe, Kenya, Ukraine and Sierra Leone. During year five, the ICED Facility continued to design gender and inclusion (G&I) tools and approaches including the design designing a G&I ambition matrix for the Private Infrastructure Development Group.

CoST

A recent independent review demonstrated that CoST delivers good VfM but its VfM framework requires improvement. This will be taken forward as part of a new theory of change and Monitoring Evaluation and Learning framework. Economy continues to be principally achieved by outsourcing the International Secretariat function to Engineers Against Poverty, thus it minimises overheads costs and benefits from using its office space, staff, and financial management systems. It continues to track input costs such as consultancy rates, air travel and the unit cost of assurance in a CoST member country. CoST improves efficiency by selecting and monitoring partners according to their efficiency of delivery, particularly CoST member programmes.

CoST improves efficiency by selecting and monitoring partners according to their efficiency of delivery, particularly CoST member programmes. CoST increasingly works in strategic partnerships such as with the Open Contracting Partnership (OCP) to develop joint standards or knowledge sharing platforms. This allows CoST to benefit from economies of scale in its work. This includes sharing the costs of the helpdesk with OCP that supports implementation of the Open Contracting for infrastructure Data Standard. It is also ensuring that the technology developed in Honduras and Ukraine are open source tools that any CoST member or a DFID government partner could adopt.
With regards to equity, CoST’s engagement with local communities in Uganda have involved many women participating in dialogue on the impacts of (new) infrastructure projects. CoST’s gender audit in Thailand examined the current levels of participation of women in the CoST Thailand programme and the potential barriers and opportunities in their participation, highlighting the need to expand the participation of women at community meetings.

Cities Alliance

Narrative reporting and audited financial statements have been provided annually. CA have submitted payment requests in line with their pre-agreed disbursement schedules. The Joint Work Programme (JWP) has a reporting system which allows for product-oriented monitoring, based on the JWP Results Framework, the ICED log frame and annual workplans. This system includes weekly monitoring mechanisms from the PMT within the CA Secretariat; bi-monthly reporting to the CA Director and Management Board; annual reporting as part of the DFID Annual Review; and annual reporting as part of the CA Annual Report to the CA Assembly. These reporting processes inform the JWP’s risk management and programming decisions. The major cost drivers of the programme remain programme implementation and oversight. This includes PMT staff, retainer-based consultants, grants and procured services. These costs are all subject to UNOPS regulations, including competitive market-tested pay and competitive procurement processes.

Coalition for Urban Transitions

The quality, timeliness and cost of the Coalition’s work is subject to a robust peer review process involving at least three internal and external reviewers. CUT negotiates fee rate discounts or co-investments and secured in-kind support from technical partners (McKinsey and Siemens) to deliver specific work streams on urban mobility. CUT receives in-kind support for its office space and leveraged networks and web-based platforms of its partners, the World Resources Institute and C40. Members of the Steering Group and the Urban Leadership Council participate on a pro bono basis and many of CUT’s research papers are peer reviewed through in-kind support.