Annual Review
Title: Better Jobs in Bangladesh
Programme Value £ (full life): £6.6million		Review date: 08 August 2020
Programme Code: [AMP ID#] / 205275	AMP start date: / 08 August 2016 / (programme started on 01 July 2017)	AMP end date: / 30 June 2024 (financial closure) / (programme end date 31 December 2023)

Summary of Programme Performance
Year	2018	2019	2020	2021	2022	2023
Overall Output Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/9085375.odt
DevTracker Link to results framework:	http://iati.dfid.gov.uk/iati_documents/49271484.xlsx

GLOSSARY
BEZA	Bangladesh Economic Zone Authority
BGMEA	Bangladesh Garments Manufacturers and Exporters Association
BIDA	Bangladesh Investment Development Authority
BJB	Better Jobs in Bangladesh
BWB	Better Work Bangladesh
BLA	Bangladesh Labour Act
DFI	Development Financial Institution
DIFE	Department of Inspection for Factories and Establishments
GEAR	Gender, Equality and Returns
GoB	Government of Bangladesh
IFC	International Finance Corporation
ILO	International Labour Organisation
ISU	Industrial Safety Unit
LIMA	Labour Inspection Management System
MoLE	Ministry of Labour and Employment
MoU	Memorandum of Understanding
NI	National Initiative
OSH	Occupational Health and Safety
OSS	One-Stop-Shop
PACT	Partnership for Cleaner Textile
PDP	Programme Delivery Plan
RAJUK	Dhaka/ Capital Development Authority
RCC	Remediation Coordination Cell
RMG	Ready-Made Garments
RSC	RMG Sustainability Council
SRO	Senior Responsible Owner
ToC	Theory of Change
ToR	Terms of Reference
VfM	Value for Money

A. SUMMARY AND OVERVIEW

Description of programme
1. Better Jobs in Bangladesh (BJB) is a £6.6 million programme to improve the working conditions and safety standards in the Ready-Made Garments (RMG) sector of Bangladesh over the period 2017-2023. BJB provides knowledge and capacity building support to the Government of Bangladesh (GoB) to improve industry inspection and compliance of the GoB’s building and fire safety standards by factories. BJB also helps strengthen occupational health and safety (OSH) in workplace. The UK contribution is part of a wider programme worth $24.5 million implemented by the International Labour Organisation (ILO), with equal contributions from The Netherlands and Canada.

2. BJB was part of the international community’s response to enhance industrial safety in one of Bangladesh’s leading manufacturing and export sector, following a major industrial accident in 2013 at the Rana Plaza. In addition to structural and fire safety of industrial and commercial buildings in the RMG sector, the programme helps the GoB develop and enforce health safety standards, now more important than before because of health risks to factory workers posed by the Covid-19 pandemic.

3. The programme has a special focus on relatively smaller RMG factories which are not covered by industrial safety initiatives, namely Alliance and Accord, supported by European and American apparel retailers. Both initiatives are now closed, following a directive from the Bangladesh High Court in favour of the RMG sector’s desire to replace them with a local initiative. The bottom tier factories, called National Initiative (NI) factories, although not directly contracted by international retailers, exist in large numbers (at last count nearly 700) and employ about 250,000 men and women. The NI factories work on low profit margins and have few incentives for industrial safety, posing significant risk to the lives of their workers and reputational risk for the sector.

4. The programme is delivered through four outputs:
1. Inspection and enforcement of safety standards by government authorities
2. Developing one-stop service for all licensing related to factory registrations
3. Improving OSH in policy and practice by GoB
4. Supporting factories directly supplying international retailers to become role models for compliance through an ILO and International Finance Corporation (IFC) initiative called Better Work Bangladesh (BWB)
5. The primary objective of the programme is to protect businesses and jobs by strengthening workplace safety in the RMG sector, a major contributor to economic growth, jobs, and poverty reduction in Bangladesh over the past two decades. The programme has strategic significance for the UK’s national interest by helping to secure apparel supply chains for British retailers. Bangladesh is the second largest supplier of garments to the UK, after China. The programme also strengthens the ILO’s ability to advocate for appropriate action by government, the private sector (especially, RMG factories and international brands), and development partners to strengthen workplace safety, workers’ rights, and working conditions, especially for women who constitute nearly 70% of the estimated 4million workers.

6. Supply chain disruptions and the collapse of international demand in the aftermath of the pandemic have hit the RMG sector hard, putting businesses, jobs and livelihoods linked to the sector at risks. This programme is being reprioritised to contain the economic and social cost of the pandemic by supporting GoB to ensure safe return of workers and supporting ILO to work with the government, private sector and development partners, including development finance institutions (DFIs) in finding appropriate solutions to the sector’s problems, especially retention of workers on the pay-rolls and survival of RMG business.

Summary supporting narrative for the overall score in this review
7. Performance of the programme during this review period is scored at A – moderately exceeded the logframe expectations. The programme has helped the GoB establish remediation and compliance protocols for the NI factories and enforce protocols through factory inspections managed by GoB’s Remediation Coordination Cell (RCC). As of May 2020, all 1549 NI factories that existed at the start of this programme have been inspected at least once. Of these, 180 factories successfully completed remediation and have become suppliers of international retailers; 98 were relocated to safer buildings; and 607 were found at the time of inspections to be structurally unfit and have been closed. The remaining 664 factories have been advised on detailed remediation measures to meet expected standards. Implementation of remedial action plans has been less satisfactory, as factories have been able to implement only 50% of the recommended remedial actions due to lack of- financing, interest to retrofit rented/shared buildings and requirement from buyers they supply to.

8. The programme has had limited impact on institutional and systemic changes necessary for sustainable improvements in industrial safety in Bangladesh. Even after the closure of Alliance and Accord, the sector remains dotted with multiple agencies, often working on industrial safety without any coordination and at cross-purposes.

9. Following the closure of the international brands’ initiatives, Accord and Alliance, GoB, RMG factories, and international brands have agreed to replace them with two local initiatives; namely (i) the RMG Sustainability Council (RSC) owned by the sector’s industry association, Bangladesh Garments Manufacturers and Exporters Association (BGMEA) and (ii) ‘Nirapon’ to be managed and run by a not-for-profit local body set up by Alliance. There still remain concerns about the effectiveness of these new organisations and their accountability to GoB. RSC has reporting responsibility towards GoB but there needs to be opportunity for the brands and unions to pass on the industry best practice knowledge to GoB to incorporate those in its policies and drive up the safety standards across the whole sector.

10. The programme has recently started reaching out to other GoB agencies, e.g. the Bangladesh Investment Development Authority (BIDA), to improve inter-agency co-ordination. However, systemic improvements must be adequately reflected in the logframe to create appropriate incentives for the implementing partners to work towards those expected changes.

Major lessons and recommendations for the year ahead
11. A single and unified institutional architecture is important for sustainability of industrial safety initiatives. In the aftermath of the Rana Plaza industrial accident in 2013, several diverse industrial safety platforms (e.g. Accord, Alliance and National Plan of Action) were formed to improve workplace safety. This multiplicity of agencies, over time, has led to confusion about their roles and responsibilities, hindering development of standards and practices acceptable and enforced across the sector. It also created growing tensions about jurisdiction between GoB, international retailers and RMG factories. BJB has rightly targeted support for building GoB’s capacity. Now that Alliance and Accord are closed, BJB needs to intensify its focus on the institutional architecture of industrial safety regulation.

Recommendations
12. ILO should work closely with GoB and the private sector and support government in developing a long-term institutional architecture of the industrial safety regulation and enforcement mechanism which is independent, efficient, and credible to protect factories and their workers, before the next annual review.

13. ILO will develop a strategic work-plan, incorporating COVID impact, by September 2020 which will include:
- The barriers to factory remediation and ways to address those through programme intervention.
- The impact of Covid-19 on the capacity development of RCC engineers.
- Improved reporting arrangements of harassment and discrimination of workers through Labour Inspection Management System (LIMA).
- A road-map for the One-Stop-Shop (OSS) for all factory licensing services of GoB.
- Partnership with environmental impact, labour rights, and disability inclusion programmes to improve the value proposition of BWB to both brands and factories.

14. ILO to agree targets based on the above work-plan with donors to include in the logframe by October 2020. This will help in: (a) better reflecting the programme’s objectives for improving institutional arrangements for safety regulations and (b) removing the process indicators already delivered.

15. DFID will bring forward the next annual review of the programme to align with the ILO calendar year reporting period. DFID’s annual review is due in August each year which makes it difficult to assess a full year’s results that ILO reports for January to December.

16. COVID-19 provides an opportunity to the programme to step up and provide support in areas that it is already working in. ILO will agree with donors on a work-plan by August 2020 for:
1. Capacity development: providing support to GoB, industry associations, NI and BWB factories to improve health and hygiene standards in the workplace.
2. Supporting workers: providing channels to workers to get information on labour rights and entitlements in case of forced redundancy.
3. Soft influence: engaging through the 3+5+1 platform (represented by ILO, three GoB Secretaries and five Ambassadors, including UK, to bring reform in labour rights, workplace safety and responsible business conduct) to ensure adherence of Bangladesh Labour Act (BLA) for protection of workers in case of layoff.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

17. The theory of change (ToC) did not change over the past year and remains relevant to the context and programme’s objectives. It is premised on the need for enabling policies and organisational capacity to secure workplace safety. Safe workplaces and decent working conditions need well-defined standards and protocols, and robust and independent surveillance and enforcement mechanisms. Improved workplace safety and working conditions will help international retailers protect the reputation of their supply chains which in turn will help protect businesses and jobs in the RMG sector in Bangladesh. This in turn will contribute to poverty reduction through economic growth and jobs for the poorer segments of society, including many women.

18. Whilst the ToC remains relevant, it needs to be unpacked further in the log frame to more clearly reflect the importance of systemic and institutional change as set out in paragraph 11 and 12. The underlying assumptions largely did not change over the last year, but COVID-19 has affected how RMG supply chains operate globally. The decline in clothing sales in EU, UK and USA translated into reduced demand for Bangladeshi RMG products. Given the sector’s importance to job creation and economic growth, and economic empowerment of the 2.5 million women directly employed in the sector in Bangladesh, it will be important for the programme to continue contributing to making the supply chains more secure for their workers.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

19. The programme’s impact on systemic change does not go far enough for a sustainable impact on improved workplace safety in the RMG sector in Bangladesh. The mid-term review, completed in May 2020, and this annual review have both concluded that there is a risk to the programme achieving its outcome targets:
1. 72% of the active NI factories have so far implemented less than 50% of the corrective measures identified by inspection for the factories to reach acceptable safety standards.
2. The programme needs to work with DIFE and other licensing agencies to ensure all follow a common work-plan agreed with BIDA to bring together all licensing on one platform within an agreed timeframe. This will make the risky factories more accountable and help GoB close those down.
3. BWB operates alongside other safety and labour rights improvement initiatives in the RMG sector. It needs to strengthen its offer to ensure brands can access social compliance, labour rights compliance, gender inclusion, and responsible business practices through one programme. This will help to make BWB services sustainable and contribute to achieving the outcome target of BWB factories becoming role models for compliance.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

20. The case for the programme continues to be strong as workplace safety has become more important than before because of the risks posed by the pandemic to business and jobs in the RMG sector in Bangladesh; and of the strategic significance of the programme to the UK’s national interest in securing the supply chains of British retailers in Bangladesh. The programme, however, needs to revisit its strategy and approach for building GoB’s human and institutional capacity to strengthen workplace safety on a sustainable basis.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	A Remediation Coordination Cell (RCC) is established / 1.2 Employers, workers and buyers are better equipped to support and sustain remediation efforts
Output number:		1	Output Score:	A
Impact weighting (%):		35%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1.1. A compliance and escalation protocol in place	Baseline (June 2017): Compliance Protocol introduced. / Milestone (Dec 2020): No additional milestone for 2020	This is not factored in scoring of the output because there is no additional target for this indicator in 2020. The Compliance and Escalation Protocol was endorsed in July 2019 by the government and now used by DIFE.
1.1.2. Proportion of relevant cases examined by the Review Panel for immediate action / (meaning- complains received by DIFE on structural safety are examined/ assessed)	Baseline (June 2017): / 0 (the Review Panel was set up in 2018) / Milestone (Dec 2020): 100% of the relevant cases examined by the Review Panel for immediate action	Met Expectation. / The review panel received two cases. Both were reviewed and actions were taken.
1.1.3. Frequency of visits to factories by RCC representatives	Baseline (June 2017): 0 (NI factories were not even visited once in a year by DIFE inspectors) / Milestone (Dec 2020): / a) 100% of the NI factories that are under remediation visited at least once by RCC engineers; / (b) 35% of them will be visited at least three times.	Significantly exceeded expectations / There are 664 active NI factories and all of them were visited by the RCC engineers once between the inception of the programme and March 2020. / 88% of the factories were visited thrice within the same time frame.
1.2.1. Percentage of NI factories who receive information on remediation and access to finance by the RCC (per factory, based on priority)	Baseline (June 2017): 0 / Milestone (Dec 2020): 60% of the active NI factories	Met expectation / Out of the 664 active factories, all received information on access to remediation finance and only five factories have accessed the finance between January 2019- March 2020.

Briefly describe the output and provide supporting narrative for the score.
21. The output scores an ‘A’ in this annual review. Of the four indicators, one was a process indicator delivered in the previous year (and hence not considered for scoring in this AR), one indicator significantly exceeded expectation for this year, and the remaining two indicators met expectation.

22. Whilst the inspection system has been established and inspections continued as expected, implementation of corrective measures recommended by inspection has been very slow. The programme is now at a midpoint and 72% of the active NI factories are below 50% completion rate of remediation action plans. Accelerated remediation will be critical for the programme to move outputs to outcomes. To ensure workplace safety, DIFE will also require a mechanism by which it can have a legal oversight on private initiatives such as RSC and Nirapon.

23. The programme supported DIFE to develop the strategic plan for setting up the Industrial Safety Unit (ISU), which will be the umbrella body within DIFE for industrial safety across all sectors. BJB will work with DIFE to promote the role of the ISU to the private sector. The programme will also work with NI factories to incentivise accelerated implementation of corrective measures, including through help in accessing finance.

24. The programme also helped DIFE design a training module for its engineers to develop skills in setting and assessing structural safety, so that knowledge remains within the organisation even after the end of the programme.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

25. The business case stated that economy will be achieved through use of best practice, especially via large procurements and savings generated through negotiations. Recruiting a private sector engineering firm to support the DIFE engineers was a large procurement and ILO has used the competitive/open bidding approach for it and saved $275,000 through negotiations which represents about 5% of the original contract value.

26. To ensure equity, BJB has a special focus on smaller RMG factories beyond the radar of the international retailers. Given the large number of women workers in the RMG factories, BJB has developed an online grievance reporting system through which DIFE inspectors collect information on physical, psychological and sexual harassment at factories. 280 DIFE staff have been trained to do this. No cases have so far been reported to DIFE on any of these issues, which indicates the mechanism may not be fully effective.

Describe any changes this output, and any planned changes as a result of this review
27. The log frame needs to be revised to:
1. Remove the process indicators which have already been delivered and should not be monitored going forward.
2. Reflect the institutional changes that need to take place to identify and suggest the best possible institutional architecture which can provide an independent and credible standard setting and enforcement mechanism after the closure of Accord and Alliance.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
28. Progress towards last year’s recommendations:
1. RCC capacity development and RSC/ISU legal oversight: (1) RCC capacity development is ongoing and affected by COVID. (2) The ISU concept has planned legal oversight on RSC or other private sector initiatives.
2. Access to finance: There is no progress to report in this review.
3. Bangladesh Labour Act (BLA) improvements: UK and other members of the 3+5+1 platform have pursued GoB for further improvement to BLA and a transition plan was signed between EU and MoLE which included a three-year plan (2020-2022) to address issues raised by ILO which includes freedom of association and discrimination and harassment of workers.
29. Lessons learnt: Remediation of the NI factories is not progressing as there is a lack of financing available to them; or factory owners do not want to invest in rented/shared properties; or there is no pressure to maintain standards from small buyers that they supply. The programme needs to be able to provide customised solutions that can achieve the highest impact. Improving government’s inspection capacity or simply following up with factories might not provide the results the programme is aiming for.

30. Recommendations:
1. The programme will need to re-design the work-plan of capacity development of the DIFE engineers by September 2020 to address the challenges arising from COVID-19.
2. The programme will identify challenges related to the remediation progress, develop action plans to address those, and reflect it in the log frame by October 2020.
3. The programme will work with DIFE to improve the channels available to workers to report sexual harassment and discrimination at work and to map the progress and challenges through each quarterly report from now on. To help this, the programme will conduct a literature review of factory based sexual harassment and provide possible solutions for improved reporting of harassment/ discrimination by February 2021.
Output Title	Framework for one-stop-shop for industrial safety and compliance conceptualised / 2.2 Labour inspection capacity of DIFE is developed, which is fair, effective and gender sensitive
Output number:		2	Output Score:	B
Impact weighting (%):		25%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1.1 One-stop-shop (Single Window Service) proposal and business processes recognised and agreed by all relevant ministries	Baseline (June 2017): Single Window Service concept agreed in principle by stakeholders / Milestone (Dec 2020): One-stop-shop (OSS) conceptualized based on a common understanding amongst various regulatory bodies.	Did not meet expectation / Discussion has started with IFC, Bangladesh Investment Development Authority (BIDA), and Bangladesh Economic Zone Authority (BEZA), but there is no action plan in place that will help to deliver the idea.
2.2.1 Proportion of labour inspectors who report increased knowledge and skills acquired through practical training (disaggregated by sex)	Baseline (June 2017): 72% / Milestone (Dec 2020): / 80%	Did not meet expectation / Training sessions were provided in 2019 on the use of Labour Inspection Management Application (LIMA) and there has been a 70% increase in using the system; but it has not been mapped whether the training helped in improving knowledge and skills for inspection.
2.2.2 Proportion of trained staff within DIFE who report increased knowledge on gender issues (disaggregated by sex)	Baseline (Jun 2017): / Nil / Milestone (Dec 2020): / 10% percentage point increase from the previous year	Did not meet expectation / The training was postponed from Q3 2019 to 2020 and has not yet taken place. ILO does not plan to deliver this training during the COVID-19 crisis, so achievement of result is unlikely in 2020.
2.2.3 DIFE’s information and knowledge management capacity strengthened	Baseline (Jun 2017): DIFE's Information and Knowledge Management System LIMA developed in June 2017. / Milestone (Dec 2020): All 24 Offices use LIMA	Met expectation / As of March, all 24 DIFE offices were using LIMA and analytical reports were published using LIMA. About 70% of the staff in these 24 offices use LIMA.
2.2.4 DIFE gender roadmap developed and implemented	Baseline (Jun 2017): 'No gender roadmap available at the beginning of the project / Milestone (Dec 2020): The Gender Roadmap is adopted by DIFE	On track to deliver 2020 target / First draft of DIFE gender roadmap developed and a validation workshop with GoB counterparts took place in June 2019. Until March 2020, the implementation plan of the roadmap was under development which indicates it will be adopted by 2020.
2.2.5 Labour Inspection Reform Roadmap reviewed, and progress reported annually	Baseline (Jun 2017): Nil / Milestone (Dec 2020): Labour Inspection Reform Roadmap progress report developed and published.	Did not meet expectation / Inspection reform roadmap was endorsed by MoLE in December 2019; but there is no plan in place to report the progress.
2.2.6 DIFE Labour Inspection report published annually	Baseline (Jun 2017): Last report published for 2016-17 / Milestone (Dec 2020): Report published by July 2019	On track to deliver 2020 target / DIFE will publish a report in July 2020 on labour inspection for the period of 2018-2019. / DIFE has published the inspection report for 2014-2018 in July 2019.

Indicator(s)	Milestone(s) for this review	Progress
2.2.7 All labour inspectors are trained systematically following the comprehensive training plan of DIFE	Baseline (Jun 2017): Nil / Milestone (Dec 2020): Comprehensive training plan developed for DIFE	Did not meet expectation / The comprehensive training plan for DIFE that was supposed to be developed in Q3 of 2019 was not developed until March 2020.

Briefly describe the output and provide supporting narrative for the score
31. This output scored a ‘B’ in this annual review. The objective of the output is to ensure that GoB has the right capacity and governance structure to effectively regulate industrial safety with staff that are credible and accountable. To do that the programme is supporting the set-up of a one-stop-shop (OSS) for industrial safety and developing a robust and accountable labour inspection system. The programme has only recently started engaging with other relevant government agencies for setting up the OSS.

32. Major achievement over the last year: RAJUK (Dhaka/ Capital Development Authority), Bangladesh Investment Development Authority (BIDA) and Bangladesh Export Processing Zone Authority (BEZA) agreed a Memorandum of Understanding (MoU) to make construction permits, occupancy certificates, and land use certificates available through BIDA’s OSS. The programme started working with IFC in January/February 2020 to assess the IT platforms of BIDA, DIFE, RAJUK, BFSCD and the Chittagong Development Authority (CDA) to make all permits related to factory registration available on one platform. This will also prevent factories from registering buildings that have already been identified as risky by both DIFE and RAJUK separately.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

33. The business case identified that the effectiveness of the programme will be in building capacity of government to deliver services and ensure sustainability which includes tracking the number of in-house training sessions provided to the newly recruited inspectors and the number of inspections completed by the inspectors. The programme has been effective in conducting inspections, using LIMA for inspections and reporting issues in the system. To put it into context, DIFE did not have any central database to report the outcome of the inspections other than keeping records manually. Now DIFE inspectors collect data through an on-line system which can help to collate those and generate information for further use.

Describe any changes to this output, and any planned changes as a result of this review.
34. This review recommends updating the log frame to include measurable indicators to map progress for the OSS development by October 2020.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

35. Progress towards last year’s recommendations:
MoU for the OSS: The MoU has not been signed to take forward the planned OSS development.
36. Lessons Learnt: IFC has been working with BIDA on multiple OSS development to improve the ease of doing business in Bangladesh. The programme needed to analyse the need of the RMG sector much earlier and offer the background information to IFC/ BIDA so that it can be integrated into the larger development that was going on.

37. Recommendation: The programme needs to develop a workplan by September 2020 that will help to map progress of the OSS development, Gender Roadmap and Labour Inspection Reform Roadmap and report the development through each quarterly report from now on.

Output Title	Framework for national OSH programme initiated in line with national OSH policies of the government / 3.2 Stakeholders' capacity and awareness on OSH built in a gender inclusive manner
Output number:		3	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1.1 National OSH profile is ready for adoption by the government	Baseline (Jun 2017): Existing OSH policy and profile / Milestone (Dec 2020): No additional target for 2020	Target met in 2019. / Not factored in this AR’s scoring. National OSH Profile approved at the National OSH Council in September 2019. DIFE is now working on developing the National Plan of Action based on this OSH Profile.
3.2.1 DIFE's capacity to monitor the operations of the Safety Committees is strengthened	Baseline (Jun 2017): Nil / Milestone (Dec 2020): All members of the DIFE OSH Unit received training on the Safety Committee	On track to deliver 2020 target / Until now 20 staff of DIFE has been trained on the Safety Committees as per the plan of the programme but all DIFE staff have been given a fast-tracked training on Safety Committees to address the health and safety standards during the COVID-19 crisis.
3.2.2 Number of Trade Union member and Safety Committee members equipped to support OSH management, Risk Identification and correction (disaggregated by sex)	Baseline (Jun 2017): Nil / Milestone (Dec 2020): 1800	Unlikely to meet expectation / The training was planned for Q3 2019. It was delayed to combine it with trainings of Workers’ Resource Centre. And now further delayed due to the pandemic.

Briefly describe the output and provide supporting narrative for the score.
38. This indicator scores an ‘B’ as one target is expected to be met in 2020 and the other is unlikely to meet the target for this year. The objective of this indicator is to improve OSH both in policy and in practice; and also, to assess whether OSH committees at factories are working in accordance with BLA. This has now become a higher priority for workers’ protection during COVID. The target for this component is to develop a National Plan of Action on OSH that can be implemented and carried forward by both the public and private sector.

39. Achievements in last one year:
1. National OSH Profile was approved by the National OSH Council in September 2019. This profile now provides a national standard for OSH best practice in line with international standards.
2. The first draft for National Plan of Action on OSH was produced by DIFE in February 2020. The action plan will work as a guiding document for both government and private sector stakeholders to define responsibilities and improve OSH standards across all sectors.
40. The major challenge identified in this review: The decision to work through the Workers’ Resource Centre for the OSH capacity improvement of trade unions is delaying the task. While this will ensure the sustainability of the training and embed it within an organisation that works with trade unions, there is a risk that the programme might not be able to deliver on its output targets of reaching 1800 workers through this training.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

41. The business case identified that the effectiveness of the programme will derive from building the capacity and incentives of stakeholders to ensure sustainability; and this will be calculated based on the number of safety committees established by trade unions and sector associations. 1929 Safety Committees were set up by the industry associations between July 2018 and March 2020, of which only 162 were directly set up with the programme’s support. This means BJB has created the incentive for trade unions and factories to support the establishment of Safety Committees that largely benefit workers.

Describe any changes this output, and any planned changes as a result of this review.
42. The review is not recommending any change in the output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
43. Progress towards last year’s recommendations:
Fast track the process of National OSH Profile: the last review recommended fast tracking the development of the National OSH Profile which was delivered in September 2019.
44. Recommendation: The review recommends to fast track the training of trade unions and safety committees on OSH management and risk identification, especially during COVID, and report the progress through each quarterly report from now on.

Output Title	Core service delivery model applied / 4.2 Engaging stakeholders to contribute to responsible business practices
Output number:		4	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1.1 Number of compliance assessment reports completed in the reporting period	Baseline (Jun 2017): Nil / Milestone (Dec 2020): 570	Exceeded Expectation / 577 Compliance assessment reports have been completed to end March 2020.
4.1.2 Percentage of PC worker representatives that are women	Baseline (Dec 2018): 35% / Milestone (Dec 2020): 45%	Significantly exceeded Expectation / Delivered ahead of time. As of March 2020- 45% of the Participatory Committee (PC) members are women. / This was on track pre-COVID. If factories remain closed or workers get laid off, then this will have an impact on the election process of these PCs.
4.1.3 Percentage of supervisory training participants that are women	Baseline (Dec 2018): 15% / Milestone (Dec 2020): 70%	Significantly exceeded Expectation / Delivered ahead of time. More than 70% participants were women in the supervisory trainings provided in factories.
4.2.1 Number of assessment reports produced that are being accessed via subscription by Brand partners	Baseline (Jun 2017): Nil / Milestone (Dec 2020): 350	Significantly exceeded expectation / Delivered ahead of time. 515 assessment reports were used by brand partners.
4.2 .2 Number of buyer partners affiliated with BWB	Baseline (Jun 2017): 17 / Milestone (Dec 2020): 28	On track to deliver 2020 target / 27 buyer partners affiliated with BWB.
4.2.3 Percentage of cost recovery viz. total expenditures	Baseline (Jun 2017): Nil / Milestone (Dec 2020): 40%	Met expectation / Delivered ahead of time. 41% of the cost of the programme was recovered.

Briefly describe the output and provide supporting narrative for the score.
45. This indicator scores an ‘A+’. Out of six output indicators, four have significantly exceeded log frame expectations. This output focuses on improving compliance standards in factories in line with Bangladesh Labour Act (BLA) and contributes by reducing the number of social/compliance audits required by brands and buyers. Better Work Bangladesh (BWB), works with factories to improve performance in social compliance to reduce the number of social/compliance audits that brands need to undertake. BWB is the Bangladesh chapter of an ILO and IFC programme called Better Work (BW). COVID will affect how the brands work with the factories, and this component has the unique opportunity to work directly with brands to ensure workers’ safety and their voice remains a priority for all.

46. Achievements over the last year:
1. Since the last review 44 more factories (total 254) were enrolled by the brand partners into the programme, which indicates the brands are finding the social audits of BWB to be useful. The number of active brands also increased from 22 to 25.
2. The formation of Participatory Committees (workers’ committees) and safety committees has increased which is an indication of workers’ engagement with factory management on issues related to workplace safety.
3. 89 female sewing operators were promoted to supervisory roles in 12 BWB factories.
47. The major challenge identified: While the brands and factories have benefitted from improvement in workers’ satisfaction, it has not necessarily translated into efficiency gains for factories. BWB’s ultimate objective of making the factories ‘role models for compliance’ will be affected if it is unable to create its value proposition that helps in reducing the number of audits in a factory.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
48. The business case stated that the efficiency of the programme will be achieved through maximising the value of partnerships with sector associations and trade unions which will reflect in number of safety committees established. The programme has been able to set up 70 safety committees at factories out of the 254 it works with. This is a 30% increase from the previous year.

49. In terms of equity, this component works at the factories with women workers using two projects called Gender, Equality and Returns (GEAR) and Mothers@Work. These projects/ initiatives are providing training to female workers to take up supervisory roles, providing support for career progression, creating an enabling environment for mothers, and improving their understanding of their rights related to maternity protection. As of now 89 female sewing operators have been promoted to supervisory roles; and 890 pregnant women, 773 lactating mothers, and 719 management staff gained improved knowledge on maternity rights and breastfeeding protection.

Describe any changes this output, and any planned changes as a result of this review.
50. The review is not recommending any change in the output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
51. Progress towards last year’s recommendations:
1. Output indicator revision: the last review recommended including an indicator to reflect BWB’s position in the industry as a standalone compliance cost reducing programme which was found to be complex as brands are still continuing some of the compliance audits on their own, which limits BWB’s capacity to grow as a standalone compliance cost reducing programme.
2. Differentiate its Skills Training component: the programme has worked in differentiating its skills training component to ensure the approach can sustain beyond the donor intervention.
3. Scale, sustainability and revenue: the revenue of BWB has increased from £563,000 to £648,000 since the last review.
4. Disability reporting and environmental impact: the component is exploring opportunities with organisations like Centre for the Rehabilitation of the Paralysed (CRP) in developing modules to support factories in disability inclusion; and also partnered with IFC’s Partnership for Cleaner Textile (PACT) programme that provides advisory services to factories for improving resource efficiency (improved use of water/ power).
52. Lessons Learnt: The factories perceive BWB to be a high cost programme led by the brands and the brands and factories have only recently started to benefit from the social compliance improvements as it added Mothers@Work and GEAR to its offer. It is now important that BWB improves its offer by partnering with other compliance projects related to environmental impacts and the improvement of labour rights. This will help brands receive a one-stop service for all of its audit requirements and factories to become role models of compliance.

53. Recommendation:
1. BWB to develop a strategic work-plan by September 2020 that will help to create an improved value proposition of BWB and build more partnerships that will help to make BWB a unique and holistic service provider.
2. BWB to clearly articulate the action points on workers’ rights, disability inclusion, and environmental impact by September 2020; and report the success and challenges through each quarterly report from now on.
D: RISK

Overview of risk management
54. The overall risk of the programme remains ‘Moderate’. The programme operates in a sector that is both politically and economically important for Bangladesh and has been hard hit by the ongoing pandemic. Programme delivery is being affected as government partners are now prioritising COVID safety over the structural and electrical integrity of factories. There are also risks associated with outputs not translating into outcomes. These have been included in the risk register and are monitored on a regular basis. The programme has stepped up minimising the impact of the pandemic on workers’ safety and actions suggested in Section C will help translate the outputs into outcomes by 2023.

55. The risks have been discussed by DFID and ILO during monthly donor meetings and are raised as soon any new risk is identified. Discussions are collaborative, and actions are taken accordingly and reported through the quarterly reports by ILO. These are also discussed within DFID through structured bimonthly Programme Delivery Plan (PDP) meetings and escalated as per the risk categorisation.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

56. Partner performance:
1. The programme faced staffing challenges at the beginning of the programme which continued until mid-2018. This had a prolonged impact on the programme in developing an influencing relationship with stakeholders and a thorough work-plan that helps to translate the outputs into outcomes.
2. An improved work-plan to address this is required; and ILO needs to work with its donors in improving its response rate and the quality of the inputs to reduce the turn-around time in decision-making.
57. Quality of financial management:
- The programme has a standard financial management system that conforms to ILO’s financial regulations and procedures. The system uses a results-based framework in order to improve accountability, transparency and enhance ILO’s reporting processes.
- The total budget of this programme is $24.5million (£19.8million) with the UK, Netherland and Canada contributing one third each. As of May 2020, $15million (about 61% of total commitment) has been disbursed to ILO, including DFID’s £5.1million (about $6.6million). All contributions go into a multi-donor trust fund.
- Till May 2020, the programme has spent and committed to spend $13.43million which represents about 89.5% of the disbursed fund.
- ILO now has $1.57million cash in hand and requires an additional $4.02million to make the commitments for activities scheduled from August 2020 and part of 2021.
- Until now, no payment has been made to ILO in advance of need and payments from all three donors are scheduled in a way that prevents ILO from holding large amount of idle cash.
- The last instalment of £1.5million from DFID is due in August 2020. ILO has already submitted analysis of its cash position that will support their payment request of August 2020.
58. Risk and Fraud Management: The programme maintains a Risk and a Fraud Register and undertakes regular internal risk management meetings. No fraud or safeguarding incident was reported during the reporting period. ILO is receptive to information requests on risk and compliance; and responses to requests on transparency issues.

59. Programme Management: The programme is managed by DFID’s Senior Responsible Owner (SRO) with support from the Programme Manager and with oversight provided by Senior Programme Manager (SPM) and Team Leader (TL). The SRO and PM hold internal programme meetings with the TL and SPM using a PDP as a monitoring tool on a bimonthly basis. All aspects of programme management are discussed, including programme interventions, risk analysis, forecasting, financial management and reporting.

60. Monitoring:
1. As per the (M&E) plan of the programme, ILO undertakes routine internal programme monitoring, to assess the extent to which the programme has achieved the results set out in the log frame and the activities committed to in the work-plan. These are reported through quarterly reports.
2. DFID and the donor partners monitor through monthly meetings and quarterly reports. Besides these, DFID and the donor partners meet on specific issues, as and when required.
3. As part of this review, the DFID programme Team (SRO and PM) conducted virtual meetings with DIFE, Department of Labour, Bangladesh Garments Manufacturers and Exporters Association, Bangladesh Employers’ Federation, IndustryAll Bangladesh Council (labour union), Accord, Nirapon, IFC, SNV (international NGO working on workers’ rights), Fakir Apparels (BWB factory), and H&M (brand partner of Accord and RSC).
61. Evaluation: The programme commissioned a third-party desk-based and virtual mid-term review and reported at end May 2020. This will now go through a stakeholder validation process before it is published. DFID has provided input in the Terms of Reference (ToR) for this review and was interviewed for mapping the progress. The programme also has a plan for a similar end-line evaluation and the ToR will be shared with DFID ahead of the review.

62. VfM measures:
- The VfM indicators of BJB suggest good economic value for the programme will be achieved by using best practice for procurement. The programme has used open competitive bidding processes for its procurements and saved about $275,000 through negotiations. This represents 5% of the original contract value.
- Efficiency will be achieved by creating impacts that encourage the sector to replicate them. The RMG factories and labour bodies have supported setting up Participatory Committees and Safety Committees at factories, replicating the model the programme developed. 1,929 Safety Committees were set up in factories, where only 162 were set up with the direct support of the programme. This provides a good example of how the programme is efficiently embedding the practice of improving workplace safety through a bottom-up approach.
- Effectiveness will be achieved by embedding measures of sustainability so that the impact will last beyond the programme. The programme has supported developing the National OSH Profile which was taken a step further by GoB with the plan to set up a National OSH Institute to centralise all OSH learning in one place so that all stakeholders have equal access. This provides a good example of how GoB is taking ahead the OSH agenda and embedding its own sustainability measures.
- Equity will be achieved by ensuring the workplace improvements benefit women and people with disabilities to continue to do their jobs in the sector. The benefits of the Mothers@Work and GEAR components have helped female workers to continue to do their jobs after giving birth and helped them upgrade their jobs from operators to supervisory roles. Until now 890 pregnant workers have benefitted from the information on their rights during pregnancy and maternity leave, and 89 female sewing operators have been supported through their promotion to deliver and sustain at supervisory roles.
- The programme continues to represent good value for DFID’s money until now.

Date of last narrative financial report	15 March 2020
Date of last audited annual statement	02 March 2020