Conflict, Security and Stability Fund (CSSF)

Summary

Project title (no more than 1 sentence):
Support to Livelihoods Interventions in Syria

Country or Countries covered by project:
Syria

How does it fit with the NSC Strategy? Which strategy objectives is it contributing to?
This programme will directly contribute to the resilience pillar of the Syria NSC strategy. Specifically sub-objectives 3.2 and 3.5, through providing sustainable livelihood opportunities to build long term resilience of those affected by the crisis and reducing the pressure to migrate. / The programme will also contribute to the Syria CSSF theory of change. In particular Outcome 2, supporting critical economic infrastructure that will enable new economic opportunities (including private sector), and outcome 5, through building more sustainable long-term economic growth and a more equitable economy provides jobs and entrepreneurial opportunities.

Total budget for CSSF:		Duration (financial years):		Lead HMG department:
£9,000,000		3 years		DFID

Implementing partner and contact details:		HMG Project officers:
Implementing partner name and contact details removed for publication		Ewan Stoves, Programme Manager and SRO / Ben Davies, Lead Adviser, Livelihoods.

Post Programme Board comments and date of agreement:
The Syria CSSF Board approved the programme at its meeting on 25 May. The Board is chaired by the UK’s envoy for Syria and includes representatives from DFID (Head of the Syria Team), FCO and MOD.

Background and context of project
Background / The Assad regime responded to protests in Damascus and Dera’a in early 2011 with swift and brutal crackdowns that deteriorated into a bitter civil war. Five years into the conflict there are over 6.5 million people internally displaced[1]. Concurrently, livelihoods have suffered immensely with the country’s legitimate local economy destroyed, replacing it with an illicit war economy that is largely controlled by armed actors and proscribed groups, especially in areas that are no longer under the control of the government in Damascus. / Prior to the war, the main sources of revenue and employment were agriculture, the public sector, small-scale trade and industry, and tourism[2]. Now, employment, business and trade have decreased considerably[3]. This lack of livelihood opportunities, with unemployment up to 90% in some areas[4], and ongoing violence will continue to encourage Syrians to turn to armed groups for employment or flee the country to the region, and potentially on to Western Europe. However, markets do still function. For example, the domestic market still provided over 50% of food consumed in Syria. / 2015/16 programming – pilot intervention / To respond to this situation, the UK, through the Conflict, Stability and Security Fund (CSSF), provided £2.2 million for a pilot livelihoods intervention, over 11 months (commencing in September 2015 and running till July 2016). The concept was a scalable fund to support small scale initiatives that improve or enable livelihoods opportunities for Syrians. The programme model invited proposals from a range of implementers (including NGOs, local councils, provincial directorates and community groups), approving those most suited to achieving the objectives of the programme and in line with UK strategy. Focusing on building on existing skills, as opposed to only supporting those most in need, the project aims to provide sustainable employment opportunities. / Through the pilot phase, the programme supported 21 separate interventions, implemented in 28 locations (rural and urban) across areas controlled by the moderate Syrian opposition. The interventions were supported through direct procurement, local subsidies or grant agreements in a wide range of sectors. / The pilot phase has been successful in providing economic opportunities for Syrians and improving the capacity of local organisations. It is on course to meet its objectives. During the pilot, interventions included support for agriculture (providing livestock and farming inputs), production (supporting bakeries, dairy, textile and shoe factories) and energy (enabling interventions supporting electricity and renewable energy). To date the programme has delivered the following results: / Provided 170 new permanent employment opportunities / Supported technical training and inputs for over 1100 farmer households / Rehabilitated six factories and bakeries / Established and equipped three poultry and two fish farms / Funded two projects working on renewable energy / Worked directly with 28 local structures (including local councils, civil society organisations and professional groups) to coordinate and support implementation. / Lessons Learned Through the Pilot Phase / The implementing partner (IP) is developing a lessons learned document to inform the next phase of implementation. Early lessons point to: / Programme Management - The experience gained as a result of the pilot phase provides firm foundations for the scale up of the project model. Tested ideas, partners, interventions and networks are now in place in Syria, alongside programme management, reporting and governance mechanisms that enable remote delivery of interventions. Operational lessons range from the need for regular field visits prior to financial disbursements, through to harnessing advances in telecommunications (skype etc.) to maintain regular communication and a sense of presence with delivery partners and project proponents. / Scope of Interventions – Previous programming through the IP had principally focused on agriculture and water. Through DFID support, the IP was encouraged to look at a broader range of livelihoods opportunities. The three outputs of the new programme include a public and private enterprise output alongside the agriculture and water ambitions of the programme. This broadening of the programme’s focus has led to recognition that much more economic activity is taking place than was expected (producers, traders, financiers, service provision) in spite of the context. / Capacity of delivery partners - The quality of the partnerships with “delivery partners” (NGO’s, Civil Society Organisations, Local Councils) has exceeded expectations. Partners have proven to be well equipped, technically proficient and intent on setting high quality standards. The programme has found it possible to challenge the ambition of the CSOs, who in-turn demonstrated their ability to respond. Despite having no staff directly deployed in Syria, working through intermediary partners has enabled the programme to capitalise on existing high quality networks within Syria. / Shifting delivery partners’ approach - A key delivery lesson has been the need to work with delivery partners to shift their approach from a humanitarian free goods / food for work model to a sustainable livelihoods / enterprise development model. In the livelihoods model, delivery partners and project proponents take on greater responsibility, control and associated risks. This transfer of ownership, control and risk is expected to result in higher levels of ambition, outcomes and represents better VFM. / Timeframes - The pilot phase supported, a rich variety of technologies and enterprises partnerships (solar PV, poultry, fisheries, seed, fodder, shoe factory, bakery). However, the short duration of the pilot phase resulted in short project delivery time frames and a heavy focus on activities such as poultry and fisheries that could be established rapidly and yield early results. Most pilot phase projects were 2-3 months in duration, and in many cases time extensions were required. This new programme will enable a wider range of longer duration livelihoods opportunities / enterprises to be supported. / Programming for 2016-19 / The need for supporting livelihoods and the resilience of Syrians is stronger than ever. Despite the conflict, in many areas, people continue to farm, trade and find legitimate employment in an attempt to make a living. / For the next phase, the programme will continue to use the same model for implementation and take it to scale based on the evidence and lessons learned from the pilot phase. This delivery mechanism is designed to be nimble – allowing the UK to adapt and flex our support and interventions as the context changes on the ground or as new areas of interest arise. This is crucial in the Syrian context with the dynamic and regularly changing battle lines and areas of control. The programme will also provide a scalable model that could be used to fund interventions to increase livelihoods options for women, men and the youth. / Based on learning from the pilot phase, DFID and programme partners will formulate a set of “project criteria” which will guide project selection. These will include a focus on building on existing Syrian skills and expertise. It has become apparent that there are Syrian entrepreneurs who have the capacity to manage businesses, but not the resources. To respond to this, the criteria will include expanding opportunities to work directly with the Syrian private sector. Funding interventions that provide opportunities for youth will also be a priority, either through apprenticeships or vocational training. The programme will continue supporting besieged areas. Depending on the intervention this could either be through technical remote support (through video conferencing) or through the provision of funding (via a hawala system) to procure physical inputs. The programme will also focus on developing and supporting supply and value chains – linking interventions from farm to market. In addition, we will look for further ways to increase support to renewable energy projects and innovative renewable energy solutions, this is particularly important in a context where fuel is hard to procure and expensive. / The programme will mainstream gender considerations; exploring what opportunities there are for interventions that provide opportunities for men and women, and which consider the impact of the approved projects on gender dynamics (see Gender section for more details). It is envisaged that the criteria will develop as the programme continues to learn and adapt to the changing dynamics in Syria. While the specific interventions are not yet known, the programme is expected to support more vocational training and apprenticeships (focusing on youth), commercial support for nascent businesses, projects linking production sources to market and renewable energy interventions (providing alternatives to regime and Daesh fuel). / The programme will continue to coordinate closely with other actors working in livelihoods and resilience. The implementers have already, and will continue to, coordinate with other UK-funded interventions, such as the CSSF funded and DFID managed, Tamkeen local governance programme (and its successor) and the agriculture programme, which works alongside the Syria Interim Government and through local councils, to provide technical agricultural support and subsidised farming inputs. In addition there will be increased emphasis on ensuring coordination with the DFID humanitarian response through formal and informal meetings and developing an overarching livelihoods strategy for UK support to Syria (covering humanitarian and stabilisation programmes). / The programme’s comparative advantage is that it can work in a wide range of locations (all within opposition controlled territory), it can test innovative approaches at a small scale and is able to target a beneficiary group considerably different from those receiving humanitarian assistance. This programme will continue to prioritise those with existing skills and moderate financial capabilities, as opposed to the most in need.
[1] UNHCR Syria Country Profile (http://www.unhcr.org/pages/49e486a76.html)
[2] Countering the logic of the war economy in Syria; evidence from three local areas, Rim Turkmani (July 2015)
[3] Assessment of Needs and Humanitarian Situation Inside Syria: Livelihoods, REACH (Sept 2015)
[4] Vulnerability and resilience to recruitment by violent extremist groups in Syria – Alert International (May 2016)

Impact and change
Impact / The programme’s impact statement is to support economic resilience and inclusive growth at community level, enabling greater choice and stability. It will contribute to resilience as well as sustainable livelihoods for Syrian people by increasing job opportunities. In addition, different points of supply chains will also be strengthened. Depending on the intervention, the programme could support production (at the agricultural level), processing of goods (potentially through factories) and at the point of sale (commercial support or providing support to businesses). Additionally, the programme will seek to increase impact by docking onto existing interventions. For example, through the pilot phase the programme supported an intervention in a besieged area that produced natural fertilizer from solid waste, which was collected as part of a project funded by a separate programme. / The programme will help to ensure that dependency on humanitarian assistance does not increase. It will enable greater resilience for Syrians in opposition-controlled areas, promote opportunities for small-scale private enterprise and contribute to reviving Syrian economic opportunities. It will lay the foundations for a longer term focus on livelihoods following a political settlement. / Expected Outcomes and Outputs / DFID has agreed with the IP a draft results framework (attached at Annex B) which has been informed by lessons learned from the pilot phase. The framework will be refined during the first year of operation. DFID’s investment in the programme will contribute to the following expected results by the end of the programme: / At the Outcome level: / 10,000 hectares of additional farming land in use yielding an additional 60,000 tons of agricultural products / 400,000 additional people in 20 communities having access to water and irrigation services. / 800 public and private entities delivering improved services / 700 income generating opportunities and 500 permanent jobs created. / At the Output level: / 150 specialist technicians (public and private entities) receive training in crop production, livestock production and food processing. / 9 agricultural infrastructure units rehabilitated and providing improved services. / 30 SME produce marketable surplus of agricultural products. / 10 Gender targeted processing and marketing projects for agricultural products. / 250 additional hectares of cultivated land irrigated. / 5 public energy networks rehabilitated to support domestic and manufacturing capability. / 500 permanent jobs created in manufacturing, agriculture services and commerce. / Business development support to 20 SMEs have increased turnover and outputs / 20 CSOs organisational capacity strengthened and delivering quality services. / Theory of change / The programme’s theory of change is set out below. / The theory of change recognises the conflict has caused the Syrian economy to contract sharply, and led to many people becoming increasingly dependent on humanitarian aid. However, there are still a large number of people with the skills and experience who would like to re-engage in legitimate economic activity. / Reviving livelihood opportunities will contribute to reducing reliance on support from humanitarian or other actors and reduce the lure of armed groups. By building this resilience the programme should contribute to the stabilisation of small pockets of opposition controlled area. As numbers of people with an economic stake in stability grow, it is assumed that support for moderate and accountable forms of governance that can deliver services will grow.

Evidence base
Reviewing the research / Unemployment in Syria is endemic and as a result remittances, sent from outside of Syria, are often the main source of household income[5]. REACH, a humanitarian data collection and analysis organisation, produced a livelihoods report which identified agriculture as one of the most common pre-conflict sources of livelihoods, particularly in the governorates under the control of the moderate opposition which have large rural based populations. In Damascus governorate, the REACH report found the majority of incomes were derived from trade and business. This evidence supports the pilot programme’s approach to building on existing skills; supporting small scale businesses in urban areas and providing agricultural and farming inputs in other areas. / Other research points to the fact that markets remain accessible and are still functioning. A 2015 survey of eight locations across Aleppo and Idlib governorates, using a modified household economy survey, found that the poor and the very poor got 40-50% of their food from markets and the rest as food aid, and rely on unskilled labouring jobs to make an income[6]. This would indicate that providing agriculture/farming inputs and reinforcing market chains should enable sustainable economic opportunities. / A comprehensive assessment of livelihoods in Southern Syria was also conducted in November 2015 by CARE International[7]. It recommends improving access to agricultural inputs, supporting processing and supporting small business development. It also highlighted travel to work as a major challenge. This was characterised by jobs being too far from where people are living, the insecurity of travelling and the cost of transport. This programme could potentially address this challenge by providing inputs for household production interventions or more localised employment opportunities. / A joint Food and Agriculture Organisation (FAO) and World Food Programme (WFP) mission in July 2015 recommended the need to increase support to backyard vegetable production, dairy processing and bakeries[8]. In addition, a paper by ARK[9] found that unrefined diesel (mazot) provided by Da’esh was being widely used to operate generators. The mazot is expensive, putting additional strain on limited resources, and provides direct funding to Da’esh. Continuing to support enabling projects (such as improving electrical infrastructure) and renewable energy sources is expected to decrease the dependency on fuel from either Da’esh or the regime. / The programme can further support countering Da’esh, and other proscribed groups, through providing alternative livelihoods options. It has been noted that the extremely high levels of unemployment, together with high prices and the absence of other sources of income, has left men of fighting age, who typically have to provide for their families, in a very exposed position and vulnerable to recruitment by extremist organisations[10]. The provision of genuine, sustainable, employment opportunities could undermine recruitment by these groups. / Monitoring and Evaluation (M&E) / During the pilot, an M&E plan was developed, which the new programme will build upon. Local stakeholders, such as local councils or NGOs, who will be receiving support through the programme, will provide the first layer of monitoring through regular reporting and providing photographic evidence. This will be complemented by a network of field monitors employed by the implementing partner. Through the pilot, field monitors have been employed in two of the governorates, and by the start of the new programme, the network will have expanded to include the other governorates. The field monitors will focus on priority projects, as directed by the management team, and conduct ad hoc site visits to review progress and delivery of the interventions, as well as collect beneficiary feedback. The field officers will also support implementing partners to build their M&E capacity. / As part of the M&E plan, the pilot has developed a package of tools to enable more consistent reporting and M&E from delivery partners. Standardising the package of reporting instruments and up skilling the partners will provide greater assurance that programme outputs are being met and the partners have the capacity to provide adequate reporting.
[5] Assessment of Needs and Humanitarian Situation Inside Syria: Livelihoods, REACH (Sept 2015)
[6] Understanding livelihoods in Northern Syria: How people are coping with repeated shocks, constant change and an uncertain future. SCF January 2015
[7] Livelihoods Assessment in Southern Syria: Dar’a & Quneitra, CARE (Nov 2015)
[8] FAO/WFP Crop and Food Security Assessment Mission to Syrian Arab Republic (July 2015)
[9] Local Councils and service provision networks in southern Syria, ARK (Feb 2016)
[10] Countering the logic of the war economy in Syria; evidence from three local areas, Rim Turkmani (July 2015)

Procurement
Management agreement / For the pilot phase IP were selected as the preferred implementer, co-managing the programme another IP. Both are based in Turkey. The new programme will see a continuation of this arrangement, with the IP directly supported by DFID through a Memorandum of Understand (MoU). They will subsequently sub-contract. / The IP were already implementing a similar model, commissioned by another donor; a €4 million intervention which ends in March 2017. UK support enabled an augmentation in scope and scale of the initiative. While under the auspice of the other agreement, the UK-funded component operates as a separate programme; with clearly defined outcomes and budget lines. The other donors are in the process of extending their programme until March 2019 with an additional €12 million. / Procurement for interventions / The IPs directly sub-contract delivery partners; including international NGOs, local NGOs, technical directorates and local councils. As previously noted, the funding takes a variety of forms. If the support requires direct procurement, The IPs procure the goods or equipment outside of Syria and then import to the project location. / Alternatively, interventions can be funded through direct financial support. If the delivery partner is new or inexperienced they will likely be supported through subsidies. Subsidies will involve purpose tied payments for specific activities. For example, this could involve subsidies to cover procurement of equipment and start-up salaries for staff, or for agricultural inputs. / More experienced partners, or ones that have worked with the IP previously, can be supported through the provision of local grants. While still tied to specific overall objectives, these will provide delivery partners more freedom in accomplishing these objectives. This freedom should enable a more flexible approach and enable the partner to be more responsive to changes on the ground. In order to be eligible for a grant, the recipient organisation must pass an assessment of their commercial capacity by the IP. Delivery partners are required to supply receipts and reporting to ensure activities have been conducted and that funding is reaching the intended beneficiaries. Receipts will cover all procurement conducted by delivery partners and will report against project activities and financial performance (see more under Flow of Funds below).

Implementing partner(s)
Value for money (VfM) / The IPs have successfully managed the programme during the pilot phase. As a result, there is a strong VfM argument to continue to use these implementers and to further refine the model that has already been developed. / Economy: Of the £9 million total programme budget, £7.8 million (or 86%) is committed to project grants, procurement of inputs or capacity building measures of partners. The remaining 14% is for staffing, operating and administration fees. This represents good value and arguably better than you would get with a commercial or multilateral partner. As some of the interventions are supported through direct procurement, there will be no additional administrative fees for these (the whole intervention budget is based on the procurement completed by the IP). Even where grants are given to Syrian organisations, the staffing costs included will contribute to providing livelihoods for people living inside Syria. / Efficiency: Where possible, implementing the programme directly through local councils, provincial directorates and local Syrian bodies provides a more efficient and sustainable mechanism for delivery. Additionally, when working with Syrian implementers, the IPs hold regular workshops, inviting them to undertake lesson learning exercises and build networks with each other. They also receive training in financial management, managing risk, collating and responding to beneficiary feedback, adhering to do-no-harm principles and undertaking M&E. Building the capacity of the local partners should deliver a more efficient and effective cohort of implementers who are better able to produce concepts and deliver programme objectives. / Effectiveness: As noted above, the systematic approach of working with existing supply chains and through governance structures should contribute to more effective and sustainable programme outcomes. Increasing the capacity of these structures to better manage production, livelihoods and economic opportunities. / Additionally, the approach of building on existing skills in Syria, and not (simply) focusing on those most in need, should provide a more effective programme. For example, establishing a textile factory of staff with existing skills in garment production and factory management is more likely to lead to a successful, self sustainable business and provide broader livelihoods outcomes. / The main cost drivers will continue to be the grants with implementing partners and direct procurement of equipment and goods. / Delivery partners / Delivery partners are identified in a number of ways; existing relationships or partnerships with the IPs, partners directed to the programme by other stakeholders or programmes, and partners that have been actively sought out. In all cases, the IPs have procedures in place for ensuring robust management of delivery partners. As noted under the Procurement section, partners that enter into financial agreements with the IPs are subject to commercial capacity assessments (which include registration in a country outside of Syria, correct banking procedures and financial management processes). Contracts are also put in place with delivery partners which include provisions for programme objectives, reporting schedules and, if required, financial remuneration. The projects are monitored to confirm performance against each accounting period. / Due Diligence / A light touch due diligence assessment (DDA) of the IP was conducted in 2015 with no serious issues raised, noting that “overall, the IP has well established and documented procedures across the components” assessed. A refreshed DDA will be undertaken prior to the programme start date, enabling the assessment to cover the full three years of the programme. The IP have an established presence and have developed a strong, effective network of Syrian delivery partners.

Implementing partner reporting and safeguards
Reporting and governance / The IP has confirmed they will provide the required progress and financial reporting to comply with DFID and CSSF standards. The IP will also provide quarterly reporting based on agreed upon templates. These will measure progress against logframe indicators, updating risks, identifying lessons learned and making assessments of VfM. / The IP will host a quarterly Programme Management Committee (PMC). The PMC, with representation from both IPs and DFID, is the mechanism for providing final approval for project proposals. The PMC will also be the main forum for discussion of other programme issues; including reviewing risk, lesson learning, ensuring the programme remains fit for purpose and horizon scanning. / To maintain sufficient oversight of the programme, DFID’s governance arrangement includes a Senior Responsible Owner who is also the Programme Manager, along with a Livelihoods Adviser. / Flow of funds / The MoU will set out the payment tranche schedule between DFID and the IP. Upon receiving a payment request, accompanied by a financial forecast and utilisation report, money will be transferred to the IP. Payment will not be made in advance of need. / Depending on the nature of the intervention and the agreement with the delivery partner, the IP will either directly procure items or will set out a tranche payment schedule. For interventions that require direct procurement of inputs, these will be conducted by the IP outside of Syria. Only in exceptional cases (e.g. the sourcing of local genotypes of seeds) will local procurement be permitted, upon approval from HQ and using a rigorous process. / Partners receiving local subsidies need to adhere to strict procedures and the IP will crosscheck all receipts (either hard or scanned copied). Payments will only be made upon satisfactory confirmation that funds have been utilised and a corresponding report. If funds have not been utilised or the partner does not deliver their required reporting, subsequent tranches will not be released. As noted earlier, grant agreements will only be given to experienced partners, which require requisite commercial capability assessments. This assessment evaluates the recipient organisation’s ability to process financial contributions, including checking if there is an appropriate accounting system and appropriately qualified personnel. / Risk assessment / Implementing in Syria is high risk. The UK has accepted a high risk appetite for programming and the programme will operate within this appetite. / The context of the ongoing conflict is a major risk. The threat of shrinking opposition-controlled territory, to either the regime or Da’esh, will directly restrict where the programme can operate and limit opportunities for livelihoods. Additionally the risk of diversion of programme funds or inputs is high, potentially heightened by the fact the programme is managed remotely. To reduce the impact and likelihood of diversion partners have taken steps such as only transporting goods into Syria once ready for immediate distribution and establishing a network of field monitors. / Due to the programme design, a major risk remains the capacity of Syrian organisations to formulate ideas and implement them. To mitigate this risk, the IPs will support and build the capacity of delivery partners through regular engagement and hosting workshops. In addition, other UK-funded programmes will also support capacity building of Syrian organisations; including the CSSF-funded and FCO led, Support for Civil Society programme and DFID’s support to local governance. These mitigating actions should reduce the likelihood of the risk materialising. / Overall, the programme is deemed high risk. Nonetheless, the mitigating actions should enable reducing some of the likelihoods and/or impact of the risk to delivery. The programme risk register maps out the main risks to the programme and the mitigating actions (see below). It will be reviewed regularly with the programme partner. Programme level risks will also be incorporated into the Syria CSSF risk register which is presented to the Syria CSSF Board on a quarterly basis. / Fraud and anti-corruption / The IP has a zero tolerance approach to fraud and corruption. Staff members sign a code of conduct agreeing to prevent corruption and report questionable behaviour, cross-checking procedures are in place and grant agreements include anti-corruption clauses. In accordance with the MoU, the IP will report any allegations of fraud to the DFID Programme Manager who will in turn alert DFID Counter’s Fraud and Whistleblowing Unit.

Human rights assessment
Human rights will be taken into account to ensure the programme is not giving preference to one community or ethnicity over another; and to ensure it promote inclusive participation, including minority groups, IDP communities and especially women. / Besieged areas / The Assad regime has increasingly used besieged areas as an economic crutch, and wealth extraction has become a key component of the regime’s sieges. Frequently there will be a small number of traders, in partnership with the regime, selling goods at extremely inflated prices. This further increases the suffering and undermines the resilience of the population[11]. During the pilot a number of projects were implemented in besieged areas. Through CSSF programmes on governance and livelihoods we have successfully demonstrated the ability to operate in besieged areas. This has been possible because there continue to be ways to access these areas through tunnels which enable the transportation of inputs, in addition hawala networks continue to operate. The programme will continue to seek opportunities to support livelihoods in besieged areas while remaining conscious of the challenging operational context in which violations of international humanitarian law (IHL) are frequently carried out by proscribed groups and other armed actors.[12]
[11] First Quarterly Report on Besieged Areas in Syria February 2016 – Siege Watch
[12] FCO Human Rights Report 2016

Gender
In accordance with the International Development Act (Gender Equality) 2014 and DFID Smart Rules, the programme has taken into account gender-related impact. Through the pilot, interventions have demonstrated that there are many ways the programme can ensure it is meeting the specific needs of women, men, girls and boys. The programme will continue to focus on supporting employment opportunities and training which are accessible to women, this will include identifying specific industries which traditionally have been managed by women, or which employ women, and where skills already exists. When needs assessments are conducted, they will also specifically look at the needs of women and girls to ensure the programme is context appropriate. / Estimates suggest women make up 65% of the population who could potentially work, however only 22% of the economically active population are women. The disparity between the number of women who could work, and the number that actually do is in part due to local traditions in more conservative areas. The PMC will consider the gender-impact of all the concept notes and encourage concept notes which focus on providing opportunities for women and girls.

Conflict Sensitivity
Due to the programme design, conflict sensitivity will be considered on a case by case basis, under the overarching effort to understand the conflict dynamics and balances of power in any area the programme operates. This will manifest itself in ensuring beneficiaries are selected appropriately and without bias, land ownership issues are properly resolved prior to concept note approval and that needs of both displaced people and host communities are considered. Delivery partners will also be required to comment on power dynamics in any potential locations for implementation. In addition, awareness-raising sessions regarding the do-no-harm approach will not only be applied during the phase of developing project proposals, but will also be included in training of delivery partners. These measures will enable the project team to better understand the situation on the ground and the impact that the project activities will have on the local dynamics. / The programme will also continue to understand and work alongside the burgeoning war economy. The ebb and flow of control of territory and the often uneasy relationships between various armed groups has led to a complex and changing situation. Despite this, the war economy that is emerging is not entirely chaotic. Armed groups do make money through looting, kidnap and levying charges at checkpoints but there are also emerging informal supply chains. The programme will continue to explore opportunities to strengthen and exploit informal supply chains. Building links between different actors, including across front lines, could support local level peace building between traders and consumers in regime and opposition held areas. The programme will continue to analyse the conflict and power dynamic to understand how the interventions approved contribute to these dynamics.

FINANCE
Budget breakdown:
	2016/17	2017/18	2018/19	% ODA	% Non ODA
CSSF costs	£3,000,000	£3,000,000	£3,000,000	100%	0%
Other donor costs	n/a	n/a	n/a
TOTAL	£3,000,000	£3,000,000	£3,000,000	100%	0%

*Full budget must be provided separately (see Annex C).
*All project implementers must follow the FCO guidance on procurement and appropriate costs. This guidance can be found on the MENAD CSSF Communities site.

Equipment
In accordance with the project agreements that will be signed with the IP, materials and equipment purchased as part of the interventions will become the property of the delivery partner on their arrival, or will be purchased in-country by the implementing partner. The IPs will record all assets purchased on an inventory.

RISK
#	Risk	Mitigating Actions	Net Likelihood (1-5)	Net Impact / (1-5)	Net Risk[13] / (1-25)
1	Low levels of capacity of partners inside Syria (councils, directorates and NGOs). Could potentially mean local partners are not able to communicate or formulate effective ideas, submit proposals or implement the project	The pilot phase demonstrated strong demand for support from Syrian partners and limited investment in building their capacity has already been made. In addition, the IPs will work in collaboration with local institutions to continue to build capacity. / The programme could work through international NGOs who have the capacity to communicate and formulate ideas. / Other UK funded programmes (i.e. FCO led CSSF funded Civil Society Programme) help build capacity of local NGOs (including proposal writing) and the current and future DFID managed local governance programmes will build capacity of local councils.	2	5	Major / (10)
2	Diversion of programme materials, inputs unaccounted for or cash grants diverted/embezzled.	Goods will not be stored in Syria until fully ready to distribute to approve beneficiaries. Distribution of goods will be done by approved and vetted partners. / Communications inside Syria will be undertaken to ensure the population knows who the support is intended for. / A complaints and a transparent system of reporting diversion back to the IP will be undertaken. The MOU between DFID and the IP stipulates all allegations of fraud must be reported to the DFID Counter Fraud Section. / Field monitors will ensure support is going to the approved beneficiaries. / DFID will close/ suspend the programme if clear diversion is occurring.	3	4	Major / (12)
3	Daesh/other proscribed groups do not allow programme activity or exercise undue influence over activities	A security adviser, working with the IP, will ensure updated information on conflict and movement of proscribed groups to provide early warning. / In the event of undue risk, the project could be terminated/ amended, in agreement with DFID.	3	4	Major / (12)
4	Livelihood projects do not generate significant income for beneficiaries and cannot be sustained after DFID funding concludes	The selection of projects will include robust economic appraisal, including marketing options. / Negotiations with local councils and communities on the acceptability of project will be undertaken to ensure a shared understanding of outcomes.	2	3	Moderate / (6)
5	Opposition lose control of programme areas to extremist groups or the conflict is such that the programme cannot operate.	The programme team will carry out a detailed assessment of programme locations. / Close cooperation/liaison with partners in Syria will enable flexibility of cooperation and adjustment of distribution. / No material will cross the border until all preparation has been completed and the material is ready for immediate distribution. / Reallocation of materials and equipment to another area under opposition control.	4	3	Major / (12)
6	Allocations done in such a way that they exacerbate existing tensions.	Programme inputs will be carefully managed by the IP. / Interventions will have clear beneficiary selection criteria and will have been required to report on beneficiary feedback quarterly. / Aid diversion will be reported if it occurs (as noted above). / Conflict sensitivity will be built into the programme and the CSSF conflict adviser will provide support where required.	3	3	Major / (9)
7	Duplication of effort with other donors, UN agencies and/or INGOs	The IP will coordinate with other livelihoods actors through the Food, Security and Livelihoods Cluster. / UK will coordinate with donors and cross-HMG, including with the DFID Syria humanitarian team.	2	2	Minor / (4)
8	Turkish / Jordanian authorities refuse permission for people and goods to cross the border.	Appropriate negotiations with authorities will be undertaken before interventions commence. / There will be further investment in the relationship with Jordanian Security Services in the South to ensure facilitation is provided when required.	2	4	Moderate / (8)
9	Turkish authorities' willingness to facilitate programming (i.e. hosting partners, enabling border crossings, taxes) is reduced	The IP will be asked to explore contingency planning for such an occurrence. We will also ask them to consider carrying out remote training and increasing procurement within Syria. / Where appropriate, the UK will lobby Turkish authorities on border crossings and access.	3	3	Major / (9)
10	Safety of implementing partners’ staff.	Security contingency plan will be developed in order to ensure implementers are as safe as possible and ensure partners are receiving information from INSO to have latest information on security incidents.	3	3	Major / (9)
[13] Net risk is derived from combining the net likelihood and impact of each identified risk. By multiplying these you arrive at net risk value, which translates accordingly: Minor (1-4), Moderate (5-8), Major (9-14) and Severe (15-25).