Annual Review - Summary Sheet

Title: EUROPE DEPARTMENT MONITORING AND STRENGTHENING EU PROGRAMMING THROUGH THE EUROPEAN DEVELOPMENT FUND (EDF)
Programme Value: £2,684,646,986.17		Review Date: 13/01/17
Programme Code: 200236	Start Date: 20/11/08	End Date:31/12/20

Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	A	A	A	A	A
Risk Rating	M	M	M	M	M

Summary of progress and lessons learnt since last review
Europe Department (ED) has made progress on eleven of the output milestones. Most notable have been the significant progress on the development and embedding of the EU Results Framework, engagement with DEVCO and other member states on the Emergency Trust Fund for Africa and continuing work to raise the quality of the EU work on gender issues. The ED programme SNEs have been a major factor in these successes. ED effectiveness in management committees was recognised by Internal Audit and at official level, ED has continued to be influential on Commission thinking.

Commission receptiveness is also an important factor and where ED capitalised and built on this a more productive relationship followed.

Progress stalled during the run up to the referendum when engagement with the Commission on policy issues was not possible, and since then the UK has needed to reguage where its voice and influence are likely to be successful.

Until the exit negotiations are concluded, the UK remains a full member of the EU and all the rights and obligations of EU membership remain in force.

Summary of recommendations for the next year
As well as working with the Commission ED plans to work with and through like minded colleagues to raise the profile of reform issues and areas where UK wants to see sustained Commission attention. This will require an adjustment of the delivery plan to focus on where DFID/ED can continue to be influential.
Key recommendations:
- Build other member state interest in commencing a dialogue with DEVCO staff to ensure the EU’s anti-fraud strategy is embedded and that they are aware of their responsibilities in identifying and raising concerns
- Continue to put pressure on the Commission to improve transparency and improved data accessibility to enable better tracking of where EU contracts are awarded
- Explore opportunities to work with the Commission on sharing experience on creating a learning organisation working closely with the Results SNE
- Through the Results SNE in DEVCO ED will continue to press for a revision of the EU Results Framework to bring it in line with the SDGs as well as the European Consensus
- Work through the Gender SNE to ensure there is a clear plan in place to follow up the next published report in April 2017
- Continue to develop and implement the ED-led cross-Whitehall engagement strategy on the EU Emergency Trust Fund for Africa Joint programming
- Continue to ensure UK red lines are maintained and provide guidance to country offices when needed
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	None
DevTracker Link to Log frame:	None

The EDF derives from the European Union’s Cotonou Partnership Agreement. It provides support to 78 African, Caribbean and Pacific (ACP) countries and Overseas Countries and Territories (OCTs) to eradicate poverty, support sustainable development and integrate ACP countries into the world economy. The Cotonou Agreement expires in 2020.

Although the EDF is managed by the European Commission (EC), it sits outside the framework of the EU general budget. The UK is required as a signatory of the Cotonou Agreement to provide on-going financial contributions to the EDF as an international treaty obligation. The UK first became a contributor to the EDF under its 4th replenishment following accession to the European Community in 1973.

The EDF is primarily used to finance EU country, regional and intra-ACP programmes in ACP countries. It also provides support to the Overseas Countries and Territories (OCTs) of four EU member states, including several UK Overseas Territories.[1] There is also a revolving loan facility managed by the EIB for the financing of risk capital investments and loans in ACP states and OCTs.
[1] EU relations with the OCTs are governed by the EU-OCT Association Decision.

Many of the ACP states have long-standing historical relationships with the UK and are members of the Commonwealth. The EC has aid and development programmes in nearly all 78 ACP countries and hence provides much needed aid and technical assistance in countries where there is no DFID bilateral programme. EC development programmes also go beyond aid into trade, investment and the provision of global public goods.

The UK’s contribution, which stands at roughly 15%, supports DFID’s priorities and affords DFID influence over the EU’s development spend to reduce poverty. UK ranks third after Germany and France as EDF contributors.

As one of 28 EU member states ED recognises it needs to focus on where it can have maximum influence, building alliances with other member states to secure progress on UK priorities or through building a direct relationship with European External Action Service (EEAS) and DG International Development and Cooperation (DEVCO).

The EDF Deliver Plan was drafted in 2014 and had the following three outputs:
a.	ensuring EU funds are well spent through continued engagement with the EU on fiduciary management including sustained improved forecasting, implementation of the Action Plan to improve financial management, and will complete a desk review of procurement and fraud procedures
b.	ensuring EU programming that focuses on priority areas of gender, risk and results, supported by improved evaluation and monitoring, and better reporting of results
c.	ensuring the EU makes appropriate use of the range of instruments available including the development of new instruments

The Delivery Plan covers the period 2015 to 2017. Although UK priorities for the EDF will remain until 2020, 2017 marked the midpoint of EDF11 and, prior to the referendum on EU membership, the beginning of the UK EU Presidency. Milestones are based on best estimates of when key EU actions are likely to have taken place and will be adjusted throughout the delivery plan to reflect the reality of issues beyond DFID’s ability to control.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Despite the constraints of the referendum and its outcome, ED had made continued progress in its priority areas and strengthened its influence, notably in management committees and in the EU Emergency Trust Fund, results framework and gender work.

ED continued to be a respected development partner particularly in our close cooperation in management committees and on the trust fund. Concerns when raised were taken seriously and addressed.

The Commission continue to improve financial management especially in predictable forecasting and follow up on ECA recommendations. ED influence on this is not high but continued attention by UK and other member states continues to keep the Commission focussed on improvements.

Developed in 2014, the current Delivery Plan is due to end in June 2017 and ED expect progress to continue until then. ED are revising the Delivery Plan to continue to the date of UK Exit from Europe, to respond to recommendations from the Multilateral Development Review while continuing to fulfil our responsibilities as a member state including tracking EU spending.

Overall output score and description

A
Outputs met expectation

Key lessons

The need for other member state support for ED priorities is especially important where Commission buy in is weak. Where we can support our priorities with support for example in the form of SNEs, there is more likely to be progress. This is especially true when trying to change corporate EU procedures or approaches such as commercial or evaluation approaches.
ED’s Seconded National Experts (SNE) programme has ensured, through the placement of strategic posts seconded to the EU, that the Gender Action Plan and EU results framework as UK priorities have been implemented.
Actions on second level priorities such as the performance based mechanism, while successful in keeping the issue alive, faced overwhelming competition from the switch of EU and member state focus to the migration crisis which diverted funding away from the initial priorities for EDF 11.

Key actions
- ED to revisit the Delivery Plan to focus on areas where UK influence remains high and/or likely to secure other member state support
- Action to progress ED priorities needs to happen quickly in 2017 while UK influence remains high at official level
- DFID should continue to push the EU to be an effective development partner for the long term
- ED should refresh the priorities for EU programming focus in management committees, and if possible, secure likeminded support in the form of a letter to the Commission.

Has the logframe been updated since the last review?

Yes. Milestones continue to be best guess where EU reports are needed, for example, the EuropeAid Annual report for results and the budget support report.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Ensuring EU funds are well spent through continued engagement with the EU on fiduciary management including sustained improved forecasting, implementation of the Action Plan to improve financial management, and completing a desk review of procurement and fraud procedures
Output number per LF		1	Output Score	A
Risk:		Moderate	Impact weighting (%):	33%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
EU Financial management improved	Autumn 2016: decrease in likely error rate in payments, no deterioration in financial mananagement highlighted in audit Tangible actions in place from CRIS action plan	[2]DEVCO’s 2015 residual error rate study (RER) estimated the RER at 2.20% (down from 2.81% in 2014). The 2012 and 2013 European Court of Auditors reports presented 12 recommendations. In 2015 DG DEVCO had fully implemented 11 recommendations, including those relating to CRIS, whilst one was implemented in most respects.
EU has robust anti fraud and corruption procedures in place	March 2016: IAD final report issues	IAD final report issued in April 2016. Further work was interrupted by the run up to the referendum and the subsequent vote to leave. We have flagged the IAD findings on fraud with like minded group with the aim to raise the profile of the OLAF/Commission approach to reporting and follow up on suspected fraud.
Procurement: / Commission has robust procurement systems in place that meet international best practice and make use of EU comparative advantage eg. pooled purchasing power	March 2016: renewed discussions with Commission on stage 2 of procurement review	Discussions with the Commission continued through to February 2016 in the context of the Multilateral Aid review which took up value for money. Further work was interrupted by the run up to the referendum and the subsequent vote to leave. ED, working with other member states, drove down the administrative element for the EU TF.
Commission sustains improved accuracy of forecasts for Member State contributions including better alignment of the profile of contribution payments with the profile of programme payments.	October 2016 EC Communication on EDF forecasts of contributions, payments and commitments shows no significant change.	[3]October Communication confirmed no change in forecasts for 2017 or 2018. Indicative figures for 2019 and 2020 demonstrate a smoothing of the payment profile making budgeting for member states more predictable.
[2] http://eca.europa.eu/en/Pages/DocItem.aspx?did=37912
[3] http://eur-lex.europa.eu/legal-content/EN/TXT/?uri=COM:2016:652:FIN

Key Points

Following the UK’s vote to leave the EU our vision for reform has been carefully refocused to take account of what could realistically be achieved by the time of our Exit and where we could secure Commission attention.  This applied especially to outputs 1.2 and 1.3. ED has continued to press the Commission on sound financial management in working groups.

Summary of responses to issues raised in previous annual reviews (where relevant)

Along with other member states ED have raised financial management issues in working groups in Brussels, notably following the ECA Audit report in November.

ED continued to put pressure on EU to engage on fraud and commercial reviews through the IAD Assurance Review and the MDR. In the run up to the referendum engagement with the Commission on these sensitive policy areas was not possible. The referendum outcome has made influencing the Commission more difficult. ED have raised the findings from the Assurance Review with other member states and will push for a coordinated push in 2017.

Recommendations

Increasingly ED will need to work through like minded groups to raise the profile of reform issues and areas where UK wants to see sustained Commission attention.

Once the revised ED EU Reform Programme is finalised we propose to commence a dialogue with DEVCO staff to ensure the EU’s anti-fraud strategy is embedded and that they are aware of their responsibilities in identifying and raising concerns. We will also work with like-minded member states to influence the EU Anti-Fraud Investigation Institution’s (OLAF) independent Supervisory Committee to improve the performance, systems and transparency of OLAF. We should be realistic about our ability to influence the Commission or OLAF directly as we negotiate our exit from the EU.

Further progress on changing the Commission approach on procurement is now unlikely. Instead ED will continue to put pressure on the Commission to improve transparency and improved data accessibility.

Output Title	Ensuring EU programming that focuses on priority areas of gender, risk and results, supported by improved evaluation and monitoring, and better reporting of results
Output number per LF		2	Output Score	A
Risk:		Minor	Impact weighting (%):	33%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
EDF programmes progress DFID priorities of gender, economic development and results	January 2016: Management committees (MCs) move beyond programme approval point to include strategic updates on eg. budget support, financing, evaluations. / July 2016: MCs discuss one horizonal issue at each Committee meeting	ED has established an effective network with DFID country offices on EU issues enabling a more systematic approach to engage geographical colleagues. This has lead to a noticeable increase in engagement which has contributed to more effective working with member states and EU institutions in country as well as in Brussels (examples include Zimbabwe, Somalia, Ethiopia, Caribbean). ED engage individually with FCO posts. Both have contributed to more effective working with member states and EU institutions in country as well as in Brussels. / List of 2016 strategic updates at EDF management committees: / State of play of the implementation of EDF Rules of Procedure one year later / Evaluation of gender equality and women’s empowerment / Strategic evaluation of the European Union's cooperation with the Pacific Region (2006-2012) / Evaluation of EU support to environment and climate change in third countries / European Investment Bank (EIB) biannual update on activities under the Investment Facility / Evaluation of the Cotonou Partnership Agreement / Update on the EU’s financial contribution to the EFSD Guarantee Fund / State of Play of the EDF11 Reserves / Results Orientated Monitoring / Regional Intra ACP / European Investment Bank (EIB) biannual update on activities under the Investment Facility
Strong evaluation processes enabling lessons learned and results to be shared	July 2016: EC report evaluations completed to EDF Committee. Active like minded group secure change from HES meetings	Commission circulated evauations to MS although only the Results Orientated Monitoring Summary Report discussed in Management Committees. ED confirmed it would be following up with a view to increasing MS/Commission engagement taking forward action on the recommendations. / The technical expertise provided by the DFID SNE based in the DG DevCo evaluation unit has been highly valued. / DFID built a good relationship with the Head of Unit, who has since left, before follow up action could happen, notably on pushing for impact evaluations (rather than the contribution evaluations the Commission does). / Engagement by other MS remains disappointing.
EU results framework reports baseline and progress data	Autumn 2016: EuropeAid annual report reflects results framework reporting	In June 2016 the European Commission published its first results report (covering projects completed between mid-2013 and mid- 2014). Alongside reporting on all three levels of the EU results framework, the report also included results information for individual countries. / The second results report (covering projects completed between mid 2014 and mid 2015) was published in December 2016 as part of the International Cooperation and Development Annual Report. Country results information has been provided separately on the EuropeAid Internet site. / Both reports were produced with substantial technical input by DFID SNEs in EuropeAid’s Quality and Results Unit.
EU programming has increased focus on improving the lives of girls and women	July 2016: First country analysis issues showing progress against new GAP	Significant DFID SNE input continues to ensure momentum on gender issues. The first round of reporting under GAP II has now been completed, with over 90% of EU Delegations and Institutions having submitted their GAP report. An interim gender helpdesk was set up in March 2016 to support Commission services with their analyses, and a longer term helpdesk will be available from January 2017. / In October 2016 ED provided guidance to DFID country offices to strengthen their country level reporting following issues they had encountered with the EU guidance. In December ED provided recommendations to the Commission on how the broader reporting template and indicators could be improved ahead of the next round of reporting, based on our experience of filling it out as a Member State.
EU programming developed in consultation with beneficiaries	January 2016 workshop, country consultations on reaching beneficiaries through CSOs, local governments etc.	Commission appetite for a workshop dissipated. However, ED continued to press the need to consult beneficiaries switching attention to the collection of evidence in support of the €2.3 bn Trust Fund programmes. The Research and Evidence[4] facility for the Horn of Africa has been set up to provide “an informal space for the sharing of ideas and critical responses coming out of the region”. Contributors included Horn of Africa societies who have been affected by migration, conflict, governance and development related issues. A similar facility is expected for the other Trust Fund windows.
[4] https://www.soas.ac.uk/ref-hornresearch/

Key Points

ED/DFID’s ability to secure change relies heavily on other member states sharing the pressure on the Commission for change and Commission openness to ED/DFID ideas. This is demonstrated starkly in the difference in achievement between the results and beneficiary engagement outputs.

Summary of responses to issues raised in previous annual reviews (where relevant)

Internal Audit found that “Feedback from the European Commission in Brussels concluded that the UK representatives (ED DFID staff) at the EDF and DCI meetings challenged decisions and instigated debate about topics, showing the UK to be a very active member state in the forum.” ED have built strong links with posts to inform positions on EU programming.

While the SNE in the Evaluation Unit has been highly valued and we can expect this to have an impact on Commission evauation processes, bilateral engagement with the Unit remains problematic.

The SNEs in the Results Unit have been instrumental in securing excellent outcomes on the development of the results framework and embedding a new culture in the Commission, including future work to capture ongoing project data and results reporting as part of the EuropeAid Annual reporting procedure.

Specific bilateral work on beneficiary engagement was not possible, however, the MDR assessment noted “DEVCO programmes have a strong history of partnering with governments, civil society and local government” as direct beneficiaries of EU funding and “EU website Cap4Dev provides a multimedia knowledge sharing platform on a wide range of development issues. It enables interaction in public groups and allows access to closed collaboration spaces. A personal profile facilitates community building and exchange among peers” which provide avenues for other beneficiaries to express views to the Commission.

Recommendations

Management Committees:
ED should develop a refreshed priorities paper based on the revised ED Reform Agenda as a basis for pressing for improved programming. ED should also engage with like minded to secure support for these priorities.

Evaluation:
The new ED Reform Programme will focus on working with the Commission on sharing experience on creating a learning organisation. This will include the use and dissemination of evidence. ED should continue to press other MS to put pressure on the Commission eg. reflection of lessons learned in programmes coming to the management committees.

Results:
A new SNE will started in January 2017. Her focus for 2017 will be a revision of the EU Results Framework to bring it in line with the SDGs as well as the European Consensus. This revision is an opportunity to integrate additional indicators on women’s empowerment and migration into the framework; as well as lobby for further disaggregation of reporting (by sex, age and other socio-economic groups) in line with the “leave no one behind” agenda. DG IDC is likely to pilot results reporting from on-going projects and programmes in the first half of 2017. This initiative will be strongly supported with a view to make results information more relevant for management decisions.

Gender:
The information from the GAP reporting will be drawn into an overarching report by mid-February and published as a Commission Staff Working Document by the end of April. This first year of reporting is important as it will set a baseline, highlighting gaps in information and capacity that can be addressed for the next round, as well as any issues with the indicators or the reporting process itself. Our key recommendation for next year is ensuring there is a clear plan in place to follow up the published report in April 2017, including what will be done to address identified gaps, improve capacity and improve the quality of the reporting. ED will continue to press that DEVCO and the EEAS are institutionally set up to deliver on this agenda.

Output Title	Ensuring the EU makes appropriate use of the range of instruments available including the development of new instruments
Output number per LF		3	Output Score	A
Risk:		Minor	Impact weighting (%):	33%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
EU budget support and state building contracts applied in appropriate circumstances and conditions respected before payments made	March 2016: Technical experts meeting reassures DFID on approach and use of budget support	ED attended the technical experts meeting in Brussels in May 2016 on the ‘results of the joint evaluations of Budget Support to Sierra Leone and Burkina Faso: lessons learned and recommendations for the future’. The Sierra Leone report was part funded by DFID covering a total of €886m in budget support. / Through a mapping exercise, ED has built a definitive picture of EU support in DFID focus and non-focus countries and this includes setting out those countries that receive budget support as part of EU support. / In May ED met with DevCo team that deals with budget support and stressed the need for results to respond to increased scrutiny on budget support from capitals. DevCo confirmed this would be reflected in the 2016 report, for publication in early 2017.
EU programming includes an appropriate use of a performance mechanism	July 2016: Commission present revised proposals	ED appointed an SRO to manage UK contribution to the EU Emergency Trust Fund. The aim was to ensure that if a mechanism was to be developed, it adhered to best practice, available evidence and was not simply a reward for the predictable. Addressing the root causes of migration absorbed the energies and finance of the EDF this year. ED continued to keep the performance based mechanism on the agenda of Brussels Committees[5] but without strong support from other member states, or a renewed interest from the Commission no mechanism has been developed or is likely to be in the foreseen future.
EU Trust Funds used to add value and meet accountability and management best practice.	September 2016: ED stocktake (governance, approval process, quality of projects) of EU trust funds	An ED stocktake on Trust Fund programmes was undertaken in October 2016. The stocktake clarified UK objectives for the Fund and ensured cross-DFID and cross-HMG coordination on the future ‘pipeline’ of projects and engagement with the Commission and EEAS. This built on prior engagement on the Fund and its projects (early-mid 2016) in which the UK was able to influence partners to press for a more evidence-based approach and ensure key concerns were addressed. While the ED-led approach has been increasingly effective, engagement on project development at country level requires further work in some instances (as well as pressing the EU to ensure its delegations engage member states at a sufficiently early stage).
Joint programming guidance supports added value for EU programming at country level	September 2016: ED June stocktake (value added, transaction costs) on number of joint programming initiatives joined	In May Council Conclusions were negotiated on pushing further on joint programming and on EU support to Afghanistan which contains references to joint programming. ED provided advice which enabled negotiators to maintain UK red lines. / ED continued to offer support to country offices where needed eg. Ethiopia. / ED was interviewed and hosted calls with DFID country offices for the independent evaluation team. Report issued in November largely reflecting UK views. / Stocktake confirmed DFID country offices continue to engage with joint programming. UK remains in the top group.
[5] ACP WG agendas and read outs

Key Points

ED’s engagement on the performance based mechanism and joint programming outputs were largely reactive in meetings in Brussels.

The main ED focus has been on the EU Emergency Trust Fund for Africa. ED’s overall objective is to ensure effective EU spend in line with DFID and cross HMG objectives on migration and development. The UK successfully pressed for  a more evidence-based and strategic approach across the three geographical ‘windows’ of the Trust Fund. In early-mid 2016, the UK worked with EU partners to agree the first projects under the three ‘windows’, working successfully to influence proposals with problematic aspects, including through extensive bilateral work with the Commission and member states and the secondment of UK experts into key EU teams. The October stocktake ensured a more coherent approach to the latest project ‘pipelines’ and ensured that the EU has developed a more strategic approach to the Trust Fund in line with the approach proposed by the UK.

Summary of responses to issues raised in previous annual reviews (where relevant)

The EU remains the only significant donor to use budget support. Alhough DFID has phased out the use of this instrument since the Delivery Plan was drafted, ED has maintained links with the relevant DEVCO Unit to ensure we can be confident that it is used appropriately.

The performance based mechanism work stalled and although ED tried to advance this the lack of other member state support has seen this lapse.

ED has maintained a very close relationship with the Commission on Trust Funds, especially for the Horn of Africa window.

ED has continued to voice concerns about joint programming, supported by other member states. The Council Conclusions in May respected UK red lines.

Recommendations

Budget Support:
ED should continue to ensure appropriateness of this instrment when considering programmes in management committees.

Performance based mechanism:
Unless other member states raise this ED will not pursue further.

Trust Funds:
ED will continue to develop and implement the ED-led cross-Whitehall engagement strategy, including meetings with key Commission and EEAS leads focused on the future ‘pipeline’ (January-February 2016) ahead of the Valletta Senior Officials’ meeting (8-9 February) and the next Strategic Board and possible future Operating Committees (May-June 2017). We will continue to influence the Commission/EEAS approach on a more strategic approach, including evidence-based project development and monitoring and a more coherent regional approach under the three geographical windows. We will ensure that the Commission / EEAS focus under the EU’s new Partnership Framework does not focus unduly on a limited set of countries, and that the Trust Fund allows for a more comprehensive and coherent series of engagements with a wider range of key countries of transit and origin on both the West / Northwest African and Horn of Africa routes.

Joint programming:
ED will continue to ensure UK red lines are maintained and provide guidance to country offices when needed.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The MDR for 2016 rated the EDF as good on organisational strengths noting:
The Commission is taking a number of actions to improve efficiency. Since the 2013 MAR update, the EU has made good progress on transparency, and taken important steps to improve reporting of results and gender equality. While there has been progress on getting the right staff to the right places, this remains an area for improvement.

It is also committed to transparency, as a member of IATI. Steps to improve the efficiency of programme processes and improvements in risk management are welcome, but more evidence of the impact of these measures would make it clearer where more work needs to be done.

The Commission have a number of processes in place to drive down costs eg. the strong use of competitive procedures, limiting the remuneration of the implementing partner to maximum 5% of the final contribution.

VfM performance compared to the original VfM proposition in the business case

As there is no business case for EDF10, we have continued to assess this by comparing the EC’s forecasted spend profile with actual spend. This is the second year under the new Commission
forecasting process which uses a more sophisticated risk methodology in assessing the Commission’s financial needs. The forecasting method has allowed the Commission to budget for additional commitments eg. from the EU Trust Fund while maintaining the ceilings for Member State contributions stable for 2016 and 2017. The Commission expects further smoothing of the ceiling from 2018.

The UK continues to press the Commission to maintain improved forecasting and low levels of cash balances to ensure cash is not held unused for long periods of time.

Assessment of whether the programme continues to represent value for money

The MDR 2016 rated the EDF as very good on the match with UK priorities index noting:

The EU is a key development partner with a significant role in meeting UK and international objectives through its neutrality, influence and convening power. The EU works well in fragile and conflict affected states and targets programmes at those most in need.

Quality of financial management

The European Court of Auditors is the EU Institution which carries out the audit of EU finances. As the EU's external auditor it contributes to improving EU financial management. The EDF’s accounts are audited every year by the European Court of Auditors. The latest European Court of Auditors Annual Report on the Financial Activities of the EDF in 2015 (published in November 2016) concludes that EDF accounts for 2014 present fairly, in all material respects, the financial position of the EDF and are in accordance with the provisions of the Financial Regulation and accounting rules. Whilst the Court did not find any material errors for the reliability of the accounts, it notes an RER of 3.8% (above 2% EU target) and has made recommendations to the Commission to address the accuracy of the data used for the preparation of the annual accounts.

The MDR 2016 noted there is evidence that there are systems and policies in place to tackle fraud and corruption and some evidence that the Commission has taken action to close down programmes where misuse of funds has been detected. It also notes that the results of OLAF investigations, the recommendations provided, as well as the measures taken, are subject to the EU legal confidentiality rules which frustrates our ability to monitor the outcome of fraud and corruption investigations.

The UK will continue to press for improved financial management systems.

Date of last narrative financial report	July 2016
Date of last audited annual statement	November 2016

E: RISK (½ page)

Overall risk rating: Minor
No elements are currently rated as high risk. Risk will continue to be monitored on an on-going basis and will be formally reviewed as part of each annual review process.

Overview of programme risk
Risk has been broken into two sources: UK and EU.

UK level risks:
- The uncertainty of an EU referendum reduces DFID’s influence over the Commission (medium)
- Ministerial de-prioritisation of DFID engagement with the Commission (low)
- ED fails to secure engagement with DFID country offices and FCO posts on EDF programming (medium)
- Limited ED technical expertise (medium)

The Referendum result in June 2016 altered the UK’s relationship with the EU and potentially the level of our influence over the EU and on EDF programming. In the short term ED has continued to engage, recognising that in some areas our influence may reduce over time. Ministers continue to attend Development Councils in Brussels and to engage with senior Commission officials and member states. DFID development expertise is still valued and sought by the Commission and engagement with like minded colleagues has been strengthened. ED has implemented a country level engagement strategy which has helped link in country offices on post referendum EU issues. ED will continue to source external DFID expertise eg. gender, evaluation where needed.

EU level risks:
- Member states delay ratification of EDF 11 (low)
- Commission programming not in accordance with new the Implementing Regulations (low)
- Limited commitment and support for reform priorities by new MEPs and Commissioners (medium)
- Limited commitment and support for reform priorities at EU senior/mid-management levels (medium)
- Limited technical expertise both at Mission/Brussels levels leading to poorly designed or poorly implemented instruments (medium)

EDF 11 was ratified in March 2015 and no longer poses a risk. EU programme documentation continues to improve notably through a revised format for trust fund programmes and a significant improvement in results reporting and logframe completion. The UK has continued to gain support for UK priorities, particularly on gender and migration through continued close engagement with counterparts.

Outstanding actions from risk assessment

None but there will need to be a continued assessment of the risks as the UK’s exit from Europe progresses.

F: COMMERCIAL CONSIDERATIONS (½ page)

UK does not have direct control over EU procurement as set out in the Practical Guide to Contract Procedures for EU External Actions.

There are a number of processes in the delivery of EU aid which are used to ensure value for money. There are guidelines on how the EU should work with its partners and how the best implementation modalities should be chosen. By choosing the most appropriate aid delivery method for each programme and/or action the EU endeavours to enhance aid effectiveness and to secure value for money.

Performance of the partnership

The EU has a wide ranging global reach, political partnership and influence and convening power. Its sheer size and regional coverage make the EU a key player in development and the EU continues to be well placed to make a significant contribution to the 2030 agenda, particularly if it takes full advantage of its coordinating role, the breadth of its expertise, influence and range of tools (trade and political) across the Sustainable Development Goals (SDGs) framework.

The EU plays a critical role in delivering at scale and is aligned with DFID in key policy areas, e.g. girls and women, economic development, peace and security. The EU also delivers assistance in places important to the UK but where DFID has no offices (e.g. Overseas Countries and Territories) and where DFID has no bilateral programme (e.g. francophone Africa).

Asset monitoring and control

The UK does not have any assets related to this programme. Any EDF assets are owned by the European Union which has its own asset monitoring and control procedures.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The EU partnership with ACP states is governed by the Cotonou Agreement. This covers a 20-year period from 2000 to 2020, and is designed to establish a comprehensive partnership with ACP states under three pillars: development cooperation, political cooperation and economic and trade cooperation. The fundamental principles of the Cotonou Agreement include equality of partners, global participation (states and non-state actors), dialogue and regionalisation. The Cotonou Agreement has been revised twice to increase the effectiveness of the ACP-EU partnership; the most recent revision took place in 2010. This recognized the role of national parliaments, local authorities, civil society and the private sector – allowing for more actors to be included to promote a broader and more inclusive partnership with ACP partners. Action has begun on a successor Agreement from 2021. The UK will continue to engage to shape this, given that the EU could remain an important development partner in the future.

The EU’s development cooperation is governed by the principle that countries own their own development. Its country-level development programmes, outlined in the national indicative programmes, are based on each country’s own development programmes. In addition, Article 8 of the Cotonou Partnership Agreements provides the framework for regular and substantive political dialogue covering a broad range of topics, for example respect for human rights, democratic principles, the rule of law and good governance. If Article 8 discussions breakdown, the Commission can consider sanctions under Article 96 (though this has rarely happened).

EU budget support payments are underpinned with a number of generic and country specific conditions that have to be met before payments can be disbursed.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There have been two significant reviews published during 2016.
The MDR 2016 assessed the EDF as a very good match against UK priorities and good on organisational strengths. It was drawn up with full Commission opportunity to comment and supply evidence which was then used to draw up a detailed assessment. The findings will feed into an ED reform programme.
The IAD Assurance Review supported the revised approach in the current delivery plan and made recommendations for the next plan to be drawn up in 2017.
The next Commission review of the EDF will take place during 2017 and will represent an opportunity to make sure EDF 11 is on target to spend resources, reallocate funds and consider whether instruments remain fit for purpose.
Monitoring progress throughout the review period

Europe Department regularly engages with the EDF by scrutinising programmes, actively participating in management committees in Brussels and on each of the outcome indicators listed in the logframe. The UK has a programme of seconded national experts in the EU. We also are active in improving the Commission’s own evaluation processes; as it is inefficient for us to duplicate effort by conducting our own evaluations of EU spend. Country offices and posts have a role to play through engagement at country level with EU programmes.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process