Title: Ghana Revenue Reform Programme
Programme Value £ (full life): £8,139,997		Review date: June 2020
Programme Code: GB-1-204918	AMP start date: March 2015	AMP end date: December 2020

Summary of Programme Performance
Year	2016	2017	2018	2019	2020
Overall Output Score	A	A	A	A	A
Risk Rating	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204918
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-1-204918

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The UK is providing £8.1 million for the Ghana Revenue Reform Programme (GRRP). The programme was initially due to run from March 2015 to December 2019. It was subsequently extended to June 2020 to allow for a strategic phasing into the next stage of UK support for tax reforms in Ghana, then to December 2020 in response to the COVID pandemic.

The programme supports a combination of tax policy and administrative reforms to increase domestic revenues and address immediate macro-economic issues.

The intended impact of the programme is to improve the fiscal position of the Government of Ghana (GoG) through increased domestic revenues. Its intended outcome is to improve domestic revenue generation through closing the current tax gap. The project is designed to achieve the following outputs:

1. Increased voluntary compliance
2. Improved GRA-wide information systems for identifying and monitoring taxpayers
3. Organisational improvements and capacity building
4. Strengthened tax policy and forecasting
5. Improved systems and accountability of non-tax revenues (NTR)

In March 2020 the programme pivoted to provide urgent support to the Government of Ghana’s response to COVID, supporting IT changes to allow taxpayers to file and pay online and the provision of related communications and guidance for taxpayers. The programme also worked with the Ministry of Finance to support analysis of fiscal options in light of COVID.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

The programme has met most of its targets for 2019-20, contributing to reforms in both the tax and non-tax revenue streams which will show dividends in the medium term.

On improving revenue collection, the programme supported the establishment of a High Net Worth Unit, which now has an organisational structure and medium-term plan in place and has successfully progressed some major cases and collected about GHC53m in revenue. The programme also supported the prosecutions policy, which is being embedded in the revenue authority’s operations and resulted in 20 cases being referred for prosecution in the year of review. Good progress has been made on the implementation of Automatic Exchange of Information (AEOI), which will support international exchanges of financial information about Ghanaian nationals for tax purposes and the GRA now has a data strategy in place to improve its data capability and enhance tax compliance.

On non-tax revenue, with support from GRRP the Non-Tax Policy Unit in the Ministry of Finance also instituted a number of reforms to increase revenues and improve fiscal space, including: the Guarantees Advance Payment for mining companies with government interest to ensure government dividends are accurately paid; 15% of profits from limited liability state owned enterprises being paid annually into the consolidated fund; and usage of 37% of internally generated funds by tertiary institutions for the payment of utility bills, which were originally being paid by the government.

The Ghana Audit Service work on exemption regimes (customs warehouses and free zones) is yielding reforms and improving reporting, both leading to increased revenues with about GHC65m (approx. £9.3m) additional tax assessments raised from their quality assurance work.

The civil society component has also generated reforms and increased citizens’ engagement in the revenue process. About 4 million people have been reached with tax information and the revenue authority is now implementing a revised form of the informants’ award to encourage reporting on tax fraud and evasion.

The only output that has not achieved its targets for this year is the one on the GRA organisational reforms (output 3), which are critical for the overall success of the revenue reform process in Ghana. The delays have been partly as a result of changes to the GRA top management team, partly due to the challenge of restructuring an organisation like the GRA, and progress has also been impacted by COVID. The programme leads are engaging with the GRA senior management team on this, and the programme will prioritise bringing output 3 back on track by the end of 2020.

Key recommendations for the next 6 months

- The programme should prioritise work on the 2020 Compliance Improvement Plan to support GRA compliance efforts and tax recovery strategies after COVID.
- The programme should support the GRA’s completion of an action plan for the GRA rationalisation project and support full implementation of the transformation unit to progress the GRA organisational reforms.
- The programme team should work with the GRA to draw up and implement a strategic plan for the newly-developed GRA data strategy, improving GRA’s existing data capability to enhance tax compliance.
- The programme team should work with the GRA to progress with the prosecution policy and strengthen national tax compliance
- The tax Development Partners (DP) group should engage the Ministry of Finance and senior Government officials to progress the tax exemption bill in Parliament. Realistically, the Bill is unlikely to pass before the election: the focus in the short term should be on ensuring that the Bill is a robust as possible and that necessary supporting analysis is completed, with support from Institute of Fiscal Studies UK (IFS) and others.
- HMRC should continue to help the GRA progress towards the International Transparency Standard to qualify Ghana as an International Financial Centre
- The Non-Tax Policy Unit’s work on revenue hearings is proving useful for improving the government’s fiscal space and expenditure efficiency and it should be sustained within the Unit’s annual activities.
- The programme should seek and engage with emerging opportunities within the civil society strand of work (ACEP) in identifying fiscal fraud through the GRA informants award scheme.
- ACEP should increase focus on customs activity to help highlight and address revenue leakage and identify areas for improvement that can be shared with GRA.
- The programme should consider supporting the newly created Governance and Ethics Unit with its Strategic and Operational Plans.
- The programme team should engage GRA to support development of an action plan for the full roll-out of Smart Office which is endorsed by GRA senior management.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

The programme’s theory of change (ToC) is based on strengthening tax policy, tax administration and taxpayer services to increase revenue generation and improve the fiscal position of the government of Ghana. The inputs in the form of non-budget financial aid and technical assistance support are designed to strengthen the tax policy and tax administration environments and improve governance and management of the GRA and non-tax revenue reform units.

The ToC was revised in 2018 to reflect added support to civil society organisations and revisions to key areas of project focus. The addition of support for the Ghana Audit Service is yielding a lot of benefits and providing additional impetus for catalytic revenue reforms. Examples include their work on the exemption regimes (warehousing regime, free zones, etc.) which highlighted institutionalised weaknesses that led to continued revenue loss, and which have already led to system changes and brought in additional revenue. Furthermore, the addition of the Civil Society work has significantly engaged citizens in the reform process, adding an additional lever for positive reforms.

Recommendation: As this programme is coming to an end in December 2020, DFID’s future support to domestic revenue mobilisation should consider further shifts towards the Tax for Development approach, supporting catalytic reforms that are both firmly aligned to GoG priorities and also increase accountability to citizens. The second phase should link revenues to spending on public services and engage with civil society actors to strengthen the fiscal contract. The goal will be a demonstrable increase in transparency and fairness in the tax system, including through the reduction of exemptions and more consistent taxation of rich (and influential) individuals.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The outcome of the programme is ”improved revenue generation (non-oil)”. The programme impact is ”improved fiscal position for the government of Ghana”. The tax revenue collected in 2019 was GHS 42.355 billion against a logframe target of GHS 45.2 billion. This shows a 12.4% increase compared to last year’s tax revenue, which is below the 20% logframe target for tax revenue growth. However, in the past year, the programme supported a 17% increase in domestic tax collections, which is a 9% real increase in revenues after adjusting for inflation. The increase is also larger than the real GDP growth for the year, showing improvement in domestic tax efforts, and early signs are that tax revenue performance has held up even during COVID, at the end of May 2020.

Impact Indicators	2019 Target	Progress
Tax to GDP (%) / Tax revenue (non-oil, excludes Non-Tax Revenue)	13.7% / GHS 45.2 billion	12.2% / GHS 42.3 billion
Outcome Indicators
Revenue collected from target work stream: / HNWI: / Prosecutions: / Automatic Exchange of Information (AEOI): / Revenue collected from non-tax revenues.	GHS 120m assessed / GHS0 / GHS0 / GHS 6.94b	GHS 53m assessed as at Feb 2020 / GHS 0 / GHS 0 / GHS 7.567m (9% YoY increase) / PAYE – GHC178m
Voluntary compliance – rate of on-time filing amongst identified tax payers, including HNWI	20% increase in on-time filing by Identified taxpayers	Not fully measured as 2020 filing date has been extended due to COVID.
[note] This was not part of the logframe target for. It is as a result to the programme support to the PAYE unit in the previous review period.

The reason the targeted 13.7% tax to GDP ratio was not achieved is due to the poor performance in customs revenues, which were outside the remit of GRRP. Customs revenue reduced by 12% from 2018 and continues to under-preform. There are a number of reasons for this. In 2019 the government reduced the benchmark prices of imports by 50%: this was expected to bring in revenue by increasing trade flows but led to a reduction in customs revenues. Analysis by MoF and GRA showed also that there was a drop in valuations for goods moving into the country. This unexplained drop combined with the reduced benchmark figures led to a failure to achieve the customs revenue growth target for the year.

Consequently, despite Ghana improving its tax collections with UK support, it has not achieved its annual revenue targets. The fall in customs receipts is a matter of concern. It results from both policy decisions and administrative failings, and action on both will be needed to address the gaps and take realistic steps to move Ghana beyond aid.

Recommendations: The programme will take a multi-strand approach to tackling this concern, including:
1. Supporting the Tax Policy Unit to finalise a strategic plan that will show the steps needed to increase Ghana’s tax to GDP and the policy approach that will be taken. This and other work to strengthen the tax policy unit’s analytical capacity will improve policy decision-making.
2. At the GRA, support on data, improving GRA’s data gathering and analysis alongside similar support for TPU.
3. Working with GRA to develop its Compliance Improvement Plan.
4. Working collaboratively with other DPs towards a strategic engagement with the government of Ghana and on key capacity building and oversight activity in the area of customs to ensure that our work is aligned and address the structural problems in Ghana’s revenue efforts.
5. Supporting ACEP’s focus on customs to identify shortfalls and inappropriate behaviour and to identify areas for improvement that can be shared with GRA.
Logframe targets will be revised in light of the extension to December 2020 and to reflect the economic shock of COVID.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The programme is entering its final six months. It has consistently scored an A. Looking ahead, for Ghana to move beyond aid, fund its development objectives and increase public accountability it is necessary to collect more revenue in both absolute terms and as a percentage of GDP. This need has become even more pressing in response to the economic challenge posed by the COVID pandemic.

The Government of Ghana has shown its commitment in making significant changes at GRA and investing in the capacity of its Ministry of Finance. Ghana is of strategic importance to the UK and the working relationship between the UK and GoG in this area is strong. It has produced good outcomes in recent years and there is potential to make significant progress if support continues.

The programme identified structural inefficiencies within the GRA leading to consistent low effort and worked with the new management team to begin to address those. A number of opportunities for increasing tax collection have been identified and are being pursued by GRA (for example enforcing tax compliance by high net worth individuals).

Some of the foundational building blocks that are needed to support transformational changes are now in place, and others are planned to complete by the end of December.

DFID will work closely with GoG officials in this period to support achievement of the key objectives by the end of the programme.

An election will also take place in December and this will limit the political will to make significant new decisions in the next few months. It is recommended that senior HMG officials engage early with the new government to ensure that there continues to be political will to make the decisions necessary to increase tax for development. This work will feed into forward thinking on the next phase of Domestic Revenue Mobilisation programme.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Activities aimed at directly increasing revenue collection/voluntary compliance
Output number: 1			Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 GRA prosecutes cases	Prosecution policy and training manual adhered to / 20 cases referred for prosecution by at least 4 offices	Partially Met: Framework for implementation was agreed and an expert was engaged to support implementation. The process is currently ongoing. / Met: 22 cases were referred.
1.2 Tax Gap Analysis used to identify focus areas	Technical Assistance knowledge transferred to team / Combined report on indirect and direct tax gap presented to management and copies printed and distributed	Met: The programme collaborated with the World Bank to support the team to design methodologies and identify data sources for calculating both the direct and indirect tax gap. / Partially met: Report on Indirect Tax completed
1.3 GRA able to identify High Net Worth Individuals (HNWI) and tax e-commerce	Three-year plan and vision agreed and approved by Commissioner DTRD / Quality assurance process in place to ensure operational and procedural manuals followed / GHS 5m of revenue collected	Met: A 3 Year Strategic Plan (2020-2022) developed and approved by the commissioner DTRD. / Met: Operational and Procedural manual followed by HNWU as part of normal operations. / Met: Ghs5,979,763.19 collected within the review period.
1.4 National Tax Compliance Campaign	Evidence of Public Consultation and Feedback collated (TADAT B Standard) / Website launched with informative and user-friendly design	Met: The updated GRA website has an interactive to receive customer feedback and about 1000 customers have so far provided feedback. / Partially Met: Work on website is about 50% complete.

1.5 Improved efficiency of Debt Management	All offices adhere to procedures in debt management manual / 30% reduction in long-term (9 months +) outstanding debt	Met: Offices conform to format for reporting prescribed in the manual and DCME oversight ensures this is done. / Met: Rate of GRA debt recovery for 2019 was 31.21%.
1.6 Automatic Exchange of Tax information with target countries	Security Action Plan followed / AEOI fully implemented / OECD Assessment passed	Met: Security Action Plan followed. Questionnaire assessment completed with positive results. In-country assessment did not happen due to COVID-19 restrictions. / Not Met: Assessment of information security measures to enable Ghana to receive reciprocal information back from CRS partners not possible due to COVID restrictions. / Not Met: OECD in-country assessment did not take place due to COVID-19 restrictions.
1.7 Africa Centre for Energy Policy	80% of whistle-blower cases submitted to GRA and Auditor-General for investigations acted upon. / 4,500,000 people reached with tax information of which 40% are women / Engagement strategy on 5 policy briefs, prepared under project, designed and implemented	Met: Percentage of whistle-blower cases acted upon is 100%, with investigation completed for 3 of such cases with recoveries of GHC1.1m made. / Met: 4,480,643 persons reached with tax information (June 12). 38.5% are women / Partially Met: Engagement strategy on Informant Reward Package developed and implemented. Engagement Strategy on GRA reforms developed, awaiting implementation.

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Significant progress was made on this output area, and an A score is appropriate. Major successes include the launch of the GRA prosecution policy which is being embedded in the institution, the development of a strategic plan for targeting the high net worth population and ACEP’s transformative work in engaging citizens to support tax compliance and challenge bad practice, which has led to the GRA institution of the informants’ award scheme. Unmet targets under this output were mainly as a result of the Covid-19 pandemic.

Additional direct revenues generated as a result of activities from this output in 2019 total GHC 21.4m (approx. £3m) against an output spend of GHC 1.94m (£266k). In addition, over 4m Ghanaians were reached with tax information.
Prosecution: The Prosecution Policy was launched in April 2019 and is currently published on the GRA website. The programme supported the GRA with an expert in mapping out the needed processes for effective prosecutions and a comprehensive analysis and recommendations were presented to the Commissioner General. The expert’s follow up actions have been delayed due to COVID-19 pandemic. The number of cases referred in 2019 were 22 of which 4 investigations were completed and passed on for prosecutions: others are in progress. GRA have recently met the Chief Justice, who agreed to set up special tax courts in Accra and Ashanti regions to prioritise cases. The next steps in the next 6 months include engaging the GRA in the implementation of recommendations for the framework for prosecution assessment.

Tax Gap: The Tax Gap Team has completed reports on the tax gap for Customs and Value Added Tax (VAT). The Personal Income Tax gap analysis is currently ongoing and should be completed by December 2020. The World Bank presented an analysis of the corporate tax gap to the new GRA leadership and the results will feed into the GRA’s compliance improvement plan for 2020. Outstanding actions for the end year include completing the PAYE report, updating the VAT and Customs Report and publishing a combined tax gap analysis for the GRA. The aim of establishing a permanent unit to produce yearly updates to the Tax Gap Reports will be reviewed in the light of current structural reorganisation of the Strategy Research, Policy, and Programmes Department.
High Net Worth: The HNWU with support from the programme has developed a 3-year strategic plan towards achieving GRA’s plans of taxing HNW in its 3rd Strategic Plan. The plan among others is to increase the HNW contribution to the domestic tax division from 0.014% in 2019 (pilot phase) to 0.5% in the next 3 years. The programme supported the establishment of the unit its pilot phase engagement. The Unit collected almost 6m GHC in 2019 and continues to make progress in 2020. GRA recently won a high court case against a celebrity pastor who had not field tax returns or made any payments for some years.
[note] The Unit focused on assessments during the pilot phase and were able to account for actual revenue collection of about GHS4.4 million against the total DTRD collection of GHS31.9 billion The expectation under the plan is to strengthen the debt management function of the Office to scale up actual revenue collection from assessments raised.
[note] 0.5% is an estimation based on international scans and expected performance. It will be adjusted to reflect the results of the baseline research on the HNWI population currently underway by GRA-RPM.

The main activity till the end of programme will include supporting the implementation of the unit’s 2020 operational plan, with a focus on their data capability, and support with the update of their procedure manual to ensure consistent good practice on all cases.

National Tax Campaign: The national tax campaign sought to strengthen GRA’s interaction with taxpayers to improve tac compliance. The main activity within this indicator for the year has been the support to the GRA website. Since the last review, the HMRC has provided further training to the website team. HMRC and GRA worked collaboratively on content production. In addition to this, the programme secured an MOU with the UK government communications service to support with strategic internal and external communications based on HMRC’s recommendation from last year. The main strategic goal for the end programme will be supporting the GRA develop an effective internal communications strategy.

Debt Management: The programme has supported the development of the training manual for debt management which incorporated latest revisions to the tax laws, specifically the Revenue Administration Act 2016, Act 915. The programme also supported the training of debt management officials in the use of the manual. The rate of debt recovery for 2019 was 31.21% from a programme target of 30%.
Automatic Exchange of Information: To aid in the systematic completion of requirements for Ghana’s full AEOI status, an information security action plan was drawn up. The security plan progressed to the point that the GRA were ready for their OECD Assessment. The opinion of the UK’s security experts on reviewing the completed assessment questionnaire was that the assessment was likely to be successful. However, the OECD team was due to visit at a time that was impacted by the Covid 19 crisis and so could not go ahead. Once restrictions are lifted the assessment will hopefully go ahead leading to a successful conclusion to the plan.

The OECD have however recognised in their progress reports for the G20 that Ghana is now compliant (pending further Peer Review) with the international AEOI standard having successfully sending out information to other jurisdictions participating with the Common Reporting Standard (CRS). The only missing element is the successful assessment of information security measures, which will allow Ghana to receive reciprocal information back from its CRS partners.

ACEP: ACEP submitted 19 whistle-blower cases to the GRA and the Auditor General.
The GRA has finalised investigations for 3 cases from the Greater Accra Region from where it recovered an amount of GHS 1,105,712.83 out of a total tax liability of GHS 1,389,860.04. The GRA expressed difficulty in locating some of the companies. With the support of ACEP, the companies have been located and investigations are continuing. ACEP will engage the GRA throughout the process and highlight opportunities for GRA to pursue prosecution to strengthen tax compliance.

The total number of people reached with tax information through the online platform is
4,480,643 persons as at June 12, 2020. Of this, about 38.51 percent are women.

The engagement strategy for disseminating the policy briefs that have been developed has been designed. Video animations on GRA's Informant reward package have been developed and used for social media campaign. Materials for media engagements to push for reforms at the GRA have been developed. Meetings have been held with a CSO partner as part of preparation for the media engagement. The policy briefs have also been shared with the Ministry of Finance’s Tax Policy.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Additional revenue generated as a result of activities from this output in 2019 totals GHC 21.4m (approx. £3m) against an output spend of GHC 1.94m (£266k). In addition, about 4m Ghanaians were reached with tax information. The output efforts aimed at strengthening equity includes ACEP’s platform for increasing access of tax information to ordinary Ghanaians and the HNW taxes collected which serves as an opportunity for redistribute income to the poor.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The main change to this output is the inclusion of strategic communications support from the UK Government Communications Service to the Tax Campaign indication programme.

Progress on recommendations from the previous AR (if completed),

Recommendation	Actions Taken
The project should work with the GRA to ensure that the prosecution policy manual is distributed and employees trained. In relation to the logframe, the definition of ‘’cases referred to prosecution’’ should be clarified. It should cover only those cases referred by reference to the procedures set out in the new policy manual and those which the GRA itself is prosecuting.	Prosecutions manual was publicly launched in April 2019 and is currently available on the website. / Reporting of cases referred for prosecutions is only based on cases referred based on the policy guidelines. Notwithstanding, all cases reported are from the debt office and task force office.
The pilot assessment of the prosecution training shows that learning outcomes haven’t been satisfactory. The GRRP should ensure that there is a robust and transparent process of trainee selection before any training takes place and that all trainings are being assessed based on the project M&E strategy.	An M&E strategy for the programme is currently in place However there haven’t been new trainings on Prosecutions in the year of review.
DFID should have regular engagement with ACEP, the GAS and the GRA to ensure potential tax evasion cases submitted by ACEP are followed up on by the GAS and the GRA. Otherwise there is the risk of losing the engagement of civil society partners.	DFID facilitated meetings with ACEP, GAS and GRA resulting in reported cases being acted upon.
DFID and HMRC should discuss the staffing arrangements of the HNWU with GRA management. Any further support should be made conditional on the GRA’s commitment of making the unit fully operational.	DFID and HMRC have engaged the GRA on staffing for the HNW unit. This has been considered in the unit’s 3rd strategic plan.

Key recommendations for the next 6 months

- The programme team should work with the GRA in agreeing an action plan for progressing with the prosecution policy, strengthening national tax compliance.
- The programme team will support the High Net Worth unit to implement identified actions (particularly on data) in its newly designed strategic plan.

The programme will engage ACEP with emerging opportunities within the civil society strand of work (ACEP) in identifying fiscal fraud through the GRA informants award scheme.

Output Title	Improved GRA-wide information systems for identifying and monitoring taxpayers
Output number: 2			Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 GRA transitions to digital recordkeeping and information management	All heads of offices complying fully with SmartOffice	Partially met: Training on primary collaboration features (Teams, email) provided to all management and Board. / Videos prepared for next wave of training for top priority workflows. / The following Smart Office + O365 Modules are live, staff have been trained on their use and regularly use them: / Email / Teams / Office productivity tools. / Though the following applications have been deployed, sufficient training has not been undertaken. Thus, these applications are not fully in use: / Workflows (memos, leave request, loan request, vehicle usage). / Portal usage (Prosecutions portal).
2.2 TRIPS implementation	TRIPS rolled out to all taxpayer offices used for GRA wide reporting / Evaluation of Oracle Database completed / Ongoing support to core DTRD system	Met: TRIPS has been rolled out to all taxpayer offices. / Met: Report submitted to CG and Vendor. / Met: Support ongoing based on demand and need communicated by GRA.

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Major successes under this output include:
- The development of the GRA data strategy, which will contribute to a digital transformation in GRA’s activities and the full deployment of TRIPs across GRA offices. The team is also supporting GRA management on the full roll-out of SMART office to improve its effectiveness.
- Supporting the deployment of the domestic tax software (TRIPS) in all tax offices. This strengthens GRA’s overview of revenue performance and operations across the organisation and will enable the use of real-time revenue data for improved risk profiling.
- Identified critical security gaps and flaws in the DTRD software and ensured that GRA and the vendor have an agreed plan to fix issues identified.
- Provided GRA with a framework to objectively assess and select an update or upgrade path for an efficient DTRD software.
- Supported the GRA in the development of its data strategy.
Challenges
The preference of the GRA staff for “manual” (or older, less efficient) processes over newer (electronic) means has delayed the roll out of new systems. In June 2020 GRA announced the formation of a new Policy and Planning, Research and Audit team (Audit Quality Assurance Unit). The Data unit which GRRP is supporting will initially be a part of this team and gradually transition into one of the divisions. There is still a great deal of work to do to deliver strong yields from the proposed data-driven GRA agenda. However, establishing a data science unit is an essential step for the process.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The full deployment of TRIPS across the GRA is improving GRA’s overview of revenue performance and standardising operations across the GRA. This will also be useful in utilising real-time revenue data for improved risking profiling which will be pursued in the next 6 months of the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The programme included a focus on the GRA data strategy as part of supporting GRA’s digital transformation for efficiency. As part of the transformation agenda, a new team is being formed with a focus on Policy and Planning, Research and Audit. The Data team will initially be a part of this team and gradually transitioned into one of the divisions.

Progress on recommendations from the previous AR

The table below describes updates on recommendations from the previous annual review.

Recommendations	Actions taken
Digitisation of files should be driven by a systematic process and start with the development of a strategy agreed and owned by GRA management. This will maximise benefits and ensure the sustainability beyond the GRRP.	The CG has recently endorsed the newly developed Data Strategy for implementation
Senior ownership and follow-up on reforms is critical for success.	The CG has recently endorsed the newly developed Data Strategy and implementation has begun.
It is important for GRA to ensure that they build the capacity to take over the management of TRIPS until a long-term solution is agreed and implemented.	This is ongoing but hampered by contractual issues with the provider.
Usage and utilisation of the of TRIPS by the GRA staff is key. The next logframe milestone should focus on supporting the units to use the system as part of their daily work.	Extensive support has been provided to embed smart office throughout the organisation.

Lessons learned this year and recommendations for the next six months

Key recommendations for the period to the end of December include
- The programme team should engage GRA to develop an action plan for the full roll-out of Smart Office which is endorsed by senior management.
- The programme team should support GRA to develop an action plan for implementing the GRA data strategy and building the GRA data capability to enhance tax compliance.

Output Title	Organisational Improvements and Capacity Building
Output number: 3			Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 Status of organisational efficiency and effectiveness	Target Operational Plan developed for DTRD / MTO and STO merger pilot conducted / Change Management Implementation Plan in place / GRA transformation unit set up and operational	Met. Operational plans developed for DTRD and other units / Partially Met. Project has started: COVID led to some delays but it is in progress for delivery in a phased approach. / Not Met. A change management ToR was developed but paused to allow for the progress with the STO/MTO merger. / Partially Met. Delayed as a result of changes to the structure but management team now appointed.
3.2 Increased capacity to collect revenue from training in areas identified through HMRC needs assessment	80% of employees achieve required pass mark for all assessments administered through SmartOffice / 80% of training Courses delivered against TNA (GRA Strategic Objective 5) / 80% of Trainees fill training evaluation assessments through Smart Office	Partially Met: Training reviews for the AEOI training, study trip to South Africa, training of stakeholders on AEOI, and training on debt management indicated that employees achieved the 80% pass mark. Training reviews on the SMART office platform are yet to take place. / Not Met: Training Needs Assessment not developed. / Not Met: SMART Office not fully rolled out
3.3 Implementation of Internal Governance/Integrity Strategy in GRA	Agree, communicate and monitor new internal Governance Strategy	Partially Met: The programme has influenced the GRA SMT to seriously consider issues of integrity and a new governance and ethics unit has been established.
3.4 Implementation of a compliance management strategy	Compliance improvement Plan for DTRD in place (TADAT B standard)	Not Met: Following preliminary work on the Compliance Improvement Plan, the development and implementation phases have not taken place.
3.5 Capacity of Ghana Audit Service built to conduct revenue audits	Model for monitoring revenue developed and deployed / Full Management reports released by GAS on Warehousing, Customs Valuation and Freezones audits (March 2020)	Met: 2 out of 3 systems developed and deployed. 3rd system in the process of development. / Met: Full Management reports released on the audits

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Progress against some key milestones has been slow, but the work is moving steadily forward, and a B marking is warranted. COVID pressures combined with the inevitable challenges that arise when making significant organisational change have slowed progress, however significant changes have happened including:

GRA have a new organisational structure with fewer direct reportees to the CG, enabling greater focus.

MTO and STO offices have been identified for merger and work is in place to transfer files. The plan is to start in the Tema region in July and Kumasi in the next few months.

The ongoing institutional reforms, including the GRA rationalisation of the Medium and Small tax offices operations and the implementation of a strategic compliance plan for 2020 and beyond will be very critical to improving Ghana’s revenue efforts.

Additional direct revenues generated to the consolidated fund from the Ghana Audit Service audits from this output in 2019 total GHC65m (approx. £9.3m) against an output spend of GHC662,772 (£90,790.68).

Organisational Efficiency and Effectiveness – The Domestic Tax Revenue Division (DTRD) operational objectives and plans have been developed and prioritised for delivery. The rationalisation of the operations of the GRA Domestic Taxes Revenue Division started in January 2020 with an initial completion due date of August 2020 and significant progress has been made across key milestones. However, several challenges including wider changes in the organisational structure and the impact of the lockdown in response to the Covid-19 pandemic has slowed the pace of delivery and the overall project timeline. The project has now been extended to 2021.

Increased capacity to collect revenue from upskilling training from HMRC. Targeted capacity training provided by HMRC in the year include Informants handling, website re-design, managing the national tax campaign and AEOI security training. This is supporting GRA’s capacity to profile and understand taxpayers for revenue collection.

Implementation of an Internal Governance/Integrity Strategy in GRA: The Internal Governance Department has undergone changes following the GRA restructuring process. Between 2017 – 2018 HMRC provided Technical Assistance to the Internal Governance Unit and developed a framework on which the transformation of the Unit could be modelled. Since then the stand-alone Internal Governance Unit has been merged with the Intelligence, Investigations and Money Laundering Units to form the new Ethics and Good Governance Department. The programme will support the unit in its strategy within the next 6 months.

Implementation of a Compliance Management Strategy.
Progress made in the period includes a number of staff being trained in the use of an integrated compliance approach, and some efforts made to access and analyse data for compliance purposes. Notwithstanding this, additional work will be required in developing the framework for effective monitoring of operational compliance and this will be led by the newly-recruited Long-Term Adviser over the next 6 months.

Capacity of Ghana Audit Service built to conduct revenue audits:

The Ghana Audit Service planned to develop and deploy three models for operating the revenue audit division of the service, namely: the Non-Tax Model for Onsite Banking Revenue Review; the Customs Import Valuation Model; and the Revenue Model for Direct Tax Audit. The Non-Tax Model and the Customs Import Evaluation Model were completed and deployed in the course of the year. The Revenue Model for Direct Tax is in progress and yet to be finalised and deployed.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

Additional revenues generated to the consolidated fund from the Ghana Audit Service audits from this output in 2019 totals GHC65m (approx. £9.3m) with GHC 24m already collected (approx. £3.4m) against an output spend of GHC662,772 (£90,790.68). The ongoing institutional reforms, including the GRA rationalisation of the Medium and Small tax offices operations and the implementation of a strategic compliance plan for 2020 and beyond will be very critical to improving Ghana’s revenue efforts.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The programme has included additional support on Human Resources Management in the GRA as part of improving the GRA organisational efficiency. This will strengthen accountability within the GRA to implement the needed reforms.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendation	Action
A key recommendation from last year’s review was to support the GRA to fully operationalise the Third Strategic Plan through the development of annual operational plans for the same period and the team to work with the GRA to set up a steering committee to oversee the implementation of the operational plans.	Operational plans are in place for all the three units. Interim governance and reporting arrangement are in place to support delivery until the Transformation Unit is fully ready to take over delivery oversight
The DFID programme should reflect on our engagement approaches with the GRA management team, and review initiatives that we are supporting to ensure our approaches and activities continue to be strategic and targeted or we risk reducing our effectiveness	DFID is engaging the GRA management team in agreeing on priorities for revenue reforms and ensuring our support is well targeted.

Recommendations
- The programme should prioritise work on the 2020 Compliance Improvement plan to support GRA tax compliance efforts and support fiscal recovery from Covid-19.
- The Implementation plan for the DRTD rationalisation should be reviewed and provided with the required support for completing agreed actions by December 2020.

Output Title	Strengthened Tax Policy and Forecasting
Output number: 4			Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Status of Tax Policy	Exemption Bill laid in Parliament / TPU independently produce 2020 revenue forecast and perform challenge function with GRA / TPU undertake distributional and revenue effects of 2020 tax reforms / TPU to cost tax policy reforms for the 2021 budget and 2020 mid-year budget review	Met: Bill currently with Parliament but yet to be passed / Met: TPU produced an independent medium-term revenue forecast (2020-2022) which was adopted after a forecasting committee workshop with the Ghana Revenue Authority. The forecast produced formed the basis for the 2020 revenue estimates in the 2020 budget statement. The Unit also produced a revised forecast of the 2020 revenue estimates using actual Jan-April tax revenue data. / Met: This activity was undertaken and served as input for decision making in formulating policy measures in the 2020 budget. / Additionally the Unit estimated the revenue effects of proposed tax policy measures to mitigate the impact of Covid-19 on tax revenue. / Met: The Unit produced policy costings of proposed 2020 tax revenues which served as inputs for decision making in the formulation of the 2020 revenue measures. / The Unit also produced policy costing estimates for proposed tax policy measures to mitigate the impact of Covid-19. / The 2021 Budget will be prepared in 2021 because 2020 is an election year. However, the revenue database which is the basis for analysis is being updated with monthly revenue data in preparation for the 2020 mid-year budget.
4.2 Status of Double Tax Agreement (DTA) Negotiations	Report on Cost Benefit Analysis of Ghana’s DTA	Partially met: DFID helped the unit procure a consultant to undertake this exercise. An inception meeting was held with PwC and a data request has been sent to GRA. Data challenges and COVID mean that the consultant is yet to submit a report: a draft is expected by the end of 2020

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The major success of this output has been evidenced mainly in the increased efficiency and effectiveness of the Tax Policy Unit and their increased contribution to the national budget preparatory processes, and all the key objectives in this area were met or exceeded. Revenue forecasts were originally being prepared by the GRA with limited challenge function from the Ministry due to limited capability. Currently the unit has capacity to independently forecast revenues and model the welfare and revenue impacts of any potential tax policy: they have fed actively into Government thinking on the economic response to COVID.

Revenue Forecasting and Analysis Capacity
The Tax Policy Unit now has independent capacity to estimate and forecast annual revenues and tax exemptions for the national budget. The TPU, with the support of IFS UK, now has a model for analysing the effect of tax policies for budgetary decisions. This is being actively utilised for the national budget preparations (used for 2020 revenue forecasting) and has been very useful in the government tax policy response on COVID 19.

Double Taxation Agreements
The Tax Policy Unit through the programme support procured a consultant to conduct a cost benefit analysis of Ghana’s Double Taxation agreements to feed into the national approach in granting double taxation agreements. The completion of that assessment has been delayed due to the COVID situation.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The output’s value for money is evidenced mainly in the increased efficiency and effectiveness of the Unit’s operations and their increased contribution to the national budget preparatory processes. Revenue forecasts were originally being prepared by the GRA with limited challenge function from the Ministry due to limited capability. Currently the unit has capacity to independently forecast revenues and model the welfare and revenue impacts of any potential tax policy.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There were no major changes to the output in the year. A planned change to the output till the end of 2020 is to support the tax policy unit in developing its medium-term strategic plann to improve the capacity and efficiency of the unit.

Progress on recommendations from the previous

Recommendation	Action
Better coordination among donors in relation to specific areas of tax policy.	DFID Ghana is leading the tax donor relationship currently and have drafted a framework for a more strategic engagement among donors and with the government.
The programme should work with the MoF and GRA’s senior leadership and other development partners to consider how to best influence the GoG in relation to Tax exemptions.	The programme and other development partners (IMF, GIZ) supported the process for preparing the exemptions bill which is currently before Parliament.

Recommendations
- The tax DP group should engage the Ministry of Finance and senior government in progressing the tax exemption bill in Parliament to enhance the revenue reform efforts underway. Realistically, the Bill is unlikely to pass before the election: the focus on the short term should be on ensuring that the Bill is as robust as possible and that necessary analysis is completed, with support from IFS and others. The IMF is also focused on ensuring the Bill is finalised and passed by Parliament.
- The programme should support the Ministry’s plans to develop a medium-term strategy for revenue policy (tax and non-tax revenue): this policy will inform decision-making and set out steps for Ghana to increase DRM and move beyond aid.

Output Title	Improved Systems and Accountability of Non-Tax Revenue (NTR)
Output number: 5			Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
5.1 % of MDAs reporting and % complying with capping policy on retained income	100%/90%	Met: All MDAS complying with capping policy.
5.2 Status of Systems for Non-Tax Revenue Collection	Revenue Hearings held for all Internally Generated Funds (IGFs) generating MDAs (100%)	Met: This is a new activity supported by the programme to strengthen revenue transparency and improve resource allocation. This activity led to the government decision of engaging tertiary institutions to utilise 37% of their IGFs for utilities to free up fiscal space within the national budget.
5.3 Status of MDAs/SOEs Accountability in non-tax revenues and dividends	All 2018 audit recommendations implemented / Banking arrangement audit completed	Partially met: 70% progress on implementation of audit recommendations. / Partially met: 80% progress on banking arrangement Audit
5.4 Status of NTRU Capacity	100% of TNA plan for NTRU implemented	Met: Planned capacity for the unit provided.

Briefly describe the output’s activities, and provide supporting narrative for the score. [max 1/2 page]

Major successes achieved under this output include the implementation of the Guarantees Advance Payment for mining companies with government interest to ensure government dividends are accurately paid; 15% of profits from limited liability state owned enterprises paid annually into the consolidated fund and usage of 37% of internally generated funds by tertiary institutions for the payment of utility bills, which was originally being paid by the central government. These and other key changes have increased revenues and improved the Government’s fiscal space.

The programme supported the processes for these reforms in 2 activity areas.
1. Undertaking a dividend audit in State Owned Enterprises and companies with government participating interest; and
2. Instituting the Revenue Hearings for MDAs generating non-tax revenues.
The revenue hearings in 2020 led to the Government decision to require tertiary institutions to use 37% of their internally generated funds for utilities, freeing up fiscal space within the national budget. The hearings also brought improvements in the Non-Tax Revenue Unit’sunderstanding of core principles of revenue forecasting including trend analysis (historical data and the policies that drive revenue performance). The Unit plans to continue with the hearings as part of its annual workplan.

The dividend audit highlighted weaknesses with the processes for reporting and paying of government dividends, with potential losses to the consolidated fund. Recommendations from this audit have resulted in policy changes including the Guarantees Advance Payment for mining companies with government interest to ensure government dividends are accurately paid; and 15% of profits from limited liability state owned enterprises paid annually into the consolidated fund
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The output’s value for money proposition can be assessed by its contribution to improving the government’s fiscal space. It is estimated that the usage of 37% of IGF’s for tertiary institutions in utilities will yield about GHC620m in additional fiscal space in 2020 for the government.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The main change for the period was the inclusion of the revenue hearings in the programme’s activity. This has been useful for increasing government’s fiscal space and efficiency in spending.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendation	Action
The unit must develop the capacity to scrutinise MDA’s statutory reporting to ensure they meet the requirements and deadlines.	The unit conducted Revenue Budget Hearing for all MDAs to ensure improve fiscal transparency and scrutiny within the MDAs generating revenues.

 Recommendations:
The Non-Tax Policy Unit’s work on revenue hearings is proving useful for improving the government’s fiscal space and expenditure efficiency and it should be sustained within the unit’s annual activities.

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall risk rating for the programme remains Major. Considering the ambitious scope of the programme the last annual review suggested that a comprehensive risk register be developed to ensure appropriate safeguards are in place. The programme team developed and maintained a comprehensive risk register which was updated regularly. / Political Current assessment and mitigation / There may be slow transition and possibility of key senior actors changing roles DFID has maintained continuous engagement with the senior managements at GRA resulted in a number of transformational changes. DFID should continue to engage with the political leadership on revenue reforms (ministry of finance). / 2020 election campaigns derails tax reforms of GRA and the ministry of finance The senior management are continuously being engaged on pace of reforms. / Compliance intervention for revenue generation suffer set back due to political interference Continuous HMG engagement of GRA senior management and senior political leaders to discuss reform progress progress / Change in GRA leadership Extension of engagement beyond senior leadership to maintain credibility within the institution for continual progress. / Operational / Change in GRA leadership -Limited support from new leadership approving programme activities and pushing general GRA reforms DFID has demonstrated professionalism in engaging with newly appointed management at GRA. / Improper programme closure losing sustainable element Ensuring the gains of the programme are sustained is key to programme success hence DFID has encouraged project heads to own programme delivery for sustainability beyond DFID. / Management / Covid 19 affected programme activities that required stakeholders to come together such as workshops, seminars The team put together a business continuity plan or ways of working when there was restriction of social gathering. This contingency plan allowed the project team to work productively via ZOOM and MS Teams. There are some activities that required experts to be in country could not take place. (For example, IFS mission and engaging tertiary students on the GRA informant rewards) / DFID should continue to review the continuity plan and adjust it accordingly. / COVID-19 - There is risk to programme delivery as external expert advisers (including from HMRC) will be unable to travel to Ghana because of Travel Advisory in place. Programme delivery will also be impacted due to restriction of movements in place. This will affect projects such as prosecutions, Cabinet office re-organisation and office rationalisation. This risk is heightened as some advisors could not travel to Ghana to continue programme activities. These advisors are virtually engaging programme partners. / More broadly the project has increased the use of the local experts to drive reforms at GRA. / Inappropriate use of grant money by grant holder. Clear guidelines on use of funds and financial reporting is part of IPs orientation at the start of each cycle. DFID monitored this risk by requesting IPs to submit monthly the bank statement. Financial reports are received and verified before subsequent disbursements. Field visits are carried out on a quarterly basis, Annual independent comprehensive Audit of the programme conducted to provide the right level of assurance for DFID. / Reputational / Programme actors at various levels engage in corrupt and fraud activities Regular engagement by the GRRP Project Manager Consultant with management and project team should continue.

Update on partnership principles

The partnership principles (PP) are regularly assessed by DFID, and the last update was undertaken in September 2019. It is assessed that the Government of Ghana is broadly committed to the four UK PPs and risk are assessed as moderate. Ghana’s commitment to the partnership principles is assessed annually. Any deterioration in commitment will be reviewed and decisions taken on implications for programming, and specifically for those giving financial aid to the Government.

Annual Statement of Progress (financial aid programmes only – delete if n/a) [1 page]

Current level of fiduciary risk and direction of travel since last ASP	Major / Stable
Specific assessment of corruption risk and direction of travel since last ASP	Major / Stable
Is a full FRA update required?	No

The key fiduciary risks and their mitigation actions are summarised below:

Risk 1: Poor Budget Credibility - Outturns against budget for consolidated expenditure show large variations and the is a worsening Aggregated Revenue Outturn.
Actions and progress: Implementation of the Fiscal Responsibility Act (2018), which places a 5 per cent cap on fiscal deficit in any given year; and backed by law should serve as a major constrain. Progress in this regard has been hampered by the Coronavirus pandemic.

Risk 2: Transparency - Sizeable amounts of central government operations are not captured by central government financial reports; transfers to Sub-National Governments (SNGs) are not transparent, which may threaten local government service delivery.
Actions and progress: The Ministry of Finance (MoF) with support from the World Bank under the Public Financial Management Reform Programme (PFMRP) is implementing the Ghana Integrated Financial Management Information System (GIFMIS), which comprises Oracle Hyperion, Oracle Financials, Oracle Payroll and the Human Resource Management Information System (HRMIS). The GIFMIS project is aimed at ultimately capturing all central government operations.

Risk 3: Poor controls over payroll expenditure - Poor application controls and incomplete linkages between human resource management and payroll. This could result in an inflated payroll with ghost workers.
Actions and progress: The Audit Service have carried out a Nation-wide Payroll and Personnel Verification Audit in line with Section 16 of the Audit Service Act, 2000 (Act 584). Analysis suggested no justification for the continuous existence of 10,689 employees on the Payroll (2% of total employees on public roll) as at June 2018.The audit service is now taking steps disallow all such persons for benefiting from the payroll and surging applicable heads if evidence is not shown to confirm their existence.

Risk 4: Revenue administration – Including multiple weaknesses - absence of risk-based
systems to effectively monitor and assess compliance and deficiencies in associated reconciliations. This means that revenue potential is not realised, which has a knock-on effect to the availability of budgetary resources.
Actions and progress: The Ghana Revenue Authority is piloting a risk-based audit approach in 2 offices with support from the Netherlands government. This is being delayed as the authority’s centralised data system is deemed deficient and a replacement of the integrated tax administration system is currently being considered. There is currently no timetable agreed for the replacement of the existing TRIPs© system, but measures are being taken to stabilise the system and address existing data quality and retention issues.

HMG is ramping up support to the Ghana Revenue Authority to fundamentally overhaul the structure and organisation of GRA, including proposals for a grass roots review and reorganisation of the HR systems and operational structures across GRA. HMG will also support processes for a risk-based approach to GRA’s compliance activities.

The Public Financial Management Act is the overarching framework for PFM reforms in Ghana. The most recent public financial management reform strategy ended in 2018 and the government has now contracted EY who are in the process of designing a new PFM strategy from 2020 – 2025 based on the recent PEFA.

Sources: Various Government of Ghana reports.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

The programme is on track to achieve its outputs and outcomes even though some planned activities did not happen or were not completed in the year under review. Thus far the programme has spent 80% of the total approved budget for the programme. In 2019 financial year a total of £1.63m was forecast out of which £1.62m was spent. The programme activities were tracked through the partners quarterly narrative and financial reports.

The 1% underspend on the programme is mainly attributed to delays in approving project activities and the outbreak of Covid-19. Regardless of the challenges faced, the financial year saw an increase in the total spend of 66% compared to previous years which had a spend of 57%.
The programme continues to present good Value for money (VFM). The main cost drivers for the programme are costs for capacity building. 20% discount arrangement has been reached with service providers for using their facilities for both residential and non-residential trainings.

The outcome of the trainings is evidence in staff performance. In the year under review for example, the PAYE team developed a working tool that helped them to efficiently perform risk assessments and profile tax liabilities without following the conventional methods. This tool helped them to assess and collect Ghs 178 million tax from companies within the Greater Accra Region and other regions.

The adaptiveness of the programme is demonstrated in the programme’s engagement with the new leadership in GRA and quickly refocusing the programme recently towards the urgent requirements of the Covid 19 response. The programme continues to focus on delivering on agreed areas of support and delivering Value for money (VFM) in line with the project’s VfM indicators. The quality of financial and narrative reports submitted by the project team has improved. Notwithstanding this, additional efforts are required to improving the quarterly VfM reporting.
Performance of partnership(s)

The programme team has built collaborative relationships with the various programme partners. The successor HMRC long term adviser within the programme is gradually building relationships across the GRA. Relationships with the Cabinet office, IFS, HMRC and GPI have contributed towards the strengthening of Ghana’s revenue effort. DFID Ghana is also leading donor efforts towards improved strategic donor government engagement on tax reforms.
Asset monitoring and control

The GRRP has maintained an asset register for the various partners. The register provides information on assets procured from inception and the respective users. All assets are properly labelled in line with DFID’s communication and branding guidance. As part of DFID’s monitoring activities, asset verification exercises have been carried out on a quarterly basis throughout the year to ensure assets are being used for intended purpose. The last verification exercise was conducted in March 2020. In the year under review the project recorded 3 fraud cases. These cases were reported immediately to the DFID Counter Fraud Unit and appropriate actions undertaken. There are 2 outstanding cases that DFID is closely monitoring to ensure they are properly closed.

Expenditure Verification - Expenditure verification exercises were led by the Finance Consultant and conducted on programme finances. All agencies have adhered to the recommendations following on from the spot check exercises. DFID’s fraud and corruption policy has been shared with project leads and this has been disseminated to team members and downstream partners.

Field Visits – The programme team (including leads from DFID) conducted an extensive monitoring visit to GRA offices in three regions (Ashanti, Western and Central Region). The exercise highlighted the need to strengthen revenue collection systems across the board. Feedback from the offices visited also indicated the need to proactively ensure regional balance in the programme’s capacity building activities.

Date of last narrative financial report	13 May 2020
Date of last audited annual statement	06 May 2019