Annual Review - Summary Sheet

Title: / Creating Opportunities for Poor and Excluded People (COPE)
Programme Value: GBP 24,200,000		Review Date: May 2016
Programme Code: / 202958	Start Date: / August 2013	End Date: / December 2016

Summary of Programme Performance
Year	2014	2015	2016
Programme Score	A+	A+	A+
Risk Rating	Moderate	Moderate	Moderate

Summary of progress and lessons learnt since last review
The Creating Opportunities for Poor and Excluded people (COPE) programme, implemented by the Manusher Jonno Foundation (MJF), has achieved all – and exceeded most – of its output indicators in its third year. The programme is also on track to achieve almost all its outcomes, with only two outcome indicators on land access unlikely to be achieved due to external factors, such as instability and uncertainty caused by local level elections, which made interactions with local government bodies more challenging. It is on track to exceed outcome targets in other areas, particularly the numbers of people able to access basic services.

MJF projects continue to benefit from strong working relationships between MJF, the 117 Non-Governmental Organisations (NGOs) it supports, and the poor and marginalised communities the programme targets. On the demand side, there is evidence that large numbers of poor and marginalised people are raising their voices against violation of their rights; claiming entitlements; capturing more space in social and political institutions; and gaining improved access to service and resources. For example, MJF has supported partner NGOs to organise a public hearing identifying over 200 health and agriculture services related problems. 169 of the issues raised were solved through successful negotiation with the respective agencies at the local level. There is also evidence of government service delivery institutions being more responsive to people’s needs within intervention areas. For example, management committees of 115 Community Clinics (CCs) played an effective role in improving the functioning of the clinics including medicine monitoring and mobilisation of local resource to improve maintenance.

With regard to policy advocacy, MJF has continued to establish effective links between grassroots work and national level policy processes. For example, MJF has supported the formulation of new Labour Rules, and Workers’ Welfare Foundation Rules, both of which have been enacted in the last year, and MJF partners have followed up the implementation of these rules at the factory level. MJF has also continued to build effective partnerships and its own capacity to deliver programmes more efficiently and effectively. For example, the programme has undertaken a review of the systems for monitoring.The major output areas have shown progress with lessons learned being fed back into the programme strategies and adjustments being carried out.

This year, based on the last AR’s recommendation, DFID commissioned case studies on transformational change processes that MJF has been involved in over the last 12 years. For example, the programme supported establishment of Disabled People’s Organisations (DPOs) who worked to enhance the capacity and confidence of people with disabilities for their constructive engagement in community development process. The DPOs play a critical role to negotiate, build alliances and establish a platform for their communication with the wider community. This has contributed to reduce their social stigma within society. The programme also explored ways that it could make stronger linkages between its different programmes (e.g. rights of marginalised people, violence against women and girls). Evidence generated from these two exercises informed a new MJF Strategy for the next 5 years.

Summary of recommendations
As the programme is in its last few months, most of the recommendations relate to preparing the ground for any future work, and following up the strategic planning work. Priority recommendations are:
- MJF should finalise its strategic plan based on the experiences of the COPE programme and an assessment of the current priorities in the field of rights and governance, in the context of the present socio-political and economic situation of the country. By October 2016
- MJF should develop its resource mobilisation strategy based on an assessment of its resources needs, the type and scope of various resources available nationally and internationally, including from the government and the private sector so that MJF can begin implementation soon after the new phase begins. During new phase in 2017
- MJF should initiate its strategy for knowledge management and institutional development for the CSO sector within the COPE period so that MJF can begin implementation soon after the new phase begins. During new phase in 2017
- Any future work should include an investment in knowledge management which will enable sharing of lessons on what works, and also demonstrate the relevance of the work to a wider range of private and non-traditional donors. This will be important to help build an evidence base on what the ambition of the Global Goals to leave no one behind means in practice, and what has been successful in realising that ambition. MJF and its network of partners are uniquely placed to contribute to that evidence base.

Recommendations and lessons for any future work include:
- The need to better integrate MJF’s thematic programmes, ensuring synergy and cross-learning between work on Rights of the Marginalised and Responsive Governance (recommendation 1.2) and in areas such as gender and disability (recommendation 1.1).
- The need to explore linkages with other programmes – particularly:
  - Dialogue with PKSF to promote the use of the revised Micro-Credit Regulatory Authority guidelines addressing Violence Against Women (recommendation 2.1), in the context of a proposed new programme on Pathways to Prosperity for the Extreme Poor (PPEP), and establishing referral linkages that could enable victims of VAW to access livelihood opportunities (recommendation 2.2);
  - DFID’s new PROKAS project, which may include some work addressing the risks of exploitation linked to labour migration (recommendation 3.1); and
  - Future DFID plans for work on Access to Justice, where the ambitious aims that MJF has are only likely to be realised through better coordination with other programmes with more substantial policy dialogue and activities supporting justice system reform (recommendation 4.1).
- As part of a strategy to tackle VAW, MJF partners should continue creation of women’s networks, groups and organisations, while introducing a stronger emphasis on sensitising boys and men – for example through the school curriculum. The objective should be to reach a tipping point in the transformation of deeply-ingrained patriarchal values that underpin gender-based violence (recommendation 2.3).
- MJF should consider how RTI can be integrated for grievance redress at the local level (recommendation 4.2).
- In order to prioritise MJF’s policy advocacy efforts, MJF is recommended to finalise its Advocacy Strategy (recommendation 6.1).

A. Introduction and Context

DevTracker Link to Business Case:	4019177
DevTracker Link to Log frame:	4685174

Outline of the programme
The UK government is providing £24.2 million over 3.5 years (2013-2016) to Manusher Jonno Foundation (MJF) to implement the Creating Opportunities for Poor and Excluded people Programme (COPE). Australia’s Department of Foreign Affairs and Trade (DFAT) provided AUD 6 million (equivalent to £3 million) for 3 years between 2012-2013 to 2014-15.

Bangladesh made significant progress against most of the Millennium Development Goals (MDGs). While the country has achieved sustained economic growth and made substantial progress to reduce the poverty gap, there remains a high proportion of the population living below $1 a day. Inequality has improved but not by much in the past 10 years. Recent analysis has identified that there remain a number of obstacles in Bangladesh for inclusive growth, most notably power, skills and governance that depress new investment, jobs and growth. Lack of accountability at all levels, politicisation and misuse of power often impedes efforts to meet basic needs and provide basic services. Social inequalities are particularly acute for women, despite the opportunities that the country’s economic development has created for employment outside the home. Children from poor families engage in hazardous work and workers often experience harsh working environments. Marginalised groups, including the extreme poor, minorities, people with disability and groups such as sex workers, transgender people and “dalits”[1] are excluded from their entitlements to public services, facilities and resources.
[1] Dalitis the deprived population in Bangladesh and elsewhere in the world. The term is used in Bangladesh to refer to “low caste” Hindus but over time has come to be used for a range of socially excluded groups, usually traditionally involved in professions perceived as unhygienic such as toilet cleaning and pig rearing. The term is perceived as an insult, although it is currently also used by members of these social groups to refer to themselves.

MJF, through partner organisations, is building citizens’ awareness and capacity to raise their voices and claim their entitlements. MJF also works with government to improve the accountability of service providers and public institutions, and to respond to citizens’ demands. The objective is to generate enough public pressure to bring about changes in governance that will secure citizens’ rights and entitlements long-term. This complements other DFID programmes working on livelihoods and social protection.

COPE provides funding, technical and organisational support, and access to national policy influence for non-governmental organisations (NGOs) and community based organisations (CBOs) selected through a competitive process. COPE currently supports 117 NGOs under the following pillars:

Programme Pillar	# Partners
Ensuring Rights of the Marginalized Population	29
Socioeconomic Development of Chittagong Hill Tracts	16
Combating Violence against Women	21
Protection of Working Children and Vulnerable Workers	22
Ensuring Responsiveness of Public Institutions	29
	117

MJF’s also provides capacity building for its partners (Output 5) and national level policy advocacy work on selected issues that are identified as important for their direct beneficiaries (Output 6).

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
COPE outcome statement is: Marginalised and vulnerable people have better access to public goods, resources and services and the programme has 10 outcome-level indicators (see table below). With the exception of two (related) indicators (4.b and 4.d) on land access, all indicators have been achieved, and in most cases well exceeded, showing that the programme is on track to achieve its outcomes.

Progress towards the outcome is achieved by building poor and marginalised people’s knowledge of their rights, and enabling them to demand those rights. By doing so, MJF and over 100 local NGO partners have been able to increase access to services and productive assets for marginalised citizens, as well as making a major contribution to structural change through law and policy reform. For example MJF reports that preparation of lists of eligible safety net recipients by project partners (linked to Indicator 1.a) was bolstered by government drives to distribute Vulnerable Group Feeding (VGF) cards, including among destitute women. Beside the direct benefits to poor people, recent case studies in six thematic areas have shown that MJF has played an important role in building the capacity of its local partners, to manage funds more transparently, increase their impact at a local level, and by working with MJF and others, become more effective in policy advocacy.

Targets for indicators 4.b and 4.d focusing on khas[2] land distribution were reduced based on the last year’s annual review. Although projects working in this area are doing high quality work, their progress has been set back by external factors such as political instability and unavailability of localrepresentatives[3], which limited interaction with government agencies and service providers. It now looks unlikely that the cumulative target of khas land acreage for the programme will be achieved.
[2] Khas land is government/public land intended for redistribution to people who depend on agriculture for a living but own no or less than 10 decimals of land. (All the land records of the government under Register No. 8 and Khatian No. 1 represent Khas land)
[3] No local government election took place since the project’s inception till March 2016. The UP election is due in April 2016.
Progress towards the remaining outcome targets indicates that programme activities are on the right track, with some above the original target, indicating that despite the shortfall against the indicator for khas land, the programme as a whole continues to represent value for money.

The overall Theory of Change (TOC) for the programme is robust. We have also reviewed the original programme assumptions in line with the TOC which confirms that they are still valid and that outputs can still be expected to lead to the programme’s outcome.

	Indicators	Milestone, March 2016	Progress	Status
Outcome Indicator 1: Increased use of services (education, health, and social protection) by poor, marginalised, and vulnerable people
1.a	Number of poor, marginalised, and vulnerable households who gained access to government safety net services.	Cumulative / 107,500 / M: 32,250 / F: 75,250	130,324 / M: 43,007 / F: 87,317	Exceeded / 121.23%
1.b	Total amount (in £million) of social safety net support received by programme beneficiaries	Cumulative / 5.16	6.26	Exceeded / 121.23%
1.c	Number of boys and girls in project areas and communities who were supported & completed primary school.	Annual / 12,000 / B:5,800 / G:6,200	14,922 / B:7,395 / G:7,527	Exceeded / 124.4%
Outcome Indicator 2: Women and girls protected against violence
2.a	Number of women victims of violence receiving compensation, resolution or legal services.	29,500	34,535	Achieved / 117.07%
Outcome Indicator 3: Vulnerable and marginalised groups' participation and representation at the national and local political structures
3.a	Number of marginalised men and women elected to local bodies (union parishad)	No target for 2016 as elections were held after March 2016.
Outcome Indicator 4: Legal rights and access to resources realised in programme areas
4.a	Number of workers having annual pay increase through collective bargaining. (25% men 75% women.)	Cumulative / 50,000 / M:12,500 / F: 37,500	50,697 / M:12,197 / F:38,500	Achieved101.39%
4.b	Number of acres of additional khas land and water bodies leased to poor and marginalised people.	Cumulative 6,000	5,235	Not acheived 87.25%
4.c	Number of women and men in programme areas having paid work and self-employment.	Annual / 12,000 / M:3,600 / F:8,400	12,873 / M:3,476 / F: 9,397	Acheived107.28%
4.d	Total value (in million £) of government khas land and water bodies accessed by beneficiaries.	Cumulative 4.8	4.19	Not achieved / 87.25%
Outcome Indicator 5: Children protected from hazardous labour
5.a	Number of working children (aged 14-17) withdrawn and reassigned from non-hazardous work. 75% boys, 25% girls)
	Withdrawn / Reassigned	8,500 / B:6,500 / G:2.000 / 6,500 / B:4,800 / G:1,700	10,937 / B: 8,006 / G: 2,931 / 8,150 / B: 6,357 / G:1,793	128.67% / 125.38%

Overall output score and description
Output	Overall Score	Impact Weighting
1.Marginalised people are organised to claim their rights and fight discrimination	A+	30%
2.Women's groups equipped to challenge violence against women and girls	A	20%
3.Rights of working children and vulnerable workers protected and strengthened	A+	20%
4.Capacity of citizens in project areas to monitor activities of government service delivery institutions	A+	10%
5.More sustainable civil society organisations	A	10%
6.Evidence generated, synthesised, and used to advocate for changes in various social development policies	A++	10%
Cumulative Score	A+

COPE has achieved all – and exceeded most – of its output indicators over the past year and is on track to achieve all its outcomes. MJF projects continue to show strong working relationships with, and understanding of, communities and their needs. They build effectively on long-standing relationships with communities and activate community support and volunteerism, and they link to local government even where it is not explicit in their mandates.

Following last year’s annual review, DFID commissioned an M&E review that carried out in-depth case studies in MJF’s six programmatic areas (VAWG, RTI, land rights, garment workers and working children) to document qualitative changes brought about through the work of MJF and its partners.

During this period, with TA support, MJF has drafted its Strategic Plan that expected to be finalised in October 2016. This will be a guiding document for MJF’s future work.

MJF’s fund management capacity is clearly demonstrated, both through its robust systems and the quality of feedback received from COPE project partners. However its role in managing COPE clearly extends beyond “fund management”. The review team saw evidence of MJF’s continuing strength in establishing effective links between grassroots work and national level policy processes – something that is rare in projects of this kind, and a real strength of the MJF approach.

Key lessons
- The case study review has confirmed findings from earlier studies that economic empowerment and reducing income poverty alone won’t unsettle the deep-seated sociocultural norms that underpin social marginalisation and gender inequality. In the context of the SDGs, DFID’s mission to Leave No One Behind will best be supported by an integrated approach that tackles the formal (legal/policy) and informal (social norms) barriers to reducing marginalisation and its everyday manifestations, including social discrimination, gender-based violence and early marriage.
- As a follow-up to last year’s annual review, some of the programme streams, like, VAW component has been able to successfully mainstream their approach and key interventions into other programmes, alongside specialist standalone projects.
- By building relationships of trust with local administration or private sector management, NGOs and CBOs can facilitate actions to protect rights of citizens in general and marginalized groups or workers in particular and improve their access to services e.g. land and disability access or workers’ entitlements.
- Involving mainstream groups to show solidarity with the demands of marginalised groups can play a catalytic role in protecting the rights of persons with disabilities, Dalits, Adivasis[4] and Sex Workers.
  [4] The term Adivasis is not confined to any particular geographical or political boundaries but is generally used in the Indian subcontinent to denote indigenous peoples. Like India, Bangladesh has its Adivasis, though their proportion in the population is much smaller, perhaps 1.5 per cent. Bangladeshi Adivasis share major ethnic, cultural, religious and linguistic distinctions from the majority Bengalis.
- Changing social norms related to discrimination and stereotypes of marginalised groups such as sex workers is a long-term process that needs sustained follow-up and action on various levels from legal provisions, livelihoods support and increased access to institutions and services.
- The alignment of the MJF supported child rights programme component with GoB law and policy has helped to get support from central and local administration. It has enabled stronger interactions between GOB and NGOs. GOB feels that NGOs are working to fulfil government obligations and policies. National and International recognition of the work can help the programme to portray as role model for the child labour elimination programme.
- Reducing targeting error and leakages of social security support programmes require not only improved selection of beneficiaries but also procedural changes in the local government institutions.
Citizen groups at different levels, from community to district levels, can support each other. For example - more established citizens at district level are more easily able to develop relationships with local administration to influence them to act in favour of poor & under privileged groups to claim accountability, transparency & participation of public service institutions.
Political and power conflicts at a local level and central level political decisions affect how far local level public service institutions can or will collaborate and how independently they can work to serve the citizens.
Key actions

For MJF
- MJF should finalise its strategic plan based on the experiences of the COPE project and an assessment of the current priorities in the field of rights and governance, in the context of the present socio-political and economic situation of the country. By October 2016
- MJF should develop its resource mobilisation strategy based on an assessment of its resource needs, the resources available nationally and internationally, including from the government and the private sector so that it feed into the proposal for a new programme and MJF can begin implementation soon after the programme begins, if approved. During new phase in 2017
MJF should develop/finalise its strategy for knowledge management and institutional development for the CSO sector within the remaining project period so that it feed into programme design and MJF can begin implementation if a new programme is approved . During new phase in 2017
Has the logframe been updated since the last review?
Yes. The logframe has been revised in line with recommendations made in the 2015 Annual Review (AR). The following changes have been made:
- The target for outcome Indicator 4.b on khas land has been reduced from 9,000 acres to 6,000 acres.
- Re-wording of the output indicator 3.1 to reflect the kind of education[5] that is being provided to enable children to enter the formal education system at grade one.
  [5] from NFE(non-formal education) to PES (preparatory education sessions)

A few recommended changes have not been made:
- No change in output indicator 2.3: Based on M&E Review’s recommendation, the 2015 AR recommended that the wording of output indicator 2.3 should be amended, to clarify what is being measured, specifically - ‘the percentage of girls in project areas remaining unmarried until age of 18’. MJF reviewed the recommendation and noted that to implement this they will need sufficient time to develop a full list of 13-18 year old girls within the targetarea. This demands that partners do a full inventory of their working area and monitor all 13-18 year old adolescent girls, which would be time consuming and expensive to implement in the current phase. Hence, MJF decided to keep the original indicator but has agreed to revise the indicator for any future programme.
- No change in output indicator 6.1 on policy advocacy campaigns: The 2014 review has suggested that output indicator 6.1 could be further divided into three sub-indicators measuring MJF’s contribution to the drafting of laws, the enactment of laws and the implementation of laws. The 2015 AR recommended that the indicators will need accompanying narrative to provide evidence of MJF’s contribution. Although the indicator was not amended, the information under Output 6 has been provided using these categories and shows that this categorisation allows MJF to better capture the range and extent of work being done under policy advocacy.

## C: DETAILED OUTPUT SCORING (1 page per output)
Output Title	Marginalised people are organised to claim their rights and fight discrimination
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
1.1 Number of people supported by the project to practice their citizen rights and tradition (annual)	150,000 / M:45,000 / F:105,000	159,612 / M:43,095 / F:116,517	A
1.2 Number of people from marginalised groups taking part in local government bodies and local forums (70% women, 30% men) (cumulative)	12,500 / M:3,700 / F:8,800	17,651 / M:5,119 / F:12,532	A++
1.3 Number of children in project areas learning in mother tongue in their schools (cumulative)	6,000 / B:2,900 / G:3,100	8,518 / B:4,089 / G:4,429	A++
1.4 Number of children enrolled in primary schools (cumulative)	70,500 / B:35,000 / G:35,500	77,259 / B:37,084 / G:40,175	A
1.5 Number of men and women received skill development training and entrepreneur assistance (annual)	13,000 / M:4,000 / F:9,000	16,499 / M:4,620 / F:11,879	A+
1.6 Cumulative number of poor and marginalised people in target communities in CHT who increase their monthly income by BDT 1000 through income generating activities. (cumulative)	8,500 / M:3,600 / F:4,900	11,382 / M:5,236 / F:6,146	A++

Key Points
This output covers a range of MJF’s work:
- Indicators 1.1. and 1.2. gather evidence of mobilisation activities across all MJF’s work;
- Indicators 1.3, 1.4 and 1.5 report on work under the two pillars of Socioeconomic Development of Chittagong Hill Tracts and Ensuring Rights of the Marginalised Population;
- Indicator 1.6 focuses exclusively on the Chittagong Hill Tracts (CHT)

All indicators have moderately or significantly exceeded milestones. As mentioned in previous reviews, facilitation of citizens to practice and claim their rights, whether through independent activity or through government committees and structures (indicators 1.1 and 1.2) lies at the core of all of MJF’s work. This is clearly one of MJF’s strengths. The programme has strong working relationships with, and understanding of, communities and their needs. They built effectively on long-standing relationships with communities and activated community support and volunteerism.

The Rights of the Marginalised (ROM) programme has been central to MJF’s work since 2002. It engages with people whose entitlements to basic resources and services are denied, whether due to negligence of service providers, lack of inclusive policies and programmes, lack of information about their rights and how to access them, or low social status. Through COPE, MJF works with people who are marginalised due to occupation (e.g. dalits, harijan[6], fisher-folk, sex-workers); minority identity (e.g. religion, caste, ethnicity); living in vulnerable or remote areas (e.g. Char, Haor or Hill areas); disability; disease status, biological identity or behavioural practices (e.g. homosexual, transgender).
[6] Harijan population is one of the subsections of the Dalit community who are traditionally involved in sweeping and cleaning. This community brought in from India by the British rulers to do the cleaning work in the cities and towns of what is now Bangladesh.

Over the last year a substantial number of marginalised people (88,708 persons) have accessed social services (health, education, safety-net, land, water-bodies, etc). Group members of different marginalised communities have raised their voice to claim and realise their rights, which has led to improvement in their lives and livelihoods (63,514 persons out of which 46,365 females and 17,149 males). 5,451 persons (3,870 females and 1,581 males) have made representations to different government and non-government committees. Receptivity to their demands on the side of the government seems to have increased.

The social acceptance of sex workers has increased visibly in some areas. For example, they held elections of their organisations involving government officials and civil society members. A host of strong mobilisation and protests were held against the forced displacement of Adivasis, brothel evictions and physical abuse of Dalits and disabled people, with support from civil society. MJF is working closely with a Parliamentary Caucus for Adivasis that has been formed to look at indigenous people’s rights.

The ROM programme has also been working to support implementation of the Rights & Protection of Persons with Disability Act 2013 (RPPD Act), and helped formulated the Rules of RPPD Act 2013 and Neuro Development Disability Protection Trust Act 2013. It has been actively pursuing the proposed Anti-discrimination Act which is now with the Ministry of Law for vetting.

Some marginalised groups are still subject to social discrimination and abuse by the powerful. For example, two brothels were evicted in the last reporting year. Local power relations and politics of attracting popular votes have played a pivotal role in attacks on sex workers and their homes.
The Socio-economic Development of the Chittagong Hill Tracts programme is working with 16 direct partners and 9 sub-partners with 109,176 girls, boys, women and men in 19 Upazillas and 55 Unions. Through these partners’ activities 2,381 indigenous students (1,119 girls and 1,262 boys) completed primary school and 8,518 children (4,429 girls and 4,089 boys) are learning though mother tongue language. MJF has contributed in the government’s initiative to introduce textbooks in five ethnic languages for children of minority groups in schools at the pre-primary level, which will be effective from the next academic year.[7] It has also been agreed to have a school calendar adapted to the CHT context.
[7] The decision was made in a meeting of the officials of National Curriculum and Textbook Board (NCTB). Ref: http://www.thedailystar.net/frontpage/govt-print-textbooks-5-ethnic-languages-1229056
In the reporting year, 24,916 students (11,462 females and 13,454 males) are studying in 332 primary schools (GoB run 125 schools and 207 community schools) of which 126 schools have initiated different IGAs and 20 schools have run community managed hostels. As part of increasing sustainability, 38 community schools have been registered with the government while another 60 schools are in process of receiving registration. Capacity building support was provided to 341 School Management Committees to improve the qualitative monitoring of school operation.
In the CHT area, livelihoods of the community are improved through diversification of income generation avenues. For example,11,626 men and women (6,279 females and 5,347 males) received skill development training and entrepreneur assistance while11,382 poor and marginalized people (6,146 females and 5,236 males)improved their monthly income by BDT 1,000 in the targeted area. This has been done through environment friendly cultivation in 50 unions and improved market linkages for which the Department of Agriculture also provided support. The group beneficiaries have saved BDT 1.9 million (cumulative) since the project’s inception. The project partners have worked in establishing market linkages for the product of beneficiaries which leads to their sustained income increase. Other major achievements are: documentation of customary land laws (now awaiting government endorsement) and capacity building training to traditional leaders for land related dispute resolution.
MJF and its partners work in a distinct way in the Chittagong Hill Tracts, with a dedicated programme team, reflecting the unique needs of CHT, such as the need to working in different languages.

Summary of responses to issues raised in previous annual reviews (where relevant)
- The last review recommended that MJF should expand its livelihood work to include a better linkage to markets in its CHT programme and opportunities to link to other UK-funded projects such as EEP/CLP and Katalyst should have been explored by DFID. The update is that MJF partners have been working in developing market linkages and the private sector has also established marketing channels to the rest of the country. MJF itself has opened a small sales centre in its office. Initial discussions with Sujog a social business company based in Singapore could not be pursued because of contractual reasons. On the other hand, since both COPE and EEP/CLP projects are at final stage, DFID considers that it would be more appropriate for MJF to explore linkages with other UK aided programmes during its future work. Keeping this into consideration, DFIDB facilitated MJF’s discussion with the design team of the new Extreme Poverty programme.
- It was recommended that MJF should explore opportunities for mainstreaming some of its other initiatives such as VAW and RTI across its ROM work. This has successfully been done with VAW component. The mainstreaming of RTI work will be taken into consideration for MJF’s future work.
- The recommendation was that MJF should ensure that its short-term approaches to working with marginalised communities (e.g. dalits) are fully consistent with its long-term goals. Based on reviewing the existing programme strategy, the Rights of the Marginalised (ROM) programme component has developed a draft action plan as how to address differential needs of vaious marginalised groups. This will be shared with DFID during next quarter.

Recommendations
1.1	MJF should ensure that there is sufficient cross-learning between programmes and partners that	they do not miss expertise from the wider rights team on cross-cutting areas such as gender and	disability. Recommended for inclusion in MJF’s future work
  1. MJF should consider how a future phase could better integrate work on Rights of the Marginalised with work on Responsive Governance, so that the two reinforce each other. Recommended for inclusion in MJF’s future work

Output Title	Women’s groups equipped to challenge violence against women and girls
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
2.1 Number of dowryless marriage in programme areas	Cumulative / 11,200	11,882	A
2.2 Number of women victims of violence in project areas supported to have access to medical and /or legal assistance.	Cumulative 42,500	45,236	A
2.3 Number of early marriages (i.e. girls under 18 years) prevented in project areas. Programme works to prevent (outside beneficiary groups) and to actively stop people from marrying underage girls.	Cumulative 11,000	13,129	A+

Key Points
Violence against women and girls is a huge challenge in Bangladesh, with around 65% of married women having experienced physical violence[8] and with wider impact on health, education and mobility. Despite the increased opportunities for education and formal employment that are available to women, there remains a widespread cultural/social tolerance for domestic violence, traditional patterns of early marriage and dowry, and ongoing vulnerability for women who remain economically dependent on men. Combating Violence Against Women and Girls (CVAWG) is therefore an important area to make progress in – and an area where MJF and partners have many years’ experience.
[8] Violence Against Women Survey 2011 by BBS

MJF’s Combating Violence Against Women (VAW) programme is contributing towards reduction of violence against women and girls by changing institutional norms and practices, and reducing impunity for perpetrators. It works at individual, household, community, sub-national and national levels, through 21 partners and 12 sub-partners in 29 districts. The coalition of partners working on VAW is the strongest across all MJF programme areas, with VAW organisations formally meeting more regularly than others to share lesson learning and best practice. The approach used included Prevention, Protection and Provision.

There have been a number of achievements in the reporting period. All the indicators have been achieved. Some of the reasons for this are increased awareness in the community and among local officials and public representatives and increased women’s leadership. Leadership development has increased mobility of primary women’s group members, along with representation and participation in local forums, social institutions and local markets. It has enabled them to be vocal in claiming entitlements from local service institutions and also provide support and solidarity for similar groups mobilising in adjoining areas. Women leaders are participating in ’Shalish’ (informal dispute resolution mechanism) as panel members in the UP village courts.

Community awareness against child marriage is increasing and people are using the government hotline to make complaints. There has been an increase in action against sexual harassment, child marriage and more girls are able to continue studying up to SSC and HSC examinations. As a result of encouragement from the higher levels of government administration, local administration and local government bodies are more responsive in stopping early marriage. As a means of changing stereotypes and gender norms, nine partners have motivated educational institutions to start sports for girls and during the reporting period. 1,400 girls are playing sports in partners working area, which increases their physical strength and confidence and challenges gender norms about seclusion and restrictions on adolescent girls.

MJF also advocates policy changes to address VAW drawing on evidence generated by the partners at the grassroots. For example, MJF and its partner NGO USHA have been working with Polli Karma Sahayak Foundation (PKSF) and Micro-credit Regulatory Authority (MRA) officials to ensure that the micro-credit guidelines address issues of VAW. For this, MJF and its partners[9] reviewed the Micro Credit Policy from a gender perspective and came up with 19 recommendations with an objective to empower female credit borrowers economically and reduce the violence against them. As a result of MJF’s advocacy, 7 of the recommendations were taken further by microcredit funds. A high level National Caucus for Women’s Economic Empowerment was initiated for policy advocacy with MRA and PKSF for gender responsive micro credit in order to spread the concept to other micro finance organizations throughout the country. Gradually MRA has included the recommendations in their rules, so that it is now mandatory for all micro finance institutions to follow. Currently, the National Caucus is disseminating and following up on the implementation of the current Micro Credit Policy with 25 PKSF Partners, Bangladesh Bank, Micro Credit Regulatory Authority and MFIs. The caucus has launched a checklist[10] to see which of the recommendations were being implemented by the 25 pilot organisations.
[9] MJF partner USHA invited key microcredit organisations including BRAC and ASA, RDRS, Shakti Foundation, Credit Development Forum, renowned Social and Economic analyst, media to review micro finance from a gender perspective.
[10] which were approved in late 2015.

During the reporting period, the number of women victims of violence receiving compensation, resolution or legal services is also higher than the milestone (ref: output indicator 2.2) with partners using the district legal aid funds and involved in the union or upazila legal aid committee. However, the majority of cases are still resolved through NGO facilitated Shalish.

In spite of impressive gains, challenges remain and new ones are emerging nationally, such as increased reporting of incidences of incest violence, use of ICT for harassment of women and girls and difficulties in the implementation of the Domestic Violence Act.

Summary of responses to issues raised in previous annual reviews (where relevant)
- It was recommended that MJF explore whether and how to engage more actively with men as part of its anti-Violence against Women work, and to link approaches to a long-term strategy for changing social norms on acceptable behaviour. The review of MJF partners has shown that men are already involved at a ratio of 1:2 in various capacities. Work has already been done to ensure gender training includes masculinity and gender norms. However, changes in men and boys’ attitudes and behaviour was not being measured and reported on. The future work of MJF will address this.
- It was recommended that MJF should look at whether its CVAWG work would be more effective as a cross-cutting issue across all programming rather than as a separate programme. This has been successfully piloted in ROM pillar where a strategy paper and guidelines have been prepared. All partner project documents have been reviewed and objectives reset as needed and partners have been provided training on VAWG aspect.
- Recommendation was that output indicator 2.3 should be amended, to clarify that what is being measured is the percentage of girls in project areas remain unmarried until age of 18. MJF reviewed this recommendation and noted to be unrealistic to implement in the current programme since it demands that partners do a full inventory of their working area and monitor all 13-18 year olds there, which is time consuming and expensive proposition. MJF agrees to implement this recommendation in its any future work. In this context, under the current programme, MJF agrees only to maintain a list of those beneficiaries, who has family members between the age of 12-18 years and accordingly, will monitor their status in regard to early marriage.

Recommendations
2.1	DFID should facilitate dialogue with PKSF and also explore opportunities to link to other UK	funded poverty programme partners to promote the use of the revised MRA guidelines	addressing VAW. For this, the future work of MJF is recommended to ensure that it	coordinates	closely, where possible, with DFID supported newly designed poverty programme, Pathways	to Prosperity for the Extreme Poor (PPEP).[11]
[11] The recommendation is made based on discussion with PPEP team.
2.2	Partners and MJF feel that the financial, livelihoods and counselling support provided for	survivors of violence is inadequate and needs to be strengthened. Although attempts are made to	link survivors to government agencies and grants, these are limited. Establishing and	strengthening referral linkages for the VAWG programme needs greater attention in	any future	work. Hence, MJF is recommended to explore possibilities of making such linkages with those	PNGOs working in PPEP programme’s geographical location through its future work.
2.3	As part of a MJF’s future strategy to tackle VAW, MJF’s grant-funded partners are recommended to	continue creation of women’s networks, groups and organisations and introduce a stronger	emphasis on sensitising boys and men including through the school curriculum and school books.	The objective is to reach a tipping point in the transformation of deeply-engrained patriarchal values	that underpin and perpetuate gender-based violence.

Output Title	Rights of working children and vulnerable workers protected and strengthened
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
3.1 Number of students received Preparatory Education Session (PES) from child center (annual)	12,000 / B:8,000 / G:4,000	13,052 / B:8,792 / G:4,260	A
3.2 Number of workers in decent working conditions supported by the programme (30% men, 70% women) / (cumulative)	42,000 / M:12,600 / F:29,400	53,298 / M:20,253 / F:33,045	A+
3.3 Number of migrant workers in project areas receiving training and support for safe and legal migration. (70% men, 30% women) (cumulative)	5,400 / M: 3,800 / F:1,600	7,021 / M:5,827 / F:1,194	A++

Key Points
Over the past year MJF has surpassed all three of its milestone targets for this output. The three indicators link to two thematic streams: Child Protection and Development (CPD) and Workers’ Rights (including migration).

The CPD stream, which is aligned in line with the Child Labour Elimination Policy and the Labour law, focuses on both preventive and rehabilitative approaches in mitigating the problem of child labour. For this, MJF’s target is to work firstly to withdraw children from hazardous work and secondly, to provide non formal education to these children with the objective of enrolling younger children of 6 to 13 years of age into government schools. Under the Labour Law, children of 14 and over are allowed to work but this component’s ultimate objective is to eliminate child labour completely through bringing back maximum number of children to formal education. Acknowledging the reality that due to economic hardship of their families, stopping work may not possible for some older children (14‑17), MJF has adopted a temporary arrangement for those children to move into less hazardous work environments.

This non-formal education is provided by MJF partners in dedicated child centres attended by working children and children at risk of working (because they are poor, their siblings work, or they do not attend school). These are usually a single year preparatory education programmes that ‘feed’ children into the formal education system, and others involve learning alongside working. Often this works as early childhood development for children who have had no organised learning or safe play spaces. After school tutorial support is introduced that reduced the dropout rate of those children, who have been withdrawn from hazardous work and enrolled into formal schools. These preparatory education programmes are a type of non-formal education (NFE), but unlike the NFE provision commonly found in Bangladesh.

Coordination with local government, local administration and other actors have been improved in respective projects areas. The alignment of the MJF child rights programme with GoB law and policy has helped to get the support from central and local administration. It has enabled stronger interactions between the government and NGOs.

At the policy level, the government has officially recognised MJF’s contribution to address the issue of child labour. For example, the State Party Report on CRC (Child Rights Convention), which was presented to the UNCRC in September 2015, acknowledged MJF and its partners’ work in the area of child labour. MJF has also prepared an alternative report, from which a number of the recommendations were incorporated into the concluding comments of the official session. These comments have now been translated into Bangla and disseminated for follow-up. As a follow-up to one of the recommendations GoB has formed a national committee for the establishment of Child Directorate where MJF is a member.

Among the challenges faced by the programme is the higher number of children and the difficulties in accommodating them in the learning centre. Also a batch of children are being prepared for enrolment in January 2017. However the present project funding will end before then.

The second thematic stream that feeds into this output area is workers’ rights. These projects aim to simultaneously work on improving the awareness of workers of their rights, organise them into associations and support their efforts to negotiate for decent working conditions (specifically, receiving wages on time, able to use leave entitlements and have standard working hours in the garments and shrimp processing sectors. Other projects also focus on potential migrant workers and agriculture workers, and COPE has a small pilot initiative with domestic workers.

Over the past year, 53,298 people have been supported to have better working conditions against a target of 42,000. A large part of this has come from the garments sector. MJF had a significant role in drafting the Rules relating to the Labour Law, which were approved in 2015 and these are now being translated into English. In the last year, workers of garments and shrimp factories in the partners working area received the 5% wage increase that was due to them. Twenty women’s trade unions have been set up and participation committees are functioning. MJF also made contribution in drafting the Domestic Workers Welfare and Protection Policy that was approved in 2015.

Though impressive gains were observed in regard to promotion of workers’ rights in the garments industry, it has been difficult to gain support for legislation on basic minimum wages for agricultural workers because of lack of political will. When supporting garments workers, it has been noted that without good relations with the factory management, it is hard to implement workers’ rights projects. MJF partners work to buildstrong relationships with factory management.

Potential migrant workers are receiving services such as information and training, visa checking, online registration, opening bank accounts, complaints handling, support for death compensation, and local mediation. The data are from the 16 centres run by 4 of MJF's partners. The proportion of women receiving support is half that targeted.

Safe and legal migration is an important issue in Bangladesh given the number of people who migrate annually (both within Bangladesh and overseas) and the risks involved. To address this, the workers’ rights stream has a special component on protection of rights of the potential migrant workers. Awareness raising activities on safe migration has a direct contribution to enhance counter trafficking in the project areas. This year, 7,021 migrant workers in project area have received training and support for safe and legal migration against a target of 5,400. To make financing easier for migrants, MJF partners have been working with the Probashi Kalyan Bank which is providing loans on easier conditions, but the number of branches is limited. Attempts are being made to ensure better remittance management but there are difficulties due to migrants’ reluctance to share information.

Summary of responses to issues raised in previous annual reviews (where relevant)
- In the light of recent evidence and reporting on the scale of human trafficking from Bangladesh, MJF collected information on safe migration through establishing migrant support centres. During the reporting period, MJF conducted a study that shows that the rate of irregular migration from MJF’s project areas is nominal.[12] MJF has decided not to undertake any additional work under the programme.
  [12] Tangail and Sirajganj districts were compared and it was found that in the former (MJF partner RAMRU’s working area), people has better access to information on legal migration procedures as a result of which they had not become victims of trafficking. On the other hand, in non-MJF supported Sirajgang district, incidences of unemployment and poverty is quite high and the people have less information about safe migration. As a result, more people had fallen victims to trafficking. Sirajganj and Cox’s Bazar emerged as areas with the greatest irregular migration.
- Based on recommendations, MJF conducted a review of the Workers’ Rights Programme that helped in discussions around formulation of its future work in this area, the outcome of which is prioritisation of the areas of workers’ rights. MJF has also decided to not to continue direct work in the informal sector but to continue supporting partner NGOs in the areas of garments and migration. A decision was made to promote the rights of informal sector workers through research and advocacy.
As recommended the wording of indicator 3.1 has been changed from ‘Non-formal Education’ to Preparatory Education Sessions to better reflect the contents of what was being taught as the objective is to enrol the children in class-1.

Recommendations
3.1MJF should ensure that its PNGOs on migration coordinate (where feasible/possible)
     closely with another DFIDB funded programme PROKAS’s Issue Based Projects on
     migration.

Output Title	Capacity of citizens in project areas to monitor activities of government service delivery institutions
Output number per LF		4	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
4.1 Number of people involved in project areas to monitor health, agricultural extension, education, social protection, nutrition services available to the poor	22,300 / M:12,300 / F:10,000	26,291 / M:12,094 / F:14,197	A+
4.2 Number of Government institutions monitored by partner organisations using social accountability tools:	Cumulative / a) Agricultural Extension Offices 150 / b) Health Facilities 300 / c) Social safety net programmes 100 / d) Schools 200	Cumulative / a) Agricultural Extension Offices 212 / b) Health Facilities 412 / c) Social safety net programmes 140 / d) Schools 292	A++

Key Points

Over the past year MJF has surpassed both its milestone targets for this output. The indicators link to MJF’s governance programme on Responsive Public Institutions. For this output, the programme focuses on both demand and supply side interaction between citizens and local officials or public servants (e.g. doctors, teachers, agricultural extension workers and other service providers) to make the latter more responsive, thereby addressing two critical issues; a) quality of participation and capacity of targeted communities to claim their rights and b) responsiveness of government mechanisms and processes which improve their accountability. Implementation of the Right to Information (RTI) Act (2009) and improving local legal services for the poor (particularly women) also constitute two important streams under the programme. The stream is also closely linked to MJF’s work on combating violence against women (see output 2).

10 partners and 3 sub-partners are active in 43 upazilas and 212 UPs with 241,122 beneficiaries in the governance performance monitoring stream of activities. The number of Government institutions monitored by partner organisations using social accountability tools has exceeded the milestones. Targeted community/farmers/beneficiaries are better at claiming their rights and their involvement in the various institutions has also increased, leading to better performance of these institutions. Government institutions are also more open to providing information. There is increased partnership between service providers and community recipients. An achievement is that local authorities havereplicated the Governance Performance Monitoring approach in others public service institutes. However, after the recent local government elections there is a possibility that the partisan elected UP Chairs may be less willing to be accountable to the citizens as their source of power lies not in their electorate but elsewhere.

Under this output, MJF also supports local government institutions in enhancing capacity of the elected representatives/local officials and activating participatory structures. Partner organisations use social accountability tools such as social audits and scorecards (mainly) to involve beneficiaries and stakeholder groups in monitoring public services, including provision (e.g. whether health facility staff and teachers show up; numbers of visits by extension officers etc.) and quality (e.g. whether a beneficiary list is prepared for safety nets).

During the reporting period, all working unions (76 UPs) have developed participatory development plan through conducting meeting at the ward level. On an average, 85% development schemes are now being implemented following this Development Plan. Local Government Institutions (LGIs) also have improved compliance of development activities and social safety-net management. Citizen’s Forums have been formed at all LGI levels and are actively involved in local level development activities. Around 200,000 people have participated in various events, like ward shava[13], planning, budgeting, etc. organized by LGIs (two-thirds men and one-third women). 2,427 persons were involved as member of functional committees of LGIs and other local institutions. On the other hand, 1,258 local institutions and public services were monitored by the community volunteers. Accountability to citizens has been improved through disclosure of budget, budget monitoring and face to face question-answer sessions.
[13] Ward Shava is the main platform for Union Parishad (UP) where the community can engage, interact and influence the UP functionaries to take decisions according to their local needs and priorities, pro-poor planning for improved service delivery,
A lesson from working in the grassroots level is that community level common citizen groups are not enough to bring about change - stronger citizen forums at different administrative level (comprising local respected citizens) are required to ensure better governance of public institutions and realize citizens rights. Based on this learning, MJF took the initiative to support establishment of district level citizens forums in two districts. Along with other actors, sustained campaign by MJF’s partners contributed to influence the policy level decision making in regard to the decentralisation process. For example, in a bid to take the fiscal decentralization at local government level, the government issued a circular om 14 October 2015 instructing to directly disburse the fund to Upazila Parishad[14] (UZP) for paying salaries and allowances of the staff of the 17 transferred departments.
[14] The second tire of rural local government in Bangladesh is the Upazila Parishad.

As part of improving legal aid services, the project activated union, upazilla and district legal aid committees in the respective working districts. This has contributed to an increase in the utilisation rate of the Government Legal Aid Fund for the poor and women. 90 Village courts are functional in 90 Union Parishads. As a result of its  successful advocacy on Supreme Court Legal Aid, MJF also became members of the  Supreme Court Legal Aid  committee in May, 2015.
Summary of responses to issues raised in previous annual reviews (where relevant)
- Recommendation to undertake a pilot initiative to mainstream RTI across its other work has been met. The review team noted that on a pilot basis, RTI has been successfully mainstreamed into the activities of an access to justice partner NGO, Shabolomby and a local governance partner NGO, RACINE.
- Recommendation was to finalise a strategy and set of activities to complement its long-term decentralisation campaign goals with efforts to achieve more concrete short and medium term changes in improving the local governance. Linked to this, another recommendation was to conduct a mapping exercise for synergies among a range of other similar initiatives on local government. Both the recommendations have been met as MJF has updated its local governance strategy paper. To complement the strategy, MJF has taken a mapping exercise of actors and accordingly, prepared a summary note which will be shared with DFIDB by August 2016.
- MJF’s Access to Justice Program is under the portfolio of ensuring responsiveness of public institutions. The recommendation was that MJF should revisit its strategy and current programmatic arrangement for Access to Justice Component. The update is that MJF has analysed its current programmatic arrangements and has decided to emphasize the governance aspects of access to justice. In relation to other interventions in the area of justice sector reform, MJF has decided to concentrate on areas where it has comparative advantage[15]. MJF has not yet shared its revised action plan with DFID. A follow-up action is recommended under 4.1.
  [15] In the reporting period, MJF along with a leading legal aid NGO has carried out a review of Criminal Procedure Code’ for future programming. MJF also considers continuing national level advocacy on Supreme Court Legal Aid where it has previously specialised.
- Another recommendation was MJF to consider piloting new & innovative social accountability tools in the remaining time under COPE, explore how it can act as an “importer” of international good practice for its partners, and seek complementarity with other existing projects such as the World Bank Global Partnership for Social Accountability. MJF is already using internationally standard set of tools and approaches. Its future plan is to further explore the possibility of doing budget and expenditure tracking by using these innovative tools.

Recommendations
4.1	Future DFID plans for work on Access to Justice, where the ambitious aims that MJF has are only	likely to be realised through better coordination with other programmes with more substantial policy dialogue and activities supporting justice system reform By August 2016
4.2 MJF should consider how RTI can integrate grievance redress at the local level.	Recommended for future work of MJF
Output Title	More sustainable civil society organisations
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
5.1 Number of small partners receiving financial support other than from MJF (cumulative)	10	11	A+
5.2 Percentage of MJF budget coming from sources other than DFID. (annual)	25%	19.64%	B

Key Points
This output reports against two indicators on the diversification of funding sources; the first for small MJF partners[16] and the second for MJF’s own fundraising achievements. Performance against the first indicator moderately exceeded 2015 milestone targets. However, the performance against the second indicator was affected by AusAid funding being withdrawn due to a strategic shift in Australian policy.
[16] Under this output, a small partner is different from MJF’s regular partners and sub-partners. The “small partners” are those locally organised CBOs or people’s organizations that have been facing multiple challenges which are attributed due to lack of capacity in managing program, insufficient grant, poor project management, and weak financial management and governance mechanisms. These organizations applied to MJF for fund but failed to qualify due to their poor capacity. As a result, MJF’s Capacity Development Unit decided to support some of these organisations to develop their systems and strengthen programme implementation.Initially, they received training to develop their organisational capacity and then MJF provided approximately £5450 for one year to implement their respective project.

MJF works with a diverse range of partners; some that are very large and well established in their own right and others that are much smaller and more dependent on MJF both as a source of funding and for capacity building and guidance. To work with multiple partners, MJF has developed mainly a two pronged approach, working directly with some organisations as “partners” and indirectly with smaller organisations as “sub-partners” through their direct partners. MJF also provides capacity development support to a group of “small partners” who applied to MJF for funding but failed to qualify due to their poor capacity. One of MJF’s goals is to build the capacity of small organisations to stand on their own feet. Most of the MJF’s larger and more established partners already receive funds from more than one source. Its partners are not wholly dependent upon MJF sources of funding. Currently, 35% local PNGOs are dependent on MJF funding for 50% of their programme budget.

The first indicator measures the progress of smaller organisations towards accessing more diversified funding sources (other than MJF). MJF and COPE contribute to this by providing capacity development support - organisational and technical capacity development, financial management training, M&E support. The achievement was slightly above the target.

The 2014 AR noted that the sustainability of civil society organisations is not only about its funding, but also about rooted they are in the context in which they work. The strength and density of the interactions of partner civil society organisations could be assessed in terms of the quality of the long-term relationships being built with communities; the nature and achievements of coalitions and networks between civil society groups, and the density and quality of interaction with Government at different levels. Sustainability is also about maintaining a presence and an identity beyond projects and campaigns and being able to pursue a goal over a long-term period. The M&E review in 2015 took this into account.

MJF has a two dimensional approach to supporting partner organizations. The first dimension is the provision of financial support through grants; the second is technical support for the immediate and long term needs as identified by MJF, but within the scope of the project. Regardless of the size and duration of the grant and the organisation, the capacity building needs are specified by a) organisation, b) individual, c) systems, d) and programme MJF also encourages cross-learning visits to other partners’ programme, peer-learning and monitoring activities, periodic participatory needs assessment and information sharing. There is also an innovative scheme for career development for women from marginalised communities. MJF-central monitors partner performance continuously. This is done through the programme staff visits and monitoring, the M&E visits and monitoring and also the Finance team monitoring. As part of the MJF ‘family’, partner NGOs are gaining a reputation for organisational standards and values which enhance their credibility not only with potential donors, but also to work effectively at local and national levels. In other words, they are being assisted to prove/demonstrate their value.

Diversifying its own sources of finance away from DFID is desirable for MJF’s future sustainability and growth. Indicator 5.2 reflects this objective. In the past year, MJF has submitted a proposal to SIDA for funding. It has received funding from DFID under a separate programme on Social Protection. In the last year, MJF has gone through a process of strategic planning exercise and also submitted a new proposal to DFID to support a newprogramme. In order to enhance its own organisational capacity and financial sustainability, the strategic planning exercise highlighted the importance for MJF to develop a resource mobilisation strategy and also a strategy for the enhancement of its own institutional strength as a learning organisation.

In the area of knowledge development and management, MJF has developed a nationally leading M&E unit in the rights and governance arena, which is capable of programme tracking and results chain functions. It has recently initiated a separate research unit. Both the M&E and research units require further strengthening. There is a realisation within MJF that it could have far greater leverage and therefore impact, if it invested in developing its knowledge management capacity. In this regard, MJF has begun to explore collaboration in this area with entities such as PRIA in Delhi, INTRAC in Oxford and the Centre for Advocacy in Washington.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID commissioned a 4-member TA team (2 internationals and 2 nationals) to support MJF’s strategic planning exercise in 2015. As an outcome of this exercise, a draft Strategy is developed that MJF is in the process of finalisation. This will be a guiding document for MJF’s any future work.

Recommendations
  1. Based on the success of COPE programme support to horizontal networking amongst PNGOs, M&E review recommended that future programming increase its focus on PNGO networking, including strengthening linkages across programmes, to ensure that lessons learned and best practice developed by PNGOs are shared and implemented more widely so that programme outcomes can be further scaled up.

Output Title	Evidenced generated, synthesized and used to advocate for changes in various social development policies
Output number per LF		6	Output Score	A++
Risk:		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Score
Number of policy advocacy campaigns on rights and governance (cumulative)	4	11	A++

Key Points
MJF has a strong focus on bringing voices from the grassroots into government policy advocacy in order to realise the rights of marginalised and vulnerable people, with some effective results. This indicator is intended to demonstrate how MJF’s role in managing COPE extends beyond fund management and in particular to reflect MJF’s upstream policy work.

Always part of a coalition, during the reporting period, MJF has played different roles in the advocacy process, depending on circumstances and strength of partner organisations, from driving the advocacy movement for policy enactment (for example, amendment of exemption list (section 7) of RTI Act, enactment of the Domestic Workers Policy 2015 and rules of the Rights & Protection of Persons with Disability Act 2013) to a more practical supportive role for drafting the law (for example, technical assistance to help the Government draft the Anti-discrimination Law and amendment to the Women & Children Repression Prevention Act 2013).

Although the 2015 Annual Review team was struck by the strong emphasis on advocacy for enactment of new laws in MJF’s advocacy portfolio, with relatively little on implementation of existing laws, the present review noted that MJF has good track record of support on policy implementation. For example, MJF and its partners are working in the field to mobilise the communities for enforcement of the Hindu Marriage Registration Act 2012; as a result of which 1,550 Hindu couples have registered their marriage for the first time in the country since it’s enactment. Similarly, in 2015, MJF partner DNet developed the RTI tracking software to be used by service providers to track RTI applications and by citizens for filing online applications for information from government or non-government offices. This will also be used to appeal to respective authorities if citizens do not get a response, and also to file complaints to the IC, if required.

The following table shows a sample of the policies/laws for which MJF and its partners have made contribution in terms of drafting, enactment and implementation.

Theme under COPE	Implementation	Enactment	Drafting
ROM	Rights & Protection of Persons with Disability Act 2013 (RPPD Act)	Ministry of Social Welfare has been formulated Rules of RPPD Act 2013 / Neuro Development Disability Protection Trust Act 2013.	Proposed anti-discrimination law
VAW	Domestic Violence (prevention and Protection) Act-2012 and rules 2013 / Hindu Marriage Registration Act-2012 and Rules 2013 / Gender Responsive and Assertiveness Micro Credit Policy 2015[17]		Women and children repression prevention act-2000(amendment 2003)-reviewed and recommendations submitted to Ministry of Women & Children Affairs (MOWCA)
Vulnerable children	Child Labour Elimination policy 2010		MJF member of national committee for the establishment of Child Directorate where.
Workers rights	Bangladesh Labor Rule 2015, / Worker Welfare Foundation Rule 2015, Domestic workers welfare policy 2015 and implementation of 5% increment in RMG and Shrimp workers / Migration Policy 2016	Bangladesh Labor Rule 2015, / Worker Welfare Foundation Rule 2015. / Official English Translation of Bangladesh Labor Act 2006.	Domestic workers welfare and protection policy 2015. / Migration Policy (2016)
Access to Justice	Policies under Legal Aid and Services Act, LASA like activation of Upazila and Union Legal Aid Committee.	Legal Aid Services Act, 2000 revised in 2013 where provision of Supreme Court legal aid committee has been included	Safe home policy of Department of social service
Monitoring of government service delivery institutions	RTI Act / New Agriculture Extension Policy (2006) / Local Governance Acts	Information Disclosure Policy guidelines and provision for government ministries and departments integrated in National Integrity Strategy	Advocacy with Information Commission for amendment of exemption list (section 7) of RTI Act
[17] Micro Credit Regulatory Authority adopted 7 recommendations in MRA rules, which MFI’s are now bound to follow.

Summary of responses to issues raised in previous annual reviews (where relevant)
- One recommendation was to commission case studies drawing on the outcome attribution and impact monitoring data, on powerful change processes that MJF has been involved in over the last 12 years. This recommendation is met as DFID commissioned six case studies (e.g. land rights, readymade garments sector, Dalits, RTI, VAW and Working Children) were completed, based on which MJF has reviewed and prioritised its policy advocacy efforts and feed these recommendations into a broader strategic planning process.
- Another recommendation was to develop an advocacy strategy for the whole programme as well as for individual components to balance a high profile legislative advocacy agenda against ongoing advocacy for more effective implementation of existing legislation and policies. This recommendation was partly addressed by developing the draft strategic plan.

Recommendations
6.1	In order to prioritise MJF’s policy advocacy efforts, MJF is recommended to finalise its advocacy strategy - by October 2016

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
MJF’s principal cost driver is the costs incurred by its partner organisations to support community mobilisation activities of grassroots organisations. These are typically local staff salaries, programme materials, and travel costs. These costs, which make up around 70 percent of the total expenditure, are all incurred in Bangladesh Taka and are driven by the local market rates in Bangladesh. The rest are MJF’s programme management costs, such as the monitoring of partners’ programme implementation and financial management, partner’s capacity building and staff development, which are also driven by rates in the local Bangladeshi market.

VfM performance compared to the original VfM proposition in the business case
MJF supports different sizes of organisations: small, medium and large. Across these partners it tracks a few indicators of value for money, focusing on both efficiency and economy.

Performance against the efficiency indicators identified in the Business Case includes:
  1. Cost per beneficiary trained to take part in income generation (ROM, CHT & VAW) - 700.00 Taka (eqv. to £6)
  2. Tk 1,000 BDT (eqv. to £8) increase in monthly income (CHT ) – increase from tk. 4,000 to 5000 (eqv. to £34 to £43)
  3. Average cost of per acre khas land redistributed is taka 24,550 (eqv. to £211) and this is the average cost for such kind of programme,

Benchmarking standard costs across different sub-grants helps MJF to drive down costs, although some variation is inevitable where projects work in remote geographical locations, with limited local infrastructure, and markets.

MJF selects those projects that have demonstrated VFM in their proposal and financial management. Therefore, all MJF supported projects demonstrate effective and efficient spending of economic resources to producing maximum benefit to the poor and disadvantaged group in different locations throughout the country.

Project cost and implementation - The COPE management always tried to implement any sub-project with optimum cost so that they can reach to many people with limited resources. Therefore, MJF prioritised projects which have lower costs per beneficiary. Projects with higher costs were only accepted if they offer benefits for the poor and marginalised people, who are in special needs or not offered by other partners.

Budget Preparation and Guideline (Economy) – MJF has prepared comprehensive budget guidelines for its partner organisations, based on its day to day experience of dealing with NGO partners. MJF reviews the key components of the project costs with partners to ensure these are consistent with the market rate. NGOs have to justify significant variations from the standard costs for common activities.
Efficient and effective use of money for procurement - MJF follows internationally recognised best practice for procurement of goods and services, and they ask partner organisations to follow similar practices. The DFIDB finance team, Programme Manager along with the UK colleague have visited MJF’s office and observed their systems and procedures. This has confirmed that MJF follows the best practices such as, division of labour, involvement of different people at different level of procurement that ensure good check and balance at different points and transparency and accountability. The procurement section of the financial manual is very clear about the process partners have to follow and documentation to preserve. It ensured competitiveness, cost effectiveness, and value for money. MJF finance staff review all procurement of their partners’ projects regularly during their financial monitoring visits and ensured that they have adhered to the guidelines. MJF partners have to take special permission from MJF finance team by giving proper explanation if any partner thinks they may not comply with the procurement process due to their operating location. In addition, MJF established the process of unit cost analysis to guide its partners to obtain maximum inputs at the lowest possible costs.
Financial monitoring and follow-up- MJF has an experienced finance team, and a system in place to ensure optimum use of donors funds. They have strong budget monitoring tool to ensure optimum uses of each penny. MJF also has established an effective financial monitoring system to oversee the costs in relation to the prescribed financial policy and procedures. MJF’s finance team visit a partner organisation twice annually to review budget, expenditure and controls. Feedback from the report is shared with the partner organisation to ensure mitigating steps are taken to ensure effective financial stewardship. The quarterly financial reports and call forwards are also reviewed by the finance team and accordingly, recommendations passed on before disbursement. Both in monitoring of financial process and its quarterly reporting, costs are further evaluated and compared to the estimates. MJF’s finance team share these reports with DFID Programme Manager during quarterly meetings. A thorough review of the reports, which make recommendations in regard to organisations to follow-up, negotiated budget and how to ensure optimum benefits out of any expenditure, gives assurance to DFID staff about the quality of MJF’s effective financial monitoring system.

Assessment of whether the programme continues to represent value for money
COPE has played a key role in supporting poor and marginalised people to enjoy a better quality of life as well as MJF’s evolution as a leading human rights based organization in Bangladesh. This year, with the exception of two land related indicators, MJF has performed very strongly against all other indicators, and in some cases, substantially exceeded expectations, in monetary as well as developmental terms. This overall VFM performance indicates that COPE continues to represent good value for money. Examples of changes resulting from programme interventions where a monetary value can be calculated include:
- The total safety net support received by the beneficiaries this year is worth £2.15m;
- Approximately £4.02m was recovered as dower money, medical and legal support;
- As a result of the project support, the factory workers’ pay increased annually £770k that has a huge economic impact on their lives.

For this sort of programme, VfM metrics do not capture every change that adds value, particularly those involving transformational change and people’s empowerment. Examples include:
- Beneficiaries from the Disabled People’s Organisations (DPOs) ensured positive changes in their life including becoming part of a social group rather than living in isolation, and improved status and reduced discrimination in their families and communities. The DPOs played a crucial role to enhance the capacity and confidence of people with disabilities for their constructive engagement in community development process. The DPOs also helped to negotiate, build alliances and establish a platform for their communication with the wider community. This has contributed to reduce their social stigma within society.
- The socially excluded groups (e.g. dalits) had been, as a result of the programme, able to make sure that their children could attend school; roads connecting their often remote villages to urban centres were built; their places of worship were supported and financed by local government assistance; alternative income generating activities were introduced in their communities.
- As a result of the project support, women and minority group representatives have become more confident and have taken leadership roles in their respective communities; or have been elected into key local government decision making bodies.

As stated earlier, there was one area where factors beyond the programme’s control made it hard for MJF partners to engage effectively with locally elected representatives to assist poor and marginalised people to gain access to khash land. It now looks unlikely that the cumulative target of khas land acreage for the programme will be achieved, despite efforts by MJF partners to use the more settled political situation in the last year. The shortfall in this area is offset by other areas where the programme has exceeded the expected outcomes.

Quality of financial management
MJF has a sound governance framework for financial management and is supported by a Finance and Audit Committee with responsibilities for risk management, internal and external audit, financial reporting, and fraud and compliance with the legal and regulatory environment. MJF uses integrated financial management system which includes sound internal control at each stage of fund transfer, financial monitoring, standard policies and procedures, secured accounting software, budgetary control, risk assessment, standard procurement, delegation of authority. As reported earlier that MJF financial staff visits partners organisation twice a year to rigorously review their books of accounts and status of implementation of any previous recommendations. The quarterly financial reports and call forwards are also reviewed by the finance team and recommendation passes on before disbursement.

The activity-based financial reporting system enables MJF tracking of all expenditures against each budget line. MJF has been conducting budget variance analysis on quarterly basis and estimates future cost through financial projections. To ensure financial accountability, in every fiscal year, MJF finance department prepares a risk assessment of all partner NGOs using a prescribed score sheet. The team also prioritises monitoring visits based on risk assessment and takes appropriate action as applicable. All financial data are posted in the central MIS (Grants Management System) on quarterly basis and all monitoring visit records are also preserved in the MIS as future reference. Over the periods, MJF has ensured satisfactory progress against audit recommendations.

The last audit FY-2015 did not raise any major observation. MJF has prepared an appropriate action plan for the previous audit observations. The review looked at the process through which MJF and its partners’ reporting suspected any fraud or corruption. It has been noted that MJF and its partners reviewed and audited their books of accounts every year, and followed-up any qualified audit report or any other observation with the respective organisations to overcoming the observations. Observations typically included staff not being paid on time, advances not being adjusted promptly or individual instances where VAT had not been deducted from payments to suppliers on transactions where it should have been.

In addition to the audits commissioned by MJF and its partners, DFIDB commissions independent audits of a sample of partners. These DFID financed audits typically highlight a similar type of findings. The regular finance staff members of MJF review financial papers of a partner organisation twice annually to ensure transactions are done as per agreement, and financial risks are taken care and controls are in place. All feedbacks are shared with the respective partner organisation to ensure effective financial stewardship. The quarterly financial reports and call forwards are also reviewed by the finance team and recommendations are passed on before next disbursement.

In case of allegations of corruption or fraud, MJF reports all cases to DFIDB who later consult with the Counter Fraud and Whistleblowing Unit (CFWU) in DFID HQ for their guidance and accordingly, based on the advice, full investigation is undertaken either by MJF or other independent bodies. If allegations are substantiated, recovery of funds and where appropriate curtail funding to next disbursements.

MJF has updated its fraud reporting system and process and is working with all of its downstream partners to ensure they are aware of DFID’s policies on counter fraud and whistle blowing unit. For this, regular training and orientation sessions are organised for PNGOs for maintaining and follow best practices, risk management and conflict of interest. Most importantly, MJF has over the years demonstrated its zero tolerance of misuse of funds or inadequate financial controls in partner organisations, terminating support to several NGOs that did not meet the necessary standards. During the reporting period, MJF discontinued funding to a NGO due to misuse of fund.

DFID is supporting MJF to update their Operating Procedures for fraud reporting and to improve and strengthen counter-fraud communications to staff across the organisation. This year, with assistance from DFID’s Programme Management team, MJF has organised 7 batches if training on Fraud, Risk and Corruption regionally for staff[18] of PNGOs in Dhaka (3 nos.), Khulna (2 nos.), Chittagong (1 no.) and Rangamati(1 no.). MJF has a plan to conduct this training in three other regions in Rangpur, Sylhet and Dhaka within this project period. MJF also conducted some regional workshops on standard practice of financial management in 7 regions and noted some feedback, suggestion from partners staff including CE to produce a ‘note book’ on the best practice on financial management which will help to ensure standard financial management in the partners level in future.
[18] Mainly Project Coordinator and Accountant but in some cases, also CEOs

MJF follow the International accounting Standard in its annual report presentation in addition to its regular donors reporting. The audited financial reports are uploaded in its official website in order to represent its transparency and accountability.

Date of last narrative financial report	11 April 2016
Date of last audited annual statement	January – December 2015 audit report; submitted on 30 June 2016

E: RISK
## E Risk
Overall risk rating: Moderate

Overview of programme risk
COPE programme is managed through an accountable grant agreement. MJF is responsible for delivering the programme and for financial oversight of DFID funds. DFID has worked with MJF for over 13 years and during this period MJF has consistently delivered results. External financial audits and procurement reviews have found that MJF has the systems and policies in place to manage DFID funds.

MJF regularly assesses risks to programme implementation and has a number of mitigating strategies which they are employing to minimise the impact of risks on their programmes. DFID also takes additional actions to address specific risks. This year, the programme’s risk register is updated based on the overall risk environment that has been changed since the project's inception. The overall assessment of risk is Moderate, based on the following factors:

MJF and its partners work on occasionally sensitive issues of rights and governance. They manage the risk of a backlash from government officials wishing to avoid scrutiny through their good relationship with the relevant regulatory bodies, and their proactive and cooperative approach to senior government counterparts, offering support in improving rules, policies and legislation as well as the challenges the implementing organisations face on the ground. As an additional measure, DFID have an ongoing dialogue with the government on how national NGO regulations could be modernised and made less cumbersome and better targeted.

There has been limited progress against the land related output because local officials have been hard to access as a result of ongoing local elections. However, the AR noted improved cooperation from the local administration (Assistant Commissioner of Land) as they agreed to accept the list of landless people produced by MJF partner NGOs.

MJF has been working to make its data more user-friendly and credible. Based on an M&E Review recommendation, implementing agencies are working on customising the presentation of data and evidence to different target audiences as required, to capture media and citizen attention. DFID has also been supporting MJF to strengthen their M&E capacity to ensure better data management and results reporting. The AR noted improvement in evidence generation and reporting that includes on-line reporting, updated webpage and well documented case studies that gathers evidence of the programme’s qualitative and transformative impact.

The previous Annual Review noted that data protection risks might arise from the personal data stored in MJF's on-line M&E systems. To address this, MJF has conducted a review of the confidentiality and personal risk posed due to online data entry of beneficiary profiles. Accordingly, it has established necessary security protocols, and also ensured that all data is anonymised.

Since 70 percent of COPE fund is spent through its grassroots partners NGOs, there is a risk that misuse of funds or allegations of corruption might adversely affect the reputation of MJF or its partners. MJF has several policies and working procedures to mitigate this risk. Further detail is referred under financial management section above.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
MJF is ahead of target across all output indicators and on track for delivery against the planned timeframe.

Performance of partnership (s)
The partnership between DFID and MJF is performing well, with good, regular communication. MJF has developed vibrant partnerships with its project implementation partners and it is clear that partners value their relationships with MJF (see Feedback from Beneficiaries on the next page for more details).

Asset monitoring and control
MJF management and grantees are equally confident and satisfied with the uses of program fixed assets. The following procedures are in place for asset monitoring and control:
- Physical verification/spot checks are carried out on a quarterly basis;
- Fixed assets are registered with ID numbers;
- External audit reports confirm validation and existence of assets in an integrated asset register.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
The Partnership Principles do not directly affect DFID funding for the COPE programme, because no project funds pass through the government. The Principles include a commitment to strengthening domestic accountability that relates closely to the mandate of COPE. While there are concerns about ongoing political instability, and a contraction of the space for independent media and civil society, there are also some signs of Government of Bangladesh commitment to increasing accountability in some of the areas the project works on, ranging from active engagement with implementation of the RTI Act to efforts to improve regulation within the Garment industry.

H: MONITORING & EVALUATION (½ page)

This annual review is conducted by the Lead Advisor and Programme Manager of COPE programme. While engagement across a wide range of stakeholders, particularly at the field level, was limited during the review, the Annual Review team had the opportunity to review of existing reports and engage in some depth with MJF’s different programme team and their M&E unit. The team also have two meetings with partner NGOs to discuss about the programme’s challenges and organisational sustainability. The review was done back to back with MJF’s Strategic Planning exercise. In general, the review team were satisfied with MJF’s monitoring approach, which is both robust and systematic, with efforts being made to improve and innovate around data collection.

The review noted that for systemic evidence gathering from beneficiaries, the partner organisations use social accountability tools (e.g. social audits and scorecards) to involve beneficiaries and stakeholder groups in monitoring of public services, including provision (e.g. whether health facility staff and teachers show up; numbers of visits by extension officers etc.) and quality (e.g. whether a beneficiary list is prepared for safety nets). Across the board feedback was very positive about both MJF and its partners. However, the importance of forming community level organisations as well bringing about institutional and legal change was stressed. The capacity development of MJF partners was also recommended as part of increased sustainability. Since partners vary in their capacity, it was recommended to have more sharing and replication amongst partners.

Evidence and evaluation
While MJF already has in place systems to ensure accurate and consistent reporting against output indicators, the M&E review, which has been commissioned in last year, helps ensure that MJF more consistently gathers evidence of its qualitative and transformative impact in future. The M&E review also supported MJF’s capacity development to undertake manageable and incremental steps to improve the generation and management of evidence, for which it proposed small adjustments to the organisational structure[19], the introduction of evaluative peer reviews based on partners’ qualitative assessment scorecards, prioritisation of learning and communication and the introduction of regular impact assessments. These are all expected to contribute to enhance the ways in which MJF and its partners capture, aggregate and share the results of their work.
[19] to strengthen its quantitative, qualitative monitoring system along with its internal M&E capacity

For impact assessment, following three activities were recommended by M&E review:
- Piloting of a peer review process in which partners come together to reflect on and challenge each other and their contribution to change.
- MJF to conduct a periodic longitudinal impact assessments[20] on the longer-term impact of advocacy gains on the lives of the poorest, including critical non-material dimensions of poverty such as dignity and (gendered) empowerment.
  [20] For this, it proposes MJF to subcontracts an independent local outfit with strong qualitative and participatory research skills.
- Commissioning of case studies, drawing on the outcome attribution and impact monitoring data across a range of 6 programmatic areas, on powerful change processes, including learning from failure. The objective is to document and understand change processes and how MJF and its partners have contributed to these.
The current AR assessed the status of the above stated recommendations and noted that piloting of a partners’ peer review and the case study work both are completed that describe MJF’s contribution to increased accountability and poverty reduction amongst the poorest and most marginal groups in Bangladesh. Drawing on the evidence produced in the six thematic case studies, it has been concluded that MJF managed and DFID funded RGCF[21]/COPE programme has, over its 12 years of intervention, made considerable gains in redistributing rights to the most marginalised and challenging accountability relationships across many sectors and in a challenging political context. The programme’s outcome contribution is interpreted an interaction of macro level policy advocacy and social change campaigning, led with political astuteness and strategic agility by managing agency MJF, and micro level work on accountability relationships by a network of partner NGOs, working over a long period of time through flexible MJF grant funding backed by organisational support and network strengthening.
[21] RGCF: Rights & Governance Challenge Fund

The AR team is satisfied by the amount and quality of evidence and data collected as part of the above stated case study work and strategic planning exercise that addressed key evaluation questions around the quality of the long-term relationships being built by partners with communities; the growth and achievements of multi-stakeholder coalitions and networks; the quality of interaction with the government at different levels; and the role of MJF as an active interlocutor between the ‘micro’ and the ‘macro’, linking pro-poor policy level advocacy. Lessons from the case study work are already used to design MJF’s strategic planning exercise. A recent centrally managed macro-evaluation of DFID’s Policy framework for empowerment and accountability portfolio has also captured some of these useful lessons, with insights for DFID’s Leave No One Behind and VAWG agendas.

In this background, the AR concludes that an impact evaluation is not essential since the major aspects of evaluation have already been well captured and well documented. However, for future work, following is recommended for MJF:
- To further strengthening systems for monitoring and improving the quality of evidence. As part of this, also to initiate the longitudinal impact assessment;
- To investment in knowledge management to enable sharing of lessons on what works, and also to demonstrate the relevance of the work to a wider range of private and non-traditional donors.

Other key M&E review recommendations concerning i) the institutionalisation of learning and reflection and strengthening intra-organisation and inter-tem processes; ii) strengthening of M&E functions and iii) the need to bring together communications, policy work, knowledge management and M&E are being dealt with in the strategic planning exercise and also in the design of the new project proposal that is submitted to DFIDB.

Monitoring progress throughout the review period
The AR was prepared over the month of May-mid June 2016

ANNEX 1 – SUMMARY SHEET FROM PREVIOUS ANNUAL REVIEW OF 2014-15

Title: Creating Opportunities for Poor and Excluded people (COPE)
Programme Value: £24,200,000		Review Date: May 2015
Programme Code: 202958	Start Date: August 2013	End Date: December 2016

Summary of Programme Performance
Year	2014	2015
Programme Score	A+	A+
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

The Creating Opportunities for Poor and Excluded people (COPE) programme, implemented by the Manusher Jonno Foundation (MJF), has achieved all –and exceeded most– of its output indicators over the past year and is on track to achieve all its outcomes.

MJF continues to impress as its projects show strong working relationships between MJF, the 117 non-governmental organisations (NGOs) it supports, and the poor and marginalised communities the programme targets. They build effectively on long-standing NGO relationships with communities, activate community support and volunteerism, which enables the project to adapt to local context – something that is most apparent in the Chittagong Hill Tracts, where the programme integrates service delivery more closely with work on rights than it does elsewhere in the country.

MJF’s fund management capacity is clearly demonstrated, both through its robust systems and the quality of feedback received from COPE project partners. Its role in managing COPE extends beyond fund management alone. The review team saw evidence of MJF’s continuing strength in establishing effective links between grassroots work and national level policy processes – something that is rare in projects of this kind.

Summary of recommendations for the next year

Priority recommendations for MJF under this Annual Review focus on three main areas:

MJF should commission case studies, drawing on the outcome attribution and impact monitoring data, on transformational change processes that MJF has been involved in over the last 12 years. by January 2016.

MJF should use the last 18 months of the current programme to pilot linkages between its different programmes. For example, could some partners in other components increase their work to Combat Violence against Women and Girls (CVAWG) or their use of the Right to Information Act (RTI), using good practice from other partners whose primary focus is in those areas?

These two pieces of work should feed into the development of a strategy to feed into forward planning.- by March 2016

The review also makes recommendations on cash management, and suggested clarification of its approach in some areas, including access to markets for CHT income generating activities, work with marginalised communities, engagement of men in CVAWG work and changing social norms, response to human trafficking as lined to migration, advocacy around decentralisation. A full list of recommendations is below.
Recommendations for DFID focus on:
- Clarifying plans for future funding by December 2015; and
- Coordination with other DFID programmes (e.g. SGSP, CLP/EEP programmes[22]) to ensure MJF is able to communicate effectively with other DFID partners in similar field (e.g. issues on land, garments worker etc)
  [22] SGSP: Strengthening Governance of Social Protection; EEP: Empowerment of the Extreme Poor; CLP: Char Livelihoods Programme
- DFID to help MJF to reach out to other donors to reduce reliance on DFID funding.

Full list of recommendations
  1. MJF should expand its livelihood work to include a better linkage to markets in its CHT programme. In order to maximise the impact of activities and ensure sustainability, it would be useful to ensure that farmers are being able to sell their products at fair prices by supporting them to access markets. To support this, opportunities to link to other UK-funded projects such as EEP/CLP and Katalyst should be explored by DFID– by September 2015.
  2. MJF should explore opportunities for mainstreaming some of its other initiatives across its ROM work, including Violence against Women (see output 2) and Right to Information (see output 4), both in the current programme and in the design of any future work.
  3. MJF should ensure that its short-term approaches to working with marginalised communities (e.g. dalits) are fully consistent with its long-term goals.

2.1.	For future programming, MJF should explore whether and how to engage more actively with men as part of its anti-Violence against Women work, and to link approaches to a long-term strategy for changing social norms on acceptable behaviour – by March 2016.
2.2.	MJF should look at whether its CVAWG work would be more effective as a cross-cutting issue across all programming rather than as a separate programme, and should pilot this approach during the remaining time available under COPE – by June 2016.
2.3	The wording of output indicator 2.3 should be amended, to clarify that what is being measured is the percentage of girls in project areas remaining unmarried until age of 18.

  1. In the light of recent evidence and reporting on the scale of human trafficking from Bangladesh, MJF should assess its current work on safe migration and identify whether there is more it can do – by October 2015.
  2. Overall the review team felt that MJF’s activities on workers’ rights had some real strengths, but emphasised breadth over depth of coverage in some areas. MJF and its project partners should develop a forward-looking strategy on MJF’s broader objectives in this space, how each of the projects is contributing to those objectives, and where and how it would be of most benefit for MJF to work in future – by December 2015.
  3. Indicator 3.1 should be re-worded to say “preparatory education” instead of “non-formal education”, because the type of education MJF supports is not non formal education as generally understood, but preparing children for school enrolment.

  1. MJF should continue its initiative to mainstream RTI across its other work using the existing community groups in other areas – a pilot initiated by August 2015.
  2. MJF should finalise a strategy and set of activities to complement its long-term decentralisation campaign goals with efforts to achieve more concrete short- and medium term changes in improving the local governance – by December 2015.
  3. Linked to the above, DFID and MJF should consider and actively seek for synergies among a range of other similar initiatives on local government. Most of these interventions have been ongoing for over a decade and future programming needs to be better informed on where DFID/MJF interventions are adding value. A mapping exercise to complement the strategy mentioned above should be undertaken by November 2015.

  1. MJF should revisit its strategy and current programmatic arrangement for Access to Justice component by September 2015. This work should be informed by DFID work with other donors and government on the shape of future support for reform in the justice sector, which will include a discussion of where NGOs can best support sustainable improvements in access to justice.
  2. MJF should consider piloting new & innovative social accountability tools in the remaining time under COPE, explore how it can act as an “importer” of international good practice for its partners, and seek complementarity with other existing projects such as the World Bank Global Partnership for Social Accountability by March 2016.

  1. DFID should clarify its plans for any future funding of MJF by March 2016 to ensure that MJF has adequate time to react appropriately (see also Recommendation C above). A future phase of funding should consider, among other aspects, the following questions:
- Is there an opportunity to have two separate streams of work: one for more mature partners and one for newer entrants who require more support to develop?
- Going forward should MJF’s approach be more focused and strategic to improve the prospects of transformational impact in a few key areas?
- How can projects leverage each other better and work more closely together?
- Can projects be given more flexibility to adjust once underway or scale up if successful?
- Is there a need for MJF to have a regional presence?
- What is the most effective way to link social and economic empowerment through the range of programmes supported by DFID?
  1. As part of the same process, MJF should invest in its own strategy development both to respond to and to guide DFID thinking and ensure its own vision of its role and future is taken into account. Once MJF has clarity on the likelihood and scale of DFID funding, MJF should develop and implement a programme strategy accordingly – by December 2015.
  2. In future, MJF should consider putting more resources into working with new/other partners and donors.

6.1.	DFID and MJF should commission case studies, to be completed by January 2016, drawing on the outcome attribution and impact monitoring data, on powerful change processes that MJF has been involved in over the last 12 years. This should include learning from failure.
6.2	MJF should review and prioritise its policy advocacy efforts in relation to the following two findings (among others) and should establish an advocacy strategy strategic document for the whole programme as well as for individual components. It should feed these recommendations into a broader strategic planning process – by September 2015:
  - Reduce number and range of issues covered in order to cover selected issues in greater depth based on clear value for money rationale.
  - Balance a high profile legislative advocacy agenda against ongoing advocacy for more effective implementation of existing legislation and policies.

ANNEX 2	Glossary

AR	Annual Review
AUD	Australian Dollar
CBO	Community Based Organisations
CC	Community Clinic
CFWU	Counter Fraud and Whistleblowing Unit
CHT	Chittagong Hill Tracts
CLP	Char Livelihoods Programme
COPE	Creating Opportunities for Poor and Excluded People in Bangladesh
CPD	Child protection and Development
CRC	Child Rights Convention
CSO	Civil Society Organisations
CVAWG	Combating Violence Against Women & Girls (VAWG)
DFID	Department for International Development
DPOs	Disabled People’s Organisations
DFAT	Australia’s Department of Foreign Affairs and Trade (DFAT)
EEP	Economic Empowerment of the Poor
GoB	Government of Bangladesh
GPM	Governance Performance Monitoring
LGI	Local Governance Institutions
MDG	Millennium Development Goals
M&E	Monitoring & Evaluation
MJF	Manusher Jonno Foundation
MOWCA	Ministry of Women and Children Affairs
MRA	Microcredit Regulatory Authority
NFE	Non Formal Education
NGO	Non-Governmental Organisation
PKSF	Palli Karma-Sahayak Foundation
PNGO	Partner NGO
PPEP	Pathways to Prosperity for the Extreme Poor
RGCF	Rights and Governance Challenge Fund
ROM	Rights of the Marginalised
RPPD	Rights & Protection of Persons with Disability
RTI	Right to Information
SDG	Sustainable Development Goalss
SGSP	Strengthening Governance of Social Protection
TOC	Theory of Change
UK	United Kingdom
UP	Union Parishad
VAT	Value Added Tax
VAWG	Violence Against Women & Girls (VAWG)
VFM	Value for Money
VGF	Vulnerable Group Feeding