British High Commission, Parcelle 1131, Boulevard de l'Umuganda, Kacyiru Sud, BP 576 Kigali | www.gov.uk/dfid | +250 252 556500
The Country Representative, / UNICEF Rwanda, / P.O Box 381 Kigali, / Rwanda.
27th June, 2018

Dear Sir,
Amendment of the MOU between the Government of the United Kingdom of Great Britain and Northern Ireland and the United Nations Children’s Fund (UNICEF) regarding the “Strengthening Rwanda’s Child Protection System to Prevent Violence and Respond to Violence, Exploitation, Abuse and Neglect – Establishment of Community-Based Child and Family Protection Workers in Rwanda” programme (Component 204142-103)
I refer to the Memorandum of Understanding (MOU) for the above project signed by DFID and the United Nations Children’s Fund on 9th December, 2014. Following DFID’s discussion with UNICEF Rwanda on the possibility of receiving additional funds, it was agreed that DFID makes available additional £32,268 to the £432,000 in the original MOU to facilitate provision of job aid tools to IZU in 2 districts in order to fully equip them with knowledge, skills and job aid materials to implement their roles and further benefit children and their communities. In addition, this amendment will rectify the error in project timelines stated in the original MOU with UNICEF to ensure complementarity with the project end date in DFID system. As a result of this I propose the following changes to the MOU:
The total contribution by DFID to UNICEF be changed from the initial £432,000 as stated in paragraphs 1 and 5 in the original MOU to £464,268 with the payment schedule as follows:
	Payment due date	UK£/Amount
1.	31st December 2014	100,000
2.	30th June 2015	50,000
3.	31st December 2015	50,000
4.	30th June 2016	50,000
5.	31st December, 2016	50,000
6.	30th June 2017	50,000
7.	31st December, 2017	50,000
8.	June 2018	32,268

The MOU timelines be changed from 30th September 2018 as stated in paragraphs 2 and 7 in the original MOU to 31st August, 2018.
This letter of amendment will place on record our common understanding of the above changes and will come into operation on the date you sign your confirmation below. This note will be known as Amendment No. 1.
Please sign both copies of this letter; return one to DFID and retain the other for your own records.
Sincerely,

Head of Office, DFID Rwanda

Confirmed for and on behalf of UNICEF:

Name:
Designation:
Date:

British High Commission, Parcelle 1131, Boulevard de l'Umuganda, Kacyiru Sud, BP 576 Kigali | www.gov.uk/dfid | +250 252 556500

APPENDIX 1

FORM OF
CONTRIBUTION ARRANGEMENT

AMENDMENT TO THE CONTRIBUTION:

MEMORANDUM OF UNDERSTANDING BETWEEN THE GOVERNMENT OF THE UNITED KINGDOM OF GREAT BRITAIN AND NORTHERN IRELAND AND THE UNITED NATIONS CHILDRENS FUND (UNICEF) REGARDING THE “STRENGTHENING RWANDA’S CHILD PROTECTION SYSTEM TO PREVENT VIOLENCE AND RESPOND TO VIOLENCE, EXPLOITATION, ABUSE AND NEGLECT – ESTABLISHMENT OF COMMUNITY-BASED CHILD AND FAMILY PROTECTION WORKERS IN RWANDA” PROGRAMME.

27th June, 2018

Dear Sir,

I am pleased to inform you of the intention of the United Kingdom of Great Britain and Northern Ireland (“the United Kingdom”) to make available to UNICEF a contribution as follows below (the “Contribution”):

(a) Programme/Project Name:	Strengthening Rwanda’s Child Protection System to Prevent Violence and Respond to violence, Exploitation, Abuse and Neglect – Establishment of Community- Based Child and Family Protection Workers in Rwanda
(b) Start/End Dates:	9th December 2014 to 31st August, 2018
(c) UNICEF Programme/Project No.:
(d) DFID Programme/Project No.:	204142-103
(e) Contribution Currency/Amount:	UK£ 464,268
(f) Recovery Rate for Indirect Costs: / (section 2, para. 17(a) of Framework Arrangement)	8%
(g) Contribution Disbursement Schedule: / (section 2, para. 18 of Framework Arrangement)	☒ The Contribution will be transferred in full / ☒ The Contribution will be transferred in accordance with the following schedule: / Payment due date UK£/Amount / 1. 31st December 2014 100,000 / 2. 30th June 2015 50,000 / 3. 31st December 2015 50,000 / 4. 30th June 2016 50,000 / 5. 31st December, 2016 50,000 / 6. 30th June 2017 50,000 / 7. 31st December, 2017 50,000 / 8. June 2018 32,268
(h) Electronic Remittance Advice to be sent to: / (section 2, para. 7 of Framework Arrangement)

I propose that this letter together with your confirmation by signature, below, that its provisions are acceptable to UNICEF, will constitute a Contribution Arrangement between the United Kingdom and UNICEF (the “Participants” and each separately a “Participant”) with respect to the Contribution, which will come into effect on the date of your confirmation on behalf of UNICEF.

The Contribution will be used exclusively for the purposes of the programme or project as indicated in paragraph 1(a) above, and as laid out in the relevant project document.

The Contribution will be disbursed subject to a disbursement schedule in accordance with paragraph 1(g) above. UNICEF will submit a payment request to DFID for each scheduled disbursement. Each payment request submitted in accordance with this paragraph should include the following information:

All amounts received under previous disbursements in accordance with this Contribution Arrangement (in UK Pounds sterling and the equivalent amounts in US Dollars);

Expenditures against previous disbursements and unutilised amounts remaining, if any (in US Dollars); and

The amount requested for further disbursement.

In the event that the Contribution will be disbursed subject to a disbursement schedule in accordance with paragraph 1(g) above, that schedule may be amended by mutual consent of DFID and UNICEF.

This Contribution Arrangement will be an arrangement supplementary to the Framework Arrangement concluded between the Participants. The provisions of the Framework Arrangement will apply except as otherwise provided herein/in this Contribution Arrangement.

It is expected that the Contribution will be fully utilised by the End Date as stipulated in paragraph 1(b) of this Contribution Arrangement or as soon as practically possible after this date. Commitments entered into by UNICEF after the End Date will require the prior agreement of DFID, to be obtained in accordance with paragraph 7, below.

This Contribution Arrangement may be modified by written agreement between the Participants.

This Contribution Arrangement may be terminated by either Participant upon giving not less than three (3) months written notice to the other Participant. Upon receipt by one Participant of the other Participant’s written notice of termination of this Contribution Arrangement, the Participants will take all reasonable and necessary measures to conclude the implementation of the Programme or Project and complete their activities in an orderly manner. In accordance with the foregoing, UNICEF may apply any unutilized portion of the Contribution to permit the orderly conclusion of the Programme or Project, including the completion of final reports, the withdrawal of personnel, funds and property, the settlement of accounts between the Participants, and the settlement of contractual commitments or liabilities relating to or in connection with the Programme or Project, including in respect of any implementing partners, contractors, subcontractors, consultants or suppliers.

Sincerely,

____________________________

Head of Office, DFID Rwanda

Confirmed for and on behalf of UNICEF: / Name: / Title: Country Representative, UNICEF Rwanda / Date: ______________________

UNICEF-DFID GBV/VAC Programme
Action Plan for additional funding
Draft submitted on 07 June 2018

Background
On May 15 2018 UNICEF Child Protection team was approached by DFID for a possibility of receiving additional DFID fund amounting to £32,373 (approximately USD 43,237 or RWF 36,751,450) to be used as part of the current UNICEF-DFID GBV/VAC programme (end date: 30 September 2018). The rational is that the additional funding, if given, should be consistent with the wider aim of reducing violence and gender inequality and represent good value for money.
So far, the funding from DFID (£432,000) has been catalytic in contributing to developing national terms of reference and standard operating procedures for IZU, deploying IZU in 30 districts and developing and rolling out the pre-service training to all 29,674 IZU. Currently, the focus of the government and UNICEF is to operationalise IZU, mainly through the partnership model with Save the Children in 11 Districts with high prevalence of child protection concerns including around GBV and violence against children. So far, 8,983 IZU in the targeted districts have been equipped with skill sets and tools through provision of refresher trainings and job aid tools to implement their roles to prevent, respond and refer child protection cases in communities. As a result, since October 2017, a total of 103,138 home visits were conducted and 62,929 children have received direct psycho-social supports from IZU in the 11 target districts. Among the total 31,035 cases reported and followed up by IZU from October 2017 is school dropouts (39%), violence within homes (21%), family conflict and abandonment (19%) and child labour (13%).
[note] Gakenke, Gicumbi, Rwamagana, Ngoma, Nyarugenge, Gasabo, Ruhango, Nyamagabe, Nyabihu, Huye, Kirehe. Huye has been newly added to the list since April 2018 instead of Nyamasheke District due to administrative issues. Nyamasheke District will be added to the phase II districts.
[note] The minimum IZU job aid package includes an ID badge, a bag, IEC materials, a reporting template, stationary, an umbrella, a mobile phone and minimum airtime.
With the support from UNICEF and NCC, Save the Children has assessed and documented the lessons learned in operationalizing IZU which can be used as a model to take to scale in the remaining districts. Findings show that the capacity of IZU is still at initial stages, while there exists a strong will to protect children. Continuous empowerment through capacity building and provision of necessary job aid materials is thus critical in fully operationalising IZU to implement their roles. Also, empowering IZU coordinators to supervise lower level IZU and building strong linkages with local authorities and the professional social workforce is the key to the success of monitoring, coordinating and sustaining the IZU structure. 11 Districts where received direct operationalisation supports have reported that working together with IZU has achieved the District, Sector and Cell social development performance, thereby contributing to the welfare of children. Also, IZU are now seen as trusted actors by community members, and are directly engaging with children and youth. Based on these lessons learned, the priority of the Government and UNICEF is to progress IZU operationalisation across the country through a phased-approach (approx. 10 Districts per phase) by 2022.

Justification
UNICEF presented three options for use of additional funds to DFID on 30 May 2018, and a decision was taken that the additional fund will be used for provision of job aid tools to IZU in 2 districts where no active support has been provided in order to fully equip them with knowledge, skills and job aid materials to implement their roles and further benefit children and their communities.
Equipping IZU with job aid tools is one of the core components of the IZU operationalisation efforts and contributes to quality service delivery of IZU. The minimum IZU job aid package includes an ID badge, a bag, IEC materials, a reporting template, stationary, an umbrella, a mobile phone and minimum airtime. So far, these items have been provided to IZU in the Districts where Save the Children is operating. It is reported that these tools play a critical role in facilitating IZU works in conducting home visits, timely communication, reporting cases, referring children to appropriate social services in time and conducting follow-ups. Especially, providing IZU with mobile phones and minimum airtime is necessary as NCC plans to digitalise the current IZU reporting and data collection system through use of mobile phone technologies across the country by next year. In NCC’s 2019 budget plan, $105,882 have been earmarked to procure mobile phones and airtime for IZU in 10 districts without any implementing partner support; however, additional supports for IZU from districts where no support has been provided or committed will significantly contribute to scaling up IZU operationalisation by fully equipping every IZU with minimum job aid tools which allows harmonised IZU services across the country. With the additional financial support from DFID, 1,476 IZU from Kayonza and Kamonyi districts can directly benefit, where currently no active support exists and needs additional supports.

Objective
The overall objective of this concept is to scale up the operationalisation of community-based child and family protection volunteers “Inshuti z’Umuryango” in Rwanda to effectively prevent and respond to violence, abuse, neglect and exploitation against vulnerable children. This will be done through providing a basic job aid package to 1,476 IZU from Kayonza and Kamonyi Districts where no active support is provided. Specific objectives include the following:
1. To empower IZU by equipping them with necessary knowledge, skills and materials to conduct their roles
2. To improve practices of IZU to prevent and address violence against children and other child protection needs in communities including gender-based violence.

Specific activities
- Review items and identify materials that need to be branded with DFID logo
- Sign a DFID visibility statement with a list of materials that need to be branded with DFID logo
- Brand the soft-copy materials with UK aid logo where appropriate before production
  [note] Details will be listed on the UK aid visibility statement to be signed by DFID and UNICEF.
- Identify a supplier to procure a minimum job aid package for IZU
- Print and procure a minimum job aid package for 1,476 IZU from Kayonza and Huye Districts
1. Do’s and Don’ts leaflet;
2. Reporting template;
3. Referral pathway;
4. Stationary;
5. ID card;
6. Bag;
7. Umbrella;
8. Mobile phone with a sim card; and
9. Air time
- Distribute the materials to 1,476 IZU during a coordination meeting
- Monitor the usage and obtain feedback during a field visit and the next coordination meeting

Targets
- 1,476 Inshuti z’Umuryango from Kayonza and Kamonyi Districts will directly benefit by receiving a comprehensive job aid package.
- 19,800 households and 5,904 children will directly benefit from IZU interventions mainly through household visits and provision of direct basic psychosocial supports. 79,200 children will indirectly benefit from IZU services through household sensitisation and community awareness raising among others.
  [note] Assuming that 20 households will be visited per village
  [note] Assuming that 4 children per household will be directly supported by one IZU by the end of this year.
  [note] Assuming that there are 4 children per household supported by IZU.

Expected results from additional funding
Through the additional funding, the UK Government will support the scale up of the operationalisation of IZU while building on current gains of the IZU initiative from the phase I operationalisation districts in order to deliver sustainable results for all children in Rwanda with a focus on the most vulnerable. This will contribute to the programme outcome: Reduced prevalence of GBV and strengthened community-level mechanisms for the prevention of violence against women, girls and boys in programme sectors.
More specifically, the funding will contribute to the provision of a comprehensive job aid package to IZU in 2 districts (Kayonza and Kamonyi) of Rwanda, where IZU have not been equipped with the comprehensive job aid package. It is expected that 1,476 IZU are equipped with necessary tools and become functional to provide adequate and timely child protection services. Once equipped with the skills set and tools to carry out their roles and responsibilities, properly monitored and supervised, IZU will play a major role in preventing, responding and referring child protection concerns, thereby significantly reducing violence against children in homes and communities. Approximately 19,800 households and 5,904 children will be directly benefiting from IZU services (home visits, psychosocial supports, reporting, referrals and follow-ups), and 79,200 children will be indirectly supported through the additional funding. The following key indicators will be monitored and reported against the log frame:
Output 1: Best practice community-based GBV and VAC prevention curriculum developed and implemented
Indicator 1.3: Number, types and frequency of interventions taken by Community Activists and VAC Friends of the Family to promote gender equality and challenge GBV and VAC in programme sectors
- # of household visits conducted to deliver positive parenting skills to reduce violent disciplinary practices
- # of children provided with basic psycho-social support
- # of child violence, abuse and exploitation cases reported and followed up

Procurement and distribution plan
UNICEF Child Protection Team will work with UNICEF Supply to directly contract local suppliers to procure job aid tools. NCC will be in charge of distributing the items to Districts and Sectors through appropriate channels, such as the upcoming IZU in-service training or IZU lower level coordination meeting planned in August 2018.

Partners
UNICEF has been working with the Government of Rwanda mainly through the Ministry of Gender and Family Promotion and the National Commission for Children to oversee the implementation of activities and the achievement of results under the Inshuti z’Umuryango programme.
For operationalisation, UNICEF and NCC have been partnering with Save the Children since 2016 in order to pilot the IZU operationalisation and build evidence to scale up in the first phase 11 Districts. Among others, NCC professional social workers and psychologists, local authorities at District/Sector/Village levels in charge of child protection and social affairs, IZU and community members are strategic partners engaged in IZU operationalisation. Others include members of the multi-sectoral child protection network at Districts and Sectors, including representatives from different sectors (Education, Governance, Health, Maison d’Acces a la Justice, Nutrition, Social Protection, Disability, Social work) and others such as the Rwanda National Police, the Joint Action Development Forum (JADF) coordinator as well as representatives of organisations working closely with child protection, including faith-based organisations.
To implement this plan of action, UNICEF will engage with the following partners: NCC/MIGEPROF, Save the Children, decentralised government authorities, IZU and community members in programme districts.

Proposed timeline and cost
	Activity	Proposed timeline	Cost
01	Review items and identify materials that need to be branded with DFID logo	Mid June 2018	0
02	Both parties to sign a DFID visibility statement with a list of materials that need to be branded with DFID logo	Mid June 2018	0
03	Brand the soft-copy materials with UK aid logo where appropriate before production	End June 2018	0
04	Identify a supplier to print and procure a minimum job aid package for IZU	June – July 2018	0
05	Print and procure a minimum job aid package (and production of branding stickers) for 1,476 IZU from Kamonyi and Kayonza Districts	August 2018	$42,370 *for breakdown see Annex I
07	Distribute the materials to IZU during a coordination meeting	End August 2018	0
08	Monitor the usage and obtain feedback from IZU during a field visit and the next coordination meeting	September-December 2018	0
	Total		$42,370 (£32,268)

Risk management
The proposal presents the following risks in terms of implementation:
- Currently all tools are not branded with DFID logo.
- Delays relating to procuring items
- Potential fiduciary risks associated with procurement processes
To align with the DFID visibility guideline, the DFID visibility statement will be prepared by UNICEF including a list of all materials that will be branded with DFID logo and signed by both parties to properly acknowledge funding from the UK government in all IZU materials. All materials will be updated with DFID logo where appropriate.
Also, UNICEF child protection staff will collaborate with UNICEF Supply to identify suitable companies for timely procurement. To mitigate potential fiduciary risks associated with procurement processes, UNICEF Child Protection and Supply will ensure procurement processes are done in alignment with the UNICEF anti-corruption and fraud policy in order to mitigate any potential fiduciary risks that may come with procurement processes.

Monitoring plan and sustainability
UNICEF and NCC will monitor the usage of materials provided through DFID grant and obtain feedback from IZU during a field visit and the next coordination meeting throughout this year. Kayonza and Kamonyi Districts are selected as districts of intervention in order to scale up IZU operationalisation since they are not included in the phase I operationalisation districts. For sustainability, UNICEF and NCC will prioritise these districts to be included in the phase II districts of the IZU operationalisation programme (planned: Q4 2018 and forward) to ensure that IZU from Kayonza and Kamonyi Districts are properly guided and mentored to maximise the usage of job aid materials provided through the generous support of DFID.

Annex I. Budget breakdown
Activity	Item	Unit qty	Unit cost	Cost	Total cost
Print and procure a minimum job aid package for 1,476 IZU from Kayonza and Kamonyi Districts	Do’s and Don’ts leaflet	1,476	RWF 100	RWF 147,600	RWF 36,752,400 ($43,238)
	Reporting template	1,476	RWF 100	RWF 147,600
	IZU poster	1,476	RWF 100	RWF 147,600
	Referral pathway	1,476	RWF 100	RWF 147,600
	Stationary (a registration book, a pen, a plastic folder)	1,476	RWF 2,000	RWF 2,952,000
	ID card	1,476	RWF 1,500	RWF 2,214,000
	Bag	1,476	RWF 3,000	RWF 4,428,000
	Umbrella	1,476	RWF 4,000	RWF 5,904,000
	Mobile phone with a sim card	1,476	RWF 8,000	RWF 11,808,000
	Airtime	1,476	RWF 6,000	RWF 8,856,000
Total					$42,370 (£32,268)
[note] Actual unit cost will be determined through the bidding process.