Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.
Title: Migrating out of Poverty (MOOP) - Research Programme Consortium
Programme Value: £6,425,233.		Review Date: October 2016
Programme Code: 114334-101	Start Date: Implementation started Sept 2011 (after year inception)	End Date: June 2017

Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	68.75	B	A	A	A+
Risk Rating	High	High	Medium	Low	Moderate

Summary of progress and lessons learnt since last review:
The Migrating out of Poverty (MOOP) Research Programme completed the majority of its research projects this year and progressed discussions on a project extension with DFID. MOOP largely met expectations across programme areas, and exceeded a number of indicators on research output and uptake. MOOP has already exceeded end-of-programme milestones for 5 logframe indicators.
MOOP completed 27 projects and is in the process of completing the remaining 3. MOOP’s 5 research teams have delivered 59 publications this reporting year, and 5 quantitative datasets are now available on the MOOP website (for Bangladesh, Ethiopia, Ghana, Indonesia, and Zimbabwe). MOOP’s research is in high demand with a cumulative total of 5,875 downloads, 153 citations and 119 dataset requests.
MOOP significantly exceeded end-of-programme public engagement targets by reaching a cumulative total of 2,140 key stakeholders at 262 conferences, seminars, workshops and consultations. MOOP also published 53 news items in newspapers and blogs, increased its social media presence, and reached 2,435 followers (from 1,800 last year) on the @MigrationRPC Twitter account. Public engagement highlights include:
- Consultation on Bangladesh’s Draft Citizenship Bill 2016 in collaboration with UNHCR.
- Launch of the national migration policy of Ghana that was informed by MOOP research.
- Briefing of DFID’s Permanent Secretary on MOOP’s research findings.
- MOOP researchers’ participation in the 2015 Global Forum on Migration and Development in Istanbul.
Summary of recommendations for the next year:
1. Conduct consultations across DFID on MOOP research findings, quality and policy relevance of research outputs to inform the planned extension of the programme (DFID by March 2017)
2. Develop a research uptake and media engagement strategy and increase dissemination beyond target countries (MOOP by January 2017)
3. Update milestones for indicators that have been significantly exceeded - to increase ambition in future years incl. indicators 1.3, 2.1, 2.2, 2.3, 3.3 (MOOP by December 2016)
4. Use DFID’s new Value for Money Framework and Risk Framework to assess the programme and report findings in the next annual report (MOOP by June 2017)
Progress on recommendations from last year’s review:
MOOP and DFID considered options for a costed extension for the period post June 2017. MOOP submitted a proposal to build on the current themes of the programme and added an additional theme on irregular migration patterns that is a high policy priority for DFID/HMG. MOOP also conducted a mini-gender audit and found that at least half of the research outputs comply with the ‘sensitive to gender guidelines’ produced by MOOP’s Gender Lead. MOOP reported challenges in increasing feedback response rates and recruiting additional interns to meet the 2017 targets. Feedback response rates were 55% this year and MOOP will not achieve the planned target of 17 interns by 2017 (see indicators 2.2 and 3.1 for details). DFID accepts that despite MOOP’s efforts, the revised intern strategy was only partially successful, but did not limit MOOP’s capacity to build impact.

A. Introduction and Context

DevTracker Link to Business Case:	2137641
DevTracker Link to Log frame:	4619082

DFID agreed a £6,425,233 contract with the University of Sussex (2011-17) for the Migrating out of Poverty (MOOP) Research Partnership Consortium (RPC). The RPC generates new, high quality research related to migration and poverty, creates new datasets, engages policy makers, and builds capacity. Its research aims for a better understanding of the relationship between migration and poverty, and the factors that mediate it. This builds on the work of the DFID-funded University of Sussex Development Research Centre on Migration, Globalisation and Poverty (2003-09).
MOOP works in five regions – East, West, and Southern Africa, South Asia, and Southeast Asia. The lead partner is the Centre for Migration Research at the University of Sussex in the United Kingdom, with five other core partners: The Refugee and Migratory Movements Research Unit (RMMRU) in Bangladesh, the Centre for Migration Studies (CMS) in Ghana, the Asia Research Institute (ARI) at the National University of Singapore, the African Centre for Migration and Society (ACMS) at Witwatersrand University in South Africa, and the African Migration and Development Policy Centre (AMADPOC) in Kenya. MOOP also has associate partners across the regions.
The intended results are:
Impact: State and societal actors will have utilised a strong evidence base on internal and regional migration to produce pro-poor migrant policies in at least 5 countries in 5 regions.
Outcome: Improved access to and demand for internal and regional migration evidence by targeted development policy stakeholders in at least 5 countries as a result of an improved understanding of migration and poverty linkages, and how this can be used to maximise benefits of migration for development and minimise risks or negative impacts.
Outputs:
1. New research: A coherent body of high quality, policy relevant new knowledge on internal and regional migration. This will include new open access databases to provide a critical resource to migration researchers globally. It will also include at least 35 research outputs that specifically address gender dimensions, with a focus on women and girls.
2. Policy engagement: Improved engagement and dialogue with key stakeholders, to promote research uptake and understanding of findings related to internal and regional migration and poverty linkages.
3. Capacity: Enhanced strategic capacity of consortium members to conduct research, and enhanced capacity of key stakeholders in government and civil society to participate in policy framing processes.
Southern governments and international donors have become more aware of the importance of migration for poverty reduction. However, they lack evidence and data to help maximise the benefits of migration and minimise potential harms. Existing datasets do not adequately cover the types of migration that poor people engage in, the drivers of migration, and the economic and social impacts on both receiving and exporting communities. MOOP helps to address this research gap by providing high quality, open access evidence on internal and international migration at local, national and international levels, to inform more effective policies.
Migration is now a higher policy priority for HMG than it was at the start of the MOOP contract, with record numbers of migrants, displaced people and trafficking victims. The UK is facing unprecedented challenges in addressing this mobility and targeting aid effectively to uphold principles of decent work and justice while fighting forced migration and exploitation. The Secretary of State is a member of the Prime Minister’s Government taskforce on modern slavery and £33 million has been earmarked from the UK aid budget to tackle the problem. While MOOP was not set up with a focus on modern slavery, the programme is relevant to understanding the context in which exploitation occurs. MOOP generates evidence on the impact of undocumented migration on poverty in source areas, to improve understanding on how the effects of economic and political crises and regional migration policy shape migrations flows, pathways, and development.

## B: PERFORMANCE AND CONCLUSIONS
Annual outcome assessment:
MOOP exceeded expectations for all 4 outcomes, while 2 outcomes (outcomes 1 and 4) met the end-of-programme targets already this year. The number of policy documents reflecting the new understandings of migration developed by the consortium more than doubled this year and MOOP reported a cumulative total of 37 documents (outcome 1). MOOP’s annual survey (response rate 28%) found that the majority of policy actors surveyed (82%) continue to benefit from MOOP research and that almost half of the respondents (47%) recognised the importance of migration and its impact on gender and social relations (outcome 2). Southern partners also continue to benefit from MOOP research, with a cumulative total of 426 requests to Southern partners to participate in government, donor and/or civil society policy framing processes on internal and regional migration (outcome 3). MOOP research is in high demand and exceeds end-of-programme expectations with a cumulative total of 5,875 downloads, 153 citations and 119 database request (outcome 4).
Overall output score and description:	A+ (moderately exceeds expectations)
Over the three outputs, MOOP exceeded the milestones for 5 indicators, is on track for 4, and off track for 1 (the number of interns). MOOP met the indicators related to research output, and performed particularly well on the number of publications and completed projects. Policy briefs and other synthesis outputs targeted at policy-makers are still limited but the number will increase in the final year. MOOP made good progress on indicators related to research communication and reported high numbers of events – already exceeding the end of project target.
MOOP’s research has influenced government policies in Africa and Asia. Examples of MOOP’s research impact include:
- Informing Malaysia-Bangladesh bilateral policy to allow migration via private labour contracts (contracts were previously government-to-government only, ignoring the biggest drivers of large flows – around 0.5 million people per year – that help deliver large mutual economic benefits).
- Influencing the Memorandum of Understanding between Saudi Arabia and Bangladesh to allow female domestic workers to retain mobile phones for safety and welfare – benefiting large numbers of vulnerable Bangladeshi migrants.
- Advising the Government of Singapore on introducing a mandatory day off per week for domestic workers – now a policy with tangible benefits to around 200,000 migrants.
- Serving on Ghana’s inter-ministerial committee on migration, with MOOP research informing Ghana’s National Migration Policy, including policies on internally displaced people.
- Developing a formal partnership with government of South Africa to provide migration data and policy advice – in part in response to attacks on migrants, and misinformation about migration.

Key lessons:
- Comprehensive gender analysis needs to be planned from the start: MOOP’s grants predate the 2014 UK gender act and gender was not routinely addressed in all proposals, though the gender audit found that some projects/outputs include a systematic and useful gender analysis. To be comprehensive, gender analysis needs to be planned from the start and included in all relevant tools such as interview guides and questionnaire design.
- Gated access to qualitative data may not facilitate its wider use: MOOP found it challenging to anonymise the 17 qualitative datasets for online publication while maintaining the analytical value of the data, and with DFID’s agreement instigated a gated access policy. However, there were no requests for qualitative data this year. MOOP is therefore working on a new strategy to facilitate reasonable access to the qualitative datasets for bona fide researchers.
- More rigorous project management has reduced delays: MOOP reported slight delays in project implementation and introduced a more rigorous project management process to reduce delays. The majority of research projects are now completed (27 out of 31).
- Multi-partner meetings promote research coherence: MOOP introduced multi-partner meetings for consortium partner staff to ensure more research coherence and knowledge exchange between research themes. The meetings contributed to more coherent research in Phase 2 of the programme and will inform the planned synthesis papers.
Key actions: See recommendations above.
Has the log frame been updated since the last review? Yes. Indicator 2.4 (number of media items published) was added to the logframe and the output wording was revised for all 3 outputs.

## C: DETAILED OUTPUT SCORING

Note: The logframe does not contain milestones for 2016 and the programme is considered to be “on track” if it achieved the mid-point between the 2015 and 2017 milestones.

Output Title	High quality and policy relevant knowledge on internal and regional migration
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		Yes[1]	Impact weighting % revised since last AR?	No
[1] DFID introduced a new risk framework with four categories (minor, moderate, major, severe) to replace the previous risk framework (low, medium, high)

Indicator	Milestone 2 / 2015	Milestone 3 / 2017	Progress
1.1 # of internal and regional databases made available to the research community (i) qualitative and (ii) quantitative	3 Qual / 3 Quant	6 Qual / 5 Quant	On track – 5 quantitative datasets, 17 qualitative datasets (c)*
1.2 # of internal and regional migration policy relevant projects comprising research and related engagement activities completed according to plan	18	29	Exceeded – 27 projects completed
1.3 # of research outputs: / i) peer reviewed articles, / ii) working papers, / iii) policy briefs / iv) conference papers/presentations, book chapters	3, 27,12,15	12,40,15,25	Exceeded - 18(c)/9(a) journal articles, 42(c)/13(a) working papers, 33(c)/13(a) policy briefs, 56(c)/32(a) conference papers/presentations and book chapters*
1.4 # of research outputs that significantly address gender dimensions, including a focus on women and girls: / i) peer reviewed articles, / ii) working papers, / iii) policy briefs / iv) conference papers/presentations, book chapters	1,10,6,7	6,15,10,15	Exceeded – 8(c)/6(a) journal articles, 25(c)/10(a) working papers, 19(c)/13(a) policy briefs, 28(c)/21(a) conference papers /presentations and book chapters*

* (c) = cumulative, (a) = annual
Key Points:
1.1	MOOP made 5 quantitative datasets available on the MOOP website (Bangladesh, Ethiopia, Ghana, Indonesia, and Zimbabwe)[2], accompanied by a User Guide and a Household Questionnaire. MOOP reported increased demand for quantitative datasets, with 118 dataset requests this year (there was just 1 request last year). The milestone for qualitative datasets is partially achieved as datasets are not available on the website due to challenges of anonymising data without making the content unsuitable for further analysis. MOOP’s interim solution is ‘gated access’ - offering qualitative datasets upon request via email[3] to bona fide researchers. The website does currently not state what types of qualitative datasets are available and what the vetting criteria are. MOOP is yet to receive email requests and is reconsidering the current access strategy to increase demand for its qualitative data.
[2] Quantitative datasets are available here: http://migratingoutofpoverty.dfid.gov.uk/research/migrationdata
[3] See Appendix 1 for a list of qualitative datasets that are available upon request
1.2	MOOP completed 27 projects. To date, 95% (18 out of 19) of Phase 1 projects and 75% (9 out of 12) of Phase 2 projects are completed. The Phase 1 qualitative survey for Bangladesh had to be dropped due to capacity issues. The 3 remaining Phase 2 projects will be completed in the next quarter. In addition, MOOP has 3 opportunistic projects near completion from within the Secretariat team. Engagement activities are ongoing and will be the main focus in the final phase of the programme (see indicator 2.1 and 2.2 for details).
1.3	MOOP exceeded the 2017 targets for all sub-indicators: The consortium produced 9 peer-reviewed journal articles, 13 working papers, 13 policy briefs, as well as 32 conference papers/presentations this year. In addition, the research consortium produced research reports (6), visual and social media (23), and other papers indirectly related to MOOP projects (17) that are currently not captured by the indicator. Publication numbers vary across projects but the majority of projects (4 out of 5) contribute to at least 3 types of publications[4]. The most productive partner this year was the Centre for Migration Studies that produced 44% of all knowledge outputs and the majority of peer-reviewed publications. Only half of the projects have contributed to the dissemination of findings through policy briefs and conference papers.
[4] ACMS is the only exception, it only produced 2 working papers this year
1.4	MOOP partners reported that 70% of key research outputs[5] address gender – they include peer-reviewed journal articles (6), working papers (10), policy briefs (12), as well as conference papers/presentations and book chapters (21). MOOP complemented the self-reports with spot-checks of working papers to assess how gender analysis was conceptualised, operationalised and implemented, which questions were raised, and which themes were explored. About half of the papers significantly analysed gender and the Intra-Household Dynamics project demonstrated particularly serious commitment. The other papers could have improved gender sensitivity by integrating gender issues in surveys, interview guides and research designs from the onset. Almost half of the conference presentation this year (16 out of 26) had a gender dimension. For example, theme leaders were invited to speak about the negotiation of gender relations through migration at the Freedom Fund and gender differences in remittances at a British Council funded event.
[5] Journal articles, working papers, conference presentations, policy briefs, book chapters
Recommendations:
- Data accessibility: Develop future plans of making the qualitative datasets available with the aim to implement them in the extension phase incl. increased transparency by publishing descriptions of all available datasets and the vetting criteria on the MOOP website and including an online request form for qualitative data with relevant screening questions (MOOP by December 2016)
- Support policy dissemination: Develop strategies to support partners that underperform on some sub-indicators incl. journal articles, working papers, policy briefs, conference papers, book chapters (MOOP by June 2017)

Output Title	Effective engagement and dialogue around research findings by policy makers, practitioners and the media
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Yes[6]	Impact weighting % revised since last AR?	No
[6] DFID introduced a new risk framework with four categories (minor, moderate, major, severe) to replace the previous risk framework (low, medium, high)

Indicator	Milestone 2 / 2015	Milestone 3 / 2017	Progress
2.1 # of external events attended by PRC partner staff in which pro-poor approaches to regional and internal migration are discussed.	70 (cumulative)	100 (cumulative)	Exceeded – 262 (c)/72 (a) external events*
2.2 # of key stakeholder representatives participating in RPC external-facing events proportion surveyed (& % of these reporting enhanced understanding of pro-poor approaches to migration)	600, / 60%, / 70%	900, / 75%, / 75%	Exceeded – 2140(c)/655(a) events*, 55% stakeholders surveyed, 76% reported enhanced understanding
2.3 # of RPC external facing events sensitive to gender dimensions of migration	50 (c)	75 (c)	Exceeded – 81(c)/21(a) events*
2.4 # of media items published which promote MOOP research			On track – 53 media items published

* (c) = cumulative, (a) = annual

Key Points:
2.1	MOOP RPC partner staff attended a cumulative of 262 activities in which pro-poor approaches to migration were discussed, significantly exceeding the 2017 logframe target (100 events). This year’s activities ranged from high-level panels and policy events with UN agencies (e.g. ILO, OECD, UNECA, UNDP) and talks or conferences organised in Africa, Europe, Asia and North America (e.g. University of Zimbabwe, University of Pretoria, University of Singapore, University of Melbourne, University of Berlin) to small-scale consultation with civil society actors and students. Highlights from this year’s engagement activities include the participation of MOOP researchers in the 2015 Global Forum on Migration and Development in Turkey, the launch of Ghana’s National Migration Policy and a briefing to the Permanent Secretary of the United Kingdom’s Department for International Development.
2.2	MOOP significantly exceeded expectations for the programme, with a cumulative total of 2,140 key stakeholders participating in RPC external facing events (end-of-programme milestone is 900). This year’s activities included engagements with representatives from the South African and Ghanaian Departments of Labour, Swiss and UK development agencies, Embassy of Denmark, and unions (e.g. International Union of Food and Agriculture, Union of Informal Workers Association). For example, the migration industry project hosted a dissemination workshop that was attended by 76 stakeholders from government and actors in the migration industry (e.g. employers, recruitment agencies) to discuss migration networks in Ghana. MOOP surveyed 55% (360 out of 655) of the key stakeholders this year and reported challenges in increasing the response rate to feedback. Of those surveyed, 76% (274 out of 360), reported enhanced understanding of pro-poor approaches.
2.3	MOOP held a cumulative total of 81 RPC external facing events sensitive to gender dimensions of migration and exceeded the end-of project target (75). For example, the research director was invited to speak at a number of high-profile international events on migration hosted by the FAO, UNESCO, the University of Oxford, and the Nordic Southeast Asia Network on Migration. She presented emerging findings from MOOP research, highlighting the different drivers for male and female migration and how gendered identities in labour markets influences migration outcomes.
2.4	This reporting year, 53 news items were published in newspapers and blogs. Media outlets include the Daily Maverick of South Africa, the Kedaulatan Rakyat of Indonesia, The Daily Star of Bangladesh, and the Star of Malaysia. MOOP also increased its social media presence and the @MigrationRPC Twitter account currently has 2,435 followers, a significant increase from last year’s 1,800. The number of ‘Likes’ on the MOOP Facebook page nearly doubled between October 2015 to September 2016, from 242 followers to 534 followers. The ARI blog[7] that started in July 2015, has attracted 1,775 unique visitors to date.
[7] ARI blog: https://arimoop.wordpress.com/
CMS also continue to engage their network of journalists in Ghana, the Media Network on Migration (MENOM), to disseminate and share research findings from MOOP using the print media, radio, televisions and social media. The 26 MENOM members were invited to all MOOP/CMS organised activities such as policy dialogues, dissemination workshops, stakeholder meetings and during celebrations of international days such us International Migrant’s Day, International Women’s Day and International Domestic Work Day among others.
Response to issues raised in previous reviews:
DFID introduced MOOP to World Bank WDR 2017 team on ‘Governance and Law’ as a potential policy influencing target for MOOP research.
Recommendations:
- Publish links to news stories online: Make links to news articles and blogs available on the MOOP website and update them periodically (MOOP by January 2017)
- Set milestone for indicator 2.4: Set 2017 milestone for the number of media items published which promote MOOP research (MOOP by December 2016)

Output Title	Strengthened capacity of consortium members and partners to design and deliver academically rigorous and policy relevant research, and to share findings with external audiences
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		Yes[8]	Impact weighting % revised since last AR?	No
[8] DFID introduced a new risk framework with four categories (minor, moderate, major, severe) to replace the previous risk framework (low, medium, high)

Indicator	Milestone 2 / 2015	Milestone 3 / 2017	Progress
3.1 # of interns reporting improved capacity to do research (or engage with it)	11	17	Off track – 12(c)/ 2(a) interns reporting improved capacity*
3.2 # of consortium partner staff reporting improved capacity as a result of attending a training course, placement or fellowship	40	50	On track – 46(c) /4(a) consortium partners reporting improved capacity*
3.3 # of boundary partners and key stakeholder representatives who report improved capacity after participation in consortium training sessions	300	400	On track – 510 boundary partners and key stakeholders (c)*

* (c) = cumulative, (a) = annual

Key Points:
3.1	A cumulative total of 12 interns reported improved capacity to do and/or engage with research, while two are about to finish and report back. With current plans, there will be 15 interns over the life of the programme and the 2017 target will not be met. The main challenge was that MOOP did not receive enough applications from qualified applicants and some qualified candidates dropped out of the application process. One likely explanation is that the internships were poorly budgeted and not attractive for competitive candidates and that the timing of recruitment was not ideal.
Interns are gaining valuable work experience in research uptake and communications, analysing country or region specific migration policies and practices. All have produced blogs about their experience of working on migration with MOOP. One intern presented preliminary findings from an analysis of the Ethiopian household survey at a diaspora conference in London in July 2016 and was nominated by the participants for the best presentation. Her research was published as Working Paper 41 on the MOOP website.
3.2	Four consortium partner staff reported improved capacity as a result of attending a training course, placement or fellowship: ARI’s staff attended classes on children and young people focusing on theories and concepts of childhood and youth, CMS staff attended a workshop organised by EU/ ECOWAS aimed at strengthening capacity on migration management, ACMS staff attended a training on digital storytelling as part of research uptake capacity strengthening, and RMMRU staff hosted several capacity building events for boundary partners working with migrants. Data is generated from reviews undertaken by partners in July/August each year and excludes Secretariat members. However, members of the Secretariat have also developed their capacity through working with partners. For example, Secretariat staff participated in a media training on migration with journalists by CMS in Ghana and develop a strategy to engage journalists in the lead up to the MOOP conference.
3.3	No boundary partners or key stakeholders in government reported improved capacity after participation in consortium training sessions, because MOOP did not sponsor any such sessions this reporting year. However, MOOP already exceeded the 2017 target last year and is on track with this indicator. In 2015, 510 boundary partners reported improved capacity.
Recommendations
Adjust milestone for indicator 3.1: Consider measures for the extension of the programme to make the internship programme more attractive for qualified candidates through training opportunities, travel schemes, etc. (MOOP by January 2017)
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Key cost drivers are direct and indirect staff costs, travel costs, research consumables and related transport costs. The University of Sussex is responsible for overall project management of the consortia partners including financial management. All consortium partners have well established financial systems which ensure that DFID funds are accounted for on an actual spend basis.
VfM performance compared to the original VfM proposition in the business case
VfM performance is in line with expectations, overall the programme is on track to meet targets, and its intended purpose. MOOP performs well on value for money and the agreed programme costs are in line with expectations and refined annually in MOOP’s budget forecasting.
Assessment of whether the programme continues to represent value for money
The programme continues to represent good value for money. Key achievements along the four dimensions of DFID’s Value for Money Framework include:
- Economy: The introduction of computer assisted personal interviewing has speeded up data collection and reduced staff time, resulting in quicker and cheaper delivery of data to the research team.
- Efficiency: Use of an Excel-based management tool has improved the team’s ability to ensure delivery of outputs across all projects, identify problem areas and to take timely action. Increasing use of payment by results has incentivised partners to become more proactive in meeting their deadlines.
- Effectiveness: The team is engaging with a wide range of policy actors through events and contributed to the development of national migration policies and the introduction of policies supporting migrant workers (see output 2 for details).
- Equity: Most of the research is led by Southern partners as lead authors on the RPC working papers. The gender audit shows that the majority of MOOP’s staff are women and that a strand of MOOP’s research on intra-household dynamics focuses explicitly on gender.
Quality of financial management
The overall budget is £6,425,233, which the University of Sussex manages within its own financial regulations, ensuring that partners adhere to good practice standards incl. well-established cost monitoring processes. Total programme spend to date is £5,525,458 (including the inception phase) with an actual spend of £957,572 within this reporting period. This spend was within a variance of 8.4% of the £1,048,325 forecast for the period.
The University of Sussex proposes an annual budget to DFID each year along with a quarterly financial forecast of predicted spend which is used to monitor/measure financial performance. DFID is advised in advance as the project progresses if any changes are required for (un)planned activities.
Payments are made quarterly to reimburse the University of Sussex on actual spend, which ensures funds are used appropriately against the agreed budget items. The University of Sussex has introduced strong monitoring of expenditures and has challenged any inappropriate expenditure. The university audits all partners and ensures that they have satisfactory internal procedures to monitor expenditure. A portion of the budget is paid to project partners in local currency and exchange rate movements will be accounted for within the budget variance.

Date of last narrative financial report	Not applicable
Date of last audited annual statement	Not applicable

E: RISK

Overall risk rating:
Moderate (using DFID’s new 4-point Risk Framework)
Overview of programme risk:
The risks remain similar to last year, but have mostly been effectively mitigated. A number of low- to medium-level risks were identified at the design stage, with the overall risk changing little over the review period. The key risks are:
- Exchange rate fluctuations: The recent fall in the Sterling value has affected the budget of the Bangladesh partner and may have other unforeseen consequences for the research programme. The MOOP Secretariat is monitoring this closely.
- Delays in programme implementation and underspend: MOOP has introduced a far more rigorous project management process that has substantially reduced risks. Thus, while there have been slight delays, the research projects are now largely complete.
- Misuse of funds: MOOP has introduced strong monitoring of expenditures and has challenged any inappropriate expenditure. Partners have to be audited and MOOP is ensuring that all have satisfactory internal procedures to monitor expenditures.
- Communicating policy-sensitive issues: Migration’s political profile and sensitivity has again risen this year and there is a risk that research results will not be used by policy actors. MOOP developed uptake plans and monitors the policy context to engage key actors strategically. Despite the challenges MOOP continues to engage with policy makers, including at the request of HMG.
- Reputational risk: Given the sensitivity around migration there is a risk that research uptake activity could be perceived as advocacy. MOOP mitigates this risk through a strong focus on research quality and communicating evidence rather than advocacy.
Outstanding actions from risk assessment
No outstanding actions. Risks are being monitored and mitigated.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The programme is progressing according to its contracted schedule and revised logframe. No contract amendments have been issued throughout this review period.
Performance of partnership (s)
Not applicable.
Asset monitoring and control
There are no project assets to record on an asset register.

G: CONDITIONALITY

Update on partnership principles	Not applicable. MOOP is a multi-country research programme, which does not provide funding through country-government systems.

H: MONITORING & EVALUATION

Evidence and evaluation:
The Annual Review team held a formal meeting with MOOP at the University of Sussex in October 2016 to discuss outputs against milestones (including successes/challenges), risks (and how these are being managed), and financial management. Follow-up clarifications questions were addressed by MOOP’s research team. The DFID team conducted a desk-based review of key documents (see list below). Following discussions, MOOP and DFID agreed on a commentary on progress against logframe indicators, changes to the logframe, and summary recommendations from this review. This Annual Review has been shared with MOOP and recommendations will be followed up at the next project meeting.
Monitoring progress throughout the review period:
MOOP’s data collection for logframe monitoring includes routine collection of data for monitoring progress at outcome and impact level. These are detailed in the logfame reporting section of MOOP’s annual report. DFID’s SRO and the MOOP Secretariat hold phone meetings at least quarterly to discuss overall progress on the programme, any individual project issues or problems and notable achievements. This helps ensure DFID is engaged with MOOP and enables DFID to provide input and direction on the programme.
This Annual Review was conducted by DFID staff in the UK:
- GCSD Team Leader and Senior Responsible Owner (SRO) for MOOP, UK
- GCSD Research Manager for MOOP, UK
- GCSD DESA Social Development Adviser, UK
Documents reviewed:
- MOOP Annual Report 2015-2016
- MOOP Annual Review 2013
- MOOP Annual Review 2014
- MOOP Annual Review 2015
- MOOP logframe
- MOOP VfM examples
- MOOP qualitative datasets
- MOOP website
- Selected publications in Appendix 2

Appendix 1: MOOP Qualitative datasets

Project Number	Details	Partner
Old Research
RP001	Indonesian Domestic Workers in Singapore	ARI
RP003	Migration into two slums in Accra	CMS
RP005	Costs of Immigration Enforcement and Perceptions of Local Government	ACMS
RP006	Bangladeshi Construction Workers in Singapore	ARI
RP007	Rohingya	RMMRU
GP001	The regulation of foreign labour intensive sectors of the South African economy: policies and practices	ACMS
GP002	Ethiopia DW and CW	Adamnesh/Amadpoc
GP004	South Asian Labour Attaches	RMMRU
GP010	Indonesia DW and CW	ARI
GP011	Ghana DW and CW	CMS
New Research
RP008	Migration Industry Singapore	ARI
RP010	Intra-HH Dynamics Indonesia	ARI
RP011	Migration Industry Ghana	CMS
RP012	Intra-HH Dynamics Ghana	CMS
RP013	Ghana Counterfactuals	CMS
RP014	Intra-HH Dynamics Bangladesh	RMMRU
RP015	Migration Industry Bangladesh	RMMRU

Appendix 1: MOOP Publications

RPC Working Papers

	Partner and/or Project	Author, title, date	Addresses Gender
WP44	CMS	Awumbila, M, L. Boakye-Yiadom, E. Egger, J. Litchfield, J. Teye, and C. Yeboah. (2016) Gains and Losses from Migration: evidence from migrant-sending households in Ghana (RP13)	Y
WP43	CMS	Awumbila, M., A. Darkwah, & J.K. Teye. (2016) Of Local Places And Local People: Understanding Migration in Peripheral Capitalist Outposts (RP12)	Y
WP42	RMMRU	Rashid, S.R. (2016) Gendered Practices of Remittances in Bangladesh: A Poststructuralist Perspective (Gender Conf)	Y
WP41	Sussex	Abdelmoneim, Y. & J. Litchfield (2016) Does Migration Improve Living Standards of Sending Households? Evidence from rural Ethiopia (GP007)	Y
WP40	RMMRU	Rashid, S.R. & J. Sikder (2016) Choosing a Life: Remittances and Youth Aspirations in Bangladeshi Villages (RP14)	Y
WP39	ACMS	Palmary, I and T. de Gruchy. (2016) Changing Policy: Lessons from the Trafficking in Persons Act (2013) in South Africa (RP17)	Y
WP38	ARI	Koh, C.Y., C. Goh, K. Wee, & B.S.A Yeoh. (2016) Who's holding the bomb? Debt-financed migration in Singapore's domestic work industry (RP08)	Y
WP37	RMMRU	Ashraf, ASM. (2016) Public Policy Formation: A Case Study of Domestic Workers in Bangladesh (RP16)	Y
WP36	ARI	Koh, C.Y., C. Goh, K. Wee & B.S.A. Yeoh, (2016) The Dynamics of Policy Formulation and Implementation: A Case Study of Singapore's Mandatory Weekly Day Off Policy for Migrant Domestic Workers. (RP09)	Y
WP35	ACMS	Misago, J.P. (2016) Migration and Socio-Economic Development in African Cities: The Dual Challenge to the Aerotropolis Project of South Africa's Ekurhuleni Metropolitan Municipality. (RP18)	N
WP34	Sussex	Winters, L. A. (2016) New Zealand’s Recognised Seasonal Employer Scheme: An Object Lesson in Policy Making –But for Whom?	N
WP33	Sussex	Sward, J. (2016) Moving to Greener Pastures? Internal Migration, Land Tenure, and Poverty in Mid-Ghana.	Y
WP32	Sussex	Qui, J. & Wu, Y. (2016) Migration, Consumption Smoothing, and Household Income: Evidence from Thailand	N

Journal articles

Partner	Author, title, date	Addresses Gender
RMMRU / (IHD in India)	Ravi Srivastava and Rajib Sutradhar (2016) Labour Migration to the Construction Sector in India and its Impact on Rural Poverty. Indian Journal of Human Development	N
Sussex	Priya Deshingkar (2016) Towards contextualised, disaggregated and intersectional understandings of migration in India. Asian Population Studies	Y N
CMS	Mariama Awumbila, Joseph Kofi Teye, & Joseph Awetori Yaro, (2016). Social Networks, Migration Trajectories and Livelihood Strategies of Migrant Domestic and Construction Workers in Accra, Ghana. Journal of Asian and African Studies, Vol. ﻿1–15	Y • Y
CMS	Joseph A. Yaro, Mariama Awumbila, Joseph Kofi Teye (2015). The life struggles and successes of the migrant construction worker in Accra, Ghana. Ghana Journal of Geography Vol. 7(2), 2015 pages 113-131	N
CMS	Mariama Awumbila (2015). Women Moving Within Borders: Gender and Internal Migration dynamics in Ghana. / Ghana Journal of Geography Vol. 7(2), 2015 pages 132-145	Y • Y
CMS	Mariama Awumbila, Joseph Kofi Teye, & Joseph Awetori Yaro, (2016). Of silent maids, skilled gardeners and careful madams: gendered dynamics and strategies of migrant domestic workers in Accra, Ghana. GeoJournal, Vol.81 No.3	Y • Y
ARI	Maria Platt, Grace Baey, Brenda.S.A. Yeoh, Chiu Yee Khoo, and Theodora Lam. (2016) Debt, precarity and gender: Male and female temporary labour migrants in Singapore, Journal of Ethnic and Migration Studies. Accepted for publication 26 July 2016.	Y
ARI	Maria Platt, Brenda S.A. Yeoh, K.A. Acedera, Chiu Yee Khoo, Grace Baey and Theodora Lam. (2016) ‘Renegotiating migration experiences: Indonesian domestic workers in Singapore and use of information communication technologies’. New Media & Society, DOI: 10.1177/1461444816655614.	Y
ARI	Brenda S.A. Yeoh., Maria Platt, Chiu Yee Khoo, Theodora Lam and Grace Baey. “Indonesian domestic workers and the (un)making of transnational livelihoods and provisional futures”. Social & Cultural Geography, DOI:10.1080/14649365.2016.1185800.	Y

Briefings for Policy Makers

Partner and/or Project	Title, date	Addresses Gender
RMMRU	RMMRU Policy Brief 15. Impact of Remittances on Education and Human Resource Development: Evidence from Bangladesh	Y
RMMRU	RMMRU Policy Brief 16. Public Policy Formulation: A Case Study of Domestic Workers in Bangladesh	Y
CMS	Migration into Cities in Ghana: The Economic Benefits to Migrants and their Households. July, 2016	Y
CMS	Social Benefits and Losses of Migrating into Cities in Ghana. July, 2016	Y
ARI	The current system is no good: The Challenges of Singapore’s Domestic Work Industry	Y

Conference Papers and Presentations

Partner	Author, title, date	Addresses Gender
ARI	Arlini S.M. 2015. “Migration, Remittances and the Impacts on the Left-behind Family Members: Findings from MOOP Household Survey in Ponorogo-Indonesia.” Paper presented at the MOOP Dissemination Seminar. 3 Nov 2015, Yogyakarta, Indonesia.	N
ARI	Khoo, C.Y., M. Platt and B.S.A. Yeoh. 2015. "Who migrates? Analysing households’ migration decision-making process through ‘gendered geographies of power’". Paper presented at Southeast Asian Studies Regional Exchange Program (SEASREP) Conference. 4-5 Nov 2015, Yogyakarta, Indonesia.	Y
ARI	Platt, M., C.Y. Khoo, B.S.A. Yeoh, T. Lam and G. Baey. 2015. "Migration, class and gender: A perspective from two Southeast Asian countries". Paper presented at Southeast Asian Studies Regional Exchange Program (SEASREP) Conference. 4-5 Nov 2015, Yogyakarta, Indonesia.	Y
ARI	Yeoh, B.S.A. and G. Baey. 2015 “Gendered labour migration regimes in Singapore: Debt, Precarity and Strategy among Male and Female Temporary Labour Migrants”. Paper presented at Southeast Asian Studies Regional Exchange Program (SEASREP) Conference. 4-5 Nov 2015, Yogyakarta, Indonesia.	Y
ARI	Goh, C. and B.S.A Yeoh. 2015. “Managing Low-Skilled Labour Migration in Singapore.” Invited paper to New Paradigms for a Changing Migration Landscape: Conference to Commemorate International Migrants Day. 17-18 Dec 2015, Bangkok, Thailand.	N
ARI	Wee, K. and B.S.A. Yeoh. 2015. “File in, filed away: placement agencies and the mediation of migrant domestic labour in Singapore.” Paper presented at Arrival Infrastructures Workshop, 10-11 December 2015, Brussels, Belgium.	Y
ARI	Yeoh, B.S.A., C. Goh and K. Wee. 2016 “Transnational Care Migration: Perspectives from Southeast Asia”. Invited paper to 6th ADBI-OECD-ILO Roundtable on Labour Migration in Asia: “Safeguarding Labor Migrants from Home to Workplace”. 3-5 Feb 2016, Tokyo, Japan.	Y
ARI	Koh C.Y. and B.S.A. Yeoh. 2016. “Bridging the Citizen/Foreigner Divide: Migrant Worker Activism and the Day-off Campaign in Singapore”. Invited paper to International Conference: Policy and Practice for Migrant Care Workers in Asia. 17-18 March 2016, Taipei, Taiwan.	N
ARI	Yeoh, B. S. A.; Baey, G.; Platt, M.; Wee, K. "Bangladeshi construction workers and the politics of(im)mobility in Singapore." Paper presented at Constructing Asia: Materiality, Labour and Capital in the Making of Urban Landscapes. 12-13 May 2016, Singapore.	N
ARI	Baey, G. and B.S.A. Yeoh. 2016. “Navigating social support in the global encounters: Migrations, precarity and diversity in Singapore”. Paper presented at Joint Conference of Humboldt University of Berlin and National University of Singapore on Diversity Encounters: Intersectional and Post-colonial Perspectives. 24-26 May 2016, Berlin, Germany.	Y
ARI	Arlini S.M., B.S.A. Yeoh, C.Y. Khoo and M. Platt. 2016. "Parental Migration, Education, Remittances and the Educational Impact of Left behind Children: Evidence from Rural Ponorogo, Indonesia". Paper presented at ISA RC28 Singapore Meeting. 26-28 May 2016, Singapore.	N
ARI	Arlini S.M., B.S.A. Yeoh and C.Y. Khoo. 2016. “Migrating for Work or Remaining in School? Youth Decision-making and Aspiration in Rural Ponorogo, Indonesia”. Paper presented to Children on the Move workshop. 10 June 2016, Kyoto, Japan.	N
ARI	Khoo C.Y. and B.S.A. Yeoh. 2016. “Responsible adults-in-the-making: Intergenerational Impacts of parental migration on Indonesian young women’s aspirational capacity”. Paper presented at Children, Family and Migration in East Asia Conference. 7-8 July 2016, Singapore.	Y
ARI	Arlini S.M., C. Goh and C.Y. Khoo. 2016. “Labour Migration and Migrants’ Aspiration: analysing the migration pattern based on social-economic status of households in rural Ponorogo, Indonesia”. Paper presented at 3rd International Sociological Association (ISA) Forum of Sociology. 10-14 July 2016, Vienna, Austria.	Y
CMS	Teye, J. K. Sierra Leone National Migration and Labour Migration Policies: Common Areas of intervention. Paper presented at a Policy Coherence Workshop organized by ICMPD under MIEUX project, The Hub Hotel, Freetown,, 1 July 2016.	N
CMS	Teye, J. K. Migration Management Capacity of the Ministry of Labour and Social Security of Sierra Leone. An assessment report presented at a workshop organized by ICMPD/ILO/IOM/ECOWAS under the DDF Project, The Hub Hotel, Freetown, 30 June 2016.	N
CMS	Teye, J. K. Drivers of Migration Today. Presentation at an Annual Public Forum of the Ghana Academy of Arts and Science, Academy Auditorium, CSIR, Accra, 6 June, 2016.	N
CMS	Teye, J. K, Yaro, J.A and Torvikey, D. Land and Agricultural Commercialisation in Ghana: Emerging Employment and Labour Relations. Paper presented at the 2016 World Bank Conference on Land And Poverty, The World Bank - Washington Dc, 14-18 March 2016	N
CMS	Teye, J. K and Alhassan O. Diaspora Engagement Programmes in Ghana. Presentation at a Consultative Meeting on the Diaspora Engagement Policy with the Ghanaian Diaspora in Nigeria, 15-18 Jan 2016, Ghana Consulate, Lagos, Nigeria.	Y
CMS	Teye, J. K., Owusu, K and Dzifa Torvikey. Effects of Climate Change/Variability on Fisheries and Fishing Communities along the Coast of Ghana. Paper presented at a Regional Conference on New Regional Formations: Rapid environmental change and migration in coastal areas, Yiri Lodge, University of Ghana, Accra, 17-18 Nov 2016.	Y
CMS	J.K Teye (2015) Patterns, Trends and Development impacts of migration at National (Ghana), regional and global levels. At International Migration, Inter/national Security and Human Rights	Y
CMS	Mariama Awumbila (2015). “Environmental Change, Migration and Livelihoods on the Coastal Zone of Ghana” Paper delivered at Symposium on Sustainable Development Goals and the Role of Research, 8-9 Dec 2015, Hannover, Germany.	Y
CMS	Mariama Awumbila (2015). “Mangrove Resource Tenure and Use in Ghana’s South Eastern Coastal Zone: Implications for Sustainable Livelihoods” (With Dzodzi Tsikata). Paper presented at the Regional Conference on New Regional Formations: Rapid environmental change and migration in coastal areas, Centre for Migration studies, University of Ghana, 17-18 Nov 2015.	Y
CMS	J.K. Teye & M. Awumbila (2015) “Addressing the Root Causes of Irregular Migration from West Africa to Europe”. Paper delivered at Migration Dialogue for West Africa (MIDWA) Experts Workshop on Irregular Migration. 6- 7 Oct 2015, Nouakchott, Mauritania.
CMS	Awumbila, M and Teye, J. K. Changing Migration Dynamics in Ghana: Policy Responses and Implications for Sustainable Development. Paper presented at a special seminar, IOM Building, Berlin, Germany, 8 Feb 2016.	Y
CMS	Mariama Awumbila (2015). Overview of National Migration Policy in Ghana. Paper presented at launch of Ghana’s National Migration Policy, Accra, 5 April 2016	Y
CMS	M. Awumbila & S. O Kwankye (2015). Ghana’s National Migration Policy: An Overview. Paper presented at sensitisation workshop for stakeholders on Ghana’s National Migration Policy, Tamale, 28 Sep 2015	Y

Research Reports
Partner and/or Project	Author, title, date	Addresses Gender
RMMRU	Tasneem Siddiqui, Ansar Uddin Anas, Abul Bashar, Tabitha Black Lock. Labour Migration from Bangladesh 2015: Achievements and Challenges	Y
CMS	Migration To Cities In Ghana: An Analysis Of The Counterfactual, Research Report	Y
CMS	Migration industry in Ghana, Research Report	Y
CMS	Migration, Intra-Households Dynamics and Youth Aspirations, Research Report	Y
ARI	Wee, K., C. Goh and S.M. Arlini. “Migration Industry in Asia: Indonesian research report.” December 2015.	Y
ARI	Wee, K. and C. Goh. “Migration Industry in Asia: Fieldwork report.” April 2016.	Y

Book chapters

Partner and/or Project	Author, title, date	Addresses Gender
Sussex	Thorsen, D. 'La migration des enfant bissa: Diversite des comportements, pluralite des representations', in Repenser Les Mobilites Burkinabe edited by Sylvie Bredeloup and Mahamadou Zongo, pp 95-120. Paris: L'Harmattan (2016)	Y
CMS	Teye, J.K., Awumbila, M., & Benneh, Y. (2015). Intra-regional Migration in the ECOWAS Region: Trends and Emerging Challenges. In Akoutou, A. B., Sohn, R., Vogl, M., Yeboah, D. (eds) Migration and Civil Society as Development Drivers - A Regional Perspective (Bonn: Zei Centre for European Integration Studies) pp. 97-124.	Y
CMS	Teye, J. K., Alhassan, O., & Setrana, M (2016). Evolution and nature of diaspora engagement policies in Ghana. In J. R. Mangala (Ed), Africa and its Global Diaspora: The Policy and Politics of Emigration. New York: Palgrave MacMillan (In press).	Y
CMS	Yaro, J. A., Teye, J. K, & Bawakyillenuo, S. (2016). An assessment of determinants of adaptive capacity to climate change/variability in the rural savannah of Ghana. In J. A. Yaro & J. Hesselberg (Eds.), Adaptation to Climate Change and Variability in Rural West Africa (pp. 59-82). Cham, Switzerland: Springer.	Y
CMS	Teye, J. K & Owusu, K (2015). Dealing with climate change in the Coastal Savannah Zone of Ghana: In situ adaptation strategies and migration. In F. Hillmann, M. Pahl, B. Rafflenbeal & H. Sterly (Eds), Environmental Change, Adaptation and Migration (pp 223-244). New York: Palgrave MacMillan.	Y

Visual and Social Media

Partner and/or Project	Description	Addresses Gender
ARI	Wee, K. “So what? It’s just a few people: How research can change policy in Singapore.” Published 17 September 2015. An interview with an NGO research consultant in Singapore, Dr. Anja Wessels. https://arimoop.wordpress.com/2015/09/17/so-what-its-just-a-few-people-how-research-can-change-policy-in-singapore/	N
ARI	Wee, K. “It takes a household to raise a village.” Published 3 November 2015. A summary of Dr. Silvia Mila Arlini’s work on how the ways in which remittances are circulated in Ponorogo affect the entire community. https://arimoop.wordpress.com/2015/11/03/it-takes-a-household-to-raise-a-village/	N
ARI	Wee, K. “The making(s) of a domestic worker.” Published 10 November 2015. An ethnographic account of the ARI team’s visit to domestic worker training centers in Jakarta, Indonesia. https://arimoop.wordpress.com/2015/11/10/the-makings-of-a-domestic-worker/	Y
ARI	Khoo C.Y. “The work-in-progress rainbow.” Published 15 November 2015. Focused on the intergenerational impacts of migration on young people’s socioeconomic mobility and aspirations from a case study. https://arimoop.wordpress.com/2015/11/15/the-work-in-progress-rainbow/.	N
ARI	Wee, K. “Yes ma’am.” Published 9 December 2015. Charts the ways in which migrant domestic workers negotiate terms of employment by subverting scripts of deference and obedience. In celebration of International Migrants Day. https://arimoop.wordpress.com/2015/12/19/yes-maam/	Y
ARI	Wee, K. “Me Migrant.” Published 9 May 2016. Reviews a book of poetry written by a Bangladeshi migrant construction worker. https://arimoop.wordpress.com/2016/05/09/me-migrant-mukul/	N
ARI	Wee, K. “It’s a match.” Published 16 May 2016. Interviews a domestic worker and an employer who have used an online matching platform to circumvent traditional employment agencies. https://arimoop.wordpress.com/2016/05/16/its-a-match/	N
ARI	Khoo C.Y. “Kasihan Bapak Ibu”. Published 23 May 2016. Focused on the intergenerational impacts of migration on young people’s educational aspirations and interrogating the idea of ‘successful’ or ‘failed’ migration. https://arimoop.wordpress.com/2016/05/23/kasihan-bapak-ibu/	N
ARI	Wee, K. “This is how domestic workers won a day off in Singapore.” Published 9 June 2016. Summarises the policy process project, which charts how (and why) the mandatory weekly day-off law for migrant domestic workers was passed in Singapore. https://arimoop.wordpress.com/2016/06/09/how-domestic-workers-won-a-day-off-in-singapore/	Y
ARI	Eng, T. “More than motorcycles and fancy homes.” Published 19 July 2016. Focused on charting remittances that migrant domestic workers in Singapore send home to Indonesia and how remittances are used. Also discusses children’s responses to migrant parents’ migration. https://arimoop.wordpress.com/2016/07/19/more-than-motorcycles/	N
ARI	Short film ‘Small Town, Big Dreams’ focuses on the impact of parental migration on young people’s aspirations in Ponorogo, Indonesia. Miko and Nisa are children of overseas labour migrants. Miko majors in business administration in the university while Nisa is pursuing a diploma in nursing at a private polytechnic. What dreams do they have for the future? https://vimeo.com/173425929	N
ARI	A multimedia project which focuses on the types of agency models in Singapore, the agents who run them, and the consequences this has for workers who use these specific agencies. Public launch on 21 October 2016.	N
RMMRU	The Daily Star: “No Justice for Rohingya?” Mar. 2016
RMMRU	Radio Interview with Voice of America: “The Misery of Middle Eastern Refugees in Europe.” Mar. 2016
RMMRU	The New Age: Bangladesh’s Treatment of the Rohingya: Privileging Humanitarianism over Expediency.” Mar. 2016
RMMRU	TV interview with Jamuna TV on the Rohingya and Bangladesh. Apr. 2016.
RMMRU	TV interview with Independent TV on the export of manpower to Saudi Arabia. May 2016.
RMMRU	The Daily Star: “Anomalous Case of Incarcerated ‘Released Prisoners.’” June 2016.
RMMRU	The Daily Star: “Case for Overcoming the Ostrich Syndrome.” June 2016.
RMMRU	TV interview with SA TV on the decline of manpower export. June 2016.
CMS	Photo Poster on Livelihood Strategies and Wellbeing of Migrants in Low-Paid and Insecure Occupations in Urban Ghana	Y
CMS	Short documentary on Migrants in Domestic and Construction Work in Ghana	Y
CMS	Talk show: International Domestic Workers Day Celebration	Y

Other papers and articles indirectly related to RPC project or to RPC staff
Partner	Author, title, date	Addresses Gender
RMMRU	RMMRU, Migration Mirror Issue 3. September- October 2015	Y
RMMRU	RMMRU, Migration Mirror Issue 4. November- December 2015	Y
ACMS / (MiWORC project)	Monica Kiwanuka, Zaheera Jinnah and Becca Hartman-Pickerill – MiWORc Report #10 – Nov 2015 - Getting the house in order: Foreign migrant workers in the domestic work sector in South Africa	Y
ACMS	L.B. Landau and I. Palmary. ‘Legacies, Linkages, and Limits: Teaching Migration Studies in a South African University,’ Migration Studies (2016). doi: 10.1093/migration/mnw007.	N
ACMS	L.B. Landau and C. Blaser. ‘Governing Multiple Elsewheres: Evaluating Local Authorities’ Response to Mobility and Translocality’, 2016. Trialog: Journal for Planning and Building in the Third World: 117/2(1-2): 33-38.	N
ACMS	T.E. Achiume and L.B. Landau. ‘The African Union Migration and Regional Integration Framework.’ 2015. Policy and Practice Brief 36. Durban: ACCORD. http://www.accord.org.za/publications/policy-practice-briefs/1422-the-african-union-migration-and-regional-integration-framework	N
CMS	Awumbila M. (2015) Linkages between Urbanization, Rural-Urban Migration and Poverty Outcomes in Africa. Background Paper for The World Migration Report, 2015	N
CMS	Teye, J. K., Yaro, J. A., & Bawakyillenuo, S. (2015). Local farmers’ experiences and perceptions of climate change in the Northern Savannah Zone of Ghana. International Journal of Climate Change Strategies and Management, 7(3), 327–347.
CMS	Teye, J. K., Acheampong, A. A, and Setrana, M. K. (2015). Migration of health professionals from Ghana: Trends, drivers, and emerging issues. Current Politics and Economics of Africa, 8(3), 459–486
CMS	Teye, J. K, Teye, I. & Asiedu, M. O. (2015). Financing housing in Ghana: Challenges to the development of formal mortgage system. Journal of Housing and Built Environment, 30, 1–16. DOI: 10.1007/s10901-013-9376-z.
CMS	Obeng, F. A, Wrigley-Asante, C., & Teye, J. K. (2015). Working conditions in Ghana’s export processing zone and women’s empowerment. Work Organisation, Labour & Globalization, 9(2), 64–78.
CMS	Bawakyillenuo, S., Yaro, J. A., & Teye, J. K. (2016). Exploring the autonomous adaptation strategies to climate change and climate variability in selected villages in the rural northern savannah zone of Ghana. Local Environment: The International Journal of Justice and Sustainability, 21(3), 361–382. DOI: 10.1080/13549839.2014.965671.
ACMS / (MiWORC project)	MiWORC Policy Brief No.3 A disposable workforce: Foreign health professionals in the South African public service	Y
ACMS / (MiWORC project)	MiWORC Policy Brief No.4 Getting the house in order: Precarity, migration and domestic work in South Africa.	Y
ACMS / (MiWORC project)	MiWORC Policy Brief No.5 A bitter harvest: Migrant workers in the commercial agricultural sector in South Africa.	Y
ACMS / (MiWORC project)	MiWORC Policy Brief No.6 Making guests feel comfortable: Migrancy and labour in the hospitality sector in South Africa.	Y
ACMS / (MiWORC project)	MiWORC Policy Update No.1 Adoption of the SADC Labour Migration Policy Framework.	N
CMS	Policy Brief published in Ghana, not yet on MOOP site: Migration for Domestic Work in Ghana: Implications for Poverty Reduction. October, 2015	Y
ARI	Khoo C.Y., M. Platt and Sukamdi. “Ringkasan Hasil Penelitian: Pola Dan Dampak Migrasi Pekerja Di Kecamatan Sampung, Ponorogo. Research Finding Fact Sheet” No. ISBN 978-979-3969-50-3. Yogyakarta: Gajah Mada University: Centre For Population And Policy Studies. (In Indonesian). http://cpps.ugm.ac.id/content/ringkasan-hasil-penelitian-pola-dan-dampak-migrasi-pekerja-di-kecamatan-sampung-ponorogo	Y
ARI	Goh, C., S.M. Arlini and C.Y. Khoo. “Migrasi Sebagai Strategi Peningkatan Kehidupan Pro-Rakyat Miskin: Studi Kasus Ponorogo. Policy Brief. Yogyakarta: Gajah Mada University: Centre For Population And Policy Studies. (In Indonesian). http://cpps.ugm.ac.id/content/ringkasan-hasil-penelitian-pola-dan-dampak-migrasi-pekerja-di-kecamatan-sampung-ponorogo	Y