Annual Review - Summary Sheet

Title: Health Pooled Fund (HPF) South Sudan
Programme Value: £112 million from DFID[1] / £135 million from partners[2] / Total £246 million			Review Date: / 1-9 November 2016
Programme Code: 203109	Start Date: October 2012	End Date: April 2018
[1] £56 million for HPF1 (Oct 2012 to Apr 2016), and £56 million for HPF2 (Apr 2016 to Mar 2018).
[2] This is for phase one and two. Sweden is yet to confirm their funding for HFP2.

Table 1: Summary of Programme Performance
Year	2013	2014	2015	2016
Programme Score	A	A	A	A
Risk Rating	Medium	High	High	Major[3]
[3] Applying the new DFID requirement for the risk level to be scored as severe/major/moderate/minor.

Summary of progress and lessons learnt since last review
This is the fourth annual review for the Health Pooled Fund (HPF) programme. The HPF has performed well in a highly challenging environment, sustaining vital health care services in South Sudan through 1,000 community health centres – the only source of health care for many ordinary South Sudanese. During the reporting period the programme expanded its coverage by adding two new states to cover eight (out of 10)[4], and was responsible for providing nearly 8 million patient consultations. Despite the fact that conflict has now spread to many areas of the country, the programme managed to achieve the majority of targets set for strengthening health systems, but struggled to achieve milestones related to community engagement.
[4] This is based on the former 10 states, and not the 28 new states which were declared in December 2015.
Progress in relation to milestones:
The programme again scored an A (“met expectations”) on the basis of performance data. For the period April to September 2016, the HPF Steering Group agreed to focus on a limited set of indicators compared to HPF1. This was due to the reduced budget scope[5] for the initial six-month inception period of HPF2; the need to focus on essential health care delivery, and pending the selection of Implementing Partners for HPF2.The table below gives a summary of performance against the three outputs in the logframe.
[5] There was a funding shortfall following an increase in HPF expenditure in early 2015, due to increase in logistics cost and partner agreement to procure additional essential medicines.

Output number	Output Description	Impact Weight (%)	Output Performance
1	Strengthened delivery of health services, particularly responsive to the needs of women and children	50%	A+ (Output moderately exceeded expectation)
2	Communities have increased ownership, governance and demand for health services	20%	B (Output moderately did not exceed expectation)
3	Strengthened health systems at state and county level focusing on policy, human resources for health, health financing, Health Management Information Systems, governance and leadership.	30%	A (Output met expectation)

Lessons learnt
- HPF management arrangements, engaging Implementing Partners (IPs) with solid on-the-ground experience, enabled health service delivery to continue during conflict,
- The Programme was able to respond flexibly and contribute to emergency responses.
- Fewer and larger consortia of IPs should deliver stronger performance and coherence, as well as reduced management transaction costs.
- HPF2 provides an opportunity to put in place building blocks for a successor programme from April 2018 to deliver a more sustainable and country-led/resourced health system, should stability return.
Summary of recommendations for the next year:[6]
[6] Full details of these recommendations including who is responsible and the timeline are contained in Section B.
- Ensure a smooth transition to HPF2, with improved involvement of Ministry of Health (MoH) and donors in the oversight, and monitoring of the HPF.
- Continue to strengthen health service delivery and access, maintaining appropriate health systems strengthening components, and strengthening harmonisation and coordination with the World Bank project.
- Develop a stronger framework for monitoring and evaluation, risk management, and Value for Money.
- Assess jointly with MoH the implications for the health system of the creation of 28+ states.
- Support HPF2 to be more conflict sensitive by considering creation of reserve funds for crisis response, allowing greater flexibility in conflict-related health responses;
- Continue advocacy to Government of the Republic of South Sudan for facilitating the work of Implementing Partners, and to increase national budget allocation to the health sector.

A. Introduction and Context (1 page)
DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203109/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203109/documents/

Outline of the programme
The impact of the programme is to develop a Government-led health system that saves lives. The overall outcome is increased access to quality health services, in particular by children, pregnant women and other vulnerable groups. The outputs this programme will deliver to achieve the outcome are:
1. Strengthened delivery of health services, particularly responsive to the needs of women and children,
2. Increased ownership, governance and demand of communities for health service,
3. Strengthened health systems at state and county levels.
The HPF brings together funding from the UK, Canada, the European Union, Sweden and USA to support delivery of the Health Sector Development Plan of the Government of the Republic of South Sudan (GRSS).[7] Donors contributed £107m over the period 2012-2016.The HPF now covers eight out of South Sudan’s former 10 states,[8] with World Bank support covering Jonglei and Upper Nile.
[7] Australia was also a donor until May 2016, but will not be part of HPF2.
[8] Two states previously supported by USAID were incorporated into HPF from April 2016, when USAID joined the pooled fund arrangement. Two of the former 10 states, Jonglei and Upper Nile, remain out of the HPF arrangement under a separate World Bank funded project.
Before the start of HPF, multiple Non-Governmental Organisations (NGOs) supported health service delivery through diverse projects supporting individual health facilities. The HPF replaced this with more comprehensive and coordinated support for primary health care delivery. County Health Departments (CHDs) lead and manage the delivery of health services, supported by the National and State Ministries of Health. A steering committee co-chaired by MoH and DFID oversees the governance of the HPF. State and County Oversight Committees provide project oversight at the lower levels.
The Peace Agreement signed by the government and Opposition in August 2015 and subsequent formation of a Transitional Government of National Unity (TGNU) has not brought sustained peace to the country. Fighting has continued, with conflict spreading to areas previously unaffected such as Western Bahr El Ghazal. June 2016 saw serious fighting and displacement in Wau and surrounding areas, whilst July saw a major outbreak of violence in the capital Juba, with attacks and widespread displacement of communities subsequently spreading across the Greater Equatoria region, continuing to date.
Implementing Partners (IPs) report a challenging year in a deteriorating operating environment, particularly in conflict-affected areas, compounded by economic downturn and inflation. International staff employed by the fund manager in Juba were evacuated in July following outbreak of violence. There has been a gradual return from August onwards and all were back in Juba by November 2016, with donors also returning. Activities in a range of locations were affected by the local security situation, including restrictions on the movement of personnel and logistics in some areas.
Significantly reduced oil revenue, together with the costs of the conflict and security, has had a significant effect on the fiscal position of the GRSS and its ability to pay for commodities and health worker salaries, with the government budget for the health sector reduced to 1.7%. Very high levels of inflation (running at 670% as of October 2016) have had a major impact on programme operating costs. The presidential decree in December 2015 to create 18 new states, has added an additional challenge requiring the creation of new state ministries and county health departments, notwithstanding highly constrained government budgets for personnel and infrastructure.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Table 2: Annual outcome assessment
Impact Indicators	Baseline (2010)	Milestone / (March 2016)	Progress (2016)[9]	Milestone (March 2017)
1. Under 5 Mortality Rate (per 1,000 live births)	106/1,000	95/1,000	99/1,000 [10]	91/1000
2. Infant Mortality Rate (per 1000 live births) [11]	66 per 1000 live births (2012)	N/A	N/A	58 per 1000 live births
3. Maternal Mortality Ratio (per 100,000 live births)	2,054/100,000	1643/100,000	789/100,000 [12]	620/100,000
Outcome Indicators	Baseline (2010)	Milestone / (March 2016)	Progress (2016)	Milestone (March 2017)
1. Percentage of 1-year-olds vaccinated with a third dose of DPT[13] vaccine	18,000 (11%)	50%	6 states = 206,268 (46.8%) [14] / 5 States (excluding Unity State[15]) = 200,663 (52.8%)	55%
2. Proportion of children under 5 with fever in the last 2 weeks who were taken to a health facility	15.3%	30%	64% (National Average)[16]	70%
3. Contraceptive Prevalence Rate	6.5%	11%	5% (National Average)	8%
4. % of births attended by skilled health personnel	7,311 (2.8%)	42,870 (15%)	6 States: 39,012 (10.1%) / 5 States (without Unity): 35,659 (10.7%)	20%
[9] Progress on indicator cell coloured thus: “has been achieved”, (green) “partially achieved” (amber) or “not achieved” (red).
[10] Unicef (2015): Source: http://www.unicef.org/publications/files/SOWC_2015_Summary_and_Tables.pdf
[11] Added to HPF2 log frame (covering the period from April 2016)
[12] Source: WHO (2015), Trends in Maternal Mortality: 1990 to 2015 www.who.int/reproductivehealth/publications/monitoring/maternal-mortality-2015/en
[13] Vaccine against three infectious diseases in children: diphtheria, pertussis (whooping cough), and tetanus.
[14] HMIS data 2016
[15] This is based on the exclusion of Unity State on the basis of its conflict-affected and as recommended in the last AR
[16] Lot Quality Assessment Survey (LQAS) 2015 Survey

As noted in previous Annual Reviews, the impact indicators are based on national targets, which are measured by national surveys. Due to conflict and availability of donor funding, national surveys which were due in 2015-16 have not taken place as scheduled.[17] In the absence of updated survey data, performance is assessed using available projections by WHO and UNICEF. Using these projections, impact targets to be met by March 2016 have been (i) exceeded in terms of the Maternal Mortality Rate (an estimated reduction to 789 per 100,000 live births) and (ii) nearly achieved in terms of the under-5 Mortality Rate.
[17] These include the Demographic Health Survey (DHS) and LQAS Survey.
The two outcome targets focused on child health have been achieved (Outcome indicators 1 and 2), whilst the two focused on reproductive health have not yet been achieved (Outcome indicators 3 and 4). The nationwide shortage of skilled birth attendants has had a negative impact on progress towards Outcome 4.
Overall output score and description: A
The HPF again scores an A for the period November 2015 to October 2016, based on performance data. For the period April to September 2016, the HPF Steering Group agreed to track progress against a more focussed set of indicators, due to the reduced budget scope for the initial six-month inception period of HPF2, to focus on essential health care delivery, and pending the completion of the procurement process to select Implementing Partners for HPF2. This ensured service delivery targets to be met despite budget constraints, the economic downturn and the disruption due to conflict. Results evidence suggests that the programme has made effective adjustments and efficiency savings to maintain this good level of performance.
.Key lessons
- The HPF has demonstrated resilience during a period of disruption due to conflict, and harsh economic conditions.
- Flexible funding/ budgeting would allow HPF to be more conflict sensitive.
- County health departments have demonstrated the ability to play a strong lead role in health planning and service delivery
- Value for Money (VfM) frameworks have been strengthened and VfM will be easier to assess under HPF2
- While currently fit-for-purpose, management arrangements should be further strengthened and improved.
- The incorporation of a nutrition component to the HPF package is a valuable addition to the programme, with new indicators for reporting in the remaining programme period.

Table 4: Summary of key actions for the coming year(including timeline and responsibility)
Action	Timeline	Responsible
1. The transition to HPF 2 to be completed by end 2016, with a clear plan to strengthen MoH and donor role in the HPF at the national level with improved coordination and collaboration.	December 2016	DFID and fund manager
2. Develop a stronger framework for monitoring and impact evaluation and a new risk management framework.	February 2017	Fund Manager
3. Assess with MoH the implications of the creation of 28 states on the health system and prepare analyses of the financial and administrative implications.	February 2017	Fund Manager
4. Resources for the health sector: (i) The consortium to ensure a robust assessment of the combined impact of conflict and the economic crisis on the health sector - to assist in demonstrating funding needs to government and donors; continue strong advocacy (GRSS, MoH and donors) for a significant increase in the sectoral budget allocation. (ii) Consider enabling HPF2 to be more fully conflict sensitive by creating reserve funds for crisis response.	March 2017	DFID and fund manager
5. The Consortium and IPs to implement the Value for Money Framework	End December 2016	Fund manager
6. Commence preparation for the successor programme from April 2018 (“HPF3”), with strong involvement of MoH and all donors in the planned three-year review of HPF in early 2017 to feed into this process.	January 2017	DFID and fund manager

Has the logframe been updated since the last review? Yes
The HPF1 log frame (as revised in early 2015) was in use until the end of March 2016 as per the business case. At this point, the programme geographical coverage expanded from six to eight states with the incorporation of former USAID supported states. Revised Key Performance Indicators were agreed by partners at the Steering Group meeting, and adopted for this period. The log frame is now undergoing a process of review and revision for the period December 2016 to March 2018 following the selection of new implementing partners to deliver HPF 2.

## C: DETAILED OUTPUT SCORING (1 page per output)
Output Title	Strengthened delivery of health services, particularly responsive to the needs of women and children
Output number per LF		1	Output Score	A+
Risk:		Major	Impact weighting (%):	50%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s) [18]	Milestones 2016 (timeline in brackets)		Progress 2016[19]
(i) Under 5 Out Patient Department (OPD) consultations treatment services (disaggregated by gender) (ii) Under 5 consultations preventive/promotive services (iii) total under 5 consultations	Male curative	500,000	2,901,179	2,701,441 / 5,402,881
	Female curative	500,000	2,501,702
	Preventive M&F	800,000	1,337,947(m) / 1,223,124	2,561,071
	TOTAL	1,800,000	TOTAL	7,963,952
	* (data not available by gender). Substantially exceeded expectation: Scored A++
1.2. % of children under five years with diarrhoea who receive Oral Rehydration Treatment (ORT)	90% (March 16)		86.7% (Av.) Moderately did not meet expectation. Scored B
1.3 Percentage of women who attended at least four times for antenatal care during pregnancy	Original Logframe: 85,740 (30%) Amended for 5 states: 105,442 (38%) (March 16)		6 states = 110,248 (27.9%) / 5 states (without Unity) = 100,515 (29.5%). Moderately did not meet expectation. Scored B
1.4 Number of acceptors new to modern contraception	9000 (March 16)		12,934 (average) / Exceeded expectation: Scored A+
1.5 Number of facilities with capacity to offer Comprehensive/ Basic Emergency Obstetric and Newborn Care (CEmONC & BEmONC) Services	(i) All HPF supported hospitals (20 in total including faith based) provide CEmONC / (ii) All 39 counties have at least 1 health centre with BEmONC		20 / 34 / Moderately did not meet expectation. Scored B
1.6 Quality indicator I: Percentage of Antenatal Care (ANC) attendees who received IPT2 (Intermittent Preventive Treatment of malaria in pregnancy)	50% (based on a dropout rate average from ANC 1 to ANC 2) (Mar ’16)		ANC IPT 2nd dose + ANC IPT 2nd or more dose 129,361 (average) – 52% / Output met expectation: Score A
**Antenatal Client IPT 2nd dose	55,918 (April-Sept’ 16)		74,127 (April-Sept’ 16) / Output moderately exceeded expectation: Score A+
**Delivery in Facility	21,750 (April-Sept’ 16)		34,061 (April-Sept’ 16) / Output moderately exceeded expectation: Score A+
**Delivery in facility by skilled birth attendant	20,662 (April-Sept’ 16)		21,052(April-Sept’ 16) / Output met expectation Score A
**Childhood vaccination( Diphtheria-Tetanus-Pertussis (DTP) - Hepatitis B) 3rd dose 0-11 months total	56,872 (April-Sept’ 16)		78,609 (April-Sept’ 16) / Output moderately exceeded expectation: Score A+
[18] Indicators in the shaded boxes represent the Key Performance Indicators adopted for the period April-Sept 2016.
[19] Unless otherwise indicated, performance data is based on HMIS data for the period to March 2016. Source: Quarterly Project Technical Reports (QTPRs)/ Log frame version October 28th 2016.

Key Points
For the period to March 2016, two targets have been met (1.5 and 1.6), two have been considerably exceeded (1.1 and 1.4), and two have not been met (1.2 and 1.3). The lag in performance target for indicator 1.2 and 1.3 is due to disruption in services delivery due to the conflict and low demand for complete antenatal care by the beneficiaries. Performance against these indicators is expected to improve, with more functional health facilities and with increased provision of promotive services at the community level through the community health strategy. For the period April to September 2016, all the indicator milestones were met, with most of them exceeding expectation, leading on balance to an overall output score of A+. A number of quality-of-care innovations and improvements are not captured in the Output monitoring. These include improved referrals procedures, increasingly skilled staff and better systems to allocate staff, improved access to essential medicines, adoption of standard treatment protocols, and improved infection control in hospitals.
Summary of responses to issues raised in previous annual reviews (where relevant)
There has generally been good progress reported, despite the challenging context. Comprehensive emergency care for childbirth has been a priority focus, and this is now in place in all 20 HPF supported hospitals, plus 2 Primary Health Care Centres. The MoH quality assurance policy and standards have resulted in stronger quality improvement mechanisms. HPF support has led to improvements in data record-keeping at facility level, together with an improvement in ensuring quality of health data at national level.
Recommendations (for the Fund Manager and consortium partners)
- Strengthen the Quality of Care oversight function within MoH at national level.
- Continue initiatives to increase the number and allocation of skilled birth attendants.
- Extend coverage and quality of services for the Clinical Management of Rape (CMR).
- Build the nutrition component which has been introduced from April 2016, with additional DFID funds.
- Support MoH to consider how best to build community-based health information into the District Health Information System.
- Strengthen the ability of programme monitoring and reporting to demonstrate increases in service delivery to hard-to-reach areas and vulnerable populations (e.g. displaced communities).

Output Title	Communities have increased ownership, governance and demand for health services
Output number per LF		2	Output Score	B
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s) [20]	Milestones 2016 (timeline in brackets)	Progress (October 2016) [21]
2.1 Number and percentage of health facilities with a health committee in place for communities to give feedback regarding health services / **New women health committee members	All functional health facilities have a committee in place (Target 100%) (March 16) / 340 (April-Sept16)	Total number of health committees in HPF Supported Health Facilities. 97% (Average.) / Output moderately did not meet expectation: Scored B / 728 (April-Sept 16) Output moderately exceeded expectation: Score A+
2.2 Number of documented joint meetings held between the County Health Department, implementing partner health committee and facility staff (4 parties)	At least one joint meeting held and documented per quarter in all Primary Health Care Centres and 50% of Primary Health Care Units (March 16)	49.6% / Output met expectation: Score A
2.3 Number/percentage of health committee representatives that are women	At least 40% of committee members are women (March16)	37% (Average.) / Output moderately did not meet expectation: Scored B
[20] Indicators shaded represent the Key Performance Indicators adopted for the period April-Sept 2016.
[21] Source: Quarterly Project Technical Reports (QTPRs)/ Log frame version October 28th 2016.

Key Points
Community engagement in health committees is now in place in all HPF supported counties, with good progress towards the target of 40% of all committee members being women. A key issue is now the need to support committees to play an active and meaningful role. The period saw a reduced focus on and availability of funding for the community engagement component. Conflict and insecurity significantly affected the running of and ability to support facility and Boma (below-village) Health Committees.
Summary of responses to issues raised in previous annual reviews (where relevant)
Committees are generally reported to be functional, though localised conflict has led to disruption. All health committees have taken action to bring on board the specified quota of female members. HPF has engaged actively in supporting the development of the Boma Health Initiative at the national level.
Action is still needed to develop a community health monitoring system (this links also to Output 1).
Recommendations for Fund manager and the consortium partners
- More support and capacity building should be provided to enable committees to function strategically; in future there is a need to assess the quality of community participation, and to consider how this could be enhanced.
- Committee members should be provided with training and support, especially women.

Output Title	Strengthened health systems at State and County level focusing on – Policy, Human Resources for Health, Health financing, HMIS, governance and leadership.
Output number per LF		3	Output Score	A
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicators [22]	Milestones (March 2016)	Progress (October 2016)[23]
3.1 Number of HPF Steering Committee meetings chaired by the Government of the Republic of South Sudan (GRSS) and number of State Oversight Committee(SOCs) meetings held	(a) 14 (cumulative) HPF Steering Committee meetings chaired by GRSS / (b) At least 3 State Oversight Committee meetings held in each state except Unity (total 15)	(a).15 / (b) 5 states have had at least 3 SOCs: 31 (Total) / Output moderately exceeded expectation: Score A+
3.2 Percentage of facilities with quarterly integrated supportive supervision visits conducted by county health department using the Quantified Supervisory checklist (QSC) tool	70%	74% (Ave.) / Output met expectation: / Score A
[22] No indicators were monitored under Output 3 for the period April-September 2016.
[23] Source: Quarterly Project Technical Reports (QTPRs)/ Log frame version October 28th 2016

3.3 Percentage of health facilities submitting timely reports through the District Health Information System (DHIS) according to the data flow policy.	80%	88% / Output moderately exceeded expectation: / Score A+
3.4 Proportion of counties with one jointplan and one review system for all government and NGO health services	Proportion of counties with one joined plan = 75% / Proportion of counties with one review system = 60% / Proportion of counties with one joined plan, and one review system = 60%	Proportion of counties with one joined plan = (39/39) 100% / Proportion of counties with one review system:= (39/39) 100% / Proportion of counties with one joint plan and one review system = (39/39) 100% / Output substantially exceeded expectation: Score A++
3.5 Percentage of counties submitting payroll forms, disaggregated by government and County Partner (Number of payroll forms completed & sent to HPF).	100% of counties apply and submit payroll for all IP staff. / 50 % of HPF supported counties/government submit payroll for staff on the government payroll	100% (39/39) of counties apply payroll for IP paid Salaries & / 64%(25/39) Counties applied payroll for Government paid Staff / Output met expectation: Score A
3.6 Percentage of counties in which Human Resource Information System (HRIS) is implemented, disaggregated by (a) facility staff and (b) CHD staff (documents scanned and filed into HRIS).	95% of counties using HRIS.	6 States = 92.3% (36/39) / 5 States (without Unity) = 100% (30/30) / Output moderately did not meet expectation: Scored B

Key Points
Targets set for local health systems strengthening have been almost fully met. As explained earlier, in order to focus on health service delivery, activities to build health systems strengthening received reduced funding and emphasis in the context of constrained resources during the transition from HPF1 to HPF2.
Summary of responses to issues raised in previous annual reviews (where relevant)
Systems strengthening activities have been built into the Terms of Reference for all Implementing Partners. Drug procurement has been organised via a separate contract using donor-pooled funds (separate from the HPF1, but integrated into HPF2). Improvements to monitoring essential drug stocks and supply are ongoing, and hospital Health Management Information Systems have been piloted in four hospitals and are now being rolled out to all hospitals.
Recommendations for fund manager and consortium members
- Continued support for local-level health systems strengthening in HPF2, where there are clear benefits for improving effectiveness, responsiveness and accountability.
- Considering current targets have nearly all been met, health systems strengthening indicators and milestones could be made more ambitious for HPF2, particularly at local and facility level, without jeopardising the need to focus on service delivery.
- Continued emphasis on Human Resources for Health is critical to ensure continued progress in efforts to build the number, skills and distribution of health staff at all levels.
- Identify options for future drug procurement mechanism/s to improve speed, responsivleness and falue for money.
- In the context of high fiduciary risk, maintain a robust Public Financial Management component and support the payroll improvements to ensure potential issues such as “ghost workers” are addressed and savings released for service provision.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

- Up to April 2016 total donor contributions amounted to £107.9m, with £56m of this from DFID. No donor funds had been received after April 2016, but are due to recommence in 2017.
- Of the donor contributions for HPF to date, approximately 99% has been spent. From November 2015 to end August 2016, £35.7m was spent under the programme.
- The government contribution to the health sector decreased from 3% to 1.7% of state budget since last year. HPF expenditure per capita is £4.54 compared to a GRSS health budget figure of £0.58 (2016/7) and actual expenditure per capita of £0.13 (2015/6). This creates a high, and increasing, level of dependency on donor funding.
Key cost drivers and performance
The original business case (2012) identified the main cost drivers of the programme to be salaries and commodity supplies, which has been found to be the case for the period November 2015-October 2016:
  - For this review period, salary support to county health personnel constitutes 39% of expenditure, compared with 38% in 2015. This is primarily due to an increase in the scale of the programme to include two additional states. The proportion of the budget spent on salaries will need careful monitoring and management going forward.
  - Factoring in the additional £18 million HPF funding committed for essential medicine procurement through a separate contract with a procurement agent, expenditure on medicines is likely to remain high as long as MoH budgetary constraints continue.
- A positive trend in VfM performance is that overall overhead costs are reducing. Service provider support (the budget for the downstream implementing partnerss) constitutes 19% of total, compared to 16% in 2015, and the overhead (consortium partner cost) is 6%, leading to a combined 25% figure for the cost of the consortium and implementing partners, a significant drop from 39% in year 2.
- Inflation has increased from 73.6% in November 2015 to 682.3% in September 2016 (with a peak of 729.6% in August following the conflict), in addition to increased costs due to deteriorating security, this has added to procurement and implementation costs.
VfM performance compared to the original VfM proposition in the business case
- The VfM framework[24] Developed in May 2016 will be applied to HPF2 following the re-structuring of budgets to enable this analysis.
  [24] These include unit costs for different service delivery outcomes and the cost of delivering different outputs.
- In terms of overall VfM performance compared to business case proposition:
  - Economy: programme inputs are procured at very competitive unit costs and follow strictly laid out procurement procedures.
  - Efficiency is difficult to assess because of the structure of budgets and expenditure reporting in HPF1; sufficient plans are in place to address this in HPF2.
  - Effectiveness: One outcome indicator (Outcome 2) has been achieved. However, expenditure data is not as yet reported per outcome to measure effectiveness data.
  - Equity: By design, the project targets vulnerable populations e.g. women and children, low socio-economic groups, and those in need of financial protection. Whilst there have been no equity surveys done to date, the programme reports show greater gender equity through the inclusion of more women in management, governance and accountability structures (38% of health committee members are now women).

Assessment of whether the programme continues to represent value for money
HPF continues to provide a good VfM approach to the delivery of health services in 8 of the 10 former states of South Sudan, when compared to alternative options such as using humanitarian architecture, particularly in terms of building local capacity and institutional strengthening, and sustainability. It has managed continuity of activities and results through periods of disruption and conflict where other partners and donors have been unable to continue. It is clear from the achievements against outputs that the programme continues to represent value for money, evidenced by over achieving on targets whilst remaining within budget and reducing management overhead costs.
Quality of financial management
The programme expenses are on a retrospective reimbursement basis, which reduces fiduciary risk. The reimbursement system is robust, with effective policies and procedures for verification of invoices and expenses for the programme. External audit follow-up report of October 2015 highlights two high risk recommendations relating to finance and organisation, which were resolved. An annual external audit is scheduled before end of 2016 to track implementation of all recommendations in the last audit report.

Date of last narrative financial report	31 August 2016
Date of last audited annual statement	2 October 2015

E: RISK (½ page)

Overall risk rating: MAJOR
Overview of programme risk
The programme risk matrix is regularly updated to reflect latest developments and assessments. This has been revised to follow the new scoring criteria. The overall risk rating is assessed as MAJOR [25].
[25] This is based on the new classification of risk as Severe/Major/Moderate/Minor replacing earlier classifications of High/Medium/Low
A number of key risks are classified as severe and have increased, including; insecurity from conflict, a related deterioration in the operating environment with more regulation of NGOs, the decline of of government resources available for the health sector, and communication / coordination challenges resulting from post-July evacuation. Key mitigating actions identified include the need to make funds available for flexibility and conflict-sensitive implementation, advocacy with government to raise their allocations to the health sector and to ensure the operating environment for NGOs gives them the flexibility and autonomy to perform, and partners’ return to Juba and improved donor/HPF/MoH coordination mechanisms. The delay in the World Bank in returning to Juba, and the uncertainty over their support to health services in Upper Nile and Jonglei represents a serious risk which is should be addressed through advocacy and engagement at the highest levels. The creation of 28 (and more) new states has important implications and challenges for health service planning, financing and delivery, and there is a need to assess and discuss these with Ministry partners, for example in terms of increased human and financial resource requirements at a time when government struggles to meet salary costs of the existing workforce.
Some risks are considered to have reduced as a result of better local institutional ability to manage disease outbreaks, enhanced capacity to plan and manage service delivery at the county level, and the extension of HPF programming to cover additional geographical areas.
Outstanding actions from risk assessment: None
Follow up action in the remainder of the programme: The Risk Management Strategy involving monthly updates to contract risk-registers and quarterly updates to programme risk register, continues to function adequately, as demonstrated in the ability to ensure effective service continuation following the July disruptions. Other programmes and partners did not manage similar continuity. The programme level risk is regularly discussed between the fund manager and DFID. It is recommended that this risk review process be broadened to include MoH and all donors, for example at the Quarterly Steering Committee meetings or interim meetings. The risk management framework will also be updated for HPF2, using the revised DFID risk scoring guidance. Implementers must ensure they report immediately to DFID any incidents of theft, criminality and fraud.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
As mentioned earlier, the programme was focused on essential service delivery for the period April-September 2016, while HPF2 contracts were being developed. The July 2016 conflict affected delivery of some key interventions, with a few geographic areas suffering significantly from interruption to services such as drug supply, and an increase in theft and vandalism of assets. The programme recovered well however, and is back on-course to deliver programme objectives.
Performance of partnership(s)
- Partnership between the MoH, the donors and HPF consortium was disrupted by the post-July evacuation and delay to the IP proposal selection process. The MoH and partners have asked for increased dialogue and involvement in decision-making processes, as well as stronger systems to manage the performance of the IPs. The Steering Committee held in early November acknowledged these issues and agreed a review of the governance mechanism and more frequent coordination meetings to jointly address MoH, donor and HPF concerns.
- DFID continues to act as lead donor on behalf of Canada, Sweden, EU and US (a new addition to the donor consortium as of April 2016). This represents a considerable managerial burden to DFID though its lead role continues to be appreciated. Donors are looking at options to support DFID’s role in leading programme management, and to increase HPF and co-donor responsibilities.

Asset monitoring and control
The asset management system is satisfactory for this programme. HPF reports on asset management on a quarterly basis. There has been a shift to ad-hoc asset reporting, especially when there is conflict-related vandalism and/or theft. This allows for immediate response and reduces delays in responding to programme challenges that may arise. In addition, national coordinators conduct random asset verification as necessary to validate the reported data.
Recommendation on Asset Management:
- An asset disposal plan should be agreed at the onset of HPF2.
- As planned, HPF2 should value and report assets lost due to theft and vandalismas soon as the loss occurs.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
As noted in previous Annual Reviews, there are no specific conditionality requirements linked to this programme, which does not channel any funds directly to or through the partner government.
The development partners agreed a set of Donor Principles (July 2014) following the outbreak of conflict in 2013 which signalled the need for engagement with government to focus on humanitarian efforts and the delivery of basic services. These Principles were being reviewed by donors in November 2016.
Whilst there is now a fragile peace agreement in place, the relationship between international development partners and government remains difficult in the light of the ongoing conflict and growing human rights concerns. There is however agreement amongst donors that basic service delivery remains an important goal and activity for donor support. Future discussion with MoH should include how to ensure GRSS budget allocation and execution to the health sector can increase.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The programme geographical coverage was expanded to eight states with a reduced budget and scope of work from April to September 2016. Key performance indicators were adopted for this period. It is recommended that where available, MoH/District Health Information System as well as HPF reporting data related for the full set of HPF2 log frame indicators is collected retrospectively for the period April to September 2016.
As milestones/ targets were met and in some cases significantly exceeded over a period with significant challenges,these should be reviewed to ensure that targets set are adequately ambitious. Due to the challenges of reporting at impact level, a review of both the types of Impact level indicators and ways in which these can be tracked without dependence on irregular national surveys is recommended, as well as the commissioning of an impact/outcome level evaluation study.
Planned independent third party monitoring of essential service delivery including health services will be valuable, particularly whilst donor and partner monitoring capacity and access is constrained, and is due to start imminently.
Monitoring progress throughout the review period
HPF;s team carry out regular field monitoring missions to implementer sites to assess progress. The missions are carried out at least once each quarter and the findings from these missions feed into the project monthly and quarterly reports that are shared with partners.

Within DFID, the Senior Health Adviser is the SRO, supported by a technical and management team. Due to travel restrictions and insecurity in South Sudan, monitoring by DFID has been limited. Field visits since July 2016 have not been possible due to the conflict, and travel outside Juba is currently not possible. In this context, DFID therefore relies on DHIS data, implmenter reporting and independent reports. Ministry of Health personnel are present throughout the region of delivery and report back on progress regularly. For the remainder of the programme DFID should continue to review asset register as part of regular asset monitoring and control. In addition to independent Third Party Monitoring, Canadian CIDA is developing a comprehensive independent Monitoring and Evaluation framework.

This review used desk review, data analysis and in-country interviews with stakeholders (MoH, the HPF consortium, donors). An in-depth workshop was conducted with Implementing Partners. No field work was able to be conducted due to security constraints. The views of beneficiaries are therefore not included, as well as those of MoH staff outside the national level (other than one interview with a state minister of health who was visiting Juba). It is hence important that beneficiary and field level feedback is built into the planned three year review scheduled for early 2017.