Business Case

Summary Sheet

Department CDD/Portfolio/ Business Plan Summary: / CYED’s 2020/21-2-24/25 Business Plan states that the Department “will lead whole-of-government work to champion the right of all girls to receive 12 years of quality education, through international influencing, campaigning, and programmes. To support this goal, we will help to strengthen education systems and teaching quality to increase basic literacy and numeracy”. / DFID’s education response to COVID-19 is to: / mitigate risks to pupils and the education workforce in the short-term, addressing safety, nutrition, wellbeing and learning and; / preserve the education system and education finance in the medium to long term, maintaining school places and schools, education funds, improving crisis response and building back better. / Through the new five-year Girls’ Education Action Plan, the UK is leading the charge on two global targets – by 2021 to get girls back to school, returning to pre-COVID-19 levels, and by 2025 to get additional girls into school, and reading.

Title: / COVID-19 Emergency Education Response (CEER)
Programme summary / This programme proposes investing £5.3m to offer emergency support to mitigate the immediate impact of the COVID-19 pandemic on education in refugee settings. This will be particularly important for the most marginalised children who are at risk of dropping out of school entirely due to the pandemic. The investment will support teachers in refugee areas to provide essential education and community outreach where there is extreme need.
What is the rationale for UK Aid spending? / Progress made on access to education is at risk due to the secondary impacts of the COVID-19 pandemic. Without direct support, the beneficiaries targeted under this programme – some of the world’s most marginalised children – will drop out of school permanently, which is at odds with Manifesto Commitments and Ministerial priorities to stand up for the right of all girls to have 12 years’ quality education. This COVID-19 Emergency Education Response supports the UK’s five-year Girls’ Education Action Plan, and new targets for access and quality in response to the COVID-19 crisis. CEER also directly contributes to DFID’s education response to COVID-19, which aims to: / Mitigate risks to pupils and the education workforce in the short-term / Preserve the education system and education finance in the medium- to long-term / The support under CEER will not do this alone of course, but continuing support to some of the world’s most vulnerable children will act as an essential building blocks for follow up support and continuing education in the most vulnerable countries. / The programme also contributes to DFID’s 2018 Education Policy’s strong focus on supporting teachers to enable all children to gain foundational skills, and targeted support to the most marginalised, and DFID’s 2018 Strategic Vision for Gender Equality, which lays out DFID’s commitment to put girls and women at the heart of the development and humanitarian offer. It also helps deliver the 2019 Single Departmental Plan by directly promoting two of the “Five Ps”: People and Prosperity. This will be through education reform to meet basic needs and supporting girls and marginalised children get the skills that can eventually lead to jobs that will help build the economy.
Programme Value: / £5,500,000		Country/ Region or Sector: Global, Education
Department/Country Office confirmation / Contact name		Children, Youth, Education Dept. (CYED) / Kate Jefferies, Education Adviser / Emma Gremley, Snr. Ed Adviser
Threshold for Approval of Business Case:		Darren Welch, Director, Policy Division
Date of Approval of Concept Note:	09/07/2020	Name of Approver Foreign Secretary, Dominic Raab
Date of Approval of Business Case	28/08/2020	Name of Approver Alicia Herbert, Head, Children, Youth and Education Department
Programme Code: / 301207	Start Date: / 01/07/2020	End Date: / 28/08/2021
Overall programme risk rating: / Further details in “Risk” section	Moderate
Vault Number:	56924519

## Abbreviation List

CAA	Central Assurance Assessment
CYED	Children, Youth and Education Department
ECW	Education Cannot Wait
CEER	COVID-19 Education Emergency Response
EiEPC	Education in Emergencies and Protracted Crises
GPE	Global Partnership for Education
HACT	Harmonised Approach to Cash Transfers
IAD	Internal Audit Department
IDP	Internally Displaced Persons
MoU	Memorandum of Understanding
NGO	Non-Governmental Organisation
ODA	Overseas Development Assistance
PCR	Project Completion Report
SRO	Senior Responsible Owner
UNHCR	United Nations Refugee Agency
VfM	Value for Money
WASH	Water, Sanitation and Hygiene

## Strategic Case

Background

School closures as a result of COVID-19 have affected more than 1.5 billion children and young people and will significantly reduce learning. Disadvantaged children, particularly girls, will suffer most and are at risk of dropping out of school permanently. Without effective mitigation, school closures have long lasting impacts on children’s well-being, learning and life chances and risk jeopardising the gains made in education over past decades and the achievement of SDG 4.
[note] https://en.unesco.org/covid19/educationresponse

Marginalised learners, including refugees and girls, will be disproportionately affected. Female pupils bear a greater negative cost of disease outbreaks, leading to higher levels of sexual exploitation, abuse, teenage pregnancy and early marriage. Children in vulnerable populations, including refugees and slum dwellers, may be at higher risk of secondary impacts of COVID-19 given existing health conditions, high population densities, limited access to basic services and limited livelihoods options. They are also less likely to be prioritised for state resources.
[note] “Evidence on efforts to mitigate the negative education impact of past disease outbreaks”, J Hallgarten, 2020. K4D Report.

Without effective mitigation, school closures have long lasting impacts on learning and life chances. After the 2005 Pakistan earthquake, in affected areas children were out of school for an average of 14 weeks but had learning levels significantly lower than their peers up to four years after the earthquake. Estimates suggest that the overall loss of learning could result in children earning 15% less in every year of their adult lives. The impact of school closures accounted for 10% of the gap in test scores, with children continuing to fall further behind once they returned to school due to the over-ambitious nature of the curriculum and pedagogies employed. In refugee settings, even a short shock can impact children’s school attendance and completion for a prolonged period, increasing exposure to protection risks, potential for increased drop-out rates, and limiting access to nutrition from school feeding programmes.
[note] Andrabi, T., Daniels, B. and Das, J., 2020. Human Capital Accumulation and Disasters: Evidence from the Pakistan Earthquake of 2005. RISE Working Paper 20/039.
[note] UNHCR presentation for ODI, 22/06/2020 https://www.odi.org/events/17021-adolescent-refugees-challenges-under-covid-19

School closures have also had a direct and detrimental impact on teachers. There may have been attrition of teachers in many countries, due to illness, fatalities, or wage delays or stoppages. Before COVID-19, there was a worldwide need to recruit an additional 69 million teachers by 2030 and losing teachers due to the pandemic will widen this gap.
[note] UNESCO, 2016 https://unesdoc.unesco.org/ark:/48223/pf0000246124

The continued presence and support of teachers during the pandemic can be a lifeline for families already on the brink. The effective delivery of education in emergencies requires teacher support systems to be established and maintained to ensure teachers show up to work, are motivated and teach effectively. Where budget constraints affect teacher salaries, paying stipends can be effective response. Retention of experienced and effective teachers is also vital, given the strong evidence that teachers’ play a critical role in improving learning outcomes. Multiple studies have shown large differences in learning for students taught by a ‘great’ teacher as opposed to a weak one and, year on year, this has a significant effect on outcomes. In fact, research has yet to turn up another school attribute with comparable influence on student learning. Ensuring that teacher cadres are maintained over the course of the crisis is therefore vital to mitigating the long-term impacts of the crisis. Evidence from the 2014 Ebola epidemic also shows that keeping teachers engaged – and engaging with students – is a crucial part of supporting return to schooling when it is possible.
[note] Cambridge Education (2017). Education in Emergencies Guidance Note. London: DAI Europe.
[note] Dolan, J. et al, (2012), Building effective teacher salary systems in fragile and conflict-affected states: Policy Report, The Centre for Universal Education, Brookings and CfBT Education Trust.
[note] Hanushek, E., & Rivkin, S. (2010). Using Value-Added Measures of Teacher Quality. Calder.
[note] Chetty, R. F. (2011). "The Long-Term Impacts of Teachers: Teacher Value-Added and Student Outcomes in Adulthood". Cambridge, Massachusetts: National Bureau of Economic Research.
[note] Hanushek, E (2011) "The economic value of higher teacher quality." Economics of Education Review 30.3: 466-479.
[note] World Bank, 2020, The COVID-19 Pandemic: Shocks to Education and Policy Responses, forthcoming.

Box 1: How are teachers contributing to continuity of learning, and preparedness, during COVID-19? / Teachers are continuing to work as much as possible to ensure continuity of education. Some examples of the types of activities UNHCR teachers are engaged in are included below. / Kenya (Dadaab): Teachers have been broadcasting programmes on the community radio station, Radio Gargaar, since the lockdown. Following social distancing and disinfecting protocols, teachers have been conducting lessons, reading stories and sharing health messages. They are working together via WhatsApp groups to create additional content including where it needs to be in local languages, and in some cases playing the FM station over loudspeaker where families may not have access to radios. / Chad: In refugee camps in eastern Chad, teachers and parents' associations have organized themselves by district and teachers are providing students with home exercises corrected each week. Papers are left outside homes, collected by parents’ groups then left for 48 hours in case of infection, marked by teachers and returned the same way for the next set. / Uganda: In 2019, UNHCR worked closely with SESEMAT (Secondary Science and Mathematics Teachers Training Programme) to train teachers on the use of online learning materials. These teachers have become “champion teachers” sharing guidance on how to make use of the Kolibri platform through WhatsApp groups for teachers. In addition, several teachers who benefited from this training have appeared on national television programmes to train and guide teachers on the use of online learning materials and how the platform works. ECW has put in funding to expand and support the use of Kolibri, but not for salaries. / Kenya (Kakuma): An education sector focused WhatsApp communication tree was activated following the closure of schools aimed at sharing important health and educational information to teachers and learners. The communication tree includes a cascade from UNHCR, Ministry of Education & partners to Head Teachers and then teachers (national and refugee staff). To ensure two-way communication and accountability, focal persons, appointed by the main education partners, ensure important updates and offline and online educational resources are shared with all the 1,182 teachers. The WhatsApp communication tree plays an important role, not only in supporting two-way communication but also support learning continuity for children, teacher training and mentorship. / Source: UNHCR

## The International Response

Internationally, education multilaterals are coordinating to develop a clear COVID-19 response strategy. Many of our key partners are offering specific support to countries to meet challenges caused by the COVID-19 pandemic. UN agencies are playing a coordinating role. UNHCR is stepping up its support refugee populations with health and sanitation, as well as continuing to advocate for refugees, including for refugee children to receive a quality education.

The Global Partnership for Education (GPE), and Education Cannot Wait (ECW) are offering increased financial support, flexibility and advocacy. Both organisations have opened new funding windows to provide targeted support to reduce the impact of COVID-19 on education systems and are supporting countries to flex existing grants to meet response needs by preparing to support countries to flex their existing grants to meet needs posed by COVID-19.
[note] https://www.educationcannotwait.org/covid-19/ and https://www.globalpartnership.org/gpe-and-covid-19-pandemic

However, there remains a funding gap for teachers in refugee settings. This is vital humanitarian support to mitigate against the immediate impact of COVID-19 for some of the most vulnerable children globally. Providing this humanitarian support will help to sustain systems to prevent a need to invest in more costly interventions to find teachers in refugee settings after the current crisis.

## Why Should the UK Intervene?

Progress made on access to education is at risk due to the secondary impacts of the COVID-19 pandemic. Without direct support, the beneficiaries targeted under this programme – some of the world’s most marginalised children – will drop out of school permanently, which is at odds with Manifesto Commitments and Ministerial priorities to stand up for the right of all girls to have 12 years’ quality education. Supporting children in refugee settings to continue their education, through supporting their teachers to continue working, supports the UK’s five-year Girls’ Education Action Plan, and new targets for access and quality in response to the COVID-19 crisis.

Support to refugee teachers directly contributes to DFID’s agreed education response to COVID-19, which aims to (i) mitigate risks to pupils and the education workforce in the short-term and (ii) preserve the education system and education finance in the medium- to long-term. The programme also contributes to DFID’s 2018 Education Policy’s strong focus on supporting teachers to enable all children to gain foundational skills, and targeted support to the most marginalised.

UNHCR are the biggest funder of refugee teachers’ salaries but are struggling to maintain these in the face of other needs. Without additional support to ensure teachers in refugee settings can continue in their roles, the most marginalised refugee children will almost certainly lose out on education now and in the future.

## Proposed Activities and Results

We will support 5,669 teachers in Chad, Kenya, Malawi, Mauritania, Pakistan, Rwanda, Sudan, South Sudan, Uganda and Yemen to deliver vital education and child protection support over 7 months. These are countries where support to teachers is at immediate risk due to funding constraints in the immediate aftermath of COVID-19.

Although the intervention is short term in nature, it is vital for sustainability and for grasping emerging opportunities to reopen education system better. Supporting teachers in refugee settings to continue their work in the short term will sustain the system and support learning in the short term and reduce the risk of major disruption of having to recruit and train a new cohort of teachers once immediate funding constraints are overcome.

## Compliance with Relevant Legislation and Commitments

Gender Equality: CEER is fully compliant with the International Development (Gender Equality) Act 2014, as well as DFID’s strategic Vision for Gender Equality (2018).

Development Act: CEER has a long-term aim of poverty reduction and to build the human capital of target countries. Humanitarian response is a priority of the UK Aid Strategy November 2015, Single Departmental Plan 2015-2020, and the International Development Act 2002. This programme firmly supports the UK national interest and UK Aid Strategy’s objectives: tackling extreme poverty and helping the world’s most vulnerable; and strengthening resilience and the international response to crises.

Public Sector Equality Duty: CEER will have due regard to the responsibilities set out in the Public Sector Equality Duty throughout the lifetime of this programme.

Counter-Terrorism Act: the risks of funding being used for terrorism is low. CEER will comply with domestic law and international sanctions on terrorist financing. We will draw on DFID expertise to adhere to best practice. Strong financial controls and risk management will be in place, and Central Assurance Assessments on relevant partners have been largely updated to incorporate DFID policy updates. These actions will strongly reduce the risk that funds for this programme are used for terrorist activity.

Climate and Environment: In terms of impact on environmental degradation and increased vulnerability to climate change, CEER is low to medium risk with limited negative impacts.

Partnership Principles: Under this programme, no UKAid money will go directly to another government, so will not use the Partnership Principles as a formal conditionality. However, support will be given in cooperation with the partner government in each country of operation following a partnership model.

Disability: CEER has equity considerations at its heart. The proportion of people with disabilities in refugee settings is higher than in other populations, so continuing to support teachers for these children will have a disproportionately beneficial impact on children with disabilities.
[note] For example, see https://www.hi-us.org/1_5_syrian_refugees_has_disability

Safeguarding: CEER will comply with DFID’s Smart Rules on Safeguarding and adopt a do no harm approach. Implementing partners will monitor, mitigate and address Safeguarding risks and will be required to have appropriate processes in place. In some contexts, the programme will work violence (including sexual violence) against women and girls is common. In line with DFID’s policy on combatting violence, CEER will seek to address harmful norms and practises, through support given by teachers in refugee settings to children at risk.

Conflict and Fragility: as part of an emergency response, CEER will need to carefully consider wider conflict and political dynamics. It is vital that multilateral COVID-19 response work does not do more harm than good. Interventions in education must have equality at their heart to not exacerbate any conflict dynamics. We will ensure conflict sensitive approaches are adopted by maintaining close engagement with multilateral implementing partners both at headquarters and through DFID country offices.

## Appraisal Case

## Appraisal of Delivery Options

This section appraises delivery options for emergency response in the education system during the COVID-19 pandemic, specifically to support to teachers in refugee situations in 10 countries to continue providing education to marginalised children.

The following criteria guided the appraisal of feasible delivery options:
  1. Make an impact quickly through partners with proven expertise;
  2. Support, not distort, existing education architecture;
  3. Global presence enabling multi-country reach without significant burden on DFID management; and
  4. Measure and deliver value for money through programme efficiencies of scale and active management of key cost drivers.

Three options were identified for appraisal: (1) “do nothing” counterfactual; (2) funding via an existing multilateral partner – ECW or GPE; and (3) delivery through UNHCR. Each of these options has been scored against criteria i-iv above on a range from 0 (does not fulfil criteria) to 5 (fulfils criteria perfectly), in Table 1 below, and additional information is given in the narrative selection below.

Table 1: Summary of Options Appraisal
	“Do Nothing” Counterfactual	Funding via ECW or GPE	Funding via UNHCR
Make an impact quickly through partners with proven expertise	0	3	5
Support, not distort, existing education architecture	0	2	5
Global presence enabling multi-country reach and reduce DFID’s management burden	0	5	3
Measure and deliver value for money	0	3	4
Total	0	13	17

## Option 1: Do nothing counterfactual

Doing nothing would result in the end of education for many of the world’s most vulnerable children, who are likely to drop out of school altogether and not return following COVID-19 school closures, without this humanitarian support. Without additional funding to support teachers in refugee situations, there would be a long interruption to the education of vulnerable refugee children, many of whom may struggle to return to education at all if this happens, and also a significant impact on the other work that these teachers do, such as health messaging.

Given the urgency of need, and the UK’s commitment to education, Option 1 is rejected.

## Option 2: Fund via an existing multilateral partner, such as ECW or GPE

DFID has explored whether the desired outcomes could be met through increasing funding to an existing multilateral partner, such as GPE or ECW, which between them have sufficient country reach to meet CEER’s objectives. DFID is the largest bilateral donor to both organisations, which are already flexing support to countries to support COVID-19 education responses. These existing modalities would not significantly increase DFID’s management burden, since the funds could be managed with our existing payments.

Both partners offer funding to programmes that are designed by the country government in cooperation with development partner groups. This modality means that we cannot define where the funds go, and government priorities are unlikely to cover teachers in refugee settings, or able to focus sufficiently on the most disadvantaged.

GPE has already repurposed £500m through its COVID-19 response window, and we consider that it would be better for them to re-purpose existing money in their budgets before granting them additional funding for this programme.

ECW’s first and second response windows, to support COVID-19 responses, is available only to existing ECW recipient countries, and therefore excludes some large refugee hosting countries (e.g. Sudan). In addition, the grants (up to $1.5m per country in the first round) are insufficient to cover teacher incentives alongside the WASH, nutrition and distance learning activities which have been prioritised.

We have considered requesting that these partners direct the funds through a specific window, for example a refugee window, but do not believe that this would lead to the impacts outlined above, due to incentives to focus on inputs rather than teachers. Supporting a separate ‘Refugee Window’ within either partner with UK funds would not enable us to target the teachers directly. The allocation of funds is decided at country level by partners, including government, who are unlikely to prioritise refugee needs, nor the education workforce specifically. It would also be less cost effective as would incur additional administration charges by transferring funds first through GPE/ECW and then to UNHCR. Doing this would also interfere with the existing education architecture.

Due to the desire to sustain existing education architecture, and reduce unnecessary administration costs, Option 2 is rejected.

## Option 3: Provide funding directly to UNHCR

The third option is to fund UNHCR, an existing partner with known expertise and experience in providing support to teachers in refugee areas.

UNHCR has existing mechanisms to support teachers in refugee settings through an established network of downstream NGO partners (see delivery chain mapping at Annex 1) which enables children affected by conflict to access education. They are currently struggling to maintain these in the face of other nutrition and health needs in refugee settings. In most camp settings, UNHCR pays for teachers whether they are nationals (where the state does not pay their salaries) or ‘incentive’ teachers (i.e. refugees themselves). In very rural refugee hosting areas, UNHCR may pay an additional incentive. Payment amounts are determined by the local context. As the largest payer of teacher incentives in refugee settings, UNHCR has established a rigorous system to support teacher payments through a network of vetted NGOs. Channelling support through UNHCR therefore has value for money benefits of using existing systems. Funding through CEER would enable UNHCR to continue these payments which would ensure teachers’ support to the education system, children and communities can continue during the COVID 19 school closures, and their part in vital outreach to get children back to school thereafter. As the largest payer of teacher incentives in refugee settings, UNHCR has established rigorous systems to support teacher payments. If DFID were to fund the NGOs directly it would mean upwards of 20 accountable grants to deliver payments, this would be costly and time-consuming to set up and difficult to monitor effectively, leading to risks which exceed our current risk appetite.

Due to the benefits of channelling funds through existing mechanisms, and to an organisation that specialises in the specified outcome, Option 3 is the preferred delivery mechanism.

## Theory of Change for the Preferred Option

CEER’s Theory of Change is presented below. Evidence for this Theory of Change is strong. It is based on extensive learning from DFID programming and responses to past crises, as well as knowledge from the global evidence base and the Education Best Buys paper. Evidence is weaker on the extent to which immediate support and technical assistance will improve the long-term resilience of education systems to crises. A summary of evidence is included below the Theory of Change diagram.

## CEER’s Theory of Change

*Figure of 300,000 children assumes that 5,669 teachers in refugee settings are reached with support and each provide support services to approx. 53 children spilt over 2 classes. The latter figure is based on the assumption that average student-teacher ratios meet UNHCR guidelines, which specify no more than 40 students per teacher.
[note] UNHCR (2003) ”Education Field Guidelines” Link: https://www.unhcr.org/uk/protection/operations/40586bd34/education-field-guidelines.html

## Evidence for the Theory of Change

Despite school closures, teachers in many contexts are continuing to serve their communities and are particularly relied upon by IDP and refugee children. They are offering remote learning and psycho-social support to students (e.g. via phones, radio or delivering learning packs) and providing vital public health information (for examples see Box 1). Their continued presence and support during the pandemic can be a lifeline for families already on the brink. While data are limited, recent research also suggests quality Education in Emergencies and Protracted Crises (EiEPC) requires teacher support systems to be established and maintained to ensure teachers show up to work, are motivated and teach effectively. Where budget constraints affect teacher salaries, paying stipends can be effective. Retention of experienced and effective teachers is also vital, given the strong evidence that teachers’ play a critical role in improving learning outcomes. Multiple studies have shown large differences in learning for students taught by a ‘great’ teacher as opposed to a weak one and, year on year, this has a significant effect on outcomes. In fact, research has yet to turn up another school attribute with comparable influence on student learning. Ensuring that teacher cadres are maintained over the course of the crisis is therefore vital to mitigating the long-term impacts of the crisis. Evidence from the 2014 Ebola epidemic also shows that keeping teachers engaged – and engaging with students – is a crucial part of supporting return to schooling when it is possible.
[note] UNDP (United Nations Development Programme). 2015. Recovering from the Ebola Crisis. https://www.undp.org/content/dam/undp/library/crisis%20prevention/Recovering%20from%20the%20Ebola%20Crisis-Full-Report-Final_Eng-web-version.pdf
[note] Cambridge Education (2017). Education in Emergencies Guidance Note. London: DAI Europe.
[note] Dolan, J. et al, (2012), Building effective teacher salary systems in fragile and conflict-affected states: Policy Report, The Centre for Universal Education, Brookings and CfBT Education Trust.
[note] Hanushek, E., & Rivkin, S. (2010). Using Value-Added Measures of Teacher Quality. Calder.
[note] Chetty, R. F. (2011). "The Long-Term Impacts of Teachers: Teacher Value-Added and Student Outcomes in Adulthood". Cambridge, Massachusetts: National Bureau of Economic Research.
[note] Hanushek, E (2011) "The economic value of higher teacher quality." Economics of Education Review 30.3: 466-479.
[note] World Bank, 2020, The COVID-19 Pandemic: Shocks to Education and Policy Responses, forthcoming.

Channelling resources through existing programmes will limit fragmentation of response. There is considerable evidence that coordination challenges are a major barrier to the effective and efficient provision of education in crisis contexts. This lack of coherence is particularly notable across humanitarian and development actors (including national governments), but is also a challenge between humanitarian actors. Channelling resources through established actors and programmes, rather than duplicating or establishing new structures, should therefore limit the extent of coordination challenges and assist in developing a more coherent response.
[note] Nicolai, S., et. al., 2016. A common platform for education in emergencies and protracted crises: Evidence paper. London, ODI.

## Value for Money

A cost-benefit analysis was not undertaken as part of the appraisal case. This primarily reflects the difficulty in monetising the benefits of the activity. Therefore, a cost-benefit analysis would not help the appraisal and ultimately the choice between the different options.

Of course, though, CEER will carefully work towards achieving good Value for Money (VfM). This ensures that we get better outcomes for the intended beneficiaries. We have used the Smart Guide tools and approaches for managing humanitarian VfM and deploy the typical DFID methodology for assessing the VFM of this intervention by looking at the 4 Es: Economy, Efficiency, Effectiveness and Equity. For humanitarian interventions, we would typically interpret 'economy' as cost, 'efficiency' as speed, and 'effectiveness' as quality.

Synergies with other programmes will also support VfM for UKAid overall. We already work extensively in very fragile settings, through bilateral programmes as well as multilateral investment in ECW. The proposed support to teachers in refugee settings maximise the impact of existing interventions which work directly at school and pupil level.

Economy: We are seeking to achieve the objectives of the Theory of Change by selecting activities achievable at the lowest cost for maximum benefit. CEER has been designed to support an intervention – payments to teachers in refugee settings – that will sustain education interventions, which in the medium term will lead to substantial cost savings compared to having to re-establish systems. In addition, working through partners already established providing support will mean that set-up and overhead costs are kept low.

Effectiveness: The quality of interventions is maximised by ensuring that we are delivering the intervention through a tried and tested, trusted partner.

Efficiency: Given the enormity of the necessary response, and the need to intervene quickly to support on-going learning and prevent school drop-outs we need to ensure that this intervention reaches intended beneficiaries as soon as possible. Using an existing partner and payment system will enable us to do this.

Equity: Both the primary and secondary impacts of COVID-19 are likely to have a disproportionate impact on the most vulnerable groups. This is true in the education sector, where the most marginalised, including girls and children affected by crisis, are likely to drop out of school if not given targeted support. CEER’s intervention has been specifically designed to support these most marginalised groups. Funding will be provided to partners to ensure an inclusive response which fulfils the global commitment to Leave No One Behind. UNHCR has pre-existing commitments to gender and protection, which have been developed and / or guided by DFID advisers.

DFID will work closely with partners before agreements are signed to ensure maximum VfM. The funding amounts for each activity are based on immediate need, informed by partners. Funding to support teachers in refugee settings is based on the numbers of teachers that require support over the next six months, and we have worked closely with UNHCR to ensure that the amount will cover just these costs.

## Commercial Case

The preferred option above will provide £5.3m through UNHCR to support to teachers in refugee settings. This section sets out the commercial arrangements for managing payments to UNHCR. Funding will be made under a Memorandum of Understanding (MoU). This delivery option has been chosen to enable us to disburse DFID funding quickly and efficiently and providing the best VfM option for DFID. The agreement used will follow DFID Smart Rules. Budgets and other information provided by partners will be scrutinised by the Programme Team before the MoU is signed.

UNHCR is the UN Refugee Agency, a global organisation dedicated to saving lives, protecting rights and building a better future for refugees, forcibly displaced communities and stateless people. UNHCR already leads internationally on support to teachers in refugee settings, and so we have strong confidence that they have the required capacity to deliver payment of salaries and incentives under CEER.

UNHCR already provides salary and incentive payments to refugees in the countries that CEER will support. However, due to the extent of need in other areas – particularly health and WASH – the agency lacks sufficient funds to cover the period from August to February 2021. In most camp settings, UNHCR pays for teachers whether they are nationals (where the state does not pay their salaries) or ‘incentive’ teachers (i.e. refugees themselves). In very rural refugee hosting areas, UNHCR may pay an additional incentive. Payment amounts are determined by the local context. As the largest payer of teacher incentives in refugee settings, UNHCR has established a rigorous system to support teacher payments through a network of vetted NGOs.

Support from CEER would enable payments to continue over this crucial time, and sustain education, and also reduce the risk of teachers leaving the system, which would be much more costly to re-establish if these teachers leave the system due to lack of support. Thus, VfM is increased.

## Maximising Value for Money

The UK engages with UNHCR regularly, through well-established relationships including a DFID institutional lead. Through this relationship, and other programmes that are funded using UKAid, the UK is active in driving greater efficiency, including value for money, stronger leadership, transparency and financial accountability from UNHCR. Working within the global community achieves our outcomes at a lower cost of administration, ensuring maximum VfM – both on our COVID-19 response but also by allowing DFID to focus on ensuring that COVID-19 does not undermine our wider programmes. In addition, by investing in existing programmes through UNHCR DFID can reach some of the most marginalised children in the world, including where we do not have a bilateral footprint.

DFID already has institutional level agreements with UNHCR , and we are reassured that our partners have an approach to VfM that will ensure that UK funds are used to achieve this maximum impact, that this is understood by partner staff and that partners have good procurement processes and capability to respond to this crisis.

## Fraud and Corruption

UNHCR has stated policies on tackling fraud and corruption and are clear on expectations and requirements from DFID and has been reviewed by a Central Assurance Assessment (CAA) with ongoing systematic follow up overseen by DFID’s institutional leads. DFID will ensure that fraud and corruption risks are regularly reviewed and updated in discussion with partners through this programme. Cash transfers will be used to support teachers in refugee settings. Payments are made electronically where possible and through direct cash transfers where not. Money can be directly traced to recipients minimizing risks of fraud or misappropriation and strong mitigation systems are already in place. Downstream partners are required to have a Harmonised Approach to Cash Transfers (HACT) assessment; if organisations are not within the UN system and therefore not covered by HACT, UNHCR manages downstream external spot-checking.

## Key Commercial Risks

The UK has worked intensively with UNHCR over a sustained period. The UK understands and has supported improvements in the organisation’s approach to risk management. As a result of the CAAs in place, and our ongoing engagement, significant improvements have been and continue to be made by partners. We are therefore confident that funding of these partners is within DFID’s risk appetite.

There will be a low tolerance for fiduciary risk. A full delivery chain map for the support to teachers in refugee settings is provided in Annex 1. If there are any changes during the life of the programme, these delivery chain maps will be updated. A risk register will be utilised to monitor risks, and this will be discussed at least every three months by the Programme team.  The main risk currently identified is the fiduciary risk around teacher incentive payments.

Given the nature of the COVID-19 context the residual risks remain high, and we will continue to monitor closely during the lifetime of this programme.

## Synergies with Existing Programmes

The activity set out in this Business Case is a humanitarian activity, to meet immediate and critical gaps. It is an intervention that our bilateral country programmes, and other investments, are not currently covering. CEER will however each support other existing education programming. Supporting teachers in refugee settings will enable education to continue, and since school and teachers so often offer more than just learning, this form of immediate support to education will also support wider DFID programming on health and social protection. We already work extensively in very fragile settings, through bilateral programmes as well as multilateral investment in ECW. The proposed support to teachers in refugee settings in some of these contexts will enable our education programmes to continue improving access to quality education for the most marginalised children in these contexts.
## Financial Case

## What are the costs, how are they profiled, and how will accurate forecasts be made?

As with other aspects of the COVID-19 immediate response, funding arrangements are short: for seven months. The MoU will include details of disbursements. DFID will allocate up to £5.3m to this programme which will all be provided to UNHCR in the 2020/21 Financial Year.How will the programme be funded?

This funding is ODA eligible, and funds have been identified for the full project life cycle. The programme will be managed and funded by DFID’s Children Youth and Education Department (CYED). During the re-prioritisation exercise we examined CYED budgets for savings this financial year in programmes which are currently unable to operate and / or which represent lesser priorities. As the need for this support is critical and time-bound, we propose using £5.3m of CYED’s identified savings to support this programme.

## How will the funds be paid out?

Disbursement will be made as a pre-payment on signing of the MoU with the partner organisation, which is standard for multilateral payments. The MoU arrangement and payment schedule will be based on the need for UNHCR to utilise funds quickly to alleviate and address critical needs. Since the funds are based on humanitarian needs and requirements from partner organisations, we are confident that these payments will not be made in advance of need.

## Cost drivers

The key cost drivers for this programme will be for personnel costs: for teachers in refugee settings. The costs are set based on local benchmarks in every country covered. Through our management relationships, we will ensure agencies continue to monitor cost drivers and ensure the programme manages costs well.

## Monitoring, reporting and accounting for funds

DFID will monitor funds throughout the programme cycle through financial reports at three, six and nine months (at project closure) from partners. UNHCR has an annual audit. Audit report and annual accounts will be provided to DFID for assurance. We will liaise with DFID’s Internal Audit Department (IAD) if and when reports of fraud or safeguarding concerns are received from partners.

## Assessment of financial risk and fraud

DFID has a policy of zero tolerance towards fraud. All financial agreements have clauses highlighting our expectations that partners will immediately notify us of any concerns, suspicions, allegations or incidents. The CAA undertaken on UNHCR includes their ability to manage downstream suppliers. DFID expects UNHCR’s fraud and corruption procedures for downstream partners to be in line with DFID’s standards of best practice.

UNHCR has established a rigorous system to support teacher payments through a network of vetted NGOs. Payments are made electronically where possible and through direct cash transfers where not. Money can be directly traced to recipients minimizing risks of fraud or misappropriation and strong mitigation systems are already in place.

UNHCR and downstream partners will use existing systems to ensure correct targeting. Payments are made electronically where possible and through direct cash transfers where not. Money can be directly traced to recipients minimizing risks of fraud or misappropriation and strong mitigation systems are already in place. Downstream partners are required to have a HACT assessment; if organisations are not within the UN system and therefore not covered by HACT, UNHCR manages downstream external spot-checking.

Given the context in which UNHCR is working the risk rating is major however, with robust mitigation strategies in place the residual risk is moderate and within DFID’s risk appetite. If fraud is detected, DFID will require full remedial action including repayment in full if the fraud involves diversion of UK funds. Continued disbursement of funds will be contingent on adequate financial oversight mechanisms.

## Management Case

## Management arrangements for implementing the intervention

The project will be managed by the Children, Youth and Education Department (CYED) in DFID which holds programme, policy and financial oversight of DFID’s central investments in education. The Senior Responsible Owner (SRO) will be an Education Adviser, who will be responsible for: monitoring the results, ensuring compliance with Smart Rules, providing technical advice and scrutiny, advising on ministerial and parliamentary engagement, and providing direction to the core programme team and the implementers. Further support will be provided by a B1 programme manager who will be responsible for: overall programme management including risk management, financial management, and all other aspects of the delivery plan.

## Monitoring and Evaluation

Results reporting arrangements will be finalised during negotiation of the MoU. Given the nature of the funding (i.e. direct salary payments to teachers) DFID’s principal form of monitoring UNHCR will be through financial reporting. A draft, simplified logframe to reflect this will be prepared and discussed with partners before finalisation. This will form the basis for assessing progress against headline outcomes. All monitoring will be disaggregated by gender, disability and IDP/host status, to understand the impact on different groups in society where possible.

Given the complex nature of the response and need to retain partners’ focus on quick start up and rapid delivery, no bespoke reports on delivery will be routinely required from UN partners.  DFID will work with the partner, using the experience of the DFID Institutional Lead where appropriate, to ensure regular dialogue combined with the reporting we will receive produces the greatest amount of information feasible.

Since the programme will last less than one complete year, we do not foresee any Annual Reviews. At the end of the programme, the SRO will prepare the Project Completion Report (PCR) in line with DFID guidelines to monitor impact against the programme logframe indicators. This will be done in consultation with country offices where the programme is active and will inform DFID’s lesson learning for future education interventions.

## Risk Management

The DFID programme team will have regular conversations about risk with UNHCR, considering the continued relevance of existing risks; noting emerging risks; reviewing the progress of mitigating actions; and recording changing levels of risk on the programme risk register. If any risks increase beyond our risk appetite, we will act quickly to escalate this to the department’s Senior Leadership Team and take mitigating actions. If an adverse event happens, whether or not it has previously been identified in the risk register, DFID procedures will be followed to escalate and control as appropriate.

DFID programmes operate in inherently high-risk environments, delivering emergency responses under challenging circumstances. The nature of DFID’s work in these contexts relies on our partners maintaining a strong control framework, actively addressing weaknesses identified and managing risk. UNHCR has strong risk management tools in place, including:

  1. Detailed policies and guidelines on risk, including safeguarding risk
  2. Strong financial controls and policies on fraud and corruption
  3. Clear reporting lines if risks increase or are realised
  4. Institutional and programmatic risk registers
  5. Embedded programme management specialists

Overall, this programme is medium risk. Risks have been identified under the following broad areas: reputational, delivery, safeguarding, fiduciary. When children and young people are the focus of programming and when this programming takes place in FCAS contexts, there is an increased exposure to safeguarding risks. Safeguarding will be given the highest priority, and detailed plans are included below. Delivery chain mapping (Flag A), risk matrix (Flag B) and child safeguarding assessments (Flag C) are attached.

Table 2 below outlines the key risks and mitigating actions.

Table 2: Risks and Mitigation Summary
#	Risk	Mitigating actions	Probability	Impact	Residual risk
	Reputational
1	Fraud, corruption, political and safeguarding concerns materialise and bring reputational harm to UK.	Regular checks that money is being effectively spent, at least once every three months. / DFID will maintain transparency through publication of projects on DevTracker / Suspend/cease partnership if risk materialises and not adequately addressed.
	Delivery
2	Programme is delivered inequitably or perceived as benefitting one group over another, meaning that the most marginalised will not be supported.	Ensure gender, conflict and disability are part of the log frame and oversight.
3	Major outbreak of COVID-19 pandemic in implementation area – schools not open, government attention disrupted, and reduced movement – could hinder efficiency of delivery.	DFID will support the partners in: / Adherence to government guidelines. / Supporting home-based learning and safety if necessary.
4	UNHCR and other partners unable to deliver within current capacity, risking programme outcomes.	DFID will support the partner to: / Carry out careful mapping of roles and responsibilities vis-a-vis project deliverables. / Leverage existing and proven systems, tools and protocols including closely following Standard Operating Procedures for teacher payments where these exist. / Maintain and manage communication lines with Ministries of Education to align with their approaches to protecting the education workforce during COVID-19 and continue to use this period as a time to lobby for greater integration of refugees into national systems, including within the education sector. / Working with local partners to be able to identify the most marginalised.
	Safeguarding
5	Schools continue to be closed so children and teachers cannot attend. Children would therefore be missing a protective environment and may then engage in harmful coping mechanisms.	Working with other parties in each country of origin to spread safeguarding messaging as necessary. / DFID will support the partners to: / Recognising this is the case due to major health risks, work in this area is to mitigate the impact whilst engaging with MoH and MoE at country level to be ready to support return to school when possible. / Provision of school modes of learning such as online learning, radio school programmes (outside the scope of this project).
6	Weak safeguarding practices mean abuse not identified and addressed risking exploitation, abuse, harassment and reputational risk.	All partners work in line with the UN Child Protection and Child Safeguarding Policies. / Check that partners ensure that all staff sign the code of conduct, understand it and provide continuous sessions for staff on code of conduct; adopt use of school incident reporting form and harmonized inter-agency reporting mechanism to ensure all cases of abuse are investigated and properly addressed. / CAA covers safeguarding, and we will liaise with Agency Leads to ensure that this remains up to date. CYED will liaise with the dedicated safeguarding team within DFID’s Internal Audit Department when reports of safeguarding concerns are received.
	Operational
7	High turnover of teaching staff compromising quality of education	Project is designed to prevent teaching staff from leaving in case there are concerns about salaries and incentives. / DFID will support the partner to work with other partners to support teacher training / development and invest in continued communication with and between teaching staff to ensure accurate information is disseminated.
8	Closure of bank branches in camp vicinities leading to delays in payments and teachers seeking other work and disengaging	DFID will support partner to: / Collaborate with commercial banks to ensure regular distribution of salaries and incentives / Ensure that transfers from UNHCR to downstream partners are regular
	Fiduciary
9	Occurrences of errors, fraud and corruption leading to aid diversion.	Adequate and credible financial management systems were critical part of the CAA. Comprehensive financial reporting requirements, where appropriate, will be set out in the arrangements and programme teams will review these closely and regularly. Ensure that implementing partners are aware of the Standard Operating Procedures around teacher payments and that these are followed; / Payments to be made to verified teachers who are registered with implementing partners or UNHCR and whose engagement is verified by schools.
10	Potential displacement of other DFID investments by CEER activities leading to lower overall efficiency of UK spend.	Engagement of DFID education advisers in country to ensure their involvement to make all investments complementary. / CEER has been designed to complement, not repeat, other investments.

## Annex [1]: Delivery Chain Map for Support to Teachers in Refugee Settings