Evaluation Report for Programme Name: Reducing Maternal and Neonatal Deaths in Kenya

Response to Summative Evaluation Report (overarching narrative)
The Reducing Maternal and Neonatal Deaths in Kenya Programme was originally a £75.3 million programme over five-years (2013-2018). After programme restructuring in 2017, the budget was reduced to £60.6m. From then the programme had three linked components all of which were included in this evaluation: / the Maternal and Newborn Initiative (MANI) health system strengthening (HSS) project in Bungoma County which included demand and supply side systems; / the County Innovation Challenge Fund (CICF) which supported 19 innovations or scale up initatives in six counties; and / the Making it Happen (MiH) health worker programme in 32 counties which delivered in-service and pre-service training on emergency obstetric and neonatal care. / This summative evaluation was commissioned by DFID to generate evidence on the effectiveness of strengthening health systems towards the reduction of maternal mortality. The evaluation assesses the relevance, effectiveness, efficiency and sustainability of the DFID-funded contributions to the improvement of maternal and newborn care in Kenya between 2013 and 2018. It also, to the extent possible, explores the impact of the Programme. / The programme uses the ‘three delays’ model, which identifies three groups of factors that may stop women and girls accessing the levels of maternal health care they need. The first and the second delays (delay in a decision to seek care, and delay in reaching care) are addressed through demand generation under MANI HSS and through about half of the projects funded under the CICF. MANI HSS, LSTM MiH and the remaining CICF projects address the third delay: to receive adequate health care. / We are pleased that the evaluation report found some positive impacts of the programme achieved through the activities of the three components, and also through the combined impacts which established Maternal and Newborn Health (MNH) as a priority in the political agenda. / The evaluation report was quality assured by EQUALS and rated excellent

Evaluation Report Title: Evaluation of the Maternal Health programme

Recommendations: DFID	Accepted or Rejected	If “Accepted”, Action plan for Implementation or if “Rejected”, Reason for Rejection
Recommendation 1: / Under its strategy for the improvement of maternal and neonatal health, DFID should continue to work with government and partners in the implementation of a comprehensive health systems approach that addresses all factors that affect service delivery as well as all levels of system governance, management and implementation: The national and county level for policy, regulations and strategies; and the county, sub-county, facility and community level for implementation. The strategy should also address the needs of all service providers in the public and private (faith-based, charitable or for-profit) sectors.	Accepted	Whilst we agree with this recommendation, our ability to implement will depend on a) technical staff capacity, b) our programmatic levers/available programme funding and c) what happens with the FCDO merger and reduced ODA in the wake of Covid-19’s global economic impacts. / Bearing the above in mind, we will continue -where possible -to work through the various levers at our disposal (bilateral MNH and FP programmes), Global Funds (such as GFATM, GAVI and GFF), multilaterals such as WB, WHO etc to support UHC in Kenya and ensure a whole system strengthening approach is taken, putting MNH outcomes front and centre.
Recommendation 2: / a) Under its strategy for the improvement of maternal and neonatal health, DFID should adopt a longer time horizon for its cooperation programmes and focus on supporting proven solutions until financial and technical implementation capacity is ensured. a. Responsibility for financing and management of cooperation programmes should be gradually transferred to domestic partners throughout the implementation period. / b) Withdrawing technical partner support when a project has ended may reduce the confidence of local partners in continuing effective programmes and activities. This should be taken into account in sustainability planning by making provisions to continue coaching and/or virtual technical support after on-site technical support has ended.	Accepted	Whilst we agree with this recommendation, our ability to implement will depend on a) technical staff capacity, b) our programmatic levers/available programme funding and c) the priorities within the soon-to-be formed new department FCDO and reduced ODA in the wake of Covid-19’s global economic impacts. / DFID K’s health team was about to begin designing a new (more holistic) health programme which would have focussed on MNH outcomes, taken a more systemic approach and a longer-term timeframe. However, the design of a new programme is currently on hold whilst future programme budgets are clarified in light of GNI reductions.
Recommendation 3: / a) When developing multi-partner programmes for MNH with a systems approach, DFID should ensure that: a. Projects within the same programme envelope collaborate to maximise synergies and do not work in isolation. This requires more than regular meeting and sharing experiences. It requires proactive thinking on how projects can jointly achieve higher value for money by coordinating their strategies and learning from each other. / b) Technical support at the operational level for health system strengthening is provided by a team working closely with the responsible national institution at the political, managerial and technical levels rather than by individually contracted experts or partners responsible for distinct systems and service components.	Accepted	This recommendation has already been implemented and this lesson was learnt from previous annual reviews…. The MNH programme partners now have quarterly meetings where we maximise cross-learning and joint conversations to maximise synergies. We are also going to share each partners’ quarterly reports with other partners. / This recommendation has also been implemented. The WB’s MDTF (multi-donor trust fund) which is part of this bilateral programme has been encouraged (Through DFID’s participation in the governance body) to move away from contracting individual consultants to working with fewer firms which can invest in these relationships.
Recommendation 4: / DFID should provide sufficient technical and financial resources to support implementation research generating credible evidence that interventions for comprehensive health systems support as well as projects piloting innovations are effective, equitable and efficient in the context where they are implemented. This goes beyond simply documenting the project outcomes.	Accepted	Whilst we agree with this recommendation, our ability to implement will depend on a) technical staff capacity (which is currently being reduced in DFID K, b) our programmatic levers/available programme funding and c) what happens with the FCDO merger and reduced ODA in the wake of Covid-19’s global economic impacts.
Recommendation 5: / DFID should ensure that its programmes for MNH support all aspects of maternal and neonatal care, including antenatal, delivery, postnatal and early neonatal care.	Accepted	Whilst we agree with this recommendation, our ability to implement will depend on a) technical staff capacity (which is currently being reduced in DFID K, b) our programmatic levers/available programme funding and c) what happens with the FCDO merger and reduced ODA in the wake of Covid-19’s global economic impacts. There is not currently enough programmatic/financial/technical support in Kenya for these aspects of health.