## Annual Review

Title: Technical Assistance for UK Africa Investment
Programme Value £ (full life): up to £4.5m		Review date: Aug 2020
Programme Code: 301001	AMP start: 15 Aug 2019	AMP end: 31 Mar 2021

Summary of Programme Performance
Year	2020
Overall Output Score	A
Risk Rating

DevTracker Link to Business Case:	N/A
DevTracker Link to results framework:	N/A

A. SUMMARY AND OVERVIEW
Description of programme
1. The programme provides technical assistance to support increased investment, including from the UK, to African countries, thereby supporting economic growth and job creation. Phase 1 (Aug 2019 to Mar 2020) covered delivery of various events supporting the UK Africa Investment Summit (UKAIS) held in London on 20 January 2020. Phase 2 (April 2020 to Jan 2021) is providing advice to African governments to tackle the COVID-19 economic response. The programme delivers through a Technical Assistance Facility (the Facility) run by PwC and is managed jointly by DFID, DIT and FCO as part of the Growth Gateway programme. The total programme budget (for both phases) is up to £4.5 million. Expenditure to date is £2.1m of which £2m was for Phase 1.
  [note] Contract procured under DFID’s General Economic Development Framework, worth up to £4.5m – draw down model, from October 2019 to January 2021.
  [note] https://www.gov.uk/government/news/growth-gateway-announced-at-uk-africa-investment-summit
2. Following the onset of the COVID-19 crisis in early 2020, the programme pivoted to support African partner governments to mitigate the economic consequences of the pandemic. For example, by supporting investor retention and development of sector recovery plans. Specific Summit deliverables are not part of this programme and are therefore not assessed or referenced here.
  [note] https://www.gov.uk/government/topical-events/uk-africa-investment-summit-2020
Summary supporting narrative for the overall score in this review
1. The programme achieved expectations and therefore scored an A against log frame targets.
2. The Facility was established quickly (from mobilisation to implementation in two months) and delivered on its key objective of supporting a successful UKAIS through successful side events, country factsheets and technical assistance. Under Phase 2, the programme is supporting African governments to prevent excessive economic damage, continue to attract and retain investment flows, prevent excessive unemployment and firm closures and keep supply chains intact.
Major lessons and recommendations for the year ahead
Phase 1 (August 2019 – March 2020):
- Timeframes: The volume of work around the logistics of events planning as well as execution of events in quick succession (5 side-events over a 7-day period in January) was a significant challenge. This scheduling was outside the programme’s control. It meant that communication plans for side events, production of factsheets and prospectuses, and design of the results framework were rushed. Building in flexibility into programme terms of reference to adapt to short-notice change of plans is essential allowing the programme to scale up and down as required.
- Flexibility and adaptability: The Facility was designed to be flexible. This proved essential in Phase 1 and worked well. It would have helped to have had a longer inception period to set up clear and efficient policies, processes and establish solid working relationships.
- Approach to monitoring: The programme collected feedback on the Summit and side events primarily through an on-line survey. This generated some useful data but could have been complemented by qualitative data. Additionally, due to time constraints baseline data could not be collected which limited the ability to assess progress against the outputs. Recommendation: For the remainder of Phase 2, DFID / the Facility should consider the best tools for obtaining qualitative and quantitative feedback as well as pragmatic solutions to collecting baseline data; and finalise an updated log frame and refreshed monitoring strategy by August 2020.
Phase 2 (April 2020 onwards):
- Pivoting a programme for the COVID-19 economic response: The flexible design meant the programme could pivot to support the COVID-19 economic response and deliver rapid technical assistance in a crisis to protect livelihoods and jobs. These interventions will run until January 2021 and will be reflected in the updated log frame.
- Project mobilisation: For Phase 2, demand led project proposals from the HMG Africa network were solicited and allocations made and approved by the Growth Gateway Advisory Group and Board (which includes representatives from DFID, DIT and FCO). While 4 projects have progressed to implementation, others had to be held up to take account of budget adjustments as a result of an overall reduction of UK ODA due to the impact of COVID-19. Recommendation: DFID programme team to finalise the portfolio of activities for Phase 2 by end of August 2020 to allow enough time to complete implementation by the programme end date of January 2021.
- Secondary benefits: Thinking around secondary benefits has progressed during Phase 2, including developing guidance and a secondary benefits plan. This has led to learnings around how ODA and non-ODA funds could work together to bolster both primary and secondary benefits to drive mutual prosperity for both the UK and Africa.
- Cross-government collaboration: The Facility is being delivered as part of the Growth Gateway programme, with DFID/DIT/FCO working closely together to design and deliver interventions. Fusion working has been put into practice throughout the programme. A lesson learning workshop on XHMG collaboration took place in July 2020 between the joint DFID/DIT/FCO team to collect and disseminate learnings and recommendations on how fusion has worked in practice and how it can be applied in other contexts.
- Climate and environment: The Summit aimed to contribute to climate and environment objectives where possible. In Phase 2, the programme has committed to a 10% International Climate Finance (ICF) spend to formalise and strengthen its contribution to a green recovery.
- Value for Money: Value for money was a key consideration throughout Phase 1. Recommendation: DFID and the Facility to design a VFM framework to guide activities during Phase 2 (including whether or not to proceed with them). The framework should include log frame indicators where relevant and can be complemented with any other indicators that may be needed to assess VFM of specific outputs as well as reflecting the Departmental VFM strategy.
Impact: Impact of work on vulnerable groups should continue to feature strongly in the programme approach. Recommendation: The Facility to better reflect impact aspirations in the programme log frame and share lessons with other DFID suppliers working in this space (e.g. on gender and inclusion) by August 2020. DFID and the Facility to consider how to better engage partners such as African diaspora to increase impact by August 2020.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
1. The intended impact of the programme is to catalyse an increase in investment from the UK (and other countries) into Africa to support sustainable economic development. To facilitate this change (outcomes), it was important to ensure that Summit attendees and the wider business community would have a more informed, positive view of each other’s countries; a greater willingness to do business together; and find it easier to do business in Africa.
2. The programme also defined intermediate outcomes to assess progress during phase 1 towards the longer-term objectives outlined above. Feedback collected from participants covered;
- whether the Summit and side event attendees acquired greater interest and knowledge in investment opportunities in Africa (17,039 views of Summit and pre event social media content, 4,000 LinkedIn expressions of interest from firms asking for further information on opportunities following the Summit);
  [note] Technical Assistance Facility Phase 1 report, June 2020
  [note] Growth Gateway Monthly update March 2020
- whether new and stronger partnerships were established (91% of Summit attendees stated that they had made new, useful connections);
  [note] UKAIS Summit feedback response survey, January 2020
- and whether perceptions and willingness around ease of doing business together improved (85% of respondents agreed that the event had improved their view of the UK as a partner to do business with and 86% agreed that the Summit and prevents were effective in showcasing Africa as an attractive destination for investment).
  [note] ibid
1. In light of the COVID-19 crisis, the Theory of Change (ToC) was adjusted to reflect the focus on providing emergency technical assistance to African governments and businesses in key trading sectors as part of the global economic response to COVID-19.
2. Immediate/short-term impacts include: protecting vulnerable and unstable economies from impacts of COVID-19, such as disrupted supply chains, decreased trade and investment flows, increased unemployment rate; and protected livelihoods of vulnerable communities, especially women and girls. Phase 2 will connect businesses, including UK businesses, to developing markets through increased trade and investment.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
1. The review team judges that the programme is on track to contribute to expected outcomes and impact. Assessment is inherently difficult due to: a) data lags in investment; b) attribution of changes in investment to the Summit/side events is not straightforward given the many factors at play in determining investment flows; and c) the long-term nature of economic development. Progress against intermediate outcomes demonstrates strong performance in measurable areas at this stage.
2. For the year ahead, the programme will continue to work with businesses and African governments to increase trade and investment that fosters long-term inclusive growth. The programme will additionally provide COVID-19 related support through seven projects in several countries covering a range of sectors (e.g. agriculture, textiles and digital finance). The Facility will deliver scoping studies, provide detailed sectoral analysis and deliver technical advice around trade and investment into African economies that generate positive benefits for poor women and men; support a green recovery; and reflect wider HMG prosperity objectives. Recommendation: The Log frame should be updated to reflect targets and outputs agreed for each of the Phase 2 projects in line with the revised ToC by August 2020.
Justify whether the Programme should continue, based on its own merits and in the context of the wider portfolio
Phase 2 has been revised to reflect the implications of COVID. The outcomes and impact remain valid: increased investment in African economies that boost growth, create jobs and tackle inequality. This means supporting investment retention; developing economic policies that help manage the worst effects of the pandemic-induced crisis; and supporting firms to pivot to new opportunities. This approach reflects the DFID Economic Development portfolio and crisis response.
## C. DETAILED OUTPUT SCORING

Output Title	Pre-summit events delivered
Output number:		1	Output Score:	A+
Impact weighting (%):		n/a	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
# of pre-summit events delivered	5	6 side events: Gender Investment, Agri-business, Manufacturing, Clean Energy, Sustainable Infrastructure.
% of people attended out of the number of invitees	n/a	62% of those invited attended the side events - 1,100 people attended the programme of events (of which 355 were female).

Briefly describe the output’s activities and provide supporting narrative for the score.
1. The Facility organised a series of side events (both pre and post Summit) which brought together key figures from companies, government, international institutions, academia and civil society on a sectoral basis to discuss specific opportunities and barriers to investment in African economies. The Facility worked alongside HMG policy leads to deliver side events.
2. This output exceeded expectations as the Facility delivered six successful events in collaboration with several stakeholders (including across Whitehall) and to very tight deadlines (2-3-month turnarounds). The events were well attended and received very good feedback from attendees.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
1. This output represented good value for money. On economy, the main cost drivers were fee rates for consultants and the venue hire costs. The programme team used the General Economic Development Framework (i.e. pre-negotiated rates for consultants which do not exceed international average rates) and ensured consultants met appropriate quality standards (by assessing CVs and fee rates for all consultants brought into the Facility). Venues that had no cost were sought where possible (e.g. the gender investment roundtable used the FCO Map Room); and 3 events shared one venue allowing the Facility to secure preferential rates.
2. In terms of efficiency, the Facility reused materials (e.g. invitations, speaker notes, run-sheets and production notes) and refined processes in light of each experience. All side events were successful - they helped build enthusiasm for the Summit; enabled dialogue on the policy and market barriers faced in investment; and created opportunities for new connections and networks (e.g. 88% of attendees across all side events agreed with the statement “I have made new, useful connections as a result of attending the event”). Equity was central to the organisation of the events; two of them focused on gender inclusion and the other events included relevant inclusion-focused content (e.g. how to measure the success of mini-grid projects from a gender perspective; how transport can consider the needs of women). Panels and audiences were diverse (including UK, African and international stakeholders and ensuring female participation).
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Output completed.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
- The volume of work around events planning as well as execution of events in quick succession (5 side-events over a 7-day period in January) was a significant challenge and necessitated specialised event delivery expertise. The scheduling was outside of the programme’s control. Building in flexibility into programme and contractor terms of reference to adapt to short-notice change of plans is essential; allowing the programme to scale up and down as required
- Most side events took place in London. This provided a challenge in ensuring appropriate attendance from African stakeholders. Regional events across Africa would have helped further diversify the attendance and engagement at side events.
- Social media channels performed well with good engagement across all platforms. Ensuring comms plans are central to delivery of side events would allow for the reinforcing of key messages (particularly by using traditional media) beyond Summit and side event attendees.
Output Title	Investment collateral has been developed
Output number:		2	Output Score:	A
Impact weighting (%):		n/a	Weighting revised since last AR?	No

Feedback collection for side events relied on an online survey. The Agri-business event had the highest rate of response at ~20% and was the only event to use physical feedback forms for attendees to share their thoughts. Recommendation: Facility to propose feedback mechanisms that lead to higher response rates by August 2020.
Indicator(s)	Milestone(s) for this review	Progress
# of investment prospectuses	n/a	21 country factsheets developed – including details of current inflation rates, FDI stock and sectors of opportunity.

Briefly describe the output’s activities and provide supporting narrative for the score.
1. The Facility developed factsheets for each of the 21 UKAIS countries. These were distributed in January 2020 at three side events (Clean Energy, Manufacturing, and Infrastructure) and at the Summit (via the app). A limited number were put on the African Investment Promotion Agencies’ (IPAs) stands at the Summit.
2. This output met expectations. The country factsheets have been shared with the HMG Africa network and will be incorporated in future market guides on the great.gov platform.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
This output represented good value for money. The main cost driver was consultant fee rates. Economy was achieved as described in para C.3. The decision to shift to less detailed factsheets enabled the Facility to focus on delivering a quality factsheet in a timely manner (effectiveness). In terms of efficiency, the factsheets were easily accessible to participants (e.g. available on the app) and facilitated participation in the event, given it catered to a mixed audience with differing levels of knowledge, needs and requirements. However, equity considerations could have been better addressed e.g. by adding stats on gender and economic inclusion.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Output completed.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
- Lead times to deliver factsheets and prospectuses were too ambitious. A flexible contract and Facility able to adapt meant that quality outputs could be produced within the limited timeframe.
- Factsheets with macro facts and contact details for IPAs and HMG Posts are useful for an audience with differing levels of knowledge, needs and requirements. Including stats on gender and economic inclusion would enhance the product (e.g. female labour force participation).
Output Title	Monitoring & Evaluation approach can inform future decisions
Output number:		3	Output Score:	B
Impact weighting (%):		n/a	Weighting revised since last AR?	No

Since March 2020 and the global COVID pandemic, much of the data needs to be updated to ensure that the material remains usable. Supply partners should also deliver a methodology guide as part of such outputs to allow for the regular updating of evolving data points.
Indicator(s)	Milestone(s) for this review	Progress
M&E approach is developed and shared with relevant stakeholders	n/a	M&E Approach developed for Phase 1 - co-development of a programme ToC and log frame with HMG UK-AIS team. Facility developed surveys sent to event attendees and a Summit app which included simultaneous feedback options. The Facility reports on each side event covered attendance, feedback, engagement via comms and leads to follow up. / M&E Approach being revised for Phase 2.

Briefly describe the output’s activities and provide supporting narrative for the score.
1. For Phase 1, the Facility developed an appropriate monitoring approach. For Phase 2, the Facility is revising the monitoring approach in light of the COVID-19 crisis. Aligned to the Growth Gateway programme, the team has adapted the ToC and set up an individual results chain per project. This includes a reference to climate impacts given the programme’s new commitment to deliver a 10% International Climate Fund spend. The Facility is developing a Phase 2 survey for internal stakeholders to gather qualitative feedback once projects have been finalised; external stakeholder engagement approach to be determined.
2. This output has moderately not met expectations. The Facility delivered a monitoring approach for Phase 1 and is revising this for Phase 2. Issues around up take of online surveys and data collection meant that sample sizes were relatively small. Due to the rapid mobilisation of the Facility, the programme was unable to collect baseline data against which to assess progress.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
This output represents good value for money. The monitoring process was comprehensive, e.g. including note takers at each event, digital feedback forms which were sent out post-event, and debriefs with the teams after each event to collate insights and lessons learned and disseminate at pace. It could have been more effective by conducting a baseline assessment on delegates’ perceptions and awareness (rather than only post-event feedback) and attracting a higher rate of survey participation among delegates. Equity was well considered - data provided was disaggregated (e.g. by gender). For economy and approach to key cost drivers of consultancy fees refer to para. C3.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Following this review, this output will be updated to reflect monitoring activities for Phase 2.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
- It is difficult to mobilise a monitoring framework whilst implementing a programme. This leads to limitations in baseline data and frameworks. A programme inception period (standard of 3 months before moving to implementation) would have made the process clearer and more streamlined.
- For Phase 1, the programme collected feedback primarily through an on-line survey. This generated some useful data but could have been complemented by qualitative data. Recommendation: For the remainder of Phase 2, DFID/ the Facility should carefully consider the best tools for obtaining qualitative and quantitative feedback as well as pragmatic solutions to collecting baseline data. An updated log frame and refreshed strategy to monitoring, review and learning should be finalised by the Facility by August 2020.
Output Title	Technical assistance outputs are delivered
Output number:		4	Output Score:	A
Impact weighting (%):		n/a	Weighting revised since last AR?	No

Value for money was a key consideration throughout Phase 1. Recommendation: DFID and the Facility to design a VFM framework to guide activities during Phase 2 (including whether or not to proceed with them). This should include log frame indicators where relevant and can be complemented with any other indicators needed to assess VFM of specific outputs.

Indicator(s)	Milestone(s) for this review	Progress
# of TA outputs delivered	n/a	Three TA outputs delivered in Phase 1 (Senegal study on Special Economic Zones, Mauritania future impact sectors report, FCO UK-Africa Insights paper); 1 project being delivered following the Summit (Uganda Agri-tech. / Seven COVID-19 economic response projects approved and 4 have started implementation during Phase 2 (Morocco textiles, Tunisia textiles and Senegal/Cote d’Ivoire digital finance, Investor retention)

Briefly describe the output’s activities and provide supporting narrative for the score.
1. This output has met expectations: technical assistance was delivered in a timely manner and to a high quality. It ensured that where supplementary support was needed to maximise a country’s participation at the Summit, a mechanism was available. Additionally, a follow-on project Uganda Agri-tech was commissioned to take forward the Summit agriculture theme and linking into COP26.
  [note] Feedback from HMG Post and key stakeholders
2. In March 2020, the Facility pivoted to provide critical support to African governments and businesses to tackle the economic consequences of COVID-19. There was high demand from across the HMG Africa network. In assessing bids, the Gateway team prioritised interventions that focused on the immediate COVID-19 economic response, demonstrated a strong development impact, highlighted the potential for secondary benefits to the UK and did not duplicate existing HMG offers/activities. Since July 2020, four projects have started (see Box 1). The Gateway Board (has approved a further 3 projects due to start in August 2020.
Box 1. Demand-led Technical Assistance projects for Phase 2
Morocco textiles: Supporting Morocco’s Economic Monitoring Committee (Gov of Morocco) and Textile and Clothing Sector Association (AMITH – relevant Moroccan Industry body) with analysis and advice to support the development of a textiles sector recovery plan, including identifying opportunities for manufacturers to pivot to PPE production; / Tunisia textiles: Supporting local Government and Kasserine cluster industry association with analysis and advice on emergency measures and developing an industrial plan for the Kasserine textile cluster in Tunisia; / Senegal and Cote d’Ivoire digital finance: Supporting the Ministry of Finance in Senegal and Cote d’Ivoire by identifying constraints and bottlenecks in accelerating the use of mobile payments and digital finance. Proposing recommendations for regulatory reform. / Investor retention: Support to Investment Promotion Agencies to retain investment following COVID-19 crisis (Ghana, Kenya, Nigeria and Senegal).

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
1. The TA projects were carried out effectively, delivered in a timely manner and to a high quality. Feedback from Posts and stakeholders for Phase 1 was very positive: the TA enabled them to maximise their country’s engagement and participation in the Summit and related opportunities. The main cost driver was the fee rates for consultants delivering the TA outputs (see para C.3).
2. In Phase 2, the Facility has so far ensured VFM through a rigorous project selection process, e.g. considering whether analysis is relevant and can be used to inform C-19 response; whether project builds on Summit objectives to ensure trade and investment gains are not lost. For the remainder of Phase 2, the Facility will need to continue assessing where support is most needed (equity); make sure that analysis remains relevant and fit for purpose (effectiveness); and maintain flexibility in its response (efficiency) in order to maximise VFM. The VFM framework to be developed for Phase 2 (see Output 3 recommendation under para C.13 above) should include relevant indicators, such as a quantitative assessment of project selection criteria and whether the TA is easily accessible (e.g. Is support going where most needed and is there sufficient awareness of the platform?); the quality and timeliness of analysis produced (e.g. How is it being used? Is it being adequately disseminated to intended recipients? Does it meet demand requirements?); and the flexibility of the draw-down mechanism (e.g. Speed of project allocation and implementation).
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Phase 2 project deliverables have been added to this output as part of the Facility’s response to COVID-19 as part of the Growth Gateway programme. The log frame will be updated to reflect this.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Small, flexible, time bound interventions can be useful in certain settings (e.g. low UK ODA footprint, small UK Post) – augmenting in house policy and advisory expertise to deliver an attractive package of support to partners.
For Phase 2, 7 project bids have been approved by the Growth Gateway Board and 4 have begun implementation. Recommendation: DFID programme team to finalise the portfolio for Phase 2 by end August 2020 to allow completion nby January 2021.
Output Title	Appropriate delegates are invited & prepared for attending the summit
Output number:		5	Output Score:	A
Impact weighting (%):		n/a	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
# of delegates invited for attending the summit	n/a	1,700 the UKAIS – the Facility supported attendee engagement ahead of the Summit by delivering an event app and supporting HMG on due diligence

Briefly describe the output’s activities and provide supporting narrative for the score.
1. This output has met expectations The Facility supported delegate engagement by developing a tailored event app. Seventy-eight percent of Summit attendees logged into the app with a similar number recording contact details of a new connection. The app had the agenda, a messaging function to support networking; and information on companies and IPAs in the innovation zone (e.g. links to reports and the UKAIS factsheets). The Facility supported the invitee due diligence process.
  [note] UKAIS app data, January 2020
2. The Facility also ensured that African Investment Promotion Agencies (IPAs) were well prepared to maximise their time at and around the Summit. The Facility led a training programme for IPAs on 15 January 2020. Many IPAs fed back that the training helped them to set up productive meetings at the Summit.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The app played an important role in facilitating engagement and networking, and contributed to the smooth running of the Summit by providing information on the agenda, companies, etc. In addition to designing the app to ensure if was fit for purpose, the Facility also drove VFM by finding a quality but cost-effective app development company (chosen through a tender process), with demonstrable experience in delivering quality multimedia content and digital products. Support to IPAs was delivered by a series of webinars, thereby cutting face to face training costs. Ensuring that these delegates were appropriately prepared to maximise their time at the Summit was effective way of contributing to summit objectives.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Output completed.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
This output demonstrated the value of creating a flexible arrangement: the Facility was able to bring in the right expertise quickly, e.g. for app build and design and for the due diligence checks.
Output Title	Summit is of high quality and well attended by businesses, countries, sectors, and partners of focus
Output number:		6	Output Score:	A
Impact weighting (%):		n/a	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
% of individuals who attend the summit out of those invited	N/A	1,700 attendees
Percentage of respondents that rate the organisation, structure and flow of the day, relevance of themes and content discussed, quality of speakers and panel discussions, venue and amenities good, very good, and excellent	N/A	Organisation: 83% positive / Relevance of themes: 87% positive / Quality of speakers: 86% positive / Venue: 77% positive

Briefly describe the output’s activities and provide supporting narrative for the score.
The Facility provided policy reports from the side events and produced four films and five infographic videos for the Summit. These contributed to the quality of the Summit set-piece segments. Attendees rated the organisation, relevance of themes and quality of speakers highly, this output has therefore met expectations.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The Facility helped achieve a high level of engagement at the Summit. Value for money was achieved by the flexible design of the Facility, enabling it to call up resources at an appropriate level when required - for example on the films and infographics.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Output complete.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The Facility was designed to be flexible to respond to changing demands. This proved essential in Phase 1 and worked well. It would have helped to have had a longer inception period to set up clear and efficient policies, processes and establish solid working relationships.
D: RISK
Overview of risk management
1. The overall programme risk has remained moderate for the review period. This is within DFID’s risk appetite. Key risks included delivery of time-sensitive work and completion of commercial processes to set timelines for both phases. The uncertain and rapidly evolving context in which the work was delivered caused ancillary impacts on stakeholder engagement and HMG staff resource levels.
2. Key risks for the year ahead include;
- Intended outcomes will be affected by COVID-19 (loss of jobs, capital flight, investment decisions put off). Mitigation: Pivot activities to respond to economic effects of COVID-19. Flexible delivery model which remains responsive to changing circumstances, including through regular review meetings, political economy analysis etc. Update results framework to reflect impact on results indicators following AR. Residual risk: major
- Delivering time-sensitive economic response projects. Mitigation: Facility to turn around ToR drafts in 48 hours; ensure close communication with SRO and HMG clients on timelines; HMG staff to provide comments swiftly; DFID to secure approval of concepts through the HMG Advisory Group and Board in advance and keep ToR approvals at programme level. Facility to implement business continuity processes when needed. Strong comms with Posts to ensure projects are relevant/feasible. Residual risk: moderate
1. During Phase 1, delivery risks were managed through a risk register and management plan overseen at programme level. This fed into the Summit risk register which was closely monitored by Ministers for the UKAIS. The Facility managed a risk register at project level, discussed in weekly Programme Management meetings with DFID. For Phase 2, DFID holds a risk register at programme level and reports to the DFID/DIT/FCO Growth Gateway Board and Advisory Group. A project level risk register is managed by the Facility and is reviewed in fortnightly meetings with the Gateway team.
2. For both phases, the programme team monitored the evolving political, economic and security context in consultation with Posts. Both HMG and the Facility’s networks were drawn on to broaden outreach for recruiting high-quality consultants and for stakeholder engagement. Recruitment process was closely scrutinised for VFM by the programme team. DFID processes were utilised throughout the programme lifecycle to ensure compliance with the International Development Act.
3. For phase 2, activities have been chosen based on pro-poor benefits underpinned by political and economic analysis. The programme team has drawn on experience from management of other cross-HMG programmes such as the Prosperity Fund.
4. For the remainder of Phase 2 careful monitoring of the external context and close communication with key stakeholders will need to continue to ensure activities adapt and reflect evolving priorities and expectations.
E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Performance of partners and DFID on commercial, and financial issues, and including consideration of VfM measures of economy and efficiency.
Commercial & financial performance
1. Total costs for Phase 1 were £2 million. DFID has approved a budget of £1.5 million for Phase 2. For Phase 1, forecasts were submitted by the contractor at the end of each month. The key performance indicators for the contract were assessed by DFID at the end of Phase 1 and upon delivery of outputs. Ten percent fees were paid based on satisfactory achievement of these indicators. For Phase 2, the contractor submits monthly forecasts of spend and DFID manages the contract on the basis of output delivery.
2. The Facility sought to maximise efficiency and economy through the choice of side event venues; managing costs through smart planning; and ensuring quality was delivered for a reasonable price. DFID scrutinised all consultancy proposals to ensure they were appropriate within the caps set by DFID’s General Economic Development Framework (GEDF).
3. The Facility adapted quickly and flexibly to changing requirements, as envisaged in the contract. Specifically, the increase in scope of work during Phase 1 was met by changing the delivery structure and a temporary increase in resources which was scaled back when no longer needed. The Facility maximised the outputs for given costs, reusing materials where possible and seeking economies of scale (e.g. materials for side events, venue hire).
4. The Facility has been effective at designing activities that take due account of the needs of the poorest and most marginalised. Cross-cutting themes of gender, disability and inclusion and climate and environment continue to be a priority for Phase 2 projects. Other critical themes such as diaspora, digital inclusion and governance have been added for Phase 2.
Delivery & programme oversight
1. The programme team held progress meetings with the Facility weekly during Phase 1 and fortnightly for Phase 2. The Facility provides a financial report and TA performance overview (including output progress, risks and priorities) ahead of each meeting. The CORA digital platform provides live reporting of risks and performance at project level which DFID can access at any time. Additionally, the programme SRO has kept in daily contact with the Facility team leader to ensure clear and frequent communication for both phases.
2. The programme team will consider country monitoring visits once travel restrictions have eased to meet key Phase 2 partners. This was not needed for Phase 1 as most activities took place in the UK or were delivered virtually.
3. The Facility sought feedback on all activities during Phase 1. Most of the comments were specific to each side event, some broader findings emerged relating to: timeframe and preparation; scope management; partnership working; invitations and registration; the delegate travel and hotel bookings process; digital engagement and information sharing; communications; and the feedback gathering process itself. These findings have been distilled into recommendations and next steps for HMG and the Facility to take forward in Phase 2.
Date of last narrative financial report	10/07/2020	Date of last audited annual statement	N/A