Annual Review - Summary Sheet

Title: Somaliland Development Fund (SDF)
Programme Value: DFID contribution £25.3m. Overall value of the Fund £ 52.3m includes contributions from Denmark, Netherlands and Norway		Review Date: January 2017
Programme Code: / 202946	Start Date: December 2012	End Date: March 2018

Summary of Programme Performance

Year	2013	2014	2015	2016
Programme Score	A	A	A+	A+
Risk Rating	Medium	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review
The Somaliland Development Fund (SDF) is acknowledged by the Government of Somaliland as one of the best performing muilti-donor pooled funds contributing to the Somali New Deal architecture. It benefits from being a bilaterally-managed Multi Donor Fund and one focused solely on Somaliland. It is consistently praised by the Government of Somaliland as its “preferred aid instrument”, manifested by the President inaugurating numerous SDF projects throughout 2016. The SDF is now entering its final year of implementation with projects expected to draw to a close towards the end of 2017. During 2016 the recommendations from the Joint Steering Committee have consistently focused on rigorous efforts to speed up implementation whilst, at the same time, strictly adhering to the standard operating procedures and building the capacity of partner Ministries and parastatals.

Achievement of results accelerated in 2016. Out of 119 broad activities planned in 12 projects under the SDF, 116 are on track to be completed on time representing a 95.8% completion rate. The major infrastructure initiatives under SDF are at an advanced stage of completion and citizens and business are already taking advantage of reduced travel time from over 129 km of rehabilitated road between Hargeisa – Berbera – Sheikh and between Kalabaydh – Dila. Over 4,857 hectares of land in Upper Maroodijeh are more productive as a result of soil and water conservation structures, potentially securing the livelihoods and food security of over 30,000 people. The rehabilitation of 7 springs in Berbera is providing an additional 60 m3 / day into the Berbera water supply system, and the new 23 km water pipeline in Hargeisa is nearing completion and will provide access to clean water for a large part of Hargeisa still reliant on expensive private water providers. The livestock holding ground in Aroori has been fully rehabilitated with new fencing and a strategy to retain pasture for livestock during lean years. Up to 90,000 heads of livestock are expected to use the facility in 2017. A Land Policy scoping review was completed and provides the Government with up to date information on all aspects of land governance to inform the development of a national Land Policy. The investment in skills across each of our partner Ministries drew to a close in late 2016. The results of this will be validated by a capability assessment in 2017.

In late 2015 a major government re-shuffle shifted the Ministers of Planning and Finance to new positions. Both Ministers had co-chaired the SDF joint steering committee since its inception. This change came at a time when the weaker elements of the SDF portfolio – Qool Qaday livestock holding ground, two rural water projects under the Ministry of Water, and the social services project in Sool and Sanaag – required dedicated Ministerial engagement. The livestock holding ground project was overhauled in 2016 and is now on track. The rural water and social services projects remain challenges for 2017 and a new set of Ministers have just been appointed in Planning and Finance as part of another re-shuffle in late 2016. The key lesson is that the SDF governance structure is robust and resilient to political change but concerted efforts will still be required to implement the more challenging projects satisfactorily by the end of 2017.

As the SDF draws to a close there are major lessons emerging including:
- There is better quality of delivery by parastatals such as the Roads Development Authority and the Hargeisa Water Authority, as opposed to the majority of Ministries where political infighting and weak management systems have often slowed progress.
- The SDF structures are more suited to hard infrastructure and struggle to coordinate with complementary investments on-going in health and education.
- SDF has delivered against an equitable agenda in locating its projects for sound political and peace-building reasons across Somaliland, but further cost benefit analysis would improve the evidence base as to what should be funded and where.
- Many of the interventions have focused on upgrading existing infrastructure which remains a government priority. In developing a successor to the SDF programme, DFID shall limit its interventions to fewer sectors though widen the scope to include more capacity building work and policy engagement.
- Participating donors will work closely with the Government of Somaliland in deciding and prioritising the development initiatives supported in the next phase of the Fund. However, DFID and its development partners shall reserve the right to veto decisions in the Joint Steering Committee.
- More training and capacity building on international procurement standards is required to mitigate against attempted interference and to protect the Fund from reputational and fiduciary risk.

Progress against previous annual review recommendations (where relevant):
1. More in depth community engagement: The secretariat has increased its engagement with local communities to mitigate potential conflict while ensuring they have a clear understanding of project activities, the overhaul of the Qool Qaday livestock holding ground being a case in point. In Aroori, the local community participated in the recruitment of range workers. Local community management committees have been established in Sool and Sanaag to manage schools and hospitals.
2. Engagement with line ministries: The SDF secretariat ensures continuous induction and on-the-job training of programme management teams on the SDF procedures e.g. financial management and procurement procedures. Capacity development was devolved to the regional offices in Sool and Sanaag who received programme management training.
3. Results verification: The secretariat continues to carry out spot checks of projects to verify reported progress and identify issues affecting implementation. Perception surveys have been undertaken in September and November 2016 on roads, water and agricultural initiatives with findings being used to establish baselines where appropriate. Information from these surveys has been used to revise the SDF logframe.
4. Government pre-financing of SDF: The original SDF design included an incentive fund. A proposal by the secretariat in December 2015 to the Joint Steering Committeee seeking government commitment to pre-finance the local SDF account used for making local payments – mainly for staff salaries, and local operating expenses – has not been taken forward given weak government commitment to reform and high levels of fiduciary risk.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202946/documents/
DevTracker Link to Logframe:	http://devtracker.dfid.gov.uk/projects/GB-1-202946/documents/

Summary of Programme
DFID and DANIDA established the Somaliland Development Fund in 2012 to provide a reliable vehicle through which public services are provided to the citizens of Somaliland. The SDF supports implementation of service delivery projects from health to education to infrastructure as well as offering technical and management expertise in building core government capacity and functions.

The SDF supports mainly technical expertise and capital costs for 12 projects and helps Government communicate the results to build accountability with its citizens. The SDF draws on international best practice to work in parallel with the civil service and public finance systems in the absence of robust Somaliland government systems. This way of operating supports the public service employees working on the SDF by providing the skills to better run and manage their own systems complementing the nascent World Bank programmes.

A key aspiration of the original SDF concept was to gradually transfer the management of the SDF secretariat processes – mainly planning, project management, and budgeting – to the Government. This was to be implemented in phases based upon monitored progress against successful implementation of public financial management reform (PFM) benchmarks. This aspiration has been delayed partly because of the extremely slow pace at which the PFM Bills were submitted to Parliament (they took 4 years) but also because of high levels of fiduciary risk. As we enter the final year of the SDF it is clear that both the political will behind PFM reforms and the appetite to shift responsibilities of the SDF to government are weak. Full management responsibilities by the SDF secretariat are now expected to remain in place for the next phase of the SDF.

Despite the slow pace of reform, the SDF has complemented the World Bank civil service programme with an innovative skills training initiative which trained civil servants in project cycle management over an intensive 9 month training period. Whilst the first phase implemented in 2015 focused on staff based in Government Ministries and Agencies based in Hargeisa, the second phase targeted staff at regional offices especially in the eastern regions of Sool and Sanaag. The UK’s National School of Government will validate this work by undertaking a full capability assessment in 2017.

B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The results delivered at output level clearly demonstrate the SDF will achieve most of its expected programme results against the planned milestones.

Outcome: Improved and better resourced core state functions for the people of Somaliland
Outcome / Indicator 1	Baseline / (2013)	Milestone / 2016	Achieved 2016	Target / 2017	Progress
Number of beneficiaries of services attributable to SDF supported projects	0	267,884	463,007	1,458,807	The programme far exceeded the milestone. The cumulative figure is now 1,325,174 beneficiaries by the end of 2016.
Outcome Indicator 2	Baseline / (2015)	Milestone / 2016	Achieved 2016	Target / 2017	Progress
% of citizens reporting improved service delivery in government sectors supported by SDF.	33%	48%	47%	63%	Improved delivery, just short of the 2016 milestone.
Outcome Indicator 3	Baseline / (2014)	Milestone / 2016	Achieved 2016	Target / 2017	Progress
Average effectiveness and efficiency of SDF-supported GoSL Ministries and Agencies (Score 1-6)	4/6	4.8/6	5/6	4.7/6	Target exceeded.

Aggregate Output Score and Description
Output	Score
Improved water and road infrastructure to promote economic and socially equitable development (Impact Weighting: 35%)	A++
Improved productive sectors enhancing incomes, food security and livelihoods (Impact Weighting: 25%)	A+
Improved capacity of GoSL institutions to manage development projects (Impact Weighting: 15%)	A+
Enhanced citizen perception of Government priorities, activities and expenditure (Impact Weighting: 10%)	A+
Improved capacity to prioritise development objectives and to plan and budget development activities (Impact Weighting: 15%)	A+

There has been very strong progress against all outputs and accordingly the programme has been rated A+. There have also been significant challenges experienced by the Fund in 2016 in implementing the projects in Sool and Sanaag, local conflict and procurement. New indicators will be added to the logframe in 2017 to properly track and manage these challenges in the final year of the Fund.

Has the logframe been updated since the last review?
The logframe was reviewed in August/September 2016. The revision of the logframe took into consideration changes in the project outputs as well as establishing realistic estimates for programme beneficiaries. The logframe review redefined some of the indicators. This logframe is at Annex 2. There any plans to revise the logframe in early 2017 given that many of the outputs for 2017 have already been exceeded.

C: DETAILED OUTPUT SCORING

Output Title	Improved water and road infrastructure to promote economic and socially equitable development.
Output number per LF		1	Output Score	A++
Risk:		Moderate	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Milestone 2016	Achieved 2016	Overall Target	Progress
Output Indicator 1.1: Quantity of water per day available for distribution in urban water systems with SDF support.	N/A	400 m3/day	1,593 m3/day	7,053 m3/day	Rated A++: An additional 1,593 m3/day was added in 2016 against the planned 400 m3/day in Hora Hadley. The target was exceeded due to optimization of the pumps in existing boreholes in Hora Hadley.
Output Indicator 1.2: Number of rural water points constructed or rehabilitated with SDF support.	N/A	14 points	41 points	218 points	Rated A++: A total of 41 water points were constructed /rehabilitated in 2016, against the target of 14. The breakdown of the total is as follows: 3 in Darasalaam, 28 water points in Gargooray, 5 berkads and 5 school rain water harvesting systems in Maroodijeeh Upper Catchment.
Output Indicator 1.3: Reduction in travel time reported on roads rehabilitated with SDF support.	N/A	60 min (baseline)	22 min	Tbc	Rated A+: In 2016, the travel time reduced from an average of 60 minutes to 22 minutes, calculated using only the Dilla-Kalabaydh road. This represents a 63% reduction in travel time. This indicator needs to include the wider SDF road portfolio in its next rating.
Output Indicator 1.4: Length of roads rehabilitated to all weather condition with SDF support.	N/A	19.2 km	25.4 km	119.2 km	Rated A++: A total of 25.4 km of road sections were rehabilitated (16.4 km for Dilla-Kalabaydh and 9.0 km for Hamas to Hargeisa) against a target of 19.2 km. The cumulative length of roads rehabilitated to date is 129.4 km against the target of 119 km (109% against the target).

Key Points
The overall rating of this output is A++. The output targets were substantially exceeded. The Hargeisa Water Authority (HWA) has contributed the bulk of the results with 5,651 m3/day, equivalent to 80%, of indicator 1.1. The Ministry of Water and Natural Resources (MoWR) was expected to contribute to the achievement of the target through completion of the Burao water system but this was delayed because of the late delivery of construction materials, mainly pipes which had to be imported. Most of the MoWR activities are expected to be completed in 2017. The milestone for Indicator 1.2 has been substantially exceeded and rated at A++ through the construction of 41 water points against a target of 14 mainly contributed by HWA - 13, MoA – 10 and MoWR – 28. Both indicators 1.3 and 1.4 have been substantially exceeded. The 63% reduction in travel time was achieved as a result of the Dilla-Kalabaydh road rehabilitation and the cumulative road rehabilitation result of 129.4 km against a target of 119 km (109% against the target). The completion of Dilla-Kalabaydh road section has benefited 195,123 people. The initial target set for 2016 did not include the Hargeisa water agency project. This was included in early 2016 which contributed to the surge in the distribution of water measured by this indicator. All results are attributable to SDF spend.

Summary of responses to issues raised in previous annual reviews (where relevant)
1. Reliable baseline data: The secretariat undertook a Somaliland perception survey between March and May 2015 which was complemented by a sub-survey carried out during August – September 2015. Citizen opinions in districts, where SDF projects in water, roads and agriculture are being implemented, were collected along with matching data from comparison districts where no SDF projects (nor interventions by other agencies) were undertaken. The analysis provided evidence-informed data values for a number of output and outcome indicators. Subsequent logframe revisions have incorporated the relevant baseline data and milestones.
2. Strengthening third party monitoring to include outcome assessments: DFID Somalia has contracted a consortium of implementing partners (Integrity, Altai and ITAD) to implement its Learning and Monitoring Programme – Somalia (LAMPS). LAMPS will provide third party monitoring/verifications and M&E technical assistance support. DFID anticipates using the LAMPS programme to support elements of the project completion report as the SDF programme finishes in March 2018.

Summary of recommendations for the next year:
1. A well field collector needs to be installed on the outskirts of Hargeisa. This will enable approximately 5,000m3/day to be introduced into the system, serving an additional 250,000 people in Hargeisa. The SDF and the EU are planning to release additional finance from their contingencies to meet this need in early 2017.
2. In order to safeguard the asset value of the rehabilitated roads, the RDA should operationalise the road maintenance policy as well as rolling out of the road maintenance guidelines detailed in the Roads Act still pending with the Parliament.
3. Water sector interventions draw on the evidence – see latest ICAI review “Assessing DFID’s Results in Water, Sanitation and Hygiene”[1] – that holistic WASH interventions secure better health outcomes. In the final year of the SDF it is important to map the partners (mainly UNICEF) who are working in the same urban water locations as the SDF to ensure that hygiene interventions are complementing our mainly infrastructure outputs.
  [1] http://icai.independent.gov.uk/report/wash/

Output Title	Improved productive sectors enhancing incomes, food security and livelihoods.
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Milestone / 2016	Achieved 2016	Overall Target	Progress
Output Indicator 2.1: Productivity of staple food (Sorghum) in Maroodijeeh Upper Catchment.	1.0 t/ha	0.9 t/ha	2.5 t/ha	0.9 t/ha	Rated A+: In the absence of the formal Food Security and Nutrition Analysis Unit data for 2016, the AR relied on yield estimates data collected by the research unit at the Aburin Dryland Agriculture Research Centre. Until validating data is received the rating for this indicator will be A +.
Output Indicator 2.2: Cumulative number of Hectares of land conserved or rehabilitated (for both agricultural and livestock use) with SDF support.	0	13,688 ha	16,288 ha	31,688 ha	Rated as A+: In 2016, the area of land conserved for agricultural and livestock use through watershed / catchment management was 16,288 ha, exceeding the target of 13,688 ha. Cumulatively, 21,783 ha of land have been conserved; representing 69% of the overall target.
Output Indicator 2.3: Number of export livestock screened through the rehabilitated livestock holding grounds	0	100% completion of Aroori LHG infrastructure	95% completion of Aroori LHG infrastructure	90,000	Rated A: The LHG activities are 95% complete. These include 89 km of fence as well as critical infrastructure: ramps, troughs, animal sheds, earth dams (balleys), animal health posts, crushes and provision of reliable water supply.
Output Indicator 2.4: Cumulative quantity of cubic meters of water per annum available in rural areas for livestock with SDF support.	0	60,524 m3 per annum	80,950 m3 per annum	158,399 m3 per annum	Rated A+: This is a new indicator introduced in the 2016 logframe review. A total of 80,950 m3 of water per annum was made available through rehabilitation of 10 small earth dams (balleys) in Maroodijeeh Upper Catchment, exceeding the target of 60,524 m³.

Key Points
The overall rating for this output is A+. The soil and water conservation structures and water catchment conservation activities in Maroodijeeh Upper Catchment area continue to deliver higher agricultural productivity measured by higher sorghum yields.

Re-forestation and seeding of rangeland as well of provision of water for livestock and domestic use were all completed and have resulted in the reduction of rain water runoff, grass rejuvenation and increased soil moisture. The increases in the land conserved, under these different projects, support livestock and increase food security and household incomes which has been vital in supporting livelihoods during 2016 given the ongoing drought.

The indicator 2.1 on sorghum was substantially exceeded with the yield averaging 2.5t/ha. The FSNAU report from which data is drawn has not yet been issued, so this AR relied on data collected by Aburin Dryland Agriculture Research Centre in Maroodijeeh. Once the FSNAU report is issued we will cross check these results. Despite the shortage of rainfall in 2016 the construction of large soil bunds and other watershed management practices are having a positive impact on agricultural activities in the area.

For indicator 2.3 the entire Aroori Livestock Holding Ground infrastructure was completed except for the water supply system, which will be completed in early 2017. The construction of the second LHG in Qool Caday was halted because of community resistance to the enclosure – in essence a major land dispute based on historical ownership and public access. A reduced programme was designed drawing on experts form the Rift Valley Institute and the positive engagement by the Minister of Planning. The new project focuses on water supply, land access, and veterinary posts and shows the ability of the SDF to adapt to the local context and its adherence to the principle of “Do No Harm”.

Summary of responses to issues raised in previous annual reviews (where relevant)
1. Conflict Sensitive Programming: In adherence with the do no harm principle, the SDF secretariat ensured continuous engagement with the local community to resolve resistance towards the Qool Qaday livestock holding ground project. The secretariat contracted the Rift Valley Institute to facilitate a series of consultative meetings with the Qool Qaday community aimed at understanding the reasons behind the resistance to the enclosure and fencing, and to identify other priorities for consideration. This helped reduce tensions and and re-design of the project. The SDF secretariat also stopped all work on the Eliefwein rural water project because of a localised conflict and excessive risk for SDF contractors to visit the site. Periodic assessments are reviewing this conflict and a decision on halting this project may emerge in early 2017.
2. Results reporting: The logframe for the SDF programme was initially revised between August and September 2016. The logframe captures the revision of Output Indicators 2.2 and 2.3 milestones taking into consideration the change in approach following community mobilisation activities in Qool Qaday in relation to the livestock holding ground. A qualitative milestone around the construction of necessary infrastructure was adopted as a milestone for 2016.
Output Indicator 2.2: Number of Hectares conserved has been revised. The target has not changed significantly despite taking out the Qool Qaday contribution. There is a slight increase from the target of 29,054 Ha to 31,688 Ha.
Output Indicator 2.3: Number of Livestock screened has been revised downwards from 138,000 shoats to 90,000. This is because the LHG is new, alongside a new management team. A qualitative milestone was adopted for 2016 because no animals were expected to pass through the holding ground until 2017.
Output Indicator 2.4: Water made available for livestock in rural areas is a newly incorporated output indicator. It reflects the project activities being carried out cumulatively by the Ministries of Livestock, Agriculture and Water Resources to provide water for livestock.

Summary of recommendations for the next year:
1. The Aburin research centre crop yield production data that was used for Indicator 2.1 needs to be cross checked with FSNAU data for validation once the FSNAU report is published.
2. The conservation and environment restoration projects are quite thinly spread. This makes monitoring and quality assurance a challenge. Future support should consider clusters and more concentrated project locations to validate impact.
3. Retain both a qualitative and quantitative milestone for the Aroori LHG for 2017.

Output Title	Improved capacity of GoSL institutions to manage development projects.
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Milestone 2016	Achieved 2016	Overall Target	Progress
Output Indicator 3.1: Size of the Development Budget (inclusive of national + external resources)	0	USD 40,000,000		USD 38,794,864	Not rated. The expenditure outturn figures for FY 2016 are not yet available so this indicator cannot be rated.
Output Indicator 3.2: Number of projects executed on time and within budget by project management teams.	0	2	4	11	Rated A+: Four projects; namely RDA- 01A (Hamas-Berbera-Sheikh Road) and RDA-02 (Dilla-Kalabaydh road) HWA, pipeline and Ayaha works, and the Land scoping study were completed.

Key Points
This output is rated A+. Indicator 3.1 will be updated when the budget estimates are available. Output indicator 3.2 on the time taken and budget precision is rated as A+. This is based on tracking of four projects in 2016 that were all completed on time and within the approved budget. The projects tracked were two roads projects implemented by the roads development authority: the Hamas-Berbera-Sheikh road upgrading and the Dilla-Kalabaydh road upgrading, the Hargeisa water authority 23 km pipeline and Ayaha works, and the Land scoping study undertaken by the Rift Valley Institute. .

Summary of responses to issues raised in previous annual reviews (where relevant)
1. Incorporating SDF into national budgetary discussion: The SDF remains the only aid instrument that is incorporated into the budget, but it remains a parallel instrument that is not explicitly incorporated into budget discussions or budgetary allocation processes. The Somaliland budget process remains opaque and untransparent. There is little interrogation of budget allocations by Somaliland civil society or the media, Parliamentary scrutiny is lacking, and the last World Bank public expenditure review was in 2014.
2. Government pre-financing of SDF: The original SDF design included an incentive fund. GoSL through its Ministry of Finance, has yet to commit to the pre-financing arrangement. This shows a flaw in government coordination and the lack of political will to deliver reform.

Summary of recommendations for the next year:
1. In July 2016 it was recommended that SDF allocations for 2017 projects be disaggregated and provided directly to the planning and statistics department in the Ministry of Finance. Engagement with the State Minister of Finance (a JSC member) should ensure that the SDF allocations are clear to both the Council of Ministers, and the budget committee, so that these SDF allocations are integrated into budgetary debates in both the Executive and Parliament.
2. Engage with the MoF budget department to ensure that the running costs for all four health and education facilities in Sool and Sanaag are included in the 2018 budget on the agreed sliding scale formula detailed in an exchange of letter in both project documents.
3. Continue to track output indicator 3.2: “number of projects executed on time and within budget by PMTs” but draw on four Ministry projects in 2017 to compare them with the mainly parastatal delivered projects under indicator 3.2 in 2016.
4. Discuss a way forward with RVI to present the Land scoping analysis to a Ministerial panel and ensure political parties and civil society are aware and inspired to use this analysis to draw up a Land Policy in the future. The request for this analysis came from the National Planning Commission and the results should be acted upon.

Output Title	Enhanced citizen perception of Government priorities, activities and / Expenditure
Output number per LF		4	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline / 2015	Milestone / 2016	Achieved 2016	Overall Target	Progress
Output Indicator 4.1: / % of people who report improved access to potable water in Hargeisa.	2%	4%	20%	7%	Rated A++: The percentage of residents that reported improvement in access to water increased to 20% (against a milestone of 4%) during the indicator survey carried out in November 2016.
Output Indicator 4.2: / % of people who report improved journey time on SDF rehabilitated roads.	5%	45%	92%	60%	Rated A++: 92% of the respondents in the SDF supported project areas of Dilla and Berbera reported reduced travel time during the indicator survey carried out in November 2016. This exceeded the planned 2016 milestone of 45%.

Key points
The overall rating for this output is A+. The indicators under this output are contributed to by HWA and RDA. The first perception survey was completed in September 2015 and a follow on indicator survey was carried out in November 2016. For indicator 4.1, the survey results show a significant increase in access to water due to interventions in Ayaha 1&2 Water Supply Project and expansion of the transmission line from Hora Hadley. Results for indicator 4.2 show a significant increase of respondents reporting improved journey time as a result of the Dilla-Kalabaydh road as well as the Hamas-Berbera-Sheikh road. It is again worth highlighting that the most predictable partners – from a results based and financial perspective – are both parastatals. The increased public perception reporting can partly be attributed to better communication on SDF in 2016. Despite A++ rating for both indicators this output should be rated at A+ because the targets were probably set at too low a level. Now that the SDF has experience with perception surveys more ambitous milestones will be set in the next logframe revision in early 2017

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2015 AR recommended an update of the logframe with a baseline from the perception survey. The logframe was revised and a mid-term citizen perception survey undertaken to establish baselines for both indicators. A second perception survey was carried out in November 2016 to assess progress against the indicators 4.1 and 4.2. The quantitative indicator survey was complimented with a qualitative survey.

Recommendations
1. The perception surveys for the water and agriculture projects should be maintained, and include additional questions relating to the impact of drought on the SDF’s investments and the influx (or not) of more people and their livestock from the eastern regions. This should be fully documented.
2. Increase awareness campaigns on the safe use of the new road infrastructure to mitigate unintended outcomes such as loss of life and livestock because of excessive driving speeds.
3. Roads signs which have been removed/destroyed should be replaced.
4. The 2017 target for indicator 4.1 on “% of people who report improved access to potable water in Hargeisa” should be increased in the next logframe revision.
5. The 2017 target for indicator 4.2 on “% of people who report improved journey time on SDF rehabilitated roads” should be increased in the next logframe revision.

Output Title	Improved capacity to prioritise development objectives and to plan and budget development activities.
Output number per LF		5	Output Score	A+
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline / 2013	Milestone / 2016	Achieved 2016	Target / 2017	Progress
Output Indicator 5.1: Average aggregate disbursement deviation from forecasts.	0	10%	5%	5%	Rated A++: For 2016, the programme disbursement deviation target of maximum 10% was exceeded with an average disbursement deviation of 5%
Output indicator 5.2: Average time from approved concept note to approved project proposal.	0	No further concept notes and project proposals expected	Not Applicable	180 days	Not Rated: No new concept notes or project proposals were developed in 2016.

Key Points
The overall rating for this output is A++. Realistic financial forecasting as well as close project supervision and implementation resulted in achieving the milestone. Disbursements have been more predictable through accurate work planning and financial forecasting with all contractors. Delays associated with unreliable schedules of delivering imported construction materials continue to affect the disbursement forecasts. For Indicator 5.2, no concept notes and project proposals were planned or developed for 2016 and none are anticipated for 2017. The average time to develop a concept note to an approved project proposal remains 124 days against the target of 180 days. This target should be retained if the SDF continues into a second phase to drive efficient and timely delivery of project design.

2016 witnessed a sharp devaluation of the UKP after its referendum to leave the European Union. This has contributed to a 10% reduction in SDF finances, set against a fully programmed SDF portfolio on pre-referendum exchange rates. The SDF has a contingency but that was exhausted because of the Euro exchange rate reduction since the start of the SDF in 2013. A concerted effort will need to be made in early 2017 to find savings across the portfolio.

Summary of responses to issues raised in previous annual reviews (where relevant)
Capacity Development: The SDF Secretariat has proposed establishing procurement units in selected Ministries in line with the draft Procurement Bill still pending a Parliamentary process and subsequent approval. Donors are being approached by the chairman of the national tender board and the roads development authority about this legislative paralysis and will lobby as appropriate. The SDF continues to support the development of government staff capacity and capability improvement through the provision of on-the-job training and coaching.

Recommendations
1. The SDF has already lost about 10% of its value in 2016 due to currency exchange rate fluctuations. Mechanisms should be put in place to protect the fund against such loses in future. The first JSC meeting of 2017 must focus on finding cost savings and take tough decisions to absorb ~ 10% financial loss.
2. No further work should take place on the incentive fund concept in line with recent IAD recommendation. The current SDF financing and disbursement implementation arrangements should remain in place until the completion of the SDF. Any subsequent phase of the SDF should consider the political economy of PFM reform before any further work on using government financial systems.
3. Any subsequent phase of the SDF should re-design the incentive fund based on political economy analysis and the status of the WB PFM programme.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The SDF key cost components are mainly the management fees and the related project expenses (operational expenses) which constitute the programme management costs. The programme management costs, as at 31 November 2016, are at 16%. The key cost component under project expenses are mainly accommodation which take up 4.5% of the individual project management costs, security (4%) and travel (2.1%). A payment by results approach adopted for the SDF programme ensures best value for money. With the principles of engagement being results-focused, payments continue to be made based on satisfactory delivery of set targets that are linked to output indicators in the logframe.

Pound stirling has significantly reduced in value against most of the major currencies – critically for the SDF against the US dollar – since June 2016. This has had a major impact on SDF finances as the UK is the major donor to the SDF. The impact of this has been a re-organisation of inputs in some projects, reducing scope of activities to focus only on infrastructure at the expense of some further civil service capacity related work. The fact that donors contribute in different currencies has not affected the overall reduced value of the SDF because the contributions are converted into US dollars in real time.

VfM performance
The SDF secretariat has developed a VfM framework which was updated in November 2016. It includes the following:

Economy
The SDF has realised savings through negotiation with suppliers. The secretariat has consistently undertaken a comparative analysis of the market rates e.g. SDF infrastructure delivery benchmarked against tender proposals’ costing. The standardization of procurement procedures and policies has ensured that the procurement processes are transparent and fair resulting in timely and competitive procurement. An example of this VFM is the cost per km for the rehabilitation of roads: before the SDF the benchmark was $105,000/km; the SDF has reduced this to an average of $70,000/km for comparable work.

The SDF has demonstrated economy in its utilisation of a high number of national and regional consultants and suppliers with a focus on engaging and building local capacity. International expertise is only utilised where it is absolutely necessary. The capacity building work is an example of this where the extension of training to Sool and Sanaag drew on Somaliland expertise in the second phase. Out of 225 consulting assignments,165 were awarded to Somaliland consultants, representing a 73% engagement rate of national consultants. The utilisation of shared resources has helped lower the secretariat’s operational costs through economies of scale, by utilising shared resources across all Mott MacDonald’s managed programmes in Somaliland.

Efficiency
The recent ICED report on VFM in Infrastructure in Somalia flagged a number of key recommendations with regard to efficiency which have been incorporated into the SDF2 business case. One key recommendation is that the programme logframe should incorporate quality elements ensuring that inputs are translated into high quality infrastructure outputs that meet the requirements of intended use. Other recommendations include the need for efficiency monitoring systems to be put in place and for clearer cost efficiency indicators and benchmarks in the logframe.

Organisational efficiency and programme governance. Mott McDonald is a consistently strong implementing partner and there are several examples of Mott actively managing partners, managing challenging relationships with line ministries, scrutinising due diligence to improve performance, and changing partners if necessary.

On time on budget. Infrastructure programmes are often fraught with delays in FCAS environments – e.g. community based conflicts, and procurement interference – making predictable budgeting a challenge. In 2016 the SDF managed all major challenges effectively meaning that all projects were on time and on budget. The SDF projects hold contingencies for budget overruns which is held within individual project budgets. Out of 12 projects, only 2 (Ministry of Water and Ministry of Livestock) drew down on their budget contingency in 2016, both because of challenges with the local community. Release of contingency funding is always approved by the JSC.

Effectiveness
Strategies and work plans have been developed in close partnership with local stakeholders to ensure local ownership and buy-in, e.g. Qool Qaday project. The SDF has made significant progress to ensure an equitable distribution of its development initiatives across Somaliland including development initiatives in the Eastern regions of Sool and Sanaag. The equitable distribution of projects has been delivered through clear instructions from the National Planning Commission – clearly shown in the table below. Through the capacity surge project and the contracting of local consultants and suppliers, the SDF is building the capacity of its private sector partners to deliver better services.

Assessment of whether the programme continues to represent value for money?
Evidence suggests the programme continues to represent value for money. Most of the project components have made good progress against outputs and outcomes, and this is reflected in the overall project score.

Quality of financial management
The SDF secretariat is on track against spend forecasting.

	2012/13	2013/14	2014/15	2015/16	2016/17
Forecast	£200,000	£5,000,000	£4,600,000	£7,857,706	£6,180,000
Spend	200,000	1,428,721	3,560,976	7,779,199	6,180,000

The secretariat has been consistent in preparing yearly budget forecasts which it shares with SDF donors and the government for discussion. The forecast is monitored regularly during the quarterly JSC meetings and the bi-monthly programme management board meetings. Substantive financial issues are proactively addressed in a timely manner.

The reduction in the £ in 2016 has been significant and the SDF contingency has been unable to cater for such a decrease. At the end of 2016 the SDF deficit is estimated at USD 2.5m. This could increase to USD 3.6m if exchange rates deteriorate another 10%. Managing this deficit will be a major challenge for 2017 and cuts in some project components are inevitable. The potential impact of this deficit is likely to be the reduced scope of some projects, and in some extreme case(s) stopping a project all together

The external audit report for FY 2015/6 provided an unqualified opinion on SDF financial statements.

Date of last narrative financial report	19 December 2016
Date of last audited annual statement	21 December 2016

E: RISK (½ page)

Overall risk rating:
The overall risk rating for the SDF is moderate.

Overview of programme risk
The overall risk of the UK’s support to the SDF not achieving its objective is assessed in the original Business Case as Severe. However, the programme’s risks have been substantially moderated with DFID working in partnership with the secretariat, the Government of Somaliland and other development partners to ensure they are alive to risks emanating from SDF development initiatives. The secretariat has continued to refine and develop its risk management processes including undertaking more community awareness and participation meetings, utilising monthly programme management board meetings and quarterly JSC meetings to monitor programme risks. In addition, the secretariat continues to update its risk register on a quarterly basis as part of its quarterly reporting requirement. Throughout the year, the risk register is revised to identify emerging and existent risks ensuring they are mitigated.

While the risks and mitigation measures set out in the Business Case still apply, there are some major risks which could adversely impact the programme in 2017, they include:
- Procurement: The secretariat continues to grapple with attempted interference in mainly social sector procurement processes, e.g. the rehabilitation of Dayaha School and Erigavo and Las Anod health facilities. The secretariat has robust and transparent financial and procurement guidelines and additional safeguards through its consortium partner PWC. There is limited procurement remaining in the SDF but those outstanding processes will be subject to the same rigour and transparency as the processes that preceded them.
- Sool and Sanaag: All aspects of our projects in Sool and Sanaag are at high risk of not meeting targets. The key issues to mitigate are: drug procurement and supply, the management of Erigavo and Las Anod by an organisation that lacks major experience of managing hospitals, the cost benefit of both boarding schools, sustainability and lack of certainty of government taking on the recurrent costs post SDF. Ensure that a new indicator tracking service delivery is added to the logframe and monitored in 2017.
- Political and security risks: Given the Presidential Election is delayed to October 2017 , there is a risk of political turbulence and lack of strong government leadership affecting programme operations. The secretariat has mitigation plans in place to manage related risks and/or limit potentially adverse impacts.
- Currency exchange fluctuations: Foreign exchange fluctuations have impacted on available funding to the programme. The secretariat, in coordination with the JSC, is closely tracking the exchange fluctuations and its impact on on-going projects.
- Prolonged drought in Somaliland could impact on SDF programme results on livestock. The drought has caused significant livestock deaths due to lack of water and pasture, thus negatively affecting the livelihoods of pastorist communities.

Outstanding actions from risk assessment
There are no actions outstanding. The risk register has been updated to reflect the new DFID risk framework.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The SDF programme is scheduled to close in March 2018. The secretariat aims to finalize all projects by September 2017. Of the 119 broad activities planned in 12 projects under the SDF, 116 are on track to be completed on time representing a 95.8% completion rate. The remaining 3 activities which include 2 activities related to the Ministry of Water Resources (Las Anod and Elefwein Water Supply System) and 1 related to the Ministry of Health (Erigavo and Las Anod hospitals) will be only partially completed and an exit strategy needs to be designed in early 2017.

Performance of partnership(s)
The working relationship with the SDF Secretariat, government and development partners has been cordial and collaborative. DFID is in regular contact with the SDF partners and stakeholders either formally or informally. Regular interactions at the JSC with government officials has resulted in a focused and coordinated approach to key issues and enhanced implementation.

The governmental ministries and agencies involved in the SDF have shown high motivation to support or lead the implementation of the programme, with respective programme management teams actively engaging to coordinate the implementation of planned activities.

Twice every year DFID Somalia conducts a Contract Performance Review (CPR) of Mott MacDonald (the SDF Managing Agent). Mott is a key supplier of DFID globally. During the last review in June 2016, Mott had a score of 83% (rated as proactive and innovative, delivering with superior efficiency and the effectiveness above Contractual expectations).

Asset monitoring and control
All programme assets are systematically recorded and reported in a comprehensive asset register, maintained by the SDF Secretariat. The asset register is reviewed and shared with DFID Somalia every six months. The SDF Secretariat last updated their register in August 2016. The secretariat has instituted an asset management policy that specifies rules and regulations on asset monitoring and control in line with DFID guidance on asset management. All partner line ministries and government agencies are sensitised on the policy and must commit to and comply with the policy including vehicle use guidelines. A clear policy needs to be endorsed by the JSC in 2017 on assets such as vehicles that may be required for any continuation of the SDF.

With the programme in its final year, the secretariat should review its guidance to ensure it provides clear and transparent guidance on the management of assets particularly in regard to handover of assets in the transition period.

G: CONDITIONALITY

Update on partnership principles and specific conditions
DFID is not providing any direct financial aid to the GoSL. All SDF donors signed a Memorandum of Understanding with GoSL in 2014 which is currently being renewed (awaiting signature by the President). The MoU underpins the SDF and the Partnership Principles are regularly monitored by DFID staff.

H: MONITORING AND EVALUATION

Evidence and evaluation
Two reviews were commissioned in 2016 to mainly inform a potential SDF 2. The first review was carried out by two consultants that were fully engaged at the start of the SDF and for much of the first two years of its implementation. The second review drew on the Evidence on Demand resource. The question posed was evidence on the gradual handover of management responsibilities of multi-donor trust funds (MDTF) in fragile and conflict affected states. The review concluded that there was remarkably little evidence on handovers. The review stated that in any MDTF the vision is always for government to gradually take on delivery with stronger management and financial systems. However, the review cautioned against driving the handover of management responsibilities too quickly, and to protect the delivery of results in the earlier years of delivery. Both reviews, looking at the SDF from different angles, have had a major influence on the on-going design of the SDF 2 Business Case. IAD undertook a review of DFID Somalia systems and programmes in October 2016. The SDF assessment was positive with some relatively minor recommendations for further strengthening.

Monitoring progress throughout the review period
For the review period, the business case, operational manuals and progress reports were reviewed. AR workshops were held with the Project Management Teams culminating in a first draft of the indicator sections of this AR report. Interviews were conducted with selected ministries as part of eliciting feedback and assessing their views on the SDF’s contribution to the NDP. 34 key informant interviews were conducted ranging from government ministers/agency managers, SDF Project managers, district level government officials as well as religious and traditional leaders. The following Ministries were interviewed: Hargeisa Water Agency; Ministry of Agriculture; Ministry of Livestock; Somaliland Roads Development Agency; and Ministry of National Planning and Development.

The results from qualitative interviews confirm the findings from the quantitative survey: beneficiaries are content with the investments in infrastructure. Project implementers are generally content with the support from the SDF, and remain confident they will meet the SDF targets before the end of 2017.

Annex 1: Revised Logframe
Somaliland Development Fund

IMPACT	Impact Indicator 1			Baseline - 2013	MS1/Baseline - 2014	MS1 - 2015	MS2-2016	MS2-2017		Targets 2015-2017	Assumptions
More stable and prosperous Somaliland	Somaliland Gross Domestic Product (GDP) per capita.	Planned	No.	348	349	350	351	352		352	World Bank GDP and poverty estimates for Somaliland is available on an annual basis
		Achieved YTD	No.	NA	N/A	N/A				N/A
		Source		World Bank GDP and Poverty Estimates for Somaliland
	Impact indicator 2			Baseline - 2013	MS1/Baseline - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017
	Poverty and economic decline index.	Planned	%	NA	9.1	8.9	8.7	8.5		8.5	World Bank GDP and poverty estimates for Somaliland is available on an annual basis
		Source		Fragile States Index report published by Fund For Peace

OUTCOME	Outcome Indicator 1			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017	Assumptions
Improved and better resourced core state functions for the people of Somaliland	Cumulative Number of beneficiaries of services attributable to SDF supported projects	Annual Planned	No	NA	0	750,000	267,884	440,923
		Cumul Planned	No	NA	0	750,000	1,017,884	1,458,807		1,458,807
		Achieved YTD	No	NA	0	862,167	463,007
		Cumul Achieved YTD	No	NA		862,167	1,325,174	1,325,174		1,325,174
		Source		Source: SDF project documents & UNFPA Population Estimates
	Outcome Indicator 2			Baseline - 2013	MS1 - 2014	Baseline- 2015	Revised MS2-2016	Revised MS2-2017		2015-2017
	% of citizens reporting improved service delivery in government sectors supported by SDF.	Planned	%	NA	NA	33%	48%	63%		63%
		Achieved YTD	%	NA	NA	N/A	47%			47%
		Source		Source: SDF Perception survey
	Outcome Indicator 3			2013	MS1/Baseline - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017
	Average effectiveness and efficiency of SDF-supported GoSL Ministries and Agencies (Score 1-6)	Planned	No	NA	4/6	4.5/6	4.8/6	Qualitative		4.7/6
		Achieved YTD	No	NA			5/6
		Source		Source: SDF Organizational Assessment tool, Data for each of the SDF-supported Ministries and Agencies (6 in 2014-2015)
					0.801219339
OUTPUT 01	Output Indicator 1.1			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017	Assumptions
Improved water and road infrastructure to promote economic and socially equitable development.	Quantity of water per day available for distribution in urban water systems with SDF support.	Planned	m3/day	0	0	448	400	6,205			Relevant government agency and the selected contractor implement the project in a timely and high quality manner. Achievement of milestone 1.4 for 2017 will depend on the allocation of funds to the roads sector by the NPC and the JSC.
		Achieved YTD	m3/day	0	0	4,058	1,593
		Cumul Achieved YTD	m3/day	0	0	4,058	5,651	5,651		5,651
		Source		MoWR, MoA & HWA -Project Management Team (PMT) Monthly Reports
	Output Indicator 1.2			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017
	Number of rural water points constructed or rehabilitated with SDF support.	Planned	No	0	0	26	14	178
		Cumul Planned	No			26	40	218		218
		Achieved	No	0	0	28	41
		Cumul Achieved	No	0	0	28	69	69		69
		Source		MoWR, MoA & HWA-PMT Monthly Reports
	Output Indicator 1.3			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017
	Change in travel time on roads rehabilitated with SDF support.	Baseline	Minutes	NA	NA	57	60	100		72
		Achieved YTD	Minutes	NA	NA	33	22			28
		Source		RDA Baseline & End Line Survey Reports
	Output Indicator 1.4			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017
	Length of roads rehabilitated to all weather condition with SDF support.	Planned	Km	0	0	80	19.2	20
		Cumul Planned	Km			80	99.2	119.2		119.2
		Achieved YTD	Km	0	0	104	25.4	0		0
		Cumul Achieved	Km			104	129.4	129.4		129.4
		Source		RDA-PMT Monthly Reports

Impact Weighting (35%)

OUTPUT 02	Output Indicator 2.1			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017	Assumptions
Improved productive sectors enhancing incomes, food security and livelihoods.	Productivity of staple food (Sorghum) in Maroodijeeh Upper Catchment.	Planned	t/ha	1	0.8	0.8	0.9	1.0		0.9	1. The rains will come on time in the appropriate quantity.
		Achieved YTD	t/ha	1	1.2	0.7	2.5			1.6
		Source		FSNAU; MoA PMT Monthly Reports
	Output Indicator 2.2			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017
	Number of hectares of land conserved or rehabilitated (for both agricultural and livestock use) with SDF support.	Planned	ha	0	0	7,000	13,688	11,000
		Cumul Planned	ha			7,000	20,688	31,688		31,688
		Achieved YTD	ha	0	0	5,495	16,288
		Cumul Achieved	ha			5,495	21,783	21,783		21,783
		Source		MoA PMT Monthly Reports
	Output Indicator 2.3			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017
	Number of export livestock screened through the rehabilitated livestock holding grounds	Planned	No	0	0	0	100% completion of Aroori LHG infrastructure	90,000		90,000
		Achieved YTD	No	0	0	0
		Source		MoL PMT Monthly Report
	Output Indicator 2.4			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017
	Quantity of cubic meters of water per annum available in rural areas for Livestock with SDF support.	Planned	No	N/A	N/A	N/A	60,524	97,876
		Cumul Planned					60,524	158,399		158,399
		Achieved YTD	No	N/A	N/A	N/A	80,950	0
		Cumul Achieved					80,950	80,950		80,950
		Source		MoA/MoWR/MoL-PMT Monthly Reports
Impact Weighting (25%)
OUTPUT 03	Output Indicator 3.1			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017	Assumptions
Improved capacity of GoSL institutions to manage development projects.	Size of the Development Budget (inclusive of national + external resources)	Planned	USD	0	34,205,307	36,384,591	40,000,000	40,000,000		38,794,864	1. Other donors follow the SDF example of putting their contribution to SL on budget. 2. SDF model encourages GoSL to refocus more on development budgeting.
		Achieved	USD	0	36,384,591	26,000,000	Not rated			26,000,000
		Source		MoF National Budget Estimates
	Output Indicator 3.2			2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017
	Number of projects executed on time and within budget by PMTs	Planned	No	0	0	2	2	7		11
		Achieved	No	0	0	2	4			6
		Source		Quarterly progress reports
Impact Weighting (15%)

OUTPUT 04	Output Indicator 4.1			Baseline - 2013	MS1 - 2014	Baseline - 2015	MS2-2016	MS2-2017		2015-2017	Assumptions
Enhanced citizen perception of Government priorities, activities and expenditure	% of people who report improved access to potable water in Hargeisa	Planned	%	NA	NA	2%	4%	7%		7%
		Achieved	%	NA	NA	NA	20%
		Source		.
	Output Indicator 4.2			Baseline - 2013	MS1 - 2014	Baseline - 2015	MS2-2016	MS2-2017		2015-2017
	% of people who report improved journey time on SDF rehabilitated roads	Planned	%	NA	NA	5%	45%	60%		60%
		Achieved	%	NA	NA	NA	92%
		Source		SDF Perception Survey
Impact Weighting (10%)

OUTPUT 05	Output Indicator 5.1			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017	Assumptions
Improved capacity to prioritise development objectives and to plan and budget development activities	Average aggregate disbursement deviation from forecasts.	Planned	%	0	5%	15%	10%	9%		11%	Fund manager maintains capacity provide robust programme management to support effective delivery.
		Achieved	%	0		12%	5%			9%
		Source		Mott's financial reports - SDF monthly forecast reports; budget monitor and invoices; DFID ARIES records.
	Output Indicator 5.2			Baseline - 2013	MS1 - 2014	MS1 - 2015	MS2-2016	MS2-2017		2015-2017
	Average time from approved concept note to approved project proposal.	Planned	Days	0	200	180	No further Concept notes and project proposals expected	No further Concept notes and project proposals expected		180
		Achieved	Days	0		124	No further Concept notes and project proposals expected	No further Concept notes and project proposals expected		124
		Source		SDF Project M&E Records
Impact Weighting (15%)	`

Annex 2: Locations of SDF Projects

Annex 3: Value for Money-Selected Projects
SDF project	Description of Unit Measure	Unit Used	Brief Activity Description		Quantities		Unit cost (USD)		Variance
			Planned	Actual	Planned	Actual	Planned	Actual	Variance	% Variance
14-01 RDA - Hamas -Berbera - Sheikh Road (1st Project)	Cost per Km of road rehabilitated (Pothole and edge repairs, Asphalt concrete overlay of 40mm and rehabilitation of 17m span bridge)	Cost/km	Overlay 35 km of Road Section (15 km for Hamas-Berbera & 20 km for Berbera-Sheikh) combined with pothole repairs	Overlay of 55.3 km (38.3 km for Hamas-Berbera & 17 km for Berbera-Sheikh)	35	55	$ 182,925.7	$ 115,775.8	$ 67,149.9	37%
14-02 RDA - Kalabaydh - Dilla Road (2nd Project)	Cost per Km of road rehabilitated (Reconstruction of base course and providing asphalt concrete wearing course of 40mm) and construction of 100m reinforced concrete drift and installing 250m of reinforced concrete culverts	Cost/km	19.2 km of base course reconstruction & asphalt concrete	20.8 km of base course reconstruction & asphalt concrete	19	21	$ 108,125.0	$ 97,742.9	$ 10,382.1	10%

14-01 MoWR	Cost per metre of pipe laid	Cost/metre
	Burao Water Supply Expansion Project	Cost/metre	Expanding 12.9km distribution network, fencing of 2# tank locations and construction of 2 small houses for caretaker & spare parts room	Expanding 13.4km distribution network, fencing of 2# tank locations and construction of 2 small houses for caretaker & spare parts room	12,900	13,400	$ 46.1	$ 38.8	$ 7.3	16%
	uPVC, 8", PN 10 + Fittings	Cost/metre			5,100	5,800	$ 45.2	$ 37.5	$ 7.7	17%
	uPVC, 4", PN 10 + Fittings	Cost/metre			7,300	8,200	$ 38.5	$ 25.2	$ 13.2	34%

14-01 MoL	Price per metre of fence bought & delivered (woven wire)	Cost/metre			89,000	89,000	$ 15.7	$ 9.7	$ 6.1	39%
	Cost per metre of 3# boreholes constructed-Aroori	Cost/metre			450	626	$ 489.7	$ 352.0	$ 137.7	28%

14-01 MoERD	Hectares of Land & Forest Conserved from Construction of Linear Bunds and other conservation activities	Cost per Hectare			1,400	1,926	$ 496.5	$ 336.4	$ 160.1	32%
	Cost per m of soil bunds constructed (Large Soil bunds)	Cost/metre			326,000	343,200	$ 1.2	$ 1.0	$ 0.2	17%

Annex 4: Risks

	Risk	Potential adverse impacts	Mitigation measures to prevent risks and/or limit potentially adverse impacts
1.	New government in place with different key actors in leadership, including the possibility that their agendas/priorities are less supportive of SDF.	In the first quarter and last quarter of 2016, various changes were made to the Cabinet members as well as other Government officials. Impacts were felt by the SDF Secretariat and the Project Holders on project implementation as key project actors were replaced, resulting in transition phases in terms of information concerning the projects. The SDF Secretariat continues to follow up closely to ensure that all new players have the relevant information regarding their projects. Some of the effects include: / Decision-making over SDF projects initially slow down like in the case of the Ministry of Education. / Some new actors such as the new Minister of Information wanting revising of agreements made by his predecessor in relation to how the Communication relates with Radio Hargeisa and the Somaliland National Television. / General misunderstanding of how SDF procedures work among new DGs and Ministers	Continue investing in building relationships with new players when they enter into Government; / Maintain strategic relationships with Government.
2.	Government crippled by political manoeuvring and tension as elections come nearer, including the potential for changes in the leadership of the key SDF Ministries/Agencies.	Decision-making over SDF projects slowed down and biased. / Voter registration was initiated and temporarily halted due to the prevailing drought in the country. It is possible that the postponement might have an effect on the preparedness by the National Election Commission and by extension could result in delays in elections. With new elections, the new actors may be less supportive of SDF. / The Presidential and House of Representatives elections that were slated to take place on the same day in March 2017 were separated. A presidential decree proposed the separation of the two elections in order to calm the discontent from Sool and Awdal region who were not content with the number of seats allocated to them in the House of Representatives. The opposition requested for a legal interpretation from the Supreme Court of the decree; the court upheld the decree.	Maintain strategic relationships with Government / Invest in building relationships with new players when they enter into Government / Continue monitoring the changing political landscape and developments in alliances and political accommodations as the country heads towards the 2017 elections.
3.	Tensions over Sool and Sanaag between Somaliland, Puntland and Somalia turning into violent conflict.	In February 2016 it was reported that Somaliland and Puntland troops exchanged fire, after the Puntland administration established a new checkpoint in Muuq village (Boocame district, Sool region, 60 km east of Las Anod), near the border between Somaliland and Puntland. The Government of Somaliland reportedly accused Puntland of creating instability in the region which prompted the deployment of new troops in Muuq village on both sides. / The SDF responded by suspending travel to the region and only allowing essential travel only to Las Anod town. Additionally, alternative accommodation as a preliminary measure was found so that field trip members could stay outside of Las Anod. / Some of the potential effects included harm to programme staff and if the situation becomes work, inability to work in Sool and Sanaag, limiting the geographical coverage of the SDF.	The SDF continues to: / Conduct detailed security planning which include daily monitoring of the security situation in Somaliland / Minimize movement of staff to or Insecure areas or suspend work in these locations all together except in those cases when it is possible for local partners/individuals to continue project implementation / Adopt a flexible approach to planning and implementation, allowing project activities to be postponed or even funds to be shifted from one project to another with the JSC approval.
4.	Insecurity (see contextual risks above)	In March, insecurity was reported in Berbera when armed local militia attacked workers who were engaged in constructing a small dock. A large police raid was set up and all assailants were captured and transferred to Hargeisa main prison. / In June 2016, the paramilitary forces of Ethiopia (region 5) launched a surprise raid (resulting in 25 deaths) in Jama Dubad village which is located in the vicinity of Gashasho, Ethiopia, this triggered protests in Burao town. The SDF is implementing Water Expansion, Environment Conservation, and Livestock Holding in the region. / There was a tribal clash in Dararweyne, approximately 35 km to the east of Eliefwein, Sanaag region. The Ministry of Water Resources Project has been affected by this incident. The proposed Eliefwein Water Supply Project was moving to the design stage of implementation at the time this incident broke out.	Same as above.
5.	Variations in price and foreign exchange fluctuations	This has affected the amount of funds available for implementation of projects and limited flexibility of making further commitments to projects that were under budgeted.	To address this, the SDF Secretariat is: / Following guidelines for dealing with exchange rate variations where other currency other than GBP are used. which were provided by DFID; / In coordination with the JSC, tracking closely the forex movements in case of further fluctuations.
6.	Prolonged Drought in Somaliland	The drought has been experienced in Somaliland for three successive seasons with below average rainfalls. Farmers and herders that make up a high percentage of Somaliland have experienced water and pasture shortage. The prolonged drought has negative effects in terms of achieving the intended impact and outcome of the SDF programme.	Participate in the Inter Cluster Coordination Group meetings and ensure the livelihoods and water projects support response and recovery from drought conditions.
7.	Losing of core staff of the SDF Secretariat due to relatively difficult working environment.	During the first and second quarter of 2016 one of the SDF Secretariat core staff announced that they were leaving. Replacement was found but the adverse impacts were still felt. All mitigation measures are in place to avoid: / Disruptions to programme implementation / Loss of institutional memory. / Replacements were found and no programme interruptions were experienced in the transition period	Mott MacDonald as the SDF Fund Manager continues to: / Provide SDF Secretariat staff with competitive package and enabling working environment; / Establish a roster of experts that can replace core staff if needed; / Set in place a robust system for knowledge management within the SDF Secretariat to manage, store and share information generated.
8.	The SDF being hijacked by one or more political/clan-based elite as regards the allocation of funds and procurement.	This risk is particularly relevant in the Eastern regions where mainly the Ministry of Education and the Ministry of Health are implementing projects. The clans have varying interests and pressure is felt by the SDF Secretariat national staff to take those affiliations into account. Community mobilisation, through the PMTs, as well as internal Secretariat procedures to protect national staff, are being continuously implemented. The potential effects of these include: / Programme failing to invest where needs are highest / Programme failing to deliver value for money due to biased choice of contractors/other implementing partners / Negative reputation of the programme amongst communities / Programme causing conflict amongst communities / Likewise, these risks need to be taken into account for the Ministry of Livestock activities in Qool-Caday where a workshop has resulted in a list of activities for potential implementation in the area instead of the LHG. Caution is to be paid as to including the various stakeholders, and further conflict and community issues need to be avoided.	The SDF Secretariat continues to / manage this risk by: / Ensuring staff made aware of political and social structures through the SDF political economy analysis which is updated at least annually; / Put into place a robust and transparent procurement system; / Maintain strategic relationships with Government at central, regional and district level.
9.	The PFM Reform Strategy and related programmes failing to or being slower than anticipated to achieve their reforms, hampering the phased approach of transferring fund control to the Government based on meeting benchmarks and instead using external systems.	There exists a perceived lack of transfer of Fund responsibilities to the Government of Somaliland among some Ministry officials, especially the new ones. While such a transfer has indeed not substantially happened yet, this has actually been the result of the absence of PFM benchmarks set by the GoSL whose achievement was expected to be the basis of the transfer of responsibilities This issue will be closely followed up over the next quarter. The effect delays in the coming up with and agreeing on PFM benchmarks include: / Missed opportunities to build core state functions, limiting the intended transformational and sustainability effect of the SDF / Non-compliance with OECD-DAC best practice that projects and funds are most effective when building internal government capacity and systems as much as possible	The SDF Fund Manager: / Continues to encourage presence of PFM-stakeholders at Joint Steering Committee meetings, creating leverage over and involvement in the reform process from the SDF side / As part of the SDF M&E system, closely monitor progress in the PFM programme / Allowing SDF funding and expertise to be used to support the PFM programme if needed and relevant
10.	Inability of the SDF to support long term interventions as the Fund progresses in time, slowing down the ‘intensity’ of the Fund towards the end of the programme period	As the end of the programme period comes closer, it is increasingly important to track activity implementation and to ensure tight planning of activity components. While the possibility of long term interventions diminishes, tracking existing activity implementation also becomes increasingly important. For activities such as the operationalization of the schools, this means moving its implementation forward to coincide with the construction of the school.	The SDF continues to: / Closely plan and track project activity implementation; / Spot opportunities for bringing forward essential activities to make the most out of the remaining timeframe and ensuring essential activities are implemented optimally; / Communicate to the JSC where adjustments in terms of time and money are needed to ensure completion of all project activities within the SDF timeline.
11.	Limited community support for and ownership of SDF projects	Discussions concerning the Qool-Caday livestock holding ground component of the MoL project have been ongoing for a considerable period. At the PB meeting of March 24, 2016 comments were raised that community members had stated their reservations about the project. These reservations are however considered to be representative only of a minority of people. / Additional community mobilisation was recommended nonetheless. The potential impact of these includes: / Projects achieving less results than planned for / Negative reputation of the programme.	The SDF Secretariat: / Ensures community consultation and acceptance prior to the project proposal development stage, including buy-in of key local stakeholders (Mayor, Deputy Mayor, clan leaders). Where this is not possible, it is highlighted, like in the case of the Ministry of Livestock. / Through the Communication Hub engages the communities in different project locations to ensure they are aware of the project objectives.

SCORING GUIDE

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review process