Project Completion Review - Top Sheet

Review Date:	January 2017

Title: Africa Enterprise Challenge Fund (South Sudan Window)
Programme Code: 202848	Start Date: September 2011	End Date: December 2016
If programme was closed >1 month early please describe in a few words why.	Programme closed to facilitate transfer of management from DFID South Sudan to DFID’s Africa Regional Department (ARD), ahead of a move to a Post-Conflict Window (PCW) to more accurately reflect the operating context in South Sudan.

Summary of Programme Performance

Year	2012	2013	2014	2015	2016 (PCR)
Programme Score	B	A	B	B	B
Risk Rating	Medium to High	Medium	Medium to High	High	Severe

Financial Position

Original Programme Value	£6,000,000
Extensions/ amendments	Reduction of AECF budget from £6,000,000 to £3,763,603 (formalized the 07/04/2016) / Extension of project end date from 31/12/2014 to 31/12/2015 (approved the 15/01/2015) / Extension of project end date from 31/12/2015 to 31/12/2016 (approved the 29/12/2015) / Transfer of £1,100,000 to ARD for the continuation of the project (approved the 04/10/2016) / Reduction of the remaining budget in DFID South Sudan from £210,216 to zero (approved on the 05/10/2016)
Log-frame revisions (with dates)	New logframe harmonised for all AECF windows (19/06/2015)
Total programme spend	£2,453,387

Follow up actions required following closure
1. The African Enterprise Challenge Fund (AECF) programme was negatively affected by the conflict and ongoing instability in South Sudan, and has therefore not performed as well as expected. DFID South Sudan will now transfer the management of the programme to DFID's Africa Regional Department (ARD), which will manage the AECF South Sudan Window (SSW) along with the AECF Agribusiness Africa Window (AAW)[1]. DFID’s ARD will also plan for the SSW to merge into the Post-Conflict Window (PCW), which - given the operating context[2] - is a more appropriate window for the South Sudan portfolio of projects. This Post-Completion Review (PCR) was completed to allow the closure of the programme within DFID South Sudan. The recommendations should be followed-up by DFID’s ARD. Given that insecurity persists and continues to weaken the economy, the Implementing Partner (IP) should conduct regular stocktakes of the progress made and challenges faced by the grantees throughout the next year and reassess risks and context to see if the programme (and individual projects) is still fit for purpose..
  [1] AECF runs competitions under different ‘windows’, which can be for a specific region or country (e.g. post-conflict states, South Sudan) or an economic sector (e.g. agribusiness, renewable energy, adaptation to climate change).
  [2] Political tensions, severe economic downturn, and increasing insecurity including in areas where AECF companies operate.
2. Given difficulties with travelling to field sites and verifying results, the IP should pilot remote verification methods to ensure that the independent verification of results can be undertaken each year upon receipt of project reports.
3. As the programme has scored two consecutive B’s at annual review (and a B at PCR), DFID ARD to agree on a Project Improvement Plan (PIP) with the IP.

A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202848/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202848/documents

Outline of programme and what it has achieved
Established in 2008, the African Enterprise Challenge Fund (AECF) is a financing mechanism that works with the private sector to provide a combination of grants and interest free loans to innovative and commercially viable business ideas that benefit small farmers and rural households. AECF currently works in eight ‘windows’ and is hosted by the Alliance for a Green Revolution in Africa (AGRA). The Fund Manager (FM) is KPMG International Development Advisory Services Africa.

In December 2011 DFID committed £6m to the South Sudan Window (SSW). An Accountable Grant was signed between DFID and AGRA for three years, with a plan to extend[3]. The programme initially aimed to support 11 projects proposed by local or international enterprises. A first round of competition was launched in October 2011. Following the selection process, five companies were contracted in 2013 and £2,112,500 (US$3,380,000) of AECF funding was approved. Grantees are:
[3] From the onset, it was expected that the SSW would be a seven year window, as for the other AECF windows.
1. Century Seed Company Ltd: a maize seed farm with national distribution and sale;
2. Honey Care Africa Ltd: honey collection, refining and sale (largely exported to Kenya), now complemented by production and processing of groundnut and sesame;
3. South Farmers Company: commercial crops production and integrated poultry venture;
4. Garden of Eden Company Ltd: maize production and market access for small producers;
5. Frontier Finance: provision of microcredit to micro-entrepreneurs in the agriculture value chain.

Following the outbreak of conflict in December 2013, DFID South Sudan refocused its strategy to increase the provision of humanitarian assistance. As the five selected companies were not operating in the conflict-affected states, support to them continued, but DFID and AGRA agreed that given the uncertain context no new investments would be made. The initial £6,000,000 budget was reduced to £3,763,603 and a no-cost extension (NCE) was granted for one year to December 2015. An Annual Review (AR) undertaken in October 2015 recommended continuing the SSW as well as merging the management of the SSW with another existing window to decrease the management burden and cost. A second NCE was therefore granted to December 2016, to enable management of the SSW to be transferred from DFID South Sudan to DFID’s Africa Regional Department (ARD).

This Post-Completion Review (PCR) is part of the transfer process and the recommendations will be used by ARD. From the start, this programme was designed for a context in which the business environment would improve through the development of conducive policies (e.g. trade policies) and new infrastructure. The conflict and resulting escalating economic and humanitarian crises have meant that this programme has performed less well than expected. Whilst it has delivered some results, these are less than in other countries (including from the post-conflict window).

Up to June 2016, the SSW has done well in disbursing 66% of the contracted commitments. Three out of five projects are operational (Century Seeds, Honey Care and South Farmers) and the latest results available show that 2,896 households (17,376 people)[4] have benefited from AECF projects, with a cumulative benefit of £430,270 (US$ 688,431). The SSW also contributed to job creation (45) and total net wages of £268,066 (US$428,906). However, following a new spike of insecurity in July 2016, the reviewer was unable to visit the projects. Communications between the FM and grantees indicated that:
[4] AECF’s primary beneficiaries can be customers (benefiting from services provided by an AECF funded project) or suppliers/producers (benefiting from the sale of their produce to an AECF funded project).
- Honey Care paused the purchase of honey due to fighting in the supply areas but was planning to resume its activities as soon as possible, including the export of honey to Kenya.
- South Farmers was affected by the looting of 25,000 chickens from their Juba farm. Crop production outside Juba was not affected. The company was still planning to establish a parent stock farm for broiler chickens in South Sudan and to stop the import of broiler chickens.
- Century Seeds: One farm of groundnuts seeds was robbed during the harvesting period and the company believes that a significant number of local farmers have fled due to insecurity.
## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment
Overall AECF has scored a B – moderately did not meet expectations. The AECF is designed to reduce poverty by catalysing private sector investments, creating jobs, and leading to wider impact on market systems and the business environment. So far, the SSW has achieved the following results:

Indicator(s)	Milestones (2015/16)	Progress (2015/16) *
1 Cumulative Development Impact[5]: / total net benefit (US$) / total net wages (US$) / development rate of return (DRR) = ratio of development impact (a+b) to funds disbursed	3,000,000 / 390,000 / 1	688,431 / 428,906 / 0.6
2 Cumulative (US$): / (a) grantee matched funding / (b) third party funding, and / (c) funding successfully facilitated by AECF Connect[6].	TOTAL: 6,131,096 / 2,806,000 / 3,325,096 / 0	TOTAL: 5,269,373 / 2,834,261 / 2,435,112 / 0
3 Number of ongoing projects: / (a) bringing a new technology or business model / (b) replicated by other market players in some way, or / (c) that have led to other systemic changes.	1 / 2 / 1	0 / 2 / 2
[5] The development impact of AECF includes all incomes achieved by the beneficiary farmers from sale of their production (total net benefit) as well as all the salaries of workers (total net wages).
[6] AECF Connect supports AECF grantees to raise capital from private investors and lenders.

* Due to the verification process, results (for outcome 1 and output 1) reviewed in this PCR are those verified by June 2016, which were achieved up to December 2015. The remaining outcome and output indicators (related to operation of the business and management of the funding windows) use data as of the end of June 2016.

The SSW has helped businesses to emerge in a very difficult environment and several of these projects would not have been implemented without AECF funding. Every £1 invested has created £0.60 of benefit thus far. The matched funding raised (i.e. funds mobilized by the enterprises to match the AECF grant) was $5.3m, which is below but close to expectations. The SSW also achieved its objective of promoting innovation and changes in the business environment[7]. While achieving these results in a context such as South Sudan is positive, various factors are impeding AECF from achieving greater impact:
[7] In 2014, the Honey Care project has positively changed regulatory procedures in South Sudan by getting certificates of origin and successfully exporting honey legally to Kenya. The Century seeds’ business model (commercialization of certified seeds) was also replicated by two players in 2015.

- Only one project was able to generate significant development impact (Century Seeds). Two of five projects did not effectively start and will now be closed (Garden of Eden, Frontier Microfinance);
- The macroeconomic conditions made the business operations difficult and much more expensive than anticipated. This is forcing companies to focus on profitable but less impactful activities. Century Seed, for instance, has changed its business model from local outgrowers[8] growing seeds to importing seeds from Kenya. Honey Care is distributing containers to harvest honey (instead of bee hives to increase production) and started to buy sesame to generate additional income. The development impact of this project on both outgrowers and beekeepers will remain limited[9];
  [8] An outgrower is a farmer that undertakes to supply agreed quantities of crop/seed, often at a price that is fixed in advance.
  [9] In 2015 the company was still working with 6,000 out growers but this was less than the 8,000 base year total.
- Grantees cannot raise funds from commercial capital sources (banks) because of the volatile political and economic environments, which further depress operations;
- Some enterprises are also facing difficulties calculating and reporting their results. For example, unclear performance information provided by Honey Care meant that the FM was not confident in reporting any development impact from Honey Care for 2015[10].
  [10] The AECF could not verify the development impact due to the prevailing volatile situation.

As a result the SSW is moderately not meeting expectations and is unlikely to meet them. A future transfer of the SSW window to the PCW should help to revise down the targets in line with a more difficult context. With more flexible management approaches on the part of the FM under the PCW, companies might also be more able to respond to challenges. However, the outlook of the SSW looks challenging and ongoing external challenges in the country make it unlikely that significant further benefit to smallholders will be achieved in the near future. Risks and context will need to be thoroughly reassessed before any further extension or transfer of this window.
Output Score and Description
	Output indicators	Score	Impact weighting	Comments
1	Business initiatives supported by the AECF generate development benefits with high outreach, in particular to: those in rural areas; very poor; women; and youth.	C	30%	Of the five projects, only three (60%) have generated some development benefits but with limited outreach. These benefits and the outreach are significantly lower than expected.
2	The business initiatives supported by AECF, are sufficiently commercially viable that the associated development impacts are sustainable	B	25%	Two of five (40%) projects were commercially viable (assessed at December 2015) but deterioration is expected in 2016 following a spike of insecurity that has led to losses (e.g. robbery), combined with a severe economic crisis.
3	AECF identifies and supports business initiatives which generate sustained and positive development impacts and which are innovative	B	25%	Four business projects in South Sudan are considered as innovative, but are not assessed as generating significant impact. There is limited external communication on these innovations.
4	AECF identifies, selects, contracts and provides managed support to business initiatives	B	20%	Overall AECF SSW struggled to find acceptable initiatives and could not attain its initial target in terms of number of businesses contracted.

Lessons and how these have been shared

1. Political Economy Analysis: A higher level of political economy analysis at the design and/or inception stage would have been beneficial to identify more accurately the risks and constraints, and may have recommended against programme implementation so soon after national independence. A more prudent approach would have been to wait until the country stabilized and became conducive to business investment. The programme performance has indeed been severely affected by the instability that has prevailed.

2. Working with the private sector in a fragile business environment: The programme would have also benefited from a thorough market survey of potential grantees during its design. Indeed, it became clear soon after the start of the programme that there was a limited pool of business-ready enterprises[11] and that most businesses were limited in size, scope, skills and capacities. The SSW struggled to find a sufficient number of credible agri-businesses to invest in. Several of the selected companies also struggled to produce accurate and timely reports. Future private sector development programmes in South Sudan will need to integrate services (e.g. mentoring, advisory services, and training) that help the companies to build their financial and business capacities[12]. This would increase programmes’ ability to work with low-capacity grantees, including marginalised groups such as women-owned businesses.
[11] Able to work with a challenge fund in which there is no function to build capacity of businesses.
[12] In the SSW, technical assistance was provided during the development of business plans. It became unavailable after the revision of the budget in 2014 when budget for additional services has been reduced to a minimum.

3. Reaching the poor and most vulnerable: One insight emerging across all AECF windows is that projects might have been over-optimistic on expected development results (i.e. creating jobs and benefits for the rural poor). In the SSW some of the supported businesses had to review their business plan to increase their financial viability. Consequently they had to scale down some of the activities that were less profitable even though they were helping rural poor to access markets and sell their produce.

4. Value for Money (VfM) and risk associated with a small single-country window: As success is dependent on the condition of one economy, single-country windows like SSW are inherently more risky than multi-country windows. At DFID level the cost of managing a small window is disproportionally high as staff time remains similar regardless of the size of the window. The SSW case also showed that the VfM decreases if funds remain unutilised[13] and cannot be reallocated through a new competition. As management fees were frontloaded, the total management cost as a percentage of funds disbursed is significantly higher for the SSW compared to other windows. This is one of the reasons why the management of the SSW is being transferred to another department and why the SSW should then be integrated into the Post-Conflict Window (PCW)[14].
[13] Funds can remain unutilised if projects fail or if less grantees than expected qualify for funding.
[14] The PCW currently operates in Democratic Republic of Congo, Liberia, Sierra Leone and Somalia/Somaliland.
## C: DETAILED OUTPUT SCORING

Output Title	Business initiatives supported by the AECF generate development benefits with high outreach, in particular to: those in rural areas; very poor; women; and youth.
Output number per LF		1	Output Score	C
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes (was 40%)

Indicator(s)	Milestones (2015/16)	Progress (Dec 2015)
1.1 Net number of primary beneficiaries benefitting from ongoing AECF funded projects, by year, expressed as number of: / (a) households; and / (b) people.	10,000 / 60,000	0 / 0
1.2 Average net benefit per household per year (US$).	80	0
1.3 Percentage of direct primary beneficiaries that live in rural areas.	N/A	- [15]
1.4 Percentage of direct primary beneficiaries that are poor (i.e. earn <US$2/day)	N/A	-
1.5 Percentage of direct primary beneficiaries that are women.	N/A	-
1.6 Net additional jobs created (FTE) through/in enterprises supported by AECF: / (a) men; / (b) women; and / (c) youth (18-35 years).	TOTAL: 80 / 40 / 40 / 64	TOTAL: 49 / 29 / 20 / 6
[15] There are no targets/results for 1.3 to 1.5 as these were to be derived from AECF verification studies, which will be conducted only for the largest projects in terms of development impact and therefore not in the SSW.

Key Points
The SSW aims to benefit 18,750 farmers/out-growers and clients by 2017 (1.1). While the programme supported 2,758 households in 2013[16] and 2,896 households in 2014[17], the number of beneficiaries was down to zero in 2015. This is partly due to Century Seeds replacing its out growers’ scheme with a more profitable seed import model. However, it is also explained by the fact that three enterprises did not submitted their results on time and Honey Care’s results were not verified (because the FM could not travel due to the conflict) and therefore could not be used. The lack of timely and reliable reporting is mainly due to the weak managerial and financial skills of grantees, which, as discussed in the lessons learned section, should be addressed to ensure accountability.
[16] With results that were largely attributable to one project (Honey Care)
[17] Results were largely attributable to Century Seeds while Honey Care results could not be verified

The net benefit per household[18] (1.2) was zero in 2015 as no households were reached. In 2014 this indicator was $161 per beneficiary household (against a target of 80$), which was due to the high net benefit attributable to Century Seeds. The number of jobs[19] created (1.6) has increased from 29 in 2014 to 49 in 2015 which is positive but remains below expectations due to conflict and the harsh economic environment. In particular, the ratio of youth employed is below expectation (12% against 80%), which is problematic given the fact that youth are highly at risk of engaging in violence and conflict.
[18] Estimate of average monetary benefit which accrues to each poor household reached by AECF funded projects
[19] The companies are asked to report both full time and part time jobs (as full time equivalents) to capture all wages

Summary of responses to issues raised in previous annual reviews (where relevant)
- R2: milestones for output 1.1 was reduced (from the objective of reaching 20,000 households to a realistic final objective of 10,000 in 2017; 30,000 to 12,500 in 2016; and 50,000 to 18,750 in 2017)
- R5: future milestones for jobs created were included, as per previous recommendation.

Recommendations for future programmes
- As the low performance is partly explained by lack of reporting and verification of results, the IP should ensure that mechanisms and incentives are in place to guarantee that all results (1.1 to 1.6) are communicated by grantees, in a timely manner, and can be verified by the FM[20].
  [20] Including through remote verification, e.g. through cellphone calls with randomly selected out growers/clients
- DFID to ensure that AECF windows implemented in similar conflict-prone contexts develop specific strategies to maximise the involvement of and the impact on youth.
Output Title	The business initiatives supported by AECF (and the products and services delivered through them), are sufficiently commercially viable that the associated development impacts are sustainable
Output number per LF		2	Output Score	B
Risk:		Severe	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Yes, up from 0%

Indicator(s)	Milestones (2015/16)	Progress (June 2016)
2.1 Ongoing projects that are profitable 36 months from date of contract: / (a) total number; and / (b) percentage	(a) 3 / (b) 50%	(a) 2 / (b) 40%
2.2 % repayable funds due for repayment that are repaid. / (a) = cumulative total repayable grants due (US$); and / (b) cumulative total repayable grants repaid (US$), / (c) = percentage.	Not due	N/A

Key Points
The results reported in 2015 by three companies indicated that two of them (Century Seeds, Southern Farmers) were profitable[21] at December 2015 (output 2.1). Despite the fact that this result is slightly below expectations, it is a remarkable result when considering the current context of South Sudan. As explained above (output 1) the changes made by some grantees in their business models, for example Century Seeds re-focusing its activities towards seed trading instead of seed production, explains how businesses can break-even within 36 months in a challenging, conflict affected context such as South Sudan.
[21] A business is considered profitable when the Earnings Before Interest, Taxes, Depreciation, and Amortization (EBITDA) are above zero. Figures are verified from the annual financial reports submitted by the grantees.

While the achievement of commercial viability is positive, it is important to monitor if businesses are able to maintain this viability, and more particularly in the deteriorating context. Further discussions are needed on the capacity of supported businesses to maintain their viability (output 2) while providing markets, jobs and/or services to the poor (output 1).

Summary of responses to issues raised in previous annual reviews (where relevant)
R6: The milestone for output 2.1 in 2017 was revised down to three projects (60%) in line with the targets set in the Post-Conflict Window (PCW), which takes into account the difficult environment by reducing the expectations related to rapid profitability.

Recommendations for future programmes
- Given that indicator 2.1 on profitability is measured only after 36 months, DFID should consider including an indicator (e.g. average level of growth) that can be monitored from the onset and that can show if projects are on-track - or not - to achieve profitability.
- For windows implemented in fragile states, DFID should consider increasing the number of months that is given to reach profitability (currently limited at 36 months from date of contract).

Output Title	AECF identifies and supports business initiatives which generate sustained and positive development impacts and which are innovative
Output number per LF		3	Output Score	B
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Yes, down from 33%

Indicator(s)	Milestones / (2015/16)	Progress (June 2016)
3.1 Total number of ongoing projects.	5	5
3.2 Ongoing projects that are marked 3 or above on the AECF innovation scale: / (a) total number; and / (b) percentage.	3 / 60%	4 / 80%
3.3 Ongoing projects achieving high development impact: / (a) total number; and / (b) percentage.	2 / 40%	0 / 0%
3.4 Ongoing projects where innovation is recognised: / (a) total number; and / (b) percentage.	2 / 40%	0 / 0%

Key Points
Following the revision of the target (recommended AR 2015) to reflect the operating context in South Sudan, the number of ongoing projects (output 3.1) is now meeting expectations. While the SSW projects have exceeded expectations in terms of innovation, these innovations have not led to a notable change in South Sudan business models. No SSW projects have achieved a high development impact.

In spite of the fact Honey Care’s results could not be accounted for, this component has achieved a B because several businesses were regarded as doing something new relative to the South Sudanese context. Therefore the SSW scored higher than expected in terms of innovation of the projects (output 3.2). This was measured through an “innovation scale” that rates each project from 0 to 6 (0 for a project that is not considered innovative, 3 for a project that is new for the company and new for the country, and 6 for a project that is new globally).

However, no external communication and discussion of the innovations was recorded and the indicator on recognition of innovation (output 3.4) currently scores zero. Though some communication might have been done, it was difficult for grantees to record or remember communication or discussion because they could not do proper media monitoring and could not follow all references to their project. This indicator therefore could not be measured. Given AECF’s main objective is the reduction of the poverty, it is important that successful business models are communicated to ensure their replication where possible.

Projects are considered to have a high development impact (output 3.3) when generating a total net benefit of $250,000 or more per annum. In the current context, where South Sudan is a complex and difficult business environment, no SSW project could achieve this level of impact ($250,000). This indicator is unlikely to be achieved in the near future in South Sudan.

Summary of responses to issues raised in previous annual reviews (where relevant)
- R7: The logframe was updated and indicators reviewed to ensure consistency with other windows.
- R8: The inclusion of a composite measure of innovation and country risk should be pursued centrally (no action required by the SSW).

Recommendations for future programmes
IP to support the recognition of innovative business models by ensuring that a communication and dissemination strategy is agreed with the different grantees and then monitored.

Output Title	AECF identifies, selects, contracts and provides managed support to business initiatives
Output number per LF		4	Output Score	B
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y (down from 27%)

Indicator(s)	Milestones / (2015/16)	Progress / (June 2016)
4.1 Cumulative number of: / (a) competitions closed; / (b) registrations completed; / (c) applications received; and / (b) eligible concept notes marked.	1 / No target / 100 / No target	1 / 493 / 187 / 116
4.2 Cumulative number of: / (a) full applications (i.e. business plans) submitted; / (b) approved; and / (c) approval rate.	10 / 8 / 80%	15 / 6 / 40%
4.3 Cumulative number of projects successfully contracted.	8	5
4.4 Cumulative number of contracted projects that closed before their original contract end date.	2	0
4.5 Cumulative project funding pipeline metrics: / (a) new funds available to projects (US$); / (b) funds committed to projects at IC stage, pre-contract signature (US$), / (c) % available funds committed; / (d) funds contracted to projects (US$); / (e) % available funds contracted; / (f) funds disbursed to projects (US$); / (g) % available funds disbursed	No target / No target / No target / No target / No target / No target / No target	3.985m / 3.380m / 84.8% / 3.380m / 84.8% / 1.982m / 49.7%

Key Points
The SSW initially started well[22] and received a high number of applications during its first competition (output 4.1). For various reasons[23], the SSW found only a few business plans to be suitable for investment (i.e. six as opposed to a target of eight) (output 4.2). After the full selection process, only five projects qualified[24] for receiving support (output 4.3). Compared to other AECF windows, a longer timeframe was required for contract finalisation because of the high degree of support required by applicants to produce concept notes and business plans which met the standards required (as discussed in lesson learned, most businesses were limited in size, scope, skills and capacities).
[22] The programme was launched in October 2011 through a series of well-attended events. The launch was accompanied by a promotion campaign in South Sudan as well as regionally, targeted at potential investors.
[23] Even compared with the other existing conflict-affected window, the pool of local (or diaspora) entrepreneurs was shallow in South Sudan, which could be explained by the lower level of education, especially in numeracy and business skills; and the limited exposure to large-scale farm estates before and during the civil war. Potential investors such as multinational companies or regional groups who had shown some initial interest in the SSW concept did not materialise.
[24] The full selection process included registration, application, concept note, business plan and due diligence/audit. Six projects were approved by the investment committee but only five went on to be contracted, others failed (at due diligence/audit stage) to meet all the requirements necessary for signing a funding agreement.

A total of $3.4m was committed and 50% of funds were disbursed by the end of 2015 (output 4.5). Whilst the programme has done well in disbursing the committed funds thus far, future disbursement of funds is now uncertain and might be further delayed given the deterioration in context since July 2016. Due to slow project progress and a lack of commitment to achieving project targets, the FM recommended the closure of Garden of Eden and Frontier Microfinance projects. The closure process is complete. This is in line with the anticipated closure of 20% of the projects (output 4.4).

Summary of responses to issues raised in previous annual reviews (where relevant)
- R9: Logframe indicators (4.1, 4.3 and 4.4) were reviewed and updated.
- R10: The use of any funds which are not expected to be disbursed should be considered by ARD.

Recommendations for future programmes
- Establish realistic timeline for the contracting stage through investigating entrepreneurs’ skills and support needs in advance;
- Ensure that selection criteria and rules (e.g. related to track record or matching grant rule) do not contribute to the exclusion of some young and promising but not yet established entrepreneurs;
- In fragile countries, such as South Sudan, integrate a built-in technical assistance facility to help to overcome the challenges related to limited skills and capacities, and to improve the access of marginalized groups (especially women, youth and the disabled) to the programme.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The main cost driver was management fees that were fixed (as part of the central programme) at 20% of committed funds (i.e. £1.2m for a seven-year £6m programme). Fees are split between AGRA (4%) who manages all fiduciary and legal matters and the Fund Manager KPMG (16%). Management fees were charged for the first two years of the window on the assumption that the value of the window was £6 million[25]. Following the reduction of the budget a reduction of £82,000 of fees was agreed with effect from 1 January 2015.
[25] AGRA gets an administration fee of £36.7k or 0.57% p.a. of committed fund that will represent after 7 years 4% of the 6,436k AECF SSW. The Fund Manager is charging a management fee of £322k, 225k, 161k, 161k and 161k for the first 5 years of the life of the SSW Fund. It does represent 5%, 3.5% 2.5%, 2.5% and 2.5% of committed funds. It should represent 16% of committed funds at the end of the 7-year project.

VfM performance compared to the original VfM proposition in the business case
The VfM performance of AECF SSW is less than initially envisaged because of:
1. the uncertain and deteriorating operating environment impeding business delivery/results,
2. the reduced size and stand-alone nature of the SSW, which decreased VfM[26]. The total management costs as a percentage of amounts disbursed to grantees was 46%, and whilst this ratio should decrease with time (if new disbursements are done), management costs will remain around 35%-40% at the end of seven years compared to the expected 20%. In addition, the management time required by DFID South Sudan to oversee the SSW has not reduced with the size of the window (but has increased with the deteriorating context) and is therefore proportionately more than other windows. It is worth investigating whether having separate DFID country teams managing individual windows provides good VfM. Transfer of the South Sudan programme management to the ARD (to be managed alongside other windows) should provide better VfM. Advisory support from DFID in country should still be sought to ensure coherence and maximise local technical input on critical project decisions[27].
  [26] Budget was reduced from £6m to £3.9m and only five SME’s were supported as opposed to eleven.
  [27] Once all disbursements will have taken place, the SSW should be transferred to the PCW managed by SIDA (Swedish International Development Agency) and will no longer be a DFID’s programme.

Assessment of whether the programme represented value for money
Following deterioration in the operating environment, this programme did not represent good value for money. The assumptions that the business environment in South Sudan was sufficiently stable and that there would be sufficient market-ready businesses were proven wrong and significantly affected the performance of the programme. Of the five businesses that passed the selection process, two could not prove the validity of their business models. The capacity of the three other businesses to be both financially viable and to generate significant development impact has not yet been demonstrated. However, closure of the five selected businesses would have been poorer value for money as, with more time (given the complex environment), more businesses may become viable. However, it will be essential to take timely decisions on down-sizing the portfolio if DFID foresees that the expected development benefits will not materialize.

Quality of financial management during programme
The quality of the financial management of the portfolio by the Executive Manager (AGRA) was identified as a major risk to the project in the 2014 annual review. Problems with AGRA’s accounting treatment of funds, inaccuracies and poor systems were highlighted. A financial due diligence (FDD) of the AECF was commissioned by DFID centrally and AGRA have invested in the capacity of their staffing since. The implementation of the FDD recommendations is monitored through the AECF Committee. DFID programme managers have been working closely with AGRA to ensure the quarterly reports they provide are accurate. Disbursement to AGRA were resumed early 2016 and no further problems have been reported.

Date of last narrative financial report	15 August 2016
Date of last audited annual statement	15 August 2016

E: RISK

Quality of risk management over the life of the programme
Except for the design phase (during which risks were underestimated) the quality of risk management was deemed appropriate. An extended due diligence process for successful applicants was conducted. While it caused delays in implementation, it was considered necessary because of the noted weaknesses of small enterprise partners and their limited business track record.

The AECF risk assessment process looks at the business model (profitability concerns with current business model), cash flow (performance concerns due to inadequate or lack of cash flow), development impact (project falling short of its development indicators), reputational (risk of fraud or political intervention), compliance (respect of all the stipulations of the funding contract) and character (credit history and personal background of the grantee). For each AECF window the FM updates a risk register at least every 6 months. The FM also updates a detailed risk assessment on each project in which “red” projects (representing high risk) are recommended for closure.

The programme risk for SSW was revised upward in 2014 (from medium to medium/high) and in 2015 (from medium/high to high). The four top risks and challenges currently identified by the FM are the volatile political situation, the insecurity, the poor economic climate and the poor infrastructure. Though the FM is correctly managing risks, the country risk remains high (now rated as severe following DFID’s revised risk categories). The increased instability during 2015/2016 has increased the country risk even further and the risk level is likely to remain at ‘severe’ level over the next few years. In addition to insecurity, businesses are particularly affected by the economic crisis and inflation which is adversely affecting availability of foreign exchange and the purchasing power of companies and people.

In line with DFID rules, it is agreed that if AGRA uncovers suspicion of fraud or corruption they undertake detailed investigations. One suspicion of fraud was identified and reported. The case has been managed appropriately by AGRA and the FM, in line with DFID policy and there was no financial loss.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
Spend has been slower than anticipated, which is mainly explained by the conditions in South Sudan, but might also be due to optimism bias (a feature of other AECF windows as well). The programme faced slow progress from implementation to operation due to the longer timeframe being required for SSW contracts to be finalised (approximately 18 months after the programme’s start date). Several partners took longer than expected in establishing their operational and production capacity, because of the difficulty of importing goods due to dollar scarcity, and fuel shortage. Some companies also faced challenges in setting up production of processing plants as a result of insecurity in the country. The original set up of the SSW was for a 7-year window and the programme was planned under the assumption that the initial 3-year contract would be extended. Despite the fragility of the environment, and the negative impact of the 2013 outbreak of violence upon the enterprises, two no-cost extensions were granted to extend support to businesses. However, the current situation in South Sudan (insecurity and economic crisis) might mean that none of the businesses are able to remain profitable in the longer term. A comprehensive reassessment of the context should be made before the signature of any future no-cost extension.

Performance of partnership(s)
The relationship between the Executive Manager (AGRA) and the Fund Manager (KPMG) and DFID was affected by the internal management difficulties faced by the Executive Manager and resulting poor financial management. The situation has improved since 2015, following the commissioning of the financial due diligence (FDD) and after AGRA invested in the capacity of their staffing. The partnership is now deemed adequate. The 2015 AR flagged the need to better institutionalise AECF experience and learning, as the historical knowledge is currently retained by high level managers only. The mobilization of new funding partners was also recommended to increase the longevity of AECF. The partnership with the Fund Manager has performed well, and they have provided a consistent managerial role to the SSW. The five business partners (supported companies) have been working under extremely difficult operating conditions, including lack of management capacity. While they have retained a positive relationship with the Fund Manager their own internal systems have been under great strain and this has sometimes impacted on their ability to report back on time.

Asset disposal and value obtained by DFID
The programme is being transferred to another team within DFID. There is no asset disposal required at this time.

G: CONDITIONALITY

Partnership principles assessment: N/A

H: MONITORING & EVALUATION

Evidence and evaluation
Evidence was collected by the FM through their monitoring and reporting process. The IP produces two reports annually: a first report on management (operations, competition management, financial management and knowledge management) and a second report on portfolio performance (performance against logframe, performance of projects, development impact). To enable better monitoring, a new harmonised logframe was agreed in 2015 with standard indicators across all windows in DFID.

In 2015 an independent mid-term evaluation of the whole AECF programme was conducted by Ecorys during which case studies were undertaken for 32 projects across the portfolio (no South Sudan case study was undertaken). This evaluation confirmed the generally positive development benefits of the overall AECF but raised questions regarding the “additionality” (i.e. whether the project would have gone ahead in the absence of funding from the challenge fund, and whether it would have happened at the same speed or scale) and sustainability of a proportion of the investments made. The final evaluation will take place in 2018.

Monitoring progress throughout the review period
The FM carried out regular visits to the contracted projects throughout the programme. Informal monitoring and conversations with partners were also held on a regular basis. In the last reporting period, at least one site visit to each the five projects was conducted between October 2015 and March 2016. Because of security and/or when project maturity was low, some projects were not visited at their field sites but discussions were held in Juba. Independent verification of development data, as well as full organisational assessments, has not been possible for all projects due to the security situation in South Sudan.

All partners were required to report annually each January, following which the FM conducted visits to verify the results. It is worth noting that some projects, for example Garden of Eden and Frontier Microfinance, had not submitted their annual reports by the time the FM was conducting the visits. In the first half of 2016, the FM therefore did not visit these two projects, which are now in the process of being closed.

In September 2015, DFID South Sudan conducted field visits to Honey Care and South Farmers, which allowed DFID to increase its understanding of the business models, the challenges faced by the companies and also the adaptation and mitigation strategies implemented by the companies to be able to operate in a context such as South Sudan. DFID also monitored the quality of relationship between companies and the implementing partner and observed a need for improvement in communication.
Annex 1: Summary sheets from each annual review over the life of the programme

Please note, no summary sheet is provided for 2012 and 2013 as this format did not exist at that time.

Annual Review - Summary Sheet (2014)

Title: African Enterprise Challenge Fund (AECF) -South Sudan Window
Programme Value: £6M		Review Date: 24-28 November 2014
Programme Code:	Start Date: September 2011	End Date: / December 2014

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	B	A	B
Risk Rating	Med-High	Medium	Medium to High

Summary of progress and lessons learnt since last review

The outbreak of internal conflict in South Sudan in December 2013, and the failure to find a lasting resolution to this conflict, has had a negative impact across all sectors. Agricultural production, the business environment and the investment climate have been severely damaged. The events in December 2013 required DFID South Sudan to revise its programming portfolio to fit a significantly changed context. DFID South Sudan’s Interim Strategy, approved by Ministers in February 2014, responded to the emergence of conflict and the vast scale of humanitarian need, and recognised that funds had to be reallocated to emergency response. As a result, funds for several programmes were reprioritised and the Interim Strategy made it clear that no new investments would be made in businesses under AECF beyond the existing five already supported[28].
[28] Note however that even prior to the outbreak of conflict in Dec 2013, the AECF target of support being granted to 11 businesses was significantly off-track

Of the six contracts originally awarded by the AECF SSW, five of those contracts had been completed and signed before the end of 2013. One (Dryland Seeds) was subsequently withdrawn[29] in June 2014 leaving a total of five from an original target of eleven businesses to be supported by the AECF South Sudan Window (SSW).
[29] The contract for Dryland Seeds was withdrawn due to due to the company failing to meet all the requirements necessary for signing a funding agreement.

Of these five businesses, only one (Honey Care Africa) has made substantial progress, is operating on a strong business footing, and its manager is confident that the business will achieve profitability in the next year. Two more businesses have remained operational (South Farmers and Century Seeds), but have been operating below expectations and capacity, having been detrimentally impacted by the conflict in various ways. The two remaining businesses (Frontier Microfinance and Garden of Eden) have struggled to become operational and their business operations have made no significant progress in the last year. However it is too early to write these enterprises off as in effect they have only been operational for eighteen months and need more time, particularly in such a fragile state as South Sudan, to prove their viability.

The key lesson learned is that the risks to running a successful Small and Medium Enterprise (SME) in a new, very fragile state - characterised by a weak governance environment, poor regulation, minimal support for business development, very low skilled employees, and high risk of conflict - were underrated in the original programme design. Both the Executive Manager (EM), the Alliance for a Green Revolution in Africa (AGRA), and Fund Manager (FM), KPMG International Development Advisory Services, Africa, agree that in retrospect it was perhaps too early to launch a programme of this nature in such a new and fragile state and that with hindsight, waiting another year or two would have been a more sensible choice. In retrospect, a higher level of political economy analysis during programme design is recommended for a programme of this nature in South Sudan and in other fragile and conflict-affected states in order to identify the risks more quickly and accurately.

It is recommended that the AECF provides early business support such as mentoring, technical advisory services and training. Currently AECF does not operate this way, but this review finds that in the South Sudanese context there is a need to provide a higher degree of additional support if businesses are to be successful.

The review also finds that a great deal more needs to be invested in South Sudan in governance, infrastructure, skills and capacity and in building a solid business environment before it is likely that SMEs will be able to flourish and succeed. A simple hard-nosed ‘sink or swim’ approach to business development is more likely to result in more SMEs failing than succeeding under existing circumstances.

Summary of recommendations for the next year

A no-cost extension for at least another full reporting year should be granted in recognition of the fragility of the environment, the lack of time the businesses have had since signing contracts, the average time taken for SMEs to become profitable even in less fragile African states, and the negative impact of the outbreak of conflict upon the enterprises. Additionally, non-extension would likely mean that several of the businesses supported over the past two years would fail, representing poor value for money on the investment made so far. However, DFID South Sudan will need to take a view on whether the time-frame cited by the FM as necessary to enable the five businesses to absorb the full grant disbursements – which would extend the programme to September 2019 – is practical and feasible.

A no-cost extension should also enable greater flexibility in relation to achievement of targets and milestones. Milestones identified in the log-frame which currently have indicators for 2015 would then be able to be assessed accurately and fairly.

The review finds that DFID should also give itself more time to assess the impact and value for money of the AECF SSW programme in a fragile state context.

Grant disbursements which were delayed against the original schedule, have only reached the half-way point and this should be considered in determining the duration of any no-cost extension There also needs to be recognition that business partners may also require an extended time period to provide matched funding.

In-kind asset valuation is still not consistent. This was raised as an issue last year, and is a problem across the entire AECF portfolio, not just the South Sudan Window. The FM should continue to follow up on consistent valuation, addressing concerns from business partners who have been unable to complete this exercise, particularly when cash-flow has been problematic.

The FM and EM need to resolve the question on the use of the ring-fenced budget for dissemination of best practice. This is still an action pending from the recommendations of the last Annual Review.

The AECF innovation ratings system is based on an initial rating by the FM of the business model but is then fixed for the duration of the project. As new businesses develop they may become more innovative as they react to circumstances. The current innovation rating system therefore is too inflexible and should be amended to enable innovation ratings to be changed through the life of the programme[30].
[30] Note that the FM does report on changes in innovation in its ‘Site Reports’, written after every monitoring visit, however these do not currently influence the original innovation rating given at the point of business plan approval and used by DFID for monitoring purposes.

AECF should consider providing early business support including training, mentoring and technical advisory services to South Sudan businesses, and possibly those in other fragile states.

Annual Review - Summary Sheet (2015)

Title: Africa Enterprise Challenge Fund (South Sudan Window)
Programme Value: £3.9m		Review Date: October 2015
Programme Code: 202848	Start Date: September 2011	End Date: December 2015

Summary of Programme Performance

Year	2012	2013	2014	2015
Programme Score	B	A	B	B
Risk Rating	Medium to High	Medium	Medium to High	High

Summary of progress and lessons learnt since last review

The South Sudan Window (SSW) of the Africa Enterprise Challenge Fund (AECF) has had another challenging year. The programme started in 2011 and DFID’s agreement with the Alliance for a Green Revolution in Africa (AGRA) to manage the programme ended on 31 December 2015. The small size of the window operating in a recently formed independent country (ranked the most fragile state in the world) which has been in conflict since mid-December 2013 has affected results. The window has done well in disbursing almost 60% of the contracted commitments to projects in this difficult environment, but suffers from limited reporting and verification of the results. Only three out of five active projects (Century Seeds, Honey Care and South Farmers Co. Ltd.) are currently reporting results and most of those results come from one project (Century Seeds). While the DFID project currently ends in December 2015 it was always expected that the SSW would be a seven year window (the same as other windows within the AECF) and therefore extended until 2017.

While the conflict continues in only 3 out of 10 states (and not the ones the AECF projects are operating in), AECF grantees have still been severely impacted by the effects of the conflict throughout the country, including difficulties in obtaining foreign exchange (due to devaluation), economic downturn, increased insecurity (e.g. robberies/theft) and fuel shortages.

The key issues identified during this annual review are:

- The window relies on one project for nearly all of its development results. Although it is common for AECF windows to be dominated by 1-2 projects, in the case of SSW nearly all the reported development results come from Century Seeds. The heavy reliance on one project for success increases the risk of failure.
- The pro-poor nature of the development results reported may be overstated. Century Seeds has changed its original project in response to market demand to work more with larger farmers as seed-out growers than it had originally intended. The development results reported for this component of the project therefore include a proportion of results which do not relate to the target rural poor population (living on less than $2 per day). More detailed verification work on these results is required.
- The value for money of the window is worse than other AECF windows. The reduced size of the window has increased the proportion of management fees paid when compared to other windows. From a DFID perspective, the management time required by the country office team to oversee an AECF window has not reduced with the size of the window and is therefore proportionately more than other windows.

Decisions need to be made about the composition of the SSW: whether to merge it with another window or to run a mini competition to utilise potential uncommitted funds. The progress of the five projects, advancement of the Peace Agreement and the status of the cessation of hostilities and any easing of the current issues in South Sudan will play a crucial role in this decision process.