   Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime.

Agencies should use Section M to provide a short summary from each Annual Review over the life of the programme (maximum 1 page per year).

Review Date:	31 August 2016

Title: Transparency International Secretariat Programme Partnership Arrangement / General PPA
Programme Code: 202505	Start Date: 1 April 2011	End Date: 31 March 2016

Summary of Programme Performance

Year	2012	2013	2014	2015	2016
Programme Score	A	A+	A+	A+	A+
Risk Rating	Low	Low	Low	Low	Minor

Financial Position

Original Programme Value	GBP 10,123,032 (Note: the amounts in this table include both our General and CHASE PPA. The report covers only the General PPA run by the TI secretariat)
Extensions/ amendments	GBP 6,748,688
Brief details of the 3 most recent log-frame revisions with dates	November 2015: updated our indicators related to communications and targets on organisational development (Outcome 1.3, Outputs 3.1 and 4.1). / January 2015: increased targets for outcomes 1.1 and 1.2 and for outputs 1.1, 1.2 and 3.2. / The previous version was the one submitted as part of the 2014-2016 extension proposal.
Total programme spend	GBP 16,871,720

Other DFID Funding

Vietnam programme – EUR 534,568 received in payments during the reporting year

Short Summary from each Annual Review over the life of the programme, 2011-15

See Section M.
A. Introduction and Context (maximum 2 pages)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202505/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202505/documents

Outline of programme and what it has achieved at the end of the PPA period

Outline of the programme
TI’s strategy 2015 was the overarching guiding document for the TI secretariat and chapters between 2011 and 2015. Its adoption was a landmark moment for the TI movement. This document sought to bring more common focus to the work of the TI movement while supporting its diversity. Continued PPA support has allowed us to take the implementation of our key strategic priorities to the next level and to develop Together Against Corruption, our 2016-2020 strategy. This new framework goes further in our ambition to become a people-centred organisation and to take on high-level cases of corruption to bring an end to impunity. With the Sustainable Development Goals (SDGs) being approved, especially Goal 16 that focuses on good governance, and the increasing demand for change (e.g. people demonstrating and speaking up against corruption in Brazil, Turkey, Ukraine, Bulgaria, Moldova, Malaysia, etc.), opportunities for impact are on the rise.

For both strategies, the secretariat developed a five-year implementation plan outlining how it will contribute to the strategic aims. It is for the continued and deepened implementation of this five year plan and for the specific role of the secretariat within the TI movement that PPA support is used. The PPA logframe reflects a few of the key strategic roles of the secretariat, such as global influencing (outcome 1, output 3), support to chapters in undertaking national level work (outcome 1, output 4) and development of evidence and recommendations on anti-corruption policy and practice (output 1). Output 2 reflects the increased focus on people engagement in the TI movement. It is important to note that, although the PPA does not necessarily directly fund changes at the country level mentioned in the report, it has been instrumental in achieving these changes. Indeed, it has allowed the secretariat to fulfil its roles, such as providing technical assistance to chapters and supporting them in developing policy advice based on existing standards. The PPA has provided the backbone that enables TI to be present in over 100 countries through its network of chapters, and to work towards change as an international coalition. The intervention logic of the PPA is based on the assumption that improved anti-corruption understanding, policy and practice by public, non-state actors and citizens all over the world (Outcome) contributes to a reduction in corruption at all levels and across all sectors of society (Impact). The four result areas are consequently interconnected. A better understanding of corruption and how it manifests itself enables citizens to be better informed when demanding accountability. Equally, information about corruption will allow TI to undertake evidence-based advocacy aiming to improve policy and practice of public and other institutions. While leading governmental and business institutions have the potential to influence the way corruption occurs within societies, public pressure can be used to ensure greater responsiveness by these institutions. Meanwhile, laws and their effective enforcement can provide the framework for operations and value-based leadership can help shape behaviours. Ultimately, working better together as a movement will enable us to become better at diagnosing corruption and will allow the various constituents of the movement to learn from each other’s interventions in citizen mobilisation, advocacy, and coalition building.

Highlights of achievements
In year 5, we recorded many new changes in policy and practice, both at global and national levels. TI’s language on governance and corruption was included in the “2030 Agenda for Sustainable Development”, which outlines the SDGs. We continued to target the G20, and influenced their new principles on public procurement and on open data that were adopted in 2015. Beyond that, we have been monitoring how G20 countries have implemented the principles on beneficial ownership transparency developed in 2014. We also made progress at the national and local level on beneficial ownership transparency (e.g. in the state of Sao Paulo in Brazil, as well as in Norway), a core issue of our Unmask the Corrupt campaign, which strives to end corporate secrecy and prevent the corrupt form hiding their assets. More broadly, the campaign has made considerable progress, with more than 125,000 people voting on the worst cases of corruption, and increased our visibility (238,000 people visited the dedicated website). Advocacy on these cases will start in 2016. In parallel, our constituency on social media further expanded; for example, our Facebook follower base went up by 30%. Our publications this year included the Corruption Perceptions Index (published in January 2016), a first regional iteration of the Global Corruption Barometer (to be followed in 2016 by other regional reports and a global one), but also a large number of smaller, but highly advocacy-focused publications, such as the “Give Back the Game” recommendations on the FIFA case. This is part of our efforts to link research and advocacy more closely. More than 4,000 citizens around the world brought forward corruption-related grievances, to which TI chapters helped find a solution. TI’s impact on people’s lives is reflected in the stories that we collect from these cases and publish in increasingly varied formats (photo, video and text). In terms of capacity development, the main achievement related to chapters’ leadership of global thematic networks, especially TI UK with its pharmaceutical and healthcare programme and TI Australia on the mining sector.

One of the major achievements of the five years of PPA is the progressive integration of people engagement and campaigning into our approach and practices. The impact that the new Unmask the Corrupt campaign has already had illustrates this change. We also accelerated our engagement with citizens through technology and social media. Increasingly, TI chapters combine “offline” hotlines with online reporting and mapping platforms. In addition, our evidence-based advocacy has led to many changes in policy and practices, both globally and at the local level, as shown in our annual reports on outcomes. We improved both the quantity and quality of evidence over the years. The Transparency in Corporate Reporting publications, for instance, have enabled us to engage the biggest multinationals, push them to enhance their reporting practices and scale up our work on business integrity. The Corruption Perceptions Index, coupled with our increased focus on social media, was critical to boost our visibility, with our website now attracting more than 3.5 million visitors a year. The Global Corruption Barometer gave space for people’s views in our research, and has allowed us to better understand what citizens think about corruption. We had some major advocacy wins in the last few years, showing that our recommendations can have significant impact. For example, the adoption of the G20 principles on beneficial ownership transparency in 2014 and the agreement on the Sustainable Development Goals (especially Goal 16) owe to the TI secretariat’s strong involvement and contribution, alongside other partners. Goal 16 is a crucial milestone for us, since it gives us and others a clear framework and mandate, and recognises that addressing corruption is essential to achieve development goals. By the end of the PPA, the TI movement is also significantly stronger. We have a formal presence in 114 countries, and chapters are stronger as an average (see section B on financial capacity). Our capacity development approach has therefore borne fruits, shifting to more horizontal learning and more targeted activities (e.g. on leadership, risk management or advocacy).

## B: PERFORMANCE AND CONCLUSIONS (6 pages maximum)

Overall Outcome Assessment

The programme was already on track last year, with only one outcome indicator that had not been achieved. In Year 5 all targets have been met, reflecting TI’s increasing impact and confirming the relevance of these areas of work as we embark into a new strategic cycle.

Indicator 1.1: TI contributed to 52 changes in policy and practice[1] (against a target of 50), including:
[1] Note that because our data collection cycles on impact are bi-yearly, the figure does not include the most recent data (January-March 2016).
- The adoption by the G20 of a set of principles on public procurement and on open data. Both processes have been influenced by the secretariat’s advocacy efforts.
- In Brazil, new laws were adopted in Sao Paulo requiring beneficial ownership transparency in real estate, following pressure from Transparency International.
- TI Macedonia contributed to the adoption of a whistleblower protection law, a first in the country. The chapter had been advocating for this for the past two years, with the help of the TI secretariat, e.g. through our global principles for whistleblower protection.
- The Palestinian Authority Medical Referrals department in Gaza adopted the recommendations that were outlined by our chapter in its report on corruption in medical referrals.

Indicator 1.2: 26 TI secretariat recommendations (against a target of 25) were adopted, including the following:
The G20 Open Data Principles were adopted with significant shaping from TI at the third meeting of the G20 Anti-Corruption Working Group in Paris in October. TI suggested amendments directly into the draft versions that were shared with us over the course of the year by the Mexican government, the G20 government lead on the issue. We also issued a position paper targeting all G20 members, which chapters shared with their G20 Anti-Corruption Working Group contacts.
TI’s language on governance and corruption was included in the post-2015 outcome document “Transforming our World: The 2030 Agenda for Sustainable Development”. In particular, goal 16 fits squarely with TI’s sustained positioning on this issue, with two specific targets on reducing corruption and bribery in all their forms and on developing effective, accountable and transparent institutions at all levels. It also reflects TI’s asks on data (par. 74.g and par. 76).

Indicator 1.3: The number of unique visitors on our website increased by 10%[2], and the target was met. This enhanced visibility partly comes from the momentum gained by the Unmask the Corrupt campaign, which has a dedicated website that attracted more than 238,000 visitors during year 5. Work was undertaken to make the TI website responsive for visitors on mobile devices. The homepage and a number of key landing pages and templates were redesigned and developed. This has resulted in a positive effect on our visitors: 73% increase in mobile users; mobile bounce rate[3] down from 63% to 37%; more visitors to the homepage are now opening the key landing pages we developed. We continue to test and optimise the design. The indicator provides a useful reference as to how many people are visiting the website. Looking forward though, the issue of engagement (i.e. visitors taking a certain action, such as subscribing, engaging in conversation with TI or donating) will become increasingly important, which implies a different approach to trying to drive up the number of visitors.
[2] Total unique visitors in reporting period were 3,521,575, including visitors on our main website and those on our Unmask the Corrupt campaign website.
[3] The bounce rate is the percentage of visitors who enter the site and then leave ("bounce") rather than continuing on to view other pages within the same site.

Indicator 1.4: 47% of the cases taken on by our chapters were solved successfully[4] since the new cases database was started in 2011. This figure is much higher than the target (30%), partly due to a change in the way it is calculated[5], but also because ALACs seem to have performed particularly well this year. Indeed, if we compare our performance using the new methodology, the percentage as of the end of year 4 would have stood at 43%, while we now reach 47%. This indicates better performance in year 5 than previously. TI’s impact on people’s lives is reflected in the human interest stories that we collect from the many cases of corruption reported to our chapters. For example, our Guatemalan chapter has put pressure on the authorities to investigate a case of kickbacks in the procurement of medical equipment by the social security. 27 people died after the contract was awarded to the company that paid the kickbacks instead of the best company. 17 people are now awaiting trial.
[4] I.e. deemed “successful” or “partially successful” by the chapter that took it on, according to our online database.
[5] The percentage is now the ratio between solved cases and closed cases. Before that, the ratio was between solved cases and the total number of cases opened by the chapter. The new methodology is easier to handle for chapters, because there is no more distinction between „initial contacts“ (complaints that were not related to corruption or that the chapter did not take on) and „cases“ (where substantial legal advice or support was given to the person).

Changes to capacities in relation to results [1]
Strategic planning
Strategic planning processes can rarely be funded through projects. Therefore the PPA was instrumental in helping us shape our goals for 2020 and develop our new strategy “Together Against Corruption”[6]. Thanks to PPA support we were able to reach an unprecedented number of stakeholders who provided input into our strategy development process. This strategy builds on our previous priorities, but brings more focus and embraces changes in context, e.g. citizens’ higher awareness of corruption and increasing willingness to fight against it.
[6] See Evidence table 1.

Capacity to engage people
In line with our strategic shift towards a better balanced mix of campaigning and evidence-based advocacy, the PPA has also increased our capacity to engage people. For example, the Unmask the Corrupt campaign and the work on grand corruption cases were new approaches for TI, and PPA funds were used to develop and pilot them. Having more than 125,000 people vote on the worst cases of corruption and reaching over 20 million people over social media through our campaign would not have been possible a few years ago, and laid the ground for our action to bring the corrupt to justice. Figures in Output 3 also show that we have been able to connect with citizens, e.g. through social media, much more than before, primarily thanks to core resources such as the PPA. The interactive map that we have developed for the launch of the Corruption Perceptions Index (CPI) is another good example: for the 2015 edition, the map was widely used and viewed by more than 2 million people in just a week.
Engaging people also means supporting victims and witnesses of corruption and helping them find a solution to their grievances. It has been the purpose of our Advocacy and Legal Advices Centres (ALACs) all through the PPA lifetime. Their number grew from 62 in 47 countries in April 2011 to 90 in 55 countries in May 2016.

Capacity to influence
Another area to which the PPA significantly contributed is global advocacy. Being able to influence global policies and debates has always been a strength of TI, but we clearly became better in this regard. Our regular presence at the Open Government Partnership, G20 and UNCAC process, as well as our involvement in the SDG process since its inception, are only a few instances. Concrete changes that we contributed to include:
- Adoption of Goal 16 on good governance in the Sustainable Development Goals
- Adoption of G20 principles on beneficial ownership transparency, a critical issue for TI
- Adoption by the EU of a law requiring all companies in the extractive sector listed on EU exchanges to report their payments by country and project
Meanwhile we engaged closely with DFID and wider HMG in the run up to the Anti-Corruption Summit called for by Prime Minister Cameron. Due to the significance of this summit and TI’s recognition of the important role the UK plays in the anti-corruption debate, the TI secretariat decided to invest PPA and other unrestricted funds in a full-time policy position, based in London, to engage with the UK government on the summit and beyond.

Financial capacity
The income of the TI secretariat rose sharply from 15 million in 2010 to 27 million in 2015, although it has stabilised in recent years. The PPA enabled us to find more sources of funding, as well as to invest in donor segments that we did not previously focus on at the same scale, such as foundations and fundraising from the public. There remains however a large potential to diversify our funding, and we developed a new investment plan in 2016 to harness this potential. As shown in the mid-term review of our strategy 2015, the financial capacity of TI chapters has also grown. In 2014, 51% of the chapters had more than 11 employees (30% in 2010) and 51% had a yearly income of 250,000 EUR or more (26% in 2010). Income growth has however been uneven across the movement and investing to ensure that more chapters benefit from our growth potential will be crucial.

Capacity to monitor and learn from our work
When the PPA started, there was no formal M&E function at the TI secretariat. Thanks to core resources such as the PPA, we now have a dedicated unit in place. We have developed an impact monitoring approach – recognised by the INGO independent review panel as good practice for other organisations – that is steered towards outcomes and learning. It aims to build a more robust body of evidence regarding what works in the fight against corruption, and why and how it works. This shift in our thinking is illustrated by the set of change markers we have developed early in 2016 to monitor our progress towards our strategic goals. They outline what specific changes the TI secretariat wants to achieve year-by-year until 2020. These allow us to clarify the progression towards our long-term ambitions, and thus help focus on how to deliver the impact that we want to deliver in the next five years. They also give us the flexibility to try new approaches, learn and adapt, allowing us to become a learning organisation and constantly improve our relevance and effectiveness.

Chapters' leadership capacity
The TI secretariat has supported the emergence of chapters’ global leadership (in addition to their mandate to fight corruption at the national level). One of the main approaches was to promote the emergence of thematic initiatives with one chapter leading and coordinating the activities, and other chapters participating. For example, TI UK leads an initiative on defence and security and another one on the pharmaceutical and health sectors, TI Kenya started a network on humanitarian aid transparency, etc. This has increased the movement’s capacity to have impact and respond to the complexity of corruption by making the most out of our diverse expertise.

Strengthened organisational standards, efficiency and accountability
The PPA has contributed to improvements in financial management, and therefore increased efficiency. This includes better financial systems, the development of a tool to assess chapters’ financial situation, and the reorganisation of the financial function to ensure a better oversight and monitoring of expenditure. New organisation-wide policies were also introduced, such as the Gender and Diversity policy. As presented below in this report, we also made progress in terms of transparency (disclosing more information), governance (e.g. the new code of ethical advocacy), and value for money.

Capacity to understand, manage and mitigate risks
Improvements in risk management are described under the Risk section. The work of our legal unit, rapid response unit (both created during the lifetime of the PPA) and the SAFE programme (Safeguarding Anticorruption Fighters Efforts) has been crucial to increase our performance in this area. They have also supported chapters more and more, which is essential as many of them are operating in increasingly difficult environments. However, it is clear that we have to go further in this direction as we start our new strategic cycle, where campaigning and individual cases of corruption (including grand corruption) are much more prominent.

Sustainability of capacity changes
Overall, most of the enhanced capacities described above will be sustained, because they relate to strategic areas of work, because they are essential to our efficiency and effectiveness, and/ or because the change does not require large investments to be maintained. However, the PPA has been a critical source of funding for us, and its end will have serious consequences on our level of ambition and capacity to further innovate and improve, unless it is replaced by a similar mechanism. Below are more explanations on each element.Strategic planning
Our new strategic cycle runs until 2020. The strategy will therefore be the main guide for the TI movement in the next five years. More importantly, it has initiated a long-term and lasting shift in our approach to fighting corruption.

Capacity to engage people
This priority is ingrained in our strategy and therefore our fundraising efforts and our core investments will continue to focus on this, among other issues. The level of our resources (especially unrestricted funding) will however have an influence over the strength of our achievements in this field and our capacity to innovate. The sustainability of the ALACs at the national level has been an issue in recent years, and the secretariat has a clear role in supporting chapters to find solutions, e.g. through raising funds from the public. There is still a potential to scale up this approach and increase its impact significantly, and unrestricted funding will play a fundamental role in doing so. The end of the PPA would therefore have serious implications on our capacity to maintain this level of support to victims and witnesses of corruption.

Capacity to influence
Global advocacy remains one of our core roles as a secretariat, and is embedded in our 2016-2020 implementation plan. We will continue to influence major global institutions such as the G20, the World Bank, the EU and regional organisations. Since 2015 this area of work is also supported by the Omidyar network – and we hope to sustain this partnership in the longer term – and to a certain extent by a EuropeAid Action Grant, aimed at strengthening the movement capacity to influence regional/ global development and practice. But a drop in unrestricted income will undoubtedly negatively impact TI’s constructive engagement with policy makers, businesses, and others, and our support in their efforts to improve on transparency, integrity and accountability.

Financial capacity
We now have a stable income and have used the increase of resources since 2010 to further invest in fundraising. As mentioned above, we developed a long-term strategy to diversify our funding, which lays stress on how we will invest to ensure the sustainability of the TI secretariat and the movement as a whole. It will be a high-level reference for making decisions related to fundraising in the coming years. Despite the increase in income we note the pressure on unrestricted funding, which are essential for the TI secretariat to be able to continue its work.

Capacity to monitor and learn from our work
The impact development approach is embedded in the M&E system that we are using to check our progress towards our 2020 goals. The process is therefore now in place but needs staff to manage it, which we consider as a priority, along with resources to gradually roll out this approach to the TI movement by providing training and support to chapters and establishing more effective ways of capturing and analysing data through an online impact log. We will also refine the approach as needed during the implementation.

Chapters' leadership capacity
Chapter-led global initiatives are a new way of working that was already piloted through TI UK’s Defence and Security programme. The approach is now recognised within the TI movement, and is integrated into TI’s 2020 strategy. The strategic shift will therefore likely be long lasting. Financial sustainability will vary depending on the case. Some of the initiatives, e.g. on defence and security and on mining, have already secured significant funding to run their activities. The PPA, however, has been instrumental in enabling the secretariat to support the incubation and the maturation of the networks.

Strengthened organisational standards, efficiency and accountability
These changes relate mostly to systems and policies that are now in place and will stay. However, unrestricted funds, particularly the PPA, have been indispensable to invest in human resources to manage our finances and our governance structure. The latter point especially is very difficult to fund through projects.

Capacity to understand, manage and mitigate risks
The risk management structure and tools will continue to help us in our work over the long term. What is crucial is to be able to invest in legal staff, support to our chapters on safety issues and civil society space more broadly. Although we will strive to raise funds for this through projects, unrestricted funding will be important to ensure that we can adapt to changing environments and that our movement is not at risk.

Funding of partnerships
Transparency International is a network of more than 110 national chapters. These are independent anti-corruption organisations and therefore have their own funding sources. However the primary role of the secretariat is to support these chapters and develop their capacity; therefore the level of unrestricted funding of the secretariat has implications on the support it can give to chapters and its contribution to building a strong TI movement.

Again, the fundraising investment plan referred to above under “Financial capacity” looks at ways of diversifying our funding and lays more particular stress on ensuring the sustainability of the movement as a whole. The goal of these investments is not only to increase the secretariat’s income, but also to increase the chapters’ financial sustainability. This plan will probably have most impact in the second part of our strategic cycle (2018-2020).

Ultimately it is clear that fighting corruption can only be successful if different stakeholders work together through coalitions and partnerships. A reduction in unrestricted funding will have immediate impact on our ability to work with partners in business (such as through the B20), multilateral bodies (such as on the SDGs, Global Compact and OECD) and governments, including DFID and wider HMG.

Learning
In the anti-corruption field, one of the most prominent changes in the last few years has been people’s increased awareness of corruption, which often resulted in outrage at the various scandals that broke out (Petrobras, LuxLeaks, Swiss Leaks, FIFA, Panama Papers, etc.) and massive demonstrations. Corruption was becoming less of a taboo, although the corrupt still often used their position and power to avoid sanctions. Building on the learning that our issue is no longer a taboo topic, our 2016-2020 strategy now more clearly includes both the need for prevention mechanisms and the need to advocate for prosecutions and fight impunity. Speaking with a bolder voice entails risks, but brings immense opportunities to prevent the corrupt from escaping justice. Having a clear campaigning approach with specific changes to work towards is key to achieve this goal. We have become better at that since the start of Unmask the Corrupt, which seeks to address grand corruption and fight impunity, but the process will continue as our new strategy unfolds. The fact that the strategy describes much more concretely how and why we will engage people and campaign is essential. As civil society space is reducing in many countries, an important implication of this shift will be to reinforce our mechanisms to protect anti-corruption activists and ensure their safety.

Our presence around the world has strengthened and we are now active in over 110 countries. The combination of global and local reach certainly remains one of the core assets of Transparency International. However, in order to ensure that we are present is strategic countries such as the BRICs, we will need to find new approaches to partnerships that could cater for cases where the traditional national chapter model is not appropriate. This could be delocalised offices (only where it is really necessary), partnerships with local networks rather than a single organisation, etc. This is what we are currently exploring in Brazil. In any case this extra flexibility in our model will not undermine the decentralised character of our network, which is essential.

Internally, the challenge of funding diversification remains, as mentioned above. Clearly, we could have invested a larger part of our budget into fundraising from new donor segments (such as individual donors or foundations) in order to sustain our income in the long term. We have started doing that in the last couple of years and have prepared a strategy for future investments in all donor segments, with a view to build a stronger TI movement.

Finally, the new strategy and our allocation of resources reflect the fact that we want to target our efforts much more, in other words do less but in a better way. This was one of the main lessons learned from the mid-term review of our 2011-2015 Implementation Plan, and the organisational change process that TI is currently conducting is part of this broader framework.

Output Score and Description
A+ – Outputs moderately exceeded expectation

## C: DETAILED OUTPUT SCORING (1-2 pages for the table and 1 for the narrative).

Output Title	To develop evidence on corruption issues
Output number per LF		1	Output Score	A++
Risk: [please select only one per output, using the new DFID risk definitions]		Minor	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number and description of TI-S research publications	10	17
Number and description of TI National Chapter research publications supported by TI-S	40	52

Key Points - Summary of progress in Year 5

TI has expanded its research and policy work, maintaining but also going beyond global flagship publications and regional summary reports to increasingly focus on more targeted outputs for advocacy purposes. This shift strengthens the link between our research and our advocacy, and ultimately impact. In addition, TI is also taking on new issues (anti-money laundering, tax, lobbying); policy papers, overview assessments and other reports, which account for a significant number of publications in 2015, are often a starting point to build evidence for our advocacy in these areas. Our publications include a large number of smaller, but highly advocacy-focused publications, such as the “Just for Show” report[7] – which assesses how the G20 principles on beneficial ownership transparency have been implemented so far – and the “Give Back the Game” recommendations on the FIFA case. Of course, we have maintained our flagship products such as the Corruption Perceptions Index, which was published in January 2016. A Global Corruption Barometer for the Middle East and North Africa[8] was produced, and more regional reports, as well as a global one, are planned for 2016. The Barometer disaggregates data by gender, although we have not yet done in-depth analyses of such data.
[7] See Evidence table 4.
[8] See Evidence table 5.

The over-achievement on indicator 2 is due to a larger number of chapters publishing their own research with the secretariat’s support than expected. For example, some chapters decided to produce reports on focus group discussions on citizens reporting corruption, as part of the Anticorrp research project, even though that was not required in the project plan.

Many of our advocacy products (which rely heavily on robust evidence being developed and made widely available) have been instrumental in moving the fight against corruption forward. Our “Just for Show” report on beneficial ownership transparency commitments by the G20 stimulated policy development in a number of countries, and our African edition of our Global Corruption Barometer (published in 2016) put the issue of tackling bribery on the public and government agenda in many African countries. Therefore, evidence-based advocacy remains one of the main defining features of TI’s overall approach and one of our key contributions to fighting corruption.

Finally, we published a topic guide on the linkages between gender and corruption[9], which provides a compilation of the most up-to-date and relevant studies and resources on the topic. It looks into questions such as how women are affected by corruption, their attitude towards the issue, and gendered approaches to anti-corruption. The guide is targeted at our national chapters, anti-corruption and development practitioners. It was published on Women’s day, and disseminated through our internal newsletters to the TI movement and the (external) subscribers to the TI Helpdesk mailing list.
[9] See Evidence table 6.

Summary of responses to issues raised in the previous Annual Review (where relevant)

No issues were raised.

Output Title	To support citizens to address corruption and promote integrity
Output number per LF		2	Output Score	A
Risk: [please select only one per output, using the new DFID risk definitions]		Minor	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of corruption grievances reported to ALACs	3600	4662 / Male: 2,157 (46%) / Female: 1,019 (22%) / Anonym or unknown: 1,486 (32%) / Percentage of female citizens among people whose gender is known: 32%
Number of case studies published of people successfully resisting corruption	40	26

Key Points - Summary of progress in Year 5

Supporting victims and witnesses of corruption to find a solution to their grievances remains a priority in TI’s new strategy. Chapters around the world continue to operate ALACs, which allow every citizen to report corruption and seek assistance. ALACs also use this information to advocate for better policies and practices. The number of corruption reports is stable compared with last year, significantly above target. The secretariat has focused a lot of its efforts on improving the data collected by chapters through this work, both in qualitative and in quantitative terms, which allows for better analyses and makes it more useful for research, outreach and advocacy. For example, we shared 10 data facts for 2015 with chapters to increase their understanding of data and visualisation opportunities. We also reviewed and amended our approaches to data analysis in order to unify them within the TI movement. To improve data quality, we updated the database and trained chapters. 12 webinars were organised, with 100 people participating. Trainings focused on improving the quality of the database use and data analyses, present new features, and, for chapters or staff new to the tool, give basic introductions on how to enter data. As a result of the secretariat’s support, chapters have increasingly used the database: in 2015, 45 chapters entered data, and 17,550 citizen complaints[10] were entered into the online database[11], for an aggregated total of 52,521 entries. Data is also much more meaningful and comprehensive than before. In particular, we halved the number of “unknown” data entries since the database was updated in August 2015.
[10] These include complaints that are not related to corruption. Indicator 2.1 only focuses on cases related to corruption.
[11] These include complaints that are not related to corruption. Some of the complaints were entered retroactively (i.e. the client had made the complaint before 2015).

We continued to use stories to evidence our impact on people’s lives and increase our reach and engagement capacity. With a view to make these stories more appealing, we have been shifting our approach to a more visual format (photos, videos) to make the most of the emotional content and to complement more traditional text stories. Most importantly, it gives people an opportunity to tell their story in their own words as opposed to TI reporting on their behalf. With this in mind, we developed a new template on our website for photo-led stories, which was used to present the winners of our photo competition[12]. In terms of video stories, we produced a multi-country documentary on our work in the Asia-Pacific region. While this approach presents new challenges in terms of budget, required skills and time (e.g. working with film crews across countries) – which is why we did not reach the quantitative target – the end product is far more powerful than simple text and can be re-purposed in many ways. One of the videos alone was viewed more than 60,000 times on Facebook. More efforts were made to promote the stories to a wider audience using a variety of distribution channels (such as social media). Two stories have been cross-posted and promoted by the ONE campaign and further collaboration is planned for 2016.
[12] See Evidence table 7.

Summary of responses to issues raised in the previous Annual Review (where relevant)

No issues were raised.

Output Title	To reach out to and influence external stakeholders
Output number per LF		3	Output Score	A++
Risk: [please select only one per output, using the new DFID risk definitions]		Minor	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of Facebook followers	10% increase	30.5% increase / i.e. 289,965, including: / (Gender) / 29% women / (Country of origin) / 14% from Bangladesh / 13% from Egypt / 8% from Tunisia / 6% from Indonesia / 4% from the United States
Number and description of TI documents with recommendations on Anti-Corruption practise and policy annually	30	44

Key Points - Summary of progress in Year 5

We had a 30.5% increase in Facebook followers since 1 April 2015 (289,965 as of 31 March 2016). 29% of them are women. 42% of Facebook users whom our posts reach are women, and 36% of users who engage with our posts are women, showing that while we have fewer female followers, they engage with our content at a higher rate. Several factors explain our over-achievement. Firstly, we kept up with the way Facebook changes the algorithm it uses to choose which content to give greater exposure and which content to ignore. Note that we had a lower growth among women. This reflects not only Facebook’s lower acceptance rate with women globally but also the fact that we have a higher proportion of users from areas where men predominate on Facebook. Secondly, we boosted[13] posts targeted to new audiences in order to increase their visibility and gain new followers. More broadly, our visibility highly benefited from the momentum that our Unmask the Corrupt campaign gained. It encouraged people to nominate and vote on symbolic cases of grand corruption, mobilised thousands of people around the world, while encouraging discussion and sharing of our posts. 125,000 people voted for the cases that they thought should be dealt with as a priority.
[13] I.e. we paid for increased visibility of selected posts.

In order to increase engagement and reach of our posts to attract new followers, we focused on creating compelling content and stories with strong visuals. Bright visuals with short headline text and direct questions proved to attract most interest. Mentioning relevant, well known figures also helped to increase reach and attention from new audiences. Around International Women’s Day we focused our communication on the issue of sexual extortion, which is a type of corruption that especially affects women and hinders the drive toward achieving gender parity – this year’s International Women’s Day theme. We featured the topic on our Facebook page, reaching 97,000 people and engaging more than 13,000 people[14].
[14] “Reach“ means that the post appeared in the person’s feed, while “engagement” refers to clicking on, liking, commenting on or sharing the post.

On the advocacy side (indicator 3.2), we also reached our target, with many current events fitting well with the areas where TI had and was developing policy recommendations. This particularly was true of sports and corruption, for example with our global corruption report released on this topic in February 2016[15]. As news stories provided an opening for policy recommendations, the report was already being leveraged ahead of its release date[16]. Another area was the incentives system for integrity in banks and the settlements that governments were striking with financial institutions found caught in wrong doing. TI issued two policy papers on both topics[17]. Both were timely pieces that were able to tap into current events and then to be used for continued work on these issues, including submissions to consultations in Canada and England on proposed regulatory changes for banks. TI used key moments such as G20 events or the adoption of the SDGs by the UN in September 2015 to develop policy recommendations and inputs to help shape the policy debates. The publication of our "Just For Show" report, which looks at how G20 governments have delivered on their anti-corruption commitments, for example, was released ahead of the G20 summit to put pressure to actually implement the Beneficial Ownership Transparency Principles adopted by the G20 in 2014[18]. This shows how TI has increasingly linked its advocacy, research and campaigning initiatives (Unmask the Corrupt focuses particularly on ending corporate secrecy and beneficial ownership). Another example is the blog post on transparent development money, released before the SDGs were adopted[19].
[15] See Evidence table 8.
[16] See http://onforb.es/22zw9gQ, http://reut.rs/22zwzUm and http://bit.ly/1P8mDtl.
[17] See Evidence table 9 and 10.
[18] See Evidence table 4.
[19] See evidence table 2.

Summary of responses to issues raised in the previous Annual Review (where relevant)
No issues were raised.

Output Title	To strengthen the capacity of the TI movement
Output number per LF		4	Output Score	A
Risk: [please select only one per output, using the new DFID risk definitions]		Minor	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of capacity development activities implemented by TI Chapters with Secretariat support	36	40
Number of trainings organised by TI-S for TI National Chapters	30	28

Key Points - Summary of progress in Year 5

We performed well on this output, although the second indicator is slightly under target. This is partly explained by the fact that our capacity development efforts have shifted from a training-focused approach to a broader learning approach, which includes chapter-to-chapter learning. While continuing some classroom training facilitated by the secretariat, we increasingly used horizontal learning opportunities, and longer-term coaching and mentoring support.

The secretariat’s support to capacity building activities implemented by TI chapters directly responded to concrete needs identified by chapters themselves. Our consultative approach ensured that they had ownership of the process. They have forged stronger connections with one another, which increases learning opportunities, and lays the ground for future actions.
The chapters that engage in horizontal exchanges (be they peer learning or direct skills transfers) can now do so more efficiently because of the deeper integration of the global TI movement. The groundwork done in previous years, encouraging and supporting chapters to develop specialised skills adapted to local contexts, puts them today in a position to transfer knowledge with more confidence. Increasing global awareness amongst chapters of the diversity of the TI movement is an essential added value of large-scale, cross regional events and programmes. Meanwhile we recognise that the TI movement needs to lead by example on matters relating to ethics and financial transparency and we are aware that more can be done in this field. The resignation of the Chair of our Chilean chapter following the Panama Papers leak was a stark reminder of the need to have the right mechanisms in place to ensure our movement lives up to what it expects from others. We have improved our governance system by fine-tuning the accreditation review questionnaire and incorporating anti-corruption capacity as a compliance requirement. In addition, the TI secretariat now delivers a yearly report to the Audit Committee of the Board, with an analysis of financial situations deserving specific attention within the TI movement. We plan to do more work on developing organisational and financial management standards that we will promote throughout the movement. This set of “best practices” will complement the accreditation criteria, which serve as the minimum requirements for chapters.

Examples of topics for capacity development activities, supported by funds, expertise and / or coordination from the secretariat, are listed below.

Governance and management
Several chapters in the Asia Pacific region invested in management best practices to keep professionalising their work. As a result, they now have a more strategic approach to ensuring value for money in their projects, with more agile financial management and better human resource systems in place. Security and safety was a focus for our chapter in Cambodia, which reviewed its security management and information management policies and implemented a thorough threats assessment to warrant high levels of staff personal safety. The chapter has now improved its risk management systems and security protocols.
Evidence-based advocacy and communication
In Brazil, the TI secretariat helped our local contact establish a partnership with a professional communications company. As a result, the organisation now has a clear communication strategy, and has markedly improved its communications and public relations expertise. Several chapters participated in peer learning and knowledge exchange to further scale up their work on individual cases of corruption.
Leadership skills
The secretariat continued supporting chapters’ leadership of global thematic networks. For example, TI UK was able to increase the sustainability of the pharmaceutical and healthcare programme that they are leading thanks to the TI secretariat’s support on fundraising.
TI Australia made an important step in developing their leadership on transparency in the mining sector and by the same token, in becoming a stronger organisation. This initiative is now funded for four years and will involve about 20 chapters.

Summary of responses to issues raised in the previous Annual Review (where relevant)
No issues were raised.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (4 pages maximum)

Key cost drivers (maximum of 5 key cost drivers per key cost)

Key costs / List the key costs of the organisation e.g. staff, transport. It would also be helpful to state whether these are fixed or variable costs.	% total budget (FY15/16) / NB this is not expected to add up to 100% as we have asked for ‘key costs’ rather than all costs.	Cost drivers / (factors that influence key costs e.g. project location, inflation. State whether there has been any change in them that has pushed up costs and whether any identified trigger points have been reached.)	Actions to manage key costs / Summarise what the organisation has done to manage the cost drivers (where this has been possible) and whether this was successful or not. DFID accepts that not all will be possible to manage, so if not please state this.
Personnel	37%	Personnel costs have remained stable at around 38.5% of total expenditure during the last 4 years. Key drivers are location (although Berlin has a relatively lower cost of living compared to other major European cities) and the skills required, which generally entail higher remunerations.	A number of key measures have been introduced and/ or improved (new grading system, standard job descriptions, loyalty payment, performance payments, development within the grades, etc.) in order to motivate and retain staff. Results have been mixed, and additional work is still needed; a complete overhaul of the remuneration system is planned for the second half of 2016. Furthermore, we have sought to include staff costs under new project funding as much as possible.
Chapters/ partners support (grants)	41%	One of the largest components of the TI secretariat expenditure is financial support to our partners to implement projects across the world (often as part of thematic or regional programmes led by the TI secretariat). Cost drivers vary a lot depending on the country and donor requirements.	Significant investment was made in staff working on project accounting in the last five years, which led to major improvements in project budgeting, monitoring and reporting processes and practices (e.g. more timely accurate and reliable financial reports). Higher staff costs have been balanced out by these improvements. Meanwhile, to ensure independence of our chapters, we have decided to further invest in strengthening the fundraising capacity of our chapters directly.
Honoraria	5.6%	Expenditure has decreased to some extent in the last five years, partly as a consequence of more work being done in-house. A key driver is the quality of consultants hired, and the application of a robust procurement system.	The procurement process has been improved and streamlined, and controls have increased to ensure that rules are applied across the board. A paperless online system unfortunately has not been implemented yet as initially planned, but is expected to be operational by the end of 2016.
Travel	5.6%	Flights are the largest component of travel costs. These have been decreasing in the last few years, with the use of new technologies (e.g. videoconference) being a key contributor.	Following numerous attempts to reduce both travel costs and the administrative burden of processing the reimbursement of travel costs to staff, a new centralised system for bookings and reimbursements was successfully set up in 2015, which brought down the overall costs significantly.

Notes: Overheads are included in the above categories and are not to be included in the aggregate. Figures refer to our own financial year, i.e. January to December 2015.

VfM performance

	How have you assessed VfM in this area? What measures have you used? State whether this has been measured as part of the enhanced VfM offer or since the beginning of the programme.	Performance in this area (if possible, compare performance over the life cycle of the programme).
Economy –whether organisation has bought inputs of the appropriate quality at the right price?	The development and application of robust recruitment and procurement processes, as well as detailed travel guidelines, have been key factors for achieving the best VfM. On chapter expenditure, the main tools have been the use of detailed budgets, comprehensive grant agreements, and regular monitoring and reporting. Measures were already in place before the VfM offer was made.	Performance has improved significantly in these areas over the years, with a major boost in 2014 and 2015 through more rigorous internal financial monitoring and controls, as well as the centralisation of the travel cost reimbursement process. For example, flight costs were reduced from €2,404,612 in 2013 to €1,499,247 in 2015 (with a constant overall budget).
Efficiency- how well organisation is converting inputs into outputs? (‘Spending well’)	Through the use of standard project management techniques (e.g. Prince2), projects are implemented efficiently by designing the most appropriate activities. Measuring efficiency has been a challenge given that (a) our outputs are rarely tangible, and (b) there tends to be a delay between the investment and the output. In order to become more effective at capturing the results of our work, TI developed a tailored approach to monitoring impact which is now being implemented.	Regarding chapter expenditure, streamlining the budgeting, contracting, monitoring, control and reporting processes has significantly improved the way the organisation manages partners’ funds. TI has definitely become better at capturing results and at aligning its budget with strategic priorities and commitments.
Effectiveness- how well the outputs produced have had the intended effect/ achieved the outcome? (‘Spending wisely’)	The work that TI mostly does – advocacy – does not easily fit within the classic and to an extent artificial division between inputs, outputs and outcomes. A lot of our investments are directed towards outcomes, and our impact monitoring approach focuses on outcomes. These were measured through indicators, and a lot of emphasis is placed on the submission of evidence, and evidence for our contribution. The new approach lays stress on “change markers”, which can be described as a theory of change for each of our strategic priorities.	Progress has been made in a lot of outcomes, at the level of policy change, but also behaviour change. This includes major progress on the G20 and SDGs front, as well as the increased visibility and citizen engagement that the Unmask the Corrupt campaign has entailed. Having being clear on our outcomes has allowed us to make better assessments on investments in activities and outputs. Concretely for example, our new strategy puts more focus on campaigning as a means to achieve change. In turn, we decided to invest unrestricted resources into such campaigning interventions, for example our Unmask the Corrupt campaign. Also, reflecting on where global power currently lies, we invested in our work at the G20 as opposed to our earlier primary focus on the UNCAC.
If appropriate, please provide details of other ways in which you have assessed VfM that do not sit within the 3 ‘Es’ set out above	A number of key organisational performance indicators are benchmarked every other year against similar organisations in the UK through the Charity Finance Group (CFG) Finance count.	TI’s performance has been positive in a number of aspects, in comparison with other organisations. For example, our finance function is more staff-intensive than for other NGOs, but this is mostly because of the large number of statutory grants that we receive, which require much stricter financial reporting than other sources of funding. In 2014, TI issued more reports to donors than the peer group on average (88 vs. 80), even though its income (and staff numbers) is less than half the peer group’s.

VfM Good practice over the lifetime of the PPA programme

Briefly - what are the top 3 VfM good practices that your organisation has implemented to maximise VfM? (this should cover the lifetime of the PPA)	Please give an example of this good practice being used and the impact it had. If there were any VfM savings please state what they were.
Formalisation of the VfM approach, including a formal policy.	Following that, information on economy, efficiency, effectiveness and equity was requested in the cover note that accompanies submissions to management and was reported in the management meetings minutes. This has been done for various items, for example additional budget requests, for which criteria were put in place to achieve maximum effect with resources used. A case in point is the development of an ‘impact log’, for which alternative providers, costs, and potential outcomes were analysed before a decision was made.
The procurement process (policies, guidelines, procedures, forms, roles and responsibilities, etc.) is regularly updated and enhanced to ensure that best practice is included and issues are rapidly remedied. Enormous efforts have also been made to ensure that the process is used consistently across the organisation.	It is difficult to assess the savings, but we can see that the procurement process is applied more and more consistently: the number of exceptions to the procedure[20] have gone down since 2014.
Integration of VfM into the M&E framework and increased focus on outcomes and impact in our M&E processes.	Our impact monitoring approach will enable us to better assess our impact. We will therefore be in a better position to adapt our approaches and learn what works and what does not, thereby improving our effectiveness and VfM.
[20] Exceptions occur when a contract of less than 5,000 EUR is awarded without resorting to the standard procedure requiring three competitive quotes. Additional sign-offs are required instead of the three quotes.

VfM learning

Given that personnel is a large part of our costs, the TI secretariat is developing effective procedures and policies related to human resources management, which facilitate the retention of valuable skills and experience within the organisation, a vital element to improve value for money. These changes mainly touch upon reassignments and an overhaul of our compensation system.

Quality of financial management during programme

On the UK financial year basis, project spending has been on track as planned year on year since the beginning of the programme. All narrative and financial reporting requirements have been adhered to. Audited financial statements were sent to donors in a timely manner, and we managed to make them available as early as beginning of April in the last three years. Audit requirements have been met in full; annual financial statements have been independently audited by renowned international accounting firms. All audit opinions have been “unmodified” (i.e. unqualified), with no material matters raised in the respective management letters.

Assessment of whether programme represented good Value for Money

a) Reflection of VfM performance over the lifetime of the programme

Our direct support to victims and witnesses of corruption has helped us understand citizens’ concerns and address them more efficiently. We have striven to reduce costs through strong procurement procedures, but also by adapting our approaches when needed (e.g. our capacity development approach, which now relies less on training and more on horizontal learning for more efficiency). We invested much more in our M&E systems (and arguably need to do so even more), which became stronger and contributed significantly to the value for money of TI’s work. We learned from and improved these systems in the last few years, and ultimately developed the impact monitoring approach and the “change markers” that we are now using. This system is outcome-oriented, and therefore enables us to assess and enhance our value for money better than ever. We have also become better at linking our budget with our strategic priorities, which helps linking inputs and outputs/ outcomes. Overall, our achievements at outcome level have been strong, and the changes as well as our contribution to them (e.g. recommendations, chapters drafting or commenting on a law, etc.) have become more and more substantial since the beginning of the PPA. At a strategic level, it is worth mentioning that our thinking has evolved a lot, from research and high-level advocacy, to engaging people, campaigning and scaling up our work on cases of corruption – always with a view to maximise our impact. What we can still do better however is to capture why, in our efforts to achieve impact, we make certain decisions. While we for example think carefully about financial investments, assessing their advantages and drawbacks, we do not always capture which other investments might have led to the same results. This is indeed complex, but something we could have done better.

b) Assessment of progress against enhanced VfM offer

Most of the activities we have committed to have been carried out, including:
- Formalisation of the VfM approach, including a formal policy that defines VfM, principles for implementation, and roles and responsibilities.
- Integration of VfM considerations in the agenda of management group meetings, when a strategic decision has to be taken.
- Training for staff on VfM.
- Revision of the project development process.
- A comprehensive assessment tool of chapters’ finances has been developed. It includes an evaluation of their project reports and overall financial status.
- Stronger focus on learning in weekly staff meetings, though this is not formalised.
- VfM has been integrated into grant agreements with our partners.
- Migration to a new financial system, which has brought major efficiency gains.
- Streamlining of ICT processes – although the economies mentioned in the VfM offer are mostly visible for travel at the moment. Further gains may come in the longer term.
- Analysis of travel and honoraria costs. Staff costs were not benchmarked as planned: we decided to focus on improving human resources management processes instead.
- The risk management framework was revised, although the revisions may not have as much impact on VfM as anticipated.
- The professional development system (development within the grade) was implemented.
- We took part in UK’s Third Sector Financial Management Benchmarking exercise.

For technical reasons (capability of the provider, integration with the new IT infrastructure) the change of procurement system has been delayed to 2016. This does not undermine the strength of our procurement procedures, but we simply have not been able to implement the improvements we expected, because the tool we had initially selected was not suitable. During the fall of 2016, we plan to work on a new purchase and procurement policy, and on the automation of the authorization and purchasing system. The VfM assessments were started but challenges – such as the availability of data to make a thorough assessment – have delayed their finalisation.

Date of last narrative financial report
Date of last audited annual statement

E: RISK (1 page)

Quality of risk management over the life of the programme

As an advocacy organisation, taking risks is an essential part of affecting change. The purpose of strengthening the risk management process is not to make the organisation more risk averse, but rather to make it more capable of identifying, assessing and addressing risks.

The TI secretariat went through major improvements in the area of risk management during the last 5 years – we had no formal process before 2011. A robust process was introduced in 2011, primarily covering institutional risks at the secretariat. While the first couple of years were mainly a learning and development phase for the organisation, by 2015 the process had been enhanced, streamlined and expanded to include risks associated to TI chapters and project partners.

Major changes were made in 2015 in order to better cater to emerging areas of work (e.g. campaigning and working on individual cases of corruption) and to address findings from the mid-term review of the strategy 2015. To encourage greater coherence, the mandate of the Risk Management Committee was revised and expanded to oversee the entirety of the TI secretariat’s risk management infrastructure, which rests on five main integrated pillars:
1. Institutional risks
2. Political and legal risks
3. Personal safety and security of TI staff
4. Media interest and reputation: response to global corruption news, events, and chapter positions
5. National chapters: strengthening risk awareness and capacity at the chapter level, and fostering resilience

The new national chapter pillar aims at strengthening the risk management capacity of the movement, not just the secretariat, and preparing ourselves better for the increased strategic focus on campaigning, grand corruption, etc. The new Chapter Financial Reporting Assessment will help us understand the secretariat’s exposure to risks linked to chapters’ financial situation, and will allow more targeted and valuable capacity development activities.

Given the size of the organisation and the nature of the risks it faces, we believe that the current risk management infrastructure at the secretariat is robust, fit for purpose, and contributes to TI’s achievements and value added. We do however recognise that our new strategic directions, particularly being more bold in speaking out against impunity, require us to invest further in risk prevention and management, for example in our legal infrastructure.

F: COMMERCIAL CONSIDERATIONS (1 page)

Delivery against planned timeframe

As mentioned in the sections relating to outcomes and outputs, the results expected have been achieved, with a few minor exceptions that are explained above. The performance of TI’s PPA has always been assessed as very positive, and activities have been implemented.

Performance of partnership (s)

Our key partners are TI national chapters, whose local reach and expertise have been essential to achieve collective impact. Many changes in policy and practice have come from chapters, supported by the secretariat through the design of anti-corruption tools, capacity development, representation on the global stage, etc. Chapters are independent local organisations, but are bound by a set of standards required for accreditation as a TI chapter. As mentioned under Output 4, we have made improvements to our governance system and internal controls (e.g. revision of accreditation criteria, development of a tool to assess chapters’ financial situation), while maintaining this principle of independence. We will also develop new standards for organisational and financial management to be applied, ultimately, across the TI movement. In order to receive additional insight into Transparency International national chapters’ internal control environment, the Board Finance Committee now requires chapters to provide their
auditors’ management letter in addition to financial statements and audit reports.

 The secretariat complements national work by advocating for global and regional reforms (e.g. SDG on governance). As recommended by the mid-term review of our strategy 2015, we have explored new ways of establishing a presence in a country where the national chapter model is not the most appropriate one. For example, we are looking at opportunities to partner with coalitions or to establish an office when necessary and relevant. More broadly, partnerships are at the core of TI’s fight against corruption. They are crucial for successful advocacy and can make it much more impactful. For example, collaboration with Global Witness and ONE boosted our visibility and reach ahead of the G20 summit, and our work with the OECD has shed light on the enforcement of the convention against foreign bribery. Strategic engagement between TI and DFID has also grown since the beginning of the PPA. The strength of the policy dialogue that emerged from this engagement is illustrated by the joint side event on Corruption and the SDGs during the 2014 UN General Assembly and in the preparation of the 2016 UK Anti-Corruption Summit. We have regularly engaged in the learning partnership, especially on issues such as institutional effectiveness and M&E, thus building strong ties with other PPA agencies and learning from their own work.

Asset monitoring and control

The majority of the organisation assets are liquid funds maintained at reputable banks (AA+) in the form of demand or time deposits. TI has a robust system of internal controls that includes qualified staff, segregation of duties, system access controls, and a delegation of authority. Bank accounts are reconciled regularly, and no funds can be transferred without the intervention of three different staff members (input, authorisation, release). Fixed assets (175,000 EUR) represented less than 2% of the total assets as of the end of 2015. These are tracked systematically through serial numbered asset tags for the purposes of financial accounting, preventive maintenance, and theft deterrence. The inventory is kept current at all times, and a physical inventory count is carried out every year; all fixed assets are also insured. There are no outstanding issues.

G: CONDITIONALITY

Partnership principles assessment
Not relevant to PPA funding.
H: MONITORING & EVALUATION (1 page)

Evidence and evaluation

Over the last 5 years TI has made progress toward being a learning organisation. Our 5-year strategy and implementation plan provide the framework for the secretariat’s work. Our annual planning and quarterly reporting system has allowed us to assess the progress made against our annual implementation plans and to inform learning and accountability reports. Our internal monitoring provides findings that are used to inform strategic decisions and improve programme design and implementation, improve allocation of resources by diverting funding from ineffective to effective interventions and ultimately to build knowledge on what works and what does not work in the fight against corruption. Findings from the internal monitoring are shared in internal summary reports and discussed in staff meetings. Multi-country projects and programmes coordinated by the TI secretariat design monitoring systems that are aligned with the larger goals of the organisation. Increasingly they mainstream the new impact monitoring approach into their work. Regular field visits, regional meetings, monitoring reports and working groups promote learning within the TI movement.

Transparency International regularly conducts learning reviews and independent evaluations to assess the effectiveness of our projects and programmes and to improve our learning and internal accountability processes. For example, in 2014 we conducted a mid-term review to evaluate the secretariat’s contribution to the strategy 2015, drawing on consultations with a large number of external and internal stakeholders. The findings led us to commission an organisational review of internal structures and managerial approaches, processes and ways of working. Insights and lessons from both assessments currently inform an organisational change process at the TI secretariat to ensure our structure and processes are better aligned with our new strategic goals. An overview of evaluations can be found on the website of the TI secretariat.

Monitoring progress throughout the programme

A formal M&E function was established at the TI secretariat in 2011. In 2011-2012, an organisational M&E system was set up, paving the way for the conceptualisation and implementation of a movement-wide approach to M&E and particularly impact assessment. In 2013 we introduced a quarterly review system that allowed us to mainstream data collection in all departments and systematically assess the progress made against our annual implementation plan. Furthermore, we introduced set of performance indicators covering strategic areas such as financial and human resources management and international board governance. A value for money action plan and policy were developed and two value for money assessments began in 2015. In 2014 we introduced a new approach to monitoring impact for anti-corruption work. It consists of two complementary elements: a matrix to support participatory impact-oriented monitoring in projects and programmes, and a limited number of impact assessments that provide in-depth insights on relevant topics and trends identified through the ongoing monitoring. The approach is highly participatory – it requires and actively promotes the involvement of both internal and external stakeholders and constituents.
## I: TRANSPARENCY (1 page)

Assessment of progress against enhanced Transparency offer

As discussed with DFID before, TI realises that it needs to set the highest standards on issues such as transparency, integrity and accountability. Governance within Transparency International includes a conflict of interest policy and codes of conduct for the International Board of Directors, international secretariat and all national chapters. Members of both the international and national chapter boards are required to compile a register of interests. An Ethics Committee led by the International Board of Directors also provides a forum for advice on ethical questions for the TI movement.

Since we submitted our Transparency Offer our Public Information Disclosure Policy is now fully operational and supported by a dedicated (part-time) Information Officer. Information outlined as disclosed in our PPA proposal has been continually kept up-to-date. We have regularly produced and published new accountability reports – for example, in the framework of the INGO Charter – that provide extensive quantitative and qualitative information as well as comparisons over the years and reports on previous commitments. While not listed in our Transparency offer, we also publish on our website decisions by our governance structures, our recruitment policy and procedures, gender and diversity policy, Relocation allowance policy, and purchase and procurement summary guidelines. We have substantially updated and improved our webpage on ethics and complaints to make it more easily accessible (including from our home page) with a view to guide stakeholders through our ethics infrastructure, which we are in the process of updating.

Within this reporting year the TI Board adopted a Code of Ethical Advocacy for our secretariat which promotes and ensures greater accountability of our work when we seek to influence stakeholders. An Advocacy Log was started on 1st May 2016 which provides an overview of meetings between staff members of Transparency International Secretariat and decision-makers from both the public and private sectors. Further new initiatives include
- We updated the Register of Interests of all TI individual members and members of our international board of directors which are all accessible online.
- While we also published our previous strategy online, our new strategy Together against Corruption was made more accessible to the general public through publishing a short video and summary of the document.
- While slightly outside of this reporting year, we published a full list with all grants currently held by the TI Secretariat on our website.
- We continued to publish to IATI and increased our data files

Meanwhile we continued to publish the TI-S Financial Statements in accordance with International Financial Reporting Standards (IFRS), and include comprehensive reports on income and expenditure for each of the projects we run; going beyond the minimal requirements of the standards. We also continued to list all donations over €1,000 and publicly disclose these and continued to post our operating budget, annual implementation plan and external evaluations online. Finally we continued to publish the decisions of our international board of directors online, an initiative we had started in October 2014.

## J: Disability (1 page)

As reported last year, the main way in which we engage with vulnerable populations such as disabled people is through our support to victims and witnesses of corruption. This demand-driven approach is based on the idea that people should have easy and equal access to mechanisms to report corruption. This is why we use various channels to increase accessibility (walk-in centres, hotlines, SMS, online platforms, community meetings). This is a key aspect of our citizen engagement strategy, and is aligned with DFID’s ambition to leave no one behind. Although we have not specifically targeted people with disabilities, many chapters have made efforts to proactively reach out to vulnerable populations in order to give them a voice and collect corruption-related grievances. In terms of data, chapters may enter information on vulnerability in the database, but we have not yet made a push in this direction: our priority in year 5 was to enhance the quantity and quality of data collected overall, in order to ensure that meaningful analyses could be made. The diversity of chapters involved and of contexts in which we are working remain challenges in terms of disaggregating data and ensuring its coherence. The quality and quantity of data may be difficult to ensure if we add too many layers of complexity (such as reporting on vulnerability) on top of the basic requirements for each case.

Internally, the disability approach is embedded in the TI secretariat’s gender and diversity policy. It highlights the principle of non-discrimination and equal treatment of every staff member, irrespective of gender or physical ability, and the secretariat’s commitment to promote diversity, both in the culture of the organization and in its management processes. The policy also applies to beneficiaries, and underlines that everyone should have equal access to TI’s programmes. It also takes into consideration the interaction between gender and disability.
Regarding human resources, German regulations require that 5-6% of employees must be people living with disability (PLWD). Any shortfall in this number requires organisations to contribute to a fund to support PLWD. We also implement other practices such as additional leave days and the provision of a suitable workplace.

## K: ADDITIONAL UPDATES (OPTIONAL SECTION) (1 page)

Any additional updates relevant to DFID

During the last five years, we have made progress in mainstreaming gender in our work. We now have a Gender and Diversity Policy, which has been in force since 2014, whose aim is to secure equal opportunities, fair and equal treatment for every single staff member. We have also been mainstreaming gender in M&E processes, e.g. pushing for considering it in evaluations, for collecting gender-specific data and feedback from men, women and minority groups. We disaggregate data where possible, e.g. on the thousands of complaints received by ALACs and on the Global Corruption Barometer results. This is key to understand better how women and men perceive and are affected by corruption. Our policy and research products contributed to building more knowledge in this area of work, including a recent topic guide that provides an overview of the linkages between gender and corruption.

Mobile ALACs and other outreach methods have been extremely valuable to make sure that we engage with as many people as possible, regardless of their location, gender or disability status. Mobile ALACs reach out to citizens in order to collect corruption-related complaints, and therefore provide opportunities for more vulnerable or rural populations to voice their concerns.

In the last few years, engaging the youth has become more prominent in our work. We mapped current efforts by chapters all over the world and a Transparency International youth booklet was prepared in collaboration with nine chapters to inspire the movement and expand this area. We now have a stronger base to include young people more effectively in case reporting and case resolution. Examples of initiatives in this field include a Youth Integrity Survey in Asia-Pacific and the creation of youth networks in Asia and in the Middle East and North Africa, all with a view to inspire young people to take action against corruption.

## L: Evidence Table (1 page maximum)

	Description	Link
1	Together Against Corruption (TI’s 2020 strategy)	http://www.transparency.org/whoweare/organisation/strategy_2020
2	Blog post on the SDGs	http://blog.transparency.org/2015/04/22/following-the-money-why-transparent-development-finance-matters/
3	G20 principles for promoting integrity in public procurement	https://g20.org/wp-content/uploads/2015/11/G20-PRINCIPLES-FOR-PROMOTING-INTEGRITY-IN-PUBLIC-PROCUREMENT.pdf
4	Just For Show	http://www.transparency.org/whatwedo/publication/just_for_show_g20_promises
5	Global Corruption Barometer, Middle East and North Africa	http://www.transparency.org/whatwedo/publication/people_and_corruption_mena_survey_2016
6	Topic guide on gender and corruption	http://www.transparency.org/whatwedo/answer/topic_guide_on_gender_and_corruption
7	Photo competition results	http://blog.transparency.org/2015/08/17/photo-competition-winner-children-are-most-affected-by-corruption/
8	Report on sport integrity	http://www.transparency.org/news/feature/sport_integrity
9	Incentivising integrity in banks	http://bit.ly/1t3e9Qi
10	Can justice be achieved through settlements?	http://bit.ly/1TZjfGX

## M: Summary Sheet of each Annual Review (Years 1-4) (maximum 1 page per year)

Year 1
Transparency International contributed to 13 changes in policy and practice, including new legislation on whistleblowing in Vietnam or the ratification of UNCAC in the Solomon Islands. With regards to outcome indicator 1.3, 1060 citations were reached in 2011. This is much higher than anticipated and confirms that TI’s research products continue to be used by a wide range of external stakeholders. Our visibility also increased through our website (+10% visitors).
Transparency International developed and published a wide range of research products, increasing the evidence on corruption issues for the Anti-Corruption movement and wider. Those evidence pieces on corruption which we envisaged to be developed were indeed published and the number of TI-S research publications in 2011 was 11 (excluding expert advice provided through the U4 Helpdesk, http://www.u4.no/helpdesk ).
We have been able to respond to this people focus by increasing our support to the TI movement in its engagement with citizens. TI-S developed a People Engagement Programme and invested in new staff to run this programme. We scaled up our support to chapters keen to be raising funds from individuals both to serve the purpose of diversification of resources, but also in terms of engaging the public meaningfully and in a variety of ways.
Reaching out to and influence external stakeholders has remained at the forefront of TI’s work in this reporting year. At the global level for example, and under coordination of the TI Secretariat, we kept up the pressure on the Group of 20 leading economies to fulfil the commitments their anti-corruption action plan set out in late 2010. At the 4th UNCAC Conference of States Parties (CoSP) we submitted 10 civil society parallel UNCAC review reports which were accepted as official documentation by UNODC. We continued to disseminate our work to an ever wider audience. In the first five days of December, after the launch of the 2011 Corruption Perceptions Index, our website was viewed more than 1 million times.
In addition to offering support and guidance on capacity issues that are critical to the entire TI Movement, the Institutional Network Strengthening Programme (INSP) also seeks to encourage and facilitate peer learning among smaller groups of Chapters as a sustainable approach to capacity development. On strategic planning, a guide for chapters was created by the secretariat, while chapters were initiating direct exchanges on the topic, e.g. TI Sri Lanka hosted the TI Pakistan and TI Nepal to share and discuss with them their own experience and approach to strategic planning. TI-S also facilitated a number of thematic capacity development workshops that brought together Chapter representatives from across all regions committed to taking a specific issue forward together. Topics included forest governance, sports and education.

Year 2
We supported and increasingly mobilised people in the anti-corruption fight, using ICTs more than ever before to bring our message across and mobilise new audiences. We became bolder in speaking out for increased transparency, integrity and accountability by public and private institutions and individuals. We were strong in our statements on the state of corruption in Europe and on multinational companies not being sufficiently transparent about their finances and structures. We engaged with global processes like the G20 and the OGP, capitalising on our extensive network of Chapters to remind governments that words and commitments only matter when they are followed up by action.
Supporting our network of Chapters in developing their capacities remained a key area of work. In addition to assisting Chapters with our holistic organisational capacity assessment, we offered them a range of new capacity development solutions, including seed funding and guidance assisting them with their strategic and fundraising planning processes. We extended this support to new emerging partners seeking to strengthen our presence in countries where we have not been active so far. We also strengthened numerous internal dimensions of our work, such as mainstreaming gender, updating our financial manual, establishing new modalities for thematic decentralisation to Chapters and shaping two future initiatives on “no impunity for corruption” and “financial sector integrity”.
Highlights
- We accelerated our engagement with citizens through ICT tools and social media. Increasingly, TI Chapters combine “offline” hotlines and support (particularly ALACs) with online reporting and mapping platforms. We also increased our social media outreach, including to Arab speaking countries.
- Our TRAC report was a great example where limited investments led to strong impact. The report targeted governments, companies and civil society and analysed the transparency of corporate reporting on a range of anti-corruption measures among the 105 largest publicly listed multinationals. Following the launch, we have been in touch with about 50 companies researched in the report wanting to discuss their scores and how they can improve their anti-corruption performance.
- Our boldest statement yet on the state of corruption in the developed world was the European National Integrity Project. This project produced a substantial body of knowledge on anti-corruption systems in 25 EU countries and was accompanied by substantial media attention reaching an estimated audience exceeding 1.2 million people.

Challenges
- As we continued to seek to engage more citizens in the fight against corruption, we became increasingly aware that victims and witnesses of corruption coming forward need protection. We also unfortunately noted how it is difficult for an increasing number of Chapters to operate freely.
- While good progress was made in policy areas relating to our issue (e.g. the new EU accounting and transparency directives), it became clear that important legislation is under pressure (e.g. Foreign Corrupt Practices Act)
As our efforts towards citizens’ engagement gained greater momentum, organising ourselves to turn citizens as active supporters will be the next creative challenge for TI.

Year 3
Achievements
- True to TI Strategy 2015, TI-S reached out to an increasing number of citizens and supported chapters in their work doing the same. TI’s ALACs continue to operate as powerful, credible and viable mechanisms for people to pursue their corruption-related complaints. The whistleblower principles, developed by TI in 2013, contributed towards a vast array of changes in discourse and policy over 2013, as described in this report. Finally, TI-S captured new and diversified audiences directly, thereby increasing the visibility of the Movement. Particular significant achievements were the tripling of Facebook friends in English; a 21-fold jump in Arabic followers and a Barometer infographic that was one of the most viewed items on the BBC’s website on the launch day.
- Strengthening the TI movement remains a priority for TI-S. In this reporting year, we particularly focussed on supporting chapters in the areas of organisational assessment and planning; governance and leadership; advocacy and communications and resource mobilisation. Doing so, we continued to support both capacity development of individual chapters as well as a number of global activities to address common capacity needs shared by chapters across the TI Movement.
- Engaging with and influencing global debates on governance remained one of our strengths in this reporting year. Advocacy efforts directed towards a number of key initiatives and organisations yielded successes such as through the G20, in the form of an agreement on automatic exchange of information; a policy position on beneficial ownership at EU level; and a G8 commitment to establish public registries of beneficial owners. TI’s recommendations were reflected in the UN’s High Level Report on the Post-2015 Agenda which calls for a governance goal and target on anti-corruption and bribery. Reflecting TI recommendations, the EU adopted a new law requiring all companies in the extractive sector listed on EU exchanges to report their payments by country and project, while large unlisted companies registered in the EU are also required to comply.

Challenges
- While civil society movements have many opportunities today to engage at the global level – for example in the G8/G20 and post-2015 processes, the space for civil society to operate at national level  is shrinking in many countries, which remains a serious concern to our movement. Chapters within the TI movement were put under threat in a range of countries in this reporting year.
- While TI has seen growth over recent years, the changing political priorities of some of our traditional donors have put financial pressure on the organisation, making it more difficult to matching our ambitions with the necessary resources. While TI-S is working hard to diversify its donor base, for example to foundations, decisions by some bilateral partners to reduce funding due to a shift in their priorities, has meant some programming, including in Africa, had to be scaled down.
- While on the one hand citizen demand for social accountability is evident in a range of countries around the world (Ukraine, Turkey and others), at the same time all too many people consider corruption to be ‘normal’ or ‘acceptable’. Our own research among youth in Asia and Pacific found for example that while over 80 per cent of young people believe that youths want to take action against corruption, 72% admit they are willing to behave corruptly if it yields personal benefit.
Year 4
Summary of progress and lessons learnt since last review
In terms of advocacy, we have had some major successes in year 4 such as the adoption of anti-corruption principles by the G20 and the inclusion of a governance goal within the draft Sustainable Development Goals. There is a clear momentum for anti-corruption action at the international level (also at the G7 and EU levels), but substantial efforts are needed to capitalise on it. The programme continues to prove its value in changing policies and practices, and our direct support to victims and witnesses of corruption has allowed us to collect more and more stories showing our impact on people’s lives. More than 60 chapters work on such cases and often mainstream this approach into their activity. We will however need to closely monitor civil society space and attacks on activists and whistleblowers, which were prominent issues in year 4. We have increased our reach through website, blog and social media alike, and the 2014 Corruption Perceptions Index received huge media attention and visibility. Partnerships with other NGOs also helped us broaden our audiences. Nationally, chapters have made efforts to reach out to more and more citizens, for example in the Middle East and North Africa, where networks of women leaders have been set up. We continued to strengthen our evidence base on corruption with 10 new publications, ranging from the Exporting Corruption Report on foreign bribery to the Transparency in Corporate Reporting report, which boosted private companies’ engagement with TI and their commitment to improve their behaviour. Finally, the TI secretariat supported chapters to develop their capacity, especially in the field of leadership, risk management, advocacy and communications. For this purpose, horizontal learning and chapter-to-chapter exchanges have proven very useful.

Summary of recommendations for the next year
- Develop a new 5-year strategy that is expected to be implemented from early 2016.
- An organisational audit of the secretariat will be performed to examine our processes and systems and see how we can further improve our value for money.
- Expand our supporter base, for example through our Global Unmask the Corrupt campaign and a new responsive website.
- Deepen our analysis of National Integrity System Assessment impact data.
- Strengthening synergies between research and knowledge products.
- Secure further partnerships to carry out regional surveys for the Global Corruption Barometer.
- Increase understanding of what works, what does not, and why in anti-corruption work.
- Continue strengthening the management and resolution of cases of corruption.
- Strengthen the TI secretariat’s value-added as a ‘broker’ and ‘facilitator’ within the TI movement

DFID Management response to the Transparency International Secretariat PCR (General Funding)

Transparency International Secretariat (TI) has produced a clear, well evidenced Programme Completion Report (PCR) demonstrating the key achievements and impact of their Programme Partnership Arrangement (PPA); both from an institutional and programming perspective.

The PCR illustrates how TI has met and in some cases exceeded the outcome and outputs targets agreed within the programme log-frame. Furthermore the PCR demonstrates a range of specific examples detailing how the PPA has contributed to key changes in policy and practice both at global and national levels. For example, the ‘2030 Agenda for Sustainable Development’ which outlines the SDGs, used TI’s language on governance and corruption. TI also played a key part in influencing the G20’s new principles on public procurement and open data which were adopted in 2015.

DFID was pleased to note a number of significant achievements as a direct result of the PPA programme, such as, improved organisational capacity in both monitoring and evaluation (M&E) and financial management. Over the period of the PPA, TI has made significant improvements to strengthen its M&E systems. For example, the development of an impact monitoring approach – recognised by the INGO independent review panel as good practice for other organisations – that is steered towards outcomes and learning. This will allow TI to build a more robust body of evidence regarding what works in the fight against corruption, and why and how it works. Key improvements are also evident in financial management which includes stronger financial systems; a new tool to assess the Chapter’s financial situation and the reorganisation of the overall financial function to ensure better oversight and monitoring of expenditure.

Another key success of the PPA programme has been the progressive integration of people engagement and campaigning into TI’s approach and practices. For example, the ‘Unmask the Corrupt’ campaign, which strives to end corporate secrecy and prevent the corrupt from hiding their assets, and the work on grand corruption cases, both new approaches for TI. The impact of this campaign is evident with more than 125,000 people voting on the worst cases of corruption and 238,000 people visiting the dedicated website.

In the last reporting year TI has met, and in some cases exceeded, most of its PPA output targets. Where targets have not quite been achieved, TI has provided clear justification as to the reason why and additional information on what has been accomplished. For example, Output 2, where the number of case studies published did not reach the required milestone; this was due to shifting to a more visual approach While this approach presented new challenges in terms of budget, required skills and time (e.g. working with film crews across countries) – which is why TI did not reach the target – the end product is far more powerful than simple text and can be used in many ways. One of the videos alone was viewed more than 60,000 times on Facebook.

Based on the information set out in the PCR and subsequent discussion with TI, DFID assessed the programme to have an overall ‘A+’ rating at its completion point after five years.

CHASE Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime.

Agencies should use Section M to provide a short summary from each Annual Review over the life of the programme (maximum 1 page per year).

Review Date:	09/08/2016

Title: Transparency International UK – International Defence and Security Programme (DSP) – Programme Partnership Arrangement / CHASE PPA
Programme Code: 202505	Start Date: 1 April 2011	End Date: 31 March 2016

Summary of Programme Performance

Year	2012	2013	2014	2015	2016
Programme Score	A+	A+	A+	A+	A+
Risk Rating	Medium	Medium	Medium	Medium	Moderate

Financial Position

Original Programme Value	2,112,225
Extensions/ amendments	1,408,150
Brief details of the 3 most recent log-frame revisions with dates	29 June 2015; 1 July 2014; 12 December 2013. / The most important amendments were twofold: (1) improving and spelling out the quantitative as well as the qualitative dimension of the outcomes, outputs, and indicators; (2) revising targets up in light of results (substantially) exceeding expectations, for example regarding the amount of practical tools produced, experts trained, and civil society capacity built Please see the logs submitted with each set of changes for details.
Total programme spend	3,510,841

Other DFID Funding

Please note that TI’s global Defence and Security Programme (DSP), based at TI-UK in London, does not receive other DFID funding beyond the CHASE PPA. Others within TI, including TI National Chapters and the global Pharmaceuticals & Healthcare Programme also based at TI-UK, do receive non-PPA funding from DFID. Please see the report of the TI International Secretariat (TI-S), who also implement the General DFID PPA.
Please see Section M.
DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202505
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202505

A. Introduction and Context (maximum 2 pages)

Outline of programme and what it has achieved at the end of the PPA period

Short summary of progress and key results from Year 5 of the PPA (1 page max)

Government Defence Anti-Corruption Index 2015/16 (GI): The GI is DSP’s most powerful tool in triggering dialogue on institutional reform, and has led to practical change in several countries, as outlined below. In 2015/16, DSP persuaded around half of the 115+ governments analysed to review our assessment before publishing, with around a third ultimately engaging in substantive dialogue with DSP. The second iteration of the GI included regional/thematic reports on the Asia-Pacific, G20, Middle East and North Africa, NATO Members and Partner States, and Africa. The reports as well as all detailed country assessments are available online at http://government.defenceindex.org/. On the back of the GI launches, a number of capacity development and events were agreed, including a Leadership Day in Ghana, training opportunities for peacekeepers in South Africa, and TI (DSP alongside their local colleagues) was invited to advise the Tunisian MOD on reform efforts.
Defence Companies Anti-Corruption Index 2015 (CI): The second iteration of DSP’s flagship CI was launched in the UK on 30 April 2015, as well as at launch events in Berlin, Paris and DC. The CI is the first index which specifically examines companies in the defence sector. It is also unique because it looks at internal company information to get the fullest picture of their anti-corruption and ethics programmes. One key focus was on investors as well as defence industry umbrella organisations. An unprecedented number of 64 companies had shared internal information (39%, up from 26.4% in 2012). Numerous companies visited DSP for detailed discussions as the CI was finalised, including Rolls-Royce, BAE Systems, Serco, L-3 Communications and ThyssenKrupp. Several companies continue to be in touch as they strive to improve their ranking in the next CI.
Sustainable country reform: DSP has continued to drive and facilitate sustainable defence and security anti-corruption reform efforts, in countries ranging from Nigeria and Afghanistan to Ghana, Ukraine, Tunisia, South Africa and Uganda. While more details are available below this has e.g. included the creation of independent oversight institutions and advising on concrete Ministry of Defence reform plans, often informed and propelled by the GI.
Thought leadership: DSP is leading policy thinking on corruption and conflict. Billions are going into security assistance programmes mainly driven by militaries, which are at risk of fuelling the problem they are trying to solve. DSP has developed best practice guidance to help militaries and policy makers tackle these corruption risks in countries like Yemen. DSP has also published lessons identified from Afghanistan and Mali. DSP brought together high level foreign policy, defence and military decision makers to agree concrete steps on security assistance during the London Summit and has also been discussing this with various key actors in DC. DSP has been asked by e.g. the OECD and UNDP to help ensuring ambitious but practical goals are set for SDG goal 16, and it has driven discussions on corruption and conflict for the UK’s SDSR. DSP was the first NGO to be invited to train the UN Department for Peacekeeping Operation’s leadership team; they have agreed in principle to allow DSP to monitor a peacekeeping mission to assess what more needs to be done.
NATO’s Building Integrity policy: DSP also work closely with NATO on the Building Integrity (BI) policy – indeed it was DSP that was the catalyst for NATO’s BI programme. Once the policy has been approved in Warsaw, DSP will be looking at how to ensure it is turned into a sustainable action plan. DSP will be working closely with SHAPE and other NATO institutions, including in developing NATO’s BI curriculum and shaping training content and exercises. TI’s long-standing engagement would have been impossible without DFID funding, particularly in the beginning, and it continues to be very much informed by the practical tools that are PPA funded (such as the GI thematic analysis specifically examining “NATO members and partner states”).

Military capacity building, doctrine and secondments: DSP has continued its very close work with the military, including the Allied Rapid Reaction Corps (ARRC) in Gloucester and the 1 German Netherlands Corps (1GNC) through planning advice and participation in their exercises. DSP runs a high impact capacity building programme which combines formal training for defence forces, leadership days, secondments, and support in developing anti-corruption action plans – often in partnership with the UK Defence Academy. In the last year DSP hosted secondees from e.g. Afghanistan, Ukraine, and Jordan. Secondments are one of DSP’s most successful interventions. A former secondee from internal audit in the Ukrainian MOD is now at the centre of defence reform efforts, alongside the training centre DSP helped to establish within the ministry.
Telling of the story of the lifetime of the PPA, showing what the programme has achieved (including highlights, key achievements etc.) (1 page max)

Over the last decade, DSP has led the way in putting defence and security corruption on the agenda of policy makers, defence companies, international organisations, and civil society. Success has been built on the credibility of DSP’s people and the quality of its research. The DSP team includes a remarkable group of experts – including former senior military and law enforcement personnel, as well as diplomats and individuals from the private sector, who understand the need for strong clean defence institutions to protect citizens. These experts have enabled Transparency International to engage with and build trust with defence and security establishments, as well as providing insight and expertise upon which much of DSP research has been founded. This expertise, combined with an approach that supports those interested in reform by providing them with practical tools (such as both indices as well as other DSP targeted risk analyses on key areas ranging from offset arrangements to security assistance or good practice during military deployments that can easily be converted into practical recommendations and action plans), has been key to DSP successes so far.
The Government Defence Anti-Corruption Index (GI) is a particularly important innovation underpinning capacity-building work, and the first ever attempt to assess in detail the existence and effectiveness of institutional (and informal) controls to manage the risk of corruption in defence and security institutions and of their enforcement. The detailed research has enabled officials in reform-minded governments to understand where they need to focus conrete action, while the implicit peer to peer comparison has proven a powerful motivator for change. 13 governments engaged with DSP directly in the immediate GI launch period, with civil society action in 17 countries and extensive media coverage (more than 250 recorded) in 28 countries.
Similarly the Defence Companies Anti-Corruption Index (CI) has played an influential role in establishing standards of compliance and transparency across the industry. 60% of companies improved their scores in the second edition of the index, demonstrating a significant increase in transparency of their ethics and anti-corruption programmes. This included Lockheed Martin, Raytheon and Bechtel, all of which now score an “A”. 63 companies provided additional internal information about their ethics and anti-corruption programmes, an 85% increase on the 2012 analysis.
Many experts and allies DSP consulted on its new strategy stressed the importance of retaining the good access TI has established in many countries and of identifying the right individuals within governments and industry with whom to engage. Others have been emphasing DSP’s high quality research and the continued appetite for good practice examples and case studies.
From 2011 to 2016 DSP has facilitated significant progress and helped to increase transparency and accountability in the defence and security sector, ensuring that these efforts focus on both the supply and the demand side and improve the understanding and thus mitigation of the detailed and sector specific risks for both. DSP’s most successful tools have been scaled up and are now applied in countries as diverse as Afghanistan, Ghana, Georgia, Nigeria, the OPT, South Africa, Tunisia, Uganda and Ukraine, as well as by international organisations ranging from the UN to NATO and the World Bank (whose decision to finally venture into security and to develop a security expenditure toolkit is considered a major milestone by DSP). While the two indices are the most popular tools, they provide a detailed action plan and concrete steps both governments and companies can take based on their own priorities and capacity and highlight good practice that can be emulated. Other tools that have proven to be in particular high demand include DSP’s tailormade capacity building and training courses (e.g. at the OF-5 level, which has also been available at all NATO schools since it was accredited). DSP guidance on good practice during military deployments and operations, DSP templates for civil society oversight, or DSP analysis of key issues that are particularly important to the defence sector, such as offsets.
Defence companies from major defence players and exporting nations have substantially reformed their systems through working with DSP, not only those from the U.S., UK, or European nations but also from markets such as South Korea.
DSP has played a major role to ensure that the linkages between corruption and security are firmly on the agenda of security as well as foreign policy makers – one very practical outcome has been the inclusion of (anti-)corruption in military doctrine, for example in the U.S., the UK, or Norway, as well as its inclusion (through DSP) in military exercises and planning.
DSP has helped civil society oversight capacity needed to hold their governments to account locally to increase substantially, with more practical tools at their disposal as well. This includes many of the 100+ TI National Chapters (e.g. in the Occupied Palestinian Terrortries, Tunisia and Nigeria) but also plenty of other civil society organisations from all around the world. This has been a key focus of DSP as reform and change ultimately need to be driven and owned locally.

## B: PERFORMANCE AND CONCLUSIONS (6 pages maximum)

Overall Outcome Assessment (max 2 pages)

DSP takes pride in the progress made against its outcomes identified over the lifetime of the CHASE PPA, including of course its most recent log frame outcome that “Government defence establishments, armed and police forces, defence companies, international organisations and civil society have enhanced knowledge of and increased access to the necessary practical tools to tackle corruption in defence and security.” While the “Telling of the story of the lifetime of the PPA” under A. above summarises the progress that has been made from 2011 to 2016, a few detailed examples from FY 2015/16 might be useful for a more thorough recent snapshot:
Nigeria: DSP has been working closely with its Nigerian partner, the Civil Society Legislative Advocacy Centre (CISLAC) in light of the threat posed by Boko Haram, which is also driven by corruption, as well as President Buhari’s anti-corruption mandate. Following expert roundtables in both London and Abuja and consulting with HMG including the High Commissioner in Nigeria, CISLAC facilitated a call from Nigerian civil society for greater efforts to stem the flow of Nigerian corrupt assets ahead of the London Anti-Corruption Summit. DSP and CISLAC joint forces to hold a workshop on defence oversight, taking advantage of attendance by Nigerian Parliamentarians on the day. DSP also presented on a panel organised by the All Party Parliamentary Group on corruption, alongside the UK’s Minister for Africa. Next steps include the formation of an anti-corruption steering committee and gathering stories of how defence corruption effects people outside of Abuja, particularly in the north. CISLAC are seeking additional funding from UNODC to supplement the initial DFID funding. Others consulted on Nigeria include the Independent Corrupt Practices Commission (ICPS), the Police Deputy Inspector General and one of Buhari’s advisers in Nigeria, as well as the World Bank.
Afghanistan: Most recently, DSP contributed to recommendations for the Brussels Conference which also inform an open letter from TI, Global Witness and Integrity Watch Afghanistan to President Ghani and the NATO Secretary General in advance of the Warsaw Summit. The recommendations have been shared and discussed with the FCO Afghanistan Unit and the State Department’s Afghanistan Office, as well as the UK embassy in Kabul, and have received positive feedback from CSTC-A / NATO RSM. A NATO Afghanistan “Building Integrity” (BI) course was delivered as part of an HQ Resolute Support UK / U.S. Capstone programme, with participants who were mainly at the 2/3 star level (with some 1 stars) from both the ANA and the ANP – plus officials from the MOI and the Presidents Information Service. Most participants were operational Brigade or Zone Commanders and hand selected by the President – thus demonstrating the overt commitment of the administration to tackle corruption despite the ongoing operational posture. Participant feedback indicates they greatly appreciated the depth of knowledge and experience in Afghanistan of the BI team. There was agreement from all attendees that the programme was of very high value and should be continued and, ideally, extended to more senior officials. Further courses are projected for the coming financial year, funded by the UK Defence Academy. DSP also moderated a discussion with the SIGAR (Special Inspector General for Afghanistan Reconstruction) at the “Project for the Study of the 21st Century” in London.
Ghana: DSP, together with TI Ghana (Ghana Integrity Initiative) and the Commonwealth Parliamentary Association (CPA), organised a programme in Ghana exploring parliamentary scrutiny of defence and security. Participating members included the Chairs and Members of the Public Accounts and Defence and Interior Committees from Ghana, a delegation of 3 UK Members and a Clerk of the House of Commons. The GI Africa results were launched in Accra in January 2016, after which the Ghanaian Defence Minister requested a “Leadership Day”. His Deputy opened the event, which featured almost 50 participants from e.g. the military, MOD, and the Kofi Annan Peacekeeping Training Center (KAIPTC), including at the highest level – the Chief of Defence Staff for example stayed throughout, as did the KAIPTC Commandant and a number of Brigadier Generals from the GAF. The TI presentations (DSP and Ghana Integrity Initiative) led to very lively and constructive debates facilitated by DSP, and the whole room agreed on a number of follow-up areas at the end. The Ghana Armed Forces Command and Staff College requested a one day module on accountability and transparency to be inserted into their conflict and crisis management training in July. This will feature Ghanaian representatives as well as participants from 10 to 15 other African nations.
Military capacity building, training and doctrine: DSP continues to be heavily involved in military capacity building and training, and has also been driving as well as responding to a strong demand for military doctrine to cover anti-corruption. DSP has continued to engage the United Nations Department for Peacekeeping Operations (DPKO) in New York on anti-corruption in peacekeeping. This led to DSP delivering training for DPKO’s Senior Leaders Programme – the first time corruption was on the agenda, and the first time an NGO was invited to lead training. The UN High Level Panel on Peace Operations issued its report in June 2015, which contains a number of anti-corruption references as suggested by DSP. DSP was also invited to brief the Higher Command and Staff Course (HCSC) in Shrivenham on corruption and insecurity. This is a 4-month joined course for selected UK Colonels and equivalents from others services as well as Colonels from the U.S., France and Germany, plus civilians from the FCO, GCHQ, and MOD. DSP took part in a civil-military exercise, Common Effort 2015, organised by the 1 German Netherlands Corps (1GNC), as well as 1GNC’s military exercise “Truthful Sword” and the Allied Rapid Reaction Corps’ (ARRC) exercise “Arrcade Fusion”. DSP has been feeding into the “Building Integrity” policy that is currently being developed by NATO, to be launched at the Warsaw Summit, in line with its strong and long standing relationship with NATO. DSP along with its secondee from the UK’s 77th Brigade delivered two sessions on corruption in operations at NATO’s Supreme Headquarters Allied Power Europe (SHAPE). DSP is working with the UK Army Land Warfare Development Centre who would like to introduce counter corruption issues into their doctrine, and with the ARRC on how to incorporate corruption in their planning processes.
Ukraine: DSP participated in the Ukraine Anti-Corruption Week at the National Defence University to further develop the Ministry of Defence’s anti-corruption programme. DSP also launched the Ukraine assessment of the GI at a press conference with the Deputy Minister of Defence and the Head of the National Anti-Corruption Bureau. The Dutch Ministry of Foreign Affairs have confirmed their support for a Defence Corruption Monitoring Committee in Ukraine. This is significant additional funding for DSP and will be the first project in which DSP is directly managing staff not based in London. Working closely with TI Ukraine, DSP will set up a civil society oversight body to monitor and provide input to defence anti-corruption reform.
Tunisia: DSP and I Watch (TI Tunisia) secured a commitment from the MOD to review their 2015 GI scores, following the launch of the GI MENA results in Tunis. A panel discussion included the MOD Director of Administration and Finance, the expert responsible for Good Governance in the Prime Minister’s Office and the Chair of the Defence and Security Committee in Parliament.
SDGs: DSP participated in an OECD workshop on how to make Goal 16 of the SDGs succeed. DSP also went to Oslo for a UNDP / PRIO workshop on SDG 16 to help set national indicators.
Uganda police: DSP held a leadership day with senior commanders of the Uganda Police Force, with a turnout of more than 30 senior (mostly commissioner level) participants. This was made possible by Dutch funding matching the initial DFID funding used.
Military and defence secondments: DSP welcomed two Afghan secondments – Mohammad Yousuf Zazai, the Head of the Military Training Department at the National Military Academy and Zemari Shafi, its Director of Education and Curriculum Development. They developed colonel level training together with DSP. DSP secondment Captain Tom Padgett from the British Army’s 77th Brigade wrote a blog about his work with DSP: http://tiny.cc/lmjf4x.
HMG: DSP contributed to the development of the most recent SDSR, working e.g. with the Development, Concepts and Doctrine Centre (DCDC) in Shrivenham and attending a group discussion with the UK Chief of Defence Staff, as well as a group roundtable on the SDSR with DFID, including the Director for SDSR and Defence at the Cabinet Office. DSP also spoke at two corruption risk workshops of the UK defence procurement business unit.
Changes to capacities in relation to results (max 4 pages)
TI could not agree more with the PPA Fund’s overarching hypothesis that “The unrestricted and flexible nature of PPA funding enables organisations to develop their capacity and systems in ways that lead to measurably improved results and value for money”.
The CHASE PPA has enabled DSP to make significant changes regarding its capacity and systems. While some of the measurable results are described above and further detail on value for money (VFM) can be found below, it is important to summarise some of the linkages.
Through the CHASE PPA, DSP was able to conceive, pilot and then scale up its two most important and most impactful flagship projects: the GI and the CI. The unrestricted and flexible nature of the PPA also made it possible for DSP to engage in ‘kite flying’ regarding further practical tools: testing various approaches and instruments that otherwise would have remained untested, piloting those that appear encouraging after thorough scrutiny and then scaling up the most promising tools.
The CHASE PPA has also allowed DSP (a) for the first time ever to fund dedicated staff focusing on certain functional areas, such as civil society liaison and fundraising and (b) to finance shared functions with other TI programmes based in London, such as the global Pharmaceuticals & Healthcare Programme. Joint functions that have been established with minimum overhead costs for all involved include e.g. communications, finance, and office management. Establishing these dedicated responsibilities has greatly helped programme staff and colleagues leading on certain content areas to fully concentrate on most effectively applying their expertise, resulting in much appreciated VFM for DSP (and others).
Funding security over the medium term has also hugely benefitted DSP, as it has provided the time that is necessary to build some of the very successful relationships that have been outlined above, not least in a sector as secretive and delicate as defence and security.
As is referenced throughout this report, CHASE PPA funding has also enabled DSP to secure significant additional income, resulting in increased sustainability for DSP (also post-PPA) and VFM for all donors involved, who benefit from lower ‘unit costs’ for trialled and tested tools (new donors) as well as others continuing to fund work that has been successfully piloted at a larger scale (DFID and other existing donors). Examples of additional funding partnerships include for example DSP’s work with the UK Defence Academy on capacity building, training and secondments; with the Dutch Ministry of Foreign Affairs in Africa and more recently in Ukraine; and with the Network for Social Change on agents and intermediaries in the arms trade.

Sustainability of capacity changes
The key changes outlined above have been and will continue to contribute building on DSP’s CHASE PPA outcome – at a larger scale, with more partners, further milestones etc.: “Government defence establishments, armed and police forces, defence companies, international organisations and civil society have enhanced knowledge of and increased access to the necessary practical tools to tackle corruption in defence and security”.
As described above funding sustainability of DSP has been greatly enhanced by and throughout the CHASE PPA, with various additional funding approaches underway to develop this further. These include a trust fund of nations that might help to finance future iterations of the GI, as well as promising conversations with a number of trusts and foundations to further extend the DSP fund for TI National Chapters, the first iteration of which is being piloted with CHASE PPA funding.
In the long term, sustaining these changes will bring significant parts of the world gradually closer to “Improved transparency and reduced levels of corruption in the Defence and Security sector, which contribute to poverty reduction and the post-MDG targets” (DSP’s impact statement).
Sustainability is also likely to be enhanced by further growth of other TI programmes in London, such as the global Pharmaceuticals & Healthcare Programme, as increased income will drive down overhead and unit costs of all shared functions and thus increase VFM.
Funding of partnerships
While DSP very much values and benefits from its work with various partners, it does not primarily work through partnerships in terms of others implementing its work. That said DSP has been piloting a small fund for TI National Chapters and is seeking additional funding in light of promising indications thus far. Most of DSP’s partners are at the strategic level, and as has been described above DSP’s experts and expertise have enabled it to engage with and build trust with defence and security establishments, as well as providing insight and expertise upon which much of DSP research has been founded. This expertise, combined with an approach that supports those interested in reform by providing them with practical tools, has been key to DSP successes so far.
DSP will of course continue to work with its partners, both in the short term and in the long run, and not least through the TI movement of more than 100 National Chapters in the world. DSP is a member of the Control Arms and other coalitions (sometimes on an ad hoc basis) and also works with various non-TI civil society organisations around the globe.
DSP of course very much hopes to continue its strategic relationships with donors such as DFID, the Dutch Ministry of Foreign Affairs, and the UK Defence Academy. DSP considers these partnerships to significantly extend beyond financial support; indeed they would not make sense without working together, sharing visions and objectives, and partnering on concrete content and actions.
DSP has a dedicated fundraising officer in place as part of the TI Fundraising Department in London, with a financial contribution from the CHASE PPA. The aim is of course to further develop DSP’s donor portfolio and to further increase diversity and sustainability.
Learning
While the development and humanitarian landscape has indeed been evolving since 2011, DSP believes that the funding it has used to develop capacity has been applied following the same rationale throughout: change and reform are best driven and owned locally, and by those who have the strongest stake in their realisation. Sustainability will only be secured if they decide to own and lead on work going forward, with DSP (and others of course) playing an advisory role and standing ready to help.
If any funding decisions could be reviewed, TI-DSP might have considered introducing a mechanism like the fund for TI National Chapters earlier, though this has not prevented DSP from forming close partnerships and alliances and to collaborate with various civil society organisations, including but also beyond TI.
While DSP’s work and approaches was naturally adapted throughout the lifetime of the CHASE PPA to secure maximum impact (and in line with the approach to innovation which was only made possible by the CHASE PPA; see above) there is a solid golden thread from year 1 to year 5 – the GI and the CI are testament to this.
Output Score and Description
A+ Outputs moderately exceeded expectation
## C: DETAILED OUTPUT SCORING (1-2 pages for the table and 1 for the narrative).

Output Title	High level governmental workshops and events addressing Defence and Security Reform best practice and initiatives conducted worldwide, including in Southeast-Asia, Africa, and whereever in the world governments express an interest.
Output number per LF		1	Output Score	A+
Risk: [please select only one per output, using the new DFID risk definitions]		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of overall TI-DSP engagements (invitations, meetings).	438 (Target: 390)	513 (Target: 458)
Level of oversight of the Afghan National Security Force post-2014.	TI-DSP engagement with Afghan civil society, the ANSF and others leads to concrete proposals for strengthened oversight of the ANSF.	Some strengthened oversight structure of the ANSF established.

FY 2015/16 has seen significant progress as far as best practice and reform initiatives are concerned. Examples include the following:

Nigeria: DSP has been working closely with its Nigerian partners, the Civil Society Legislative Advocacy Centre (CISLAC), in light of the threat posed by Boko Haram which is also driven by corruption, as well as President Buhari’s anti-corruption mandate. DSP and CISLAC joined forces to hold a workshop on defence oversight, taking advantage of attendance by Nigerian Parliamentarians on the day. DSP also presented on a panel organised by the All Party Parliamentary Group on corruption, alongside the UK’s Minister for Africa. Next steps include the formation of an anti-corruption steering committee and gathering stories of how defence corruption effects people outside of Abuja, particularly in the north. CISLAC are seeking additional funding from UNODC to supplement the initial DFID funding. Others consulted on Nigeria include the Independent Corrupt Practices Commission (ICPS), the Police Deputy Inspector General and one of Buhari’s advisers in Nigeria, as well as the World Bank.
Ghana: DSP, together with TI Ghana (Ghana Integrity Initiative) and the Commonwealth Parliamentary Association (CPA), organised a programme in Ghana exploring parliamentary scrutiny of defence and security. Participating members included the Chairs and Members of the Public Accounts and Defence and Interior Committees from Ghana, a delegation of 3 UK Members and a Clerk of the House of Commons. The GI Africa results were launched in Accra in January 2016, after which the Ghanaian Defence Minister requested a “Leadership Day”. His Deputy opened the event, which featured almost 50 participants at the highest level. The TI presentations (DSP and Ghana Integrity Initiative) led to very lively and constructive debates facilitated by DSP, and the whole room agreed on a number of follow-up areas at the end. The Ghana Armed Forces Command and Staff College requested a one day module on accountability and transparency to be inserted into their conflict and crisis management training in July. This will feature Ghanaian representatives as well as participants from 10 to 15 other African nations.
Ukraine: DSP participated in the Ukraine Anti-Corruption Week at the National Defence University to further develop the Ministry of Defence’s anti-corruption programme. DSP also launched the Ukraine assessment of the GI at a press conference with the Deputy Minister of Defence and the Head of the National Anti-Corruption Bureau. The Dutch Ministry of Foreign Affairs have confirmed their support for a Defence Corruption Monitoring Committee in Ukraine. This is significant additional funding for DSP and will be the first project in which DSP is directly managing staff not based in London. Working closely with TI Ukraine, DSP will set up a civil society oversight body to monitor and provide input to defence anti-corruption reform.
Tunisia: DSP and I Watch (TI Tunisia) secured a commitment from the MOD to review their 2015 GI scores, following the launch of the GI MENA results in Tunis. A panel discussion included the MOD Director of Administration and Finance, the expert responsible for Good Governance in the Prime Minister’s Office and the Chair of the Defence and Security Committee in Parliament.
Uganda police: DSP held a leadership day with senior commanders of the Uganda Police Force, with a turnout of about 35 or so senior (mostly commissioner level) participants. This was made possible by Dutch funding, which DSP used to match the initial DFID funding.
HMG: DSP contributed to the development of the most recent SDSR, working e.g. with the Development, Concepts and Doctrine Centre (DCDC) in Shrivenham and attending a group discussion with the UK Chief of Defence Staff, as well as a group roundtable on the SDSR with DFID, including the Director for SDSR and Defence at the Cabinet Office. DSP also spoke at two corruption risk workshops of the UK defence procurement business unit. Furthermore, DSP fed into the International Development Committee enquiry regarding tackling corruption overseas.
On Afghanistan specifically, DSP contributed to recommendations for the Brussels Conference which also inform an open letter from TI, Global Witness and Integrity Watch Afghanistan to President Ghani and the NATO Secretary General in advance of the Warsaw summit. The recommendations have been shared and discussed with the FCO Afghanistan Unit, the State Department’s Afghanistan Office, and the UK embassy in Kabul, and have received positive feedback from CSTC-A / NATO RSM. A NATO Afghanistan “Building Integrity” (BI) course was delivered as part of an HQ Resolute Support UK / U.S. Capstone programme, with participants who were mainly at the 2/3 star level (with some 1 stars) from both the ANA and the ANP – plus officials from the MOI and the Presidents Information Service. Most participants were operational Brigade or Zone Commanders and hand selected by the President – thus demonstrating the overt commitment of the administration to tackle corruption despite the ongoing operational posture. Participant feedback indicates they greatly appreciated the depth of knowledge and experience in Afghanistan of the BI team. There was agreement from all attendees that the programme was of very high value and should be continued and, ideally, extended to more senior officials. Further courses are projected for the coming financial year, funded by the UK Defence Academy. DSP also moderated a discussion with the SIGAR (Special Inspector General for Afghanistan Reconstruction) at the “Project for the Study of the 21st Century” in London.

The indicator above, “Strengthened oversight structure of the ANSF established”, was a specific agreement between DFID CHASE and DSP to try to include a solely qualitative indicator. While the GI 2015 assessment, conducted by independent and non-TI Integrity Watch Afghanistan, found that “the current government has significantly stepped up oversight over procurement contracts and the development of anti-corruption training for select personnel”, a more nuanced (and less dichotomous) indicator might have been more measurable with certainty – a lesson DSP has already identified for the development of current and future log frames throughout the programme.

Output Title	Defence industry and governments worldwide influenced to conduct arms trade and transfers more responsibly, with improved controls against corruption, industry standards and codes of conduct.
Output number per LF		2	Output Score	A+
Risk: [please select only one per output, using the new DFID risk definitions]		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Cumulative number and description of states TI-DSP engages (including via regional organisations) to convince them to implement the anti-corruption mechanisms in the UN Arms Trade Treaty.	12 (Target: 10)	19 (Target: 17)
Number of regional and national defence industry umbrella organisations TI-DSP works with.	18 (Target: 11)	24 (Target: 22)

Three sections in the UN Arms Trade Treaty help states to address the corruption risks at the various stages of an arms transfer, including at the highest level of arms export criteria (not authorising an export if undermined by corruption and money laundering); with a particular focus on diversion; and encouraging states to collaborate. In light of the ATT passing in 2013, DSP re-worked its question on arms export controls in the GI 2015/16. Arms export controls and decisions, including a proper application of the ATT, were a major focus of the GI 2015/16 and featured in all five GI reports (Africa, MENA, Asia, G20, NATO and partners). Concrete recommendations for improvement were included in the policy recommendations for various states. These were newly introduced in 2015 and developed with the GI experts (assessors / peer reviewers) and local civil society, and all of them are visible online as soon as the assessment is accessed. Examples include Brazil, Canada, France, Germany, Italy, Mexico, and Turkey.

Defence industry umbrella organisations: DSP has continued to have a strong relationship with the UK’s ADS Group since the launch of the CI 2015. The team has presented to the ADS Business Ethics Steering Committee twice. During the first meeting, DSP Director Katherine Dixon met the Steering Committee and introduced the new structure of DSP. At the second meeting, DSP discussed plans for a report about reducing corruption risks around the use of agents in defence procurement. This meeting led to a number of additional meetings with individual company members of the Steering Committee. DSP also spoke at the ADS Business Ethics Forum event in November 2015, presenting on plans for the DSP Industry Integrity team and giving an update about the Government Defence Anti-Corruption Index. DSP attended the DII (Defence Industry Initiative) annual conference in June 2015 and presented on the results of the CI 2015. Katherine Dixon was invited to the IFBEC (International Forum for Business and Ethical Conduct in the Aerospace and Defence Industries) annual conference in November 2015 – a forum DSP helped to set up with Lord Robertson, a former NATO Secretary General, years ago, and which brings together the main Western defence companies to discuss anti-corruption and integrity issues. Katherine Dixon was also invited to present and take part in a panel discussion about offsets in defence procurement at the OECD Integrity Forum 2016. DSP visited Spain to strengthen links to TEDAE (Spanish Association of Defense, Aeronautics, Security and Space Technology Companies) and to the Ministry of Defence; and to introduce DSP and our work, particularly on the GI and CI. DSP also held several meetings with key defence industry stakeholders to inform the upcoming project on agents, including Avibras, Rheinmetall and AIDC Day & Zimmermann.

Output Title	Produce practical tools that can be directly applied by civil society, governments, and the defence industry so that they are better able to address defence and security corruption and have increased capacity to do so.
Output number per LF		3	Output Score	A++
Risk: [please select only one per output, using the new DFID risk definitions]		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Cumulative number of new practical tools developed by TI-DSP to address defence and security corruption.	25 (11 new) (Target: 22)	38 (13 new) (Target: 33)
Number of experts trained in defence and security anti-corruption available to civil society, industry, and governments.	55 (Target: 35)	61 (Target: 60)
Number of civil society organisations engaged by TI-DSP to build their capability in tackling defence and security corruption.	161 (Target: 95)	172 (Target: 166)

DSP practical tools are produced based on both concrete demand by DSP’s target audience and partners as well as DSP’s strategy, which is driven by gaps and needs that have been identified. DSP produced a number of new practical tools in FY 2015/16, including of course the GI (a total of 5 thematic reports with concrete recommendations and next steps) and the CI but also e.g. guidance on suspension and debarment produced for DSP by U.S. law firm Covington (pro bono); a training module for the Higher Command and Staff Course (HCSC) in Shrivenham; a one-day training course for junior officers (trialled in South Africa, also for Malian participants); a report on “Security assistance, corruption and fragile environments. Exploring the case of Mali 2001-2012”, which includes practical guidance and lessons identified; a session for a UK defence procurement business unit; possible doctrine input for the UK Land Warfare Development Centre; a report on corruption among UN Troop Contributing Countries (TCC) including guidance and recommendations on security assistance and Operational Transparency, Accountability and Counter-Corruption Training (OpTACC). The GI and the CI have been and continue to be applied by governments and companies to design and implement reform efforts, in countries such as Ghana, Tunisia or Colombia and by companies such as Finmeccanica, Hindustan Aeronautics, and Rolls-Royce. DSP has built on the initial suspension and debarment analysis to facilitate a dialogue with various legal experts in London to support implementation of the 2011 Defence and Security Procurement Contract Regulations (DSCPR) and the Public Contracts Regulations (PCR). DSP’s capacity building and training courses, including those accredited by and available at the various NATO schools (Monterrey, Oberammergau) continue to inform DSP’s strategic partnership with the UK Defence Academy on ‘Building Integrity’ in key CSSF and other HMG target countries, as well as DSP’s work on training with the Norwegian MOD and its Centre for Integrity in the Defence Sector (CIDS). The findings from Mali are of great help for DSP’s work on Yemen and other fragile states. DSP became the first civil society organisation to brief UN DPKO’s leadership course, and DPKO is planning to ask DSP to produce a detailed review of a mission on the ground to identify lessons to be learned (see also below). The OpTACC is currently being further refined by DSP’s second secondment from the UK’s 77th Brigade and is also informing DSP’s participation in (civil-)military exercises such as “Arrcade Fusion” by the ARRC in Gloucester or “Truthful Sword” by the 1 German / Netherlands Corps.

DSP was able to further add to its list of trained experts, including through ‘train the trainer’ events as part of its partnership with the UK Defence Academy. New trained experts include for example Mohammad Yousuf Zazai, the Head of Afghanistan’s Military Training Department at the National Military Academy and Zemari Shafi, its Director of Education and Curriculum Development, as well as Captain Tom Padgett from the British Army’s 77th Brigade, Colonel Raed Albdour, formerly of the Jordanian Special Forces and Colonel Hassan, also of the Jordan Armed Forces. Colonel Albdour has been also used by DSP as a senior advisor in Tunisia, where the Jordan military is an example for reform efforts the Tunisian MOD would like to emulate.

As has been emphasised, DSP’s work with partners in civil society (TI and others) is key to realising its outcomes. DSP was able in FY 2015/16 to further build the capacity of a number of civil society organisations, including Corruption Watch South Africa, Ghana Integrity Initiative (GII-TI Ghana), I Watch (TI Tunisia), TI USA, TI Armenia, the Civil Society Legislative Advocacy Centre (CISLAC) in Nigeria, TI Germany, the Flemish Peace Institute, TI Indonesia, TI Mexico and TI Malaysia. GII joined DSP for a Leadership Day delivered to senior representatives from Ghanaian defence establishments at the request of the Defence Minister. CISLAC are working closely with DSP towards the creation of a high-level steering committee within the MOD, tasked with developing an anticorruption policy and monitoring the implementation of reforms, in collaboration with the Anti-Corruption and Transparency Unit (ACTU). I Watch are leading the dialogue with the Tunisian MOD on defence reforms based on the GI assessment, drawing on DSP support as needed. DSP took part in the Carnegie Middle East Centre’s conference on renegotiating civil-military relations in Arab states in Beirut. DSP also spoke at the Open Society Foundation’s conference, which was attended by the heads of several major foundations. The aim was to inform private philanthropy’s approach on work on defence and security issues.

Output Title	Policy makers and international organisations worldwide (including UN, AU, African Development Bank, World Bank, EU, and NATO) influenced to address the danger of defence and security corruption as a prominent issue on their agenda.
Output number per LF		4	Output Score	A+
Risk: [please select only one per output, using the new DFID risk definitions]		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of international organisations TI-DSP is actively working with to convince them to initiate defence integrity building or countercorruption initiatives.	24 (Target: 17)	30 (Target: 27)
Number of high-level decision makers in international organisations TI-DSP is engaged with who acknowledge the importance of tackling defence/security corruption.	76 (Target: 70)	84 (Target: 81)

DSP continued to engage international organisations and high-level decision makers within them, including (but not limited to) the following: UN DPKO’s Senior Leaders Course as well as the UN Undersecretary General for Field Services and the Peacebuilding Support Unit, the 1 German / Netherland Corps, NATO JFC Naples as well as NATO’s Partnerships and Cooperative Security Committee (PCSC) who were briefed on DSP’s thoughts for NATO’s upcoming “Building Integrity” (BI) policy, the UN Expert Independent Review Panel on the response of the UN to allegations of sexual exploitation and abuse in the Central African Republic, UNODC Regional Office in Eastern Africa, the World Bank, the African Peace Training Support Association, the OECD’s SDG team, and the EU’s Human Rights, Gender, and Democratic Governance Unit. DSP became the first civil society organisation to brief UN DPKO’s leadership course, and DPKO is planning to ask DSP to produce a detailed review of a mission on the ground to identify lessons to be learned.

DSP sent a coordinated TI submission to the EU on its global strategy on Foreign and Security Policy, highlighting the need to address the relationship between corruption and conflict and instability; acknowledge the risk to global security posed by trends of growing military expenditure with a lack of transparency and accountability from emerging powers; and consider actions to reduce corruption, bribery and illicit financial flows as signatories to the UN Sustainable Development Goals. DSP also gave a presentation on SSR lessons at an EEAS expert seminar convened as part of their attempt to produce an EU-wide Strategic Framework for supporting SSR.

DSP launched the GI NATO report in Brussels, organised by the Flemish Peace Institute and attended by representatives of NATO delegations (Poland, Hungary), think-tanks, and academia. The Belgian Ambassador to NATO, François de Kerchove d’Exaerde, opened the event. A senior NATO BI representative from the Headquarter delivered a speech which very much stressed the overlap between DSP findings and recommendations and NATO’s focus on building integrity, as well as the constructive complimentary relationship between DSP and NATO tools. Following the NATO 2016 Summit in Warsaw, DSP is now working closely with a number of member states, particularly the BI lead nations, to provide guidance for the practical implementation of NATO’s new BI policy both at the national level and across the alliance.

At the “International Anti-Corruption Conference” (IACC) in Malaysia, DSP ran a joint session with the U.S. State Department on “Fighting corruption in the security and defence sector”. The session started with a panel featuring DSP and TI Russia. This was followed by breakout sessions, each revolving around a specific problem statement organised along DSP’s GI typology’s risk areas and led by TI national chapters: Political (Honduras and Tunisia), Personnel (South Africa), Operations (Germany), Procurement (Malaysia). Following this, the U.S. State Department and Department of Defense became a main driver alongside DSP for the security focus of the Anti-Corruption Summit in London. A DSP dinner on security which was very much endorsed and supported by John Kerry’s office and hosted by U.S. Under Secretary Sarah Sewall. The dinner featured e.g. General Sir Nick Carter, the UK Chief of General Staff; Vice Admiral Frank Pandolfe, Assistant to the Chairman of the Joint Chiefs of Staff at the U.S. Department of Defense; Paul Arkwright, UK High Commissioner to Nigeria; Brigadier Alastair Aitkin, Commander of the UK’s 77th Brigade; Ikram Afzali, Executive Director of Integrity Watch Afghanistan, and Akaash Maharaj, CEO of the Global Organization of Parliamentarians Against Corruption (GOPAC).

Modest indicator increases reflect DSP’s already existing and strong relationships with various international organisations and key decision makers, which of course continue.

Key Points - Summary of progress in Year 5 (1 page max)

In Year 5 of the PPA, DSP has met if not outperformed against the vast majority of its targets – both at the outcome as well as at the output level.

Key achievements (outlined in more detail under “A”) included the launches of the CI 2015 as well as the GI 2015/16 and the reform efforts that were driven by them. These included not only various defence companies that made significant improvements to their systems but also governments ranging from Nigeria and Afghanistan to Ghana, Ukraine, Tunisia, and South Africa. DSP very much welcomed the introduction of the SDGs and continues to work on making sure that SDG #16 is realised properly, based on measurable indicators which take into account that the failure to tackle security issues is one of the biggest barriers to development, particularly in the world’s least developed states. DSP therefore continues to feed into global as well as national conversations on determining useful indicators, such as those it was invited to join by the OECD and UNDP.

DSP also continued to work closely with various militaries, be it to build their anti-corruption capacity and deliver training or to help them include anti-corruption into their doctrine, planning, and exercises. DSP welcomed another round of military secondments, e.g. from Afghanistan, Jordan, and the UK’s 77th Brigade. DSP continued to work closely with DFID and others in HMG on a number of important issues such as the London Anti-Corruption Summit and the SDSR. The theme of corruption causing instability and insecurity remains prominent.

DSP has been building on MEKANIC and has been tailoring it to its new strategy to ensure it fits DSP’s needs in 2016. MEKANIC is now lead by each of the three new DSP teams (Accountable Defence Sectors, Conflict and Insecurity, Industry Integrity). Based on the experience of 16 MEKANIC meetings a decision has been made to combine some of the more recent elements that have been particularly helpful, such as individual team members each facilitating a dedicated session, with some of the early foundations when MEKANIC meetings were first developed, such as limiting the time to roughly half a day and keeping the group size at a level that allows for everyone to contribute substantially, meaning that they benefit properly from attending the meeting and DSP benefits properly from their expertise and experience. The International NGO Training and Research Centre asked DSP to produce a ‘praxis note’ to enable others in the sector to learn from MEKANIC. This praxis note identifies some of the main MEKANIC benefits (meetings and beyond) in more detail. Both MEKANIC as well as DSP’s new strategy of course heavily draw on lessons identified, as do the GI and the CI which were both launched in their second iteration. [Please also see the comment above in the Output section (“C”) on the indicator relating to oversight over the Afghan security forces and the lesson DSP has identified from this particular indicator.]

DSP and TI-UK overall continue to monitor and mitigate the relevant risks, striving to improve existing systems e.g. on travel risks. Sustainable funding remains a priority for the Board as well as the operational staff.

Summary of responses to issues raised in the previous Annual Review (where relevant)

Following consultations with various stakeholders and experts from all relevant backgrounds (including e.g. governments, defence companies, civil society, and donors) DSP was pleased to launch its new 2015-2018 strategy. One key feature of the strategy is a very clear sense of where deeper engagement should take place and can have the most impact.

Consultations on future iterations of the GI and CI to maximise their usefulness and impact are underway. TI-UK as a whole now has both a Director of Finance, Resources and HR as well as a dedicated HR Manager, which has already resulted in performance and capacity management systems improving. DSP has been holding off on purchasing tracking software, as the merits of different options are currently being assessed for all of TI-UK (thus facilitating cost savings and VFM for all involved).

“Building Integrity” course delivery has been and continues to be reviewed, which is already reflected in new training material and new training experts who have been identified. DSP has further increased participation in selected workshops and has been re-developing its framework for TI National Chapters and other partners. One major new tool is a “Chapter Fund” that has been set up and is being piloted for the former.

DSP continues to work closely with DFID, including of course CHASE and also the FACT team. Follow-up work and collaboration after the London Anti-Corruption Summit are currently being discussed.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (5 pages maximum)

Key cost drivers (maximum of 5 key cost drivers per key cost)

DSP of course continues to be very much committed to Value for Money, which forms a key part of its overall mission to increase transparency and accountability. The key cost drivers are (a) expert staff, (b) project costs, (c) senior advisors, (d) travel and (e) office space and printing. The organisation has been successful at keeping costs low with optimal results. It continues to apply the same policies and procedures supporting VfM which, under ‘economy’, ‘efficiency’ and ‘effectiveness’, were described in a 2012 independent PPA evaluation on VfM as ‘excellent’.

Key costs / List the key costs of the organisation e.g. staff, transport. It would also be helpful to state whether these are fixed or variable costs.	% total budget (FY15/16) / NB this is not expected to add up to 100% as we have asked for ‘key costs’ rather than all costs.	Cost drivers / (factors that influence key costs e.g. project location, inflation. State whether there has been any change in them that has pushed up costs and whether any identified trigger points have been reached.)	Actions to manage key costs / Summarise what the organisation has done to manage the cost drivers (where this has been possible) and whether this was successful or not. DFID accepts that not all will be possible to manage, so if not please state this.
Salary	55%	DSP has 15 full-time staff. There is a good gender balance across the staff, with the current Director also being female.	In an effort to keep costs down, salaries are kept at median rates. The organisation has also augmented its staff with secondees from governments (typically two at any one time), and by engaging research students who are keen to do their thesis or dissertation on a subject that is relevant to DSP.
Project costs	8%	DSP is happy that project costs constitute its second biggest cost driver, ensuring that its staff’s special skills contribute directly to realising DSP’s outcomes and overall impact.	Projects are always planned with VFM in mind, and DSP actively encourages others to take forward work locally and to own it, which creates both sustainability and saves costs.
Senior advisors	7%	One of DSP’s approaches to staff development is to pair younger professionals with a highly experienced senior person such as former Ambassadors, Permanent Secretaries, and Senior Defence Leaders in each area of its work.	This approach would be prohibitively expensive if DSP were to pay anywhere near market rates, which range from £1000 per day for public sector work to £2000 for private sector work. This also provides valuable training and mentoring which would otherwise be very expensive. DSP’s rate continues to be approximately £250 per day. Both Senior Advisers and full-staff staff are encouraged to travel at home and abroad with an appropriate number and selection of publications which, at various meetings, conferences and working group discussions, helps maximise the impact of their work.
Travel	6%	Work on anti-corruption activities requires significant face-to-face contact.	DSP has continued to rely on budget airlines, programmed travel during the less expensive times, and searched for the best possible hotel deals. Records also show evidence of DSP staff travelling to multiple locations to synergise across a number of in-country engagements. It also uses local chapters and partners to provide administrative, financial, and logistical support in-country. This reduces preparatory time, reduces costs and results in efficiencies, ensuring that the time spent by experts on the ground is used wisely. Partners are also encouraged to lead on the processing of feedback on training and to provide follow-up reports on training requirements, or the need for revised approaches and curricula. The contribution made by local partners also supports immediate follow-up with in-country DSP stakeholders. This is particularly important when multi-country trips are taken by staff.
Office space and printing	5%	Office space including desks, meeting room. Printing publications as well as training material, leaflets.	DSP continued tracking the unit printing costs this year, and getting quotes for bulk printing. Overall, this has enabled a significant reduction (close to 25%) of costs from previous years over the PPA extension. DSP is based at Community Action Network (CAN) Mezzanine which solely offers office spaces for charities and at reduced rates. The use of existing (and leftover) training material which was used again for similar training programmes also contributed to reduced printing costs.

VfM performance

	How have you assessed VfM in this area? What measures have you used? State whether this has been measured as part of the enhanced VfM offer or since the beginning of the programme.	Performance in this area (if possible, compare performance over the life cycle of the programme).
Economy –whether organisation has bought inputs of the appropriate quality at the right price?	DSP has been comparing prices and agreeing bulk purchases, including through pooled procurement. The long term contractual arrangement of the PPA was very helpful in this regard. The introduction of a dedicated Finance and HR Director for all of TI-UK as well as an HR mananger were further helpful recent developments. As of 2016, TI-UK has access to a specialist travel agency, offering reduced deals.	The costs for printing, design, and travel have gradually been declining.
Efficiency- how well organisation is converting inputs into outputs? (‘Spending well’)	Publication distribution is constantly reviewed, including digital vs. hard copies. Practical tools are disseminated through a diverse range of channels – (very) interactive websites, social media etc. A key element of DSP’s approach for impact is to feed into existing capacity building, training, doctrine etc.	Continuous improvements, also regarding multiplier effects that utilise partners and other actors have led to sustainability and more impact because ownership is less dependent on DSP.
Effectiveness- how well the outputs produced have had the intended effect/ achieved the outcome? (‘Spending wisely’)	The GI and the CI have led to substantial government and private sector reform. Each of them are used by ‘the other’, i.e. the GI by companies and vice versa, plus professional service firms. DSP continues to train the trainers, with multiple training partners such as UKDA, CIDS, and NATO. DSP together with Lord Robertson helped to create IFBEC years ago, which is now fully owned and run by the defence industry.	The have been continuous improvements, and more relationships of a more sustainable nature have led to more multiplication.
If appropriate, please provide details of other ways in which you have assessed VfM that do not sit within the 3 ‘Es’ set out above	DSP’s commitment to value for money supports its VfM proposition in the original business case, which has been sustained throughout the PPA partnership period. It has continued to apply ongoing scrutiny to its VfM procedures and, where possible, has ‘scaled-up’ these efforts in view of new products, services and policy communities. The organisation defines value for money as ‘ensuring that maximum quality outcome is achieved for every resource spent’. It includes the 3 Es of economy, effectiveness and efficiency in this definition. In each strategic planning meeting (board meetings, MEKANIC, management meetings, etc.).	DSP always ensures that two central themes are discussed by way of incorporating VfM into its planning. These themes include: 1) what the organisation is learning about which interventions / approaches are effective and 2) how it might implement these interventions in an efficient and economical way.

VfM Good practice over the lifetime of the PPA programme

Briefly - what are the top 3 VfM good practices that your organisation has implemented to maximise VfM? (this should cover the lifetime of the PPA)	Please give an example of this good practice being used and the impact it had. If there were any VfM savings please state what they were.
One of DSP’s approaches to staff development is to pair younger professionals with a highly experienced senior person such as former Ambassadors, Permanent Secretaries, and Senior Defence Leaders in each area of its work.	This approach would be prohibitively expensive if DSP were to pay anywhere near market rates, which range from £1000 per day for public sector work to £2000 for private sector work. This also provides valuable training and mentoring which would otherwise be very expensive. DSP’s rate continues to be approximately £250 per day. Both Senior Advisers and full-staff staff are encouraged to travel at home and abroad with an appropriate number and selection of publications which, at various meetings, conferences and working group discussions, helps maximise the impact of their work.
The second iterations of the GI and the CI have both been launched using website with increased interactive opportunities, presenting the wealth of data in multiple ways that cater to the needs of different audiences. This has helped to significantly increase the reach of the GI and the CI, as well as the pick up for both.	The improved and more interactive websites have meant that the need to print hard copies has decreased. It has also led to extensive pick up in regions of the world which TI-DSP would be unlikely to reach with hard copy distributions, such as Egypt. It has also further facilitated the trend of companies using the GI and governments factoring in the results of the CI, e.g. when making procurement decisions, while professional service firm have both indices available at their fingertips. The websites are also ideal to – not least in the spirit of transparency and constructive collaboration – publish statements made by governments and companies alongside the TI research.
DSP’s training and capacity building partnerships, particularly with the UK Defence Academy (UDKA) but also with the Centre for Integrity in the Defence Sector in Norway (CIDS) and with NATO, have been excellent multipliers for DSP’s knowledge and practical tools and have created sustainable progress.	Working with partners and large training organisations has helped DSP to develop specific training material that is now accredited and available in the public domain for everyone to use, at minimum costs as compared to DSP developing this on its own. ‘Piggy backing’ on existing courses also reduces costs and creates sustainability, as does training the trainers who are then available to the world at large, with guaranteed standards of quality and delivery in place.

VfM learning (1 para max)

Please see the section above.

DSP continues to try to learn from its VfM experience, which has e.g. led to the following actions being taken:

- Integration of VfM considerations in the agenda of management group meetings, when a strategic decision has to be taken.
- Revision of the project development process.
- Stronger focus on learning in staff meetings, as part of DSP’s MEKANIC approach.
- A travel agency is now available for all of TI-UK, which has led to further savings and offers otherwise not available, financed by DSP and the other elements of TI-UK.
- Human resources management processes have been improved, with a dedicated HR manager now in place (again financed by and for TI-UK as a whole).
- The risk management framework and risk register continue to be revised.
- A professional development system (development within the grade) has been implemented.

Quality of financial management during programme (1 para max)

TI-UK has a robust financial management system. Detailed budgets and business plans are prepared annually. Project expenditures are then monitored on a monthly basis by project managers and any variances are carefully reviewed and investigated. All financial and narrative reporting requirements of DSP’s funding partners are adhered to. It is audited on an annual basis, and all audit recommendations have been, and will continue to be, implemented. All annual financial and audit reports can be found on the TI-UK website.

Assessment of whether programme represented good Value for Money (1 page)

a) Reflection of VfM performance over the lifetime of the programme (1 para max)

DSP continues to represent strong value for money. As outlined above, the programme is both economical in terms of the cost of key inputs such as office space and printing are adequately controlled and minimised. The programme is also efficient as the cost for hiring and retaining the high quality staff and senior advisors responsible for converting inputs into outputs is managed effectively. Lastly, based on the way in which DSP innovates, and takes risks in order to reach its key objectives, the programme is effective. As reducing corruption in defence and security is ‘uncharted territory’, the organisation’s approach is to test several approaches simultaneously, rapidly discarding the less optimal approaches and scaling up the most optimal. The PPA structure enables the freedom to take this experimental approach. The PPA funding also communicates an element of confidence for other donors considering providing DSP with strategic or programme/project funding.

b) Assessment of progress against enhanced VfM offer

Value for Money steps

Economy
TI-UK has developed a ‘Governance and Procedures’ manual that has a VfM concern weaved throughout. This helps to ensure that key cost drivers are effectively managed and ‘economy’ is developed, enhanced and deepened.

DSP also pairs up young professionals with highly experienced senior persons, for example former Ambassadors and Generals, who it attracts through the high quality of its work, its access, and its impact. This would be prohibitively expensive if DSP was to pay anywhere near market rates, which range from £1000 per day for public sector work to £2000 for private sector work for individuals with such experience. DSP’s rate is £250 per day.

Efficiency
In addition to the above, TI-UK is fine-tuning its management process, ensuring that it optimally converts activities to outputs. The work of a taskforce that has been identified across the organisation has further been enhancing efficiency.

Effectiveness
DSP has also been improving its Monitoring, Evaluation and Learning (MEL) system to help achieve the organisation’s strategic objectives. Two additional colleagues are now involved in MEL. DSP has re-evaluated and re-assigned performance indicators to relevant project officers and project/programme leads, enabling us to better capture data.

In addition, DSP is building on MEKANIC, its key MEL mechanism. It uses its monitoring and evaluation (M&E) for learning and strategic decision making, and to inspire new ideas and projects. These strategic decisions lead to projects which are monitored and evaluated, forming a virtuous cycle.

Measuring VfM
DSP remains very interested in trying to establish the VfM of a particular intervention in a particular location, with DFID CHASE economists and policy leads. This was highlighted in past feedback from DFID, pending DFID CHASE capacity. This measure would enable us not only to evaluate the effectiveness of our VfM approach, giving us an opportunity for improvement, but will also enable DSP to share lessons with other partners in civil society.

Date of last narrative financial report	1 June 2016
Date of last audited annual statement	21 October 2015

E: RISK

Quality of risk management over the life of the programme

For this programme, risks include (1) DSP chooses countries where corruption is so deeply entrenched that it becomes difficult to make visible progress (2) based on the number of countries that DSP could engage in, and the high number of countries and companies involved in both the GI and CI, the organisation spreads itself too thinly (3) a recent and significant growth in business activity cannot be supported by current organisational policy and structures, and (4) engagement in (post) conflict states such as Afghanistan pose a significant risk to the lives of team members.
These risks are mitigated through (1) enhanced research and analysis capacity which, together with the support of senior advisers, supports the thorough evaluation of target countries before planning any intervention (2) being strategic about where the organisation engages and having a future commitment to clarifying how DSP should engage more ‘deeply’ with a limited number of countries; in addition, further conceptual clarity on how flagship products, such as the CI and GI, will be supported in the future will also mitigate against the risk of being spread too thinly as a result of two major programme commitments (3) by investing in a more robust management structure, and by having introduced a new strategic plan in 2015, the organisation is developing appropriate policies, structures and systems to support organisational growth (4) travelling as safely as possible, e.g. with NATO / the UK military in Afghanistan, having adequate travel insurances and working closely with those on the ground where DSP intervenes. DSP has also introduced an improved travel risk assessment system and requires staff travelling to higher risk regions to undertake hostile environment training. DSP has further strengthened its relationship with the Global Security Manager at TI-S, who shares frequent relevant country updates and alerts with the relevant DSP managers and staff. This includes not only high-risk destinations but also countries such as Ghana or Indonesia. While DSP of course remains keen to have an impact also in those countries that are most heavily hit by conflict and fragility, DSP did decide to turn down a potential engagement in Somalia as it felt that the security of staff in this instance could not be guaranteed as much as would have been necessary.
TI-UK has an organisation-wide Risk Register that is regularly reviewed and updated by the senior management team. Strategic risks are reviewed by the Board of Trustees, and further scrutinised in detail by the Finance and Audit committee on a quarterly basis. DSP completed and submitted the Overseas Security and Justice Assistance assessment form, which indicates that the programme carries minimal risk of spending DFID funds in activities or interactions with actors that could raise human rights concerns. Whilst potential human rights abuses in DSP’s countries of engagement have been identified, the organisation mitigates against these risks by following a general ‘TI approach to human rights risk’ procedure and good practice. The risk of human rights abuse is also mitigated through the due diligence efforts which are supported by local chapters and in-country partner organisations.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

Funding and all associated activities have been completed within the expected timescales.

Two of the targets agreed with DFID in the results framework until 31 December 2016 were already met by 31 March 2016, focused on additional funding sources and implementing the recommendations made in the DFID CHASE Annual Report for FY 2014/15. Baselines have been revised and targets increased accordingly. DSP also met if not exceeded all its planned milestones for FY 2015/16, as per the overview above. This follows last year’s Annual Review, which, without requesting additional funding, recommended that all but one of the agreed upon targets for the end of 2015/2016 be revised upwards. As a result of this recommendation, DSP has been delivering more than what was agreed upon for the same amount of money and time.

Performance of partnership (s)

The majority of DSP’s support to capacity-building, research, policy development and international influence is based on strong partnerships with both government and non-governmental organisations. DSP has for the first time ever provided support to partners via the “Chapter Fund”, for which only accredited TI National Chapters are eligible. The organisation is totally independent in how it manages its day-to-day operations. DSP collects feedback from its partners and, through monitoring, review and learning mechanisms such as MEKANIC, involves partners in internal strategic planning. For example, DSP has developed excellent partnerships with the Centre for Integrity in the Defence Sector (CIDS) in Norway and with the UK Defence Academy. It has jointly delivered Building Integrity (BI) training in a wide range of countries with them this year. Similarly, DSP partners with international and regional organisations such as the UN, NATO, and the African Union. The benefits of this partnership include achieving goals through support to strategic partner organisations, knowledge transfer and sustainability. DSP also enjoys a good relationship with DFID, particularly at the head office level. Closer interaction with in-country UK Defence Attachés has been facilitating wider cross-HMG knowledge of DSP’s global work.

Asset monitoring and control

Assets are monitored and controlled appropriately. There are no outstanding issues.

TI-UK manages assets through a system of asset monitoring and control. This responsibility lies with the department led by TI-UK’s Finance and Resources Director. The organisation has a Fixed Assets Register that is updated annually. Regular and on-the-spot asset checks and controls are undertaken by TI-UK’s Office Administrator. The system is revised and updated regularly, based on the quarterly meetings of the Finance and Audit Committee, to ensure that it follows best practice in asset monitoring and control.
G: CONDITIONALITY

Partnership principles assessment

Not relevant to PPA funding.

H: MONITORING & EVALUATION

Evidence and evaluation
DSP's ability to stimulate anti-corruption reforms depends on it effective, efficient and consistent delivery of programme results. For this reason, the organisation places significant emphasis on monitoring, evaluation and learning (MEL). As part of the 2015 change in leadership, an extensive review was initiated. This exercise involved the review of key internal documents and consultation with a range of organisational stakeholders. Findings from the review have impacted on the theory of change of DSP as a whole, how it is structured, and where/how the organisation works. Three new dedicated teams have been introduced: Accountable Defence Sectors, Conflict and Insecurity, and Industry Integrity. While of course functioning complimentarily, these three teams each work towards their distinct objectives, have their own MEL in place, and – perhaps most importantly – have a dedicated manager facilitating thematic development as well as that of staff in each of these important DSP areas.

DSP was also one of the organisations that was chosen to participate in the DFID fund-level evaluation last year. As such, Coffey undertook an evaluation of its work and, within the context of wider strategic discussions, Coffey staff notified DSP and stated that their own organisation was now seeking to learn from DSP and adopt a MEKANIC-like process to support their own advocacy projects.

MEKANIC meetings are ‘learning’ events run as needed by all three DSP teams (Accountable Defence Sector, Conflict & Insecurity, Industry Integrity) and which bring together key stakeholders who play an important role in the defence and security sector. The acronym MEKANIC stands for: Monitoring, Evaluation, Knowledge – Understanding and sense-making, Affirmation, Building Effective Networks, Influencing and Theory of Change. MEKANIC has been widely recognised as good practice within the Monitoring, Evaluation and Learning community. For example, DSP was asked to prepare a briefing note for The International NGO Research and Training Centre’s (INTRAC) website in order to enable other civil society organisations to learn from it.

DSP has also conducted external research into defence and security reforms in both Poland (deemed a powerful example by states in transition globally) and Honduras, and recently into the impact of the GI 2015 as well as training delivered to participants at the Colonel-level (via in-depth phone follow-up with participants from various years). These initiatives form part of DSP’s ‘learning’ that inform its strategy and theory of change, and help others (i.e. governments and civil society organisations) to learn from them.

Monitoring progress throughout the programme
DSP collects data for monitoring and review purposes on an on-going basis. Output and outcome indicators, as well as corresponding evidence, are assigned to teams, as well as project and programme leads responsible for documenting progress. The project and programme leads report to the MEL officer every quarter. The MEL officer then collates these notes and produces a quarterly monitoring report (also informed by the DFID CHASE PPA) that is shared with management and the TI-UK Board and which also forms part of the pre-reading material for each MEKANIC meeting. The data and analysis supporting MEL is fed both internally and externally through different documents which are tailored for the requirements of each recipient group. The cumulative approach taken to the development of quarterly reports ensures that updated and peer-reviewed (through the MEKANIC process) data is prepared for the timely publication of DSP’s annual reports.

The organisation uses a series of follow-up forms/questionnaires that are distributed to and completed by course and secondment participants. Feedback received has been carefully reviewed and, where required and appropriate, course materials and teaching methods have been updated throughout the course of the year. Exit interviews are also used for both secondees and research interns.

## I: TRANSPARENCY

Assessment of progress against enhanced Transparency offer

Transparency steps

DSP remains highly committed to the maximum levels of transparency both in terms of what it demands from governments, companies, and civil society and regarding its own data, information, policies, etc.

Producing programme data and making it publically available
DSP continues to improve the quality of the data it has available and can thus share with others. DSP has e.g. been developing a series of follow-up forms to be completed by course participants and secondments. These accompany interviews as a practical component of a wider new M&E strategy for DSP’s capacity building, e.g. for in-depth telephone follow-up with Colonel-level participants from different courses (over multiple years) and different regions of the world.

Making financial information public
In addition to enhancing transparency in our programme work, we are also enhancing the transparency of our financial information. DSP as part of TI-UK adheres to the highest standards of financial transparency. The TI-UK website contains key information, including extensive annual financial and audit reports that enable anyone to see how we utilise our financial resources.

TI-UK has invested in a full-time book keeper, its first ever Director of Finance, Resources and HR and an HR manager. These measures will further strengthen TI-UK internal systems, including its financial system, and improving the quality of the data we make available on our website.

Enhancing transparency with others
TI-UK, including DSP, constantly works with partners to implement the transparency agenda. One recent example includes engagement with BOND on how best to measure UK NGO transparency, and providing advice based on the very extensive methodological experience that TI including DSP has to offer.

Additionally, TI-UK has recently embarked on two new transparency projects:

TI global Pharmaceuticals and Healthcare Programme (PHP) – successfully piloted according to the DSP model and now up and running.

1. TI-UK joined the TACOD project funded by the European Union. This project seeks to promote open data as a tool to detect and prevent corruption. TI-UK focused on the impact aspect of this analysis:
  1. Case study analysis (Freedom of Information and Open Data)
  2. Impact of open data - using positive and negative case studies of the use of open information to address corruption
  3. Identifying the significance of the open information
  4. Identifying enhancements in open data laws, regulations and approaches to facilitate greater anti-corruption outcomes

## J: Disability

TI-UK is an equal opportunity employer. Its ‘Governance and Procedures Manual’ stipulates that the organisation does not discriminate based on anything other than merit in employment, including disability. In addition, the manual states that TI-UK staff will treat each other and those that they work with respectfully and with due consideration for such things as disability. Equality is a key value that TI-UK cultivates and abides by.

In terms of programme activities, DSP attempts to mainstream disability as much as possible, despite some anticipated challenges of working at the global policy level. As a member of the global “Control Arms” coalition, DSP is proud to work towards a more responsible and more transparent arms trade alongside a number of outstanding organisations that focus fully on disability, but also on the rights of victims and victim assistance. These include for example Action on Armed Violence, the Alliance for Peace and Disability Rights, the Transitions Foundation of Guatemala or the Réseau d’Actions Paisibles des Anciens combattants pour le Développement Intégré de tous au Burundi (RAPACODIBU) – all of them having worked towards a robust UN Arms Trade Treaty alongside Oxfam, Amnesty, Saferworld, DSP and others, and now advocating and offering practical tools for an ambitious and effective implementation of the ATT.

DSP has veterans among its staff and senior advisors.

Corruption is obviously not the sole but one important driver of conflict and violent extremism, as e.g. evidence from the International Crisis Group (on Boko Haram in Nigeria) and a study commissioned by DFID on why local men join the Taliban in Afghanistan demonstrate. 15 of the bottom 20 of TI’s Corruption Perceptions Index (CPI) 2014 were fragile and conflict states. Corruption creates frustrated, disaffected populations. As a recent study by the Institute for Peace and Economics on “tipping points” demonstrated, a small increase in corruption can translate into a large increase in the following: political terror, political instability, violent crime rates, violent demonstrations, organised crime, access to small arms and light weapons, homicide rates, and level of perceived criminality. All of these are major factors that lead to disabilities, with the poor and marginalised often being the most likely victims.

Even before conflict breaks out, good governance can be a key mechanism to ensure that disabled individuals and groups are represented and have a voice when political decisions are being made. During conflict, more professionalised militaries with robust rules of engagements (and codes of conduct) are less likely to use tactics that are particularly prone to result in civilians becoming disabled – indiscriminate approaches, as well as of course e.g. intentionally maiming people. Responsible defence governance and accountable defence establishments are important in this regard.

Post-conflict, security sector reform (SSR) efforts need to ensure that people with disabilities receive the support they need, as well as the representation they are entitled to. This is difficult if SSR is undermined by corruption – which is too often the case, not least in light of the CPI reference cited above.

## K: ADDITIONAL UPDATES (OPTIONAL SECTION) (1 page)

As per the original business case in 2012, DFID CHASE funds DSP e.g. to support countries do develop defence integrity and anti-corruption programmes, with a particular focus on conflict or unstable environments; to develop practical tools enable governments, companies and civil society to address defence and security corruption; and to support international organisations to deliver integrity or anti-corruption initiatives.

The failure to tackle security issues is one of the biggest barriers to development, particularly in the world’s least developed states. Conflict-affected countries are among those who performed the worst under the MDGs, with few states hitting even one of the 21 targets. Including corruption in SDG16 was vital to ensuring these states do not get left behind again. Given the links between corruption and insecurity, tackling defence sector corruption, improving trust in the armed forces, and disrupting organised criminal networks is essential.

A lack of accountability, poor governance and corruption in the security sector undermines government legitimacy, weakens democratic institutions, stalls economic and human development, and increases fragility and instability. It disenfranchises populations, enables arms to flow into conflict environments, and empowers corrupt leaders to abuse populations with impunity. The defence and security sector accounts for large portions of national budgets - USD 1.6 trillion in 2014; it is highly technical; and often highly secretive. It is thus fertile ground for corruption. Little progress will be made towards human development and democracy without tackling the abuse of power within defence institutions.

DSP strives for a world where transparent defence institutions serve open governments that are accountable to ordinary people; and where defence institutions’ primary purpose is the protection of all citizens. Only under these conditions can it be ensured that no one is left left behind, and that the poorest of the poor and those people who are most excluded and at risk of violence and discrimination are not denied the opportunity to realise their full potential or to share in progress.

DSP’s Government Defence Anti-Corruption Index (GI) is its most powerful tool in triggering dialogue on institutional reform, and has led to practical change in several countries. In 2015/16, DSP persuaded around half of the 120 governments analysed to review our assessment before publishing, with around a third ultimately engaging in substantive dialogue.

DSP institutional risk assessments can be inverted into an anti-corruption action plan and drive reform efforts, e.g. in Georgia in 2013. Globally many CSOs are using the results to engage in dialogue with MODs, e.g. in Tunisia, Ghana, and South Africa (see above).

DSP runs a high impact capacity building programme which combines formal training for defence forces, leadership days, secondments, and support in developing anti-corruption action plans – often in partnership with the UK Defence Academy. In the last year DSP hosted secondees from e.g. Afghanistan, Ukraine, and Jordan. Secondments are one of DSP’s most successful interventions. A former secondee from internal audit in the Ukrainian MOD is now at the centre of defence reform efforts, alongside the training centre DSP helped to establish within the ministry.

DSP works with the UN on peacekeeping. It was the first NGO to be invited to train the Department for Peacekeeping Operation’s (DPKO) leadership team. DPKO have agreed in principle to allow DSP to act as a monitor for a peacekeeping mission to assess what more is needed to be done.

DSP also work closely with NATO on the Building Integrity (BI) policy – indeed it was DSP that was the catalyst for NATO’s BI programme. Once the policy has been approved in Warsaw, DSP will be looking at how to ensure it is turned into a decent action plan. DSP will be working closely with SHAPE and other NATO institutions, including in developing NATO’s BI curriculum and shaping training content and exercises.

Alongside the above, DSP is leading policy thinking on corruption and conflict. For example, billions of dollars are going into security assistance programmes mainly driven by militaries, which are at risk of fuelling the problem they are trying to solve. In Yemen, over half of USD 1billion military assistance is unaccounted for and some has ended up straight in the hands of the Houthis. DSP has developed best practice guidance to help militaries and policy makers tackle these corruption risks. DSP has also published lessons identified from Afghanistan and Mali.

## L: Evidence Table (1 page maximum)

“Transparency International offers valuable lessons for the BI [Building Integrity] discipline and contributes tremendously to the effort to understand and address corruption in a preventative manner. We very much appreciate your support to the BI Programme and your valuable contribution […]. My staff and I look forward to our ongoing collaboration.”
(Letter to DSP from Terry Stamatopoulos, NATO Assistant Secretary General for Political Affairs and Security Policy, 2 April 2015)
“As you note, in the UK work is underway on our Strategic Defence and Security Review (SDSR). The SDSR will consider how we can enhance our efforts to tackle corruption in the area and ensure we take account of the role of corruption when setting out how the UK should promote democracy, security and prosperity in fragile countries and regions overseas.”
(Letter to TI-UK from The Rt Hon David Cameron MP, Prime Minister, 17 July 2015)
“I am Captain Sekou Elhadj Alousseni from Mali, […] who attended the International Security Course in Cape Town. I really would like to thank you very sincerely, your lecture was very instructive, educative and very interesting [and] well understood. It is also broadened our knowledge […] [T]hank you again hoping that we are going to keep in touch forever.”
(Capt DIAKITE, 33rd Airborne Regiment, Mali, in charge of training and education, 1 July 2015)
“I read this chapter and wished aloud that I had this knowledge before my first rotation to Iraq in 2004. I worked at a member of an Advisory Support Team training one of the first Regular Iraqi Army Battalions and made nearly every mistake possible. Clearly the authors have previous experience building partner capacity. As I read each item to consider regarding host nation security forces and corruption, I literally shouted aloud, “Yes!” as I saw in print a list of all the things I failed to consider back in 2004.”
(Fletcher Security Review of DSP corruption on operations handbook, http://tinyurl.com/zqz27cx)
“One way in which we may be able to support you would be through our Supplier Mentoring Program, in which one of our trained Ethics Officers would work with you, specifically addressing the key components of an anti-corruption program as assessed by TI-UK”.
(Lockheed Martin communication to its suppliers, 2015)
““We express our appreciation [to] Transparency International for such establishment of compliance program. Your report to the assessment on the Anti-Corruption is motivated to improve our compliance program and is helpful to build the compliance system (particularly your questions on assessment paper were good guideline for us to upgrade the compliance program).”
(Poongsan Cooperation communication with TI-DSP)
“The South African National Defence Union (Sandu) says it is demoralising for soldiers to serve in the South African National Defence Force (SANDF) when senior officials are getting away with corruption and incompetence and are receiving political protection and appointments.
 Pikkie Greeff, Sandu National Secretary, made the comments at a recent Transparency International Defence Anti-Corruption in South Africa Civil Society Workshop in Johannesburg.”
[DefenceWeb, “Corruption in SANDF demoralising soldiers – Sandu”, 18 June 2015, http://tiny.cc/zvnf4x]

[Please note that DSP has an extensive scrapbook collection and is more than happy to share additional content.[21]]
[21] This also includes media coverage, see e.g.: Aryn Baker, “Corruption in Military Defense Spending Could Be Behind Rise in Africa Terror Attacks”, Time Magazine, 18 January 2016 (http://tinyurl.com/gprtnm7). Pete Guest, “Ghost Soldiers And Overpriced Jets: How The Arms Industry Fuels Corruption”, Forbes, 19 January 2016 (http://tinyurl.com/hq9tspd). Rick Gladstone, “Armies Used by U.N. Fail Watchdog Group’s Test”, New York Times, 3 April 2016 (http://tinyurl.com/j75sr2r).
## M: Summary Sheet of each Annual Review (Years 1-4) (maximum 1 page per year)

## This section should be used to provide a short summary of progress (and any follow up actions) from Years 1 to 4 of the PPA. This section should complement the information provided at Section A.

Year 1

Year 1 of the CHASE PPA saw a major focus on the United Nations Arms Trade Treaty (ATT) negotiations, with DSP engaging 33 states and working closely with ‘progressive’ states at the second and third ATT Preparatory Committees (PrepCom), as well as the fourth PrepCom which focused on procedural agreements for the final conference in 2012.
There were a number of new defence integrity and counter-corruption programmes, including DSP feeding into a new Greek defence procurement law and Norway announcing a defence integrity / anti-corruption project with multiple nations in South East Europe that also involved DSP.
IFBEC, the International Forum on Business Ethical Conduction Business in the Aerospace and Defence Industry that DSP had helped create alongside Lord Robertson opened its membership to individual defence companies rather than just umbrella defence associations, with involvement from outside of Europe and the U.S. also increasing – the October 2011 meeting was attended by representatives from the Chinese, Japanese, Brazilian and Canadian defence industries. DSP was a keynote speaker.
DSP developed three new practical tools: (1) a defence budget transparency report which includes a questionnaire tool for civil society and others; (2) detailed offsets due diligence guidance; (3) a report on “The Third Line of Defence” which includes a template as a tool to design auditing systems. These practical tools have been applied and commented on, for example, by a number of TI national chapters around the world and by SIPRI. The offsets due diligence guidance has been praised by offset finance specialist Blenheim Capital, whose founder and CEO stated that “We believe that for offsets to achieve their full potential there needs to be increased transparency throughout the process and welcome Transparency International’s report”.
Various TI National Chapters started to work on defence and security issues, including in the OPT, Turkey and Malaysia.
New international initiatives were launched by the OSCE, including on border security and as part of the Irish chairmanship of the OSCE. A number of important defence and security decision makers highlighted the importance of addressing corruption, e.g. from NATO and the United Nations and including for example General John R. Allen (Commander ISAF), General HR McMaster (Director of Shafafiyat) and Ambassador Dirk Brengelmann (NATO Assistant Secretary General for Political Affairs and Security Policy).
Year 2

In their Independent Progress Review of DSP, the Channel Research evaluators concluded that “[T]he PPA grant represents a major step in TI‐DSP’s evolution, making it possible to consolidate its existing expertise and develop new tools that are potentially of strategic importance, as well as expanding its engagement with all three sectors: governments, companies and CSOs. The programme is highly innovative and, through its unrivalled expertise, is making ground-breaking advances in a sensitive and critically important sector.”

Top 3 highlights:

Highlights 1: the Defence Companies Anti-Corruption Index (CI) and the Government Defence Anti-Corruption Index (GI)

In October 2012 and January 2013 DSP launched two major indices to assess corruption risks within the defence sector and provide all major stakeholders with a benchmarking tool to assess progress over time. A report was produced to assess the initial impact, indicating that the indices contribute to an open dialogue and policy changes.

DSP follow up engagements with 47 defence companies, and 14 made changes to their systems based on this. There is pressure from other governments to include them in the next GI.

The impact on TI National Chapters has also been great: 47 did some of the research, and 31 took advocacy positions at the time of the launches. Media coverage was excellent with more than 400 articles, 163 in the international press.

Highlight 2: The United Nations Arms Trade Treaty (ATT)

DSP very much welcomes the historic adoption of the ATT. It is the result of years of work by concerned countries, its diplomats and TI’s partners in civil society. It is also the result of TI-DSP’s own work with governments (and DFID in particular), investors and the defence industry. DSP is calling on states to see the treaty as a starting point to set new international standards.

Three sections in the ATT will help states to address corruption risks at the various stages of an arms transfer, including as part of the strictest level of arms export assessment criteria, alongside international humanitarian law and human rights law, in Article 7.1.b.iv.

Highlight 3: Engaging the Afghan Security Forces and the international military on developing guidance for corruption prevention in stabilisation operations

One of DSPs key innovations was to bring our constructive and preventive approach to Afghanistan. DSP has worked with the Afghan MOD, MOI, ANA and ANP to run high level corruption prevention courses and have been advising them on how to reorganise themselves for better anti-corruption effects. DSP has been briefing deploying ISAF troops, including about which interventions risk make the problem worse. DSP led a review of ISAF anti-corruption activity (particularly “Shafafiyat”) and DSP’s proposed new strategy has been adopted. This work has led to a large body of new knowledge about how to tackle corruption in stabilisation operations, which DSP are currently developing into guidance.

Year 3

Top 3 achievements

Highlight 1: Launch of the ‘Corruption and Peacekeeping: Strengthening Peacekeeping and the UN’ report and subsequent engagement with the UN and Member States

Corruption threatens the success of peacekeeping missions, yet there is no systematic policy, guidance or training that specifically addresses it. DSP’s report launched on October 9, 2013 in New York offers suggestions for how these risks should be defined and addressed and suggests that the UN and Troop and Contributing Nations can lead in developing a policy framework.

The launch of the report had an exceptionally good attendance: 110 attended, including the Permanent Representatives or Deputy Permanent Representatives from the U.S., Jordan, Liberia, Canada, dozens of counsellors from other nations, dozens of military and police attachés, representatives from the UN Department for Peacekeeping Operations (DPKO), UN Office of Internal Oversight Services (OIOS), UN Public Ethics Office, and the Director of UN procurement.

Whilst everyone involved in peacekeeping outside of the UN and indeed some within the UN have greatly welcomed the recommendations of the report, the UN DPKO was particularly defensive, not least in light of revelations regarding Haiti and the misconduct of UN troops which was rightfully receiving much scrutiny at the time The key achievement has been how DSP managed to bring Member States on board with the call for reform. Norway is now leading on working with other member states towards reform from within. Separately, the U.S. mission has introduced counter-corruption language into a crosscutting resolution on peacekeeping under negotiation in the Fifth (Administrative and Budgetary) Committee that will take place in the next reporting period.

Highlight 2: TI co-hosts high-level panel with the Munich Security Conference

The evidence-base and the continuous constructive engagement that has been built over the last few years has allowed DSP to launch a coordinated effort engaging the security policy-making world in this reporting year, with a particular focus on fragile and (post-)conflict states.

As part of this, DSP and TI Germany launched their ‘Corruption as a threat to Stability and Peace’ report at the Munich Security Conference. TI co-hosted the break-out session on “The ‘conflict conundrum’” which featured e.g. UK Secretary of State for Defence Philip Hammond, Libyan Foreign Minister Abdul-Aziz, and NATO SACEUR Commander General Breedlove.

This is the first time since the inception of the Munich Security Conference in 1963 that corruption in defence and security was discussed as a major security concern. TI has already been invited again to the 2015 conference where follow-up discussions will take place. This is well aligned with DSP having been asked to contribute to various efforts to include anti-corruption elements as e.g. military doctrine is being updated.

Highlight 3: Corruption risk assessment of the security forces in Burundi and follow up

The experience and evidence generated in the first two years of the CHASE PPA has also been leveraged to extend DSP’s work to Burundi. Burundi is a fragile developing country of some 10 million people, still recovering from 15 years of civil war and mass killings. Whilst the country was making modest progress at normalising things deteriorated severely in 2015 and the military and the police, formed of previous combatants, consume the bulk of the country’s budget and aid.

DSP used the CHASE PPA to initiate engagement in 2012, which led to a formal request by the Dutch Embassy and the Ministry of Good Governance of Burundi for a thorough assessment of corruption risks in both the military and the police, and to provide recommendations. This project has enhanced DSP’s knowledge of converting the detailed Government Defence Anti-Corruption Index (GI) into concrete recommendations and actions. This was also the first time that DSP’s police anti-corruption assessment methodology has been used, generating a huge body of replicable knowledge for assessing corruption risks in police and security forces in fragile and weak states.

Year 4

According to the independent CHASE PPA Annual Report reviewer, Professor Ann Fitz-Gerald from Cranfield University, DSP had a strong year 2014/15. In addition to either achieving or exceeding all milestones set for the 4 outcome indicators, the organisation was deemed to be in a good position to achieve all PPA programme outcomes for December 2016.
Its work and policy influence had achieved high profile media coverage. The DFID Secretary of State’s keynote speech delivered at the 2014 TI-UK Annual Lecture led to the establishment of a DFID / TI ‘Global Security’ policy working group which reflects the critical link between security, stability and corruption, and whose work did inform the 2016 UK-hosted Global Summit on Anti-Corruption.
Through DSP engagement:
1. 12 nations and a total of 18 international organisations to date have initiated counter-corruption initiatives for the defence sector
2. 30 major companies, such as e.g. Airbus Group, Avibras Indústria Aeroespacial, Bechtel Corporation, Nammo and Rheinmetall AG have improved their anti-corruption policies and systems
3. and 30 Civil Society Organisations (CSO), including various TI National Chapters but also non-TI NGO coalitions in countries as diverse as Croatia or Ghana, are showing enhanced capacity to work on reducing corruption in the defence sector
The organisation has also achieved deeper forms of anti-corruption engagement in a limited number of countries including Afghanistan and Ukraine. This deeper engagement includes the development of local policy and/or plans, organisational capacity, and regular, locally-delivered, training and educational programmes. DSP also led the successful roll-out of its Companies Index (CI). Internally, DSP managed a successful leadership transition and facilitated organisational growth through the development of a more robust management structure.
DSP has learned about the utility of strategic funding, and PPA funding in particular, in promoting wider donor confidence and supporting innovation, risk-taking and organisational growth. It also continues to benefit from the support provided by ‘MEKANIC’, an in-house mechanism which supports the organisation’s ongoing monitoring, evaluation and learning. Based on the CI roll-out experience, and the regional consensus and ‘peer review’ process that this generated, it has also acknowledged the value of taking a region-by-region approach to the launch of future indices. The organisation has also realised the limitations of the current organisational structure and has developed a new structure which better aligns with the organisation’s strategic direction and growth. Furthermore, it has recognised the importance of ensuring that organisational growth plans are supported by effective personal development programmes for the majority of DSP’s relatively young staff. Lastly, the organisation acknowledged the greater impact achieved by the dissemination of shorter policy documents and practical tools.

DFID Management Response to CHASE PPA PCR

Transparency International (TI) has exceeded expectations and proved to be a strong and reliable partner for DFID throughout the lifetime of the Programme Partnership Arrangement (PPA). The programme completion report (PCR) illustrates how TI leads in its sector and the organisation has the capability to influence multinational corporations, civil society and governments to fight corruption and enhance the trust and integrity of those in authority.

One of the most prominent tools TI has developed is the Government Defence Anti-Corruption Index (GI). TI’s in-depth analyses of more than 115 countries provide examples of defence procurement practices which harm the wider economy. TI plays an important role in fighting for accountability, and has used this Index to help bring about substantial government and private section reform. For example, TI has worked with government institutions on reform efforts, such as in the Tunisian Ministry of Defence, MOD, where the index has suggested operational weaknesses. To support efforts on sustainable anti-corruption reform TI has successfully engaged directly with high-level government officials; for example in Ukraine on Ministry of Defence reforms.

At the level of individual companies and organisations, reform can help ensure businesses remain accountable and open to citizens. The GI and Corruption Index (CI) has allowed TI to be a leader in training companies to be more open, transparent and follow procurement regulations through capacity building and training courses; these include prominent defence companies such as Rolls Royce and Leonardo-Finmeccanica. Moreover, TI has worked closely with the UN Department for Peacekeeping Operations (UN DPKO) to brief the leadership; TI will maintain this work by producing a detailed review on a mission.

 TI has made substantial contributions to addressing the corruption risks of arms transfers. TI has worked closely with civil society groups and academics in providing recommendations for better application of the UN Arms Trade Treaty (ATT) and consequently has supported countries such as Mexico, Turkey and Brazil in their implementation of the ATT. TI shares information in an open and transparent way and its own organisational progress on transparency and accountability throughout the lifetime of the PPA has increased. TI has worked closely with DFID to share annual audited statements online and they are now available free to download. TI has shown it delivers value for money (VfM) throughout the PCR, providing specific examples in this review of organisational changes.

The PPA funding has enabled TI to make significant changes regarding its capacity and systems. This included funding to hire dedicated staff focusing on functional areas such as civil society liaison and fundraising, and also on shared financial functions with other TI programmes.

In conclusion, TI has been an important partner to DFID and the rest of the UK Government. The 2016 anti-corruption summit, hosted by the UK Government in London, demonstrated TI’s ability to provide timely and influential inputs and recommendations to a range of partners. The results of TI’s efforts as set out throughout the PCR provide a good foundation for the organisation to continue to advocate and work for long-term reform for an accountable, open and transparent world. Overall, DFID rates this programme as an overall A+ based on TI’s work, organisational changes and achievement over the past 5 years.

PPA Extension reporting

Review Date:	31 January 2017

Title: Transparency International PPA Extension Report – (General and CHASE)
Programme Code: 202505	Start Date: 1 April 2016	End Date: 31 December 2016

A. SUMMARY AND SUSTAINABLITY

Summary of key achievements during the nine month extension period
These nine months were marked by significant achievements in the fight against grand corruption, with many countries committing to increased transparency around beneficial ownership at the UK’s Anti-Corruption Summit in London in May 2016. Our “Unmask the Corrupt” campaign is also bearing fruit: the TI International Secretariat has since January 2015 worked to convince the Panamanian Supreme Court, the U.S. State Department and the U.S. Department of Justice’s Kleptocracy Unit to act on its recommendation to legally sanction former Panama President Ricardo Martinelli, who resides in Miami. These efforts contributed to Panama formally initiating extradition proceedings in September 2016. Organisationally, the PPA extension has enabled the TI International Secretariat to initiate a complex change process through which we re-organised the way we work around major strategic streams and functions. We also managed to diversify our funding by significantly increasing our income from foundations and the private sector.

For the CHASE PPA, and beyond the examples provided under Section B, the extension period saw a number of achievements that ensured that TI Defence & Security (TI-DS) was well placed to further increase its impact in 2017. These included concrete action following the 2015-16 iteration of our Government Defence Anti-Corruption Index (GI), with more than 10 countries initiating reform efforts and e.g. creating task forces to address the most pressing risk areas. We put corruption and insecurity on the top tier policy agenda, most significantly by bringing together senior diplomats and the military for a group discussion led by U.S. Undersecretary Sewell in the margins of the Anti-Corruption Summit in London. We have maintained a strong focus on capacity building, including through our contribution to the UK Defence Academy’s Building Integrity programme. TI-DS has taken part in capacity building or training in almost every continent, including South Africa and Jordan as well as with the UN and the EU, and we have hosted military secondees from e.g. Jordan and Ukraine. On the private sector side we published significant new research into the risks posed by agents in defence contracting. Our full time secondee from the Army’s 77th Brigade led the establishment of a working group that is looking at how the Army can included anti-corruption considerations in planning for future operations and defence engagement.

Summary of the key changes and/or improvements that will be sustained at the end of the extension period
The commitments made at the UK Anti-Corruption Summit are clearly long-lasting ones. Beneficial ownership transparency and grand corruption are becoming more prominent issues, and TI as well as other organisations will be able to hold governments to account regarding their commitments as those were formally recorded. Internally, the change process at the TI International Secretariat will improve our ways of working in the long term, and it has enabled us to improve and expand our operating procedures.

CHASE PPA funding has enabled TI Defence & Security to secure significant additional income, resulting in increased sustainability for TI-DS post-PPA and VFM for all donors, who benefit from lower ‘unit costs’ for tested tools (new donors) as well as others funding work that has been successfully piloted (DFID and other existing donors). Sustainability will also be enhanced by the growth of other TI programmes in London, e.g. the global Healthcare Programme, as increased income will drive down overhead and unit costs and further increase VFM. TI-DS has helped civil society develop the oversight capacity needed to hold their governments to account, including through practical tools like the GI. In the long run, the capacity of local civil society to engage constructively on issue of defence and security is key to sustainable results. This is an area we intend to focus on even more in the future – ensuring that capacity building efforts are linked to the development of robust oversight functions that will remain in place long- term.

B: PERFORMANCE
Principle 1	Consolidation of current PPA/SGA work to contribute towards the new Sustainable Development Goals (SDGs)
General PPA: 53 examples of TI-S recommendations being adopted
CHASE PPA: 3 additional concrete reform actions facilitated by TI Defence and Security that contribute to the achievement of Goal 16 and/or improve resilience and response to crises
Risk:		Minor	Impact weighting (%):	50

Key Points - Summary of progress during the nine month extension
In May 2016, the UK held its Anti-Corruption Summit in London – the development of the agenda benefitted from substantial input provided by a team from Transparency International and Transparency International UK. We had previously focused our advocacy on the G20 and its Anti-Corruption working group for issues such as beneficial ownership transparency, open contracting and open data, yet the Chinese G20 presidency was posing considerable challenges to advancing this agenda. We thus refocused our efforts on securing an ambitious agenda for the London Anti-Corruption Summit. We produced guidance documents with key areas for the Summit (preventing corruption, ending impunity for corruption, and empowering citizens to report corruption) as well as how the Summit might be structured (inclusive, open and in partnership, with a plan for implementation).

We have continued to be involved in Summit follow up, for example through integrating key commitments into the OGP National Action Plans and co-organising a workshop focused specifically on the beneficial ownership and public contracting commitments made at the Summit. Because of the high number of commitments made by countries at the Summit (we recorded more than 700), this first indicator’s progress is significantly higher than expected. To provide a few examples: some countries have signed up to publish registries of who owns and controls companies, and some stated that they would increase transparency around the beneficial ownership of companies bidding for public contracts, while others agreed to implement Open Contracting Data standards.

The failure to tackle security challenges is one of the biggest barriers to development, particularly in the world’s least developed states. Conflict-affected countries are among those who performed the worst under the MDGs, with few states hitting even one of the 21 targets. Including corruption in SDG16 was vital to ensuring these states do not get left behind again. Given the links between corruption and insecurity, tackling defence sector corruption, improving trust in the armed forces, and disrupting organised criminal networks is essential. During the extension period, TI-DS has facilitated three additional concrete reform activities, as per the extension log frame:

- In Nigeria, we developed a long-term strategy to strengthen accountability and transparency in the Nigerian defence sector. Our initial engagement has produced some positive results: the Ministry of Defence has agreed to host a Leadership Day which will take place early this year and TI’s local partner CISLAC are now the principal voice for the media and the government on defence corruption issues. They are also working with local focus groups in different regions of Nigeria to identify their most pressing needs.
- In Ukraine, we established the Independent Defence Anti-Corruption Committee (Nezalezhny Antikorrupciynii Komitet z pytan oborony, or “NAKO”). The Committee comprises six members, three national – Sevgil Musaeva, Volodymyr Ogryzko, Oleh Rybachuk – and three international experts – Lt Gen Tim Evans, Drago Kos (co-chair), and James Wasserstrom. The committee has held two meetings, drafted research on security assistance corruption risks, and is setting up a corruption reporting hotline, and has had promising meetings with key stakeholders, including the MOD, Ukroboronprom, and the National Anti-Corruption Bureau. Its mandate and terms of reference have been published, and its 2-year strategy will be published in Q1.
- NATO developed its Building Integrity policy this year. We briefed the NATO Partnerships and Security Policy Committee ahead of the Warsaw Summit and our recommendations were largely taken on board, including through the subsequent drafting of the action plan. More practically we worked with NATO’s rapid reaction forces to include corruption-related issues in exercises, scripted storylines for two exercises with the 1st German-Netherlands Corps (1GNC), and saw the Allied Rapid Reaction Corps (ARRC) in Gloucester use TI guidance to adapt their staff processes to address corruption.

Principle 2	Organisational effectiveness
General PPA: 5 initiatives (policies, systems, guides, etc.) newly developed and/or improved to ensure that TI-S is fit for purpose for its role in implementing TI’S strategy
CHASE PPA: 7 key recommendations made by the independent expert in the TI CHASE PPA Annual Report FY 2015 implemented by TI Defence and Security to increase its operational effectiveness
Risk:		Minor	Impact weighting (%):	20

Key Points - Summary of progress during the nine month extension
2016 was a key year for the TI movement, with the start of a new strategic cycle, and for the TI International Secretariat, which underwent major organisational changes. The structure was modified in order to better focus on the priorities outlined in the Secretariat’s Implementation Plan 2016-2020. These changes also include the development and/or improvement of many processes and policies, e.g. on internal communications (“internal” also includes National Chapters, individual members and the Board of Directors), project development, handling external corruption-related complaints etc. Standard Operating Procedures will be prepared to compile all of these policies and processes.

Also worth stressing is the TI Guide to Strategic Planning, a TI global capacity development toolkit originally developed in 2011, which was reviewed and updated in 2016 to support TI chapters in developing their own strategic plans within the framework of ‘TI Strategy 2020: Together against Corruption’.

In the extension log frame, TI-DS committed to implementing at least 7 recommendations made by the independent expert in the TI CHASE PPA Annual Report FY 2015. As of 31 December 2016, the following recommendations had been implemented:
- A new organisational strategy has been introduced and is being implemented.
- The TI-DS defence corruption indices (government and companies) have been further developed, with the second iteration of both having been launched successfully (see above).
- Improved performance and capacity management systems have been introduced across TI-UK.
- New processes for country engagements have been introduced, with increased clarity regarding breadth and depth.
- The TI-DS training and capacity building offer has been improved and increased.
- TI-DS has continued to field expert participants for high-level events.
- TI-DS has strongly focused on and facilitated the capacity development of others active in this space (see sustainability above).

Principle 3	Diversification and innovation
General PPA: 60% increase in TI International Secretariat’s income from foundations and the private sector
CHASE PPA: 5 additional sources TI Defence and Security attracts funding from for dedicated anti-corruption work in defence and security
Risk:		Moderate	Impact weighting (%):	30

Key Points - Summary of progress during the nine month extension
One of our priorities was to diversifying the TI International Secretariat’s income, more specifically by increasing income from foundations and the private sector. This was achieved, with a 61% progress on foundations and 58% on the private sector, amounting to close to EUR 4.5 million overall. Kindly note the 2016 numbers are not yet final as our financial statements will only be finalised and audited in the coming weeks. We are however reasonably certain there will not be major variances. The reasons for exceeding the targets substantially are as follows: When setting our targets for growth in the PPA extension period we did expect to benefit from our earlier efforts to diversify our income, but we were careful not to be too optimistic as the funding landscape remained volatile. In the end our growth percentages were substantially higher than expected mainly due to our efforts to strengthen our engagement with foundations (especially through policy dialogue leading to positive financial spin-off). For example, in 2016, we benefitted particularly from our new partnership with Omidyar and our cooperation with the BHP Billiton foundation. With regards to corporate income, the majority of growth comes from the fact that we took the implementation of our partnership with Siemens to scale and secured increased support from Ernst & Young.

TI Defence & Security committed to securing at least one additional source of funding during the extension period. Examples of additional funding partnerships include for example TI-DS work with the UK Defence Academy on capacity building, training and secondments; with the Dutch Ministry of Foreign Affairs (MFA) in Africa and more recently in Ukraine; and with the Network for Social Change on agents and intermediaries in the arms trade. TI-DS has also been able to secure funding from the Arab Reform Initiative to support their training and capacity building for Syrian experts ahead of the (hopefully at some point) post-conflict status of Syria and from the CSSF West Africa for work in Nigeria, building on what is outlined above. The partnership with the Dutch MFA is being extended from its Africa- and Ukraine-focus to general support for the global work of TI-DS.

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202505/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202505/documents