Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme (see Annex B).

Review Date:	22, 27, 28 September

Title: Development Research Uptake in sub-Saharan Africa (DRUSSA)
Programme Code: 202004	Start Date: 1 Oct 2011	End Date: 30 Sept 2016
If programme was closed >1 month early please describe in a few words why.

Summary of Programme Performance

Year	2012	2013	2014	2015
Programme Score	A	A	A	A
Risk Rating	Medium	Medium	Medium	Medium

Financial Position

Original Programme Value	£3.7m
Extensions/ amendments	£1,261,955
Log-frame revisions (with dates)	Revised July 2015
Total programme spend	£4,548,520

Follow up actions required following closure
- ACU to submit the final invoice to DFID before end October 2016.
- DFID and ACU to complete asset disposal process before end October 2016.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717199.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5066598.xlsx

Outline of programme and what it has achieved

Development Research Uptake in sub-Saharan Africa (DRUSSA) was a five-year programme with the aim of improving the capacity of universities across sub-Saharan Africa to contribute to, and increase the demand for, research evidence in the development of policy and practice. DRUSSA worked with 22 universities in 12 countries to build the capacity of universities at strategic and operational levels and create sustainable links between universities and groups that use research to make decisions. The programme also worked with policy-makers in ministries in Ghana and Uganda to help increase demand and develop capacity to find and apply research evidence.

The main delivery partners were:
- The Association of Commonwealth Universities (ACU), UK – grant holder
- The Centre for Research on Evaluation, Science and Technology (CREST), University of Stellenbosch, South Africa
- Organisation Systems Design, South Africa

Further partners were involved in the delivery of output 5, in the final two years of the programme:
- The Council for Scientific and Industrial Research – Science and Technology Policy Research Institute (CSIR-STEPRI), Ghana
- The Institute of Statistical, Social and Economic Research (ISSER), University of Ghana
- The Ugandan National Council for Science and Technology (UNCST)
- The Economic Policy Research Centre (EPRC), Uganda

Five things the programme wanted to achieve at the output level were:
1. A core of specially trained and qualified university staff who can provide the strategic and operational leadership and expertise to ensure their University’s research is disseminated effectively (lead partner: CREST).
2. Strengthened strategic leadership and organisational capacity within DRUSSA partner universities to achieve greater use of their research by external groups (lead partner: ACU).
3. New contributions to the evidence base about research communication and use in Africa and globally (lead partner: CREST).
4. Keeping the DRUSSA network well informed about the programme, encouraging peer learning, and strengthening relationships in the region to sustain universities' capacity for research uptake (lead partner: OSD).
Political leaders and civil servants within 6 development oriented government ministries in Ghana and Uganda with improved capacity and incentives to use research evidence in the formulation and implementation of development policy (lead partner: ACU).
The programme successfully improved capacity to manage research uptake within participating universities, including through improved structures and strategies. All policies and strategies developed are fully resourced. At least 18 universities have structures in place for formal stakeholder engagement and most of these show promise of sustainability. Evidence regarding improved capacity within government ministries to use research evidence is mixed. There is evidence that ministers and civil servants have greater appreciation for evidence-informed policy-making but there is relatively little evidence demonstrating improvements in behaviour change.

A particular strength of the programme was the work to embed research uptake structures, strategies/policies and processes within the universities. The programme had a flexible approach, enabling institutions to identify their own pathways to improvement and supporting them to meet their objectives. The progress made, and efforts to ensure senior buy-in, bodes well for the future in relation to sustainability and continuing development of research uptake capacity within the participating universities. The ACU is considering what role it might play to provide continued support to those universities where it is needed.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment – A - met expectation

Outcome statement: Improved capacity of universities to contribute research evidence in pro-poor policy and practice and increased appreciation, understanding and demand for university-produced development research evidence.

Indicator 1 Research uptake management is established as an organisational management practice as evidenced in the development, implementation and adoption of research uptake policies, strategies, structures and procedures in place to support it.

Target 1 At least 18 participant universities have improved capacity to manage research uptake through aligned structures, functions and trained staff.

Achievement:
- This target was met with all 22 participating universities having improved capacity in some form. Examples of improved capacity from the benchmarking exercise are given below under output 2 with additional examples in the DRUSSA final benchmarking report 2016. The University of Rwanda has integrated research uptake into its performance management system. Funding allocation is partly dependent on researchers satisfying certain research uptake criteria.
- All policies and strategies developed by universities as a result of the DRUSSA programme are fully resourced. While most require some commitment of funding, some of the key activities are cost-free to implement such as better cross-functional working between offices.
- As revealed in output 2, policies and strategies are already being implemented so there is a strong likelihood that they will continue to be rolled out after the DRUSSA programme ends.
- Staff training is one of the weaker areas of achievement during the DRUSSA programme. Relatively little training has been cascaded within institutions but it is hoped that the multi-faceted approach to strengthening individual capacity through the Masters/PhDs, short courses, communications campaigns involving direct support from DRUSSA staff, and train the trainer workshops will increase the likelihood that sustainable individual learning opportunities will be provided for and within participating universities.
- Vice Chancellors have been discussing how to take forward the networks developed through the DRUSSA programme. They are planning to raise funds to run a conference in 2017 to which non-DRUSSA universities may be invited. This shows strong commitment by DRUSSA universities to learning from each other as strategies and policies are implemented, structures are put in place and staff have their capacity strengthened, and shows promise for higher quality research uptake in the future across sub-Saharan Africa.
- The DRUSSA programme team has also influenced organisations and structures beyond the participating universities. For example, Kenya’s National Audit Office now includes research uptake in its audits of universities and DRUSSA has supported the NAO in developing indicators that link research uptake with socio-economic change.

Target 2 Non-participant universities in the SSA region are aware of learning and lessons that can be applied within their universities through connection with the regional Research and Innovation Management Associations (RIMAs) and /or other stakeholders.

Achievement:
- Half-day action learning workshops, led by DRUSSA staff or representatives of DRUSSA universities, were offered at 12 RIMA conferences during the programme period on topics such as the basics of research uptake and strategic institutional research uptake management. Around 200 non-DRUSSA university representatives from around 40 universities attended those workshops and were given a handbook to take back to their workplace.
- After workshops or presentations at RIMA conferences, DRUSSA staff and DRUSSA university representatives (around 20 senior university representatives in West Africa and 13 in East Africa) were often asked for information about joining the DRUSSA programme. This demonstrates that the DRUSSA programme was relevant at a time when research uptake is becoming central to research design in the context of external research funding and the need to demonstrate research impact. The outputs from the DRUSSA programme, including an online research communication training resource, will continue to be available online on the ACU website once DRUSSA.Net is closed.
- The short course in science communication (face to face and online) was offered to both DRUSSA and non-DRUSSA universities and take-up from non-DRUSSA universities was strong (210 people).
- While non-DRUSSA universities were not able to participate in the benchmarking exercise, they could replicate it as the benchmarking reports reveal much about how it was done and the DRUSSA team has published handbooks, papers and presentations on institutionalising research uptake and developing strategies.
- While these achievements have raised awareness within non-DRUSSA universities, there is not yet any evidence to demonstrate change in structures, resources and processes within those universities.

Indicator 2 Universities are recognised by policy-makers and practitioners as sources and contributors of development research evidence.

Target 1 At least 18 universities demonstrate formal stakeholder engagement and sustainable pathways for development research uptake.

Achievement:
- Before the DRUSSA programme, there were processes for stakeholder engagement within certain university departments but they were not formally mandated or recognised by senior leaders. Now stakeholder engagement is profiled in university-wide policies and strategies.
- At least 18 universities now have structures for formal stakeholder engagement and pathways for uptake. The majority of these show promise of sustainability beyond the DRUSSA programme. Examples include:
  - The University of Calabar, Nigeria, has established ties with the Calabar Chamber of Commerce through regular meetings on university research outputs.
  - The University of Fort Hare, South Africa, has established a public-facing magazine to communicate research activity to public stakeholders
  - At the University of Ibadan, Nigeria, a Research Links Office identifies private sector research needs
  - Mbabara University of Science and Technology, Uganda, is partnering with the Private Sector Foundation to ensure that students can get placements in various industries and companies across Uganda
  - The University of Nairobi hosted a Nairobi Innovation Week in 2015 and 2016, in partnership with three government ministries and stakeholders from the Kenya Private Sector Alliance, as well as NGOs and community bodies, to provide a platform for showcasing research.
- There are anecdotal examples, collected by the DFID review team, of Fellows returning to their universities and refocusing university practice such as generating more time-responsive research products.

Target 2 Six ministries in Uganda and Ghana demonstrate improved capacity and incentives to use research evidence within the formulation and implementation of policy[1].
[1] This target previously applied to four universities as well as six ministries. During the PCR process the ACU and DFID agreed that reference to universities should be removed because DRUSSA’s focus on use of evidence was aimed at change within ministries rather than universities.

Achievement:
- This target is moderately not met. While there is evidence that ministers and civil servants within the six ministries have a greater appreciation for, and confidence in, evidence-informed policy-making as a result of this programme, there is currently very little evidence of improved capacity and none regarding incentives.
- Through the fellowships and policy symposia funded by the DRUSSA programme, a number of evidence-informed policies have been developed within government ministries. It is too early to assess whether those policies have had impact on poverty reduction. Little evidence was generated on the improvement in skills arising from training events for civil servants. The capacity of ministries to formulate evidence-informed policies without external support is therefore unclear.
- The policy symposia helped to break down distrust between policy-makers and researchers and there is evidence from the Ministry Capacity Assessment surveys that policy-makers now engage more with researchers.
- The adoption of DRUSSA-informed training by the Government of Uganda and integration into its professional development programmes for civil servants means that there is a sustainable structure that should support evidence-informed policy-making in the years to come.

Output Score and Description - A - met expectation

Lessons and how these have been shared

DRUSSA was a multi-national programme working across academia and policy and sought to build relationships between those producing research and those using it. The geographic nature of the programme enabled learning and ideas to be shared across a wide spectrum of experience which encouraged universities to adapt and adopt approaches that would be applicable to their contexts. This would not be possible if it had focused on a narrow set of countries. Furthermore, the programme acted at the individual, the institutional and the systemic level while most other interventions to improve research uptake have been aimed at particular university departments leading to a more limited impact and chance of sustainability.

The Scoping Study which led to the development of the DRUSSA programme was a useful tool to inform programme design, and it also instilled confidence that universities wanted to participate in the programme. Buy-in from Vice Chancellors was a key step in ensuring dedicated budget for research uptake and Vice Chancellor conferences in 2015 and 2016 paved the way for strengthened and refined commitments to research uptake after the DRUSSA programme ends. Participating universities identified Leaders and Champions who would keep programme implementation on track within their respective universities. These three roles proved to be critical for consistency during changes in personnel.

Participating universities invested a substantial amount of their own resources in taking forward the changes they wanted to make. It was an important element of the DRUSSA model that the programme did not fund any new posts or office set-up costs but that these were funded from the core university budget. This demonstrated commitment to the goals of the programme and increased the likelihood that the gains made will be sustained and plans established will be taken forward.

The programme did not advocate any particular model to institutionalise research uptake capacity but worked with each university in a tailored way as identified through the benchmarking programme. This flexible and responsive approach has been valued by the universities.

Value for Money indicators should be established at the start of the programme in order to build up a clear picture of value for money indicators over time. Similarly it is important to agree protocols for assessing the impact of capacity interventions at the start of the project, including in ways which are sensitive to cultural sensitivities.

Given the interest in the DRUSSA programme from other research capacity programmes in sub-Saharan Africa and more widely, ACU has committed to consider a concise learning document that could be shared.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	A core of specially trained and qualified university staff who can provide the strategic and operational leadership and expertise for research uptake management in their university
Output number per LF		1	Output Score	B
Risk:		Moderate	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Progress
1.1 Number of Masters and PhD awarded in STS Programme	Minimum of 16 Masters and Doctoral candidates graduate from the programme	16 Masters students completed the course.
1.2 Number of DRUSSA participants completing short courses.	Minimum of 40 delegates (annually) from DRUSSA partner universities have completed 8 courses in research uptake / 30 participants demonstrate improvement in skills/understanding in post-course assessment / 50% are reported by managers to be applying those skills in the workplace / 25% of all participants who have taken courses continue to apply skills in the workplace.	Annual average of 58.6 delegates completed 8 courses. / No post-course assessment was carried out. / 13 of 20 course participant survey respondents said that job description had changed. / 19 of 20 course participants surveyed said they were applying learning at work.
1.3 Number of non-DRUSSA participants completing short course in science communication.	Minimum of 20 participants (annually) complete online short course in science communication	Annual average of 51.5 non-DRUSSA participants completed the online short course.

Key Points

- 1.1. Some of the 16 Masters students are waiting to graduate but all have completed the course. No PhDs have been completed yet, though most should complete within the next two years, with CREST committed to provide continued supervision beyond the end of the programme. The average time for PhD completion in African universities is 4.8 years, so it would have been difficult to achieve within this 5-year programme. All of the students are part time and work alongside their course. 40% of the students were female.
- 1.2. 66% of short course participants were female. There was one year when the minimum of 40 short course delegates was not reached due to visa issues. As delegates were senior university staff (e.g. Deans of research), CREST felt it was culturally inappropriate to carry out pre- and post-course assessments. This contradicts training good practice that all course participants should complete such assessments to ensure relevance of course content and assess learning outcomes.
- 1.2. For the remaining parts of this target, which focus on application of skills learned during the courses, CREST used a survey which was sent to all 42 delegates who completed the consolidated short course in 2015 and to which 20 responded. Progress against this indicator is therefore subject to reporting bias and a relatively low response rate, and there is no assessment of skill demonstration. CREST felt it was culturally inappropriate to ask managers of senior university staff whether trainees were applying their new skills, so used a proxy indicator about a change in job description.
- 1.3. The online version of the science communication course was rolled out in the last two years of the programme. While the target was exceeded, the target was not adjusted in light of high demand in year 4 (see below). In the future, CREST is planning to offer the course twice a year to meet demand. Although the course included weekly assessments and a project towards the end, the target does not include an assessment of how people applied the learning following the course. Most of the feedback at the end of the course was about how the participants had learned about the importance of good science communication and gained confidence, but there were also a couple of examples of where the skills were already being put into practice:
  - “I have been able to take what I have learnt in the course and influence what is being developed in terms of science communication in my organisation.”
  - “From the first week I re-looked the way we communicate science news. I started implementing new plans and strategies in my work as communicator almost immediately.”
- This output has enabled CREST to make a focused effort in developing individual courses on research uptake which are lacking for sub-Saharan African researchers. These courses will continue to be offered and will be self-sustainable. CREST now has approval to offer Masters courses on Research Uptake / Impact Assessment and Science Communication next year and has already received 20 applications.
- Although the training courses were delivered to expectation, the failure to measure learning outcomes means that it is not possible to say that the output statement has been achieved. For this reason this output has been given a B score.

Summary of responses to issues raised in previous annual reviews (where relevant)

As participation in the online short course exceeded the target in year 4 (85 students compared to a target of 20), it was recommended that a more realistic target was set for the number of online course participants in the final year of the programme. This recommendation was not taken up by CREST and the target was not changed. However, for the online course starting in September 2016, CREST did make 50 places available and enrolled 62 participants.

Recommendations for future programmes

Where programmes provide a variety of courses at different levels and durations (e.g. PhD, Masters, short courses), consideration should be given to how those who complete the courses at various levels will then contribute to organisational capacity strengthening. This includes thinking about learning outcomes, relative financial investment in course development and delivery and staff retention.

Output Title	Strengthened strategic leadership and organisational capacity within DRUSSA partner universities to achieve greater uptake of their research by external users.
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	50
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Progress
2.1 University leaders are better informed and develop collaborative models and principles to improve research being taken up at strategic and policy level within and across participating universities.	At least 18 universities have research uptake strategies or policies and can demonstrate specific examples of projects that have benefitted as a result of implementation. / At least 18 universities have completed final Process Benchmarking programme that surveys, examines and reviews change and good practice being incrementally developed across universities with survey reporting 50% positive change from baseline across 18 universities. / Senior representatives at 2 universities in an additional two countries have engaged with Higher Education policy-makers at symposia to strengthen research communication and its potential application in higher education policy.	20 universities have strategies or policies in place which fully encompass, or include sections on, research uptake. / 19 universities completed the benchmarking programme survey each year. Across all universities, there was at least a 50% positive change across the key indicators. / 2 universities in 2 further countries (Botswana and Mauritius) engaged with Higher Education symposia.
2.2 Strengthened organisational capacity within participating universities is improved to enable research being more accessible to policy-makers and practitioners. Workshops, working groups, communities of practice and training materials are carefully planned and put in place to support this.	At least 18 universities have achieved 50% targets in their university change programmes to embed practices that support research being made more accessible to external users and can demonstrate impact of changes that have been made. / Tailored training in research uptake is being delivered across all participating universities. / Drawing on the RU Campaigns coaching and learning and in-service digital training, the communications network is embedding research uptake in university practice	21 universities met at least 50% of their targets. / All universities are delivering awareness-raising workshops. 14 universities are delivering or planning to deliver independent research uptake induction workshops. / The impact of the communications network on embedded research uptake has not been quantified.
2.3 Number of DRUSSA partner universities who have compiled and made publicly accessible a comprehensive record of their policies, literature and learning on Research Uptake Management for the benefit of others.	At least 16 universities have compiled and made publicly accessible a comprehensive record of their policies, literature and learning on Research Uptake Management for the benefit of others.	17 universities have contributed their documents and resources (50 in total) for dissemination by the Research Uptake Management e-Library on DRUSSA.Net.

Key Points

- 2.1. All of the strategies and policies have been developed since the start of the DRUSSA programme. The programme team did not specify what these should look like and neither did they quality assure them, but they did ask universities to make them achievable and contextually appropriate. This led to inclusion of research uptake in a variety of documents, mainly featuring strongly in research, research uptake or communication strategies and policies. Research uptake was given relatively little coverage in some, less relevant policies (e.g. an Intellectual Property Policy at one university) but these were complemented by more focus on research uptake in other documents.
- 2.1. 19 universities completed all three surveys and attended all three conferences. The other universities completed two surveys and attended all three conferences or completed three surveys and attended two conferences. Of the 49 individuals who served as Leader or Champion across all partner universities over the course of the final programme year, 15 were women (31%), reflecting the relatively few women in senior university positions. Positive change highlighted during the benchmarking process since 2012 included:
  - The number of universities with offices, units or staff that could support individual researchers in research uptake increased from 13 to 21. For example, the National University of Science and Technology, Zimbabwe, established a research uptake management office within its Research and Innovation office, staffed by a DRUSSA Masters graduate.
  - The number of universities providing training or other resources for research staff to engage with external stakeholders increased from 10 to 17. For example, Makerere University introduced courses for PhD students and researchers in research management, scholarly writing and communication skills.
  - The number of communication channels used to communicate research increased by 63%, particularly the development of web pages and digital platforms. A journalist specialising in research and uptake has been appointed by the University of the Free State to write articles on research findings.
- 2.1. Engagement in Higher Education symposia occurred in Ghana and Uganda in year 4. In the final year of the programme, the DRUSSA team was involved in discussions in Ghana regarding the inclusion of research uptake in a National Research Council which is being established. Recommendations were agreed at the end of the symposia in Botswana and Mauritius and there is commitment to meet again to discuss implementation of the recommendations.
- 2.2. Nine universities met at least 80% of their targets. The DRUSSA team tried to make sure expectations were realistic and encouraged universities to start with the targets that were achievable. Targets around research impact have generally not been met yet, but other difficult targets (such as setting up structures) have been achieved. The University of Nairobi is implementing a number of strategies and policies related to research uptake; has established a Directorate of Research and Extension governing research uptake policy and activity; has established training workshops related to research uptake; includes research relevance to national policy objectives in university performance contracts; has adopted a new research information management system; and delivered open days and policy-facing research events. Several universities[2] have incorporated elements of their research uptake institutional change programmes into new research policy frameworks. Fifteen universities have projected their institutional change programmes beyond completion of the DRUSSA programme, with longer term plans already in place at Kenyatta University and the University of Ghana. The impact of changes has not been measured (this is a weakness acknowledged by the DRUSSA team) but in some cases it is too early to assess impact.
  [2] University of Buea, University of the Free State, University of Limpopo, Makerere University, University of Mauritius and University of Nairobi
- 2.2. All universities are committed to embedding content from a DRUSSA online guide on communicating research, introduced at a Train the Trainer workshop in April 2016, in induction programmes.
- 2.3. There is no evidence on whether the materials have been downloaded and used.

Summary of responses to issues raised in previous annual reviews (where relevant)

The year 4 annual review recommended that training developed should be well adapted to what is most useful for the universities and most likely to be rolled out – and where possible embedded in existing processes. DRUSSA’s new online guide on communicating research and a follow-on guide for researchers in research uptake include Train the Trainers activities to enable training to be rolled out more widely across universities.

The year 4 annual review recommended that the digital knowledge platform should only be integrated into university systems where they have sufficient capacity and are genuinely likely to use it. A user needs survey in September 2015 revealed that a third party website was equally valuable to users and more cost-effective. It was agreed that a sustainable, open access online learning resource would be developed on the ACU website.

Recommendations for future programmes

A strength of the DRUSSA programme has been the work to strengthen capacity at the institutional level. This has been lacking in other research uptake capacity strengthening programmes. However, the value of policies and strategies can only be realised if staff possess the capacity and resources to implement them. Progress on embedding training was made relatively late in the DRUSSA programme and may threaten the extent to which the strategies and policies improve the effectiveness of research communication to policy-makers and practitioners.

It is important to ensure that monitoring and evaluation frameworks are built into the design of institutional policies and strategies. The DRUSSA team acknowledged that more support would be required to help universities develop appropriate indicators to track their progress and impact, and assess what works in the future.

Output Title	New contributions to the evidence base about Research Uptake and Impact Assessment in Africa and globally
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	10
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Progress
3.1 Research undertaken and publication of documents and reports - specifically Review Report of scholarship on Research Uptake and Impact Assessment	Scholarly research paper published in peer-reviewed journal (print/ online).	1 paper published, 2 accepted for publication.
3.2 10 in-depth case study reports on RU in development research projects at Group of 24 universities	10 case studies completed and disseminated to multiple audiences on DRUSSA.net and special interest platforms and site, through seminars and RUM conferences.	10 case studies completed and disseminated
3.3 Development of an operational DRUSSA M&E Framework to inform regular M&E reports	Synthesis of quarterly progress reports published as an End of Programme Outcome Evaluation Report and disseminated to internal DRUSSA audiences	The End of Programme Outcome Evaluation report is the final DRUSSA report submitted before this Programme Completion Review. Programme staff intend to disseminate it to DRUSSA universities for transparency.

Key Points

- 3.1. The journal papers (all open access) are:
  - Grobbelaar, S., De Wet, G., 2016. Exploring pathways towards an integrated development role: The University of Fort Hare. South African Journal of Higher Education 30 (2016): 162-187, http://dx.doi.org/10.20853/30-1-558.
  - Grobbelaar, S., Harber, T., 2015. Towards the institutionalisation of research uptake management in Sub-Saharan African Universities. Accepted for publication in Journal of Higher Education in Africa in November 2015.
  - Grobbelaar, S., De Wet, G., 2016. Research uptake and intermediary platforms: An integrated facilitating system for sustainable community development at the University of Fort Hare. Accepted by Innovation and Development in September 2016.
- 3.2. The majority of the case studies are summaries of DRUSSA MPhil theses (see output 1) which the students have summarised along with giving their reflections on their MPhils. A list of studies is given in annex A. The case studies have been disseminated on DRUSSA.Net and the DRUSSA team reported that they are being disseminated by the authors at conferences though no examples were given. The DFID review team looked at the case studies and deemed them to be concise and informative. However, the review team were not able to find the case studies on DRUSSA.Net which raises concerns that the documents would not found by those who could make use of them.

Summary of responses to issues raised in previous annual reviews (where relevant)

In response to a recommendation in the previous annual review, CREST used some of the programme budget to make the journal articles openly accessible.

Recommendations for future programmes

The decision during implementation to include summaries of Masters theses developed under output 1 of the DRUSSA programme as case studies and to support the students to write the case studies themselves was a good one. It provided an opportunity for them to practise communicating to different audiences. Future capacity strengthening programmes should consider how learning can be reinforced through involvement of individuals in delivery of different programme outputs.

Output Title	The DRUSSA network is well informed about all elements of the programme, peer learning is encouraged, and relationships in the region are strengthened to sustain universities' capacity for research uptake.
Output number per LF		4	Output Score	A
Risk:		Minor	Impact weighting (%):	10
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Progress
4.1 Number of universities that are providing examples of research uptake outputs that can potentially influence, inform and affect their identified audiences/users.	Up to 40 members of the communications network, from 18 universities, take part in user-centred activities/events / Participants report improvement in research uptake communication skills/understanding / 50% of universities provides at least one example of a project-level research uptake communications campaign on their website	Over 80 people were involved in this year’s campaign on repurposing research for different groups. / Participants reported that they had gained knowledge and confidence. / 13 of 22 universities published an article or blog on the university website.
4.2 Audience size for DRUSSA.net and other DRUSSA communications	Public use of DRUSSA.net is maintained (43,500 unique visitors annually). / Network of 900+ registered professionals working or interested in research uptake receiving the DRUSSA eDigest and eAlerts. / At least 18 universities have contributed an additional 1 or more articles in the year sharing learning and progress; published on DRUSSA.net the e-digest and delivered at regional workshops/ symposia.	In year 5 there were 143,527 unique visitors. / 1,256 professionals are registered to receive the e-Digest and e-Alerts. / 20 universities contributed 1 blog for DRUSSA.Net with 13 of those contributing more. Some of the work was presented at RIMA conferences.
4.3 Regional network relationships, particularly RIMAs, are strengthened to support continuation of the universities' capacity for research uptake management	Regional networks, particularly RIMA committees, commit on areas where they can support continuation of research uptake awareness and training. / DRUSSA university RIMA members share progress and lessons learned at 4 SSA regional conferences, seminars, workshops or meetings held within the programme duration.	The 4 African RIMAs have committed to support continued awareness and training in research uptake and have incorporated research uptake into the African RIMA Professional Competency Framework. / DRUSSA university RIMA members have shared progress at 3 sub-Saharan African RIMA conferences (6 papers).

Key Points

- 4.1. This year’s campaign, which involved working directly with teams in universities and putting on events, was repurposing research for different audiences. Participants chose a piece of research produced previously and repurposed it. 53 Research Uptake Communicators (38 female) from 21 universities participated in a peer-learning event in Johannesburg to prepare material for university websites. The DFID review team appraised the website articles and while they were of varying quality, they were generally informative and easy to read.
- 4.2. The number of unique visitors to DRUSSA.Net in the final year of the programme has exceeded expectation. Unfortunately OSD has not measured the number of downloads or whether and how people use the information they find.
- 4.2. Around two-thirds of all registrants are people who have not participated in the DRUSSA programme.
- 4.2. Learning and progress has been shared by DRUSSA university representatives at RIMA conferences, but there is no evidence of it being shared elsewhere. However, DRUSSA, through consortium partner OSD, has had a presence at most of the relevant regional meetings.
- 4.3. There are 4 Research and Innovation Management Associations in Africa – West Africa (WARIMA), Southern Africa (SARIMA), East Africa (EARIMA) and Central Africa (CARIMA). On behalf of the RIMAs, SARIMA has secured funding for a short course and train the trainer guide aimed at high level long-term issues that universities have to manage in order to be contributors to socio-economic development. This course will be accredited by CREST and rolled out in three years’ time.
- 4.3. Research uptake was included as a main conference theme at the three RIMA conferences and DRUSSA was invited to run a workshop for research managers to introduce them to research uptake. CARIMA did not have funding to run a conference. One of the DRUSSA champions at Buea University in Cameroon has been Chairperson of CARIMA.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous annual review recommended that the programme consider how to make DRUSSA.Net resources available following the programme. A non-active version of DRUSSA.Net will be available for one year following programme completion to enable DRUSSA universities to make the most of the content. A compendium of materials has been selected from DRUSSA.Net and will become part of the Learning Resource that will be hosted on the ACU website beyond the life of the programme.

Recommendations for future programmes

Where websites are established (subject to approval by the Government Digital Service), it is essential that use of those sites is measured, particularly given the scale of investment that is often required to develop websites. While there are challenges in finding a suitable mechanism to measure use, Google analytics alone will not sufficiently demonstrate how useful the content is. A recent DFID-funded evaluation of online research portals found that the majority of users enter sites through a Google search for a specific topic or article so the number of unique users or time on the site is not necessarily a good indicator of relevance.

Output Title	Political leaders and civil servants within 6 development oriented government ministries in Ghana and Uganda have improved capacity and incentives to use research evidence within the formulation and implementation of development policy.
Output number per LF		5	Output Score	B
Risk:		Major	Impact weighting (%):	10
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Progress
5.1 The extent to which Ministers and senior civil servants in six ministries actively engage with policy-focused research during and following attendance at policy symposia.	60% of mid-level civil servants interviewed report increases in top-down requests for and interest in research evidence.	In Ghana, the number of daily requests for evidence by civil service managers almost doubled. In Uganda, 58% of survey respondents reported an increase in requests from one or more of their senior colleagues.
5.2 Existence of evidence to indicate changes in both the formal and informal working cultures in the selected ministries to encourage the use of research evidence in policy formulation and policy implementation.	Fellows report indications of changes in the informal working culture when compared against baseline in 4 out of 6 ministries. / Formal policies and/or procedures are in place or in development in at least 3 of 6 ministries.	There is some evidence on indications of changes but it is not clear whether these will be sustained when DRUSSA ends as many examples may be linked to fellowships or policy symposia. / In Uganda, training courses for civil servants about using evidence are now being adopted nationally.
5.3 Number of civil servants within selected ministries possessing and applying skills to seek out and use research evidence within their policy-related work	60/90 participants demonstrate improvement in skills/understanding in post-course assessment / 50% are reported by Fellows to be applying those skills in the workplace. / 50% or 3x baseline (whichever is lower) of policy documents reviewed, reference an evidence base.	A total of 93 people in Uganda and Ghana attended short courses. 94% reported an increase in understanding and 74% gave specific examples of how they would apply the skills. / No assessment by Fellows was carried out. / There is no reliable evidence that civil servants have developed evidence-informed policy without support from DRUSSA Fellows.

Key Points

- 5.1. During the course of the programme 27 policy symposia were held (15 in Ghana; 12 in Uganda). These were attended by Ministers, senior civil servants, mid-level civil servants, researchers and DRUSSA Fellows. Civil society, the private sector and the media were also represented. The topics were chosen by the ministries. In Ghana, each symposium focused on a discrete policy issue of importance to the national agenda, such as the impact of currency fluctuations. In Uganda, each Ministry had separate symposia to discuss topics of interest, such as education or agriculture.
- 5.1. In Ghana, civil servant survey respondents (response rate unknown) reported that following policy symposia the number of daily requests for evidence from their managers had almost doubled. In Uganda, 58% of survey respondents (69 people out of 120 to whom questionnaires were sent) reported an increase in requests from one or more of their senior colleagues. In both countries the number of requests for evidence by Ministers decreased. The DRUSSA programme team suggests this was due to increased satisfaction with the amount of evidence contained in documents submitted to ministers by civil servants. There is evidence, albeit limited, that decreased Ministerial demand was not because Ministers had become less committed to evidence-informed policy-making.
- 5.2. DRUSSA placed twelve Fellows in ministries in two cohorts. Increased interest in, and confidence in using, research evidence is confirmed by the ministerial capacity assessment survey, especially in terms of increased interaction with Fellows, which raises concerns over sustainability after the fellowships end. Fellows reported indications of positive change in the informal working culture of the ministries, though this evidence should be treated with caution due to risk of optimism bias. Much of the evidence provided by Fellows links to work they had done with ministry staff themselves or could have been related to the policy symposia. Therefore it is not clear from their examples whether the changes will be sustained when DRUSSA ends. However, there is some evidence reported by ministerial staff in Ghana which indicates sustainable change in informal working practices. For example:
  - “I have a deepened understanding on basic tools and how to relate well in job place”
  - “I have acquired the skills to be able to differentiate a good research from a bad one.”
  - “Knowledge in research has increased. It has aided me in writing papers on taxation and reviewing others’ work.”
- 5.2. In Uganda, the Ministry of Public Service manages all formal working policies. DRUSSA staff met with the Ministry and use of research evidence is now integrated into the professional development offering for civil servants including parliamentary civil servants. No evidence was provided on development of formal policies to encourage the use of evidence in Ghanaian ministries.
- 5.3. In Uganda, a short course on “handling science and evidence” was developed with the aim of enabling senior policy advisors and programme managers in ministries to improve their ability to understand, commission, evaluate and use research evidence. The course was delivered to 43 participants from the three target ministries. A masterclass based on the Executive Education course drew 57 participants from 21 ministries, some of whom were from the three target ministries. In Ghana, 50 middle-level policy professionals were trained through a short course consisting of three modules. No post-course assessment of skills developed was carried out in either country.
- 5.3. One of the roles of the Fellows was to support course participants in applying their acquired skills in the workplace. The Uganda Ministry Capacity Assessment Survey indicated that 79% of the programme participants were applying their skills, though it is not clear whether all of these had attended training courses. In Ghana, no assessment was carried out by the Fellows on skills use by course participants.
- 5.3. In Uganda, the baseline for policy documents referencing evidence was zero. The programme team felt it was not feasible to undertake a further review of policy documents due to observer bias since the only documents they had access to were those that the programme had influenced. By the end of the programme key policy review support documents for the National Energy Policy, Universal Education Policy, Early Childhood Development Policy, National Agricultural Policy and National Fertiliser Policy that were produced by the three target ministries were evidence-intensive. However, the Fellows played a role in development of those policies so the extent to which civil servants have the capacity to carry out evidence-informed policy development in the future is unclear. No evidence was provided for Ghana.
- Overall, this was a challenging and ambitious output area within the timeframe. The programme team have had difficulty in directly assessing against the targets set, but anecdotal evidence from a small number of discussions with beneficiaries in this area suggests that there have been a number of positive and unintended outcomes. While the focus was on upskilling ministry staff, the Fellows themselves reported improved professional development through the programme and provided examples of how they have promoted better working practices within their own institutions – ensuring policy-relevant research products. There is also some evidence to suggest that the relationships developed between ministries and academics will continue beyond the end of the programme, on an informal basis.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous annual review recommended that gender representation at the symposia be improved. This was a focus in both countries in year 5, though gender representation depended in part on the gender make-up of the participating ministries and universities, which is predominantly male at senior levels. Female participation at symposia in both countries in year 5 actually decreased slightly.

Recommendations for future programmes

While this output is relatively difficult to design indicators for, there are some clear lessons for future capacity strengthening programmes. First, it is important to avoid subjective assessment, particularly where it is likely to be affected by self-interest such as the possibility of Fellows being overly optimistic about the impact of their work on sustained ministry capacity. Secondly, targets should aim to assess changes that can be sustained beyond the end of the programme.

While the focus of this output was on national government, the programme found that a number of participating universities were engaging with local level government. This was particularly successful when supporting the development of a specific policy reform. Future programmes should consider the potential impact of engaging at local as well as national level.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The primary cost driver has been staff costs, with staff spend representing 43% of total programme spend. This has been invested in a number of activities including: supporting institutions, whether on an individual basis or through delivering events such as the benchmarking conferences; designing and delivering courses; and facilitating lesson sharing.

Travel and accommodation costs have featured strongly as a cost driver in the last 2-3 years of the programme (approximately 42% of expenditure during that period). These costs were incurred for programme staff, participating universities and Masters/PhD students.

VfM performance compared to the original VfM proposition in the business case

The business case tied programme value for money to results. It also stated that value for money of activities would be managed through procurement and active comparison of costs for training and facilitation inputs, etc.

Following a recommendation in 2013 the programme made efforts to restructure activities and cut strands that were not providing good value for money. For example, investment in output 4 was reduced, with the interactive online “Coffee station” being closed as it had not been as well used as anticipated. This meant that there was less interaction between and with the universities online but to compensate the programme focused on how people were communicating.

The year 3 annual review recommended that the programme team develop stronger VfM measures. Measures were then developed into a VfM framework but, despite a recommendation to carry out data collection at the year 4 annual review, the framework was only populated with data at the end of the programme. These were discussed at the Project Completion Review meeting with the DRUSSA team. The key indicators (all related to economy) suggests that the DRUSSA component interventions were relatively expensive (often reflecting design and start up costs):

- Around £20k was invested in each Masters/PhD student. In comparison, an overseas student at Stellenbosch University pays around £10-12k per year for fees for a Masters course but DRUSSA students also had their travel and accommodation costs paid for by the programme when they travelled to Stellenbosch for courses and contact time with supervisors, sometimes for a month at a time.
- The cost of the online science communication course which started being delivered in year 5 (4-6 hours a week over 6 weeks) was £315 per participant. This included the staff and direct costs invested in design so the cost per participant will therefore significantly decrease as the course is rolled out further. In comparison, under the DFID-funded Strengthening Research and Knowledge Systems programme, an online research writing course cost up to £6 per participant per day in FY2014/15, but that did not include design costs.
- The average cost of each benchmarking conference (3 days) per participant was £1,540. This included flights, accommodation, catering and conference facilities.
- In the year after DRUSSA.Net was launched, the cost per use was £2.57 due to relatively few visitors and design costs. By the end of the programme the cost per visit was 1 pence, reflecting both low maintenance costs and relatively high numbers of visits.
- The policy symposia cost around £126 per participant to run. Under the DFID-funded Building Capacity to Use Research Evidence programme, similar events in Zimbabwe cost around £75 per person.

Regarding efficiency, participating universities made in-kind investments in the programme (e.g. staff time, provision of venues) which kept programme costs down. Although an estimate is not available, it was standard practice across the institutions and a positive sign of commitment to programme objectives.

Regarding effectiveness, expecting university investments in-kind and taking other actions to ensure university buy-in such as involving Vice Chancellors, and establishing DRUSSA Leaders, Champions and Communicators meant that the programme gains are likely to be sustained and built on after the end of the DRUSSA programme. The DFID review team gathered anecdotal evidence from beneficiaries in Uganda that the work had made a positive impact on policy-making. Even if the impact on capacity strengthening within ministries were limited, the Fellows had made a significant contribution to evidence-informed policy development which should have a positive impact on poverty reduction within the target countries.

Assessment of whether the programme represented value for money

Comparative costs with other programmes should be treated with caution due to different contexts and the cost factors included in the calculations. With these caveats taken into account, the DRUSSA programme performed less well than its counterparts from a cost perspective in producing programme outputs. However, based on our assessment of performance against the log frame with the majority of outputs meeting expectation and evidence of sustainability, we feel that on balance the programme provided good value for money. It would have been beneficial if the programme had measured value for money earlier in order to provide a clear demonstration and make improvements in relation to economy.

Quality of financial management during programme

The quality of financial management has improved throughout the programme, though issues remained in the last year, such as inaccurate (though improved) forecasts and quarterly underspends. DFID recognises that a change it requested regarding quarterly forecasting and a number of changes in DFID programme manager throughout the programme have made the task of improving financial management more challenging. Programme staff were slow to populate the VfM framework with data, meaning that there was less opportunity during programme implementation to assess value for money and make improvements.

Money is not directly granted to the universities involved in the programme, reducing the complexity of the financial management and hence the risk of fraud and corruption. There were no fraud or corruption concerns during programme implementation. The year 4 annual review recommended that ACU’s fraud, bribery and money laundering policies be collated into a single document. This has not been done but is still an intention of the ACU.

Date of last narrative financial report	21 September 2016
Date of last audited annual statement	31 July 2015

E: RISK (½ page)

Quality of risk management over the life of the programme

The DRUSSA team maintained a risk matrix over the course of the programme.

Key risks in relation to participating universities included:
- Dwindling commitment to the programme. This did not materialise. The number of participating universities decreased from 24 to 22 due to issues outside of the programme’s control (two universities merged and one dropped out due to political issues), but commitment from the 22 universities continued right to the end. A concerted effort to involve Vice Chancellors and establish Leader and Champion roles was likely to play a role in sustained commitment.
- Staff turnover. This was a particular a risk for the training aspects of the programme because trained staff might leave the university without passing on their skills. This did not transpire, and some course participants had their roles expanded to incorporate their new skills. The train the trainer events helped to mitigate this risk by seeking to embed the programme’s commitment to individual level capacity strengthening into institutional structures.
- Women’s participation in Masters courses which they did alongside work at the universities. Support mechanisms were deployed as issues arose.

Key risks in relation to programme management included:
Managing finances across different currencies. The South African Rand hit a 10-year high during the course of the programme. With DFID’s permission, ACU bought currency ahead of time, at ACU’s risk if it was not used up. This enabled planning around spend which would otherwise have been driven by currency fluctuations from one month to the next.

Unanticipated risks included:
- Issues external to the programme which affected delivery, such as ebola and terrorism. The programme team ensured it had sufficient back-up plans and flexibility in case these kinds of events happened.
- The programme manager was ill for some time in 2015. ACU was quickly able to identify cover for her role so that the programme could continue to be implemented.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme generally delivered what it set out to deliver. There were concerns at the year 4 annual review that there were some minor delays and potential further delays, particularly in relation to output 1 and output 5 in the final year of the programme. Some activities were not delivered until the last few months, such as a number of policy symposia, online science communication courses and the train the trainer course for universities. This has limited the time available to assess sustainable outcomes from those activities.

Performance of partnership (s)

Partnerships were essential to DRUSSA given the breadth of outputs in this complex programme. The presence of CREST and OSD in the consortium meant that DRUSSA had a presence in sub-Saharan Africa, which meant that OSD staff could easily attend events associated with output 4 and in the case of CREST means future provision of research uptake courses. The addition of partners in Ghana and Uganda when output 5 was added meant that close oversight of activities was possible.

The DFID and ACU (lead grantee) partnership has been good overall. This was a complex programme, including a number of outputs, and the review team acknowledged the challenge of explaining it to each new DFID Research Uptake Manager who became responsible for the programme as the programme progressed.

Asset disposal and value obtained by DFID

The programme made no investments in assets over the value of £1000 using programme funds. As part of the Project Completion Review we have agreed, with approval from the Head of Department, that the following assets be disposed of in the following ways:
- 1 iPad bought for ACU will be transferred to another DFID-funded programme.
- 2 laptops bought for CREST are too old for upgrade or use according to Stellenbosch University’s IT department. They will be scrapped according to the conditions set out in DFID’s Smart Rules.
- 1 desktop bought for CREST and a printer and multifunction device bought for OSD will be transferred to CREST for use by the DRUSSA PhD students (who should complete their PhDs within the next two years), students attending courses developed during the DRUSSA programme that CREST will continue to run and students participating in the new research uptake and science communication Masters and PhD courses.
- 2 laptops and a desktop bought for OSD will be sold based on resale quotes.

G: CONDITIONALITY (½ page)

Partnership principles assessment

Not applicable. The DRUSSA programme was a global programme and did not provide funding through country government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

DRUSSA was designed as a responsive programme so it was adapted as needed. The logic behind the theory of change has remained accurate and unmodified. There was a review at the end of year 2 which resulted in changes in output 2 and output 4 activities, mainly for value for money reasons.

Owners of outputs 3 and 4 in particular kept an eye of external evidence that might influence activities.

The addition of output 5 in year 3 of the programme was as a result of DFID-funded research into African governments that highlighted an unhealthy distinction between supply and demand.

No evaluation of the DRUSSA programme is planned.

A Ghana country case study was carried out by an external consultant in the final months of the programme to assess progress towards programme outcomes amongst key beneficiaries. The findings were drawn on by the programme team while assessing programme against log frame indicators and writing their final report, but the final output is not accessible and work is required to ensure the main lessons and insights from the programme can be shared with others.

Data collection was good with regards to inputs e.g. how many people attended a conference and whether they were male or female. The majority of participants at courses, Higher Education symposia, Vice Chancellors’ meetings and policy symposia, and the majority of Leaders and Champions, were men. This is mainly due to the targeted participants being senior within their institutions, and in African universities and ministries senior staff tend to be men.

Monitoring progress throughout the programme

Monitoring of the programme by the programme team was informed by a Monitoring and Evaluation Framework and followed through with numerous surveys, questionnaires and case studies across the programme outputs. These were used to identify change as well as to inform DRUSSA design. The DFID review team appreciated the rich data that the programme was able to offer, but noted that more could have been done to collect data on learning outcomes and demonstration of skills following training and data on use of DRUSSA.Net.

As part of the Programme Completion Review, the DFID programme team spoke to a small number of beneficiaries. This process complemented the delivery team’s reporting and allowed a deeper understanding of how the programme is viewed by those who have experienced different aspects.

The progress of this programme was monitored by DFID Research Uptake Managers, through quarterly reporting and quarterly phone meetings held with the programme team. The current DFID Research Uptake Manager attended a meeting on Thursday 22 September 2016 with ACU and CREST to discuss outputs 1 and 3. The current DFID Research Uptake Manager and the most recent DFID Research Uptake Manager attended a 2-day Project Completion Review meeting at the ACU on 27 and 28 September 2016. The review meetings consulted the programme team: Karrine Sanders, Dr John Kirkland, Ben Prasadam-Halls, Liam Roberts, Sara Calamassi and Paul Walker (ACU), Professor Johann Mouton, Dr Sara Grobbelaar and Marthie van Niekerk (CREST), Diana Coates and Alison Bullen (OSD) and Ismail Barugahara (UNCST). Review meetings drew on the draft DRUSSA final report and appendices provided.

Annex A: List of case studies produced under output 3

Original document	Authors and university	Title of case study
Research team project	Sunita Facknath (Mauritius)	Quantification and movement of sediments and agrochemicals under various types of mulches
Research team project	Yap Boum II (Epicentre, Mbarara University)	Saving lives of children with proper malaria rapid diagnostic tests
Journal article	Sara Grobbelaar (CREST); Gideon de Wet (UFH)	Exploring pathways towards an integrated development role: The University of Fort Hare
Journal article	Sara Grobbelaar (CREST); Tom Harber (ACU)	Towards the institutionalisation of research uptake management in Sub-Saharan African Universities
MPhil	Damaris Mbui (UoN)	Research utilisation at the University of Nairobi
MPhil	Samuel Mutarindwa (UR)	Research utilisation at the university of Rwanda: College of science & technology
MPhil	Theogene Nyandwi (UR)	Research utilisation at the university of Rwanda: College of Medicine & Health Sciences
MPhil	Frederick Owusu-Nimo (Ghana)	Research output and collaboration in Ghana
MPhil	Eme Owoaje (Ibadan)	Perceptions of researchers at the University of Ibadan about users’ utilisation of research results
MPhil	Heather Ndlovu (NUST)	Science communication at the NUST in Zimbabwe

Annex B: Summary sheets from previous annual reviews[3]
[3] The template used for the first 2 annual reviews did not include summary sheets.

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Development Research Uptake Sub Saharan Africa (DRUSSA)
Programme Value: £4,973,903		Review Date: September 2014
Programme Code: 202004	Start Date:10 Oct 2011	End Date: 10 September 2016

Summary of Programme Performance
Year	2014	2013	2012
Programme Score	A	A	A
Risk Rating	Medium	Medium	Medium

## Summary of progress and lessons learnt since last review
Overall the Development Research Uptake Sub Saharan Africa (DRUSSA) programme is performing well. The programme is supporting 22 Universities in Sub Saharan Africa to improve their capacity to undertake research that is relevant and appropriate for intended users, to communicate it well and maximise the chances that it will used by stakeholders.

The programme is contributing to a significant change in some universities as they recognise the need to ensure their research contributes to the well-being of their local and national populations, whether it is though working with local communities on local challenges to health, livelihoods, etc, or though contributing evidence to national policy debates. The Universities also recognise this means they need to change the way they do things and the DRUSSA programme can help. By the end of the 5 years the majority of the 22 universities will have improved their capacity to ensure research evidence contributes to pro-poor policy and practice.

The new extension to the programme, aimed at improving demand for university research at the level of (selected) national ministries, has been running for a year. This element of the programme is making good progress, although it has been subject to some delays.

The programme partners continue to work well with the universities and their efforts are clearly valued by the universities. We commend the partners focus on catalysing sustainable change through the programme.

Management across the programme and collaboration between the partners is improving. However, there is still potential for more cohesion between the different outputs, which the programme team recognise. Allowing more time for partners to plan together may help to ensure that the whole team’s work is greater than the sum of its individual activities, working to achieve the overall outcome.

One of the major recommendations of last year’s review was to assess the communications work and improve Value for Money (VfM). Change in this area has been completed and we are pleased to see the readjustment of the programme to provide more focussed individual support to the universities with less spend on broader communications.
## Summary of recommendations for the next year
- Continue to improve programme management by streamlining process for working together across so many partners; increasing effectiveness and reducing transaction costs. Time saved could be used to ensure sufficient time for joint planning to maximise the synergies between the outputs to achieve the overall outcome. Strengthen accuracy of forecasting during the course of each quarter.
- Prepare the Terms of Reference for the independent evaluation by early 2015 so that evaluators can be appointed in sufficient time to evaluate the impact of the programme so far and report before the end of the programme.
- Develop stronger Value for Money measures, with information on these collected over the next year.
- Ensure there are opportunities for joint planning between partners to continue to improve synergy between different parts of the programme.
## Outputs
- Centre for Research, Evaluation, Science and Technology (CREST) should ensure that it discusses its four day consolidated course with other partners so that it maximises the opportunity to build on the work they are doing through the support function and working groups.
- The accredited online science communication course that is developed by CREST should be offered at a discounted rate for DRUSSA universities.
- As the Association of Commonwealth Universities (ACU) considers how it will support universities with decentralised training, based on the survey of activities in this area recently completed, it is essential this is done in consultation with CREST and considered alongside the accredited online courses being developed to ensure that DRUSSA funding is maximised.
- A communications plan for the literature review and case studies should be developed and implemented to get maximum value from the documents (CREST are aware of this need).
- We recommend the programme team closely monitor the quality of the fellows appointed and the level of support they receive. Given there are very few fellows it will be important that they are effective and have a workload that makes best use of their time.
- The programme should ensure that the pressure to deliver multiple symposia in a short time frame does not compromise the quality and that this part of the programme has enough human resource to support this.

Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Development Research Uptake Sub Saharan Africa (DRUSSA)
Programme Value: £4,973,903		Review Date: 18-19 August 2015
Programme Code: 202004	Start Date: 30th Sept 2011	End Date: 30th Sept 2016

# Summary of Programme Performance
Year	2015	2014	2013	2012
Programme Score	A	A	A	A
Risk Rating	Medium	Medium	Medium	Medium

# Summary of progress and lessons learnt since last review
The DRUSSA programme continued to make steady progress during the past year, putting itself in a strong position to achieve lasting, sustainable outcomes in the final year of implementation. This will be in part dependent on the success and pace of activities that take place during the next twelve months, which includes comprehensive sharing of evaluative programme learning with immediate partners and the broader sector.

DRUSSA is supporting 22 universities across twelve countries in Sub Saharan Africa to improve their research uptake capacity, in order to maximise the chances that the research they produce will used by stakeholders. The programme implements a range of activities at multiple levels, including training at the individual level (from short courses to PhDs), the strengthening of organisations through support to strategy formulation and the development of appropriate operational structures. A limited amount of resources have been reserved to influence the environment universities are working in, through activities such as high-level symposia on Higher Education with relevant government ministries in DRUSSA countries, which appear to have been successful.

The progress that universities across the programme have made varies considerably, which is largely to be expected given the range of different contextual and environmental challenges that they face. It is inevitable that all of the universities will still have some capacity weaknesses by the time the programme is completed next year. Therefore it is important that DRUSSA helps to diagnose areas which require further strengthening following programme completion, so that universities can implement research uptake reforms independently. However, the programme’s support to university change programmes to embed practices that improve research accessibility, and its interactions with regional Research and Innovation and Management Associations (RIMAs), is improving the sustainability of work and strengthening longer term institutional links.

The DRUSSA extension project, which commenced in 2013, is working with three ministries in Ghana and three ministries in Uganda to increase demand for research evidence from policy making institutions. It is facilitating high level symposia on relevant policy issues, providing training to civil servants on use of evidence and seconding researchers into the ministries as policy fellows. Whilst this work has inevitably been subject to delays related to political issues, good progress has been made this year and there is the potential for activities to become embedded beyond the life of the programme, with a high level of interest from ministries to expand links with the research sector.

The previous annual review recommended that improvements were made to programme management practices by; ensuring more cohesive planning across output strands; reducing the transaction costs of collaborative working; and working more closely on an ongoing basis. Feedback gained from the review suggests that partners are working more closely and joint planning has become stronger, improving the effectiveness of programme management.

The previous review also recommended further development of Value for Money (VfM) measures and construction of a Terms of Reference for the planned independent evaluation that will take place next year. The programme was initially very slow to act on this and although more progress has been demonstrated recently in the form of a draft set of VfM indicators, these are yet to be populated with performance data.

Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMPas part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised throught the duration of the programme which were not forseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process