Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime.

Agencies should use Section M to provide a short summary from each Annual Review over the life of the programme (maximum 1 page per year).

Review Date:	09/08/2016

Title: Saferworld Programme Partnership Arrangement / CHASE PPA
Programme Code: 202709	Start Date: 1 April 2011	End Date: 31 March 2016

Summary of Programme Performance

Year	2012	2013	2014	2015	2016
Programme Score	A+	A+	A+	A+	A+
Risk Rating	Medium	Medium	Medium	Medium	Moderate

Financial Position

Original Programme Value	£5,217,490
Extensions/ amendments	£3,478,320
Brief details of the 3 most recent log-frame revisions with dates	2014-16 – extension logframe – defined target for the 2 years extension / 2013/14 logframe included South Sudan, Kyrgyzstan and Tajikistan in addition to the original 12 countries (2011 logframe), demonstrating the effects of decisions made using the PPA funds.
Total programme spend	£8,695,810

Other DFID Funding

See Annex A

Short Summary from each Annual Review over the life of the programme, 2011-15

See Section M

A. Introduction and Context (maximum 2 pages)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202709
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202709

Outline of programme and what it has achieved at the end of the PPA period

Year 5: Saferworld (SW) continued to consolidate its community security work with individuals and communities. We trained and supported a total 106 community action groups including15 new groups in 4 countries (a total of 42 new groups in last 2 years), that implemented 105 action plans to address threats to security identified collaboratively at community level. Our partnerships with civil society organisations and networks/platforms/coalitions led to the training of 213 Civil Society Organisations (CSOs) in 10 countries (a total of 424 in last 2 years), many of whom are accompanied or mentored regularly, to influence authorities. 28 authorities (37 in 2 years) at national and 64 at subnational level (86 in 2 years), in 8 countries, have developed or implemented new approaches/policies in part as a result of SW and partners’ technical input.
We could see more substantial and sustainable changes in relationships and behaviours between communities, CSOs and authorities, for instance in Somalia (CSOs and Electoral Commission working together in preparation for the elections), in Kyrgyzstan (law on ‘police evaluation criteria’), Kenya (national and county governments working with CSOs to draft the National Peace Council bill), South Sudan (by-law passed by Minister of Local Government against carrying guns in public places), or Nepal (CSO invited to facilitate annual local budget planning). These achievements are the result of consistent, longer-term involvement in these communities, with a key focus on creating and maintaining trust, and encouraging active engagement and empowerment.

At the global level, working to influence external actors, SW was instrumental in shaping the 2030 Agenda to address root causes of violence and armed conflict, specifically inclusion of Global Goal 16, and shaping the Indicator Framework[1] This is the result of several years of work and engagement with important partners, networks and decision-makers, particularly in countries like Brazil, China, India, South Africa and Turkey.
[1] Reference 3

At national governmental level, we raised awareness of the SDGs framework through consultations on the prospects of implementing its peace-related aspects in Kenya, South Sudan, Myanmar, Pakistan and India. Through innovative research, strategic partnerships and global advocacy, we also contributed to the development of a robust and effective indicator framework.

At the European Union (EU) level, SW produced an operational guidance handbook for conflict-sensitive EU programming, and has been leading a team of consultants contracted by the European Commission to develop an online course on conflict sensitivity to guide the design and implementation of EU projects.

SW, together with Conciliation Resources, has influenced EU conflict analysis and early warning processes through engagement in 32 contexts across Africa, Asia, Middle East and Latin America. SW published in-depth research on constructive alternatives to current counter-terrorism approaches, looking at US, UK and EU counter-terror, stabilisation and state building in Afghanistan, Somalia and Yemen. At the organisational level, there has been a more consistent use of our innovative outcome monitoring and harvesting methodology. We published a report on five years developing and implementing this, Doing things Differently[2], which has been widely circulated and downloaded (835 downloads). We designed a micro-site for our Programming, Monitoring, Evaluation and Learning Guide, which includes our gender-sensitive conflict analysis methodology in which we trained 12 SW trainers, and developed a new gender and conflict toolkit. Working together with the Uganda Land Alliance and London School of Oriental and African Studies (SOAS), SW piloted the toolkit in Moroto District, in the Karamoja region of Uganda in March 2016. The results have shown how shifts in access to resources and livelihoods have had an impact on people’s ability to live up to societal notions of masculinity and femininity. These changes have exacerbated existing grievances and tensions between communities, the government and multinational mining companies. The toolkit will be further used and tested in Saferworld programmes in Yemen, Somalia, Sudan and Myanmar.
[2] Reference 10

We successfully bid for and won two commercial tenders and contracts, an indicator of significant organisational development.

Lifetime of PPA: SW has come a long way as a result of PPA funding. When SW was first awarded the grant, we had a staff group of 77 in 9 countries, with pilots or early stage community security work in Bangladesh, Caucasus, Kenya, Kosovo, Kyrgyzstan/Tajikistan, and South Sudan. We had offices in Kosovo, Kenya, Nepal, Uganda and South Sudan, with four or five staff in each. We had an experienced and committed policy and advocacy team, working to achieve a UN Arms Trade Treaty (ATT), and three Security and Justice advisers, one communications officer, one planning and evaluation adviser, three HR staff, and a small operations, finance and funding team.

Our ambitious new Strategic Plan (2011-14) committed us to working at a greater level of scale, with a more global perspective, and testing our ability to respond to crises. We conceptualised our work for the first time around behaviour and relationship change, focusing on four important categories of actor: individuals and communities; civil society; authorities and external actors. We introduced strategies, consistent conflict analyses, outcome mapping and theories of change for all our programming, substantially advanced our MEL work, and committed to serious change in scale and reach. We aggressively pursued substantially larger funding for work in South Sudan, opened up work in MENA, scoped out programming in Myanmar, and widened our programming in Somalia. We chose to test two options for working at a greater level of scale (working with one large partner in Bangladesh; become a larger operational programme in South Sudan), based on the relevant context and the underlying principle of agency and ownership from local organisations.

In mid-2016, SW can point to significant progress, and some noteworthy achievements. We have programming in South Sudan that reaches into eight states, with nine local partners, eight field offices, supporting 35 community security working groups, working to alter their own local environments. Moreover, this was despite a three-month period in 2012 when our operation would have closed had it not been for PPA funding. We managed a security-induced evacuation of all staff in 2013 and returned almost immediately, adapted our programme, and expanded, having more than doubled our income from other donors. We have just won a competitive tender for the multi-donor conflict sensitivity resource facility, and have a staff cadre that is 12% East African, 88 % South Sudanese.

We have opened an office in Yemen, and maintained a staff group there throughout the conflict. One of our pilot community security working groups CSWGs has kept working, entirely self-managed and sufficient, addressing local needs created by the conflict. We have secured funding for a programme in Myanmar, achieved through careful relationship-building, scoping and conflict analysis undertaken by our staff and paid for initially by PPA funds investment. In Bangladesh, by working with BRAC we have introduced community security into 16 communities, with a core staff of only three. We have also opened an office in Somalia, for the first time, and won substantial funding for civil society-led processes on domestic election monitoring, and community security. By far the most challenging work has been investing with our civil society partners to advocate at national level and hold authorities to account. We have some successes with civil society engagement in policing reform through platforms, with evidenced influence on police reform in Kenya, Kosovo and Kyrgyzstan[3] and with new national legislation on small arms and light weapons (SALW) in South Sudan. And at sub-national level, we see positive changes between communities and authorities around police /community relations in Nepal, Georgia, Bangladesh, South Sudan, Kyrgyzstan and Kosovo.
[3] Reference 4, reference 7 and reference 8

At the Global Level, we celebrated the culmination of 20 years of uninterrupted work on Arms Control, with the adoption into force of the ATT, and committed to carry on and support attempts at implementation. Our long-standing staff, often supported by strategic funds such as the PPA, made their expertise count as brokers, advisers, mediators, and coalition-builders. We used what we had learned advocating for the ATT to play a brokering and leadership role in the review and negotiations for the new SDGs, and our evidence shows that SW made a contribution much greater than its size, in both successes[4].
[4] Reference 2 and reference 3

In all of these endeavours we invested PPA funds initially, with a view to leveraging funding from a wider pool of donors, while ensuring that the PPA income was used strategically to plug short gaps, keep essential staff, shore up our management, finance and MEL systems, track value for money (VFM), and create much needed security planning and support. SW’s mix of programming, policy, and learning enables the organisation to have much greater influence than its size would suggest, and this comes from judicious use of flexible and tied programme funding, and investment in staff, partners, and learning. SW now has 16 offices, 153 staff, 47 partners, reaching substantially larger numbers of conflict affected populations (an estimated 610,870 persons minimally), and can point to really global policy influencing that may reach many more.
## B: PERFORMANCE AND CONCLUSIONS (6 pages maximum)

Overall Outcome Assessment  Outcome (relating to Bangladesh, Caucasus, Kenya, Kosovo, Kyrgyzstan/Tajikistan, Nepal, Pakistan, Somalia, Sudan, South Sudan, Uganda, Yemen, and global policy):Individuals and Communities, Civil society, Authorities and External Actors strengthen their approaches and capacities for preventing violent conflict, building peace and addressing the needs of conflict-affected (or at risk) communities, (in accordance with SW's organisational change model)
In SW’s baseline report, we detailed working at the community level on issues of safety and security, through a community security 4 stage approach, in Bangladesh (2 pilot sites), Caucasus (16 Community reference groups in Shida Kartli, 2 South Ossetia, 5 East Abkhazia), Kenya (16 peace committees), Kyrgyzstan/Tajikistan (11 CSWGs) Nepal (7 CSWGs), South Sudan (3 assessments).
Most of these were either pilots or at an early stage of formation. By 2016, our community security work has expanded to 16 sites (BD), 18 Kyrgyzstan/Tajikistan, 5 districts and 30 RDFs in Nepal, 10 locations in 8 states in South Sudan (population served 140,000), has shrunk in Caucasus, and been refocused in Kenya around police monitoring forums. We have added work in Yemen (2), one of which has sustained itself throughout the current conflict, Armenia/Azerbaijan (1) and Kenya (8), adding up to 130 groups in total, reaching at least 611,000 people in conflict-affected communities.
Each community sets its own locally-specific approaches based on detailed analysis (Community Security Assessments and Mapping), develop action plans involving authorities, and receive seed money to address community priorities. There is significant evidence of change generated through these plans and processes, ranging from locally-designed and implemented agreements to create safer markets, reduce revenge killing from cattle raiding, support emergency police services (South Sudan); responses to emergency needs of conflict affected population (Yemen); generating local data for incident reporting and/or working closely with authorities on early warning and action (Kenya; Georgia proper; Armenia/Azerbaijan); active leadership by young men and women to negotiate with local authorities (Nepal, Yemen, Bangladesh, South Ossetia); creating fora for community/police relations (South Sudan, Bangladesh, Central Asia, Nepal); raising awareness and increasing reporting on crime/Gender Based Violence - GBV (Kenya, Bangladesh, Nepal, South Sudan); addressing land rights and local state border conflicts (Uganda, South Sudan); and research on masculinities and conflict (Nepal).
Our Community Security handbook, published after 10 years of work and a key result from our Community Security Learning and practice group (supported by the PPA) has enabled this scale up in many different contexts, and been used by UNDP (training on their programmes) DFID (deep embedded resource) and Dutch MoFA (manual). Using PPA funds to invest we have leveraged funding from additional donors (USAID in Nepal, INL in Krygyzstan/Tajikistan, Dutch MoFA and Embassy in South Sudan) to increase the scale of our work.
In our baseline report the organisation detailed working with CSOs in Central Asia (2), Yemen (4), Uganda (1) Caucasus (2), Nepal (1), and Somalia (3). We now have formal MOUs with 49 organisations across 12 countries, have trained at least 200, and have detailed evidence of the many ways in which those organisations and networks have supported communities to create community working groups (as above), train community-based organisations (CBOs) in conflict analysis/resolution (Pakistan 89, Nepal 65), advocate with those communities for greater state responsiveness (formation of 38 Police-Community Relations Committees in South Sudan); 23 in Bangladesh; involvement in local budget monitoring and conflict sensitivity of local planning (Kenya, Nepal, Uganda); bringing community perspectives, gender sensitivity and recommendations to police reform processes (Kenya, Kosovo, Krygyzstan, Egypt), consulting and coordinating across communities to develop bottom up recommendations for external actors (Somalia, Yemen); playing an active part in accountability processes (domestic election observation in Somalia, police-community relations in Central Asia, Kosovo, South Sudan) and peace advocacy (Yemen).

Our key partner in Kosovo now raises funds exclusively from other sources, and two of our Somalia partners have raised funds independently. As part of our working at scale agenda, we partnered with BRAC in Bangladesh to bring security issues into their community empowerment model, and a new approach to community-led outcome reporting.

Our relationship with Yemeni civil society activists means we have been able to continue to work with local youth initiatives throughout the conflict on Facebook pages (1100+ members) and our regional innovative WhatsApp peacebuilding training (part of our programme adaptation) for activists (220 youth across the governorates).

We supported over 50 CSOs, across 16 countries, through a major EU-funded programme, Capacities for Peace, focusing on early warning systems as a conflict prevention tool. As just one example, noted in our IPR 2012 and our most recent evaluation, the nascent youth network on police reform in Krygyzstan, Civic Union, was clearly in its infancy and its work disconnected to national level advocacy with a hands-on role being played by SW. By 2016 Civic Union has shown it can organise local research (400+ participants), national level roundtables, and advocate on key local priorities to representatives from the Ministry of Internal Affairs, Parliament, local police and local authorities, and has been invited to be part of a new parliamentary working committee on amending and updating the National Law on Police[5].
[5] Reference 1 and reference 7

In our baseline report the organisation detailed technical support processes to authorities in Kenya, Kosovo, Nepal and South Sudan focused on National Peace structures (Kenya), SALW legislation (South Sudan), police reform (Kenya and Kosovo)[6], and the National Action Plan 1325/1820 (Nepal).
[6] Reference 4 and reference 8

To date we can demonstrate SW and partners significant contribution to police reform processes including influencing the inclusion of community policing and security in national strategies, in Kenya[7], Kosovo[8], and Krygyzstan[9], SALW legislation in South Sudan; conflict sensitivity of local and national level policy in Uganda and an increased understanding of the principles of conflict sensitivity in the development and implementation of the Peace, Recovery and Development Plan for Northern Uganda (PRDP)[10].
[7] Reference 8
[8] Reference 4
[9] Reference 7
[10] Reference 9

We supported key governments throughout negotiations on the detail of the scope of the ATT with technical expertise, and have since been very involved in ATT implementation involving officials from 12 West African countries; the EU ATT Outreach Project in Ghana and Zambia; and started our first national assessment of ATT implementation in Liberia[11].
[11] Reference 2

In our baseline report we detailed three areas of our work to influence external actors: policy/practice recommendations; training of key staff in conflict sensitivity, and DFID focused briefings. To date we have successfully completed two global policy processes which show SW’s ability to influence global debates and have our messages included in key UN processes: the ATT[12], and the 2030 Agenda.
[12] Reference 2

We can evidence substantial SW achievements: expanded and deepened support for the inclusion of peace within the global policy community; reduced resistance of influential rising powers as key blockers; successful technical advice (scope of the ATT, and content of the monitoring framework adopted by the UN Statistical Commission in March 2016).[13]
[13] Reference 3

We can demonstrate technical inputs to Chinese companies in South Sudan (conflict sensitivity assessments of infrastructure), and success in providing confidential HelpDesk support to both DFID (CCVRI) and SIDA (latter contract just renewed) and The Netherlands MFA’s new Security & Justice policy framework draws heavily on SW’s work.

We produced an operational guidance handbook for conflict-sensitive EU programming, and have now been awarded the competitive tender for the Conflict Sensitivity Resource Facility in South Sudan through DFID, on behalf of a donor consortium. The resulting Global Study from the UN High Level Review on Women, Peace and Security reflected important themes in SW’s work, including the need to challenge militarisation and address the role of masculinities.

We provided input to the UK-led Preventing Sexual Violence in Conflict Initiative adopted by the G8 and the UK’s National Action Plan on UNSCR 1325. SW’s China programme established an innovative Conflict Prevention Working Group comprising Chinese and UK policy experts from a range of backgrounds (including universities, think tanks, non-governmental organisations, the military and consultancies), to engage over two years in constructive dialogue with experts in the field of conflict prevention.

SW has trained a minimum of 379 external actors in conflict sensitivity and produced 80 DFID/UK Government-focused briefings over five years.
Changes to capacities in relation to results[[1]]
[[1]] Results can include outcome and output level achievements which may have been reported in the logframe, or may be external to logframe results.
Development of capacity and systems: SW has used the PPA to make demonstrable improvements in its capacity and systems to enable the implementation of its strategic vision -evident in two strategic plans to date. The unrestricted and flexible nature of this funding has been used strategically, and as such tracing the capacity and systems development to results and better VFM requires us to take an overview and provide examples. Capacity development can be described in the following ways:
Core functions capacity – this is defined as funding, finance, management, human resources, operational/security, communications (internal and external) and organisational development/MEL. In the five year period we have increased our funding capacity across the board and decentralised that capacity in one regional environment (East Africa), while integrating policy, MEL, and communications staff into proposal development; we increased our finance capacity through recruitment of a Director, Manager, and regional/project staff, and training for all budget holders and finance staff; we invested in human resources staff at HQ (Director) and country-level in 10 locations, revised our performance management processes, and recruited managers at country and sub-country level to facilitate scale up; in operational terms we have opened offices in eight states in South Sudan, in Pakistan, Central Asia (4), Bangladesh, Myanmar, Yemen, Somalia, with necessary operational staff to support scale up, and closed offices in Kosovo and Sri Lanka; we have invested in security advisers in our most volatile environments, introduced SOPs, and Security Plans for all environments, and HEAT training for appropriate staff. To enable coherence across the organisation we increased our communications capacity to support internal information and knowledge-sharing through an intranet, and redevelop our website into a centre of excellence. Finally, our MEL capacity has increased from one expert, to six, with four of those based in country programmes for the first time, and paid for from grant-funding.
Core systems: these increases in capacity benefit from the following systems: a funding database to track our funding pipeline; a new SUN financial system used in an integrated fashion across the organisation;, a standardised performance management system with CASCADE; a Security and Risk Management system; an internal intranet and upgraded website; an organisation-wide programming approach (Conflict Analysis, Theory of Change, outcome mapping, strategies) and biannual outcome monitoring and harvesting methodology; a three year strategic planning cycle; and a structured approach to learning-by-doing through Learning and Practice Groups. We have developed and instituted manuals and handbooks for finance (local and global), staff (local and global), protocols for fundraising and communications, and guidance and training for conflict analysis, theory of change, and outcome mapping and harvesting.
Programme and policy/advocacy capacity: our staff represent our greatest added value, and at the same time enable our in-depth accompaniment and capacity-strengthening approach to partnership. This staffing has increased by 48% in the time frame, which includes significant planned growth in our programmes in South Sudan, Central Asia, Nepal, and piloting/innovation in Yemen, Egypt, Myanmar, Pakistan and Sudan. We have relocated policy/advocacy staff to regional or country offices (Kenya, Nepal, South Sudan and Uganda), while retaining and expanding global expertise in London on Security and Justice, Arms Control, SDGs, China, Rising Powers, and Gender. We have developed an ‘advocacy platform’ approach, with capacity in Brussels, London, Beijing and Washington.
Systems to support programme/policy/advocacy development: our PMEL micro-site, funding protocols, advocacy toolkit, Learning and Practice Groups, and upcoming gender and conflict tool kit all support staff and partners. Our twice yearly institutional outcome harvesting feed into our biannual organisational reporting, and are used for external accountability to funders and partners alike, and feed into our learning products. Our quality review of publications gives programme and policy staff rapid feedback from peer reviewers. Staff are offered secondments where possible, and given time to participate in evaluations or reviews of other programme work. New management processes include staff development plans.
Results and VFM:
Finance and Funding: the new SUN system and finance capacity leads to greater absorption capacity, more timely tracking of over or underspend, better analysis of cost drivers, on-time reporting and improved financial accountability chain with partners. This has enabled scale-up in South Sudan, Krygyzstan and Somalia. Our successful audits demonstrate good financial management, and our ability to win competitive bids and commercial contracts has increased, as has our diversity and volume of income (2011-12 = £6.7k and 2015-16 = £12.1m = 85% growth).
HR/Operations/Security: the new performance management systems, People in Aid, membership and HR managers in-country support substantially larger programmes funded on a performance basis, evidenced by successful scale up in Kyrgyzstan (from programme largely managed through frequent international visits from London staff[14] to decentralised local management of full programme funded by INL, three offices, with seven staff and necessary systems) and South Sudan and consistent support to Yemeni staff throughout conflict, hibernation, and continued programming, all managed remotely.
[14] Reference 1
Management structure: a new management structure and approach devolves decision-making, and leads to faster, more efficient expenditure, and programme adaptation. This can be seen in South Sudan and Yemen, in conflict break-outs, and in necessary adaptations for scale up. It reduces the need for international travel for management purposes, ensuring staff exchanges are focused on programme and policy learning.
Programme/policy/advocacy/MEL: improved design of programmes, through developed theories of change linked to our strategic plan in all programmes, and a more sophisticated monitoring system focused at the level of changes, rather than just outputs, shows in high evaluation scores in bids, and high scores in reporting. Active support from PPA-funded communications and MEL staff can be seen to have results in partners capacity, their advocacy, and the results that stem from them (e.g. communications team trained LYA to produce policy briefs, these directly influenced the police recruitment and police evaluation criteria in Krygyzstan[15]; Somalia Non-State Actors Platforms -NSAs- thematic Policy Groups spawned work on election observation and led to new independent Domestic Observer platform SCISEF with own funding)[16]. Our new website circulates and promotes the work of partners through news, blogs, twitter, online annual review, Facebook, and is used demonstrably more as a centre for expertise and materials. Our policy work is successful at global level (see p6).
[15] Reference 7
[16] Reference 5
Sustainability of capacity changes: As stated in our IPR, ‘a main financial function of the PPA is to support core management and policy staff, enabling SW to retain staff, experience and learning’.[17] This hasn’t changed substantially, although it has been expanded to include communications and MEL leadership, innovation and learning. SW’s public policy work success is demonstrably a direct result of retaining expert staff[18] sustained over the long-term by building contacts, and strengthening networks and coalitions[19] and being ahead of the curve[20] through judicious use of strategic funds. Similarly, SW engages in countries and programmes over long periods and creates sustainable partnerships through extensive capacity building.[21]
[17] Reference 1
[18] Reference 2 and reference 3
[19] Reference 1, reference 2 and reference 3
[20] Reference 3
[21] Reference 4, reference 5, reference 6 and reference 7

The PPA has allowed scope for innovation that can attract project funding[22] - demonstrated in Armenia/Azerbaijan (line of control incident reporting); Shida Kartli (Early warning and response platform MyElva), Yemen (remote WhatsApp training) - and support learning (outcome harvesting, Learning and Practice Groups -part funded by other grants) enabling linkages between programmes, policy, and advocacy to be more than the sum of their parts. It has enabled SW to strengthen its management capacity and systems in a period of grant-led expansion in order to increase the scale of programme work where appropriate[23],and this can be seen from the results we have achieved, alongside the change in our funding profile.
[22] Reference 1
[23] Reference 1

The proportion of PPA to overall income has reduced from 25% to 14 % over this period, and the results have expanded considerably (as above). The use of PPA funds to support gaps in funding for both SW and partners[24], start-up scoping and laying foundations[25], or sustain long-term policy outcomes[26], demonstrates strategic use of limited flexible funding as an investment to leverage greater funding. This investment is critical, as an organisation like SW without a funding stream of individual giving/marketing can only operate if its leadership, fundraising, impact and accountability, communications, and policy expertise is enabled to generate the additional value required for greater reach. 0% investment cannot generate any returns, whereas it is clear with the right mix of expertise, capacity and systems, an organisation the size of SW can do considerably more through small investments of flexible funds, without losing its added value (expert staff, long-term partnerships and shared learning for the sector).
[24] Reference 7
[25] Reference 2, reference 3 and reference 7
[26] Reference 2 and reference 3
As such, priorities and mechanisms for sustainability revolve around SW’s key added value.
Retaining capacity to work on the ground in high-risk, volatile, fragile settings, on conflict, security and peace-building;
- High quality experienced staff to design and implement context-specific programming that is conflict and gender-sensitive, adaptable to rapidly-changing environments, regularly reviewed and learned from, and feeds evidence into national and global policy priorities;
- High-quality experienced policy/advocacy/communications staff that lead research, collect evidence, provide technical support, operate as facilitators and brokers, lead global policy processes, link these to national programming and commit to implementation once policy has been reformed or agreed;
- High-quality and experienced communications, MEL, funding, finance, human resources, operations, and risk management staff and systems that link and support programming across countries
Prioritising investment in partners as key actors in social change in conflict affected and fragile environments, and through them to support conflict affected communities on holding their politicians, elected officials and appointed officers to account
Building learning into all programming
Mechanisms to sustain changes include building higher % of costs of key staff into programme/project grants, locating staff in appropriate, more cost-efficient places, maintaining a core staff group in HQ to ensure leadership, organisational coherence and protect key added value, investing in leadership and processes to ensure good VFM without compromising on quality, working in consortia with southern partners, streamlining learning budgets through all programming.
Funding of partnerships: Our range of partners varies considerably with context: what kinds of organisations exist, which issues they address or are permitted to show interest in, what approaches they take to effecting change and what resources they draw on are all shaped by the political, social and economic climate. In many contexts there are few or no organisations working on the topics that SW specialises in, not least because of their sensitivity, so SW often ends up trying to 'grow its own' partners by either working with nascent and not-yet-formal groups (e.g. women activists in North Africa) or by partnering with organisations that are strong in related areas but have not worked directly on the relevant issues (e.g. BRAC in Bangladesh, INSEC in Nepal). This means that to a considerable extent the nature of SW's partnerships is shaped by the range of choices available in a given context and how these map onto its agenda.

Whilst there is substantial evidence to suggest that SW’s work with partners has resulted in some sustainable change – both in terms of tangible results related to activities as well as broader changes in relationships and behaviour – there are also several factors that challenge sustainability of our partners in the short and longer term. As a general point, on-going funding for small local organisations, most of our partners, is scarce. The lack of core funding and the dominance of short-term project funding from other donors restricts partners’ ability to sustain the changes in their interventions and build organisational and operational capacity.

Sustainability of partners needs to be built over a long term partnership. Our accompaniment model involves relationships at different levels of engagement, and in many occasions the provision of core funding to partners. For instance, our partnership FIQ in Kosovo lasted 10 years and involved at least 14 serving members of SW staff working directly with FIQ at some point both on project-related activities and in capacity-strengthening (SW’s communications supporting FIQ’s communications strategy; SW’s HR providing advice). In addition, over its ten-year relationship, the flexibility to undertake relevant, responsive programming, and the support to core costs from SW was fundamental to FIQ being able to build its institutional capacity. FIQ started with an annual income of less than €5,000 and is now an organisation capable of handling funds of up to €350,000 annually, reporting on expenditure to multiple donors[27].
[27] Reference 4

The stability of the context/country also impacts the sustainability of local organisations. In Somalia, Saferworld set up the NSA Platforms and has focused on capacity-strengthening and supporting the diversification of their funding base. Now they are seen as valuable actors in policy dialogue around key state building, democratisation and governance issues by both local and international actors, authorities, communities and other beneficiaries. However, this still has not turned into donors directly funding them at the levels needed – platforms with an approx. turnover of USD200,000. We are currently engaged in a long-term transition towards their financial independence - combined funding from all our projects was 95% last year and 85% this year with a view to reducing to 75% next year. An immediate drop in 75% of their funding may lead to these key platforms disappearing[28].
[28] Reference 5

SW has been very busy fundraising against anticipated loss of the PPA and in the short term we have been able to secure funding for some of our partnerships, particularly in the next couple of years –e.g. South Sudan, Kyrgyzstan and Somalia. However, this is very limited project funding and does not fund the intensive capacity strengthening, nor key core costs of partners, that can contribute to sustainability over time. In addition, working in a number of conflict affected/fragile states requires SW to be flexible and responsive to partners’ needs considering the changing contexts where space may be shrinking and conflicts are still latent.
Learning: The alignment between the PPA grant and SW’s organisational strategic plans ensured resources were utilised effectively, and investments in capacity development were relevant and linked to forward-looking strategic goals. Our experience led to key lessons and insights on how investments in capacity brought added organisational value (see above).

SW’s income more than doubled over five years, and while some level of growth was likely regardless of the PPA, establishing and maintaining an infrastructure to sustain quality, accountability, learning and effectiveness would not have been possible without the flexible attributes of the grant. Further, the strategic nature of the instrument proved indispensable for operating in conflict affected and unpredictable environments, where flexibility, responsiveness, adaptive management are the hallmark of effectiveness.

Output Score and Description
A+ Outputs moderately exceeded expectation

## C: DETAILED OUTPUT SCORING (1-2 pages for the table and 1 for the narrative). This section should provide a summary of progress in Year 5 only, and should be repeated for each output.

N.B. Output tables can extend over 1 page, where agencies are able to present full disaggregated data. However, agencies must keep within the 1 page limit for the narrative.
Please apply the new risk ratings provided in the Guidance (giving only 1 per output).

Output Title	SW and local partners provide support to community members in identifying and addressing their community security and justice needs in collaboration with local authorities (Y2011-2014 in Caucasus, Kenya, Kyrgyzstan/Tajikistan, Nepal, Pakistan and South Sudan; 2014-2016 in Bangladesh, Caucasus, Kyrgyzstan/Tajikistan, Nepal, South Sudan and Yemen)
Output number per LF		1	Output Score	A+
Risk: [please select only one per output, using the new DFID risk definitions]		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Disaggregated data
1.1 Number of action-oriented community groups formed (and continually supported) by members of conflict-affected communities - with SW support - through which communities can identify their security related needs and priorities, and develop a shared purpose and vision for change	15 action-oriented community groups formed	15 newly formed action-oriented community groups (total 106 groups supported)	Total number of women (all groups) / 703 women
			Total number of men (all groups) / 1038 men
			Number of groups per country	New	Total
			South Sudan / Caucasus / Kyrgyzstan/Tajikistan / Pakistan / Nepal / Bangladesh / Yemen	7 / 1 / 6 / 1 / - / - / -	35 / 4 / 18 / 2 / 30 / 16 / 1
1.2 Number of groups that successfully implement community security action plans, in dialogue with authorities, with support from SW and partners	70 groups successfully implement plans	105 groups successfully implementing plans	Number of groups per country / South Sudan: 35 / Caucasus: 3 / Kyrgyzstan/Tajikistan: 18 / Pakistan: 2 / Bangladesh: 16 / Nepal: 30 / Yemen: 1
			Number of new actions plans developed / South Sudan: 35 / Caucasus: 4 / Kyrgyzstan/Tajikistan: 18 / Pakistan: 5 / Bangladesh: 8 / Yemen: 1

Key Points - Summary of progress in Year 5
All of the 106 groups supported by SW in 2015/16, 105 have successfully set and delivered action plans with significant changes seen in most communities, even in very challenging environments such as Yemen and South Sudan. In South Sudan the action plans of the community security working groups (CSWG) focused particularly in mapping crime and insecurity hotspots, sharing those with the community and local authorities; on how to address violence associated with cattle raiding, alcohol consumption and the proliferation of arms. Visible improvements were noticed in the coordination between communities and local service providers (35 new police officers deployed in Juba), increased number of crimes reported to the police (community reported the looting of property and stealing of cattle to police in Rumbek Centre), increased number of crimes acted upon by police (paramount chief recovered cattle from Galweng in Rumbek Center), and improved relationship between police and community (police commissioner ordered police officers not to ask for money from community members in Kuajok, Warrap State). In Bor, Jonglei State the CSWG engaged with executive director of Bor municipal council to ban production, sale and consumption of local brewed alcohol as a mechanism to reduce crime rates in Bor town. This was a result of the concerns raised by the community and was addressed by authorities in February 2016.

In Kyrgyzstan/Tajikistan the key issues that the community groups address in their action plans are: tensions between Kyrgyz and Tajik in the border area; radicalisation, including a growing number of people going to Syria; low level of trust in local authorities; and intolerance towards immigrants and ethnic Kyrgyz returning from Tajikistan. In Batken province as a result from their experience exchange with the local CSWG, the youth from the cross border communities took the initiative to form youth groups and taking a leading role in solving inter-ethnic issues and promoting peace among youth. They are also influencing their parents and other adults, which is a very rare situation in Kyrgyzstan tradition.

In the border area between Armenia and Azerbaijan, the CSWGs (Armenian Community Network and Azerbaijani Community Network) have identified the following issues in their action plans: daily violations of ceasefire agreement; lack of drinking and irrigation water; poor night lighting and damaged roads; poor quality of health services (particularly women health services); and absence of village clubs and community gathering spaces, which were prioritise by the communities. Community development/business centres were built in the villages of Jafarli, Agdam and Alibeyli. In Eastern Abkhazia coordination between community representatives, civil society, healthcare, local council workers and a local police officer has identified drug abuse as the main concern. As a result of this process a local youth NGO developed a project proposal for an anti-drugs youth programme, which involves the Ministry for Education, and is currently looking for funds to implement their programme.

In Bangladesh CSWGs identified child marriage, violence against women, child labour, political violence, theft, hijacking, gambling, and drug abuse as the main problems in their communities. The groups worked with local government and security providers to improve relations among community, local authorities and security providers; In a mini perception survey conducted by BRAC (SW partner) respondents said that 75% of their action plans/initiatives – including initiatives tackling gambling, sexual harassment against women and girls, political violence, drug abuse and early marriage – had improved or significantly improved safety as a result of the programme. However, community participants also reported that work was still needed to tackle some security issues; this was particularly evident when communities were asked about violence against women/domestic violence. In Nepal the Youth Group of Baijapur and Kachanuapur VDC also prioritized child marriage as a major problem among youth. The group action plan implemented awareness training (through street drama performances) and played a crucial role in campaigning to reduce child marriage.

In Yemen, the community action group (CAG) in Muthafar have increasing confidence to discuss and engage with other stakeholders on community security and security issues; the CAG have come to be trusted and respected by the local community, because of its access to local authorities and local leaders who supported its numerous initiative/action plans – from work on waste management, food and water provision, electricity and other basic goods to the community. One CAG group member has been nominated by 22 organisations to be the main coordinator of relief operations in the entire district of Muthafar; another who is a police officer has become the head of the Bab Musa police station in Muthafar

Summary of responses to issues raised in the previous Annual Review (where relevant)
Recommendation from the last AR: Saferworld continues to develop explicit national ToCs for all its focus countries that place greater emphasis in its community security work on influencing sub-national authority planning processes, integrating security issues into these rather than developing SW-specific project plans. The continued development of partnerships with local and national authorities, donors and NGOs will be critical to scaling up.

This is an ongoing process, with significant progress achieved as illustrated in examples of our work in South Sudan, where the CSWG increased cooperation and coordination with state authorities and local police (details in section above). In Central Asia, for the first time Tajikistan local authorities participated in the activities of the Local Crime Prevention Centre (LCPC) in the border area and supported transportation of participants. In Jalal-Abad province in Kyrgyzstan regional authorities supported the LCPC by providing funds for the implementation of the action plan (over 10% of the action plan's budget was covered by those funds).

Output Title	In Bangladesh, Kenya, Kosovo, Kyrgyzstan/Tajikistan, Nepal, Pakistan, Somalia, Sudan, South Sudan and Yemen, local civil society organisations receive support from SW to develop the skills and capacities required to play an effective role in addressing conflict-related issues in their contexts.
Output number per LF		2	Output Score	A++
Risk: [please select only one per output, using the new DFID risk definitions]		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Disaggregated data
2.1 Number of local CSOs that receive targeted and tailor-made high-quality training / capacity-building from SW on how to effectively advocate for improved approaches and / or greater accountability from authorities and policymakers, building on the view of their constituents (in Kyrgyzstan/Tajikistan, Kenya, Kosovo, Somalia, Sudan and Yemen)	High quality, tailor-made training / capacity-building provided to 52 CSOs	67 CSOs provided with high quality training	Kyrgyzstan/Tajikistan: 2 / Kenya: 40 / Somalia/Somaliland:3 / Caucasus: 5 / Sudan: 1 / Yemen: 16
2.2 Number of local CSOs that receive training and mentoring from SW on how to support communities to identify and address their conflict / security related needs and problems (in Bangladesh, Kyrgyzstan/Tajikistan, Nepal, Pakistan, South Sudan and Yemen)	20 CSOs have received training and mentoring from SW	146 CSOs have received training and mentoring	Bangladesh: 19 / Nepal: 30 / Pakistan: 17 / South Sudan: 9 / Uganda: 70 / Yemen: 1

Key Points - Summary of progress in Year 5
Saferworld’s work has greater reach, impact and sustainability by working through partnerships. In Somalia and Somaliland, SW provided training to its CSO partners Puntland Non-State Actors Association (PUNSAA), South Central Non State Actors (SOSCENSA) and Somaliland Non-State Actors Forum (SONSAF). These trainings focused on: mediation design, thematic working group revision, fundraising, public financial management and constitutional. In addition it provided orientation and deployment training to voter registration observers in six locations, training a total of 180 persons (120 men and 60 women). With SW support, the SONSAF re-structured the Somaliland Civil Society Election Forum (SCISEF) and proactively expanded their mandate to include long-term election observation (including observing the voter registration process) and resolving disputes between different political actors, to remove obstructions and blockages, and build consensus. SW has also facilitated SCISEF launch in 6 locations and quarterly meetings. In Kenya, workshops with 40 CSOs resulted in CSOs that are members of the National Steering Committee on Peacebuilding and Conflict Management (NSC) forming CSO working groups on governance, natural resources, countering violent extremism and transitional justice, improving coordination within the NSC and with the government and reducing duplication of interventions and competition between CSOs.

With SW support, the Kenyan directorate of peace building and conflict management (DPBCM) invited state and non-state peace actors to meet regularly in preparation for possible election violence during the 2017 elections.

In South Sudan, SW has provided training to nine CSOs (74 men and 30 women) on state level advocacy; conflict-sensitive approaches and research methodology; gender sensitivity; community security and conflict sensitivity. This resulted in Change Agent Association (CAA) one of the CSOs supported and trained by SW in Yambio, and the Adeesa support group association (a women’s organisation), mobilising other CSOs to advocate for peace by organizing a peace conference, showing that, with adequate support and capacity building, local CSOs can take the lead in advocating for peace. This has extra significance in the local context because it is rare for women to take lead on advocacy and community mobilization.

In Pakistan, SW provided training to 17 CSOs (15 men and 5 women) to analyse conflict dynamics, and address these dynamics through their own work. Following these trainings the Board of CTE (Balochistan) decided to include conflict transformation and peacebuilding in their strategy, and apply conflict-sensitive approaches to its youth programming. RAHBAR (KP) has applied conflict sensitive approaches to its natural disaster and resilience programming. CPDI (Islamabad) was able to apply new skills in their community policing programme to strengthen problem-solving approaches.

In Bangladesh, SW aims at the district level to foster collaborative relations and a shared understanding of security dynamics. It supports an informal network of CSOs, media, and academia in the field of peace and security to enhance their visibility and coordination for a more effective mobilisation and advocacy at the national level. With this network SW has organised district level workshops, a national level CSO dialogue and a national event that included also donors, INGOs, experts, and journalists.

In Nepal, SW is supporting civil society organisations and academics from the different regions to enhance their respective monitoring and analysis capacities, as well as their collective contribution to a country-wide early warning system.

In Kyrgyzstan SW provided trainings to local CSOs that focused on: community security; gender sensitivity, conflict sensitivity and conflict analysis; leadership and project planning for youth. SW also provided policy briefs, technical guidance, expertise and support to Civic Union (a national network of 24 CSOs), one of the leading agents actively advocating for and promoting changes in the current police legislation. The result of its work is evident in the recent law on ‘police evaluation criteria’. This is significant as it is the first time in the Central Asia republics that a law has been adopted stipulating that police will be evaluated by the public[29].
[29] Reference 7

In the Armenia/Azerbaijan programme, SW organised a workshop on conflict sensitivity and a workshop on participatory photography for the Civil Society Institute (CSI) and the Humanitarian Research Public Union (HRPU).

Output Title	National and/or subnational authorities receive support from SW and partners to assist them in developing effective policies and practical approaches for building peace, justice and security
Output number per LF		3	Output Score	A+
Risk: [please select only one per output, using the new DFID risk definitions]		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Disaggregated data
3.1 Number of formal / informal governing authorities that receive quality technical input and/or support from SW and partners at the national level, in the development of new policies and practices related to conflict prevention and security and justice (including but not limited to: Caucasus, Kenya, Kosovo, Kyrgyzstan/Tajikistan, South Sudan, Uganda and Yemen)	SW has provided quality technical input and/or support to 5 authorities at the national level	28 national level authorities	Kyrgyzstan/Tajikistan: 1 / Kenya: 21 / Somalia/Somaliland: 2 / Caucasus: 3 / Yemen: 1
3.2 Number of formal / informal governing authorities that receive quality technical input and/or support from SW and partners at the sub-national level in the development of new policies and practices related to conflict prevention and security and justice (including but not limited to: Bangladesh, Caucasus, Kenya, Kyrgyzstan/Tajikistan, South Sudan, Uganda and Yemen)	SW has provided quality technical input and/or support to 10 authorities at the subnational level	64 sub-national level authorities	Kenya: 30 / Bangladesh: 9 / Caucasus: 11 / Uganda: 10 / South Sudan: 4

Key Points - Summary of progress in Year 5
Saferworld’s work with authorities (national and sub-national) is particularly important but challenging to effect changes at community-level. In Kenya, S W supported bi-monthly meetings that included representatives from 21 government bodies together with members of National Steering Committee on Peace Building and Conflict Management to discuss issues on peace and security and develop action plans on how to effectively coordinate responses. SW also supported a consultative workshop with 30 county government officials on the National Peace Bill which focus on developing peacebuilding structures. As a result, the county governments, the national government and civil society organisations drafted the national peace council bill to define the roles of the national and county governments in peacebuilding. The bill includes the establishment of county peace forums, which are representatives of the national peace council at the county level. The CPFs are linked directly to the directorate of peace building and conflict management (DPBCM), which enhances coordination between county and national structures. SW facilitated the county government consultations and the drafters meeting and the DPBCM used its network to bring together all the actors involved.

In Somaliland, SW has provided support to the parliament subcommittee on social affairs & security (PSC) on how to partner with civil society organisations to jointly review the House of Representatives (HOR) legislation. This has included a legal review and 18 consultations across six regions reaching 1493 people. The process is still ongoing, however we believe that the consultations held by the subcommittee will eventually influence the final text of the new HoR legislation and the work of the Civil Society Constitutional Review Taskforce will influence the review and amendment of the Provisional Constitution. As a result of this and the work SW has done with civil society organisations, the Somaliland’s National Electoral Commission (NEC), SONSAF and the Academics for Peace and Democracy (APD) agreed to work together and collaboratively to review the HOR law which governs parliamentary elections for the Lower House in Somaliland, and the NEC has agreed to partner with CSOs in the implementation of voter education for the voter registration process. This is significant because the NEC and the PSC have never collaborated with CSOs before. In this process SW prepared and developed a strategy with SONSAF & APD on how to approach both PSC and NEC, facilitated discussions between the key actors, and negotiated with NEC.

In Abkhazia, SW organised a seminar on community-based policing for representatives of law enforcement agencies (Ministry of Interior, police, and security service) and civil society organisations, and facilitated a study tour for Abkhaz officials in Scotland’s Police College.
In the Armenia / Azerbaijan borderline, 11 village mayors participated in the trainings of community based needs assessment and practical skills workshops.

In Kyrgyzstan SW has provided training on community policing to members of the ministry of interior and facilitated an exchange visit to Northern Ireland.

Finally in South Sudan, SW works with local authorities, which include village chiefs, quarter council, mayors and local police. In total we have trained 96 persons (64 men and 32 women) from these local authorities. These trainings focus on conflict-sensitive approaches and research methodology; gender sensitivity; community security and conflict sensitivity.

SW co-organised a high-level event on Global Goal 16, gender, peace and security in South Africa in March 2016, and facilitated discussions between, 47 representatives from the government, civil society, and development partners in Kenya to raise awareness, discuss relevance of Global Goal 16 and agree joint actions to support it.

Summary of responses to issues raised in the previous Annual Review (where relevant) N/A

Output Title	External actors (incl. donors, external governments, and / or relevant multilateral agencies) receive SW analysis, policy options and training aimed at influencing and strengthening their policies and approaches for engaging in fragile and conflict-affected countries
Output number per LF		4	Output Score	A+
Risk: [please select only one per output, using the new DFID risk definitions]		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Disaggregated data
4.1 Number and quality of research papers and policy briefings / reports published or electronically circulated by SW and disseminated to external actors	44 briefings, papers / reports have been published or electronically circulated	101	Advocacy: 14 / Arms control: 6 / Rising powers / SDGs: 28 / Security and Justice:16 / China: 9 / Constructive alternatives to counter-terror: 10 / Conflict sensitivity: 18
4.2 Number of external actors (disaggregated by gender) receiving relevant, high quality training from SW, or participate in relevant and productive SW-facilitated seminars / roundtables, on engagement in fragile and conflict-affected countries	50 external actors have received training or participated in SW-facilitated seminars / roundtables	540	Thematic area	Numbers
				total	men	women
			Advocacy / Security and justice / Conflict sensitivity / Arms control / Gender, peace and security	83 / 155 / 92 / 33 / 177	47 / 85 / 62 / 30 / 84	36 / 70 / 30 / 3 / 93
4.3 Number and quality of products (including briefings and submissions) provided to the UK Government by SW, which build on evidence and lessons learned from SW programme implementation	The UK Government has received 14 products building on evidence and lessons learnt from SW's programming	28	Some examples: / - 3 country reports on constructive alternatives to counter-terror and stabilisation (Afghanistan, Somalia and Yemen) / - 1 summary report to DFID CHASE, Somalia unit (FCO/DFID), FCO Conflict Department/CSSF Secretariat, FCO Yemen/MENA team, National Security Directorate (FCO), multilateral research group (FCO), Conflict and stabilisation lessons team(SU) / - Written feedback to DFID CHASE on their revised fragile states strategy / - Turkey in Somalia and masculinities briefing shared with HMA Somalia / - Seminar: UK-China cooperative approaches to dual-use and arms trade controls

Key Points - Summary of progress in Year 5
SW was instrumental in shaping the 2030 Agenda to address root causes of violence and armed conflict, specifically inclusion of Global Goal 16, and shaping the Indicator Framework[30] This is the result of several years of work and engagement with important partners, networks and decision-makers, particularly in countries like Brazil, China, India, South Africa and Turkey. SW secured the participation from its country programmes in key debates at the UN, and has been part of Beyond 2015’s and the Transparency, Accountability and Participation (TAP) Network’s working groups on indicators and has contributed significantly to their advocacy outputs. This has included a formal position paper of the TAP Network, which has been circulated widely and endorsed by over 40 organisations. SW was invited to participate in a meeting in Cape Verde in June 2015, which shaped the future work of the Praia Group and has held numerous bilateral meetings with many members of the IAEG-SDGs establishing good relationships with one of the co-chairs. SW has spoken about these issues at numerous high-level events including a meeting on governance indicators in Tunis and at a regional African Union event, which served to coordinate the positions of the African countries on the indicator framework[31].
[30] Reference 3
[31] Reference 3

SW co-authored a briefing paper on ‘Promoting peace through the Sustainable Development Goals: What role for the Forum on China-Africa Cooperation?’, and a blog on ‘China-Africa FOCAC Summit: how China can help African countries advance peace in the 2030 Agenda’ together with SALO ahead of the Sixth FOCAC Summit in Johannesburg in December 2015. The Austrian MFA and Development Agency pledged to integrate outcomes of a SW workshop on Global Goal 16 into strategic review/development of country strategies. In January 2016 European Union EEAS and DEVCO held a joint technical workshop facilitated by SW, to consider how Global Goal 16 will be adopted into policy and practice.

SW strategic plans gives prominence to gender and conflict sensitivity, therefore these areas remain a key focus for training and research. SW measures the quality of its training and research/publications work in two ways: uptake into policies and practices by others and independent assessments based on a set of quality criteria (started in 2015). This is now part of a systematic process of quality control where we can learn how to improve the quality of our publications. The Swedish international development agency (SIDA) is using SW publications (masculinities and global study submission) as part of their staff training on women, peace and security; the OSCE used the masculinities report to help design their first project on masculinities and peacebuilding in Central Asia; MenEngage distributed recommendations from SW masculinities report at a session on masculinities at an NGO conference on women, peace and security; and the Global Study on Women, Peace and Security reflects SW messaging on conflict prevention, early warning and masculinities and referenced SW research.

Within SW programmes, nine country teams develop context analysis on gender as a driver of conflict and programming ideas, and South Sudan team practising greater gender sensitivity in community security work.

Our conflict sensitivity and China teams have completed a conflict analysis for a major road project in South Sudan, and fed into the development of guidelines for the China National Petroleum Corporation to inform their CSR strategy. SW has also been part of major global level initiatives aimed at promoting business for peace, as well as joining an expert group contributing to the development of a publication on measuring the impact of businesses contribution to peace, linked to the implementation of Agenda 2030.

On security and justice, the Justice as Peace expert blog series was launched and has produced six pieces of work in conjunction with senior staff from UNDP (rule of law focus), LSE (climate), the University of Ulster (gender), Cambridge University (architecture and the use of public space), the ODI (SDG goal 16), and USIP (CVE). These are now amongst the most popular articles on SW website.

Through its advocacy work, SW has built contacts within the United States Government and within the policy community in Washington, communicating with the National Security Council, Senate Foreign Relations Committee, and the directors of offices such as the Bureau of Democracy, Human Rights and Labor Affairs and the Office of Transitional Initiatives (USAID). SW has contributed to high-level policy documents such as the US Government’s Quadrennial Development and Diplomatic Review, and now regularly helps to shape policy design workshops such as the Peace and Stability Operations Training and Education Workshop.

Summary of responses to issues raised in the previous Annual Review (where relevant) N/A
DFID recommendations: Saferworld considers engaging in the public health approach to violence prevention as a natural extension of its gender and community security work. This focuses on identifying and addressing the factors that make communities and individuals at risk to becoming perpetrators and victims of violence and may help to enhance the focus of community security plans.

This recommendation, including how looking at conflict and violence as a ‘disease’ can contribute to identifying key conflict drivers and/or mitigation leverage points was considered. It is too early however to adopt this perspective as a mainstream approach to community security interventions, but its potential is being explored. For example, Saferworld recently hosted a visit from the Director of Innovation & Development at Cure Violence, a US-based organization that focuses on a public health approach to violence prevention, considering the epidemiology of violence and how to ‘cure’ it. Cure Violence also participated in a Saferworld-organised session at the 2016 European Development Days focusing on the implementation of the 2030 Agenda for Sustainable Development: the objective was to facilitate a reflection on what makes societies peaceful in order to start leveraging the new development agenda to make a tangible difference to people’s lives.

On a related but still significant theme, that looks at the impact of violent conflict as a public health issue, Saferworld’s Yemen programme supported in autumn of 2015 a consultation process launched by the Yemen Health Network, in collaboration with Medact, to gather views on likely forward trajectories for the health system in Yemen and to discuss ways of supporting health system rehabilitation after the conflict. A workshop summary provides an overview of the key areas covered and outlines responses to scenarios describing future paths for Yemen.

Output Title	SW incorporates new elements into its Monitoring Evaluation and Learning (MEL) system including an Outcome Mapping, Monitoring and Harvesting approach and trials a more systematised beneficiary feedback mechanism
Output number per LF		5	Output Score	A
Risk: [please select only one per output, using the new DFID risk definitions]		Minor	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
5.1 Number of teams collecting and reviewing outcomes on a quarterly basis	100% of SW teams are collecting and reviewing outcomes on a bi-annual basis	Myanmar not yet, Central Asia not in a systematic way / 90% of SW teams collecting and reviwing outcomes on a bi-annual basis
5.2 The number of partners and community action groups that participate in setting outcomes for their work and provide feedback on the changes they are seeing as a result of working with Saferworld.	At least 12 community action groups are participating in setting outcomes for their work, monitoring them and reporting on them.	74 community groups
		Country	Groups
		South Sudan / Caucasus / Nepal / Bangladesh / Yemen	35 / 1 / 21 / 16 / 1

Key Points - Summary of progress in Year 5 –
There has been a more consistent and wider use of the outcome harvesting methodology and review process across SW. In 2015/16 the internal bi-annual reporting process was completed by all programmes and thematic teams. This means that at least twice a year these teams conduct outcome harvesting sessions. SW experience using the outcome harvesting approach has been compiled and published in the learning paper ‘Doing things differently: rethinking monitoring and evaluation to understand change’ in January 2016[32]. Since then the paper has been downloaded 835 times from the SW website, SW was an invited speaker to the Interaction Protection Roundtable in Washington, in November 2015, and presented at a Bond event Evaluation in Campaigns and Advocacy: How do we know if we’re making a difference? in March 2016.
[32] Reference 10

In three country programmes (Kenya, Nepal and South Sudan) there are dedicated MEL staff and all other programmes have MEL focal points, which connect to our Organisational Development Unit to mainstream and roll out the approach.

Saferworld completed an updatable microsite for its PMEL guide, which can be made available off an on-line to all staff. It is focused around our Change Model, peace conditions, actor categories, and five strategic objectives. It guides staff through conflict analysis, power analysis, theory of change, outcome statements, developing strategies, outcome harvesting, reporting, guidelines for evaluation ToRs and SW’s learning approach (cross organisational and Learning and Practice Groups).

We tested our gender-sensitive conflict analysis methodology through a training of trainers (TOT) in December 2015 for a group of 12 staff from across our programmes. The feedback from the participants in the TOT has been incorporated in the methodology and some of those trained have already introduced colleagues in other teams to the methodology and/or have used it in programme activities and team annual planning exercises. Finally, we have also secured funding to develop a Gender and Conflict Analysis toolkit, designed and piloted in Uganda and about to be published.

Partners working with 35 groups in South Sudan have been trained in the outcome monitoring and harvesting methodology, and use their new knowledge and experience to engage directly with community working groups on setting their results. We were also the subject of third party monitoring through our donor in South Sudan, to test ideas about collecting feedback data through SMS from community stakeholders by a third party. The learning from this will be used to improve understanding about the challenges of this kind of approach, and its conflict sensitivity aspects, and fed through into the conflict sensitivity resource facility.

Summary of responses to issues raised in the previous Annual Review (where relevant)
DFIDs recommendation: Saferworld considers the benefit of broadening output and outcome 5 to focus on organisational development. Saferworld also considers how the outcomes identified through the outcome harvesting work can be clearly communicated to DFID against the conflict and security objectives in its strategic plan to feed into next year’s Project Completion Report.

The body of evidence in this report is the product of our MEL system and in particular the methodology to capture outcomes (‘harvesting’). As described above there has been progressive uptake in using the outcome harvesting and review process across SW. In 2015/16 the internal bi-annual reporting process was completed by all programmes and thematic teams, i.e. convening at least twice a year to conduct review and adaptation sessions. This is an ongoing process to deepen the use of this methodology and encourage our partners to participate and adopt a similar approach themselves.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (5 pages maximum) This section is focused on the lifetime of the programme – not just Year 5.

Key cost drivers (maximum of 5 key cost drivers per key cost)

Key costs / List the key costs of the organisation e.g. staff, transport. It would also be helpful to state whether these are fixed or variable costs.	% total budget (FY15/16) / NB this is not expected to add up to 100% as we have asked for ‘key costs’ rather than all costs.	Cost drivers / (Factors that influence key costs e.g. project location, inflation. State whether there has been any change in them that has pushed up costs and whether any identified trigger points have been reached.)	Actions to manage key costs / Summarise what the organisation has done to manage the cost drivers (where this has been possible) and whether this was successful or not. DFID accepts that not all will be possible to manage, so if not please state this.
Staff cost: fixed	49%	Costs are primarily driven by location, i.e. cost of living in each country of operation. No cost of living changes made for UK staff due to poor donor funding outlook. Salary scale changes made for attract new staff to lead commercial tender work.	Staff costs as a prominent driver are closely monitored by: (i) having a performance management system to support efficiency and effectiveness (ii) conducting annual reviews of salaries in all countries by: / - assessing financial and salary conditions and local inflation to review pay scales, and / - an annual Board-level review of proposals for recruitment in each country that is based on local market conditions
Travel costs: variable	9%	Saferworld cannot influence flight cost and often flights routes with few commercial competitors. Low(er) oil prices have held or reduced flight costs in the year	SW’s travel costs (second largest cost driver) are largely paid via two London-based preferred suppliers. Both suppliers are reviewed annually. Costs can only be influenced by carefully booking in advance, avoiding peak seasons where possible and minimising flight-change charges.
Accommodation and meeting costs: fixed	10%	There is a large range of hotels and locations used for conferences.	Costs managed by using preferred suppliers for regularly used hotels and obtaining annual fee quotes; changing locations and timings to reduce conference/seminar costs where possible
Consultants: variable	2%	In our specialist area there are often only a few consultant suppliers	- use preferred suppliers to deliver known quality work / - well-structured consulting assignments, ensuring payment made only on delivery

VfM performance

	How have you assessed VfM in this area? What measures have you used? State whether this has been measured as part of the enhanced VfM offer or since the beginning of the programme.	Performance in this area (if possible, compare performance over the life cycle of the programme).
Economy –whether organisation has bought inputs of the appropriate quality at the right price?	Cost Mapping: Our extensive work cost mapping to realistic in-country targets deliver the best cost for travel, daily living expenses, and venue hire, to ensure they are current and realistic. / Staff retention: we place strong focus on staff retention. We achieve this by offering competitive salaries and including regular rest and recuperation breaks, and by establishing a strong ethos of promoting and encouraging internal capacity-building and advancement opportunities, as well as ensuring staff have access to strong management and HR support. / Cost-effective and minimised international travel: we seek to minimise costs through the utilisation of in-country staff, international travel is booked through country preferred suppliers, usually with 2 different suppliers. All travel is economy class or makes use of UN transport	Cost Mapping: costs have been held largely constant over last 2-3 years for staff and consultants. Travel costs also held, due to a mix of control factors, strong Sterling and lower oil prices / Staff retention: excluding short term contracts and grants coming to an end, retention rates are comparable with previous years / Minimising international travel: Annual data is studied to ensure the best cost is available, for example planning activities to avoid peak periods for costs
Efficiency- how well organisation is converting inputs into outputs? (‘Spending well’)	Knowledge of personnel delivering the programme: our efficiency is based on the quality of our staff delivering the programme. The success of many programmes is contingent on our ability to access the right expertise and knowledge at the right times, and translate this into practical, operationally useful programme work. A high proportion of some budgets are allocated to staff salaries (typically 30%, but some as high as 60%). We believe it is essential for our work, and indeed demonstrates good VfM. / Working with local partners and utilising local resources: We have made long-term investments in developing effective partnerships with reliable and capable local organisations. Over several years, we have mentored local partners, thereby helping to make them more effective agents of change at the local level. / Leveraging resources and funding from equivalent programmes: We continuously seek to leverage resources and identify synergies between different programmes being implemented by staff and local partners. This allows us to maximise VfM and promote the most efficient use of resources.	Proportion of budgets allocated to staff: Utilising our new Sun database, salary costs can be easily analysed across 3 years’ of programme activity by project. We have analysed this data to ensure we are focusing the right level of staff on key projects / Partner expenditure in programme budgets: again, utilising the Sun database, we are able to analyse actual and budget data in 2015-16 / Leveraging resources and funding: learning, synergies, and maximising resources across funding streams can be seen throughout the period with MEL systems, Learning and Practice Groups, payment for core staff, and policy/advocacy integration being jointly paid for from tied-project funding and PPA funds, ensuring that flexible funds are released whenever possible, while retaining a balance for coherence. Examples include Community Security Learning and Practice Group (50% split across funds), MEL staff (increase paid for by project funding in three places), policy/advocacy support (initially only 15% funded by tied-project funds, now 35%)
Effectiveness- how well the outputs produced have had the intended effect/ achieved the outcome? (‘Spending wisely’)	Adopt a robust, relevant and adaptable theory of change: Programme effectiveness is inextricably tied to the quality and salience of the theory of change (TOC). We have extensive in-house experience of developing and adapting TOCs in relevant contexts; Develop MEL frameworks for all programming, improved evidence, and use in commissioned evaluations / Effective risk management, drawing on local knowledge:	PPA funds have supported the development of our Change Model, and PMEL Guide, used in all contexts. Greater success in grants, and competitive bids demonstrate quality of this approach. / All programmes have improved MEL, with considerable evidence collection evident at all levels, tied into an intranet system. This provides primary evidence for evaluators to test and verify. All outputs achieved across PPA, with over-achievement in many areas, plus unexpected outcomes at global policy level. 22 evaluations commissioned, with much higher quality; quality review of publications leading to more streamlining and focus. / Effective risk management, drawing on local knowledge: our regular assessment of security and personnel risks informs all programmes, being informed and resourced by experts, e.g. Somalia dedicated position
If appropriate, please provide details of other ways in which you have assessed VfM that do not sit within the 3 ‘Es’ set out above	Our paper on VFM seeks to understand our added value and to link this to inputs over time, with special focus on the balance between flexible and grant-funding. This allows us to focus our strategic decision making around core added value in three areas: quality of staff, partnerships, and learning. PPA funds allowed us to commission three evaluations which not only asked questions about efficiency and effectiveness, but also sought to test the relationship between financial inputs and significant change, in particular to disaggregate types and sources of funding that had enabled that change to occur. The analyses have been used to draft a working paper for ourselves and partners, in order to better understand the relationship between the values that are implicit in and underpin how Saferworld works and the type of funds needed to realise that change. Those values are expressed through our staff, who tend to stay with Saferworld for long periods and develop detailed expertise on technical issues; the way we work in partnership and through coalitions, building and brokering relationships through long-term accompaniment; and through gathering evidence of the potential inherent in different approaches (community security, perceptions of justice, civil society advocacy on police reform) and sharing it through advocacy, policy and learning both internally and externally. As such, we have sought to understand the cost of our work in relation to these aspects: staff expertise, partnership development, and our learning model.	These studies highlight the extent to which efficient use of strategic funds investment has been a critical factor in maintaining the quality needed for this work to achieve its full potential and be effective over the longer term. They also highlight the need for a flexible funding / grant funding mix, and demonstrate that flexible funding allows SW to maintain efforts when grant funding experiences a hiatus (e.g. when donors are rethinking strategies), invest in core funding or support for effective partners at crucial times in their development, and underpin our evidence collection and learning. / This forms part of management conversations about restructuring, and cutting staff capacity in this period of uncertainty. While we have frozen 8 vacant posts, and made 8 posts redundant we are determined to keep core capacity by using temporary secondments, temporary reduction in working hours, sabbaticals, etc. We know that without these staff we will be unable to compete for alternative or commercial funding, and will be at risk of losing them to private contractors. Our strategic planning period has been brought forward to examine our cost-recovery models, location and capacity of core staff, and investment in seeking other sources of flexible funds (to complement other donor funding and management fees)

VfM Good practice over the lifetime of the PPA programme

Briefly - what are the top 3 VfM good practices that your organisation has implemented to maximise VfM? (this should cover the lifetime of the PPA)	Please give an example of this good practice being used and the impact it had. If there were any VfM savings please state what they were.
Staff costs are the largest cost and therefore this cost is of primary importance. Saferworld has fair salary rates based on real, on-the-ground costs for implementing in complex environments such as South Sudan and Somalia, as well as fair rates in all other locations. We have external experts (Birches) to confirm these salaries are competitive, comparing benefits packages against nine NGOs with similar profiles.	During our last 2 commercial tenders as lead, as well as the survey data stated, we have direct information from UK and European NGOs and research bodies to confirm our view that salaries at Saferworld are appropriate. Comparing this salary data to the CV information on staff quality, qualifications and experience, we are confident that our salaries are reasonable for staff but lower than some similar organisations.
Our infrastructure of offices, giving us reasonable, safe office accommodation with IT connectivity and meeting room space have been set up at a fair cost. Local staff, using their expertise, can maintain low overheads (we have low overheads relative to others in the industry, operating an efficient business structure from modest headquarters) and negotiate with suppliers of a range of services including hotels, car hire firms and venues for workshops, resulting in considerable savings for programmes.	Support costs as a % total expenditure has remained low and consistent over the 5 years of the PPA.
Close accompaniment of partners, including intensive training in financial management (possible because of high-quality local finance staff), communications, core conflict-prevention, analysis and sensitivity approaches, advocacy, and MEL that is straightforward and prioritises the main areas that partners and their community partners wish to prioritise. These bring our expert staff from one part of the organisation to another, leveraging internal experience and support.	Our partners in South Sudan, Yemen and Bangladesh are now proficient in outcome harvesting, and regularly collect data with their communities that they use in their reporting, bring into biannual reviews, and are made available to external evaluation consultants. This process was supported by a combination of PPA and Dutch MFA grant funding over four years (50/50), and enabled core PPA funded staff, and grant-funded staff to support cross-organisational programme development, using an adaptive learning approach. This investment in partners led to an expansion from 2-8 states in South Sudan

VfM learning
Like many small organisations with a PPA for the first time, Saferworld has had to work hard to understand what would constitute a meaningful VFM assessment in our niche area of work. To do so, and to understand how the three Es differ from standard evaluation methodology, we have sought to bring together our learning on cost drivers and benchmarking, and to identify what is the key added value is of Saferworld’s work and approach, to ensure that the value of what we bring to the sector is clear.

Our analysis shows that VfM is a balance between ensuring control of costs where that is possible, using our experienced staff in cross-organisational teams to improve quality and leverage greater funding, decentralising core functions where our operations are substantial enough and can be self-supporting, and investing in staff retention, capacity-strengthening of partners, coalition-building, evidence collection and learning.

We have come to better understand the relationship between the values that are implicit in and underpin how Saferworld works and the type of funds needed to realise that change. As such, we have sought to understand the cost of our work in relation to these aspects: staff expertise, partnership development, and our learning model. The first two were examined through the aforementioned evaluations, whereas the learning model is much harder to disaggregate, as it is built into all our programming, advocacy and policy work.

We can, however, confidently say that SW’s Community Security Handbook which distils 10 years of community security experience, was based on evidence, gathered and analysed through our Community Security Learning and Practice Group, a cross-organisational body that brings together policy, programming, advocacy, communications, and MEL practitioners, and it was as much the process as the output that has added value to this element of our work. This Handbook is now used by UNDP and Netherlands MFA for their programmes, as we as being a well-established resource in DFID. In addition, the potential that our modified outcome harvesting approach has for being a realistic instrument for adaptive, conflict- and gender-sensitive programming (‘Doing things Differently’) is based on five years of practical application.

Quality of financial management during programme ( 1 para max)
The Finance Director reports to the Board on the performance of the organisation against budget. An annual budget is approved by the Board in April each year and formally updated twice a year. All management staff review monthly financial data and explain their performance to their teams, line managers and the finance department. The UK audit of the SW charity covers all entities around the world; in addition all overseas registered offices also receive a local audit, and around 75% of donor funding also receives project audits. All statutory audits were unqualified in all years of the PPA. Senior management were satisfied that the procedures during the year ensured all key financial issues were addressed and no significant adverse control recommendations were received from UK or overseas auditors. Financial management capacity has been built over the 5 years of the PPA as Saferworld has doubled in size. These changes have included:
- Upgraded posts: 6 Finance Manager posts have been created in overseas locations since 2012, staffed with experienced local staff to ensure appropriate performance management and local control environments suitable to their territory;
- Development of a new world-wide finance performance system (implemented to plan and budget in time to commence planning for 2015-16).

Assessment of whether programme represented good Value for Money

a) Reflection of VfM performance over the lifetime of the programme Saferworld is a small peace-building and conflict prevention organisation working in complex, conflict-affected environments, on programming that is primarily focused on behaviour and relationship-change. In 2011 we committed to working at a greater level of scale, which we have achieved in many countries by investing our PPA funds strategically and judiciously. Our overall income has grown from £6.7m in 2011-12 to £12.1m in 2015-16 (a rise of approximately 85%), almost all of which has been raised from donors other than DFID. Our partnership base has expanded to 49 partners in 16 countries, and we reach at minimum 611,00 people living in conflict-affected areas. We spent 2.1% of our total funds on fundraising, much lower than comparable organisations, and punch above our weight in the global policy debates that matter[33]. We have experienced, expert staff, with specialised technical knowledge and resources, facilitation and relationship skills, capacity to orchestrate sensitive work in complex environments, and the tenacity and authority to lead global policy processes. As stated in the VfM learning section above, we believe our progress has demonstrated excellent VfM from PPA funding.
[33] Reference 2 and reference 3

b) Assessment of progress against enhanced VfM offer
Saferworld has an internal position paper defining its vision and definition of VfM. This paper states and explains our commitment and approaches, demonstrating what SW values are and how the organisation invests in those areas.
At the internal level and as part of SW commitment to VfM the following processes have been institutionalised.
On tracking costs:
- Clear definition and identification of key cost drivers are in place,
- Tools and processes to track identified key cost drivers have been developed,
- Procurement guidelines have been reviewed,
- Annual review of high-value procurements to examine VfM in procurements has been conducted.
Reviewing effectiveness:
Saferworld has conducted several reviews on long-term partnerships and policy work. The learning from this is included in the VfM paper. We are using our VfM principles for strategic decision-making processes involving strategic funds. Saferworld remains committed to the continual review of institutionalised processes

Date of last narrative financial report	30 October 2015
Date of last audited annual statement	30 October 2015

E: RISK ( 1 page) This section is focused on the lifetime of the programme – not just Year 5.

Quality of risk management over the life of the programme
The nature of Saferworld’s work, which deliberately focuses on addressing complex drivers of conflict and insecurity in fragile and conflict-affected countries, means that there is a degree of risk involved. Saferworld has developed robust systems to ensure that all aspects of risk are managed, including staff safety and security, operational and financial risk. Saferworld has a risk management procedure embedded in our regular review processes that gives management a high degree of assurance that key risks are addressed. This process involves:
- Annual review of risks, developed by programme and support staff in each country and division
- Risks are identified and scored together with mitigation action to leave a score of ‘resultant risk’
- Risk matrices from each country are reviewed at regional and executive level
- Worldwide risks to the Saferworld group are assessed and mitigation action discussed by the Executive team
- Group-wide risks plus the significant risks from country and divisional teams are summarised and presented for discussion at the Board on an annual basis
- Financial analysis and projections are consistently prepared (including different possible scenarios) and shared with the Board - including anticipating the end of the PPA funding. An outcome of these preparations has been expanded work done in sourcing support from trust and foundations and a further review of cost recover procedures and practices.
Our country and thematic strategies follow well-developed strategic planning guidelines which include diagnostic tools which enable informed risk assessment such as conflict analysis, stakeholder and power analyses, political economy analysis and tailored security assessments (with related security plans) for each place where we are operational. Saferworld’s risk management approach has been consistently strengthened with regional (and where relevant country) risk management teams in place with a revised set of Standard Operating Procedures (SOPs). Risk matrices are reassessed quarterly during the quarterly review process and updated as appropriate. Updates to changing risks are made by exception to the Executive Team and the Board.
In addition to the above process, a Risk Management Team (RMT) in London meets biannually to respond to emerging issues and is focused on staff safety and security. This team comprises the Executive Director and the Directors of HR, Programmes and Policy. Saferworld has also completed and updated DFID’s Overseas Security and Justice Assessment (OSJA) to substantiate organisational risk management efforts (latest update in April 2016). Institutional risk management generally (terrorism, corruption, auditing, procurement) has been prioritised.
Processes are also tailored for each local context. In a high risk environment such as Somalia the programme team formally reviews the country-level risk matrix every quarter in the Senior Management Team (SMT) and undertakes a comprehensive review of the Security Policy on an annual basis. On an operational basis, risks, particularly for security, are reviewed on a trip-by-trip basis to ensure that the latest security information is obtained before clearance is given.

F: COMMERCIAL CONSIDERATIONS (1 page) This section is focused on the lifetime of the programme – not just Year 5.

Delivery against planned timeframe
Over the life of the PPA and extension periods, Saferworld has planned and managed annual budgets as detailed above. PPA funds are invested each year and the progress of spending monitored against our annual business plan goals and three year strategic plan targets. Appropriate actions have been taken to ensure that investments deliver the benefits sought, for example the Sun accounting system, and that projects are delivered on time. Unspent funds are redistributed throughout the year as the need arises to maintain progress against targets.
In overview, we are confident that these processes have ensured all PPA-funded activities have been completed and all funds spent effectively.

Performance of partnership(s)
Partnership with local organisations is a central element to Saferworld’s overall theory of change. During the PPA period we have maintained formal partnerships with nearly 50 organisations in 16 countries, with partners mainly in charge of overall implementation of project activities in their respective contexts, working directly with the communities and local authorities, and Saferworld providing technical support, accompaniment, policy input and advocacy platforms. Our outcome harvesting collectively done with partners and ongoing accompaniment enables us to evidence the changes we have contributed to collectively and supports in the ongoing development of our partnership approach.

The quality and length of our partnership has been key in sustaining our work. In Somalia, Saferworld’s support to three Somali NSAs and their respective members in the three regions, have enabled local perspectives to be heard on a broad range of issues in state building and peacebuilding. Their increased professionalism and improved institutionalisation of good governance mechanisms, has in turn led to their credibility growing with donors, other CSOs, international actors and government authorities[34]. This is evidenced through increased engagement in the New Deal, and in the national 2016 electoral process, including the formation of a taskforce to undertake policy dialogue, public outreach and consultations on the Constitutional Review Process. In South Sudan, the work with our partners has enabled Saferworld to establish a state-level national presence and win a contract to lead a Conflict Resource Facility for donors. In Nepal, the partnership with INSEC and CWIN facilitated achieving the outcomes of the project and partners’ different strengths and capacities were fully realized, and SW’s training and on-going accompaniment meant that partners also learned how to adopt a Do-No-Harm approach in their entire organisational activities[35]. SW provided FIQ with expertise in SALW control and security policy, as well as crucial skills in strategic planning, financial management and project management. Giving FIQ core costs at a critical time for its institutional development helped FIQ make the step change towards becoming a national NGO with country-wide influence.[36]
[34] Reference 5
[35] Reference 6
[36] Reference 4 DFID response to Saferworld PCR The programme completion report (PCR) complements the strong and strategic relationship DFID has had with Saferworld throughout the lifetime of the Programme Partnership Arrangement (PPA). The organisation has clearly shown how its ambitious objectives, set through the lifetime of the PPA, have positively impacted on the poorest communities throughout the developing world. The PPA funding allowed Saferworld to set high-level strategic objectives and follow through in implementation by supporting safety, security, justice and stability in fragile and/or conflict affected countries. Saferworld’s ability to use the flexible funding mechanism effectively is clearly and concisely reported throughout the PCR. For example, when security concerns in South Sudan led to an evacuation of Saferworld staff, the PPA enabled Saferworld to keep its operations open and to return quickly with a new, adapted and expanded programme. UK civil society continues to make a substantial contribution to promoting peaceful and democratic norms around the world. Saferworld has been at the forefront of such efforts, for instance using PPA funding to retain and develop staff and using their expertise to utilise them as brokers, mediators, coalition builders and advisors on the Arms Trade Treaty. This highlights how important and vital the PPA funding was to organisations and for DFID in achieving wider UK objectives. Furthermore, over a 3 year period the UK government successfully lobbied for the Global Goals (GG) to cover areas that were not covered in the Millennium Development Goals. In particular, Saferworld contributed to this effort and was at the forefront of in shaping an inclusive GG16. Moreover, to broaden support for GG16 Saferworld engaged directly with Brazil, China, India and South Africa and secured strategically located states such as Turkey in debates at the UN. It is important to recognise Saferworld’s pro-active approach to successful programme management and the visible results this has achieved. For example, through Saferworld activities in South Sudan citizens had more confidence and more trust in state institutions such as the police to actively report crimes. In Bangladesh, Saferworld has successfully worked with local communities in an iterative manner to improve relations between community members and security provides. Moreover, Saferworld’s direct engagement in state institutions such as the House of Representative (HoR) in Somaliland has proved effective in influencing the text of legislation on social affairs and security. Throughout the PCR it is evident Saferworld has made significant progress towards improving the lives of the poorest in the world. Each output shows the progress Saferworld has made towards positively transforming lives. While a key function of PPA support is to act as a catalyst for other funding it is inevitably unclear to what extent results are the consequence of PPA support and to what extent they are down to other funding (we recognise that due to the nature of the PPA funding these are a consequence of both). Furthermore, despite the strong narrative, our assessment for some outputs is that there is insufficient basis to say that expectations have been substantially exceeded as Saferworld has suggested and we are recommending a downgrading to ‘exceeding objectives’ in places. Transparency and value for money (VfM) are built in to every programme and project in DFID. Effective delivery of aid through DFID VfM guidelines encourages the sector to be efficient in all its aid programmes. The PCR narrates how DFID has directly contributed to organisational changes within Saferworld and how DFID has promoted the ideas of transparency and VfM in delivering aid. DFID has worked closely with Saferworld and its values have clearly been adopted. In addition to the successful progress stated above, the organisation has taken DFID’s recommendation from last year’s annual review and invested in a process to review the quality of its freely available publications to make its dissemination practise reach a higher than anticipated audience. In conclusion, DFID rates this programme as an overall A+ based on their work, organisational changes and achievements over the past 5 years. Appendix 1 PPA Extension reporting Review Date:	31 January 2017 Title: Saferworld PPA Extension Report Programme Code: 202709	Start Date: 1 April 2016	End Date: 31 December 2016 A. SUMMARY AND SUSTAINABILITY Summary of key achievements during the nine month extension period Saferworld trained and supported 125 community action groups (12 new groups) who implemented action plans to address security issues identified by communities (40 new plans in 2016). Saferworld trained and supported 48 CSOs (a total of 463 persons) on gender and conflict sensitivity (in South Sudan, Uganda and Nepal), election security and observation (in Somalia and Kenya), police reform (in Kyrgyzstan and Tajikistan), policy and advocacy (in Nepal), and peace building and conflict resolution (in South Sudan). Saferworld continues to invest in innovation. Saferworld have developed and implemented a remote learning peacebuilding course using the ‘WhatsApp’ (available in English and Arabic) for youth networks in Yemen. Saferworld and its partners supported a total of 307 representatives from local authorities to develop and/or implement new approaches and policies. This include: in Kyrgyzstan a prevention policy for juvenile crime and school extortion; in Nepal with district authorities to adopt Saferworld’s conflict sensitive and community security/safety approaches, and advocate for others to follow; and in Uganda for three sub-counties to budget for land conflict resolution mechanisms. Saferworld secured funding from Dutch and Swedish Ministries of Foreign Affairs to continue work on SDG 16, both at national and global levels. Saferworld’s primary focus has been to help bring about lasting change on the ground in contexts which have experienced profound and chronic conflict and insecurity. In Bangladesh our partnership with BRAC was decisive in influencing their commitment to implementation of Goal 16 in country, with a $10 million project focused on SDG 16 implementation which is currently in development. Saferworld Kenya produced a 2030 Agenda set of recommendations for implementation of Goal 16 and is a key player in the SDG Kenya Forum, actively working on SDG implementation in Kenya. A number of key international donors have now started to engage on how to support Goal 16 implementation. These donors include the Netherlands, UK, Canada, Germany and the European Commission. Summary of the key changes and/or improvements that will be sustained at the end of the extension period Over the past 5.5 years, the PPA funding has enabled Saferworld to: i) engage in countries and programmes over this sustained period and create solid and enduring partnerships through extensive capacity building; ii) retain expert staff; iii) allow scope for innovation that can attract project funding; iv) support learning enabling linkages between programmes, policy and advocacy; v) and strengthen management capacity and systems. Progressive improvement in these areas is making sustained commitment to positive change possible in many contexts where we work. Over this nine-month period in particular Saferworld and its partners in Sudan, Somalia and Pakistan have secured additional funding for five year programming through the Netherlands MFA, Addressing the Root Causes of Conflict (ARC) Fund, amounting to EU15m, enabling us to scale up our work in the same vein as in South Sudan, streamline our learning platforms and reach additional communities. We have assessed and updated our cost-recovery model, and streamlined learning budgets through all programming. If Saferworld and our partners are to sustain the level of quality, flexibility, innovation and cross-organisational learning essential for community security and peacebuilding in highly conflict-affected environments, there must be investment in leadership development. Saferworld also needs to protect our intellectual property and key added value, whilst maintaining a core group of experienced staff in HQ to ensure organisational coherence, risk and security management, good governance and Value for Money (VfM). This means focusing our fundraising on alternative sources of flexible and core funding as a matter of priority. ## B: PERFORMANCE Principle 1	Consolidation of current PPA/SGA work to contribute towards the new Sustainable Development Goals (SDGs) R 1.1: Communities and Civil Society - Consolidating and building on work with community action groups: communicating the lessons learned from S&J programming, and developing an area of work to address perceptions of injustice, and Civil society works with local c2ommunities and/or leaders, providing training, gathering and providing information for wider communication and/or advocacy. R 1.2: National and sub-national authorities: Government institutions in Kenya, Somalia, Uganda and Bangladesh work with Saferworld and partners on a range of issues, including gender and conflict, conflict early warning systems, voter and civic education and alignment of national plans with GGs 5 and 16. R 1.3: External actors: Consolidating and promoting work with external actors (UN agencies, EU, OECD, US, UK, Sweden, INGOs, commercial actors, multi-mandate organisations) on the ATT, gender and conflict analysis, implementation of the GGs (including indicator and baseline development (national and international), cross-sectoral coordination) and constructive alternatives to highly-securitised counter-terrorism interventions . Risk:	Moderate	Impact weighting (%):	50% Key Points - Summary of progress during the nine month extension Saferworld has continued to work with communities and civil society to promote peaceful and inclusive societies (SDG16), consolidating the work of community groups and CSO partners across Kyrgyzstan, Tajikistan, South Sudan, Myanmar, Bangladesh, Yemen, and Armenia/Azerbaijan. In South Sudan, we added a more explicit peace-building component through cross-border dialogue on peace-building and democratisation between South Sudanese and Sudanese youth, and local peace-building initiatives in highly conflict-affected areas in new locations. In Tajikistan, we implemented a new US State Department-funded project on community policing, and in Myanmar a community security project in Karen state funded by the Peace Support Fund. In Somalia/Somaliland we made significant progress on preparation for the elections in 2017, including the development of a civil society election dispute resolution committee, the drafting of new legislation for the election of the House of Representatives, the deployment of election observer teams and widespread civic engagement on the voter registration process. Saferworld Pakistan programme worked with national and sub-national authorities to promote gender-responsive policing in the KP police department, provided training, reviewed guidelines and procedures, and introduced female police desks at police stations. As a result of our country experience and our research on lesson learning (e.g. Western counter-terror, stabilisation and state building efforts in Afghanistan, Somalia and Yemen since 2001, highlighting the track record of these efforts and lessons from them), we won a consortium bid for the Netherlands Knowledge Platform on Security and Rule of Law (KPSRL), and are regularly invited to contribute to strategy development in this area (DFID CHASE, World Bank). We also made significant progress developing justice programming this year, particularly in Pakistan and Myanmar. In Pakistan our ARC programme with Oxfam Novib came out of research on access to justice, identifying bottlenecks and constraints in the criminal justice system, and focuses on alternative justice provision. In Myanmar, a joint Saferworld-ODI report  sets out the common disputes, crimes and injustices that people experience in Mon and Yangon, the ways people seek to resolve these issues, as well as an assessment of the quality of justice they are able to access. In relation to SDG 5, Saferworld’s new Gender analysis of conflict toolkit enables local, national and international organisations and peacebuilding practitioners to research how masculinities and femininities interact with conflict dynamics. We have completed multiple presentations and training sessions and have many planned collaborations to use it (e.g. with Oxfam Novib, Pax Christi, USIP and EC DEVCO). It has already been integrated into our Sudan, Somalia, Pakistan and Yemen programmes. Saferworld tendered for and won the Conflict Sensitivity Resource Facility (CSRF) in South Sudan, a significant commitment by donors to conflict sensitivity in its programming. We also won renewed contracts for Confidential Helpdesks with SIDA and Austrian Aid, aimed at ensuring conflict sensitivity is at the heart of their programming (e.g. assessing conflict sensitivity of programmes in Bangladesh and South Africa), and ensuring conflict sensitive approaches by humanitarian actors (particularly cited as having influenced Sida’s humanitarian engagement). We launched a National Assessment Methodology to enable current or prospective States Parties to the Arms Trade Treaty (ATT) to gain a full understanding of how their existing laws, regulations, institutions, mechanisms and practices are, or are not, in compliance with the ATT. This methodology helps states to identify what steps should be taken, and in what sequence, in order to close implementation gaps in a cost-effective way. Principle 2	Organisational effectiveness R 2.1: Consolidating and institutionalising organisation-wide support to staff to align with relevant components of the self-assessment standards set by the Core Humanitarian Standard (CHS). R 2.2: Consolidating and embedding organisational progress on evidence-based learning approaches across Saferworld’s work including (i) designing programme reviews of theories of change and the related quality of evidence, (ii) utilising data from the evaluation of 5-years of the PPA from organisation-wide sources of evaluation and learning, (iii) through quality reviews of key publications, and (iv) building on pilot VfM criteria/questions for wider application in proposal development. Risk:	Minor	Impact weighting (%):	30% Key Points - Summary of progress during the nine month extension Saferworld was a member of People in Aid, and has sought to apply the relevant criteria from the CHS despite not being a humanitarian organisation. We have a standardised performance management system which aims to promote and encourage excellence at all levels of the organisation, to continually improve its performance, and to enhance the quality of individuals’ work. This approach aims to embed a culture of trust, transparency and openness where constructive feedback on behaviour and performance is seen as the norm. Each staff member has annual objectives agreed with line manager, as well as a learning and development plan. This is intended to align with the Quality Criterion of Pillar 8 of CHS. In 2016 Saferworld launched its Programme, Monitoring, Evaluation and Learning (PMEL) Guide microsite for use across the organisation. The PMEL guide consolidates and brings together all PMEL guidance material developed in the last five years. The guide is aimed at Saferworld staff and partners and allows all to have a clear understanding of how Saferworld plans, measures and assesses the value of its work. The PMEL guide is focused around Theory of Change, Analysis, Learning, Monitoring & Evaluation, and Reporting, with strategies for addressing the drivers of conflict at its heart. Saferworld continues to develop our Outcome Monitoring and Harvesting approach throughout our programmes, and in the last nine months we conducted sessions with teams and partners in our programmes in South Sudan, Kenya, Somalia, Kyrgyzstan, Tajikistan, Uganda and Sudan. The Outcome Harvesting process feeds into our biannual organisational reporting, and is used for external accountability to funders and partners alike, and provides evidence for our learning processes and programme adaptation. This has enabled the organisation to assess and update all programme theories of change for the new Strategic Plan, and develop more extensive theories for all programme applications. Saferworld was scored consistently the highest in all our ARC-funded submissions. Evaluation and reviews are conducted across our programmes to measure and assess quality and effectiveness. In the last nine months we evaluated our contribution to the development, adoption of and indicators for the SDG 16; we conducted evaluations of community security work in Yemen, South Sudan, Bangladesh, Nepal, and Kyrgyzstan. As part of learning processes we offer staff secondments where possible, and give them opportunities to participate in evaluations or reviews of other programme work (for example, we have done this in Nepal, Kyrgyzstan, Uganda, Sudan and South Sudan). We also run an annual quality review of publications with an external panel of consultants. Saferworld has an internal position paper defining our vision and definition of VfM which we keep updated. This paper states and explains our commitment and approaches, showing what Saferworld values and how it invests in those areas. Saferworld has conducted several VfM reviews, on long-term partnerships, and policy work. The learning from this is included in the VfM paper. Principle 3	Diversification and innovation R 3.1: Saferworld’s relationship with Foundations/Trusts/Donors, particularly in the EU and US is deepened and strengthened. R 3.2: Build a coalition/alliance of partners with complementary skills to support bids for commercial tenders and contracts. Risk:	Minor	Impact weighting (%):	20% Key Points - Summary of progress during the nine month extension Saferworld’s commitment to increase its reach is demonstrated through greater income generation (from £6.7M in 2011/12 to nearly £15M in 2016-17) and we have made significant progress over the last nine months in securing up to 60% of the funding required to realise our 2017/18 plans. We continue to seek and attract the flexible/strategic funding essential to realise our added value and effectiveness in responding to turbulent and conflict-prone environments. We have invested this year in research and cultivation of Trust and Foundation funding in and our future Fundraising Strategy, which will continue to prioritise flexible and unrestricted funding. We have secured meetings with major trust and foundation funders, contributed to several trust and foundations’ strategies, and realigned our Funding Team to reflect the changing funding and investment sector, diversifying our specialisms and experience. In the last nine months Saferworld secured new grants from the Netherlands MFA ARC fund totalling EU15m over five years for our programmes in Somalia, Sudan and Pakistan; an extension grant from the Embassy of the Netherlands in South Sudan ($2m); increased and/or extension funding from the EU, and the US State Department for our work in Tajikistan and Krygyzstan. We won three competitive tender bids (Conflict Sensitivity Resource Facility in South Sudan – DFID; HelpDesk – Austrian Aid; and the Knowledge Platform on Security and Rule of Law – Netherlands). We continue to apply for selective commercial contracts where they clearly fit our niche, selectivity using our limited fundraising resources wisely. We have invested time and resources in developing the necessary protocols, agreements, and trust and governance arrangements to enable successful commercial bids, and have used these tools to ensure we are both value-driven and competitive. We now have key peacebuilding partnerships in place that span the UK, the US and Switzerland. Currently, resources are primarily made up of direct project funds and overall, the majority of our funding – both strategic and project-specific – is from government statutory funding. As is clear from our evaluations and VfM position paper, Saferworld’s niche and added-value is sustained by maintaining a good balance between a range of funding streams. This ensures we have the organisational agility necessary to respond to new policy issues/pilot new programmes and ideas, and keep our key staff. DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202709 DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202709

Asset monitoring and control
As part of standard financial management, London and local accounting staff monitor the use of fixed assets, working capital and cash. Saferworld has few fixed assets due to the nature of its work. All environments hold fixed asset registers and additional controls for the type of assets, e.g. mileage logs for vehicles. Working capital balances comprise largely partner balances which are monitored monthly and regularly reconciled. SW policy is to pay partners monthly and further advances are contingent upon adequate financial reporting. Only experienced partners who have demonstrated good financial management receive flexibility in this approach.
G: CONDITIONALITY

Partnership principles assessment

Not relevant to PPA funding.

H: MONITORING & EVALUATION (1 page) This section is focused on the lifetime of the programme – not just Year 5.

Evidence and evaluation
SW’s Programming, Monitoring, Evaluation and Learning Guide structures the strategies of all our programmes around a gender-sensitive conflict analysis, an actor/power analysis, theories of change and outcome statements. It incorporates an outcome harvesting approach to collecting results on a biannual basis, though which staff assess context, outcomes, level of significance, and contribution to outcomes by SW and partners. In 2012-3 SW developed an online intranet system (Karacel) to capture this. The monitoring data, reports on all outcomes and activities, and input data used for biannual reporting, is used to produce reports filtered by programme, actor category, and donor.
SW has invested most heavily in ensuring that MEL is incorporated into our community-based approach, by empowering partners and communities to understand and use outcome-focused approaches which capture changes in behaviour and relationships by concentrating on what others do differently as a result of our work. Our teams in the field work closely with our partners to generate, and discuss these changes, why they are significant and the kinds of contribution SW and partners are making to them. Our Learning Paper on MEL, Doing things Differently, has been widely accessed, and we have received unsolicited feedback from organisations as varied as Unicef in Myanmar, International Alert, International Federation of Red Cross and Red Crescent Societies, CAFOD, BOND, ROLE who have used it in trainings, and consultants training people on Outcome Harvesting (eg Ricardo Wilson-Grau).

SW makes use of periodic evaluations of programme work that is funded by other donors, to test and complement our evidence base. We have full MEL frameworks for our largest programmes, which include linked theories of change, detailed outcome statements, and an ‘outcome and significance’ review of all community security action plans, by communities, partners and Saferworld. During the 5 years of the PPA, SW has done 22 evaluations and reviews (both internal and external) that covered all its programmes and 2 of its global policy areas (2030 Agenda and ATT). In 2014, SW piloted a bespoke Programme Review and Improvement process (PRIMP) reviewing three aspects of our work in Kosovo/Western Balkans, and extended that to a review of our Sudan programme.

Monitoring progress throughout the programme
As part of feedback on our PPA, in 2015 SW introduced a process to review the quality of its publications. This is now part of a systematic process of quality control. Every year we pick four types of publication and put them out for external review. We use the following criteria: (i) whether the style and length of the publication is appropriate for the specific audience; (ii) whether it is timely in its publication, dissemination and presentation to the appropriate audience; (iii) whether it contains practical recommendations that can be implemented; (iv) its readability and whether it is written in plain language (English or other language); (v) whether it is properly and effectively referenced; (vi) the level and quality of analysis; (vii) whether the claims that are being made in the report are adequately substantiated with robust evidence.

In 2015 the Masculinities report was considered timely and useful for readers, using simple and genuine language and containing practical recommendations and a high quality of analysis. The Armenia/Azerbaijan briefing was considered timely, using clear language and made concrete recommendations; however the specific audience was not clear.

In 2016 all 4 publication reviewed were considered timely, appropriate for the specific audience and written in clear and plain language. They all contained practical recommendations, although it was suggested that two documents could perhaps expand more about certain roles for certain actors in these recommendations and include more thorough references. All 4 publications were assessed as having high level and quality of analysis and robust evidence.

## I: TRANSPARENCY (1 page)

Assessment of progress against enhanced Transparency offer
Saferworld remains committed to transparency throughout its operations and is constantly reviewing ways to build upon and enhance its approach. Saferworld’s commitment to transparency has required input from individuals and teams from all parts of the organisation, thereby embedding a culture of collaborative transparency practices across Saferworld.

Internal and external use of transparency data

- Saferworld worked with Bond to evaluate the external quantity of transparency data that the organisation was publishing. Saferworld has since been following up on the recommendations made as a result of the findings in the Bond report.
- In addition to the Bond publication, Saferworld has undertaken a comparative analysis of similarly-sized organisations with relevant thematic approaches with regard to their external transparency approaches. Saferworld was found to be ahead of its contemporaries in this respect.
- Saferworld has created an internal working group who meet quarterly to discuss the development of the organisation’s approach to transparency. This has allowed more open discussion on transparency issues and has resulted in information on Saferworld’s approach to transparency to be circulated to all staff and trustees.

Progress on enhanced commitments beyond IATI minimum requirements:

- Saferworld has taken the strategic decision to publish data substantially above and beyond the minimum required by DFID. Saferworld now publishes information to IATI quarterly on all grants valued at over £50,000, having reduced the threshold above which to publish data from £100,000 in quarter 4 of 2015/16. The organisation is now exploring options regarding reducing this threshold further for data published in the 2016/17 financial year.
- Saferworld now has a comprehensive Transparency Policy, which is outlined on the organisation’s Open Information page, alongside links to the organisation’s IATI implementation schedule and activity data uploaded to IATI by quarter.
- Saferworld is in the process of exploring the possibility of publishing information on the geo coded locations of its activities to IATI, as part of the organisations regular publishing of transparency information. There are a number of considerations to be taken into account, such as both the logistical impact on country teams and the security impact on Saferworld staff and beneficiaries. We are also drawing on the approaches that other organisations are taking. This review is an ongoing process.
- Saferworld is investigating the possibility of splitting information on transactions published between actual expenditure and disbursements to partners, and reporting on this every quarter. Until this is the case, Saferworld is publishing details on disbursements and expenditure annually in order to fulfil its commitment to DFID (this can be provided if required).
- Saferworld continues to be a member of the Bond Transparency Work Group and is actively participating in its meetings and discussions.
- Saferworld remains committed to building the capacity of local partner organisations to increase their openness, transparency and accountability.

## J: Disability (1 page) This section is focused on the lifetime of the programme, with particular emphasis on addressing any issues raised in the 2014-15 Annual Review feedback and on answering the questions outlined in the accompanying PCR guidance document.

We feel that the best contribution we can make to the well-being of people living with disability is by preventing conflicts that would have particularly severe impacts on them as a very badly disadvantaged group that can suffer disproportionately from the destruction of institutions and physical infrastructure that results from large scale armed violence. To achieve this, however, our focus is necessarily on the factors that are most significant in driving conflict rather than on mitigating impacts for specific groups of survivors/victims.

Although we would welcome and make full use of evidence to the contrary, apart from being aware of the risks of failing to address the specific needs of ex-combatants living with physical and mental disability, we are not aware of any major conflict having been significantly driven by the marginalisation of people living with disabilities, and therefore while we agree with the principle of mainstreaming their needs and potentials within our work, it is also true that we can only do so effectively by focusing strategically on conflict drivers rather than its effects on particular groups in the way that other humanitarian or development agencies must do.

Nonetheless, we have networked effectively with leading CSOs championing the rights of disabled people to ensure the integration of a critical focus on addressing inequalities and marginalisation of all vulnerable people into the SDGs and UK aid policies, and as a matter of routine would take steps in any community where we engage to ensure all those who are potentially excluded are supported to engage effectively in our participatory design, implementation and MEL processes. We still have further work to do to integrate monitoring data on this approach into our global systems, but will aim to do so by the end of the PPA grant period in December 2016.

## K: ADDITIONAL UPDATES (OPTIONAL SECTION) (1 page) This section is focused on the lifetime of the programme – not just Year 5.

Any additional updates relevant to DFID

Pakistan - Women at the forefront of the peacebuilding process

Throughout Pakistan, women have traditionally faced both legal and cultural barriers to their participation in local and national decision-making. However, in recent years some progress has been made that challenges this paradigm, bringing women’s rights voices to community discussions and decisions, and challenging gender norms. With this in mind, Community Appraisal and Motivation Programme (CAMP) and Saferworld were keen to bring rural women to the forefront of peacebuilding discussions in their local communities, enabling their voices to be heard when conflicts that affected their own lives were being resolved. The opportunity was a local conflict in Maina village (Malakand district in the Provincially Administered Tribal Areas (PATA), in Khyber Pakhtunkhwa province) around a village path that was causing tensions between farmers and travels, involving different local tribes. To address the issue, a small grant of PKR 452,000 (£2,900) was provided by CAMP to civil society organisations (CSOs) in Malakand, who had been trained in conflict analysis, mediation and dialogue, advocacy, the role of jirga, and community-driven initiatives for peace. This cluster of CSOs was led by the Malakand Welfare Society (MWS) and supported by Sikandar Welfare Organisation (SWO) and Women Awareness and Development Society (WADS). Together they used the small grant to resolve the conflict in Maina village and contribute to local peace efforts. During consultations between the community and the CSOs, the community proposed that the passageway be paved and the blocks removed. It was clear that the issue was a priority for the community, both men and women, so the CSOs planned to resolve the conflict through facilitating dialogue, holding a peace jirga (mediation) and paving the passageway. Since women were an important stakeholders (half the 2,200 beneficiaries were women), the CSOs worked hard to involve the women in planning and implementing the project. Despite the challenge of involving women in public gatherings in a rural area, women became part of the Community Action Group (CAG), as well as of the jirga; with 27% and 32% representation respectively. Women who were part of the CAG and jirga provided support and organised awareness and sensitisation campaigns on the importance of peace for other women in the village. The female teachers involved in the project also raised awareness among their students about the importance of peace. Six women also received training on peacebuilding so that they could be a part of future efforts to resolve conflict at family and community levels. It was unusual for women to be part of village-level consultations, especially in such a conservative rural area, but the experience was well received. According to Rahman Ghani, a beneficiary from this project, “[the] initiative was much needed… the training that I along with other members of the community, including women, got under this project will help in resolving future conflicts through involvement of all members of the community” (discussion with Rahman Ghani during CAMP team’s monitoring visit to the project site, 3 December 2014). At the end of the project the path was paved with support from the small grant as well as a contribution from the community. The project resolved a long-standing community conflict through real community participation, involving women in the peacebuilding process for the first time in the village.

## L: Evidence Table (1 page maximum) This section should be used to provide links to external evidence of achievements listed in the narrative, limited to a maximum of 10 throughout the report.

Ref. No.	Document name	Notes	Comments
Ref. 1	Independent Progress Review of Saferworld’ s PPA with DFID, October 2012	External Review	Funded by PPA
Ref. 2	Saferworld’s contribution to achieving the Arms Trade Treaty – 20 years of work / http://www.saferworld.org.uk/resources/view-resource/1074-saferworldrsquos-contribution-to-achieving-the-arms-trade-treaty-ndash-20-years-of-work	Learning Paper	Paper funded by PPA
Ref. 3	Ensuring that the UN 2030 Agenda for Sustainable Development promotes peaceful, just and inclusive societies - An evaluation of Saferworld’s contribution, 2011 – 2016, June 2016	External Evaluation	Confidential Funded by multiple donors, including DFID
Ref. 4	Together we are wiser - From strategic partnership to institutional friendship – A commentary on Saferworld’s approach to partnership in Kosovo, December 2014	PRIMP review – external consultant	Confidential funded by PPA as part of PRIMP
Ref. 5	Final Evaluation of Saferworld support to Non-State actors platforms in Somalia, May 2015	External evaluation	Confidential – programme funded by EC
Ref. 6	Final evaluation report of the Community Initiatives for Common Understanding project and Internal Post-project Evaluation in Siraha district – Nepal, May 2016	External and internal evaluation	Confidential – programme funded by USAID
Ref. 7	Final project evaluation: Saferworld’s community security / community policing programme in Kyrgyzstan, March 2016	External Evaluation	Confidential – programme funded by INL
Ref. 8	Institutionalising Comprehensive Police Reforms in Kenya – Final Evaluation Report, November 2015	External Evaluation	Confidential – programme funded by G of Netherlands
Ref. 9	Advisory Consortium on Conflict Sensitivity – Uganda – Final Review, June 2014	External Review	DFID review, programme funded by DFID
Ref. 10	Doing things differently: Rethinking monitoring and evaluation to understand change / http://www.saferworld.org.uk/resources/view-resource/1027-doing-things-differently-rethinking-monitoring-and-evaluation-to-understand-change	Learning Paper	Funded by PPA

## M: Summary Sheet of each Annual Review (Years 1-4) (maximum 1 page per year) This section should be used to provide a short summary of progress (and any follow up actions) from Years 1 to 4 of the PPA. This section should complement the information provided at Section A.
Year 1 – 2011/12
Programmatic level
PPA funding has allowed Saferworld to implement organisational strategic objectives, identified in Saferworld’s Strategic Plan 2011-14, such as responding to crisis and conflict; working to scale; and developing a new regional programme in the Middle East North Africa (MENA) which would not have been possible to the same extent without these funds. This has enabled Saferworld to respond to the conflict in Southern Kordofan (Sudan) by making direct contact with war affected communities; channelling local voices to international actors; undertaking extensive advocacy internationally; to invest in programme design and development by exploring how to work at a larger scale with potential for greater impact in Kenya, Somalia and South Sudan; and to conduct scoping work in and on target countries in MENA: i.e. Egypt, Libya and Yemen. Risks were undertaken in all these activities as returns cannot be guaranteed. Nevertheless, Saferworld’s work in Southern Kordofan was recognized, target country programmes have developed working to scale models that they secured funding for, and, a new regional MENA programme and team was established, including deepening Saferworld engagement in Yemen and initiating a programme of work in Egypt.
Organisational level
A large proportion of Saferworld’s policy development and advocacy was conducted by conflict advisers and advocacy specialists resourced substantially through the PPA. This enabled us to conduct cross-organisational comparative learning, research and analysis across a wide range of conflict-affected contexts and to formulate policy and practice recommendations that were up-to-date, evidence-based and innovative. We continued to trial new methodological approaches to conflict analysis and community security. Moreover, PPA funding has allowed us to improve our investments in human resources, financial management and monitoring, evaluation and learning systems. The PPA has also allowed us to improve our communications so they are more innovative, conducting a communications review and developing a new communications strategy. We improved our website, developed our blog, and increased our exposure on Twitter and Facebook. PPA funding also enabled SW to invest more in building its internal capacity on gender, peace and security issues, funding a gender audit, development and delivery of training for staff across a number of programmes and production of a resource pack to accompany this.
Value for money
In 2011-12 we undertook a review of core financial data on Sage (our accounting system) and restructured our accounting system to produce key donor reports and, for the first time, aggregated summary financial data for management.  We also reviewed all processes of input and output of data to automate where possible and improve speed of reporting.
Our drivers of cost were headcount; staff salary; additional staff costs; consultant costs; travel; meetings and conferences.  For the first time, our system detailed how each employee is costed to projects.  It allowed the analysis for each donor of staff working on a project, and also reports for each staff member of how time has been changed in each period.
Score
A+

Year 2 – 2012/13
Programmatic level
Individuals and Communities: 40 Community Security action plans were developed and 37 implemented in Nepal (12), Central Asia (12), the Caucasus (8) and Kenya (5).
These projects address barriers to security and development facing communities, and - through demonstrating that problems can be tangibly addressed – start to increase willingness to engage with authorities and break down feelings of isolation and apathy.
Civil Society: 16 CSOs across 6 regions / countries have demonstrated increased skills, confidence and capacity in issues of community security, conflict-sensitivity, and inclusive governance and political processes: Caucasus (2), Central Asia (3), Kosovo,(1) Somalia (3), Bangladesh (1), Uganda (3), Yemen (3). Of these, 9 are additional CSOs to last year.
Authorities: 6 institutions have developed new or strengthened approaches, policies or strategies (Kenya National Police Service (NPS), National Steering Committee on Peacebuilding and Conflict Management (NSC) and Independent Electoral and Boundaries Commission (IBEC); Government of Uganda, South Sudan CSSAC Bureau; Kosovo Ministry of Interior). At least 3 institutions have started to change their practices in line with new strategies / policies / approaches: the NPS, the Municipal Community Safety Councils (MCSCs) in Kosovo, and District Local Governments in Uganda.
External Actors: Saferworld’s research, analysis, policy development and advocacy has had considerable success informing and influencing the policies and practices of external actors at international and national levels including: governments (9 - UK, US, China, Mexico, Sweden, Norway, Costa Rica, Uruguay, Palau); multilateral organisations (4 - UN, EU, OECD, G8); UN High Level Panel; civil society organisations and networks (4 - Control Arms, Beyond 2015, InterAction, Alliance for Peacebuilding) representing over 500 CSOs; and INGOs and other actors (10 – Global Witness, Christian Aid, International Alert, Crisis Action, The Elders, SD Direct, IDS; ODI; ICAI and the British Council). Out of this total of 27 actors, 22 were additional in year 2.
Organisational level
PPA funding has enabled Saferworld to design, develop and contract out an integrated intranet and M&E system, Karacel. SW has devolved functions at country level (South Sudan, Central Asia, Yemen, Pakistan, Bangladesh, USA) and key staff close to the place of programme delivery (opening of offices in Bishkek, Sana’a, and Islamabad). This in turn has driven development of stronger financial and operations systems, the restructure of cost centres, faster financial data processing, and improved security risk management. PPA funds have allowed SW to scope possibilities for US presence; it was instrumental in augmenting SW’s capacity to leverage additional resources (by being perceived as an endorsement, providing a means to pledge match funds when required by another donor, and especially by enabling the organization to be strategic and responsive to new opportunities when they arise); it supported SW in continuing to play a leading NGO role in drafting and pushing forward text for the ATT, and in ensuring that peace and conflict issues are included on post 2015 agenda.
Value for Money
Saferworld practice for cost control is effective management account review, including annual meetings and training of Finance staff, and monthly summaries of project performance. Significant achievements include core data analysis (possible for the first time from restructured Chart of Accounts) providing a solid base for cost driver analysis.
Score
A+
Follow up actions
In the Logframe SW made minor changes to two output indicators, agreed with DFID as part of the year 1 annual reporting process.

Year 3 - 2013/14
Programmatic level
During year 3, SW has more than exceeded results in the logframe. Initial targets for indicators were exceeded representing the impacts of the investments made in organisational effectiveness through the PPA grant. The three key successes in year 3 include:
Extensive reach of SW’s community security work: SW’s community security work in Kenya, South Sudan, Bangladesh, Nepal, Caucasus, and Central Asia has not only grown in numbers of communities that SW now works with but has also begun to demonstrate stronger community ownership of the approach.
Stronger relationships between communities and authorities: building relationships between authorities and communities is challenging but fundamental to SW’s community security approach. Nevertheless, SW has seen dramatic progress in shifts in relations between communities and both local as well as national authorities.
Policy achievements: SW’s policy and advocacy work has seen exemplary developments during year 3. Some noteworthy examples are: (i) The adoption of the Arms Trade Treaty by the UN General Assembly, and subsequent signing by Britain and 117 additional states. (ii)Significant in-roads into the post-2015 agenda where all of SW’s key asks for the post-2015 framework were taken up in the final HLP report; (iii) SW’s work in China has also made remarkable progress with uptake among high-level officials, private companies, and high-ranking Chinese military officers, acknowledging the need to combat diversion of Chinese SALW and ammunition and improve end-use monitoring and verification.
Organisational level
A number of specific investments were made, which have contributed directly to the strategic development of the organisation in a number of critical areas considered necessary for the fulfilment of our goals, especially in a more effective and sustainable manner: Further training and development of systems to gather evidence, learn about our results, and communicate them more readily; the placing of London-based roles to regional and country offices, including fundraising functions and four finance manager posts (Kenya, South Sudan, Uganda and Kyrgyzstan); Data and analysis on organisational capacity was also enhanced made possible by the restructuring of SW’s Chart of Accounts and core data; Practical improvements in the quality of our communications (internally and externally) has made our advocacy more effective, and increased the numbers of people accessing our reports and recommendations.
Value for Money
SW views VfM as putting greater focus and clarity on the benefits obtained through our work (requiring effective planning, monitoring and evaluation), and that resources are being used in the best way to achieve the best results (requiring appropriate management and the monitoring of these resources). SW was committed to institutionalising VfM approaches and addresses this through numerous projects. It does, however, bear repeating that more traditional ‘cost-comparison’ VfM approaches are not appropriate for the nature of work and countries that SW supports
Score
A+
Follow up actions
Changes have been made to outcome and output results to better reflect the increased capacity that the PPA grant has facilitated, in order to leverage more programme-specific funds.

Year 4 – 2014/15
Programmatic level
During year 4 Saferworld continued to consolidate its community security work. During the year, we have trained 95 community action groups (27 new ones this year in three programmes), who implemented 86 action plans to counter threats to security identified collaboratively at community level. 211 CSOs have been trained in 10 countries, many of whom are accompanied or mentored regularly, to influence authorities. 31 authorities, 9 at national and 22 at subnational level, in 8 countries, have developed or implemented new approaches/policies in part as a result of SW and partners’ technical input. 34 external actors (including UN, EU, UK, China, India, Brazil, and South Africa) have taken up SW and partners’ recommendations, at least 14 of which have a global impact. Five SW country programmes have included gender analysis in their planning. Some important examples to support numbers above include: in South Sudan, where despite ongoing civil war local authorities allocated land for communities, and police have started to provide assistance in-kind. This work over four years demonstrated the importance of consistency in engagement and is a validation of our community security theory of change. In Kenya, enhancing the accountability of the police service saw the growth of accountability structures like the Community Safety Forums, and development of community policing guidelines.
International policy/advocacy successes include the adoption and subsequent entry-into-force (24/12/15) of the ATT, a significant change to which Saferworld has made 20 years of consistent contribution (at an estimated cost of GBP 900,000), the inclusion of Global Goal 16 in the zero draft of the SDGs and the uptake of indicators to which SW has been a key contributor.
Organisational level
In year 4, we conducted two important evaluations of our policy and partnership successes: (i) SW’s work on the Arms Trade Treaty (ATT) (from 1993/94), and (ii) the 10-year partnership with the Forum for Civic Initiatives (FIQ) in Kosovo. Both had a VfM section which traced historic costs, which was new for SW. SW’s MEL approach to monitoring outcomes and evidence enabled more regular, consistent learning, and programme innovation, adaptation and expansion. This is evident from the inclusion of another state in South Sudan’s programme of work, and the growth of youth work in Nepal, Sudan, and Yemen. The regular reviews of our community-security approach generated evidence for policy-making at various levels of governance, and has been built on our Community Security Handbook by producing a Guide to Programming and MEL. SW’s risk management approach has been consistently strengthened to respond to changing risks in the environments where we work to ensure effective delivery. Also financial management capacity has improved during the year with the development of a new world-wide finance performance system (implemented to plan and budget for 2015-16).
Value for Money
As part of our enhanced commitment on VfM Saferworld has (i) tracked key cost drivers, (ii) conducted an evaluation on a long-term policy programme (ATT) using a VfM lens, (iii) assessed a long-term partnership by taking a VfM approach, and (iv) introduced a new financial management system to better track finances. Saferworld has seen significant successes in its programmes, for example in scaled-up impact in South Sudan, where an organisational commitment to invest PPA funds in 2012 has resulted in scaling up of operations. VfM approaches can also be seen in how the largest development organisation in the world – BRAC –has started using Saferworld’s M&E and conflict sensitive programming.
Score
A+
Follow up actions
No changes in logframe since the last review with PPA managers in October 2014.

Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process