2016 Girls' Education South Sudan (GESS) Annual Review – Summary Sheet

Title: Girls' Education South Sudan (GESS)
Programme value: £60 million		Review date: November 2016
Programme code: 202511	Start date: April 2013	End date: September 2018

Summary of programme performance

Table 1: Annual Review Scores

Year	2014	2015	2016
Programme Score	A	A	A+
Risk Rating	Major	Major	Major

Summary of progress and lessons learnt since the last review
This is the third Annual Review for the Girls Education South Sudan (GESS) programme, a 6-year programme which started in April 2013. GESS has performed well, despite the numerous challenges presented by the fragile environment and deteriorating socio-economic context. To date 120,000 girls have received a cash transfer for attending school and 3,810 schools have benefited from a capitation grant which helps pay teachers’ salaries. Overall, progress against the three programme outputs has either met or moderately exceeded the 2016 milestones, as indicated in Table 2, with many individual milestone indicators substantially exceeded. The programme overall is therefore scored A+ (“moderately exceeded expectations”).

Table 2: Progress in Relation to Milestones

Output number	Output Description	Impact Weight (%)	Output Performance
1	Enhanced household and community awareness of and support for girls' education	25%	A+ ( Output / moderately exceeded the 2016 expectations)
2	Effective partnerships between government and local organisations to deliver a community-based school improvement programme	60%	A+( moderately exceeded expectation)
3	Increased knowledge and evidence available to policy-makers of what works to promote girls' education in South Sudan	15%	A output met the 2016 expectations.

The renewal of conflict in Juba in July 2016, and the increased instability that followed, presented significant challenges for the GESS programme in what was already a highly fragile environment. The GESS team, and Ministry of General Education and Instruction (MoGEI) officials have confirmed that the surge in conflict has negatively affected GESS programme implementation. Activities that were temporarily delayed, with the average delay being 3-4 months, included payments of cash transfers to girls and capitation grants to schools, the provision of training to teaching personnel, and evaluation and research activities.

In response to the changing context, GESS developed an Interim Strategy for August- October 2016, which put in place enhanced measures to mitigate against the increased level of risk, while maintaining project activity as far as possible. This, however, resulted in an increase in project costs due to extra investment in security, staff relocation and remote working arrangements. Education is a key protective factor for children, and in particular girls, in fragile and conflict affected states, and the continued functioning of GESS contributes to the protection of children in South Sudan. In child protection in emergency contexts, schools serve an important role in monitoring the safety and well-being of children in the communities within which they operate.
Summary of 2016 achievements (as of 30th September 2016)
- GESS has established and maintained an effective partnership with MoGEI, education partners and the Education Donor Group. This has ensured increased ownership of, and commitment to, GESS by MoGEI, efficient and cost effective sharing of resources with other organisations, and the potential to attract additional funding and resources from other donors.
- Consistent with previous years, progress against all the three outputs have either substantially or moderately exceeded the 2016 milestones, with the exception of Indicator 3 of Output 3 (primary school teacher and pupil attendance) which has slightly decreased
- The SSSAMS[1] system recorded an enrolment of 1.29 million children as of 30th September 2016. By November 2016 this had increased to 1.32 million. This data illustrates the programme’s continued capacity to deliver during a period of increased fragility and conflict. The combination of direct financial support alongside community messaging was a significant contributory factor to the programme’s continued functioning.
  [1] South Sudan School Attendance Monitoring System
- School radio broadcasts reached 2,000,000 adults, substantially exceeding the targets of 1 million.
- 122,460 girls received cash transfers for the first time
- 3,810 schools received capitation grants (pre-primary, primary and secondary) under joint Government Republic of South Sudan (GRSS) and GESS funding.
- 1,541 schools benefitted from the wider package of school improvement plans which included support to teachers, provision of education materials and improvements to school infrastructures.
- The pilot teacher professional development activity in output 2c has reached 218 schools. This school-based training offered a cost-effective approach to improving the quality of teaching. We recommend the scaling up of this activity to support improved standards of teaching (indicator 2.3 (iii))
- GESS has created education resources, information and systems since 2013 that can now be scaled up with minimum overhead costs.

Responses to 2015 recommendations
Two reviews were conducted in 2015, the second “light touch” review to ensure synchrony with logframe milestones. Review (i) March 2015 made 11 recommendations, and Review (ii) September 2015 (light touch) made four. GESS has positively responded to and implemented 13 out of the 15 agreed recommendations. Responses to recommendations are summarised below.

Summary of recommendations for the next year
At present, the implications of the new 28 states governance structure[2] on the education delivery system, and on the GESS project in the longer term, are still emerging. However, there are reports of reduced organisational and human capacities at local, Payam[3] education levels, and it is recommended that support to schools at a local level is prioritised in 2017.
[2] The Boma is the locality governance structure, essentially a town and outlying areas council that forms part of an overall county structure
[3] Administrative division below county, but above Boma level.

## A: INTRODUCTION AND CONTEXT (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202511/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202511/documents

Outline of the programme
GESS was designed to respond to the significant need for education in South Sudan, where girls in particular are considerably disadvantaged as a result of a combination of socio-economic and cultural factors. Girls' education indicators are poor; there are seven girls for every 10 boys in primary and five girls for every 10 boys in secondary education. In 2012, only 864 girls were in the final year of secondary education nationwide. Only 12% of teachers are female across the primary and secondary sectors. Literacy rates for girls are 40%, compared to 60% for boys.

Girls' restricted access to educational opportunities has been exacerbated by certain cultural practices and by conflict. Whilst education is cited by many communities as a priority, social pressures and practices, particularly early marriage, result in low school enrolment rates for girls. These problems occur within a fragile state, where education provision continues to be disrupted by the conflict within South Sudan.

The intended impact of the programme is to transform the lives of a generation of girls in South Sudan through education by increasing their enrolment and retention in education, and improving levels of achievement. The targeted age ranges of the programme span primary and secondary education – Primary 5 (P5 - 11 years of age) to Secondary 4 (S4 - 18 years of age). The programme aims to:

- Enhance household and community awareness of the value and importance of girls' education through social and behaviour change communication and community mobilisation
- Support the delivery of a community-owned school improvement programme through cash transfers to all girls attending classes from P5 to S4, and payment of capitation grants to primary and secondary schools to support schools’ continued functioning. There are also interventions aiming to strengthen school governance, mentoring to girls, teacher training and development of teaching/learning resources to improve standards and learning outcomes
- Implement and sustain a pupil and teacher attendance monitoring system
- Comprehensive research and evaluation activities to inform future interventions.

The expected results are:
- 150,000 girls in primary and 50,000 in secondary schools directly supported by the programme
- 240,000 girls benefiting from the programme's broader package of support
- 300,000 boys benefiting from the programme’s broader package of support
- 1,000,000 adults (aged 15 years and above) reached through behaviour change communications to families, communities and leaders
- 2,600 schools benefiting from capitation grants
- Improved learning outcomes, reduction in drop-out and repetition rates
GESS directly aligns with Gender House, DFID's Strategic Vision for girls and women,[4] which commits to increased numbers of girls completing secondary education.
[4] https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/67582/strategic-vision-girls-women.pdf

## B: PERFORMANCE AND CONCLUSIONS (1–2 pages)

Annual outcome assessment

The headline outcomes for 2016 are:
- By the end of September 2016, the weighted average promotion rate from upper primary to secondary (P5-S4 – 11 to 18 years of age) was 86.0% (F: 92%; M: 80.1%): achievements above target milestone.
- There were 178,715 (P5-P8 – 11 to 14 years of age) and 24,184 (S1-S4 – 14 to 18 years of age) girls in school. The milestone for the 2016 review year was 130,000 and 36,000 – primary and secondary respectively; the primary enrolment is above target, while the secondary achievement is below the milestone[5].
  [5] It is important to note that these are the intended ages for these school years, however, an important caveat to this is that there are frequently older children in primary classes and SSSAMS reports indicate a high proportion of adult females attending school.
- The average attendance rate for girls at upper primary and secondary (P5-S4) was 87.87%, against a target of 88% (from at least 700 schools), almost exactly on target.
- The percentage of adults in the sample study (BBC Media Action longitudinal study) who place importance on sending girls to school increased from the baseline of 27% to 36%.

Sustainable Development Goal 4 specifies that improved access to education should be accompanied by high-quality learning and improved learner achievements. In 2016, girls have demonstrably progressed in their South Sudan Certificate of Secondary Examinations (the SSCSE 2015/2016 results pass rate was 74.3% against a planned milestone of 65%). GESS is central to this progress in that the cash transfers and other support has enabled an increased number of girls to remain in education. The primary result was not available at the time of review.

The above outcomes indicate that the performance of the project in 2016 was consistent with the previous year's good performance. The overall goal, improved girls' enrolment, retention and learning at primary and secondary school, is being substantially achieved.

Overall output score and description

All three outputs have either met or exceeded the 2016 milestones, as indicated in Table 2. The overall output score is therefore A+.

Key lessons and observations

- GESS has a coherent project design, a clear and well-articulated log frame and theory of change.
- Much of the progress made by GESS over the last three years can be attributed to dedicated and technically competent staff, with a stable workforce that enables continuity. There is an evident commitment to partnership working from all programme stakeholders. The relationship with government at central and local levels of the education governance system has been sustained despite the noted challenges. Although travel outside Juba was prohibited during the review, engagement with locality State Anchors (SA’s) from outlying states further evidenced these positive relationships on the ground. The role of the SA’s is to provide direct support and monitoring at local, school level, to ensure that key programme activities are coordinated and delivered effectively.
- There are robust quality assurance systems and internal monitoring procedures across all the three output activities, and the validation process of the cash transfers and school capitation grants is sufficiently strong to protect funds from misappropriation and fraud. There is tangible evidence of payments reaching intended recipients and accountability mechanisms. However, there is a need to increase the role of the government in all aspects of the programme in order to develop their capacity to directly and actively support the education sector.
- Feedback from both girls and teachers clearly indicated that cash transfers and capitation grants are the most popular components of GESS. They were described as ‘life support' to South Sudanese education and learning. Schools that received capitation grants were more likely to remain open during the current instability, with better facilities and more conducive learning environments. Girls in receipt of cash transfers were more resilient and are more likely to remain in school.
- A review of the activities implemented under Output 1 (radio and community mobilisation) demonstrates that the topics selected were consistent with the beneficiaries' requirements and targeted social and cultural norms that impact on the retention of girls in education. At the peak of the conflict period, the Juba editorial teams directed the local partner FM radio stations to broadcast topics and messages that reflected the emergency context, focussing on safety, impact of socio- economic factors on retention, and the emergence and resolution of conflict within schools. This demonstrates a flexible and relevant approach to the current fragility in South Sudan.
The GESS project has developed substantial educational resources, data and information, systems and effective delivery structures. Therefore, it is recommended that the focus for the coming year should be the effective utilisation and dissemination of the developed resources.

Key lessons
Overall, GESS has established an effective education aid delivery structure nationwide and has positively impacted on girls' enrolment and retention in education in South Sudan in a time of great need and fragility. The systems and the capacity created have the potential to scale up to reach other vulnerable groups such as orphans and children with special needs. Extending cash transfers to girls in P1-P4 (ages 5 to 10 years) has the potential to improve enrolment and retention rates for younger children.

Key actions
GESS are currently attempting to mitigate the risk of qualified teachers leaving the profession by negotiating with the EU to support teachers' incentives. Other areas for future consideration are the scaling up of the current pilot professional development for serving teachers, and the radio and community mobilisation activities

Has the logframe been updated since the last review?
Yes. During 2016, GESS has joint funded Capitation Grants with GRSS due to the marked economic deterioration impacting on government’s ability to do so. This revised milestone indicated that GRSS was to support 2,965 schools, while GESS will support 235 schools. Outcome Indicator 3 has also been modified to exclude boys from the attendance rates – this indicator is now specific to P5-S4 girls’ attendance rates only.

C: DETAILED OUTPUT SCORING (1 page per output)

Output title	Enhanced household and community awareness of and support for girls' education
Output number per LF		1	Output score	A+
Risk:		M	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone for September 2016	Progress achieved
1.1 Number of adults (15 years+) reached with girls' education radio outputs	Planned: 1,400,000	Achieved: 2,000,000 / Milestone substantially exceeded expectation: target for 2018 achieved / (A++)
1.2 Number of school communities reached with the community mobilisation activities	845 school communities	Achieved: 913 / Milestone moderately exceeded expectations. Well on track to achieve milestone in 2017 (A+)
1.3 Percentage of people in the sample study who demonstrate awareness and understanding of elements of the school system that supports girls' education	(Baseline 22%) / 2016: 27% / (Baseline + 5%)	Achieved 53%: baseline +31% / Milestone substantially exceeded expectation (A+)

Output 1: Output 1 consists of 3 indicators. Overall, all three indicators either moderately or substantially exceeded the 2016 expectations. BBC Media Action is responsible for delivering the above three milestones. Cumulatively, so far 400 original programmes and associated content, all relating to broader aspects (topics) of the planned GESS results, were recorded in nine local languages, reaching an audience of 2,000,000; over 100 of these programmes were recorded in 2016. This review found that the broadcasts not only promoted girls' education but also increased awareness of overall GESS activities, particularly the cash transfers and capitation grants. Community mobilisations, public service announcements, interactive drama and visual storytelling materials have been used to complement the schools' radio programme.

BBC Media Action have conducted and concluded a midline 2016 Survey, community mobilisation research and qualitative research around programme content to determine the impact of their activities. The data has also been triangulated with Knowledge, Evidence and Research and SSSAMS monitoring information.

Summary of responses to issues raised in previous annual reviews (where relevant)
GESS produced a detailed response to the 2015 AR recommendations in November 2015, priority actions are summarised below:
- Enhanced training of Radio Producers
- Improved capacity building of community mobilisation officers (CMOs)
- Mainstreaming gender awareness training for producers and CMOs, as well as teachers
- Improved quality assurance for radio programming through mentoring and training

Recommendations
The behavioural change and communication strategy has proven effective in terms of keeping the importance of girls education on the agenda in a time of considerable fragility and conflict. The flexible and conflict sensitive approach messaging should be prioritised in the coming year.

Output title	Effective partnerships between government and local organisations to deliver a community-based school improvement programme
Output number per LF		2	Output score	A+
Risk:		M	Impact weighting (%):	60%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones: end of September 2016	Progress achieved
2.1 Cumulative number of (unique[6], individual) girls receiving cash transfers	Planned: 105,000 / (GESS = 105,000 / GRSS = 0)	Total = 122,460 / GESS = 122,460 / GRSS = 0 / Output moderately exceeded expectation (A+)
2.2 Cumulative number of schools receiving capitation grants	GRSS = 2965 / GESS = 235	GRSS = 3,095 primary; 234 pre-primary / GESS = 481 unique schools*: 237 secondary; 244 primary / Output moderately exceeded expectation (A+)
2.3 Cumulative number of schools receiving full package of community-based school improvement programme	School governance = 1500 / Supportive supervision = 1500 / Teacher development = 200 / School-based mentoring = 200 / Low-cost learning materials = 200	School governance = 1541 (A+) / Supportive supervision = 1541(A+) / Teacher development = 218 (A+) / School-based mentoring = 305 (A+) / Low-cost learning materials = 159 (B) / Overall moderately exceeded expectation: (A+)
[6] “Unique” in this context referring to first-time receipt of cash transfer.

Output indicator 2.1: Cash transfers: Charlie Goldsmith Associates (CGA) maintains the SSSAMS electronic database system, with programme stakeholders also having a role in the distribution of cash transfers. During 2016 GESS has validated payment to 122,460 'unique1 girls' in both primary and secondary schools, exceeding the target of 105,000.

Output indicator 2.2: Capitation grants: Capitation Grants have been crucial in ensuring that schools have continued to function during the increased conflict and instability as they have provided financial support to teachers and provided much needed education resources and repairs and adaptations to school infrastructure. There were delays in payments to schools, attributed to the need for negotiation between GESS and MoGEI to transfer some primary school payments to GESS. Despite these challenges, 71% of all county officials and 85% of Payam officials surveyed said that both the functioning of, and standards in schools in their locality, had improved since 2014. The midline survey reports indicated that during 2014 and 2015 the most common reported use of capitation grants was the payment of incentives to volunteer teachers, with other uses including improvements to school infrastructure.

Output indicator 2.3: School based improvement programme: By the end of September 2016, Output 2C has exceeded 4 of the 5 quality indicators.1,541 School Management Committees were trained on school governance and the management of school activities and finance. This indicates that good progress is being made with the strengthening of leadership and governance in schools, as well as increasing community engagement and ownership of educational services

Summary of responses to issues raised in previous annual reviews (where relevant)

- County Education officers’ job description now include governance training to School Management Committees
- Simplified manuals developed to streamline CG and CT processes
- Accountability strengthened and CG uses now posted publicly, and development plan and budget templates simplified
- Ministry increased efforts to ensure CGs released on-time
- Enhanced support for remote schools introduced
- Mentoring programme reviewed and training improved
- Additional County Education officers enrolled to ensure wuality education component is strengthened

Recommendations
GESS has been instrumental in sustaining education in a protracted emergency context with the financial support to Girls and Schools. This has included taking on additional responsibility for Cash Transfers due to Governments inability to do so. GESS should sustain being a replacement for Government, so a high priority for 2017 is to work with the Ministry of Education to develop a sustainable approach with Government as the lead agency with increased resource commitments as feasible given current economic climate.

Output title	Increased knowledge and evidence available to policy-makers of what works to promote girls' education in South Sudan
Output number per LF		3	Output score	A
Risk:		M	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2016	Progress achieved
3.1 Cumulative number of relevant research and evaluation studies conducted and disseminated to policy-makers	Planned: 6	9 – GESS Midline (2016) / School Survey 2016 – by CGA / Household Survey 2016 – by CGA / County and Payam Survey 2016 – by CGA / Sub-national Public Financial Management Survey – by CGA / Longitudinal Qualitative Survey – by CGA / The Learning Assessment – by CGA / The remaining three surveys were conducted by BBC Media Action / Output moderately exceeded expectation (A+)
3.2 Maths and English Learning Assessment administered to sample of schools	Planned: 2	2: tests completed in all 10 (historical states). Sample size 8,243 pupils which marks 95.3% of the targeted learners / Output met expectation (A)
3.3: Percentage of primary and secondary schools with SSSAMS reporting attendance of pupils and teachers regularly (at least six times per academic year); defined pro rata as five times by 30 September	70%	60%: this result represents an 18% improvement over 2015 achievement; however, it is still below the milestone / Output moderately did not meet expectation (B)

Key points

Output 3: Overall this output met the 2016 expectations.

Output indicators 3.1 and 3.2: Despite the previously noted challenges, nine national midline surveys and research activities were completed during 2016. The School, Household, Country, Payam, Sub-national Public Financial Management Survey, and Longitudinal Qualitative Surveys, as well as and the Learning Assessment were conducted by CGA. BBC Media Action also analysed the efficacy of their programme interventions in year, with final data analysis ongoing at the time of this review.

Output indicator 3.3: This is the only indicator that performed slightly below expectation. For schools to qualify for capitation grants they are required to register and regularly report on the SSSAMS system. Schools primarily report using SMS messages. In 2016, 3448 schools have submitted electronic reports. Of these schools 60% have made five or more reports. However, due to the ongoing conflict, mobile network coverage is variable. To mitigate this, State Anchors and Payam Education Supervisors currently attempt to physically access difficult to reach schools in order to secure data for uploading to the SSSAMS system – this has led to consistent levels of reporting from schools.

Summary of responses to issues raised in previous annual reviews (where relevant)
Responses to issues raised in the 2015 Annual Review are detailed in the GESS report to DFID dated November 2015 in summary progress includes:

- Improved use of lesson learning and research to sharpen impact on girls’ enrolment, retention and educational outcomes
- School Attendance Monitoring System (www.sssams.org) streamlined to reduce reporting burden, and more used by local authorities for management

Recommendations
Monitoring and reporting of school registration and attendance will continue to present challenges. GESS, and third party monitors, should ensure that schools are robustly monitored at a local level to directly obtain data where required and verify data presented electronically.

## D: VFM AND FINANCIAL PERFORMANCE (1 page)

Spending	Financial Overview
Approved spending (managed funds 1 April 2013–30 Sep 2018	£60,059,425
Actual spend in previous quarter (1 July 2016–30 Sep 2016)	£2,917,047
Proposed spending in next quarter (1 October 2016–31 December 2016)	£6,305,441
Cumulative spend to date 30 September 2016	£35,073,089
Cumulative balance to date 30 September 2016	£24,986,366

GESS reports against its VFM indicators on a quarterly basis, with full reporting at year end (30 September) and each calendar year (31 December).

Key cost drivers and performance
The project's main cost drivers remain cash transfers and capitation grants. Cash transfers have become more expensive in USD terms because of the significant fall in value of the GBP. Given the pressures on the overall GESS budget the project has had to cut transfer value amounts in both GBP (£28 to £26) and (more sizeably) in USD terms ($42 to $32). Impact of this reduction in value is currently being measured but there has been no reduction in attendance or increase in drop-out rates to date. Capitation grants have become a greater funding obligation for the project as the government's income position has deteriorated such that the project is now supporting primary as well as secondary schools. Given pressure on project funds, capitation grant value amounts have fallen significantly in GBP terms (from around £2,000 per school in 2014 to approximately £400 per school in 2016).

The project's next main cost drivers are fees and expenses across the programme. There is upward pressure on these costs given the security context and reduced GBP value. Despite this, the project has continued to reduce its overall management charge (12.6% in 2015 to 10.9% in 2016) and is on track for the 8.8% target by 2018).

VfM performance compared to the original VfM proposition in the business case
The programme VfM benefits are dependent on the girls’ retention in education and improved learning outcomes, increase in average promotion of more than 4% and cost effectiveness of the cash transfers and capitation. In 2016 attendance reporting of pupils and teacher was stronger than in previous years, despite the deteriorating security and operational context. Particularly notable was the high proportion of schools that ‘keep on reporting’ and have been able to retention.

The girls’ pass rate for South Sudan Certificate of Secondary Education 2015-16 = 74.3% according to National Examinations Council compared favourably to the target of 70%. The average promotion rate was 87.0% against a target of 84.1%. The significant gender gap on average scores in 2014 has closed in the 2016 results. Average scores in the midline survey results including GUN are marginally lower (national average test scores decreased from 45.74% in 2014 to 44.70% in 2016), this being attributable to the outbreak in conflict. Cumulatively, 184,212 individual girls are confirmed to have received Cash Transfers over the course of the programme. A total of 62,187 girls are confirmed to have received a Cash Transfer for the first time in 2016. The cumulative number of schools receiving capitation grants were 3,359 primary schools and 242 secondary school.

Assessment of whether the programme continues to represent value for money

- Negotiations with the Co-Op Bank reduced execution costs for cash transfer payments to £3 per transfer from a starting offer of £8.40, as well as securing a preferential exchange rate 15% above market rates. With over 150,000 transfers being disbursed, this amounts to savings of £810,000 on the execution charge and around £600,000 on the exchange rate.
- Despite a serious decline in the government's income position, GESS has managed to secure a release of around £200,000 from government budget towards capitation grants.
- A partnership between GESS and USAID's Room to Learn project provided additional learning materials to schools to the value of $300,000.
- The Government’s Education Management Information System has been unable to report in 2016. SSSAMS[7] has continued to report national enrolment data across South Sudan in the same period.
  [7] www.sssams.org

The overall VFM of the project relates to the cost-effectiveness of interventions which increase the levels of enrolment, retention and learning of girls in education, and the continued functioning of schools. A recent project-commissioned econometric study (Global Education and Sussex Research academic paper[8]) indicates the significant positive impact that cash transfers and capitation grants delivered in 2014 and 2015 on levels of school enrolment, despite the poor security context.
[8] To be published in 2017

Quality of financial management
By 30 September 2016, GESS’ actual spend was £35,073,089 (58.4%) out of the approved spending of £60,059,425.There is a clear structure and process for the management of programme finances, and monthly financial management meetings. Reporting of incidents to DFID is a mandatory requirement and there is evidence to show that this occurs, although timeliness could be improved. The financial overview of split per sub-output also indicates good consistency of planned expenditure vs. budget utilisation. This is a good indication of efficiency and that the project is on track.

It has become necessary to transport some programme funds for Cash Transfers and Capitation Grants by air given the current security situation, which increases costs. The Payment Agent (Cooperative Bank) undertakes this with the necessary security in place and having secured approval from Government to transport the funds. GESS is exploring alternatives to the physical transport of cash, such as mobile money systems.

Date of last narrative financial report	24th November 2016
Date of last audited annual statement	Not required

E: RISK (½ page)

Overall risk rating MAJOR
GESS have been proactive in the management of risks. The programme has a risk management framework in place and a monthly risk register is updated and shared with DFID. The risk matrix centres on the external context, reputational and fiduciary risks.

Overview of programme risk
During 2016, there were significant and considerable challenges and risks to the GESS programme. The escalation in conflict in July, significant economic decline, increased inflation and the creation of a 28 state governance structure (from previous 10 states) were the main risk drivers. There were also challenges associated with the exchange rates of the UK Pound Sterling against the US dollar.

GESS has responded coherently and responsibly to the increased level of risk. The impact of continued insecurity on the programme is currently most pronounced in Central, Eastern and Western Equatoria, Upper Nile, Unity, Jonglei and Lakes states. The continued unpredictability in South Sudan suggests that GESS will need to continue to adapt to rapidly changing circumstances.

The Central Bank of South Sudan floated the exchange rate in late 2016; the first two quarters of 2016 were affected by the official exchange rate of GBP against SSP being below the market rate. This has impacted on the value of the Capitation Grants, Cash Transfers and operational costs of the programme. To sustain the value of the cash transfers and capitation grants, GESS mitigated this through a one-year contract with Cooperative Bank.

There are also risk factors in relation to quality and standards, due to potentially high levels of attrition of qualified teachers and head teachers due to the effects of inflation, delayed salary payments and the low status of the teaching profession. The midline surveys identified that volunteers, sometimes with only primary-level education, are filling the positions left vacant by qualified teachers. The shortage of qualified teachers potentially undermines the quality inputs of the GESS programme, and as lower standards may impact on rates of retention as well as educational outcomes.

High levels of poverty invariably impact on enrolment and retention rates for both boys and girls. Poverty is a driver of early marriage, which impacts directly on girls, the need for older children to be economically active to support their families (and themselves) leads to increased risk of children not completing their education. This risk cuts across both education and child protection – early marriage and child labour both constituting child rights violations.

Outstanding actions from risk assessment
GESS and the DFID management team regularly review and adapt to the changing risk conditions with South Sudan. Actions recorded in the November 2016 Risk Register are all under active management and mitigation, and include addressing difficulties with access; tracking Cash Transfers to eligible girls who have been displaced; using Capitation Grants to improve teacher attendance; exploring alternatives to transporting cash; increasing oversight and scrutiny to ensure girls cash receipts are safeguarded; continued due-diligence on state and county partners, and promoting ownership of project components by stakeholders and actors at all levels.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Overall, the programme is on track to achieve its planned spending targets. By the end of September 2016 GESS had a cumulative spend of £35,073,089 against a budgeted disbursement of £60,059,425. This equates to 58.4% of the overall approved spending. The programme is within the planned time frame; the targets for 2016 have been met. The impact area of primary Gender Parity Index (GPI) is already above the 2017 milestone, and the girls pass rate at primary and secondary levels have achieved the set target. Most girls' scores increased since 2014 while boys' scores decreased. Generally, there was stronger progress pattern at upper primary (particularly girls’ numeracy results), with less at secondary. as it correlates with enrolment data.

Performance of partnership(s)
GESS have consistently demonstrated professionalism in their service delivery and readiness to maintain the ongoing partnership with DFID, MoGEI, the consortium partners and the state anchors. The GESS team have also promptly and regularly communicated with DFID and also held monthly programme meetings. They coordinated various activities with the ministry for instance the Education Transfer Monitoring Committee chaired by the Ministry and the GESS Steering Committee which is chaired by DFID with the Ministry as a co-chair. GESS consortium works with state anchors in the implementation and holds a programme review after every six months.

Asset monitoring and control
The GESS programme submits an updated asset list periodically and control measures are in place through risk matrix and incident tracker (where assets are involved).

The planned spending of the project period ending 30 September 2016 was 27% below forecast because of two main factors: 1) delayed payment of cash transfers to girls; and 2) reduced activity by all state anchors due to spreading insecurity after July 2016. Both factors were the result of continued insecurity in the country, particularly in the most populous Equatoria areas that contain the largest numbers of schools and students. Because of the prolonged insecurity, schools in some counties were closed and state anchors were unable to continue with their work. Planning and organising the cash transfers to girls was delayed, though payments recommenced in early October 2016 and are now proceeding well. Payment of cash transfers and distribution of capitation grants are expected to continue without further delay.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
The programme does not utilise general or sector budget support. The GRSS has committed SSP 60 million (approx. GBP 600,000) to fund primary school Capitation Grants, with GESS providing joint funding to bridge the gap created by current economic factors.

An additional £2 million in funds was allocated to GESS by DFID South Sudan in early 2016 to cover the costs of cash transfers and Capitation Grants to Primary Schools. The Capitation Grants have been utilised to ensure that schools remain open, functional and provide much needed stability. This funding was allocated on the understanding that Government would be responsible for these costs in future. Given the current economic climate GESS should revisit this agreement with the Education Ministry to mitigate against problems emerging at year end, and into 2017/18.

H: MONITORING AND EVALUATION (½ page)

Evidence and evaluation
For this review year, the focus group discussions with stakeholders and the nine surveys and research studies carried out by GESS have provided evidence of the project outcomes and impacts. In addition, there is an independent draft academic paper (Global Education and Sussex Research) specific to the impact of cash transfers and capitation grants.

During the review year, the project data has been continuously disaggregated. The quarterly reports and researches completed by GESS document project disaggregated data by gender and by state. This indicates that the previous year's recommendation to disaggregate data to indicate levels of performance and impact has been implemented.

There is good evidence that the theory of change proposed in the GESS Business Case is effective and achieving its desired objectives. However, addressing cultural and institutional barriers that limit girls’ access to education will be difficult to overcome within a period of five years. There is a need to tackle the core cultural barriers so that girls can make genuine choices in their lives. There is good evidence that project inputs are working towards this end, and the programme supports the needed sustained government and social advocacy, promoting gender mainstreaming in all sectors of the education system.

The review process
This Annual Review was undertaken by a single independent Education Specialist, Hassan Ahmed, who was in-country from 7 to 15 September 2016. The consultant visited and held focus group discussions with GESS Secretariat, MoGEI, GESS Partners, and State Anchors. Four schools in total were visited (three primary and one secondary), and a sample of girls who received cash transfers as well as trained girl mentors were interviewed.

Monitoring progress throughout the review period
The GESS Secretariat has a robust system of quarterly planning and performance review that involves all consortium partners and state anchors. The quarterly report provides a regular update of progress against the log frame, supported by a narrative of challenges faced and lessons learned. Each state anchor reports financial progress on a quarterly basis.

DFID has been unable to undertake direct monitoring visits due to the security situation. This has led to an urgent need to establish robust programme monitoring and DFID has established a rapid response Third Party Monitoring process. This will undertake targeted verification visits to confirm the accuracy of reporting and the delivery of work undertaken by the implementing partners, by analysing and collating information on service delivery and beneficiary feedback. This mechanism for monitoring was put in place in late 2016. An independent Mid-Term Review is scheduled for February 2017.