## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | DFID Turkey and support for Facility for Refugees in Turkey 1 & 2
IMPACT | Impact Indicator 1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
Refugees in Turkey can meet their basic needs, participate in education, receive healthcare, and find livelihood-opportunities. Affected host communities are supported to ensure that quality of life and positive inter-community relations are maintained. The Turkish society and responsible institutions find themselves supported in hosting the refugee population. (from EURF) Ensure political recognition of UK burden sharing to support wider development, humanitarian and migration objectives (UK specific) | % of Syrian boys and girls (5-17yrs) enrolled in formal education | Planned | 59 | 65 | 65 |  | 65
|  | Achieved |  | TBD | 684919 | TBD
Source
3RP
| Impact Indicator 2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| % of Syrians refugees reporting access and satisfaction with health services in targeted provinces | Planned | Not measured | TBD | TBD |  | TBD
|  | Achieved |  | TBD
Source
3RP
| Impact Indicator 3 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| % of assisted Syrian refugees and host community members that are gaining income | Planned | Not measured | TBD | TBD |  | TBD
|  | Achieved |  | TBD
Source
3RP
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
School age Syrian refugees have access to and receive quality education in the Turkish education system | Total number of Syrian refugee children enrolled in the Turkish education system | Planned | 210710 | Not set |  |  | 400000 | • Coordination and partnership between EU, UN, IFIs and GoT • EU-Turkey Statement holds • IPA process stable • No. of refugees remains manageable and Turkey's policy conducive, including returns that are voluntary, safe and dignified • There is donor support post-FRIT2 • There can be support for non-Syrian refugees in FRIT2
|  | Achieved |  | TBD | 1082172
Source
FRIT EU Results Framework and Monitoring Reports
| Outcome Indicator 1.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Average number of children per classroom in the provinces with the highest number of Syrian refugees | Planned | TBD | Not set |  |  | TBD
|  | Achieved |  | TBD
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.1 | Output Indicator 1.1.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Access of refugee children and youth to educational programmes increased | Number of Syrian refugee children who followed Turkish language classes funded by the facility | Planned | 0 | 260000 | 202500 |  | 390000 | • Implementers have sufficient capacity and minimum acceptable operating environment to implement projects • The needs assessment and other sources of information accurately identify the needs of refugees and host communities • Turkey continues to integrate refugees into the Turkish school system
|  | Achieved |  | 301456 | 98994
Source
FRIT EU Results Framework and Monitoring Reports
| Output Indicator 1.1.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of Syrian refugee children and youth enrolled in non-formal education funded by the facility | Planned | 0 | 44000 | 54950 |  | 39000
|  | Achieved |  | 69704 | 41047
Source
FRIT EU Results Framework and Monitoring Reports
| Output Indicator 1.1.3 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of refugee children enrolled in school receiving CCTE | Planned | 0 | 230000 | 550000 |  | 450000
|  | Achieved |  | 356611 | 562016
Source
FRIT EU Results Framework and Monitoring Reports
| Output Indicator 1.1.4 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of higher education scholarships funded by the facility granted to Syrian refugee students | Planned | 0 | 598 | 910 |  | 913
|  | Achieved |  | 475 | 875
Source
FRIT EU Results Framework and Monitoring Reports
IMPACT WEIGHTING (%) | Output Indicator 1.1.5 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of Syrian refugee and host community students enrolled in VET institutions supported by the facility | Planned | 0 | New indicator | xx |  | 20000
|  | Achieved |  | TBD
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.2 | Output Indicator 1.2.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Conducive learning environment promoted | Number of educational personnel trained, funded by the facility | Planned | 0 | Not set | 72530 |  | 29530 | • Implementers have sufficient capacity and minimum acceptable operating environment to implement projects • The needs assessment and other sources of information accurately identify the needs of refugees and host communities • Turkey continues to integrate refugees into the Turkish school system
|  | Achieved |  | 24119 | 172765
Source
FRIT EU Results Framework and Monitoring Reports
IMPACT WEIGHTING (%) | Output Indicator 1.2.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of educational personnel receiving salaries and/or incentives funded by the facility | Planned | 0 | New indicator | 8400 |  | 12800
|  | Achieved |  | TBD | 7364
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1.3 | Output Indicator 1.3.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Education infrastructure improved | Number of existing schools upgraded in standards funded by the facility | Planned | 0 | Not set | 1790 |  | 708 | • Implementers have sufficient capacity and minimum acceptable operating environment to implement projects • The needs assessment and other sources of information accurately identify the needs of refugees and host communities • Infrastructure environment continues meets EU tendering and competition rules
|  | Achieved |  | 48 | 3902
Source
FRIT EU Results Framework and Monitoring Reports
IMPACT WEIGHTING (%) | Output Indicator 1.3.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of schools constructed funded by the facility | Planned | 0 | Not set | 360 |  | 175
|  | Achieved |  | 0 | 28
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Health of Syrian refugees improved | Prevelance of main communicable diseases (CD) among Syrian refugees in the provinces with the highest concentration of Syrian refugees | Planned | Not measured | New indicator |  |  | 30% decline | • Coordination and partnership between EU, UN, IFIs and GoT • EU-Turkey Statement holds • IPA process stable • No. of refugees remains manageable and Turkey's policy conducive, including returns that are voluntary, safe and dignified • There is donor support post-FRIT2 • There can be support for non-Syrian refugees in FRIT2
|  | Achieved |  | TBD
Source
FRIT EU Results Framework and Monitoring Reports
| Outcome Indicator 2.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Prevelance of main non-communicable diseases (NCD) among Syrian refugees in the provinces with the highest concentration of Syrian refugees | Planned | Not measured | New indicator |  |  | TBD
|  | Achieved |  | TBD
Source
FRIT EU Results Framework and Monitoring Reports
| Outcome Indicator 2.3 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Refugee population per migrant health unit | Planned | NA | Not set | 780 |  | 4000
|  | Achieved |  | 34100 | 785
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2.1 | Output Indicator 2.1.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Operational capacity of healthcare system in provinces with high influx of Syrian refugees increased | Number of health workers receiving salaries funded by the facility | Planned | 0 | New indicator | 3090 |  | 850 | • Implementers have sufficient capacity and minimum acceptable operating environment to implement projects • The needs assessment and other sources of information accurately identify the needs of refugees and host communities • Turkey continues to integrate refugees into the Turkish health system, including continuing to support migrant health centres
|  | Achieved |  | TBD | 3213
Source
FRIT EU Results Framework and Monitoring Reports
| Output Indicator 2.1.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of facility-funded community mental health centres providing services | Planned | 0 | New indicator | 19 |  | 10
|  | Achieved |  | TBD | 17
Source
FRIT EU Results Framework and Monitoring Reports
| Output Indicator 2.1.3 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of health workers trained, funded by the facility | Planned | 0 | New indicator | 7830 |  | 4520
|  | Achieved |  | TBD | 7800
Source
FRIT EU Results Framework and Monitoring Reports
IMPACT WEIGHTING (%) | Output Indicator 2.1.4 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of state hospitals constructed, funded by the facility | Planned | 0 | Not set | 2 |  | 2
|  | Achieved |  | 0 | 0
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2.2 | Output Indicator 2.2.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Utilisation of health care services by refugees increased | Number of primary healthcare consultations provided to refugees, funded by the facility | Planned | 0 | Not set | 8653370 |  | 8610000 | • Implementers have sufficient capacity and minimum acceptable operating environment to implement projects • The needs assessment and other sources of information accurately identify the needs of refugees and host communities • Turkey continues to integrate refugees into the Turkish health system, including continuing to support migrant health centres
|  | Achieved |  | 4700581 | 11920990
Source
FRIT EU Results Framework and Monitoring Reports
| Output Indicator 2.2.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of ante-natal care (ANC) consultations funded by the facility | Planned | 0 | Not set | 857710 |  | 732000
|  | Achieved |  | 987434 | 2236581
Source
FRIT EU Results Framework and Monitoring Reports
| Output Indicator 2.2.3 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of refugees who received mental health and psychosocial support services funded by the facility | Planned | 0 | Not set | 150640 |  | 140600
|  | Achieved |  | 241849 | 574258
Source
FRIT EU Results Framework and Monitoring Reports
IMPACT WEIGHTING (%) | Output Indicator 2.2.4 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of refugees who received specialised treatment in the area of post-operative and rehabilitative care funded by the facility | Planned | 0 | Not set | 24930 |  | 17900
|  | Achieved |  | 14617 | 21945
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs) |  | #NAME?
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Improved socio-economic conditions of Syrian refugees | Percentage of Syrian refugee households with per-capita expenditure equal or below the Minimum Expenditure Basket (MEB) Number of persons under temporary or international protection receiving monthly resource transfers through ESSN or other mechanisms | Planned | Not set | Not set | 1772000 |  | 63 | • Coordination and partnership between EU, UN, IFIs and GoT • EU-Turkey Statement holds • IPA process stable • No. of refugees remains manageable and Turkey's policy conducive, including returns that are voluntary, safe and dignified • There is donor support post-FRIT2 • There can be support for non-Syrian refugees in FRIT2
|  | Achieved |  | 73 | 2463773
Source
FRIT EU Results Framework and Monitoring Reports
| Outcome Indicator 3.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Percentage decrease in the mean Livelihoods Coping Strategy Index | Planned | Not set | Not set |  |  | 15% decrease
|  | Achieved |  | 6.36
Source
FRIT EU Results Framework and Monitoring Reports
| Outcome Indicator 3.3 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of Operational SMEs owned by refugee and host community member residing in Turkey | Planned | Not set | Not set | 1110 |  | TBD
|  | Achieved |  |  | 539
Source
FRIT EU Results Framework and Monitoring Reports
| Outcome Indicator 3.4 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of refugees and host community members who participated in social cohesion activities | Planned | Not set | Not set | 136430 |  | TBD
|  | Achieved |  |  | 455906
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3.1 | Output Indicator 3.1.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Persons under temporary or international protection are provided with monthly resource transfers through ESSN or other mechanisms funded by the facility | Number of persons under temporary or international protection receiving monthly resource transfers through ESSN or other mechanisms funded by the facility | Planned | 0 | Not set | 2468160 |  | 2925000 | • Implementers have sufficient capacity and minimum acceptable operating environment to implement projects • The needs assessment and other sources of information accurately identify the needs of refugees and host communities • The EU will develop an appropriate exit strategy for ESSN support through FRIT2
|  | Achieved |  | 2395057 | 2463773
Source
FRIT EU Results Framework and Monitoring Reports
IMPACT WEIGHTING (%)
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3.2 | Output Indicator 3.2.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Refugees and host community participation in employment-related services increased | Number of Syrian refugees and host community members who participated in employability skills training programmes funded by the facility | Planned | 0 | Not set | 45820 |  | 71370 | • Implementers have sufficient capacity and minimum acceptable operating environment to implement projects • The needs assessment and other sources of information accurately identify the needs of refugees and host communities • Turkey continues to integrate refugees into the labour market and recognises refugee skills based qualifications
|  | Achieved |  | 5957 | 39061
Source
FRIT EU Results Framework and Monitoring Reports
| Output Indicator 3.2.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of Syrian refugees and host community members who participated in cash for work programmes funded by the facility | Planned | 0 | New indicator |  |  | 1480
|  | Achieved |  | TBD
Source
FRIT EU Results Framework and Monitoring Reports
IMPACT WEIGHTING (%) | Output Indicator 3.2.3 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of Syrian refugees registered with ISKUR (Turkish Job Centre equivelant) | Planned | 0 | New indicator | 13800 |  | 12750
|  | Achieved |  | TBD | 11471
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3.3 | Output Indicator 3.3.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Entrepreneurship among Syrian refugees and host community members promoted through SMEs support | Number of SMEs that benefitted from coaching funded by the facility | Planned | 0 | New indicator | 1110 |  | 1100 | • Implementers have sufficient capacity and minimum acceptable operating environment to implement projects • The needs assessment and other sources of information accurately identify the needs of refugees and host communities • The regulatory environment for refugee led SMEs in Turkey remains conducive
|  | Achieved |  | TBD | 539
Source
FRIT EU Results Framework and Monitoring Reports
IMPACT WEIGHTING (%) | Output Indicator 3.3.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of SMEs that received financing through the facility (e.g. financial incentives, micro-grants) | Planned | 0 | New indicator | 440 |  | 800
|  | Achieved |  | TBD | 152
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3.4 | Output Indicator 3.4.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Refugees and host community participation in employment-related services increased | Number of operational community centres supported by the facility | Planned | 0 | New indicator | 30 |  | 30 | • Implementers have sufficient capacity and minimum acceptable operating environment to implement projects • The needs assessment and other sources of information accurately identify the needs of refugees and host communities • Turkey continues to integrate refugees into Turkish communities and the policy environment continues to support social cohesion
|  | Achieved |  | TBD | 50
Source
FRIT EU Results Framework and Monitoring Reports
IMPACT WEIGHTING (%) | Output Indicator 3.4.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of refugees and host community members who participated in social cohesion activities funded by the facility | Planned | 0 | Not set | 136430 |  | 114960
|  | Achieved |  | 109406 | 455906
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 4 | Outcome Indicator 1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Migrants are received and hosted in adequate conditions | Proportion of removal centres assessed as being in compliance with official (GoT) standards | Planned | NA | Not set |  |  | TBD | • Coordination and partnership between EU, UN, IFIs and GoT • EU-Turkey Statement holds • IPA process stable • No. of refugees remains manageable and Turkey's policy conducive, including returns that are voluntary, safe and dignified • There is donor support post-FRIT2 • There can be support for non-Syrian refugees in FRIT2
|  | Achieved |  | TBD
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4.1 | Output Indicator 4.1.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Migration management capacity increased | Number of persons who received training in migration related topics, funded by the facility | Planned | 0 | Not set | 1750 |  | 1200 | • Implementers have sufficient capacity and minimum acceptable operating environment to implement projects • The needs assessment and other sources of information accurately identify the needs of refugees and host communities • GoT standards for removal centres remain adequate against international comparators
|  | Achieved |  | 1089 | 2903
Source
FRIT EU Results Framework and Monitoring Reports
IMPACT WEIGHTING (%) | Output Indicator 4.1.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of migrants receiving facility-funded assistance whilst hosted in removal centres | Planned | 0 | Not set | 110000 |  | 110000
|  | Achieved |  | 86665 | 325589
Source
FRIT EU Results Framework and Monitoring Reports
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTCOME 5 | Outcome Indicator 1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Strong FRIT coordination between EU, GoT, Member States (MS) and UN. UK playing leading role on FRIT strategic direction and engagement with GoT. | Clear strategic direction of FRIT agreed by EU Member States and the GoT, with strong coordination between GoT and EC | Planned | FRIT1 designed in Brussels with limited MS, UN, GoT input | Strategic Concept Note agreed that reflects UK priorities in place for second tranche | Sustainable approach to second FRIT 2 underway, including ESSN 2 |  |  | • Coordination and partnership between EU, UN, IFIs and GoT • EU-Turkey Statement holds • IPA process stable • No. of refugees remains manageable and Turkey's policy conducive, including returns that are voluntary, safe and dignified • There is donor support post-FRIT2 • There can be support for non-Syrian refugees in FRIT2
|  | Achieved |  | Presented in June 2018
Source
| Outcome Indicator 2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| UK and EU recognition by GoT (and UK recognised by EU) for burden sharing | Planned | Uncertainity of continued participation of UK in FRIT 2 | Agreement for UK to participate in FRIT 2 in Draft EU Withdrawal Agreement | Contribution Certificate agreed with European Commission that reflects SoS red lines on voting rights, participation of UK organisations and ability to raise human rights concerns
|  | Achieved |  | In draft agreement text
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 5.1 | Output Indicator 5.1.1 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1) | Assumptions
Strengthened FRIT governance and coordination. UK playing leading role on FRIT Steering Committee. Increased transparency with MS. | Number of FRIT Steering Committee meetings, with quality and substantive discussion focused on UK priorities | Planned | 0 | 10 meetings; UK attendance and strategic engagement at each meeting | 13 Meetings, SC consulted on FRIT2 development with UK priorities recognised |  | Continued UK strategic engagement at all SC meetings | • Post Brexit, the UK continues to contribute to FRIT2 and maintains a comparable level of oversight as with FRIT1
|  | Achieved |  | 10 SCs - UK priorities recognised, including through FRIT2 strategic concept note | 13 SCs - UK priorities recognised
Source
| Output Indicator 5.1.2 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Regular and quality reports by the European Commission on implementation of the EU-Turkey Statements | Planned | 0 | 9 reports produced | Increased transpaerency on results and monitoring and evaluation |  | Full transparency by EC on FRIT reporting
|  | Achieved |  | 9 produced, including strategic direction for FRIT2
Source
| Output Indicator 5.1.3 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| Number of project level factsheets shared with MS. | Planned | 0 | 50% projects | 100% projects |  | 100% projects
|  | Achieved |  | 30% (21 / 71) | 100% projects
Source
IMPACT WEIGHTING (%) | Output Indicator 5.1.4 |  | Baseline 2016 | 2018-09-01 | 2019-09-01 | 2020-09-01 | Target (end FRIT1)
| DFID access and influence to EC, implementers and Government of Turkey | Planned |  | Regular meetings at senior and working level with key implementers, EC and GoT - indicates behaviour, policy or programming change | MoU in place with GoT; UK exercising governance role in FRIT 2 successfully; access continues.
|  | Achieved |  | Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Total (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1
2
3
4
5
6
7
8
9
10

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.