Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programme’s performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	15 February 2017

Title: Support to International Agricultural Research Centres that benefits Poor People
Programme Code: 202748	Start Date: 12/01/2012	End Date: 12/03/2016
If programme was closed >1 month early please describe in a few words why.	Not applicable.

Summary of Programme Performance
Year	2012	2013	2014	2015	2016
Programme Score	A+	A	A	A	A
Risk Rating	Low	Low	Low	Low	Low

Financial Position
Original Programme Value	£30,000,000
Extensions/ amendments	2012: additional funding of £10 million approved / 2015: one year extension of programme timeframe with additional funding of up to £10.2 million
Log-frame revisions (with dates)	None
Total programme spend	£48,116,417.16

Summary of Progress
An estimated 800 million people are undernourished globally and access to high-yielding, disease, drought, flood and pest resistant crops is essential to combat hunger, reduce humanitarian crises from crop failure and underpin livelihoods of poor farmers. New technology is also important for growth in the agricultural sector. This programme aimed to tackle poor availability of, and access to, high-yielding, disease, drought, flood and pest resistant crops and the knowledge needed to protect these crops from pests and diseases for small-holder farmers in developing countries. This is essential to combat hunger, reduce humanitarian crises from crop failure and underpin the livelihoods of poor farmers. This programme developed and delivered a range of agricultural technologies and innovations, as well as new research and knowledge, to reduce poverty and hunger, and support adaptation to climate change.
The programme has met expectations and delivered against its intended outcomes through the Centres funded – World Vegetable Centre (AVRDC), CABI, Crops for the Future (CFF), Global Forum for Agriculture Research (GFAR), International Centre for Insect Physiology and Ecology (icipe) and International Centre for Integrated Mountain Development (ICIMOD) and. Highlights include:-
- CABI’s Plantwise[1] programme, which won the OECD[2] Development Innovation Prize in March 2016, reached 4.5 million households in 34 countries through a network of plant health clinics and plant doctors, which provide farmers with practical, science-based diagnosis and advice to prevent and manage crop loss from pests and diseases
  [1] Plantwise is a global plant health programme which works closely with national agricultural advisory services to to help farmers lose less of what they grow to plant health problems.
  [2] Organisation for Economic Co-operation and Development.
- AVRDC bred disease, pest and heat tolerant vegetables (22 varieties of 9 crops in 5 countries in Africa and 39 varieties of 13 crops in Asia), and developed integrated pest management strategies;
- icipe’s push-pull technology for the control of parasitic weed, striga and stem borer in maize was adopted in over 120,000 households (62% of them female-headed) in 8 countries in East Africa. icipe developed and tested an effective and low cost biopesticide[3] to control ticks in livestock. Registration of this biopesticide is currently underway in Kenya which will enable the product to be sold to farmers.
  [3] Biopesticides are naturally occurring pesticides derived from: animals, plants, bacteria, and certain minerals
- ICIMOD supported the Governments of India and Nepal to develop a regional flood information outlook system to improve national flood risk assessment efforts through proactive engagement with key stakeholders.

Follow up actions required following closure
DFID issued letters to the World Vegetable Centre (AVRDC), CABI and icipe in August 2016, outlining recommendations following the final performance review to determine eligibility for the annual discretionary performance-based payment. Key recommendations are reproduced below for each of these three Centres, who – as outlined below – are now receiving funding under Phase II of this programme of support to international research Centres. An additional, programme level recommendation was to increase engagement between Centres and DFID Country Offices, where appropriate. CABI has been particularly proactive in engaging with Country Offices and DFID will continue to facilitate links during the next phase of funding.

World Vegetable Centre (AVRDC)
- Develop a clear vision and strategy for the next 3-5 years for the organisation, including a clear approach to the uptake of key technologies – outlining partnerships required to deliver impact, the operational research agenda around impact, and scaling strategies
- Continue to make progress on publishing research outputs with a strong focus on gender

CABI
- Continue to deliver quantitative evidence of impact for the Plantwise programme, and clarify the impact level being targeted (reduced yield gaps, increased productivity, or increased household incomes and nutrition)
- Maintain good progress made on producing research outputs with a strong focus on gender. This could include analysis of the differential uptake and impact of Plantwise recommendations by men and women.
- Continue to develop the Plantwise Online Management System (POMS) and generate evidence of its utility in driving management decisions in country

icipe
- Develop the evidence base to demonstrate the impact of icipe’s core science work, including a clear strategy to improve the quality and relevance of impact evaluations
- Continue to focus on gender disaggregation in output reporting and gender analysis in research outputs
- Develop a clear approach to scaling and delivery for fruit fly and climate-adapted push pull technology for the next 3 years

Based on their strong performance, continued alignment with DFID research priorities, and value for money, DFID has approved a new phase of funding to three of the Centres funded under this project (CABI, icipe and the World Vegetable Centre). The new project’s code is 205271.

## A. INTRODUCTION AND CONTEXT (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717589.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3719418.odt

Outline of programme and what it has achieved
The UK invested £48.1 million in a group of International Agricultural Research Centres over a five year period (2011-2016) – to address the need set out in the 2011 UK Government Office for Science Foresight report[4] for more effective agricultural research investments to address growing global concerns around food security. This investment was approved in two phases. In 2011, a business case was approved to provide up to £30 million to scale up our core funding to five international research Centres – World Vegetable Center (AVRDC), Centre for Agriculture and Biosciences International (CABI), Crops for the Future (CFF), Global Forum on Agricultural Research (GFAR), International Centre of Insect Physiology and Ecology (icipe). ICIMOD was added to the programme in 2012 after a robust value for money assessment to support their work in mountain regions.
[4] UK Government Office for Science, Global Food and Farming Futures Foresight project, 2011
A brief description of each of the Centres is set out below.
- AVRDC focuses on breeding and commercialising improved vegetable lines, reducing post-harvest loss and improving nutritional value of vegetables.
- CABI, an international organisation headquartered in the UK, plays a unique role in curating and delivering scientific expertise and knowledge to solve problems in agriculture;
- CFF focuses on developing solutions for diversifying future agriculture using underutilised crops to improve food and nutritional security and livelihoods of the poor;
- GFAR is a partnership organisation working, at national, regional and international levels, to advocate for, and catalyse, collective actions that strengthen and transform agri-food research and innovation systems;
- ICIMOD, a regional organisation, based in Nepal aims to enable sustainable and resilient mountain development for improved and equitable livelihoods through knowledge and regional cooperation;
- icipe is the only international research Centre which focuses on insect science and its role in sustainable development, ensuring environmentally safe, affordable and accessible tools and approaches to controlling insect pests and disease vectors.
These Centres were selected following a value for money review of a group of research Centres, using Multilateral Aid Review framework criteria. In 2012, additional funding of £10 million for CABI and icipe was approved, based on evidence of excellent research quality with development impact and value for money for DFID during a 2012 review of the Centres’ performance. Funding to both CFF and GFAR ceased from 1 April 2014. In the case of CFF, the primary reason for this was that CFF could not demonstrate that they had sufficiently strengthened their approach to gender analysis, environmental mainstreaming, and continuous improvement of research quality. In the case of GFAR, the key reason was that GFAR had failed to demonstrate sufficient progress in developing its approach to measuring and demonstrating impact during the first years of the programme. In both cases, DFID judged that progress made by the two Centres was not sufficient to demonstrate continued value for money for DFID funding. In 2015, the overall programme was extended by a year (to August 2016), with increased funding of up to an additional £10.2 million. Total approved funding was for up to £50.2 million.
Throughout the programme, each of the selected research Centres focused on three or four key deliverables; for example, new improved vegetable lines with good nutritional and/or disease resistant properties, roll out of new national plant health systems in 30 countries, scaling up of “push-pull” control of striga in cereals in Africa and an integrated pest management technology for control of African fruit fly and mechanisms for tracking investments in Agricultural Research for Development (AR4D) and for building user feedback into international agricultural research systems. DFID formally assessed performance against the agreed key objectives on an annual basis through the DFID Annual Review process, and through an additional performance management and review process linked to a discretionary performance-related payment. The programme scored an A+ in 2012 and an A in all subsequent years, and delivered against the objectives as set out in the original business case, including:
- CABI’s Plantwise[5] programme, which won the OECD[6] Development Innovation Prize in March 2016, reached 4.5 million households in 34 countries through a network of plant health clinics and plant doctors, which provide farmers with practical, science-based diagnosis and advice to prevent and manage crop loss from pests and diseases
  [5] Plantwise is a global plant health programme which works closely with national agricultural advisory services to to help farmers lose less of what they grow to plant health problems.
  [6] Organisation for Economic Co-operation and Development.
- AVRDC bred disease, pest and heat tolerant vegetables (22 varieties of 9 crops in 5 countries in Africa and 39 varieties of 13 crops in Asia), and developed integrated pest management strategies;
- icipe’s push-pull technology for the control of parasitic weed, striga and stem borer in maize was adopted in over 120,000 households (62% of them female-headed) in 8 countries in East Africa. In addition, icipe developed and tested a biopesticide product to control ticks in livestock, registration of which is currently underway in Kenya to permit commercial sales.
- ICIMOD supported the Governments of India and Nepal to develop a regional flood information outlook system to improve national flood risk assessment efforts.
The additional performance management and review process, referenced above, was part of a Performance Management Framework Mechanism (PMFM) which aimed to improve performance of the individual Centres in specified areas, and lead to results closely aligned to DFID priorities. In addition to assessment against programme deliverables, the review process involved assessment of the Centres’ performance against good governance measures; for example, robust financial systems, an environmental management system with targets for reducing carbon footprint and metrics on energy use, and HR policy and operational plans for ensuring gender balance in organisational structures and research processes implemented. On the basis of the annual performance review, DFID decided upon the eligibility of each of the Centres for a discretionary performance-based payment to enable further scale up of successful programmes. In this way, by explicitly linking funding to performance and delivery, DFID was able to exercise significant influence over the Centres’ programmatic performance, and their institutional development against key governance and management indicators. This meant, in addition to driving strong programme delivery, DFID was able to ensure the Centres’ approaches to key DFID priority areas, such as gender inclusivity, were strengthened. These approaches govern the Centres’ entire portfolio of programmes and research – not just those involved in delivering DFID’s required outputs under this programme – therefore measuring and incentivising greater focus on these areas harnessed additional value for money from this programme. Overall, the performance management system was successful in incentivising good progress from the Centres, with each Centre clearly demonstrating that they were responding to recommendations made following each yearly performance review.
An external evaluation of the performance management system, conducted over the period 2014-2016, concluded that the performance management system established by DFID provided the Centres with “a clear focus on the agreed outputs and outcomes. It has also been effective in facilitating the delivery of high quality research, the agreed results, and value for money”[7]. The evaluation also identified a number of key lessons – outlined below – which have been disseminated within DFID and which have directly informed the design of the performance management system currently operational under the new phase of funding to the World Vegetable Centre (AVRDC), CABI and icipe. Based on the conclusions of the external evaluation, combined with DFID’s own experience in managing the programme, the review team concludes that the performance management system was effective in driving improved performance in priority areas, and in ensuring value for money for DFID funding. It also enhanced flexibility: DFID was able to reward strong performance by the Centres by awarding them additional funding which was then used to further scale up successful programmes.
[7] Landell Mills (2016) ‘Evaluation of DFID’s performance management funding of international agriculture research Centres – Final Report’: http://iati.dfid.gov.uk/iati_documents/5332933.pdf

Key lessons from the external evaluation of DFID’s performance management funding:
- Regular dialogue and clear communication between the Centres and DFID is essential to the success of performance management.
- The performance management system should be designed in such a way that funds can be planned for by the Centres.
- Clear agreement in advance on the measures used to assess performance and the ways in which these will be applied is important to promote a shared understanding of the review mechanism.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Overall Outcome Assessment
The programme set out to generate new research and technologies that would contribute to agricultural growth, improvements in nutritional status and poverty reduction. The intended outcomes of the programme, at the time of the original Business Case in 2011, were:
- New technologies, products and knowledge to address agriculture yield gaps, hunger and malnutrition;
- Technologies, products and knowledge put into use at scale;
- A step change in systems to measure impact
The programme was successful in achieving these intended outcomes. Key successes against each of the three areas are outlined in Table 1 below. While DFID funding was important to achieving the outcomes, success also built on previous funding from DFID and other donors.
The programme scored an A+ in 2012, and an A in all subsequent years.
Table 1: Impact delivered by DFID funding to Research Centres
Intended outcome	Achievements
New technologies, products and knowledge to address agriculture yield gaps, hunger and malnutrition	AVRDC bred and released disease, pest and heat tolerant vegetables (22 varieties of 9 crops in 5 countries in Africa and 39 varieties of 13 crops in Asia). Improved varieties are have also been included in home garden seed packs in four African countries. / CABI conducted new research on the economic impacts of key invasive species at national and household level, which included producing Africa’s first invasive species distribution maps. This work provides baseline evidence which can underpin future programmes.
Technologies, products and knowledge put into use at scale	Over 120,000 households (62% of them female-headed) in eight countries in East Africa adopted icipe’s ‘push-pull’ technology for the control of parasitic weed, striga and stem borer in maize. Over 30,000 hectares of land were treated with biopesticides developed and tested by icipe and its commercial partners to control fruit flies. / CABI’s Plantwise programme reached 4.5 million households in 34 countries through a network of plant health clinics and plant doctors. Plantwise provides farmers with practical, science-based diagnosis and advice to prevent and manage crop losses from pests and diseases. / CABI’s Knowledge Bank, which supports and is linked to the Plantwise programme was upgraded and now supports national decision making on plant health in over 30 countries. / AVRDC support to home gardens in 15 countries has enabled more than 118,000 households to grow more than 35 types of 29 vegetables crops, increasing their incomes and consumption of vegetables in the home. They have worked with 9 private companies to provide more than 106,000 seed kits and continue to work with some of them using feasible business models to ensure continued availability of seed. / AVRDC’s research and development activities on grafting has made available nine rootstock lines (1 tomato, 5 eggplant and 3 chili pepper) with different combinations of tolerance/resistance to flooding, bacterial wilt, fusarium wilt, root-knot nematode and Pytophthora blight. The rootstocks have been introduced to at least 19 countries in Asia, Africa, the Americas and Oceania. Tens of millions of tomato and pepper seedlings grafted onto WorldVeg rootstocks are planted annually, increasing productivity and income of growers and nursery operators. / Tomato varieties developed by AVRDC accounted for 87% of commercial tomato seed production in Tanzania and generated economic gains of $254 million over the period 1993-2014. African eggplant varieties developed by AVRDC accounted for 100% of commercial seed production in Tanzania and generated economic gains of $5 million over the period 2003-2014. While, in both cases, these time periods span more than just the programme timeframe (2012-2016), the examples provide an indication of the level of impact achieved by AVRDC’s work. / ICIMOD has successfully influenced agriculture relevant policies in a number of countries and has supported the Governments of India and Nepal to develop a regional flood information outlook system to improve national flood risk assessment efforts.
A step change in systems to measure impact	AVRDC made significant progress in strengthening its capacity in impact evaluation during the programme. New appointments of personnel led to a significant increase in impact work, including impact-related research publications. / CABI made good progress on impact evaluation, undertaking a wide range of assessments using a variety of methods. These included a major evaluation of Plantwise in Kenya, a retrospective analysis of the impact of improved coffee processing, an impact evaluation of mobile agri-advisory services, and several other studies of Plantwise. / ICIMOD also made good progress on impact evaluation. There was a demonstrable increase in ICIMOD’s impact assessment and monitoring work relevant to agriculture and development during the programme, including an ongoing randomised control trial (RCT) of the Centre’s Nepal agriculture extension programme, in partnership with J-PAL. / icipe made progress on monitoring and evaluation, and introduced results-oriented monitoring in projects. By the end of the programme, the Centre had a number of impact studies underway and planned, including studies on the impact of multi-technology adoption on nutrition security and child stunting, stem borer control on poverty reduction, and biological control interventions on maize productivity and poverty reduction. / The Global Forum on Agricultural Research (GFAR) – funded during the first two years of this programme – failed to demonstrate sufficient progress in developing its approach to measuring and demonstrating impact. This was one of the reasons why DFID ceased funding to GFAR in 2014.

Output Score and Description
The programme logframe contained two outputs:
- Output 1: Centres generating high quality research outputs
- Output 2: Organisational behaviours which underpin effectiveness and value for money for DFID are strengthened
These two overarching outputs were designed to encompass Centre-specific targets agreed between DFID and each of the Centres at the outset of the programme.
Each of the four Centres funded during the whole programme generated high quality research outputs, and each evidenced developments in key organisational behaviours. Further detail is provided in the following sections. A key output was the number of peer-reviewed publications from each Centre, an indicator of high quality research.
- AVRDC published a total of 405 peer-reviewed publications during the funding period, and, in the area of organisational behaviours, made particularly strong progress on environmental targets;
- CABI published 494 peer-reviewed research outputs, and made good progress driving further gender inclusivity in HR practices;
- ICIMOD published 248 peer-reviewed publications – making particular progress in increasing the number produced each year during the last two years of the programmes – and strengthened its environmental management work;
- icipe published 551 peer-reviewed journal articles and made good progress on integrating gender analysis into the Centre’s research activities.
Both Output 1 and Output 2 have therefore been scored an A at Project Completion Review. Progress made by each of the Centres against indicators for each of the two outputs is outlined in detail in Section C.

Lessons and how these have been shared
The external evaluation of DFID’s performance management funding, commissioned by DFID in 2014 and finalised in 2016, produced a number of key lessons specific to the performance management system. These included:
- Regular dialogue and clear communication between the Centres and DFID is essential to the success of performance management
- The performance management system should be designed in such a way that funds can be planned for by the Centres
- Clear agreement in advance on the measures used to assess performance and the ways in which these will be applied is important to promote a shared understanding of the review mechanism.
These lessons have directly informed DFID’s approach to performance management of the three Centres (World Vegetable Centre, CABI and icipe) funded under a new programme of funding which began in 2016. In addition, the final report produced by the external evaluator has been widely disseminated within DFID to assist other teams in designing fit for purpose performance management systems for other programmes.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Centres generating high quality research outputs
Output number per LF		1	Output Score	A
Risk:		Minor	Impact weighting (%):	70%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Key Points
Indicator(s)	Milestones
Centres on track with agreed deliverables	The milestones are Centre specific and too many to list here. However, the summary below provides detail on each Centre’s performance against planned delivery of agreed deliverables.

Each Centre reports to DFID on an annual basis against agreed deliverables and performance was assessed against milestones. The programme has consistently achieved an Output Score of A, indicating that outputs meet expectations throughout the lifetime of the programme. The summary below provides an overview of what each Centre delivered with DFID funding. Throughout the funding period there was a strong focus on delivering innovation and scale to reach smallholder farmers in development countries.

World Vegetable Centre (AVRDC)
- AVRDC bred disease, pest and heat tolerant vegetables (22 varieties of 9 crops in 5 countries in Africa and 39 varieties of 13 crops in Asia), and developed integrated pest management strategies;
- AVRDC support to home gardens in 15 countries has enabled more than 118,000 households to grow more than 35 types of 29 vegetables crops, increasing their incomes and consumption of vegetables in the home. They have worked with 9 private companies to provide more than 106,000 seed kits and continue to work with some of them using feasible business models to ensure continued availability of seed.
- AVRDC’s research and development activities on grafting have made available nine rootstock lines (1 tomato, 5 eggplant and 3 chili pepper) with different combinations of tolerance/resistance to flooding, bacterial wilt, fusarium wilt, root-knot nematode and Pytophthora blight. The rootstocks have been introduced to at least 19 countries in Asia, Africa, the Americas and Oceania. Tens of millions of tomato and pepper seedlings grafted onto WorldVeg rootstocks are planted annually, increasing productivity and income of growers and nursery operators.
- Research and analysis conducted by AVRDC demonstrated that AVRDC-developed tomato varieties accounted for 87% of commercial tomato seed production in Tanzania and generated economic gains of $254 million from 1993-2014. For African eggplant, AVRDC-developed varieties accounted for 100% of commercial seed production in Tanzania and generated economic gains of $5 million from 2003-2014.

CABI
- CABI’s Plantwise[8] programme, which won the OECD[9] Development Innovation Prize in March 2016, reached 4.5 million households in 34 countries through a network of plant health clinics and plant doctors, which provide farmers with practical, science-based diagnosis and advice to prevent and manage crop loss from pests and diseases. This success has been supported by a wide range of activities including development of the Plantwise Online Management System (POMS), development of Plantwise apps to support Plant Doctors, and the roll-out of tablets to Plant Doctors in 9 countries.
  [8] Plantwise is a global plant health programme which works closely with national agricultural advisory services to to help farmers lose less of what they grow to plant health problems.
  [9] Organisation for Economic Co-operation and Development.
- Plantwise is also supported by the Plantwise Knowledge Bank, an open access internet resource, which has been updated and expanded during the reporting period. It now contains information on 2,500 crop pests in 80 languages, over 2,000 validated, updateable factsheets with links to nearly 10,000 further factsheets and videos, thousands of images to assist with diagnoses and interactive maps showing pest distribution. The Knowledge Bank, which supports and is linked to the Plantwise programme was upgraded and now supports national decision making on plant health in over 30 countries.
- CABI-commissioned evaluations of the Plantwise programme in a number of countries have indicated that there is a high likelihood that plant clinics would continue after withdrawal of donor support. Sustainability of the Plantwise model has been a key priority for DFID during the funding period. An on-going evaluation of Plantwise in Kenya will deliver robust evidence on the effectiveness of the programme in 2017, and has already indicated a high level of satisfaction with the service and confirmation that farmers use the advice they receive.
- New research on the economic impacts of key invasive species at national and household level including Africa’s first invasive species distribution maps. This provides the baseline evidence for future programmes.
- Since 2009, 7 million farmers to have received plant health/nutrition-sensitive agricultural information through CABI supported mobile platforms.

Crops for the Future (CFF)
CFF received a total of £300,000 funding under this programme, spread over two years. This enabled them to improve their web based information system to provide reliable and useful information about Neglected and Underutilised Species (NUS). NUS are potentially very valuable for improving food and nutritional security and livelihoods of the poor in a context of climate change and increased dependence on a limited number of staple crops. CFF also acted as a co-convener of several symposia and conferences, delivering papers during these events to promote awareness amongst policy makers, researchers and donors for the potential of NUS to make contributions to improved livelihood, nutrition, income and sustainable agriculture consistent with the targets of the Millennium Development Goals.
While acknowledging CFF’s niche role with respect to NUS, DFID ceased funding to CFF due to weaknesses in organisational systems, particularly gender analysis and environmental mainstreaming, poor peer review systems and the lack of a track record in the delivery of significant results and research of a consistently high quality.

Global Forum for Agriculture Research (GFAR)
GFAR only received funding during the first years of the programme and consequently delivered limited outcomes as compared to other Centres that received more significant funding for six years. GFAR is a multi-stakeholder forum and does not deliver technologies and products, unlike the other Centres. GFAR provides an open and inclusive space for fostering dialogue, agreeing priorities and catalysing collective actions by the many stakeholders involved in agri-food research and innovation. Actions are delivered through GFAR partners rather than GFAR directly. In the period during which they received funding, GFAR supported a number of regional and global consultations including the:
- Global Conference on Agricultural Research for Development in partnership with CGIAR[10].
  [10] A global partnership of agriculture research organisations
- Global Conference on Women in Agriculture.
The GFAR Secretariat also provided input to a wide range of processes, including the Economist Conference in Amsterdam, the EC Joint Research Council, the Oxford Policy Centre, the CGIAR-FAO Food Security Futures Meeting and the Irish EC Presidency Conference on hunger, nutrition and climate justice.
Funding to GFAR ceased at the end of Financial Year 13/14 as DFID’s performance assessment considered that GFAR was not sufficiently results-based and unable to demonstrate its impact. GFAR needed to become much more able to articulate its specific contribution to wider global processes and undertake fundamental governance reforms if they were to achieve their global ambitions on agriculture for research and development.

International Centre for Integrated Mountain Development (ICIMOD)
ICIMOD conducts research and development activities in the countries in which it operates and as a result delivers a different range of outcomes as compared to the other Centres. For example:
- ICIMOD has supported the Governments of Nepal to reduce the risks they face from flooding by developing an evidence-based regional flood information outlook system to improve national flood risk assessment efforts.
- In Pakistan, ICIMOD engagement ensured the inclusion of a mountain perspective in the national food security policy. This is essential in order to ensure those living in often overlooked, marginal areas are accounted for in policy-making.
- Following the earthquake in Nepal in 2015, ICIMOD was able to support the response by providing information on geohazards in the region resulting from the earthquake.
- Additionally, ICIMOD has supported the piloting and scale up of agriculture-based value chains for over 5000 people in mountain areas.

International Centre for Insect Physiology and Ecology (icipe)
DFID funding to icipe has supported them in three research areas: development and scaling of the push-pull approach[11], development of biopesticides for the control of fruitflys and development of acaricides for the control of ticks. Results delivered include:
[11] http://www.push-pull.net/
- Over 120,000 households (62% of them female-headed) in eight countries in East Africa have adopted icipe’s ‘push-pull’ technology for the control of the parasitic weed, striga, and stem borer in maize. These households have been reached directly by icipe and are georeferenced in monitoring systems. Additional households have been reached through partners, including One Acre Fund and World Vision, and icipe is working to improve data collection through partners to provide a more comprehensive of uptake of the technology.
- icipe research work has identified a number of potential biopesticides during the reporting period and icipe have commercialised a number of products in partnership with Real IPM, a private sector company in Kenya. In 2016, over 30,000 hectares of land were treated to control fruitflies with biopesticides developed and tested by icipe and its commercial partners. Biopesticides are derived from natural sources such as animals, plants, bacteria and fungi and can be used to control pests without leaving pesticide residues that are harmful to humans.
- Research to develop new tick control strategies is at an earlier stage, and during the reporting period a number of potential biopesticides to control ticks were screened. Potential products have been identified and are currently undergoing large scale trials in Kenya to support product registration.

Indicator(s)	Milestones
Research publications including the number in peer-reviewed journals	Ratio of peer reviewed publications to total publications is stable or increases.

Table 2 provides a summary of publication data across the four Centres that received funding for four years or more during the programme. It should be noted that the tracking of publication data is principally about Centres setting targets and delivering against them. Each Centre works in a specific technical area and therefore the figures are not directly comparable between Centres. For example, AVRDC publishes the highest number of peer reviewed articles, but specialist horticulture journals, appropriate to their work are not considered high impact globally.
Figures 1 and 2 highlight the two key metrics tracked during the programme: the total number of research publications and the number of peer reviews journal articles in journals with an impact factor of greater than 2.

Table 2: Publication Data
Centre	Baseline		2012-13		2013-14		2014-15		2015-16
	No of Research Pub’tns	No in Peer Reviewed journals	No of Research Pub’tns	No in Peer Reviewed journals	No of Research Pub’tns	No in Peer Reviewed journals	No of Research Pub’tns	No in Peer Reviewed journals	No of Research Pub’tns	No in Peer Reviewed journals
AVRDC	186	40	286	96 (8 in a journal with an impact factor >2)	242	81 (12 in a journal with an impact factor >2)	185	86 (23 in a journal with an impact factor >2)	276	102 (24 in a journal with an impact factor >2)
CABI	148	122 (26 in a journal with an impact factor >2)	100	93 (37 in a journal with an impact factor >2)	121	102 (18* in a journal with an impact factor >2)	105	88 (32 in a journal with an impact factor >2)	136	89 (25 in a journal with an impact factor >2)
ICIMOD	89	19	19	11 (5 in a journal with an impact factor >2)	65	38 (28 in journals using an impact factor >2)	185	95 (40 in a journal with an impact factor >2)	134	85 (38 in a journal with an impact factor >2)
icipe	86	80	123	96 (48 in a journal with an impact factor >2)	125	88 (40 in a journal with an impact factor >2)	205	136 (68 in a journal with an impact factor >2)	203	151 (74 in a journal with an impact factor >2)

Figure 1: Number of research publications produced yearly.	Figure 2: Number of peer-reviewed publications in high impact factor journals produced yearly

Figure 1 shows that, while there have been fluctuations in the total number of publications produced yearly, the overall trend is stable or increasing for all Centres. More importantly, with the exception of CABI, all Centres have seen an increase in the number of publications in high impact factor journals. This reflects the fact that CABI’s core business is the management of knowledge and information as opposed to conducting basic or applied research. Across the whole programme, the ratio of peer reviewed publications to total publications increased at the start of the programme, but then remained relatively stable across the four years at between 55 and 60%. However there was marked variation between Centres, with CABI and icipe showing a decline and AVRDC and ICIMOD seeing an increase.
In addition to tracking the number of peer-reviewed publications produced by the Centres each year, the annual performance assessment process included a formal review of research quality, conducted by DFID’s Senior Research Fellow. Each Centre was required to submit a selection of their five best publications produced during the reporting period. The Senior Research Fellow then assessed these publications against three key criteria:
- Quality of research – are the publications ‘original, significant and rigorous’ research?
- Relevance for agriculture and/or development
- Role of the organisation – what role did the organisation play in the design, conduct and delivery of the research?
AVRDC, CABI, ICIMOD and icipe all performed well against these criteria:
- AVRDC’s publications demonstrated that the Centre was conducting a range of types of research (lab analysis, qualitative interviews, plant breeding) with strong relevance to agriculture during the programme.
- CABI’s research output was also highly relevant to agriculture, with a strong focus on crop protection.
- ICIMOD’s research was of good quality, but primarily focused on climate and climate change. Direct links to agriculture, development and livelihoods were relatively limited.
- icipe’s publications evidenced the Centre’s involvement in a range of types of research relevant to agriculture, particularly insect pest management.

Indicator(s)	Milestones
High quality case studies made available for publication, demonstrating impacts at scale and responding to issues of climate adaptation, empowerment of women, food and nutrition security	By programme end, a total of 6 published case studies on R4D and other websites.

The purpose of setting this indicator was to incentivise the Centres to provide DFID with impact case studies on a regular basis. It provided a quantifiable measure which drove Centres to afford higher priority to the communication of evidence and impact assessments – a key priority for DFID and the broader development research community. In this way, this indicator complemented the other indicators under Output 1 – ensuring Centres were not only generating high quality research, but were also working to find effective ways to disseminate knowledge and findings.
Each centre produced a steady stream of case studies throughout the programme, meeting the target, which helped to raise the profile and publicise the work undertaken by the Centres with DFID support. The quality of the case studies was, however, variable, and not all were of sufficient quality to submit them for publication on the main DFID government website. The review team therefore concludes that progress against this indicator during the programme was not as strong as other areas of Output 1.
- AVRDC submitted a number of case studies during the programme, covering topics such as home gardens and gender in Bangladesh; a study on adoption rates of improved tomato varieties in Eastern and Southern Africa; and a study focusing on how training provided by the centre in off-season tomato production affected the income and pesticide use of smallholder vegetable farmers in Bangladesh;
- CABI developed a range of case studies during the programme – most of which have been published on the CABI website. These focused on topics ranging from the impact of CABI’s Global Health database on public health in Africa, to the centre’s experiences of working with partners to communicate key messages to farmers on soil fertility management.
- ICIMOD produced one case study per year of the programme, focusing on issues including weather insurance and resilience to droughts in China, India and Thailand, and entrepreneurship in farming value chains.
- icipe produced five case studies during the programme, focusing on topics including the protection of livestock from the tsetse fly in Kenya; icipe’s bio-prospecting programme which contributes to the conservation of the Kakamega Forest through the domestication of indigenous medicinal and insecticidal plants; and two studies on ‘push-pull’.

Indicator(s)	Milestones
Research outputs with specific focus on women’s empowerment and gender analysis generated and widely disseminated	Each year: / at least two outputs with a gender focus / at least one peer reviewed publication with a gender focus published

As noted in the 2016 Annual Review, the Centres’ performance against this indicator was somewhat variable during the programme. ICIMOD made good progress on integrating a stronger gender analysis into their research work throughout the programme; however, the other Centres’ progress was less consistent. Notwithstanding this, however, by programme end all Centres had made a positive step change in gender inclusivity in research outputs.

World Vegetable Centre (AVRDC)
- AVRDC made good progress on gender particularly during 2015 and 2016, establishing a widening range of activities and partnerships. Approximately ten ongoing projects have some degree of gender research included – for example, the ‘Creating women entrepreneurs through agricultural innovation’ component of an AVRDC project in Bangladesh is working to improve the economic and social status of women by creating economic opportunities through vegetable grafting in the production of seedlings. The centre also increased its number of publications focused on gender.
- The centre performed less well in ensuring gender inclusivity in its small vegetable gardening and grafting technology research areas. The small vegetable garden research and development project had a milestone target of training at least 3000 women in home gardening in 2015/16; however, the centre achieved only 65% of this target. In addition, the number of female participants at the training in grafting technology undertaken in Central Africa and Myanmar was very low.
- As outlined earlier in this Project Completion Review, a key recommendation for AVRDC following DFID’s final annual performance review of the programme was that the centre continued to make progress on including a strong gender focus in research outputs. The centre’s performance during the final year of this programme was promising, and DFID will continue to track this indicator closely during the new phase of funding to AVRDC, CABI and icipe.

CABI
- CABI strengthened its gender outreach and planning work under the Plantwise programme in 28 countries, conducting rigorous appraisals in Bangladesh, Ghana, Kenya and Pakistan. These involved a comprehensive review to identify access barriers and to develop strategies to increase women’s attendance at clinics where it is low.
- The centre produced a range of studies and research publications with a specific focus on the empowerment of women, including a study of food security and socio-economic conditions of women involved in kitchen gardening in Pakistan, a gender impact assessment study of CABI interventions, and a literature review of gender perspectives in the adoption of integrated soil fertility management practices. CABI also implemented gender-disaggregated data collection processes.
- Under the new phase of funding (2016-2020), DFID will closely monitor CABI’s continued progress on gender, including in particular an analysis of the differential uptake and impact of Plantwise recommendations by men and women.
International Centre for Integrated Mountain Development (ICIMOD)
ICIMOD performed well on gender integration throughout the programme, producing a range of publications with a strong focus on gender issues. These included a publication on women’s empowerment in climate change adaptation in Nepal; a working paper taking a gendered perspective on flood early warning systems; and a study on gender and integrated water resources management in education and research.

International Centre for Insect Physiology and Ecology (icipe)
- icipe produced a number of research outputs with a focus on gender during the programme, including a publication on integrated pest management technology awareness and gender participation in mango markets; a study on women in push-pull agriculture; and a publication on beekeeping for women’s empowerment in Kenya.
- icipe made good progress by the end of the programme on integrating gender analysis into the centre’s research and development activities. The centre’s strategy for push-pull technology dissemination was structured to provide equitable access with respect to gender. The centre also made a significant investment in boosting its capacity, recruiting a gender specialist and advertising for two further gender specialist posts.
- Under the new phase of funding, DFID will monitor icipe’s progress in further integrating gender analysis and gender-disaggregated data.

Recommendations for future programmes
In order to provide greater visibility of programme outcomes and facilitate monitoring of progress, future funding should have clearer, quantifiable outputs, particularly for reach and impact, and indicators for each centre. These will be reviewed on an annual basis as part of the Annual Review process to ensure they remain appropriate and incentivise the appropriate research. (by March 2017)

Output Title	Organisational behaviours which underpin effectiveness and value for money for DFID are strengthened
Output number per LF		2	Output Score	A
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Key Points
Indicator(s)	Milestones
Robust financial systems and sources	This indicator is measured by: / Indirect/Direct cost ratio (this ratio seeks to measure how much research programme activity a Centre is able to support on its institutional cost base) / Audit opinion (an external auditor’s opinion on the Centre’s financial statements indicating whether the Centre’s financial accounting and reporting processes meet required standards) / DFID costs as a % of total funds (the ratio of DFID costs to total costs gives us an indicator of how dependent a Centre is on DFID and how diversified its funding sources are. Figures can vary considerably year on year, and so 40% is set out as an indicative threshold and basis for discussion, rather than an absolute figure over which we should not go)

The following table sets out the Centres’ year-on-year performance against the measures set out above. As for publications, these figures are not directly comparable between Centres. There is no common approach to defining direct/indirect costs across Centres. Each Centre sets its own targets against which it is assessed.
Table 3: Centre Financial Management:
Centre	Indirect/Direct cost ratio				Unqualified Audit Opinion	Proportion of DFID funding
	Baseline	13/14	14/15	15/16		12/13	13/14	14/15	15/16
AVRDC	0.23	0.19	0.18	0.18	Yes	13.0%	13.5%	12.5%	14.2%
CABI	0.14	0.13	0.11	0.11	Yes	<25.0%	25.0%	19.0%	20.0%
ICIMOD	0.17	0.14	0.14	0.14	Yes	7.0%	9.0%	5.7%	5.1%
icipe	0.23	0.16	0.19	0.19	Yes	14.9%	29.5%	16.5%	18.0%

Figure 3: Centres’ progress in reducing indirect costs as a proportion of direct costs:

Indicator(s)	Milestones
A clear plan and strategy (environmental management system) in place	Progress on this indicator is tracked by looking at evidence of: / Specific targets for reducing the carbon footprint and wider environmental impact / Metrics on energy use, waste, travel and transport / Processes for regular reporting to the Senior Management team

Key progress highlights against this indicator are set out below by Centre. Funding to CFF and GFAR ended before the impact of introduction of an environmental management strategy was achieved.
World Vegetable Centre (AVRDC)
- AVRDC achieved a steady downward trend in its carbon footprint throughout the programme – reducing its footprint by 25% between 2010 and 2015. The Centre attributes this success to initiatives to enhance awareness, eliminate waste and introduce energy-efficient systems and equipment.
- Following an internal assessment of possible initiatives to switch to more renewable resources, the Centre decided to progressively abolish the use of peat moss as a growing medium for seedlings in the glasshouses. Peat moss is a non-renewable resource, and indiscriminate harvesting leads to the release of carbon into the atmosphere and destruction of wetlands. The Centre set a target of a 50% reduction in peat moss use by 2015, but in fact achieved a total discontinuation of the use of the resource by late 2015.

CABI
- To make progress against this indicator, CABI established targets in three key areas: direct emissions (from gas, fuel oil and owned transport); indirect emissions (from energy use and electricity); and a third category for other indirect emissions (for example, water, waste and commuter/business travel).
- Overall, the Centre made good progress during the funding period in all these areas, achieving a 6% reduction in electricity use and a 5% reduction in indirect emissions due to increased recycling and a reduction in business travel. Slight fluctuations were experienced in some areas in particular years (for example, 2015 saw a small increase in direct emissions as compared to the previous year, attributed to colder weather requiring more energy use for heating).
- Paper consumption in the UK offices decreased by 25% during the programme, following the introduction of SharePoint for document management and team-working.

International Centre for Integrated Mountain Development (ICIMOD)
- ICIMOD established an Environmental Management Policy, the primary objective of which is to reduce resource consumption per unit staff member, and minimise the waste generated from operations.
- With the aim of reducing its institutional carbon footprint and promoting renewable energy, the Centre installed an interactive solar photovoltaic (PV) system at the ICIMOD complex. This hybrid system sources electrical energy in the following priority order: 1) the solar PV system; 2) the national grid; and 3) generator backup. Any surplus energy generated from the system is returned to the national grid. With this system, ICIMOD is approaching energy independence for its basic operations at the headquarter building in Kathmandu.
- ICIMOD organised an ‘Environment Footprint Reduction Innovation Competition’ to encourage staff to think about ways to reduce their footprint by changing their behaviours and adopting innovative practices. This has led to the organisation of an ‘ECO club’ which develops and promotes environmentally-friendly practices across the Centre’s office complexes.

International Centre for Insect Physiology and Ecology (icipe)
icipe developed an Environmental Management Strategy and made good progress against the milestones for this indicator during the programme:
- An Environmental Management Committee was established to coordinate the Centre’s activities relevant to this indicator, setting targets and monitoring progress made against them
- The Centre implemented a range of water-saving measures, including the installation of water tanks, the recirculation of water used in cooling plants, and the installation of water efficient plumbing
- The Centre made considerable efforts to reduce carbon emissions, installing solar and thermal electricity generation projects on two of the Centre’s major campuses
- New energy and water efficient fixtures were installed across the Centre’s campuses
- The Centre established a staff awareness programme on the need and opportunities to increase recycling efforts and reduce waste, and introduced new policies on travel and transport
- The Centre has a long-running programme of tree and vegetation planting on campuses and field stations to offset carbon emissions

Indicator(s)
HR policy and operational plans for ensuring gender balance in organisational structures and research processes implemented

Key progress highlights against this indicator are set out below by Centre.
World Vegetable Centre (AVRDC)
- The Centre maintained a roughly 50/50 split between male and female employees throughout the funding period.
- AVRDC developed and introduced a set of guidelines for ‘diversity positive recruitment’, which specifically addresses gender issues. Areas covered by the guidance include interview planning, gender-balanced selection panels, and decision-making.
- AVRDC staff members are briefed on issues relating to balanced gender participation in organisational activities, and how they can promote gender in their groups and teams. The centre periodically collects data on gender composition at centre, region and research project level, and seeks ways to maintain and increase the balance.

CABI
- CABI refreshed its CABI Workplace Gender Strategy in June 2014, setting out the Centre’s approach to improve gender equity in policies and practice across the organisation. The strategy includes a set of gender balance indicators, in areas including gender pay equity, flexible working practices, recruitment and promotion policies, and communication mechanisms.
- By programme end, 29% of applicants to CABI positions were female, yet women accounted for 50% of interviewees and 51% of appointees.

ICIMOD
- ICIMOD completed two gender audits during the programme – one in 2012 and a second in 2016. These audits were tasked with reviewing the extent to which ICIMOD’s technical capacity, management, political will and organisational culture were conducive to gender inclusivity. Following each audit, ICIMOD management developed and implemented an action plan to address areas identified for improvement.
- At the beginning of this programme, women accounted for 30% of ICIMOD staff. By programme end, this had increased to 37%.

icipe
- icipe established a ‘talent pipeline’ to support the development of early career scientists, giving priority to early- and mid-career female scientists. Through this initiative, the Centre actively seeks opportunities to promote and grow the careers of scientists in the talent pipeline, including opportunities for external international recognition.
- The Centre identified the low number of female applicants for postgraduate and postdoctoral programmes (approximately 29% of applicants to icipe programmes are women) as an issue, and actively sought to increase the number of female applicants by extending the reach of programme announcements and creating stronger partnerships with capacity building organisations that focus on women scientists (for example, AWARD, OWSD and UNESCO).

Recommendations for future programmes
Continue to support Centres to integrate gender across their institutions (on-going)

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)
Key cost drivers and performance
DFID provided multi-year core contributions to the Centres, with an additional discretionary annual performance-based payment based upon their achievements against key deliverables and progress against institutional development targets.
Including a discretionary performance-based payment element in the funding system increased transaction costs for DFID, both technically and administratively, because it involved a systematic assessment of each Centres’ performance and value for money on an annual basis. This systematic assessment was undertaken in addition to regular programme reporting and the standard DFID Annual Review process. The additional value gained from this process, however, enhanced the value for money of this programme in a way which more than offset the internal transaction costs required to implement it. The performance management system provided a robust framework for close engagement between DFID and the Centres, and for ensuring that key organisational and behavioural changes were tracked throughout the programme as well as programmatic deliverables.

VfM performance compared to the original VfM proposition in the business case
The original Business Case (2011) outlined two key ways in which the project would deliver value for money:
1. By ensuring the Centres focused on results and on measuring impact
2. By improving the efficiency of DFID’s management of international agricultural research Centres
The programme’s performance against each of these two key areas is outlined in the table below:
Original VFM proposition #1: Ensuring the Centres focused on results and on measuring impact	Four of the Centres originally funded under this programme (World Vegetable Centre (AVRDC), CABI, ICIMOD and icipe) all made good progress in measuring and demonstrating impact and results, and responded well overall to recommendations made by DFID each year following the DFID Annual Review and additional performance review process. Key successes and achievements in impact evaluation are outlined elsewhere in this Project Completion Review, particularly in the discussion of Output 1. GFAR – as outlined earlier – did not demonstrate sufficient progress in developing its approach to impact evaluation and results focus, and DFID therefore ceased funding to this Centre in 2014. / The review team concludes that the programme performed well against the first value for money proposition included in the business case, meeting expectations.
Original VFM proposition #2: Improving the efficiency of DFID’s management of international research Centres	The performance management approach adopted under this programme provided a clear framework for closer engagement between DFID and each of the Centres. The annual performance review process, after which DFID decided on each of the Centre’s eligibility for that year’s performance-based payment, provided a mechanism for DFID to take a more directive approach with the Centres in relation to key organisational behaviours. DFID utilised the performance-based payment mechanism to incentivise and drive progress by each of the Centres in important areas such as financial management, environmental management, and inclusive HR policy. / While DFID recognises that the performance management system requires further refinement (and has endeavoured to incorporate lessons learned from experience and from the external evaluation in DFID’s new phase of funding to three of the international research Centres), the review team concludes that the programme performed well overall against the second value for money proposition included in the business case. Key achievements made by each of the Centres in organisational behaviour areas are outlined elsewhere in this Project Completion Review.

In late 2016, DFID’s Research and Evidence Division (RED) articulated a ‘quality and value at each step’ approach to value for money in research. This framework recognises that assessing Value for Money for agriculture research investments is challenging, as the outcomes and impacts (key value factors) cannot easily be determined. While the evidence of positive rates of return from investment in agriculture research is clear, this is not sufficient for ensuring value for money at programme level.
The framework sets out a number of key principles for ensuring value for money. These are outlined below, along with a brief description of how this project performed in each area:
Picking the right problems – the Centres funded under this project were all selected following a rigorous appraisal process during Business Case development. A key criterion for selection was evidence of the Centres’ development impact:
- AVRDC was selected for its capacity to deliver new technologies, particularly disease resistant vegetables, which have a direct impact on agricultural productivity and nutrition
- CABI was selected for its strong track record in delivering tangible development outcomes in the area of plant health, and high quality scientific publications.
- CFF was selected for its niche role in providing reliable and useful information about Neglected and Underutilised Species (NUS). NUS are potentially very valuable for improving food and nutritional security and livelihoods of the poor in a context of climate change and increased dependence on a limited number of staple crops. [As outlined elsewhere in this Project Completion Review, DFID ceased funding to CFF in 2014, primarily because CFF could not demonstrate that they had sufficiently strengthened their approach to gender analysis, environmental mainstreaming, and continuous improvement of research quality.]
- GFAR was selected for its potential to provide a mechanism for priority setting in the field of international agriculture research, and to strengthen and bring coherence to systems generating and sharing new agriculture research globally. [As outlined elsewhere in this Project Completion Review, DFID ceased funding to GFAR at the end of financial year 2013/14, as DFID’s performance assessment process concluded that GFAR was not sufficiently results-based and impact-focused.]
- ICIMOD was added to the programme after a robust value for money assessment to support their work in mountain regions.
- icipe was selected for its unique position as the only international research Centre working primarily on insect-related challenges of food security in Sub-Saharan Africa, vector-borne diseases of people and livestock, and protection of the environment.
1. Working through strong partnerships – DFID utilised the performance management framework to establish a productive partnership with each of the Centres, using this leverage to influence broader institutional development and change as well as strong delivery of programme deliverables.
2. Always requiring good quality – the quality of research produced by each of the Centres was closely scrutinised throughout the programme, as detailed elsewhere in this Project Completion Review, particularly in the discussion of Output 1.
3. Programme Management – the performance management framework provided a structure for robust DFID management of this programme. Additionally, the Centres themselves maintained strong programme management capacity throughout the programme, in some cases building further capacity in key areas such as gender and impact assessment, in line with DFID priorities.

Assessment of whether the programme represented value for money
In addition to using the four key value for money principles, the RED VFM framework recommends use of the ‘4 E’ framework for analysis of value for money. The programme delivered value for money in several key ways:
- Economy and efficiency: All Centres made good progress in key organisational behaviour areas, outlined earlier in this Project Completion Review, which relate to the efficiency of institutions’ internal processes and controls. Key successes included the strengthening of impact evaluation capacity across the Centres and a sustained focus on internal cost and financial management;
- Effectiveness: All Centres produced high quality research during the DFID funding period, meeting and in several cases exceeding targets agreed between DFID and each Centre for their specific focus areas. The performance of all Centres was tracked and assessed not only through regular reporting and the DFID Annual Review process, but also through the additional performance management system with discretionary performance-related payment. The external evaluation of the performance management system concluded that this additional review structure provided the research Centres with a clear focus on agreed outputs and outcomes, and was effective in facilitating the delivery of high quality research, the agreed results, and value for money.
- Equity: All Centres increased their focus on gender inclusivity in both research outputs and HR policies. Key successes in promoting gender inclusivity in both areas are outlined elsewhere in this Project Completion Review (see Output 2 and the coverage of safeguarding risk in Section E).

Quality of financial management during programme
The Centres’ financial management and stability was monitored throughout the programme:
All payments outlined in the Memoranda of Understanding between DFID and the research Centres were made as planned, with the exception of one delayed payment to one Centre during the final year of the programme. At the time, potential internal control weaknesses had been identified at that Centre, and DFID delayed payment pending the outcome of an external audit of the robustness of the organisation’s controls. The auditors concluded that there were no major control weaknesses, and identified only minor areas for improvement in some areas. The Centre’s management drew up a timebound and measurable action plan, which was accepted by DFID and other core donors. DFID released the outstanding payment and continued to monitor the Centre’s progress against the action plan. No further concerns or issues arose.
All Centres provided annual audited statements in time for the annual performance reviews undertaken throughout the programme. Payments from DFID were duly recorded and all audited statements were given an unqualified audit opinion by an internationally recognised accountancy firm. The annual performance reviews took place during June/early July each year, and Centres were notified by the end of July of DFID’s decision whether or not to award the discretionary performance-based payment. Performance payments were issued in August of each project year. Table 4 shows total expenditure for the programme. Table 5 summarises performance-based payments by programme year.
Table 4: Summary of Disbursements to Centres (Pounds Sterling)

Table 5: Summary of performance-based payments by programme year
	Performance Review Year – successful in receiving payment (yes/no)
Centre	2011	2012	2013	2014	2015
AVRDC	No	No	No	Yes	No
CABI	Yes	Yes	Yes	Yes	Yes
icipe	Yes	Yes	No	No	No
GFAR	No	No	Funding stopped	Funding stopped	Funding stopped
ICIMOD	Not yet funded	No	No	Yes	Yes
CFF	Not reviewed		Funding stopped

Date of last narrative financial report	AVRDC	31 December 2015
	CABI	31 December 2015
	CFF	2 September 2013
	GFAR	1 December 2012
	ICIMOD	31 December 2015
	icipe	31 December 2015
Date of last audited annual statement	AVRDC	31 December 2015
	CABI	31 December 2015
	CFF	31 December 2012
	GFAR	1 December 2012
	ICIMOD	31 December 2015
	icipe	31 December 2015

## E: RISK (½ page)
Quality of risk management over the life of the programme
DFID revised its risk categorisation model in mid-2016. The review team has assessed the quality of risk management during the programme against the new categories, below.
Risk category	Key risk areas for the programme	Summary of risk management during the programme
External context	The key external context risk for the programme was that public opinion in target countries might oppose specific technologies and products delivered by the Centres.	This risk was not realised during the programme and in general public opinion and the legal environment with respect to agricultural technologies has been positive during the funding period.
Delivery	One possible delivery risk for the programme was that multi-year funding to the Centres might have encouraged complacency or faltering performance, due to the relative certainty of DFID funding over the programme period.	In addition to the standard DFID Annual Review process, DFID measured the Centres’ performance annually against agreed objectives to determine their eligibility to receive an additional performance-related payment. These payments were only made if DFID was satisfied that the Centres had demonstrated excellent performance in specific focus areas over the reporting period. Based on DFID’s experience of managing the performance management system, along with the conclusions from the external evaluation, the review team concludes that the system successfully mitigated any risk of the Centres becoming complacent in their performance over the project – and indeed drove greatly improved performance in key areas.
	Another key delivery risk was that research outputs delivered by the Centres might fail to have relevance to the needs of poor farmers or end users, or that research quality may have been poor.	DFID monitored the development impact and relevance of all Centres’ research outputs throughout the programme, and formally on an annual basis through both the DFID Annual Review and the additional performance management process. In addition, as international research organisations, the Centres were also subject to regular external review processes which examine issues of quality and relevance in some detail. All Centres maintained their strong track record in generating high quality research outputs during the programme, and – responding to direction from DFID – began to deepen their engagement with other partners in order to focus more on the dissemination and uptake of research products.
Safeguarding	A primary safeguarding risk for the programme related to gender inclusivity – in particular that research products or initiatives developed by the Centres might fail to address or even exacerbate gender inequality.	DFID monitored the Centres’ performance against specific gender inclusivity targets for research outputs. In addition, DFID utilised the performance management system to incentivise greater gender awareness and inclusivity within the Centres themselves. The programme was very successful in ensuring and safeguarding gender inclusivity. Key successes included: / CABI strengthened gender outreach and planning on the Plantwise programme, in 28 countries. The Centre undertook rigorous appraisals in Bangladesh, Ghana, Kenya and Pakistan, including a comprehensive review to identify access barriers and to develop strategies to increase women’s attendance at clinics where it is low. Internally, CABI increased its proportion of female staff since 2014, and has no gender pay gap issues. / The World Vegetable Centre (AVRDC) increased the number of its research publications focusing on gender issues during the programme. The Centre developed a gender strategy, allocated additional funds for strengthening gender capacity in AVRDC, and provided staff training on gender inclusivity in 2013 and again in 2015. In both East Africa and Bangladesh, the Centre utilised a gender consultant to secure advice on gender integration in research. / ICIMOD incorporated gender analysis into a range of studies and new concept notes – for example, a concept note for climate-smart villages, developed towards the end of the programme funding period, gave special attention to differential impacts on gender. ICIMOD also undertook a ‘gender audit’ of its internal processes and structures and prepared a work plan, and increased its proportion of female staff by 7% during the programme. / icipe made good progress on integrating gender analysis in its research and development activities, for example, the Centre undertook two major gender studies of its key technologies, and structured the technology dissemination strategy for the ‘push-pull’ workstream specifically to provide equitable access with respect to gender. Internally, icipe appointed a number of gender specialists, provided gender training for icipe staff, and established a ‘talent pipeline’ to support the development of early career scientists, giving priority to female scientists.
Operational	A key operational risk for this programme was that the performance-related payment might fail to drive institutional development from the research Centres.	The performance funding mechanism drove notable improvements in research Centre performance by incentivising greater focus on areas including gender and impact assessment. The external evaluation of the performance-related funding mechanism concluded that it had been effective in driving high quality performance from the Centres.
Fiduciary	A key fiduciary risk was that the Centres might experience fraud or financial mismanagement.	DFID assessed the effectiveness of the Centres’ internal controls at the outset of the funding period, and continued to monitor this during the programme. As noted elsewhere in the Project Completion Review, DFID delayed payment to one Centre during the final year of the programme. At the time, potential internal control weaknesses had been identified at that Centre, and DFID delayed payment pending the outcome of an external audit of the robustness of the organisation’s controls. The auditors concluded that there were no major control weaknesses, and identified only minor areas for improvement in some areas. The Centre’s management drew up a timebound and measurable action plan, which was accepted by DFID and other core donors. DFID released the outstanding payment and continued to monitor the Centre’s progress against the action plan. No further concerns or issues arose – with this Centre or any of the other Centres funded under the programme.
Reputational	All of the risk areas outlined above carried an element of reputational risk – specifically, that any of the above risks might be realised without appropriate measures in place to mitigate the impact.	The review team concludes that risk management of the programme was robust and effective throughout the funding period – protecting DFID from reputational risk associated with risk mismanagement, and driving high quality performance, research quality and institutional development from each of the Centres funded.

## F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe
The programme met its objectives and delivered outputs against the planned timeframes.
Further details on the programme’s performance from a value for money and commercial perspective are set out in Section D.
Performance of partnership(s)
DFID established and maintained a successful partnership with the research Centres throughout the programme. The performance management system provided a clear framework for discussions between DFID and the Centres, and fostered a shared understanding of aims and objectives.
Asset disposal and value obtained by DFID
All Centres submitted an up to date asset register at programme end, showing the location, purchase price and purchase date of assets purchased or part-purchased using DFID funds.
DFID provided core funding to the Centres during this programme, thereby delegating authority for asset management to the Centres. DFID has therefore not sought to oversee the disposal process for obsolete assets.

G: CONDITIONALITY (½ page)
Partnership principles assessment
N/A – the partnership principles were not relevant to this programme, as this was a global research programme which did not involve the delivery of funding through government systems.

H: MONITORING & EVALUATION (½ page)
Evidence and evaluation
External evaluation of the performance management system
In 2014, using the Global Evaluation Framework Agreement, DFID commissioned an evaluation of the multi-year performance management arrangements introduced under this programme. This Performance Management Framework Mechanism (PMFM) was a key component of the funding which was allocated based on performance against three to five high-level deliverables for each Centre, based on reports from the Centres, their review by DFID and a formal review meeting between each Centre and a DFID team. The PMFM was intended to improve performance of the individual Centres in specified areas, and lead to results more closely aligned to DFID priorities.
The final report of the evaluation was received in January 2016. The evaluation had two main objectives:
1. To assess the effectiveness of DFID’s performance management funding mechanism in delivering high quality research, delivery of results and value for money.
2. To make recommendations to DFID’s Research and Evidence Division on performance management funding of research, including metrics.
The evaluation’s main findings were that the PMFM processes that have been established by DFID, including setting the key deliverables at the outset of the funding and the annual performance review, provided the Centres with a clear focus on the agreed outputs and outcomes. It has also been effective in facilitating the delivery of high quality research, the agreed results, and value for money.
The results-based funding strengthened the Centres’ activities in several key areas. For example, some Centres are now building in appropriate impact assessment measures into the design of new research projects. Meanwhile, the attention paid to gender and women’s empowerment indicators by PMFM has had some success, supporting the efforts of the Centres to produce more gender-focused publications while helping to ensure that organisational structures and process were more gender-sensitive.
However, the evaluation also identified several areas for improvement. While the Centres were overwhelmingly positive about the multi-annual core funding, the evaluation did not find sufficient evidence to suggest that the performance-based payment element was effective. Only two of the four Centres received performance-based payments throughout Phase 1, awarded for strengthening institutional capacity and promoting new research lines. The other recipient organisations were unclear about the criteria for awarding a performance-based payment, and if and how some agreed-upon goals were weighted differently to other goals in DFID’s considerations for awarding performance-based payments.
Issues over clarity and communication were identified as the primary cause behind several other shortcomings. For example, Centres did not embrace robust impact assessment to the level that DFID had hoped for. Clearer communication between DFID and the Centres on what this would entail and understanding the limitations of impact measurement in relation to existing research projects would have helped manage expectations and establish realistic targets. More clarity on how to measure VfM and a closer collaboration on a more explicit theory of change, at an earlier stage, would also have helped make the PMFM more effective. Better communication and clarity over expectations would have helped the Centres develop a clearer idea of what they were aiming to achieve.

Impact evaluation by the Centres
The quality and extent of the Centres’ impact assessment and evaluation work was a key focus area for DFID throughout this programme. DFID measured the Centres on the development of their impact assessment capacity. Key successes achieved by the four Centres funded throughout the full programme cycle are outlined below.
World Vegetable Centre (AVRDC)
AVRDC made significant progress in strengthening their capacity in impact evaluation during the programme. New appointments led to a large increase in impact work, including work on cost-effectiveness, the use of trial registries, partnerships with IFPRI and others, and a significant increase in the number of impact-related research publications.
CABI
CABI made good progress on impact evaluation during the programme. A wide range of assessments, using a variety of methods, were undertaken, including a major evaluation of Plantwise in Kenya, retrospective analysis of impact of improved coffee processing, impact of mobile agri-advisory services, and several other studies of Plantwise (phone surveys, satisfaction surveys, household surveys).
ICIMOD
There was a demonstrable improvement in ICIMOD’s impact assessment and monitoring work relevant to agriculture and development during the project. A key impact study is a major randomised control trial (RCT) of the Nepal agriculture extension programme, in partnership with J-PAL.
icipe
icipe made a significant investment in boosting its capacity in impact assessment through the recruitment of a new Head of Social Science and the Impact Assessment Unit, with international experience and a strong focus on adoption and impact evaluation. In addition, the Centre appointed a number of monitoring and evaluation staff within projects and recruited a gender specialist.

Monitoring progress throughout the programme
Progress was monitored formally using two key processes – the standard DFID Annual Review and the additional performance management system to establish Centres’ eligibility for performance-related payments each year.

Project Completion Review process
This project completion review drew upon the previous annual reviews and performance reviews.
The project completion review process was led by an internal DFID team comprising the DFID Senior Responsible Owner and Deputy Programme Manager, supplemented by inputs from all stages of the programme lifespan from other Livelihoods Advisers, DFID’s Senior Research Fellows, and Social Development Advisers.

Key documentation reviewed (list not exhaustive)
- Business Case – 3323090
- Log frame - 3719418
- AVRDC 2011 Annual Report – 3616290
- AVRDC 2011-12 Performance Review Report – 3616313
- CABI’s 2011 Annual Report – 3614199
- GFAR’s 2011-12 Annual Report – 3615720
- icipe’s 2011 Annual Report – 3615013
- DFID’s 2011 performance review letter of AVRDC – 3616377
- DFID’s 2011 performance review letter of CABI – 3614451
- DFID’s 2011 performance review letter of GFAR – 3616013
- DFID’s 2011 performance review letter of icipe – 3615079
- AVRDC 2012-13 Annual Report – 4031057
- CABI’s 2012 Annual Report – 4031094
- GFAR’s 2012-13 Annual Report – 4031218
- ICIMOD’s 2012-13 Annual Report – 4143382
- icipe’s 2012-13 Annual Report – 4031201
- DFID’s 2012 performance review letter of AVRDC – 4168537
- DFID’s 2012 performance review letter of CABI – 4168557
- DFID’s 2012 performance review letter of GFAR – 4168565
- DFID’s 2012 performance review letter of ICIMOD – 4168570
- DFID’s 2012 performance review letter of icipe – 4168552
- DFID assessment of CFF performance – 3616694
- DFID Annual Review #1 – 3823758
- AVRDC’s 2013-14 Annual Report – 4554926
- CABI’s 2013-14 Annual Report – 4555447
- ICIMOD’s 2013-14 Annual Report – 4555456
- icipe’s 2013-14 Annual Report – 4555048
- DFID’s 2013 performance review letter of AVRDC – 4680616
- DFID’s 2013 performance review letter of CABI – 4680612
- DFID’s 2013 performance review letter of ICIMOD – 4680614
- DFID’s 2013 performance review letter of icipe – 4680618
- DFID Annual Review #2 – 4140266
- AVRDC 2014-15 Annual Report – 5067741
- CABI 2014-15 Annual Report – 5068322
- ICIMOD’s 2014-15 Annual Report – 5068414
- icipe’s 2014-15 Annual Report – 5068334
- DFID’s 2014 performance review letter of AVRDC – 5190725
- DFID’s 2014 performance review letter of CABI – 5190714
- DFID’s 2014 performance review letter of ICIMOD – 5190727
- DFID’s 2014 performance review letter of icipe – 5190732
- DFID Annual Review #3 – 4923268
- DFID notification letter to GFAR on cessation of funding – 4381119
- AVRDC’s 2015-16 Annual Report – 5441880
- CABI’s 2015-16 Annual Report – 5444582
- ICIMOD’s 2015-16 Annual Report – 5449301
- icipe’s 2015-16 Annual Report – 5441927
- DFID’s 2015 performance review letter of AVRDC – 5541643
- DFID’s 2015 performance review letter of CABI – 5541639
- DFID’s 2015 performance review letter of ICIMOD – 5541648
- DFID’s 2015 performance review letter of icipe – 5541651
- DFID Annual Review #4 – 5321113
- External Evaluation Report of DFID’s Performance Management Funding – 5332933

Annual Review 2015 - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to International Agricultural Research Centres that benefits Poor People
Programme Value: £50,293,715		Review Date: 12/03/2016
Programme Code: 202748	Start Date: 01/04/2012	End Date: 31/03/2016

Summary of Programme Performance
Year	2015	2014	2013	2012
Programme Score	A	A	A	A+
Risk Rating	Low	Low	Low	Low

Summary of progress and lessons learnt since last review

Overall progress is on track, and the programme scores an A. The four international agricultural research Centres which receive funding under this programme currently are largely meeting expectations against the main indicators relating to research delivery and scaling of technologies. Three of the four funded Centres, received a performance related payment linked to organisational delivery, due to having fully met or exceeded the milestones for the key deliverables with an excellent performance against organisational and quality of research. The other Centre (icipe) was largely on track against agreed deliverables and milestones, but progress on specific areas particularly impact evaluation had been slow. Performance against organisational behaviours (i.e. financial management, environmental management systems, gender sensitive HR systems and policies) was good.

During the year a new approach to assessing quality was piloted, stimulated by Centre’s concerns that the former system, using the use of publications metrics in combination with the assessment of other research outputs, was insufficient. This was a useful exercise and has been incorporated into the 2016 performance review process.

DFID commissioned an external evaluation of the programme which is now completed. The evaluation is of wider interest within DFID Research and Evidence, and amongst other donors agricultural research. Lessons will be shared across DFID via the Evaluation Department Learning Seminars.

Summary of recommendations for the next year
Recommendations #1 and #2 are rolled over from last year’s Annual Review, as they continue to be relevant.

Where research Centres have a strong presence and are scaling up technologies in specific countries, they should approach the Agriculture Research team to discuss how this overlaps with bilateral programme priorities, and where appropriate facilitate an introduction to Country Offices (Research Centres, ongoing).

Research Centres are encouraged to initiate a discussion with the DFID Agriculture Research team on the partnership or aspects of their performance as required (Research Centres, on-going).

DFID should share the evaluation findings and proposals for a new phase of funding with other core donors, with a view to discussing the proposed mechanism and exploring options for closer coordination and collaboration (by mid 2016).

Centres should from 2016 onwards include only publications which are undertaken by their own researchers and own funds, and where publications recognise the affiliation of the author with the research institution.
Annual Review 2014 - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Support to International Agricultural Research Centres that benefits Poor People
Programme Value: £40,093,715		Review Date: 12/03/2015
Programme Code: 202748	Start Date: 01/04/2012	End Date: 31/03/2015

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	A+	A	A
Risk Rating	Low	Low	Low

Summary of progress and lessons learnt since last review

Overall progress is on track, and the programme scores an A. The four international agricultural research Centres which receive funding under this programme currently are largely meeting expectations against the main indicators relating to research delivery and scaling of technologies. One of the 4 funded Centres (CABI), received a performance related payment linked to organisational delivery, due to having fully met or exceeded the milestones for the key deliverables with an excellent performance against organisational and quality of research. The three other Centres were largely on track against agreed deliverables and milestones. The main recommendations to Centres following the mid 2014 review related to impact evaluation, gender analysis and mainstreaming and strategies and partnerships for uptake of technologies. Performance against organisational behaviours (i.e. financial management, environmental management systems, gender sensitive HR systems and policies) was good.

This review is a light touch one, since DFID has commissioned an external evaluation of the programme which is currently underway. This evaluation is expected to feed into future decisions in DFID agriculture research programme on use of performance management systems.

Summary of recommendations for the next year

Where research Centres have a strong presence and are scaling up technologies in specific countries, they should approach the Agriculture Research team to discuss how this overlaps with bilateral programme priorities, and where appropriate facilitate an introduction to Country Offices (DFID to follow up via communication to research Centres in March 2015).

Lessons will be drawn during the next Annual Review (due February 2016) on the effectiveness of this new mechanism to assess quality of research by the DFID Review team, drawing on feedback from Centres.

DFID Agriculture Research team should formally draw attention of the partners to their availability for follow up discussions on partnership or aspects of performance (recommendation #3) (March 2015).

Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMPas part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised throught the duration of the programme which were not forseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process