Annual Review - Summary Sheet
This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Safe and Inclusive Cities (SAIC)
Programme Value: £6.6m ; DFID Contribution £4.5m		Review Date: August 2016 (reporting until June 2016)
Programme Code: 203205-102	Start Date: Jun 2012	End Date: July 2017

Summary of Programme Performance

Year	2013	2014	2015	2016
Programme Score	A	A	A+	A+
Risk Rating	High	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review
Safe and Inclusive Cities (SAIC) completed all 15 research projects this year. It met expectations (logframe outputs achieved or exceeded) and addressed some of the recommendations from last year and the Midterm Evaluation Report.
With 125 publications on urban violence in 16 countries (including DRC, Ghana, India, Sri Lanka, South Africa, Mozambique, Pakistan, Zimbabwe), SAIC exceeded this year’s milestone. Among the key highlights of the research is the identification of drivers of urban violence that need to be addressed in programming. They include social exclusion, vigilantism, displacement and resettlements, corruption, gender inequality, economic hardship, child maltreatment, and alcohol abuse. SAIC research findings suggest that levels of violence can be reduced with public employment programmes, urban upgrading, provision of basic services, interventions to change gender norms, livelihood opportunities for youth, and school reform.
Policy and outreach activities have reached over 2,000 beneficiaries including high ranking policy actors (country presidents or vice presidents, mayors, heads of international organisations) and SAIC research was reported in leading media outlets (e.g. The Economist, BBC Mundo, Al Jazeera). SAIC also implemented four regional policy conferences in New Delhi, Santiago, Johannesburg and Dakar.
Research uptake highlights this year included:
- Chile’s Ministry of Crime Prevention integrating verbatim questions from SAIC research on social cohesion into the National Victimization Survey
- Côte d’Ivoire research on youth directly influencing policy through integration of findings into programmes by UNESCO and USAID, with the Principal Investigator honoured by the President
Programme-level synthesis and the development of policy recommendations are ongoing and not all projects have produced policy briefs or synthesis documents yet. The ultimate programme-wide research quality, policy relevance and impact can only be assessed in the next 9 months.  It is critical that the final year is used to strengthen the research synthesis across programmes and promote policy engagement to significantly influence development policy. This is important given DFID’s ambition of maximising the impact of social research on the most challenging development problems.
SAIC has developed an improved web platform with dedicated pages for the 15 research projects[1]. Most outputs are available online on publishers’ websites[2], but some are not yet on SAIC’s project sites. SAIC will make all project-level outputs, findings, policy recommendations, impact stories and visual and media content (pictures, infographics, project documentaries, interviews) available online in the final year.
[1] SAIC project sites: https://www.idrc.ca/en/initiative/safe-and-inclusive-cities
[2] See list of publications with links in Appendix 1

Summary of recommendations for the next year
- Agree on a communications plan to develop project-level synthesis reports on main findings, policy recommendations and dissemination of findings (DFID and SAIC by January 2017)
- Publish all project-level outputs, findings, policy recommendations, impact stories as well as visual and media content (pictures, infographics, project documentaries, interviews) on dedicated SAIC project pages on the website (SAIC by July 2017)
- Take a sample/selection of research products and use the DFID network to review their quality, policy relevance and impact – and use these assessments to inform the Project Completion Report (DFID by July 2017)
- Update the final targets for key indicators in the logframe that significantly exceeded expectations (DFID and SAIC by December 2016)

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Quest 3809359
DevTracker Link to Log frame:	Quest 5135457

People are moving into cities at an astonishing speed – 54% of the world’s population now live in cities, up from 24% in 1960. Some cities have become centres of multi-layered violence. Criminal and organized violence, sometimes associated with the drug trade, has become entwined with national politics. Gangs and militias may substitute for public authority, offering some protection to communities, but often at great cost. Social violence, including violence within the household, is also a significant problem, particularly for vulnerable youth and women. Rapid urbanisation brings these problems to the fore, especially in developing countries.
Safe and Inclusive Cities (SAIC) is a 5-year research programme (2012-2017) aimed at building the evidence base on the drivers of urban violence. It is funded in partnership with Canada’s International Development Research Centre (IDRC) and implemented by IDRC. DFID provides up to £4.5m and IDRC contributes £2.1m. The programme is now in its final year.
SAIC works with experts from around the world to identify what drives urban violence as well as what works – and what doesn’t – to reduce violence. Following a competitive call for proposals - which significantly surpassed expectations of both quality and quantity, and as a result of which the programme was doubled in size – 15 research teams were selected to undertake research in 40 cities across 16 countries[3] in sub-Saharan Africa, South Asia, and Latin America and the Caribbean.
[3] SAIC includes Brazil, Chile, Colombia, Costa Rica, Cote d’Ivoire, DRC, El Salvador, Ghana, India, Mozambique, Pakistan, Peru, South Africa, Sri Lanka, Venezuela, and Zimbabwe.
Projects address gaps in knowledge and test the effectiveness of violence reduction theories, strategies and interventions. These include promoting social cohesion and capital, fighting gender-based violence, encouraging urban renewal and regeneration, and enhancing protection of vulnerable groups. SAIC also builds knowledge gained from a range of interventions to address urban violence, such as pacification and community policing, community interventions, and slum upgrading. SAIC projects also produce new data sets on violence and violence prevention.
All SAIC research projects have been completed although the publication of project outputs is ongoing. The proramme’s focus in the final year is on producing synthesis reports on the project findings and dissemination. The programme is scheduled to finish in July 2017 and has a number of project closure events which include a conference in Nairobi targeted at a wide range of stakeholers, including DFID country offices, and events at the United Nations’ Habitat III conference in Quito, Ecuador.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
SAIC made good progress in informing policies or programmes aimed at reducing violence with research findings (outcome 1). Projects in Chile, Côte d’Ivoire, and South Africa reported direct engagement with senior officials and uptake in policy making (see section ‘Summary of progress and lessons learned’). SAIC has contributed to events organised by international policy actors such as World Bank, OECD, and UN-HABITAT. IDRC identified SAIC contributions to policy documents written by the Institute of Development Studies, USAID and the World Health Organization.
SAIC increased efforts to inform policy actors and researchers with SAIC research (outcome 2). Research was presented at a cumulative total of 130 events, attended by leading policy makers (e.g. mayors and deputy mayors), international organisations (e.g. World Bank, OECD, and UN HABITAT), and donors (e.g. GIZ).
This year SAIC research was cited 86 times. 95% of citations came from projects in Southern Africa and Latin America, which have produced ~75% of peer-reviewed publications. SAIC has recorded 96+ mentions of SAIC research in newspapers, magazines, radio and TV outlets. For example, popular newspapers in India reported on SAIC research findings on the causes and consequences of violence (e.g. The Hindu, Gujarat Samachar, Assam Tribune).
Overall output score and description:	A+
SAIC exceeded milestones for 2 out of 3 outputs. SAIC met indicators related to research output, and peformed particularly well on the number of peer-reviewed publications and working papers. Policy briefs and other synthesis outputs targeted at policy-makers are still being developed. SAIC made good progress on indicators related to research communication within and outside the SAIC network with a high number of external presentations. SAIC’s network building and pursuit of external funding has increased to support future work that builds on SAIC projects.
Key lessons
- Limited capacity for research synthesis in project teams limits communications and impact: Some project teams contracted communication experts to support programmes (e.g. Cote d’Ivoire, DRC, Ghana) to make findings on gender, social cohesion and community works more accessible.
- Research network activities are in high demand: Across the SAIC network there is increasing demand to share methodologies and research findings. SAIC projects have started Southern-led discussions to develop a more formal network around urban violence to sustain cooperation after the current programme ends, with development of action plans to apply for further funding. IDRC supports this initiative but deliberately takes a hands-off approach to encourage Southern ownership of the network.
- Gender analysis should have been more strongly emphasised at the outset to ensure rigorous analysis across all projects: SAIC’s grants predate the UK gender Act 2014. While some projects are explicitly focussed on gendered analysis, and all projects are committed to collecting gender disaggeregated data, there are cases in which the analysis could have been more rigorious. The Mid Term Review instigated a range of remedial efforts, but gender impact could have been greater if it had been rigorousy addressed at the design stage.
Key actions	See recommendation above
Has the logframe been updated since the last review? No

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	New high-quality knowledge or analytical tools on the relationship between urban violence, poverty, and gender and other inequalities are generated and communicated to key stakeholders.
Output number per LF		1	Output Score	A++
Risk:		Moderate	Impact weighting (%):	33
Risk revised since last AR?		Y[4]	Impact weighting % revised since last AR?	N
[4] DFID introduced a new risk framework with four categories (minor, moderate, major, severe) to replace the previous risk framework (low, medium, high).

Indicator(s)	Milestone for June 2016	Progress
Number and type of publications, tools, briefs, etc. produced	10 publications produced and disseminated	Milestone exceeded – 125 publications produced and disseminated
Number and type of key stakeholders who receive SAIC research results	10 examples of evidence that key stakeholders received SAIC research results	Milestone achieved – At least 10 key stakeholders received SAIC research results
Degree to which technical quality standards (scientific integrity and scientific merit) are visible in reports prepared by research partners.	3 peer-reviewed publications produced	Milestone exceeded – 38 peer-reviewed publications produced

Key Points
1.1	This year’s milestone was exceeded more than tenfold, with a total of 125 publications[5], including peer-reviewed journal articles, book chapters or books (38), which are subject to external quality assurance. The others are working papers (35), policy briefs (17) and other non-peer reviewed publications (35). All 15 projects have produced at least two publications and 60% of projects reported at least one peer-reviewed publication this year. The most prominent research topics are the link between social cohesion and violence, organised crime and youth violence, the effectiveness of public work programmes in violence reduction, and the link between urban planning and violence. Dissemination of publications is achieved through stakeholder engagement and media outreach (see indicator 1.2).
[5] See list of publication in Appendix 1
Research synthesis is work in progress. SAIC summarised the trends across research programmes in 4 briefs, infographics and short documentary films. A key synthesis document is the midpoint update of research findings across SAIC project titled “Learning how to make cities safer”[6] that has become the most popular document downloaded from the SAIC website (269 unique views). Another highlight is a documentary film on the community work programme that is available on Youtube and has been viewed 66 times to date[7]. Progress on research synthesis is slower: Of the 15 projects, only 3 developed policy briefs, 5 infographics, and 2 audio-visual materials to communicate research findings.
[6] Available online: https://www.idrc.ca/en/article/learning-how-make-cities-safer [Accessed: 26 September 2016]
[7] Available online: https://www.youtube.com/watch?v=NcSWeoaek9c [Accessed: 26 September 2016]
1.2	SAIC exceeded the stakeholder engagement target at least threefold through direct contact with at least 32 senior-level stakeholders. African leaders from local or international governance institutions were the main targets of this year’s activities, compromising almost half of all high-level engagements. They include the Deputy President of South Africa, ministers and members of parliament from Zimbabwe and Cote d’Ivoire, mayors of four African cities (Dakar, Attecoubé, Bamako, Durban, and Mbuji-Mayi), and UN-Habitat’s Head of Projects. Activities in Latin America were predominately targeted at policy leaders from Chile and Peru and activities in Asia were focused on leading Indian civil society organisations.
SAIC research has reached other relevant policy and civil society actors through 107 presentations this year. Highlights include presentations at events hosted by the World Bank, the Organisation of Economic Cooperation and Development, UN-Habitat, and GIZ. The 96 documented instances of media coverage are also likely to have reached additional audiences. Highlights include references to SAIC research in newspapers with global readership such as The Economist (global), the Guardian (UK), and Le Monde (France) and television appearances on BBC Mundo and Al Jazeera. SAIC also reported active engagement on social media channels and monitoring of citations of research using Altmetrics, a system that tracks online shares of academic articles. This year, SAIC publications ranked among the top 25% of articles followed by Altmetrics. To improve the accessibility of research online, SAIC redesigned the IDRC website and will make all project-level outputs available online in the final year. The previous SAIC website recorded 5,000 unique page views and it is expected that the redesign will lead to an increase in the number of page views.
1.3	The target of 3 peer-reviewed publications was exceeded almost 13 times this reporting year. SAIC produced 38 peer-reviewed publications and the majority of projects (60%) have produced at least one peer-reviewed publication. The most productive projects of high-quality research are in Ghana, Venezuela and South Africa, producing about three quarters of all peer-reviewed publications. The citations of peer-reviewed SAIC research are almost four times higher compared to last year, with a total of 86 references to date[8]. Current research is published in journals focused on criminology, economic, geography, health, migration, political science, and psychology.
[8] Last year’s annual report mentioned 16 citations
Recommendations for the next year:
- Report on research impact: Develop and report a wider range of metrics such as the proportion of leadership by Southern researchers and women in publications (author or co-author), average impact factor of journals where SAIC research is published, number of citations of peer-reviewed research, total number of downloads of non-peer reviewed research papers from the SAIC website, and number of shares or mentions of SAIC research on social media (SAIC by July 2017)
- Provide research communication support: Support projects that have limited capacity in research communication with resources and advice on designing policy briefs and other synthesis documents (SAIC by July 2017)
- Improve website search functions: Include a search option on the IDRC website that allows to access SAIC outputs by publication type, topic and country (SAIC by July 2017)

Output Title	SAIC-funded researchers produce and communicate relevant evidence on the most effective strategies and interventions to reduce urban violence to key stakeholders.
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	34
Risk revised since last AR?		Y[9]	Impact weighting % revised since last AR?	N
[9] DFID introduced a new risk framework with four categories (minor, moderate, major, severe) to replace the previous risk framework (low, medium, high).

Indicator(s)	Milestone for June 2016	Progress
2.1 Number and type of publications of SAIC findings on the most effective strategies and interventions to reduce violence.	7 examples of evidence that SAIC findings on the most effective strategies and interventions to reduce violence are being produced in key forums (for example: peer-reviewed journal articles, presentations at influential/marquee workshops, conferences or seminars, articles in leading newspapers or development bulletins, radio programs, etc.)	Milestone exceeded – 30 peer-reviewed journal articles specifically addresses effective interventions
2.2 Number and type of key stakeholders (by category) who received SAIC-generated information on effective strategies and interventions.	10 examples of evidence that key stakeholders have received SAIC-generated information on effective strategies and interventions, including through SAIC outreach activities, and provide positive feedback about the research’s usefulness to policy or practice, in oral or written form	Milestone achieved – At least 10 key stakeholders received SAIC research results

Key points
2.1	SAIC has produced 30 publications that specifically address the effectiveness of violence reduction strategies, exceeding the cumulative target of 13. Three SAIC projects specifically focus on the effectiveness of violence prevention programmes. For example, research found that after an urban upgrading intervention in Khayelitsha (Cape Town) levels of violence were reduced by 7% in intervention areas compared to control areas.
2.2	SAIC shared the findings on effective strategies more generally. Output indicator 1.2. describes stakeholder and media outreach activities in more detail.
Recommendations for the next year:
- Research synthesis on effective strategies and interventions: Develop a policy brief that critically assesses the evidence base of strategies and interventions that have been tested with SAIC research (SAIC by July 2017)
- Engage with DFID country offices: Plan engagement on SAIC research findings with DFID country offices through presentations at country offices or engagement of DFID staff at SAIC events (SAIC by July 2017)

Output Title	A multi-disciplinary urban violence research network supports knowledge exchange among researchers and research partners, particularly in the Global South, and fosters a new generation of specialists to engage in high-quality policy-relevant research.
Output number per LF		3	Output Score	A
Risk:		Major	Impact weighting (%):	33%
Risk revised since last AR?		Y[10]	Impact weighting % revised since last AR?	N
[10] DFID introduced a new risk framework with four categories (minor, moderate, major, severe) to replace the previous risk framework (low, medium, high).

Indicator(s)	Milestone for June 2015	Progress
3.1 Number, type, and examples of knowledge exchange among SAIC researchers, and between SAIC researchers and non-SAIC researchers on SAIC topics.	10 examples of knowledge exchange	Milestone achieved – At least 10 examples of knowledge exchange activities among SAIC researchers
3.2 Number of junior and community researchers (disaggregated by sex) who are learning through project activities.	5 examples of evidence that junior and community researchers are learning through meaningful project activities such as participating in data collection and analysis, training, teaching SAIC material in classes, fellowships, etc.	Milestone exceeded – Approximately 2,000 individuals trained
3.3 Evidence that SAIC projects are able to leverage new funding from sources other than DFID and IDRC for projects involving one or more SAIC research partner.	Evidence that SAIC researchers are developing new projects that build on SAIC research	On track – 11 project proposals developed that build on SAIC research

Key points
3.1	The 10 prominent examples this year include events hosting 10-100+ participants aimed at knowledge exchange and network building within the community of SAIC researchers. They include workshops, webinars, panel discussions, and conferences, including four SAIC regional policy conferences in New Delhi, Santiago, Johannesburg and Dakar. Outcomes included newspaper articles in the national press (e.g. Business Standard, The Hindu) and increased levels of online engagement on SAIC-related content captured on Storify. Participants reported that they value sharing of methodologies, identification of similarities and trends across SAIC projects, and opportunities to challenge dominant discourses from their perspective as Southern researchers. SAIC reported only on the most significant 10 examples of knowledge exchange but noted that the number is likely to be higher if informal activities were included. More details on engagement with non-SAIC researchers are provided under indicator 1.2.
3.2	SAIC reported that around 2,000 individuals benefitted from SAIC activities. They include undergraduate students exposed to SAIC research through coursework across all 15 projects (600), students that learn about SAIC findings in SAIC-related fieldwork in Chile and Zimbabwe (312), fieldworkers trained to conduct surveys in Brazil and Mozambique (91), research training of early career researchers in Cote d’Ivoire (20), and practitioners trained on intervention strategies (112).
Capacity building highlights include a fellowship award to a researcher for SAIC-related activities by the Rockefeller Foundation, and a prize awarded to a SAIC principal investigator by Côte d’Ivoire’s President. Additionally, a researcher was hired as permanent staff because of good performance in the SAIC programme and three SAIC project staff used their research experience as a springboard to conduct graduate studies in South Africa and Brazil. SAIC also established a CAD 150,000 conference participation fund to help early career researchers to present research findings and expand their network at academic and policy events.
Most SAIC projects have not maintained gender-disaggregated data of stakeholder engagements and current data is too limited for any meaningful assessments of gender equity.
3.3	There is some evidence that SAIC researchers are developing new projects that build on SAIC research and that they are on track meeting the 2017 target. 5 research teams (India, Sri Lanka and South Africa, Cost Rica and El Salvador) have presented proposals to IDRC and other donors for new research that builds on SAIC research. They include proposals to the Ford Foundation and USAID (by the Indian projects). Anticipating the 2017 target, 6 SAIC projects have attracted additional funding of CAD 557,000 (approximately GBP 305,000) for SAIC-inspired work. Funders include the German Development Agency, the European Union, the Pan-American Development Foundation, and the Rockefeller Bellagio Center.
Recommendations for the next year:
Adjust indicator 3.3: Develop strategies to support SAIC-inspired work beyond the end of the project and set a measurable 2017 funding target (SAIC by July 2017)

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
IDRC is responsible for overall project management including financial management. IDRC has well established financial systems which comply with requirements to report to the Canadian Government. IDRC accounting and audit systems ensure that DFID funds are allocated and accounted for by each project funded. Key cost drivers are direct and indirect staff costs, travel costs, research consumables and related transport and supervision costs for the fifteen research grants.
Programme spend to date is £3,433,263. IDRC receives UK aid funds in pounds and operates in Canadian dollars. Multi-year exchange rate trends led to a total underspend of £254,737.
Payments are released in 2 stages against the annual forecast and are monitored against project progress with variances largely attributed to exchange rate movements. SAIC calculates its budget in dollars and claim the sterling equivalent. The favourable exchange rate has allowed SAIC to claim less than the maximum amount agreed in the MOU resulting in an “unused” budget. However, the recent exchange rate movement has resulted in a less favourable rate and underspent funds will be used.
IDRC provides annual audited reports on how DFID’s contribution is attributed within the organisation’s systems. DFID/IDRC have regular management meetings to discuss issues on the portfolio of projects which is also used as an opportunity to pass on information on any DFID initiatives that may link with this programme.
VfM performance compared to the original VfM proposition in the business case
VfM performance is in line with expectations, and overall the programme is on track to meet all its targets, exceed many of them, and meet its intended purpose.
The main criteria for success in achieving VfM are the uptake of SAIC research and the use of findings by policy actors. IDRC is already receiving good responses to research publications and will focus on research synthesis and communication in the final year. Previous exchange rate gains have been invested in a full-time Knowledge Translation Officer responsible for research uptake activities.
Assessment of whether the programme continues to represent value for money
The programme continues to represent good VfM. Progress is underpinned by the fact that IDRC has well established systems and processes to ensure VfM is achieved throughout the project. VfM is one of the ongoing management criteria and IDRC’s project manager closely tracks each project to address quality and cost issues to ensure the projects remain on delivery schedule. 15 research outputs are currently in peer review stage or full publication with the expectation that all will be published by end October 2016.
Key achievements along the four dimensions of DFID’s Value for Money Framework include:
- Economy: Travel costs were reduced through more efficient scheduling of multiple in-country meetings and events as well as remote engagements with experts. Additionally, IDRC management costs (‘indirect’ costs) are capped at a maximum of 11%.
- Efficiency: IDRC exceeded the majority of indicator targets without an increase in total programme spend.
- Effectiveness: IDRC research was used to inform policy making in Chile, Côte d’Ivoire, and South Africa and findings were included in policy reports by USAID and the World Health Organization.
- Equity: IDRC integrated a focus on gender and inclusiveness in research projects as advised in the mid-term review. SAIC asked partners to explore gender dynamics of men’s and women’s differential experiences of violence and exclusion.
Quality of financial management
IDRC’s regulations ensure proper and efficient use of resources and effective internal control. Annual budgets are negotiated and agreed with individual project partners based on the deliverables and financial projections reflected in their workplans. These projects are managed effectively by the SAIC team with payment being made in arrears on actual spend to ensure funds are used appropriately. IDRC and their partners are accountable for all expenditure incurred. SAIC is covered by IDRC’s policies on fraud, accountability and transparency
Financial forecasting has been within projections and the project is on track with all projects having been completed. IDRC is managing a budget of various currencies incl. £Sterling, the IDRC contribution in Canadian Dollars and range of further currencies to fund projects across Africa, Asia, and Latin America.
Recommendation:
Report on Value for Money of the programme using DFID’s 4 value for money indicators – economy, efficiency, effectiveness, and equity (SAIC by July 2017)

Date of last narrative financial report	9/6/16
Date of last audited annual statement	12/1/16

E: RISK (½ page)

Overall risk rating: Minor / Moderate / Major / Severe

Overview of programme risk: The overall risk rating is moderate. All projects are completed and the final publications are now being prepared. Key risks are:
- Limited IDRC staff capacity: IDRC reported growing demands on staff to support finalisation, synthesis and dissemination of research findings in the final year. SAIC mitigated this by hiring a full-time Knowledge Translation Officer and in-country consultants to support the team.
- Limited research uptake: Some projects lack the capacity and experience to produce and disseminate research synthesis targeted at non-academic audiences, which could negatively affect policy uptake. SAIC’s new Knowledge Translation Officer is developing a strategy in collaboration with partners to build research synthesis capacity and maximise research uptake.
- Unequal levels of research outputs: The majority of peer-reviewed research outputs are produced by a limited number of projects in Africa and Latin America, while one project in Asia produced the majority of policy briefs. SAIC is promoting more even contribution to research through regular communication, progress meetings, standard reporting requirements and support for research synthesis.
- Discontinuation of the SAIC network: As the project is coming to a close in 2017, the SAIC network risks dissolving unless action is taken to maintain the partnerships. IDRC is planning to develop mechanisms to maintain the network activities beyond the end of the project.

Outstanding actions from risk assessment

IDRC continually monitors programme risks and is proactive in responding early to instances which may affect overall progress. IDRC worked with grantees to finalise key research activities and outputs to ensure the project are completed on time. IDRC reacted quickly to advise DFID of a suspected incidence of fraud and initiated an audit to be carried out on the organisation liaising with DFID on procedures followed. The forensic audit cleared the organisation of any fraudulent activity.

In the Risk Matrix, each risk has a mitigation strategy which helps to ensure that any emerging issues will have minimal impact on the programme and allows IDRC to pre-empt problems as they develop.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
SAIC is on track to deliver within the planned timeframe and has in place robust policies, procedures and systems for managing finances and procurement and mitigating risks. SAIC plans activities by programme area and a work plan will be presented for approval. All projects have been completed and the focus is now on the dissemination and uptake of the research findings.
Performance of partnership(s)
DFID has an open and effective working partnership with IDRC. This involves frequent contacts, and more formal quarterly meetings to discuss project progress, identify areas of specific interest to DFID, and consider formal corporate reporting requirements. These contacts ensure knowledge sharing between the organisations, and that both parties are up to date on current thinking, so that any departmental priorities can be addressed. DFID’s SAIC management team has taken an active role in conversations with IDRC about establishing a strategic relationship with IDRC.
Asset monitoring and control
The project has no assets.
G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable. This is a multi-country research project, which does not provide funding through government systems.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The Annual Review team held a formal meeting with SAIC via conference call in August 2016 to discuss outputs against milestones (including successes/challenges), risks (and how these are being managed), and financial management. Follow-up clarification questions were addressed by SAIC’s programme manager. The DFID review team conducted a desk-based review of key documents, including a detailed report of the programme’s performance over the review period submitted by the partners, and key research and communication outputs (see list below). The Annual Review has been shared with IDRC and recommendations will be followed up at the next project meeting.

Monitoring progress throughout the review period

DFID and the IDRC project manager have formal quarterly meetings to discuss and monitor overall programme progress and any individual project issues that have arisen, problems and notable achievements in the SAIC programme. This enables DFID to provide input and direction during the project implementation phase.
This Annual Review was conducted by DFID staff in the UK:
- GCSD Research Manager and Senior Responsible Owner (SRO) for SAIC, UK
- GCSD DESA Social Development Adviser, UK
- GCSD Lead Conflict Adviser, UK
- GCSD Team Leader, UK

Documents reviewed
- SAIC Business case (Quest doc – 3809359)
- SAIC Annual Review 2013 (Quest doc - 4249901)
- SAIC Annual Review 2014 (Quest No 4737552)
- SAIC Annual Review 2015 (Quest doc – 5201687)
- IDRC Progress Report (Quest doc – 5547949)
- IDRC Financial Report
- SAIC Logframe
- SAIC Engagements with Key Policy and Practice Stakeholders
- SAIC Project-Level Findings Details
- SAIC Publication Progess Update
- Updated list of SAIC outputs by country
- SAIC Impact Stories (Quest doc – 5645465)
- SAIC VfM Examples (Quest doc – 5645464)
- Selected publications in Appendix 1

Appendix 1: SAIC-produced outputs

Publications marked with * indicate those that explicitly engage with the question of identifying the most effective strategies and interventions to reduce violence. Grey text indicates this publication was reported in a previous annual report.
Table 1: Distribution of publications by type among SAIC projects (outputs reported in the 4th Annual Report)
Project/Type of Publication	Accepted peer-reviewed	Under review	Non-peer-reviewed	Policy briefs	Working papers & others	Total
FLACSO-Costa Rica & El Salvador	1		3			4
LACSO-Venezuela	9		5			14
Univ de Chile					4	4
Univ Cape Town-South Africa	5				1	6
Centre for the Study of Violence and Reconciliation-South Africa	2			3	7	12
Univ of Zimbabwe					11	11
Univ of Kinshasa-DR Congo			17		1	18
Univ of Ghana	9			2		11
Univ Alassane Ouattara-Cote d’Ivoire			2			2
Inst for Business Administration-Pakistan		1	1			2
CEPT University/Inst for Human Development-India				13	7	20
International Centre for Ethnic Studies-Sri Lanka/Centre for Development Studies-India	2	2	1		3	8
Tata Inst for Social Sciences-India, Brazil, South Africa	6		3		1	10
Inst Promundo-Brazil/Mozambique	1		2			3
Human Sciences Research Council-South Africa/Brazil	3		1			6
TOTAL	38	3	35	18	35	129

Table 2: Distribution of publications by type among SAIC projects (Cumulative outputs)[11]
[11] These figures may conflict with past reports. This is due in part to grantees informing IDRC that they changed publication plans reported as published in previous years. Other inconsistencies are due to some early working papers being reworked and submitted for consideration by peer-reviewed journals. In these cases, the paper has been counted only once, lowering the number of previously-reported publications.
Project/Type of Publication	Accepted peer-reviewed	Under review	Non-peer-reviewed	Policy briefs	Working papers & others	Total
FLACSO-Costa Rica & El Salvador	1	1	4		1	7
LACSO-Venezuela	9		5			14
Univ de Chile					4	4
Univ Cape Town-South Africa	9		1		4	14
Centre for the Study of Violence and Reconciliation-South Africa	3			3	7	13
Univ of Zimbabwe			1		11	12
Univ of Kinshasa-DR Congo			17		4	21
Univ of Ghana	11			2		13
Univ Alassane Ouattara-Cote d’Ivoire			2			2
Inst for Business Administration-Pakistan		1	1		2	4
CEPT University/Inst for Human Development-India	1			13	15	29
International Centre for Ethnic Studies-Sri Lanka/Centre for Development Studies-India	3	2	1		6	12
Tata Inst for Social Sciences-India, Brazil, South Africa	10		3		2	15
Inst Promundo-Brazil/Mozambique	2		2			4
Human Sciences Research Council-South Africa/Brazil	6		3			9
TOTAL	55	4	49	18	56	173

Peer-reviewed publications (reported in the 4th Annual Report)
1. Bagson, Ernest and Adobea Yaa Owusu. 2016. “Securing the urban space on whose terms? Insights from poverty and crime baseline survey in Tamale, Ghana.” Ghana Journal of Geography. 8.1 (Special Issue): 124-147. *
2. Barolsky, Vanessa. 2016. “Is social cohesion relevant to a city in the global south? A case study of Khayelitsha.” South African Crime Quarterly. 55 (Special Issue on Social Cohesion): 17-30. *
3. Barolsky, Vanessa and Chandra Gould. 2016. “Making sense of the duality of social cohesion.” South African Crime Quarterly. 55 (Special Issue on Social Cohesion): 3-5.
4. Bond, Patrick. 2015a. “The Intellectual Meets the South African Social Movement: A Code of Conduct is Overdue when Researching such a Conflict-Rich Society.” Politikon: South African Journal of Political Science. 42.1: 117-122. * [Subscriber access only; IDRC has the manuscript.]
5. -----. 2015b. “Economic, Ecological and Social Risks in Durban’s Port-Petrochemical-Coal Expansion.” Man in India. 94.3: 471-500.
6. Bowman, Brett. Garth Stevens, Gillian Eagle, Malose Langa, Sherianne Kramer, Peace Kiguwa, and Mzikazi Nduna. 2015. “The second wave of violence scholarship: South African synergies with a global research agenda.” Social Science and Medicine. 146: 243-248. *
7. Briceño-León, Roberto, ed. 2016. Ciudades de Vida y Muerte. La Ciudad y el Pacto Social para la Contención de la Violencia [Cities of Life and Death. The City and the Social Pact to Contain Violence]. Caracas: Editorial Alfa. * [Available for purchase on Amazon, or IDRC has copies.]
8. Briceño-León, Roberto. 2016. “Las explicaciones sociales de la violencia homicida: Evidencia de Colombia, Brasil y Venezuela.” [Social explanations of homicidal violence: Evidence from Colombia, Brazil and Venezuela] In Jose Vicente Tavares Dos Santos and Cesar Barreira (eds.), Paradoxos de segurança cidadã. [Paradoxes of citizen security]. Porto Alegre: Tomo Editorial and CLACSO. *
9. -----. 2015a. “Violencia urbana, sistema normativo y democracia en Venezuela [Urban violence, the legal system, and democracy in Venezuela].” in M. Gomez and R. Perez Perdomo eds. Cultura Jurídica y Políticas en Venezuela Revolucionaria [Legal and Political Culture in Revolutionary Venezuela]. Caracas: Universidad Metropolitana. * [Not available online or for purchase; IDRC has the chapter manuscript.]
10. -----. 2015b. “La desigualdad no causa la violencia, la violencia produce desigualdad [Inequality doesn’t cause violence, violence produces inequality].” In J. Marta Sosa ed. La Desigualdad en Venezuela [Inequality in Venezuela]. Caracas: Editorial Fundavag. * [Not available online or for purchase; IDRC has the chapter manuscript.]
11. -----. 2015c. “Violencia urbana en Venezuela: Quiebre del pacto social y vulnerabilidad en Venezuela [Urban violence in Venezuela: Breaking the social pact and vulnerability in Venezuela].” in Markus Gottsbacher and John de Boer (eds.), Vulnerabilidad en Contextos de Violencia: Experiencias de América Latina y del Caribe. Mexico City: Siglo XXI. * [Currently available only in Spanish; English, open-access version forthcoming.]
12. -----. 2015d. “Caracas: From heaven branch to urban hell.” In Kees Kooning and Dirk Kruijt (eds.), Violence and Resilience in Latin American Cities. 53-72. London: Zed Books. * [Available for purchase; IDRC has the chapter manuscript.]
13. -----. 2015e. “Pandillas, mafias y bandas: Una visión sociológica del delito organizado [Gangs, mafias, and militias: A sociologícal view of organized crime].” in Roberto Briceño-León and Alberto Camardiel (eds.), Delito Organizado, Mercados Ilegales y Democracia [Organized crime, illegal markets and democracy]. 15-37. Caracas: Editorial Alfa. * [Not available for purchase online; IDRC has the chapter manuscript.]
14. -----. 2015f. “El estado y el delito organizado: Exceso y vacío normativo [The state and organized crime: Excess and regulatory vacuum].” in Roberto Briceño-León and Alberto Camardiel eds. Delito Organizado, Mercados Ilegales y Democracia [Organized crime, illegal markets and democracy]. 39-59. Caracas: Editorial Alfa. * [Not available for purchase online; IDRC has the chapter manuscript.]
15. Briceño-León, Roberto and Alberto Camardiel. 2015. “El delito organizado como amenaza a la democracia [Organized crime as a threat to democracy].” in Roberto Briceño-León and Alberto Camardiel eds. Delito Organizado, Mercados Ilegales y Democracia [Organized crime, illegal markets and democracy]. 189-212. Caracas: Editorial Alfa. * [Not available for purchase online; IDRC has the chapter manuscript.]
16. Desai, Ashwin. 2015. “An Aerotropolis Lands in Durban, South Africa: Exploring the “Satanic Geographies” of Fast Capitalism.” Capitalism Nature Socialism. 26.3: 1-13. [Subscriber access only; IDRC has requested the manuscript.]
17. Frimpong, Louis K. 2016. “Geography of fear of crime: Examining Intra-urban differentials in Sekondi-Takoradi Metropolis, Ghana.” Ghana Journal of Geography. 8.1 (Special Issue): 79-102. *
18. George, Ann, and Irudaya Rajan. 2015. “Changing Cities and Changing Lives: Development Induced Displacement in Kochi, Kerala.” Cities People Places: An International Journal on Urban Environments. 1.1: 1-18. *
19. Jabar, Ardil, Dylan Barth, Richard Matzopoulos, and Mark Engel. 2015. “Is the introduction of violence and injury observatories associated with a reduction of violence in adult populations? Rationale and protocol for a systematic review.” BMJ Open. 5:e007073. *
20. Khan, Sultan. 2015. “Development public policies, emerging contradictions and prospects in the post-apartheid South Africa.” in Gustavo Lins Ribeiro, Tom Dwyer, Antonadia Borges and Eduardo Viola, eds. Social, Political and Cultural Challenges of the BRICS. Sao Paulo: ANPOCS: 181-206. [Large file; may take some time to download.]
21. Lakshman, Iresha, Asela Ekanayaka, and Rajith W. D. Lakshman. 2016. “Going to school from a relocated urban community: struggling for education within imposed walls.” Migration and Development. Online. * [Subscriber access only; IDRC has the manuscript.]
22. Langa, Malose and Themba Masuku. 2015. “The role of ex-offenders in implementing the Community Work Programme as a crime and violence prevention initiative.” African Safety Promotion Journal. 13.2: 78-91. *
23. Langa, Malose, Themba Masuku, David Bruce, and Hugo van der Merwe. 2016. “Facilitating or hindering social cohesion? The impact of the Community Work Programme in selected South African townships.” South African Crime Quarterly. 55 (Special Issue on Social Cohesion): 41-48. *
24. Maharaj, Brij. 2015. “The turn of the south? Social and economic impacts of mega-events in India, Brazil and South Africa.” Local Economy. 30.8: 983-999. [Subscriber access only; IDRC has the manuscript.]
25. Martinez-Alier, Joan, Isabelle Anguelovski, Patrick Bond, Daniela Del Bene, Federico Demaria, Julien-Francois Gerber, Lucie Greyl, Willi Haas, Hali Healy, Victoria Marin-Burgos, Godwin Ojo, Marcelo Porto, Leida Rijnhout, Beatriz Rodriguez-Labajos, Joachim Spangenberg, Leah Temper, Rikard Warlenius, and Ivonne Yanez. 2014. “Between activism and science: grassroots concepts for sustainability coined by Environmental Justice Organizations.” Journal of Political Ecology. 21: 19-60.
26. Matzopoulos, Richard, and Brett Bowman. 2016. “The Sustainable Development Goals put violence prevention on the map.” [Letter to the editors] Journal of Public Health Policy. 37: 260-262. * [Subscriber access only; IDRC has the manuscript.]
27. Oni, Tolu, Warren Smit, Richard Matzopoulos, Jo Hunter Adams, Michelle Pentecost, Hanna-Andrea Rother, Zulfah Albertyn, Farzeneh Behroozi, Olufunke Alaba, Mamadou Kaba, Claire van der Westhuizen, Maylene Shung King, Naomi Levitt, Susan Parnell, and Estelle Lambert. 2016. “Urban Health Research in Africa: Themes and Priority Research Questions.” Journal of Urban Health. Online. *
28. Oteng-Ababio, Martin. 2016. “Beyond poverty and criminalization: splintering youth groups and ‘conflict of governmentalities’ in urban Ghana.” Ghana Journal of Geography. 8.1 (Special Issue): 51-78. *
29. Owusu, George. 2016. “Introduction: Crime and poverty nexus.” Ghana Journal of Geography. 8.1 (Special Issue): 1-10. *
30. Owusu, George, Adobea Yaa Owusu, Martin Oteng-Ababio, Charlotte Wrigley-Asante, and Isaac Agyapong. 2016. “An assessment of households’ perceptions of private security companies and crime in urban Ghana.” Crime Science. 5.5: Online. *
31. Owusu, George, Charlotte Wrigley-Asante, Martin Oteng-Ababio, and Adobea Yaa Owusu. 2015. “Crime prevention through environmental design (CPTED) and built-environment manifestations in Accra and Kumasi, Ghana.” Crime Prevention & Community Safety. 17. 4: 249-269. * [Subscriber access only; IDRC has the manuscript.]
32. Owusu, George, Martin Oteng-Ababio, Adobea Yaa Owusu, and Charlotte Wrigley-Asante. 2016. “Can poor neighbourhoods be correlated with crime? Evidence from urban Ghana.” Ghana Journal of Geography. 8.1 (Special Issue): 11-31. *
33. Pérez Sáinz, Juan Pablo, Rodolfo Calderón Umaña, and Gilbert Brenes Camacho. 2014. “Exclusión social, violencia y ámbito doméstico. Evidencia y reflexiones desde Centroamérica.” [Social exclusion, violence, and the domestic sphere. Evidence and reflections from Central America] Papeles de Población. 87: 9-41. *
34. Roberts, Benjamin and Steven Gordon. 2016. “Pulling us apart? The association between fear of crime and social cohesion in South Africa.” South African Crime Quarterly. 55 (Special Issue on Social Cohesion): 49-60. *
35. Schuurman, Nadine, Jonathan Cinnamon, Blake Walker, Vanessa Fawcett, Andrew Nicol, Syed Hameed, and Richard Matzopoulos. 2015. “Intentional injury and violence in Cape Town, South Africa: an epidemiological analysis of trauma admissions data.” Global Health Action. 8. Online. *
36. Taylor, Alice and Tatiana Moura. 2015. “Gendered urban violence(s) and non-violent trajectories in Rio de Janeiro.” in Markus Gottsbacher and John de Boer, eds. Vulnerability in Violent Contexts: Experiences from Latin America and the Caribbean. Mexico City: Siglo XXI. * [Currently available only in Spanish; English, open-access version forthcoming.]
37. Wrigley-Asante, Charlotte. 2016. “Gendered perception of crime and safety: insights from different socio-economic urban neighbourhoods in Ghana.” Ghana Journal of Geography. 8.1 (Special Issue): 103-123. *
38. Wrigley-Asante, Charlotte, George Owusu, Martin Oteng-Ababio, and Adobea Yaa Owusu. 2016. “Poverty and crime: Uncovering the hidden face of sexual crimes in low-income communities in Ghana.” Ghana Journal of Geography. 8.1 (Special Issue): 32-50.

Previously reported peer-reviewed publications
1. Barolsky, Vanessa. 2014. “Violence in Khayelitsha: Finding a way out.” HSRC Review, 12.4: 8-11.*
2. Bowman, Brett, Garth Stevens, Gillian Eagle, and Richard Matzopoulos. 2014. “Bridging risk and enactment: the role of psychology in leading psychosocial research to augment the public health approach to violence in South Africa.” South African Journal of Psychology. Online. [Subscriber access only; IDRC has the manuscript.]
3. Bruce, David. 2015. “Preventing crime and violence through work and wages: The impact of the Community Work Programme.” South African Crime Quarterly 52: 25-37.*
4. Cassidy, Tali, Gabrielle Inglis, Charles Wiysonge, and Richard Matzopoulos. 2014. “A systematic review of the effects of poverty deconcentration and urban upgrading on youth violence.” Health and Place, 26: 78-87. * [Subscriber access only; IDRC has the manuscript.]
5. Cassidy, Tali, Melikaya Ntshingwa, Jakub Galuszka, and Richard Matzopoulos. 2015. “Evaluation of a Cape Town safety intervention as a model for good practice: A partnership between researchers, community and implementing agency.” Stability: International Journal of Security & Development, 4.1: 1-12.*
6. Datta, Amrita and Shivani Satija. February 28, 2015. “Crime against women and children in Delhi: Analysis of secondary and empirical data.” Economic and Political Weekly, L.9: 87-97. [Subscriber access only; IDRC has the manuscript.]
7. Desai, Ashwin. 2015. “Of Faustian pacts and mega-projects: The politics and economics of the port expansion in the south basin of Durban, South Africa.” Capitalism Nature Socialism, 26.1: 18-34. [Subscriber access only; IDRC has the manuscript.]
8. Kato-Wallace, Jane, Gary Barker, Marci Eads, and Ruti Levtov. 2014. “Global pathways to men’s caregiving: Mixed methods findings from the International Men and Gender Equality Survey and the Men Who Care study.” Global Public Health: An International Journal for Research, Policy and Practice, 9.6: 706-22.*
9. Khan, Sultan, and Malcolm Wallis. 2015. “Planning and sustainable development of low income human settlements in KwaZulu-Natal.” Journal of Human Ecology, 50.1: 43-58.
10. Maharaj, Brij, and Meghan Crosby. 2014. “So what’s new? Post-apartheid evictions, displacement and forced relocations.” in Nico Kotze, Ronnie Donaldson and Gustav Visser, eds. Living in a Changing Urban Landscape: Proceedings of the IGU Urban Geography Commission (Urban challenges in a complex world). Johannesburg: University of Johannesburg.
11. Matzopoulos, Richard, and Jonathan Myers. 2014. “The Western Cape government’s new integrated provincial violence prevention policy framework: Successes and challenges.” Aggression and Violent Behavior, 19: 649-654.* [Subscriber access only; IDRC has the manuscript.]
12. Mdlalose, Bandile. 2014. “The rise and fall of Abahlali baseMjondolo, a South African Social Movement.” Politikon: South African Journal of Political Science, 41.3: 345-353. [Subscriber access only; IDRC has the manuscript.]

Forthcoming publications (accepted for publication)
1. Anwar, Nausheen. Forthcoming 2017. “Negotiating the field: Ethical dilemmas and methodological reflexivity researching in diverse ethno-religious and violent settings in urban Pakistan.” Area. [IDRC has the manuscript.]
2. Barolsky, Vanessa. Forthcoming 2016. “Loving thy neighbour in times of violence: social cohesion and collective efficacy in South Africa.” Psychology in Society. [IDRC has the manuscript.]
3. Barolsky, Vanessa and Ignacio Cano, eds. Forthcoming 2017. Understanding violence in South Africa and Brazil: a problem of social cohesion, inequality and poverty. Pretoria: HSRC Press. [in drafting stage]
4. Collyer, Michael, Kopalapillai Amirthalingam and Danesh Jayatilaka. Forthcoming 2016. “The right to adequate housing in post-conflict Colombo, Sri Lanka.” In Katherine Brickell, et al. eds. Geographies of Forced Evictions. London: Palgrave. [IDRC has the manuscript.]
5. Oteng-Ababio, Martin, Adobea Yaa Owusu, George Owusu, and Charlotte Wrigley-Asante. Forthcoming 2016. “Geographies of crime and collective efficacy in urban Ghana.” Territory, Politics, Governance. 4.3. * [Not yet published online; IDRC has the manuscript.]
6. Oteng-Ababio, Martin, George Owusu, Charlotte Wrigley-Asante, and Adobea Yaa Owusu. Forthcoming 2016. “Longitudinal analysis of crime trends and patterns in Ghana (1980*2010): A new perspective.” African Geographical Review. * [IDRC has manuscript.]

Under review (reported in the 4th Annual Report)
1. Anwar, Nausheen. “Negotiating the field: Ethical dilemmas and methodological reflexivity researching in diverse ethno-religious and violent settings in urban Pakistan.” Under review with Area.
2. Herath, Dhammika, Asela Ekanayaka, and Rajith Lakshman. “Development forced displacement and resettlement: Urban re-housing in Colombo from a wellbeing perspective.” Under review with Journal of Refugee Studies.[IDRC has the manuscript]
3. Rajan, Irudaya and Indu Kalamani. “Community profile of Edachira in Kakkanad, Kochi: Coping Mechanisms of those Displaced by the Smart City Project” under review as a CDS Working Paper. *
Previously-reported articles under review
Calderón Umaña, Rodolfo, and Karla Salazar Sánchez. “Dinámicas de violencia en tres comunidades costarricenses socialmente excluidas.” [Violence dynamics in three socially excluded Costa Rican communities] under review with Revista de Ciencias Sociales.*

Non-peer-reviewed publications (reported in the 4th Annual Report)
1. Albornoz Arias, Neida and Rina Mazuera Arias, eds. 2016. El Táchira en cifras 2015: El contrabando en las ciudades de frontera desde la perspectiva de la institucionalidad [Tachira in figures 2015: Contraband in border cities from the perspective of institutionality]. Táchira: Universidad Catolica del Táchira. * [Not available online; IDRC has the manuscript.]
2. Anwar, Nausheen H., Daanish Mustafa, Amiera Sawas, and Sharmeen Malik. 2016. Gender and Violence in Urban Pakistan. Karachi: Institute for Business Administration. [Pending posting online; IDRC has a copy.]
3. Barolsky, Vanessa. 2016. “Research Brief: Is social cohesion the missing link in preventing violence?” Pretoria: Human Sciences Research Council. *
4. Bhide, Amita. 2015. “Revisando o deslocamento urban na India [Reviewing urban displacement in India].” In Joana Barros, Anelise Gutterres and Evanildo Barbosa da Silva, eds. Caderno de Debates 4: BRICS: tensões do desenvolvimento e impactos socioambientais [Book of Debate 4: BRICS: Development tensions and environmental impacts]. Rio de Janeiro: FASE. *
5. Bhide, Amita and Durgesh Solanki. 2016. Transforming the Slum through creation of Property Market: A case study of M-Ward in Mumbai. Mumbai: TISS University. [Pending posting online; IDRC has a copy.]
6. Bond, Patrick. 2015. “South Africa: Exploding with rage, Imploding with Self-Doubt – but Exuding Socialist Potential.” Monthly Review: An Independent Socialist Magazine. 67.2.
7. -----. 2014. “Contentious Constitutionalism, Commodification, and Commoning: South African Civil Society tackles Constitutional Reform” in Tyanai Masiya and Charles Mutasa, eds. Civil society and constitutional reforms in Africa. Harare: MWENGO. [Not available online; IDRC has the manuscript.]
8. Briceño-León, Roberto. 2016. “Para comprender la violencia en Venezuela [To understand violence in Venezuela].” SIC 782. *
9. Briceño-León, Roberto and Alberto Camardiel. 2016. “Pobreza y violencia en Venezuela [Poverty and Violence in Venezuela].” In Anitza Freitez, Marino González and Genny Zúñiga, eds. Una mirada a la situación social de la población venezolana. Caracas: Universidad Católica Andrés Bello. [Not available online; IDRC has the manuscript.]
10. -----. 2015. “Informe de Violencia del Observatorio Venezolano de Violencia 2015 [Violence Report of the Venezuelan Violence Observatory 2015].” Caracas: Observatorio Venezolano de Violencia. * [Not available online; IDRC has the manuscript.]
11. Briceño-León, Roberto and the Venezuelan Violence Observatory staff. 2016. “Informe conjunto para el II Examen Periódico Universal (EPU) de la Organización de las Naciones Unidas (ONU) [Joint report for the 2nd Universal Periodic Review (UPR) of the United Nations (UN)].” Caracas: Observatorio venezolano de violencia. [Not available online; IDRC has the manuscript.]
12. Burte, Himanshu, Lalitha Kamath, and Nirali Joshi. 2016. Global Narrative Report. People, Places, and Infrastructure: Countering urban violence and promoting justice in Mumbai, Rio, and Durban. Mumbai: TISS University. [Pending posting online; IDRC has a copy]
13. Burte, Himanshu and Shruthi Parthasarathy. 2016. The Place of Spatial Justice: Jogeshwari Vikhroli Link Road (JVLR), and the transformation of an informal urban landscape in Mumbai. Mumbai: TISS University. [Pending posting online; IDRC has a copy]
14. Collyer, Michael. 2015. "Text box 9: Urban migration and different forms of urban violence.” In International Organization for Migration. World Migration Report 2015. Migrants and Cities: New Partnerships to Manage Mobility. Geneva: IOM.
15. FLACSO-Costa Rica and American University. 2015. “Violence and Community Capabilities: Insights for building safe and inclusive cities in Central America.” CLALS Working Paper 8. Washington, DC: American University.
16. Kamath, Lalitha and Radhika Raj. 2016. City Building and Regime Creation in the Peripheries for Mumbai. Mumbai: TISS University. [Pending posting online; IDRC has a copy]
17. Kankwenda Mbaya, Justin, François Mukoka Nsenda and Willy Mbalanda Lawunda. 2015a. “Approche théorique et empirique à l’étude de la pauvreté urbaine en RDC : Note de revue de la litterature [Theoretical and empirical approach to the study of urban poverty in DRC: Note on the literature review].” Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 71-77.
18. ----. 2015b. "Kinshasa – Mbuji-Mayi, problématique des inégalités, de la pauvreté et de la vulnérabilité des citadins [Kinshasa – Mbuji-Mayi, problems of inequality, poverty, and vulnerability of urban dwellers]. Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 83-86.
19. Kundu, Ratoola and Shivani Satija. 2016. Changes, Continuities, Contestations: Tracing the contours of the Kamathipura’s precarious durability through livelihood practices and redevelopment efforts. Mumbai: TISS University. [Pending posting online; IDRC has a copy]
20. Lobho, Jean-Pierre and Lwa Djugudjugu. 2015. "Instabilité politique et pauvreté en République démocratique du Congo [Political instability and poverty in the Democratic Republic of Congo]." Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 78-82.
21. Mpiana Tshitenge wa Masengu, Jean Pierre. 2015. « Les va et vient des Kuluna entre les centres de détention et la cite à l’aune des opinions des habitants de la Commune de Ngaba [The comings and goings of Kuluna between detention centres and the city with respect to the residents of the Commune of Ngaba]. Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 41-47.
22. Mulamba Feza, Ingrid. 2015. "Les femmes, la pauvrete et le microcredit informel en RDC [Women, poverty and informal microcredit in DRC]." Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 61-65.
23. Musao Kalombo Mbuyu, Celestin. 2015. “Services publics et actions de la Police nationale congolaise. Un bilan a demi teint ? [Public services and actions of the Congolese National Police: Mixed results?].” Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 21-34.
24. Mwene Batende, Gaston. 2015. "Heureux ceux qui ‘sèment.’ Églises de réveil et paupérisation des adeptes à Kinshasa. [Blessed are those who ‘sow.’ Revivalist churches and impoverishment of followers in Kinshasa]." Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 87-90.
25. Ngoma-Binda, P. 2015. “Homme et femme au cœur de toute vie sociale. Quel sens et quelle place pour le genre dans une société matrilinéaire ? [Man and woman at the heart of all social life. What sense and place for gender in a matrilineal society?] Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 48-54.
26. N’goran, Koffi Parfait. 2015. “Biceps, Machetes and Kalashnikovs: Radioscopy of Violent Construction of Youth Dreamt Identities in Côte d’Ivoire.” International Journal of Business, Humanities and Technology.[12] 5.5: 9-17. *
  [12] This journal may be a predatory journal, which is why we are including it as a non-peer reviewed publication.
27. N’goran, Koko Lucie, Ismaila Bakayoko, and Joceline-Boli Agbadou Nakpon. 2016. “Conception Magico- Religieuse Des Agressions Sexuelles Et Du Viol Des Filles De 04 Mois A 18 Ans A L’ouest De La Côte D’ivoire (Duékoué Et Guiglo).” [Magico-religious conception of sexual assault and rape of girls aged 4 months to 18 years in the west of Côte D’ivoire (Duékoué Et Guiglo)] European Scientific Journal.[13] 12.2. Online. *
  [13] This journal may be a predatory journal, which is why we are including it as a non-peer reviewed publication.
28. Olela Nonga, Donatien. 2015. “Approche sociohistoire de la violence urbaine dans la ville de Kinshasa [Social history approach to urban violence in Kinshasa].” Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 4-9.
29. Pérez Sáinz, Juan Pablo, Larissa Brioso, Rodolfo Calderón Umaña, Margarita Montoya, Karla Salazar Sanchez and Mario Zetino. “Exclusión social, violencia y respuestas comunitarias en ciudades centroamericanas: explicando variaciones para orientar políticas. Informe final de investigacion” [Social exclusión, violence and community responses in Central American cities: Explaining variations to orient policies. Final research report]. San Jose: FLACSO-Costa Rica.
30. Pérez Sáinz, Juan Pablo and Karla Salazar Sanchez. 2014. “Cariari: comunidades con presencia de Territorios Seguros: Informe de investigación” [Cariari: Communities where Territorios Seguros is present: Research report]. San Jose: FLACSO-Costa Rica. [IDRC has the manuscript.]
31. Salazar Sanchez, Karla and Juan Pablo Pérez Sáinz. 2014. “Seguridad Comunitaria en Concepción Arriba de Alajuelita: Informe de investigación” [Community security in Concepción Arriba de Alajuelita: Research report]. San Jose: FLACSO-Costa Rica. [IDRC has the manuscript.]
32. Sekimonyo wa Magango and Gaspard Ambemane Akemane. 2015. “De l’effectivité des lois relatives à la parité homme-femme en RDC [On the effectiveness of gender equity laws in DRC.]" Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 55-60.
33. Shomba Kinyamba, Sylvain. 2015a. “Editorial.” Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 3.
34. -----. 2015b. “Violence juvénile à Kinshasa : Contexte et le prévention possible [Youth violence in Kinshasa: Context and possible prevention].” Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 10-20.
35. -----. 2015c. “Gangstérisme juvénile à Kinshasa : Soubassement et illusions – desillusions lies aux stratégies de lutte [Youth gangsterism in Kinshasa : foundation and illusions – disillusions related to anti-gang strategies].” Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 35-40.
36. -----. 2015d. "Obsession identitaire souverainiste et exclusions urbaines en République démocratique du Congo [Sovereignist obsession with identity and urban exclusions in the Democratic Republic of Congo]." Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 66-70.
37. Shomba Kinyamba, Sylvain, and Donatien Olela Nonga. 2015. Monographie de la ville de Mbujimayi [Monograph of the city of Mbujimayi]. Kinshasa: Editions M.E.S.
38. Shomba Kinyamba, Sylvain, François Mukoka Nsenda, Donatien Olela Nonga, Theo Macaire Kaminar, Willy Mbalanda. 2015. Monographie de la ville de Kinshasa [Monograph of the city of Kinshasa]. Kinshasa: ICREDES.
39. Slegh, Henny, Esmeralda Mariano, and Silvia Roque. 2016. “Being a Man in Maputo: Masculinities, Economic Stress and Urban Violence in Maputo Mozambique. Results from the International Men and Gender Equality Survey (IMAGES).” Washington, DC, and Rio de Janeiro: Promundo. [Pending final lay-out]
40. Taylor, Alice, Tatiana Moura, J.L. Scabio, E Borde, J.S. Afonso, and Gary Barker. 2016. “This isn’t the life for you: Masculinities and non-violence in Rio de Janeiro, Brazil. Results from the International Men and Gender Equality Survey (IMAGES) with a focus on urban violence.” Washington, DC, and Rio de Janeiro: Promundo.
41. Tshishimbi Katumumonyi, Evariste. 2015. “Urbanisation, pauvreté et détérioration de l’environnement urbain à Kinshasa [Urbanization, poverty and the deterioration of the urban environment in Kinshasa]. Special issue of Mouvements et Enjeux Sociaux [Social Movements and Issues]: 91-93.
Previously-reported Non-peer-reviewed publications
1. Cano, Ignacio, Doriam Borges, and Eduardo Ribeiro. 2014 revised edition. “‘Os Donos do Morro’: Uma avaliação exploratória do impacto das Unidades de Polícia Pacificadora (UPPs) no Rio de Janeiro.” [The Slum Owners: An Exploratory Assessment of the Impact of Police Pacifying Units (UPPs) in Rio de Janeiro] São Paulo: Fórum Brasileiro de Segurança Pública and Heinrich Boell Stiftung. *
2. Cano, Ignacio, and Thais Lemos Duarte. 2014. “Milícias.” [Militias] in Rodrigo Ghiringhelli de Azevedo, Renato Sérgio Lima, and José Luiz de Ratton (eds). Crime, policía e justiça no Brasil. [Crime, police and justice in Brazil] Sao Paulo: Editora Contexto. [Available for purchase online; IDRC has the manuscript.]
3. Matzopoulos, Richard, Morna Cornell, Brett Bowman, and Jonny Myers. September 6, 2014. “67th WHA Resolution on violence prevention misses the mark. [Letter]” The Lancet. 384.* [Subscriber access only; IDRC has the manuscript.]
4. Pérez Sáinz, Juan Pablo, ed. 2015. Exclusión Social y Violencias en Territorios Urbanas Centroamericanos. [Social Exclusion and Violences in Central American Urban Areas] San José, CR: FLACSO.
5. Stewart, Julie, Rosalie Katsande and Olga Chisango. 2014. “Shelter, a home, a house or housing?” Harare: Southern and Eastern African Research Centre on Women’s Law. *

Policy Briefs (reported in the 4th Annual Report)
1. Bhide, Amita and Radhika Raj. 2016. Mumbai in Redevelopment Mode: Implications for Violence and Justice. Mumbai: TISS University. [Pending posting online; IDRC has a copy]
2. Brankovic, Jasmina. 2016. “Women’s Contribution to Social Cohesion and Violence Prevention through the Community Work Programme." CWP Policy Brief 3. Johannesburg: Centre for the Study of Violence and Reconciliation. *
3. Bruce, David. 2015a. “The Good, the Better and the Best: How the Community Work Programme Can Reach Its Full Potential as an Instrument of Community Development in South Africa,” CWP Policy Brief 1. Johannesburg: Centre for the Study of Violence and Reconciliation. *
4. -----. 2015b. “Working for Safety: The Community Work Programme as a Tool for Preventing Violence and Building Safer Communities,” CWP Policy Brief 2. Johannesburg: Centre for the Study of Violence and Reconciliation. *
5. Centre for Urban Equity. N.d. [2016a]. “Ahmedabad Policy Brief 1: Vatwa Resettlement Sites: Constrained Mobility and Stressed LIvelihoods.” Ahmedabad: Centre for Urban Equity. Also available in Gujarati. *
6. -----. N.d. [2016b]. “Ahmedabad Policy Brief 2: Vatwa Resettlement Sites: Basic Services and Amenities: Deprivations and Infrastructural Conflicts.” Ahmedabad: Centre for Urban Equity. Also available in Gujarati. *
7. -----. N.d. [2016c]. “Ahmedabad Policy Brief 3: Vatwa Resettlemtn Sites: Thefts, Robberies, and Burglaries.” Ahmedabad: Centre for Urban Equity. Also available in Gujarati. *
8. -----. N.d. [2016d]. “Ahmedabad Policy Brief 4: Vatwa Resettlement Sites: Illicit Activites and Goondagardi [Felony].” Ahmedabad: Centre for Urban Equity. Also available in Gujarati. *
9. -----. N.d. [2016e]. “Ahmedabad Policy Brief 5: Vatwa Resettlement Sites: Gender Insecurity and Violence Against Women.” Ahmedabad: Centre for Urban Equity. Also available in Gujarati. *
10. -----. N.d. [2016f]. “Ahmedabad Policy Brief 6: Bombay Hotel: Tenure Insecurity and Land Conflicts in Informal Commercial Subdivisions.” Ahmedabad: Centre for Urban Equity. Also available in Gujarati. *
11. -----. N.d. [2016g]. “Ahmedabad Policy Brief 7: Bombay Hotel: Everyday Conflicts in Basic Services in Informal Commercial Subdivisions.” Ahmedabad: Centre for Urban Equity. Also available in Gujarati. *
12. -----. N.d. [2016h]. “Ahmedabad Policy Brief 8: Bombay Hotel: Crime, Violence and Unsafe Spaces in Informal Commercial Subdivisions.” Ahmedabad: Centre for Urban Equity. Also available in Gujarati. *
13. -----. N.d. [2016i]. “Ahmedabad Policy Brief 9: Bombay Hotel: Gender Insecurity and Violence Against Women.” Ahmedabad: Centre for Urban Equity. Also available in Gujarati. *
14. -----. N.d. [2016j]. “Guwahati Policy Brief 1: Women’s Safety and Transport in Guwahati.” Ahmedabad: Centre for Urban Equity. Also available in Assamese. *
15. -----. N.d. [2016k]. “Guwahati Policy Brief 2: Hill Settlements: Deprivations as Conflict and Conflicts due to Deprivations.” Ahmedabad: Centre for Urban Equity. Also available in Assamese. *
16. -----. N.d. [2016l]. “Guwahati Policy Brief 3: Hill Settlements: The Land Rights Movement.” Ahmedabad: Centre for Urban Equity. Also available in Assamese. *
17. -----. N.d. [2016m]. “Guwahati Policy Brief 4: Deprivations and Conflicts in Street Vending in Guwahati.” Ahmedabad: Centre for Urban Equity. Also available in Assamese. *
18. Institute of Statistical, Social, and Economic Research (ISSER). 2015a. “Urban Crime Prevention and Community Social Cohesion: The Case of Urban Ghana.” ISSER Policy Brief. 2. Accra: ISSER. *
19. -----. Forthcoming 2016. “Sexual crimes in Ghana: Does poverty play a role?” ISSER Policy Brief. 4. Accra: ISSER. *
Working Papers, and Other Outputs (reported in the 4th Annual Report)
1. Bhide, Amita. 2015. “Social Economic Conditions and Vulnerabilities in M (East) Ward, Mumbai.” Mumbai: TISS University. [Pending posting online; IDRC has a copy]
2. Brankovic, Jasmina. 2016. "Integrating Learning, Monitoring and Evaluation into Policy-Oriented Research: Lessons from CSVR’s Urban Violence Project." Johannesburg: Centre for the Study of Violence and Reconciliation. *
3. Burte, Himanshu and Nisha Kundar. 2016. Mapping Report: Mumbai. Mumbai: TISS University. [Pending posting online; IDRC has a copy]
4. Chisango, C. O. 2015a. “Bulawayo Survey Field Report.” Harare: Southern and Eastern Africa Research Centre on Women’s Law. *
5. -----. 2015b. “Mbare Survey Field Report.” Harare: Southern and Eastern Africa Research Centre on Women’s Law. *
6. -----. 2015c. “Hatcliffe Survey Field Report.” Harare: Southern and Eastern Africa Research Centre on Women’s Law. *
7. Desai, Renu, Darshini Mahadevia, Shachi Sanghvi, Suchita Vyas, Rafi Malek, and Mohammed Sharif Malek. 2016. “Bombay Hotel: Urban Planning, Governance and Everyday Conflict and Violence in a Muslim Locality on the Peripheries of Ahmedabad.” CUE Working Paper 31. Ahmedabad: Centre for Urban Equity.
8. Ekanayake, Asela, and Kopalapillai Amirthalingam. Forthcoming 2016. “Relocation of Urban IDPs in Colombo: An analysis of income inequality and livelihoods.” ICES Working Paper. Colombo: International Centre for Ethnic Studies. [Not available online; publication pending approval of Asela Ekanayake’s Master’s degree, of which this is the thesis.]
9. Institute of Environmental Studies, University of Zimbabwe. 2015. “Safe and Inclusive Cities Survey Report.” Harare: Southern and Eastern Research Centre on Women’s Law. *
10. Institute for Human Development. 2015. “Symposium on Making Cities Safe and Inclusive: Perspectives from South Asia [Report].” New Delhi: Institute for Human Development. * [Pending posting online; IDRC has a copy.]
11. Jayatilaka, Danesh, Kopalapillai Amirthalingam, and Shyana Gunasekara. 2015. “Conflict, Displacement and Post-War Recovery: A Community Profile of Passaiyoor East in Jaffna, Sri Lanka.” ICES Working Paper 7. Colombo: International Centre for Ethnic Studies. Also available in Tamil. *
12. Joseph, Yogi, and Renu Desai. 2015. “Planning and Designing Streets for Safe and Inclusive Cities: Report on course offered as part of CEPT Winter School 2014.” Ahmedabad: Centre for Urban Equity. *
13. Kankolongo Mbombo, Matthieu. 2015. “Les patrouilles de la police nationale congolaise à Mbujimayi et les dessous de ‘l’opération café’ : facteurs explicatifs et issues possibles [Congolese National Police Patrols in Mbujimayi and the bottom of ‘the coffee operation’: Explanatory factors and possible outcomes." CDS Working Paper 93. Kinshasa: Chaire de Dynamique Sociale. [Pending posting online; IDRC has a copy]
14. Lakshman, Iresha, Dhammika Herath, Mohommad Alikhan, and Asela Ekanayake. 2016. “Experiences of a relocated community: A case study of Sinhapura, Wanathamulla.” ICES Working Paper. Colombo: International Centre for Ethnic Studies. Also available in Sinhala. * [Pending posting online; IDRC has a copy]
15. Langa, Malose. 2015a. A Follow-Up Report on the Community Work Programme in Bokfontein. Johannesburg: Centre for the Study of Violence and Reconciliation. *
16. -----. 2015b. The Impact of the Community Work Programme on Violence in Orange Farm. Johannesburg: Centre for the Study of Violence and Reconciliation. *
17. Mahadevia, Darshini, Aseem Mishra, Anurita Hazarika, Yogi Joseph, and Tinam Borah. 2016. “Safe Mobility for Women: Case of Guwahati.” CUE Working Paper 28. Ahmedabad: Centre for Urban Equity.
18. Mahadevia, Darshini, Aseem Mishra, Yogi Joseph, Arup Das. 2016a. “Informal Development, Services Access and Land Rights Claims: Dynamics of Conflicts in Hill Settlements, Guwahati.” CUE Working Paper 29. Ahmedabad: Centre for Urban Equity.
19. -----. 2016b. “Street Vending in Guwahati: Experiences of Conflict.” CUE Working Paper 30. Ahmedabad: Centre for Urban Equity.
20. Maseko, Sian and Everjoice Win. N.d. “PAR Manual for Practitioners.” Harare: Southern and Eastern Africa Research Centre on Women’s Law. [Pending posting online; IDRC has a copy]
21. Mandipa, Esau. 2014. “Safe Cities Literature Review on Relevant Constitutional and Legal Provisions.” Harare: Southern and Eastern Africa Research Centre on Women’s Law. *
22. Masuku, Themba. 2015. A Case Study of the Ivory Park Community Work Programme. Johannesburg: Centre for the Study of Violence and Reconciliation. *
23. Masuku, Themba, Malose Langa and David Bruce. 2016. The Community Work Programme in Kagiso Johannesburg: Centre for the Study of Violence and Reconciliation. *
24. Mohor, Alejandra and Bastian Castillo. 2015. “Violencia en tres ciudades latinoamericanas [Violence in three Latin American cities].” Santiago: Universidade de Chile. [IDRC has the manuscripts, one for each city.]
25. Mohor, Alejandra and Liliana Manzano. 2014. “Encuesta de percepción en barrios [Neighbourhood perception survey].” Santiago: Universidade de Chile. [Research instrument; IDRC has a copy.]
26. Mullagee, Fairuz, with David Bruce. 2015. Building a Good Nation in Manenberg: A Case Study of the Manenberg Community Work Programme. Johannesburg: Centre for the Study of Violence and Reconciliation. *
27. Mureithi, L., A. Africa, N. van Schaik, T. Naledi, R. Matzopoulos, and R. English. 2015. “Injury Morbidity Surveillance in Nyanga and Khayelitsha in the Western Cape.” Technical Report. Cape Town: Health Systems Trust.
28. Mutembedzi, Joshua. 2014. “Policy and Government Literature Review.” Harare: Southern and Eastern Africa Research Centre on Women’s Law.
29. Puwana, Zukiswa. 2015. The Community Work Programme in Grabouw. Johannesburg: Centre for the Study of Violence and Reconciliation. *
30. Sharma, Nikita and Bhim Reddy. N.d. “Media Analysis: Delhi.” New Delhi: Institute for Human Development.
31. Sinha, Indu. 2016. “Capturing Violence through Media Reports: The Case of Patna, Bihar.” New Delhi: Institute for Human Development. [Pending posting online; IDRC has the manuscript]
32. Southern and Eastern Africa Research Centre on Women’s Law. 2013. “A toolkit for Engaging Women and Communities.” Harare: Southern and Eastern Africa Research Centre on Women’s Law. *
33. Theatre Arts Department, University of Zimbabwe. N.d. [2015?] “Theatre as Community Engagement.” Harare: Southern and Eastern Africa Research Centre on Women’s Law. *
34. Tocornal, Ximena and Maria Isabel Toledo. 2013a. “Manual de investigación en terreno: Especificaciones para la primera fase de preparación para el terreno [Field Research Manual: Specifications for the first phase of preparation for the field].” Santiago: Universidade de Chile. [IDRC has a copy of this tool.]
35. -----. 2013b. “Manual de investigación en terreno: Especificaciones para la segunda fase de preparación para el terreno [Field Research Manual: Specifications for the second phase of preparation for the field].” Santiago: Universidade de Chile. [IDRC has a copy of this tool.]
36. Tsanga, Amy. 2013. “Unearthing Exclusions, Towards More Inclusive Zimbabwean Cities.” Harare: Southern and Eastern Africa Research Centre on Women’s Law. *
37. Zimbabwe Lawyers for Human Rights. N.d. [2015?] “Mobile Clinic Report for Hatcliffe.” Harare: Southern and Eastern Africa Research Centre on Women’s Law. *
Previously-reported working papers and other outputs
1. Anwar, Nausheen H., Daanish Mustafa, Sarwat Viqar, Amiera Sawas, and Humeira Iqtidar. 2014. “Urbanization, Gender & Violence in Millennial Karachi: A Scoping Study.” Contested Development Working Paper 66. London and Karachi: King’s College London and Institute of Business Administration.
2. Bhide, Amita, et al. 2014. “The city produced: Urban development, violence and spatial justice in Mumbai.” Mumbai: TISS University. [Pending posting online; IDRC has a copy]
3. Centre for Urban Equity. 2014. “Workshop Report: Stakeholder Consultation on Safe and Inclusive Cities: Ahmedabad.” Ahmedabad: Centre for Urban Equity.
4. -----. 2014. “Workshop Report: Stakeholder Consultation on Safe and Inclusive Cities in Guwahati.” Ahmedabad: Centre for Urban Equity.
5. FLACSO-Costa Rica y FLACSO-El Salvador. N.d. “Exclusión Social y Violencia en Comunidades Urbanas Centroamericanos: Reflexiones a partir de un análisis cuantitativo.” San Jose: FLACSO-Costa Rica. [Working document; IDRC has a copy.]
6. George, Ann, and S. Irudaya Rajan. 2014. “Rebuilding lives: Stories of struggle, agency and resettlement of the development induced displaced in the suburbs of Kochi.” Thiruvananthapuram: Centre for Development Studies.
7. Health Systems Trust. 2013a. “Injury Morbidity Surveillance in Nyanga and Khayelitsha in the Western Cape: Phase 1 Summary Report September/October 2013.” Cape Town: Health Systems Trust.
8. -----. 2013b. “Report on the Rapid Assessment of the Injury Morbidity Burden at Health Services in 3 High Violence Communities in the Western Cape.” Cape Town: Health Systems Trust.
9. Mahadevia, Darshini, Renu Desai, and Aseem Mishra. 2014. “City profile: Guwahati.” CUE Working Paper 24. Ahmedabad: Centre for Urban Equity.
10. Mahadevia, Darshini, Renu Desai, and Suchita Vyas. 2014. “City profile: Ahmedabad.” CUE Working Paper 26. Ahmedabad: Centre for Urban Equity.
11. Matzopoulos, Richard, et al. 2014. “Injury Morbidity Surveillance in Nyanga and Khayelitsha in the Western Cape: Phase 2 Summary Report.” Cape Town: University of Cape Town.
12. Rajan, S. Irudaya and Ann George. 2014a. “Some betterment and multiple agonies- Findings from a study of development induced displaced in Kerala.” Thiruvananthapuram: Centre for Development Studies.
13. -----. 2014b. “Is there a Kerala ‘model’ of displacement? Findings from a study of development induced displaced in Kochi.” Thiruvananthapuram: Centre for Development Studies.
14. Reddy, Bhim and Nikita Sharma. 2015. “Slums, citizens and violence: Initial observations from qualitative survey in Patna and Delhi.” New Delhi: Institute for Human Development.
15. Risbud, Neelima. 2014. “City Profile: Delhi.” New Delhi: Institute for Human Development. [Pending posting online; IDRC has the manuscript]
16. Satija, Shivani. 2015. “Political context, crime and violence in Patna and Delhi.” Institute for Human Development Working Paper. New Delhi: Institute for Human Development. [Pending posting online; IDRC has the manuscript]
17. Sawas, Amiera, Daanish Mustafa, Nausheen H. Anwar, Humeira Iqtidar, and Sarwat Viqar. 2014. “Urbanization, Gender and Violence in Rawalpindi and Islamabad: A Scoping Study.” Contested Development Working Paper 67. London and Karachi: King’s College London and Institute for Business Administration.
18. Shomba Kinyamba, Sylvain, et al. 2015a. “Revue de la littérature empirique sur la pauvreté." [Review of the empirical literature on poverty] Kinshasa: Université de Kinshasa. [IDRC has the manuscript]
19. -----. 2015b. "Revue de la littérature empirique sur la violence." [Review of the empirical literature on violence] Kinshasa: Université de Kinshasa.
20. -----. 2015c. “Revue de la littérature empirique sur l’urbanisation.” [Review of the empirical literature on urbanization] Kinshasa: Université de Kinshasa.
21. Tiwary, Rakesh and Nikita Sharma. 2015. “City profile: Patna.” New Delhi: Institute for Human Development. [Pending posting online; IDRC has the manuscript]

Films
1. Centre for the Study of Violence and Reconciliation. 2016. The role of the Orange Farm Community Work Programme in preventing violence. Johannesburg: Centre for the Study of Violence and Reconciliation. *
2. Human Sciences Research Council. 2016. Social cohesion: The missing link in overcoming violence and inequality? Pretoria: Human Sciences Research Council.
3. Institute for Human Development. 2016. Divided City. New Delhi: Institute for Human Development. [Pending final edits.]
4. Université Alassane Ouattara. 2016. Faire l’incroyable [Do the unbelievable]. Bouaké: Université Alassane Ouattara. [Pending final edits.]