Project Completion Review - Top Sheet
This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	March 2017

Title: Review of Impact of the Sierra Leone Free Health Care Initiative (FHCI)
Programme Code: / 202706	Start Date: Apr 2012	End Date: 31 December 2016
If programme was closed >1 month early please describe in a few words why.	Not applicable.

Summary of Programme Performance

Year	2013	2014	2015	2016
Programme Score	C	A	A	A+
Risk Rating	Low	Low	Medium	Moderate

Financial Position

Original Programme Value	£1,000,000
Extensions/ amendments	6-month no cost extension granted in April 2015. Changed the end date to 31 December 2016.
Log-frame revisions (with dates)	March 2016: / Outcome modified to “Evidence produced on the extent that FHCI has impacted on key health and health system indicators, and use of this evidence by stakeholders.” / Outcome Indicator 1 modified to: “# Impact Review reports which have progressively evidenced the degree to which FHCI has impacted on the nation's health and health system performance.” / Outcome Indicator 2 modified to: “% of key stakeholders interviewed (by DFID) who are aware of the results and feel that the results have informed policy/strategy.” / Output indicators 1.1-1.4 should be combined into 1.1 with completion in 2014 indicated in achievements.
Total programme spend	£997,343.60

Follow up actions required following closure
- Advocate for government to develop a health financing strategy.
- Advocate for increased government resourcing for FHCI commodities procurement.
- Encourage the Ministry of Health and Sanitation (MOHS) and Districts to work collaboratively and develop joint approaches to address systemic challenges (e.g. staffing; managing (and timely rotating of excess) FHCI stock commodities between hospitals and PHUs to reduce stockouts.)
- Disseminate widely the review recommendations to continue informing discussions on FHCI and related health provision.
- Support efforts to improve quality of care in public facilities.
- Encourage MoHS to develop a new M&E strategy that provides an overarching framework for M&E work in the health sector.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202706/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202706/documents

Outline of programme and what it has achieved
Sierra Leone’s Free Health Care Initiative (FHCI) was introduced in April 2010 to in response to high levels of mortality and morbidity amongst mothers and children. FHCI removed user fees for pregnant and nursing women with children under the age of five recognising the cost, or perceived cost of accessing care, was a barrier to them taking up health services on offer. FHCI also sought to strengthen the supply side with reforms in infrastructure, Human Resources for Health (HRH), drugs and equipment’s supply, governance, Monitoring and Evaluation (M&E), communication and financing.

DFID commissioned an independent evaluation of the FHCI in 2012 to know whether the intended results would be delivered and to evaluate the policy’s impact. The inception period, contracted through the then DFID Human Development Resource Centre (HDRC[1]) in July 2012, finished in April 2013 (instead of December 2012). This was due to a cholera epidemic that restricted MOHS’s participation in the evaluation design process. By the time it was completed, DFID had changed its global framework service provider for evaluations from HDRC to the Professional Evidence and Applied Knowledge Service (PEAKS), and Oxford Policy Management Limited (OPML) was procured as the new team of evaluators through this framework. OPML started work in January 2014.
[1] DFID Human Development Resource Centre (HDRC) was managed by HLSP and Cambridge Education, members of the Mott MacDonald Group. HLSP and Cambridge Education are trading names of Mott MacDonald Limited.

Progress was, however, delayed further by the Ebola epidemic which reduced the use of health services and contributed to increased morbidity and mortality. OPML staff were unable to visit during this period to conduct fieldwork, due to the risk of infection. Whilst some data collection took place, it did not meet the criteria for an ‘Impact Evaluation’ as a valid baseline could not be established. The programme was therefore changed to a ‘Review of Impact of Sierra Leone’s Free Health Care Initiative’. The programme’s end date was also changed to December 2016 to allow research and interviews to be completed.

This project completion review (PCR) is based on OPML’s final review report entitled Sierra Leone Free Health Care Initiative (FHCI): process and effectiveness review[2]. It was published in December 2016. The review asks key questions on whether FHCI has contributed to saving lives through improved health outcomes for the target groups; the extent to which FHCI represents value for money (VfM); how effectively it has been implemented; whether it addressed the right interventions; the other barriers still remaining; the equity effects; unintended consequences and sustaining FHCI in the future.
[2] http://www.opml.co.uk/projects/evaluation-free-health-care-initiative-fhci-sierra-leone
The review concludes FHCI has met a clear need in Sierra Leone. It is appropriately designed and is delivering services to the target beneficiaries. It has stimulated development partner funding and retained the political will and momentum needed for important systemic reforms. Consensus amongst stakeholders is that it is significant and worth supporting. Other gains of FHCI include revitalised structures for sector governance; increased staffing; better systems for staff management and pay; new monitoring and evaluation systems; facility audits conducted; improved infrastructure and solid awareness campaigns. From a VfM perspective; additional financial resources from donors has reduced household spending on health from 83% in 2007 to 62% in 2013. FHCI is considered cost-effective, saving an estimated 561,500 – 594,200 life years during 2010-13, at a cost in the region of $420-$445 per life year saved. Weaknesses in its implementation are also highlighted including the inconsistent supply of FHCI commodities and the loss of health gains made before the Ebola epidemic struck. On whether FHCI has led to improved health, the review is uncertain, but highlights data that shows a reduction in under-five mortality since it started.

Suggested improvements include monitoring to improve the quality of care in public facilities; overcoming residual barriers (e.g. lack of transport to facilities and socio-cultural barriers); improved resourcing (i.e. for staffing and drugs) and addressing systemic institutional challenges in both the MOHS and districts. On sustainability, it recommends ‘an increased focus and public investment in health care’ to enhance performance and accountability in the sector.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment
IMPACT - Evidence of improved maternal, newborn and child health in Sierra Leone.
Indicator 1: Review provides evidence of the degree to which the FHCI has impacted on women and children's health.	Baseline: Current understanding to be determined by inception report. Target: Review establishes the role of the FHCI in improved health outcomes

OUTCOME - Evidence produced on the extent that FHCI has impacted on key health and health system indicators, and use of this evidence by stakeholders.
Indicator 1: # Impact review reports which have progressively evidenced the degree to which FHCI has impacted on the nation's health and health system performance.		Baseline of 0; Target of 3. Achieved: 3 by December 2016
Indicator 2: % of key stakeholders interviewed (by DFID) who are aware of the results and feel that the results have informed policy/strategy		Baseline: 0%. Target: 75% Achieved: 75% by December 2016.

Impact
The annual reports have progressively demonstrated the degree to which FHCI has impacted on health (although the absence of baseline data and weaknesses in the datasets have limited some analysis).

The final evaluation report concludes that whilst it is not possible to measure if maternal mortality has changed as a result of the FHCI it has likely contributed to reductions in under five mortality. The 2013 Demographic Health Survey ( DHS) reports a sharp reduction in under five mortality immediately after the start of the FHCI with levels falling from 187 per 1,000 live births in 2009 to 147 in 2010. Mortality rates then continue to fall in the following years reaching 126 per 1,000 live births in 2012. This improvement is attributed to increased coverage of maternal and child health services in the country with the gap between geographical and wealth groups closing significantly. One of the evaluation’s studies also indicated that access to maternal care for disabled women was slightly higher that for non-disabled mothers which is encouraging.

The introduction of FHCI resulted in a tripling in the number of consultations of under-fives at health facilities to 300,000 a month but then declined rapidly as facilities struggled to cope with the increased demand. The attendance was beginning to approach the 300,000 mark again in 2014, but was then severely affected by Ebola.

There have been clear improvements in the uptake of services such as antenatal care increasing from 88% in 2009 to 98% in 2010/11. Protection from malaria during pregnancy has greatly increased from before FHCI with the doubling of women using insecticide bed nets and receiving intermittent preventative treatment reaching 53% in 2013. Whilst birth rates in health facilities remains low the coverage of post-natal care is improving from 60% in 2009 to 73% in 2013. Vaccination rates for children under one year has increased from 41% in 2009 to 68% in 2013 and the proportion of children receiving treatment for childhood illnesses (such as acute respiratory infection) has doubled to 45%.

It is not yet possible to measure what the impact of the Ebola epidemic is on maternal and child mortality. Whilst the number of deaths from Ebola are known, it is suspected that many more deaths will have been caused by the population’s reduced utilisation of services during 2014 and 2015. A DHS will be conducted in 2017. Once this data is available, it would be useful to consider whether the pre- existence of the FHCI enabled the country to recover from the epidemic, and recover the health gains quicker, than if such a policy had not been in place.

Outcome
The review’s intended outcome - “Evidence produced on the extent that FHCI has impacted on key health and health system indicators, and use of this evidence by stakeholders” – has been achieved.

It is only now that normal health programmes, which would use this evidence, are being restarted or redesigned after the disruption of the Ebola epidemic. However the Government and partners such as the World Bank; GIZ and the UN agencies have used the findings of the evaluation to inform their plans and programmes going forward. In addition, the evaluation may be useful to advocate to other donors to invest in Sierra Leone and thereby expand the limited amount of development partners in the country.

Output Score and Description
	Output	Weight	Summary	Score
1	Improved understanding of the impact and operational effectiveness of the FHCI.	30%	The inception report was produced on time. Initial analysis was built on and some baseline date collected (despite the ebola epidemic). A dissemination strategy was defined and satisfactorily implemented. It is too early to assess whether research will be taken up, The Sierra Leone environment is not strong in doing so. However partners have reported using the report to inform their plans in the sector. Articles submitted for peer review mean a much wider audience is being reached and will likely stimulate greater take up over time. Target has been met.	A
2	Effective and participative annual impact review process that remains within budget.	50%	Reports have been produced on time and to budget. The Health Financing Unit (HFU) has benefited from training and mentoring support and developed a health financing strategy. Additional resources (presentations; literature) remain accessible to HFU. Target has been met.	A
3	Improved understanding of the socio-cultural considerations of the uptake of free health care amongst the FHCI target group.	20%	The research strategy was defined, updated and quality assured during the project’s lifetime. All research field work and data aggregation were completed. Target has been met.	A

Lessons and how these have been shared
The final review report sets out the range of lessons learnt across the entire health system in detail and proposed recommendations on the way forward. These have been widely shared during the period April 2016 to January 2017 in presentations; discussions and policy briefings across Government (e.g. State House, MoHS, Ministry of Finance and Economic Development (MOFED)) and with development partner organisations and international and local non-governmental organisations (NGO). They are informing and will (hopefully) positively influence policy discussions as future programme priorities are being considered (e.g. by DFID; WB; GIZ; Government etc.). The key national/international stakeholders met are listed in the review. All the reports are available on the OPML website. Some of the links are included below:
1. http://www.opml.co.uk/projects/evaluation-free-health-care-initiative-fhci-sierra-leone
2. http://www.opml.co.uk/publications/news/opm-evaluation-recognised-uk-department-international-development
3. http://globalhealth.thelancet.com/2016/05/31/free-health-care-initiative-sierra-leone-six-years-six-lessons
4. http://www.kit.nl/health/webinars-sexual-reproductive-health-rights-fragile-environments/

Key recommendations:
Quality of care: needs improvement with clear clinical standards and protocols developed and incorporated into training. The review suggests updating the 2008 Emergency Obstetrics and Neonatal Centre (EmONC) needs assessment. DFID’s new Saving Lives programme for Sierra Leone has recently done this through support provided to the United Nations Population Fund (UNFPA). Work to start refurbishment is being tendered locally by the MOHS. The development of quality of care indicators and score cards for health facilities is also being supported under the Saving Lives programme through WHO.

Address barriers to access and deepen decentralisation: FHCI has reduced household costs and improved the supply of care, but more community engagement is needed to raise awareness of entitlements; benefits of health services and danger signs for women and children. Stronger inter-sectoral collaboration between MOHS and other Ministries is recommended. Similarly with Districts, including timely budget disbursement and improved capacity for District Health Management Teams (DHMT) to plan, supervise and monitor programmes is recommended.

Governance: MOHS needs to lead on health policy and the health system. Parallel systems should be avoided (e.g. drugs supply) by building planning/staffing capacity.

Health financing strategy: should be developed to provide coherence between FHCI and other policy strands. Greater accountability and transparency are needed to monitor performance. Additional public funds are needed for FHCI drugs and supplies and plans to generate this through withholding taxes will be insufficient for FHCI or universal health coverage in Sierra Leone for a while. Continued/increased donor support will be needed. Hybrid solutions to release funding and/or using Government supply and procurement systems should be considered. Data on health financing also needs to be improved to capture true costs of FHCI and improve measurement of lower household out-of-pocket (OOP) payments. The World Bank, following DFID’s lobbying, have committed to support the Government to develop a health financing strategy.

Develop and implement a robust and comprehensive M&E strategy for health especially in areas where data is weak i.e. quality of care, staffing, drugs and financing.

Human Resources: improve payroll management to keep it updated; decentralise HR functions to district level for greater responsiveness and strengthen central HR management capacity for MOHS to lead planned reforms. DFID is supporting health payroll cleansing and Huma n Resources for Health (HRH) reforms under the Saving Lives programme which are being implemented through the Clinton Health Access Initiative (CHAI) and World Health Organisation (WHO).

Infrastructure, drugs and supplies - health infrastructure needs to be improved. A ‘pull’ system is needed to reduce stock-outs of drugs and medical supplies, plus timely delivery of commodities. An effective monitoring system is needed to manage the supply chain at all levels and budget made available from Government and partners to ensure a continuous supply of commodities for hospitals and Peripheral Health Units (PHUs). DFID is supporting the reform of the National Pharmaceutical Procurement Unit (NPPU) and has provided all of the FHCI commodities for a year (September 2016 to August 2017) to enable the Government to establish and budget for a new drug supply system.

Communications: Any reforms should be well communicated. Implementers should be consulted first so they can raise any practical concerns before wider communication is made to the public (e.g. FHCI was communicated to the population first before health workers, and this caused tensions).

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved understanding of the impact and operational effectiveness of the FHCI.
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Yes – to reflect updated DFID Risk Framework measures	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 An inception report produced, including revised methods, data sources, baseline FHCI progress and impact to date.	July 2014	Done. Target met.
1.2. A Short research uptake and dissemination plan produced and executed (Produced by May 2016 and executed by December 2016)	July 2016	Done. Target met.
1.3. Policy brief produced	4 in December 2016	Done. Target met and exceeded.

Key Points
This output was updated after the January 2016 annual review. Disseminating the review’s finding widely has provided stakeholders a clear understanding of the benefits to Sierra Leone in adopting the FHCI for the specific target group. The review confirms that lives of pregnant and lactating mothers and children under the age of 5 have been impacted, with reduced spend by households over the years since it was introduced on health services. Detailed analysis about progress (or not) in the supply side and flagging where progress has been made and implementation weaknesses. This allows stakeholders to consider how to develop and design programmes to help meet critical needs. The policy briefs are particularly helpful in drawing out the critical issues succinctly and on the recommendations of what needs to be done to continue implementing FHCI over time.

Summary of responses to issues raised in previous annual reviews (where relevant)
OPML completed the FHCI fiscal space analysis and has shared it widely. The Health Financing Unit at the MOHS has benefitted from training and support and is adopting the review’s suggested approaches for FHCI funding. DFID used the study to lobby the Government and the World Bank on the need for a comprehensive health financing strategy. The World Bank have since committed to supporting the MOHS develop the strategy over the next year. This will also help the Government access new funding such as the Global Funding Facility for Reproductive and Maternal Health.

Recommendations for future programmes
Recommendations for future programmes are detailed earlier and in the website links provided and have been shared widely.

Output Title	Effective and participative annual impact review process that remains within budget.
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	50%
Risk revised since last AR?		Yes – reflects new Risk framework	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Data sources and methodology reviewed in the inception report and revised annually to ensure they are relevant to annual impact review process.	Jul-14 / Jan-15 / Jan-16	Done. Target met.
Annual reports submitted on time. (includes final impact review report)	Jan 15 / Jan 16	Done. Target achieved.
Annual reports submitted within budget. (includes final impact review report)	Jan 15 / Jan 16	Done. Target achieved.
A final project completion report (PCR) submitted, detailing progress against this logframe and deliverables and expenditure of all project funds.	Jan 17	Done. Target achieved.
A short capacity building plan developed and executed (Produced by May 2016, executed by Dec 2016)	Dec 16	Done. Target achieved.

Key Points
Data available to do the analysis was limited and a range of different measures have been used to ensure related questions have been answered.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations for future programmes
Recommendations for future programmes are detailed earlier and in the website links provided and have been shared widely.

Output Title	Improved understanding of the socio-cultural considerations of the uptake of free health care amongst the FHCI target group.
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		Yes – reflects new Risk framework	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Appropriate research strategy designed and implemented.	Jan 16	Done. Target met.
% of research field-work and data-aggregation completed.	Dec 16	Done. Target met.
Policy and final report includes substantial analysis and recommendations regarding the equity of the FHCI and socio-cultural considerations of uptake	Dec 16	Done. Target met.

Key Points
Despite the ebola outbreak, the research strategy, field work and data collection were satisfactorily completed. OPML triangulated through focus group discussions and wider literature reviews. These efforts and policy briefs have contributed to updating stakeholders understanding of the socio-cultural and other challenges and constraints beneficiaries face to access health care.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations for future programmes
Recommendations for future programmes are detailed earlier and in the website links provided and have been shared widely.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The main cost drivers are consultant costs for research, project management; report compilation and the related operating costs. These have been properly managed through a milestone contract.

VfM performance compared to the original VfM proposition in the business case
The Business Case did not include measurable VFM indicators but took the view that ‘the proposed £1 million represents exceptional value for money for the breadth of outcome from this project’. The amount was equivalent to 0.75% of total FHCI investment by DFID during the period 2012/13 – 2015/16. It was also below DFID’s accepted practice of evaluation costs not exceeding 5% of total programme budgets. The last two annual reviews have revalidated this point, confirming these costs are cost-effective and represent very good value for money. The project has stayed within budget and all milestones in the contract have been met.

Concerns about the review results being challenged because of the absence of baseline and other data are no longer valid. The extension period provided sufficient time to complete outstanding research and fieldwork. Data gaps must be contextualised to Sierra Leone, where there is generally a lack of available data and of questionable quality. These concerns were addressed by OPML adopting mixed method approaches, triangulation of data sources and modelling studies. Comments on the strength of evidence are also set out in the full review report. A high level of interest has been generated by the review suggesting stakeholders consider the results and data used to be both relevant and valuable for policy discussions and future programmatic decisions. For example, DFID’s new £150m Saving Lives in Sierra Leone Business case, drew on early results from the review and this has influenced programme decisions e.g. substantial investments in refurbishing EmONC infrastructure. These are demonstrable examples of how the review is influencing policy decisions. Value for money of the project is very good.

Assessment of whether the programme represented value for money
Based on the VfM performance comparison to the VfM proposition in the Business Case, the programme has offered value for money. When the circumstances changed because of the Ebola epidemic it adapted its approach, taking forward elements that could be dealt with remotely. The extension period was agreed recognising this and has allowed the required time for all remaining fieldwork and research, to be satisfactorily completed.

Quality of financial management during programme
Total expenditure on the programme is £997,343. This covers £800,220 for the OPML management contract and £197,123 previously spent on the earlier contract with HDRC in 2013, which delivered the inception report before the global contract was transferred to PEAKS. Since the 6-month extension the OPML contract has been changed and milestones with deliverables and dates for meeting them have been the process for managing related finances. Financial reporting has been included in the quarterly narrative with breakdowns of quarterly costs in fees per day and the number of days deployed for individual consultants during the quarter.

Date of last narrative financial report	October 2016
Date of last audited annual statement	30 September 2016

E: RISK (½ page)

Quality of risk management over the life of the programme
The major risk the project faced was taking forward the fieldwork and research whilst there was an on-going Ebola outbreak in Sierra Leone. OPML was able to continue operating remotely and pausing elements of the review that would have required external staff in country. The project was extended for 6 months to end in December 2016, to allow sufficient time for outstanding work to be done that was delayed by the epidemic.

Overall risk rating: Moderate. The key risk around (i) Data quality undermining the validity of recommendations; (ii) a lack of uptake of findings, resulting in limited impact remain valid. It is too early to tell whether these will arise now the review is complete and being more widely disseminated. The mitigation measures listed in the 2016 Annual Review to reduce these were adopted during 2016.
These mitigation measures still remain valid and can be actioned in the future.

Overview of programme risk:
The project made good progress throughout and finished all field work and analysis and has delivered a final report ahead of schedule. The risk of an Ebola epidemic delaying implementation could not have been predicted.

The key lesson for any future evaluation programme is to ensure proper baselines are established to coincide with the start of the programme. This could help avoid questions about data quality in the future. In Sierra Leone contingency plans should be flexible and recognise the need to adapt the pace or manner of implementation in the event of a significant (if undefined) public emergency (like ebola) that can have nationwide impact and adversely affect programme implementation.

Overall risk rating: Moderate
The programme was categorised as a moderate risk in 2016 for the risks mentioned above.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The contract and performance of OPML has been managed by DFID Sierra Leone through an output based contract linked to the Terms of Reference of the review and milestones set out in the contract. Invoices have been paid on satisfactory achievement of deliverables. Although delivery did not go according to the planned timeframe due to 2012 cholera outbreak and 2014 ebola crisis, the 6-month time extension ensured all deliverables were submitted as per the revised schedule. The final review report was submitted in April 2016, ahead of schedule. It is important to record that despite the visit hiatus caused by ebola, some activities were conducted remotely, and this contributed to completing the final report earlier than planned.

Performance of partnership (s)
OPML established an effective partnership throughout and worked well with its sub-contractor, Focus 1000 to deliver the focus group discussions, with senior MoHS officials and DFID. All were kept informed of progress and presented initial results regularly. OPML was also responsive to MOHS requests for capacity building during the period. DFID staff changes and disruption to normal programming during the Ebola crisis caused some institutional memory loss. This was satisfactorily addressed in 2016 when DFID transitioned back to normal development programming.

Asset disposal and value obtained by DFID
There are no assets purchased under this programme.

G: CONDITIONALITY (½ page)

Partnership principles assessment
As the programme did not include financial aid, an assessment of the partnership principles was not required for its implementation and the disbursement of funds. However the evaluation reports that the FHCI has been pro poor and increased the equitable access of health services to poor communities in Sierra Leone. This provides evidence of the government’s commitment to development and equity which is assessed under the partnership principles.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
In 2015 the project was re-named as a ‘Review of the Impact of the Free Health Care Initiative’. This reflected concerns about the absence of baseline data when the project originally started. As mentioned earlier, OPML has used alternative data sources, triangulated results, made greater use of modelling and qualitative data, and interpreted cautiously. OPML has included its assessment of the confidence that it has in its results in the final review report as well.

Monitoring progress throughout the programme
This project completion review was a desk based review carried out by Desmond Woode, Health Policy Adviser for DFID Sierra Leone Basic Services Team (BST), with assistance from Zynab Rodney-Sandy, Programme Manager, BST. Angela Spilsbury, Senior Health Adviser and BST Team Leader is the quality assurer for this review. Monitoring has been done through close analysis of quarterly reports; annual reports; the final review report; policy briefs and compared with the original business case, latest log frame and Terms of Reference.

Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against VfM measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised through the duration of the programme which were not foreseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review and PCR process