Annual Review - Summary Sheet

Tanzania Land Tenure Support Programme
Programme Value: £4,740,000		Review Date: 05 October, 2016
Programme Code: / 202843	Start Date: 20 October, 2014	End Date: 30 June, 2017

Summary of Programme Performance
Year	2014/15	2015/16	2016/17
Programme Score	C	C
Risk Rating	Medium	Moderate

Summary of progress and lessons learnt since last review.

The LTSP business case was approved in October 2014; the original LTSP design anticipated that the inception period of 6 months would start once the technical advisers were contracted. Due to protracted contracting of technical advisers, there was a15-month delay before the technical advisers joined the program in January 2016. The inception phase ran from January 2016 to June 2016. This review is based on the year one milestones.

Summary of progress since the last review
There have been severe delays in delivering against the original logframe, due to delayed recruitment, cumbersome procurement processes, and the change of the Senior Technical Advisor. In addition, there are divergent views between DPs on whether the programme should carry out plot-level adjudication, demarcation and certification (producing Customary Rights of Occupancy - CCROs), or finish its activities at the earlier stage of zoning village land into different permissible land uses (ending once Village Land Use Plans have been produced).
The objectives of the programme are still important for Tanzania, and there are signs of improvement and momentum in the programme that will allow it to deliver effectively against a revised logframe However, to achieve that, a number of actions have to be taken to get things back on track. Positive progress since the last review includes:
- The Program Implementation Unit (PIU) has started some implementation of the three planned outputs; Land tenure regularisation (LTR), Policy and Institutional Development; and improving transparency and the impact of large-scale land deals.
- The PIU team is committed and hardworking, with core seconded staff from the Ministry working well with Technical Adviser (TA) from Land Equity; most of the TA team demonstrates good knowledge of the situation in Tanzania; the Project Coordinator has a more confident grasp of programme activities and has had time to strengthen networks with the Ministry of Lands, housing and human settlements development (MLHSSD).
- Overall, programme activities appear to be well integrated with Ministry activities: the PIU is engaged with the National Land Policy review, Ministry staff have been working on LTR activities and on the baseline survey for the impact evaluation, and demonstrate greater knowledge of LTSP activities.
- The LTSP team has introduced several additional activities, which are not yet fully captured in the logframe and, as such, are not adequately reflected in this review, including:
- Design and piloting of a large farm survey to improve the quality of the data to be published on ownership and conditions of farms over 50 acres in Tanzania, key to achieving Output 3;
- Translation of two land-related Acts into Kiswahili to make them more accessible to Tanzanian citizens; and
- Design and implementation of an impact evaluation study, including a baseline survey, which is currently being piloted, essential for monitoring the outcome and impact of the LTSP.
Lessons learnt:

PIU capacity and planning, and lines of accountability: the difficulties in starting up the LTSP, and the delays in recruitment and procurement indicate that DPs needs to be realistic about the start-up time needed for programmes that are integrated into government systems, and need to build inception phases into log frame. Lines of accountability for all involved in programme implementation need to be very clearly defined to ensure that someone is fully accountable for the success or failure of the programme, and that the roles of technical advisors are clear to all. The programme will require closer management and support to ensure timely delivery of results.
- Level of systematic engagement of the DPs to LTSP: there appear to be different levels of commitment and engagement of the three DPs with the programme and with each other. Some of the DPs do not respond quickly to reports issued by the PIU, which makes it hard to produce a combined set of responses to the PIU; in addition, there appears to be different levels of understanding of the operations of the programme and these has led to contributed PIU delays in decision making.
- The relative weighting of VLUPs and CCROs: not all the DPs are contributing financially to the LTSP support doing systematic LTR across the three districts to issue 300,000 CCROs. This resulted in suspending disbursement for the part of the budget allocated to issuing CCROs, pending more information on the cost structure and resolution of the focus on CCROs; this has caused uncertainty for the programme and delays in starting this part of the LTR activities.
- Clarity on the objective of the programme: Conflicting pressures on the objectives of the programme have been present since the design phase, both from government and DPs. More open and timely discussion between the DPs and between the DPs and the government could have minimised this issue.
- The role of the technical assistance service provider: it is important for the PIU to be able to draw on a range of experiences and practices both from within Tanzania and outside to inform how it approaches and designs its activities, and this is a core function of the technical assistance. Where this knowledge falls outside of the area of core expertise of the technical advisors, it will be important for the service provider to support further by inputting information based on its deep knowledge of Tanzania’s land sector and institutional memory, sharing lessons, carrying out analytical tasks and providing quality assurance of outputs. This review identifies several areas where further support is needed; including bringing expertise with comparative experiences (both from within Tanzania and from other countries) on developing cost-effective land tenure regularisation methodologies. Also, providing additional analytical capacity in certain areas to ensure these are completed on time and to a high standard of quality (e.g. setting up the M&E framework; analytical frameworks and identification of studies).
Summary of recommendations for the next year
- Logframe review: Building on the review of the inception phase and recommendations from this Annual Review, revise the logframe to address shortcomings highlighted in this review and to adjust output indicators and activities to take account of delays to date and the proposed extension of the programme timeframe. This review needs to decide whether the logframe should introduce the establishment of VLUPs as a separate output, rather than as an activity under Output 1.
- Technical assistance service provider should bring more active engagement to make the PIU’s operations draw on high quality analysis and perform its activities efficiently.
- Procurement: DP should consider to undertake the direct procurement of large bundles of high value goods and services (e.g., the supply of high-resolution satellite imagery - HRSI) to avoid delays in the government procurement service.
- Objective of the programme:
- PIU and DPs should ensure that the programme keeps focused on testing innovative, cost-effective LTR methodologies rather than becoming too focused on the number of CCROs that it issues.
- Come to a resolution about the relative weighting of village land use plans (VLUPs) and CCROs to prevent further delays in LTSP, clarifying the relative arguments and ensuring that the choice is based on robust, significant evidence.
- Engagement of DPs: positive engagement of DPs with the LTSP and with each other needs to increase to provide greater oversight and understanding of the programme, and to present a common position when discussing issues with the PIU.
- Financial management and project governance: review planning capacity in the PIU as well as clarity over lines of accountability and delegation of authority, possibly introducing Key Performance Indicators (KPIs) as part of reporting.
- How best to reflect progress: the LTSP’s current logframe does not adequately capture the extent of progress made over the past year. Following this annual review, drawing on findings from the review of the inception phase carried out in April 2016, the programme will need to undertake a detailed review of the logframe.
- Value for money: Establish clear metrics and milestones for assessing and monitoring value-for-money across the programme (and for LTR activities specifically) and use M&E system to monitor these.
- Technical assistance: review expectations of TA, including the value for money provided by the current level of assistance and the performance incentives in the contract between the service provider and the government. Agree on KPIs for the future.
- Change the timing of annual review years and programme implementation years in the logframe to reflect on the GoT budget circle which is June - July
A. Introduction and Context

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-202843/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202843/documents

Outline of the programme
The three-year land tenure support programme (LTSP) will tackle weaknesses in the land administration system that constrain efficient delivery of land services and good governance, targeting processes of how land certificates are issued to rural and urban citizens, and how land is leased to investors. The programme will support the Government of the United Republic of Tanzania (GURT), through the Ministry of Land Housing and Human Settlements Development (MLHHSD), to make information on land records and processes of land allocation publicly available, and clarify and address current constraints to protecting legitimate land claims. Ultimately, these measures are expected to strengthen security of tenure, contributing to growth in agricultural production, and more and better-planned investment in urban infrastructure, including housing. The programme has introduced a multi-stakeholder group (MSG) to strengthen civil society oversight of government services and actions in the land sector, and coordination between government, civil society and private sector actors. DANIDA is facilitating the design of an additional programme to support civil society organisation (CSO) engagement in the MSG.

The programme will also improve the cost-effectiveness of surveying and adjudicating land, and issuing certificates in two target districts, which will create cost savings for future rollout of national implementation of land laws.

The programme’s intended impact is to increase confidence to invest for all landholders in Tanzania. The main expected outcome is more transparent and accountable land governance, and effective land administration systems in Tanzania. This outcome is expected to lead to more secure tenure and will result from three outputs:

- Output 1: Proven low cost and equitable land tenure regularisation implemented in three districts – benefitting an estimated 300,000 landowners.
- Output 2: Policy and institutional framework strengthened (including the creation of a MSG in line with GURT’s international commitments on land governance)
- Output 3: Transparency improved and greater benefits from investment for all land use right holders (including the publication of data relating to existing and future large-scale land transactions).

Change in Context[1]
[1] This section partly draws on the LTSP inception report.
Since the elections in October 2015, there is a new Minister for Lands, along with a new Permanent Secretary, and other changes in personnel. The President and ruling party (CCM) made strong manifesto commitments on land issues, and focussed all strategies towards independence from donor and a renewed focus on transforming Tanzania to a middle-income country by 2025. From December 2015, major land conflicts have arisen, markedly between agriculturalists and pastoralists, especially in Mvomero and Kiteto.
There is a new proposal for a Ministry of Lands organogram with — as the Law dictates — a more central role for the Commissioner of Lands and the MLHHSD is also developing a new corporate Strategic Plan, funded through the World Bank funded-Private Sector Competitiveness Project (PSCP). In parallel, in early 2016, the government launched a review of Tanzania’s 1995 Land Policy, which underwent a national public consultation exercise and is currently under review. It also recently established a Land Investment Unit, aimed at promoting land-based investment in Tanzania through improving the quality of land data, registering all data and records on large-scale investment around the country, and keeping track of land values.
Alongside these broader events, USAID has launched a new programme – the Feed the Future Land Tenure Assistance activity – to support registration of rural land in two districts (Iringa and Mbeya) in Tanzania.

Two initiatives focusing on agricultural investment have started:
- Landesa’s RIPL – DFID funded initiative which is working with TNRF, a Tanzanian NGO, to develop a Tanzania-specific guide on how to realise responsible investment in land.
- The Partnership for Accountability Commitment, formed under the New Alliance, is a partnership of government, private sector, donors and non-state stakeholders, seeking to enhance the policy environment for agricultural investments in Tanzania, and is chaired by the Prime Minister’s Office. One of its main activities this year is to seek ways to enhance access to land, while reducing land-related conflicts including by accelerating land titling and registration.

B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The outcome will not be achieved within the original timeframe envisaged by the Business Case due to delays in the start-up of the programme and some ongoing delays since the inception period. The programme end date — originally scheduled for June 2017 will need to be extended until June 2019 for the programme outcome to be achieved. Improved planning by the LTSP team and MLHHSD and clear, coordinated action by the DPs will also be necessary.
Overall output score and description

The overall output score is C: Outputs substantially did not meet expectations.
This is partly due to a mismatch of output indicator milestones with the real timing of the programme launch and implementation. It is also partly due to delays with procurement and planning of activities, some of which have arisen as a result of disagreements over the main objectives of the programme.
Key lessons

- Planning: DPs need to be more realistic about the start-up time needed for Financial Aid programmes operating through government systems, and be prepared to adjust milestones accordingly.
- Partnerships with other DPs: It would be good to nominate a lead DP to engage with the PIU, representing the views of the group of DPs; collaborating DPs need to engage frequently with one another, having regular meetings to ensure a common understanding of the programme.
- Procurement: as recommended in the first Annual Review, DPs and PIU should undertake proactive assessment of procurement options for forthcoming needs; this is being discussed with respect to the purchase of high-resolution satellite imagery (HRSI) and will be a model to be monitored closely for any future lessons.
Key actions

Logframe revision: revisit output indicators and milestones taking into account the issues raised in this AR. lead – PIU with support from external service provider or LEI Head Office, and in consultation with DPs.

Performance of the PIU: scrutinise and improve the PIU’s approach to achieving targets, and overall planning. Time – six months as part of the improvement plan; lead – DFID

Programme objectives and messaging: clarify programme objectives and ensure that messaging on this is consistent from all stakeholders involved. lead – DFID, SIDA and DANIDA with PIU.
Has the logframe been updated since the last review?

At the time of the last Annual Review (October 2015), annual milestones for the logframe had not been established as this was put on hold until the start of the programme inception phase. Initial milestones were set during the inception in January-June 20016. However; many output indicators remain unrealistic given the current progress of the programme. The logframe needs to be urgently updated and approved, especially for Output 1, where milestones need to reflect intermediate steps in strengthening village land institutions. In addition, impact weightings for the outputs need to be revised.
C: DETAILED OUTPUT SCORING)

Output Title	Proven low cost and equitable land tenure regularisation implemented in two districts – benefitting an estimated 300,000 landowners.
Output number per LF		1		Output Score	C
Risk:		Moderate		Impact weighting (%):	34
Risk revised since last AR?		N		Impact weighting % revised since last AR?	N
Indicator(s)		Milestones	Progress
1.1 Number of parcels demarcated, adjudicated and registered in ILMIS (or equivalent) in target areas		50,000	The sequence of activities leading to parcel adjudication has begun. Village Boundary Surveys and rehabilitating village registries is underway. District Land Use Framework Plans have been developed for Kilombero, Ulanga and Malinyi, but no Village Land Use Plans or parcel adjudication activities have begun. If suggested revisions to project year and milestone target are accepted, and no more delays occur, the programme may reach this milestone by mid-Year 2 of implementation (June 2017)
1.2 % households collecting title		95%	No titles issued yet – see above.
1.3 % of those registered as land owners in target areas that are women, disaggregated by female headed households and co titling with husband		25%	No titles issued yet – see above.
1.4 Average cost (of production) of title		US$20	No titles issued yet – see above.
1.5 % demarcation and adjudication complying with programme social safeguards		100%	No demarcation and adjudication carried out yet – see above. Safeguards to be determined.
1.6 % decrease in number of land disputes in villages compared to baseline in target areas		30% below	No titles issued yet – see above. Baseline data on land disputes needs to be collected.

Key Points
The LTSP inception report that came out June 2016 highlighted the challenges associated with delivering LTR, such as the need to streamline processes to control costs and quality, provide accurate and consistent messages to stakeholders, and decide the price of CCROs to ensure households collect and use these. It also suggests a number of entry points for how the programme will address these challenges. Proposed activities include: gaining institutional buy-in for using a general boundaries approach for adjudication, developing a manual of operations for field activities setting out standards and approaches for all LTSP activities, delivering training, hiring local staff, providing support on Land Use Planning, GIS and carrying out quality control.[2]
[2] LTSP Inception Report (2016) pg. 45
Progress since the inception period
The delivery of activities in output 1 has fallen substantially behind schedule. Delays stemming from the disagreement about the balance between VLUPs and CCROs coupled with slow procurement have affected activities under this component. The impact of these delays is that the programme will miss its Year 1 (December 2016) targets to deliver any CCROs. If the programme adheres to the latest proposed sequence and timeline (September 2016), it is likely the programme will deliver a smaller number of CCROs by mid-2017. As of September 2016, the programme and DPs were discussing the option to reduce the planned number of CCROs in Year 1 from July 2016 –June 2017 to 25,000. Slow procurement has also delayed the start of intermediate activities, including the baseline survey, and demarcation of village boundaries.
The programme is contracting service providers to undertake these activities, and procurement through the MLHHSD’s procurement system is taking longer than the programme originally anticipated. In response, PIU has divided the workload and created a first phase of activities in a subset of 48 villages and agreed with the MLHHSD’s procurement department to fast-track procurement for this work by contracting the Ministry’s staff. Where it has moved ahead, work is being delivered successfully and to schedules agreed, and underpinned by strong budgeting and planning. Planned activities that have been partially or fully delivered include:

Activity	Responsible entity	Status -September 2016	Further information
Development of District Land Use Framework Plans for 3 districts	Contracted to the National Land Use Planning Commission (NLUPC)	Completed – awaiting final approval by District Councils before frameworks are gazetted.	NLUPC collated all information on land use and available public services in each district.
Procurement of materials for public awareness for VLUPs and CCROs	PIU, through tender	In progress: ToRs for awareness materials have been prepared, and materials have been acquired and disseminated to the districts.
Village Boundary Survey (VBS) in 48 villages	Contracted to MLHHSD’s Survey and Mapping Directorate.	In progress: VBS sensitization meetings - 23 villages / -Boundary demarcation - 4 villages. / - 61 Control Points established.
Procurement of satellite imagery	PIU	In progress: TORs for imagery have been prepared. / - Analysis by PIU of costs for using UAVs suggested that satellite imagery is the preferred option. / - PIU and MLHSSD agreed to use DP procurement for satellite imagery.
Procurement of materials for CCROs	PIU	In progress: A contract to acquire materials to produce 170,000 CCROs has been finalised and awaiting signature.
Land registry IT system	PIU	In progress: the MLHHSD’s Directorate of ICT is designing the system.	The PIU is ensuring its system will be compatible with the ILMIS database through consulting the ILMIS database manager

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A
Recommendations:
- Resolve uncertainty over whether the programme will title individual plots: DPs and PIU should come to a resolution about the relative weighting of village land use plans (VLUPs) and CCROs to prevent further delays in LTSP, clarifying the relative arguments and ensuring that the choice is based on robust, significant evidence. Develop a model cost saving methodologies on LTR through innovative methods: PIU should prepare forecasts it will bring down costs of LTR activities in line with programme targets. Analysis should be presented in a discussion paper that sets out the activities involved and cost drivers, and explains what is and isn't included in costing. This should then set out pathways for cost-reduction and comment on opportunities and challenges of different options, and any support the programme will need from MLHHSD leadership to trial practices that may contravene current regulations or practices. The cost reduction LTR due to innovations should be reflected in unit costs expected towards the programme's objective in Year 3. e).
- Carry out study on the nature of land conflicts, and seek information on costs associated with conflicts: findings from the PIU's commissioned study on conflicts should be extended to research financial losses associated different types of conflict, experienced through losses to household activity (e.g. crop losses, foregone planting, litigation expenses and/or foregone investments) to build an understanding of the frequency and magnitude of conflict-related economic losses. Similar questions should be considered for insertion in the Baseline Survey. Revise logframe to incorporate intermediate steps: building on the review of the inception phase and recommendations from this Annual Review, revise the logframe to address shortcomings highlighted in this review and to adjust output indicators and activities to take account of delays to date and the proposed extension of the programme timeframe. PIU and DPs needs to decide whether the logframe should introduce the establishment of VLUPs as a separate output, rather than as an activity under Output 1.
- Communications, public awareness and sensitisation: as proposed in the inception report, the PIU should identify a set of key messages to communicate. These should focus on what the programme is doing, and what villagers in target areas should expect to get from demarcating and certifying their land. When discussing CCROs, these messages should explain clearly the low likelihood of using CCROs to access loans. The PIU should also consider sharing information on what conditions villagers will need to meet to access loans from  neighbouring banks. The PIU should ensure that all staff carrying out work on behalf of the programme know, and use, these messages. This should include staff carrying out sensitisation for ongoing activities. If these do not yet exist, the PIU should develop scripts that all frontline staff use. Timing – as soon as possible; lead - TL LTR and Communications Expert. This should not await procurement of the communications strategy or any other public awareness services.
- Monitoring of messaging should be included in the M&E framework. Timing: in line with development of M&E framework; lead - M&E TA.

Output Title	Policy and institutional framework strengthened (including the creation of a Multi Stakeholder Group in line with GoT international commitments on land governance)
Output number per LF		2	Output Score	C
Risk:		Moderate	Impact weighting (%):	33
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Multi-stakeholder group established and operating effectively (i.e. senior representation with constituency fully represented)	Composition agreed, ToRs adopted and at least 3 quarterly meetings conducted. / Draft policy on Climate Change included in revised land policy.	Composition agreed – organisations identified; ToRs drafted and approved by LTSP Steering Committee; ToRs to be approved by 1st formal MSG meeting (planned but awaiting final nominations of individuals from TALA/World Bank). / Three meetings held so far between PIU and CSOs to launch the MSG. / No evidence of draft policy on climate change being included in revised land policy.
2.2 Necessary changes in legal, policy and institutional framework to safeguard tenure security, and clarify land allocation/transfer procedures implemented	Changes identified and agreed with MSG/NLAC and other stakeholders	Some changes identified through National Land Policy review; to be discussed with MSG during 1st meeting. Themes for 11 possible studies identified for discussion at MSG and included in the budget.
2.3 Climate change and resilience incorporated into national and local land use planning procedures and policies	Policies reviewed and key stakeholders identified	None to date. Acknowledgement by PIU team that connections need to be made with the relevant Ministry. NLUPC also interested in including in land use planning guidelines.

Key Points
Activities in this area started since the last Annual Review and have gained momentum following the inception review. Key actions include:
- The LTSP Policy and Institutional Development team are now in place with the recruitment of a technical advisor in February 2016 and the team lead in June. The team is closely engaged with the National Land Policy (NLP) review: the team lead is a member of the Secretariat formed by the MLHHSD to review the NLP. The team is in contact with other legal reform initiatives, particularly the review of the Tanzania Investment Act, where the MLHHSD is represented by the Land Investment Unit lead.
- The MSG has been formed: the composition was agreed by stakeholders through a series of (three) meetings to comprise nine organisations from GURT, Development Partners, civil society and the private sector:
- GURT: Ministry of Lands, Housing and Human Settlements Development (two representatives), President's Office Regional Administration and Local Government, Ministry of Agriculture, Livestock and Fisheries, and Ministry of Natural Resources and Tourism;
- Development Partners: World Bank;
- Civil society: Tanzania Land Alliance (TALA), Action Aid International Tanzania.
- Academic institution: University of Dar es Salaam – Faculty of Law.
- Private sector: Tanzania Chamber of Commerce and Agriculture (TCCIA).
- Individuals have been nominated from all member organisations and the 1st formal MSG meeting took place on September 29, 2016. To date, the PIU has struggled to get timely responses from TALA to involve them in the MSG and other activities. This is a key concern given that TALA is the main representative of land-related CSOs in Tanzania; this could affect programme performance negatively and is not under the control of the PIU
- The MLHHSD is in the process of creating the National Land Advisory Council (NLAC) with the idea that the MSG will act as a technical working group to feed ideas into NLAC. In principle, the Ministry’s Permanent Secretary will act as the link between the MSG and NLAC, and it will be important to monitor how this works in practice.
- The PID team has created a rough list of 11 studies to analyse issues in the land sector that may require legal and policy changes. There are great windows of opportunity for adding value and inform changes in the legal and policy framework opening up with the NLP review and review of the Tanzania Investment Act. The challenge will be to develop the planned studies and get the MSG working effectively in time to take advantage of those windows. The themes of the studies would benefit from detail and background on their need, as some seem better defined than others, and some seem to overlap (e.g. two studies on guidelines for investment in land).
- The Ministry Directors did not sign off output indicator 2.3. The PIU team is identifying the relevant Ministry to launch work on this and have also started discussions with the National Land Use Planning Commission (NLUPC) about including climate change issues in land use planning guidelines; the NLUPC have expressed interest in this.
In addition to activities planned in the logframe, the PIU identified the need to translate two relevant Acts into Swahili: Land Act No.4 of 1999 and the Land Disputes CoGOT Act No. 2 of 2002. Printing for the Land Disputes Court Act will start on 31st October, 2016 and for the Land Act on 15th November, 2016.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A – no recommendations were made in the first Annual Review.
Recommendations
- Logframe revision: Reduce expectations for Output indicator 2.2, prioritising no more than four studies and aligning these with the proposed timing of the next steps of the review of the NLP – a review of the legal and regulatory framework. Proposed new indicator: commission four studies to provide evidence on key issues for influencing discussions on the legal and regulatory framework for land.
- In addition, Output 2.3 – commences formal discussions with the NLUPC and incorporates climate change issues into Guidelines for Land Use Planning. Include this as an indicator in the logframe to be able to push for the review of the Guidelines as a delivery. Review progress of the CSO support programme: To increase the capacity of TALA to participate in the MSG, and other activities, the CSO support programme that DANIDA is leading will be important to the success of the LTSP and needs to be up and running as soon as possible. During the inception review, the financial agreement was due to be signed in May 2016; this has still not been done. lead - DANIDA.

Output Title	Transparency improved and greater benefits from investment for all land use right holders (including the publication of data relating to existing and future large scale land transactions)
Output number per LF		3	Output Score	C
Risk:		Minor	Impact weighting (%):	33
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 % of existing and new large-scale land acquisitions with key information available in a public database (information to be defined through MSG)	50%	Original data not published; new data collected in 7 districts in Morogoro to establish survey design and methodology.
3.2 Guidelines for roles and responsibilities of investors, government and villages approved by MSG and implemented across government	Draft produced and consultation begins	Engaged with LIU, which has mandate to take this forward.
3.3 Benefit sharing model developed, and agreed by stakeholders and reflected in all relevant projects and tenders	Options prepared and analysed, consultation begins	ToR for study prepared and consultant identified.

Key Points
Activities during the period under review (Oct. 2015 - Sept. 2016)
- Inventory of large farms conducted in seven districts of Morogoro; undertaken by the MLHHSD with LTSP funding and engagement in collaboration with the National Bureau of Statistics and the World Bank. Data is currently being verified by the World Bank to lay the foundation for rolling out the survey across the rest of Tanzania, subject to additional funds becoming available from DFID. There are clear intentions to publish the data once all has been collected and verified. If funding is made available quickly, the aim is to finish the survey in the rest of Tanzania by the end of this calendar year; data should be available for publication in Year 2 (October 2016-September 2017). It is important to note that this activity originally intended only to facilitate publication of existing data. The LTSP has acted as a catalyst for a more rigorous, systematic survey of large farms generating more accurate and up-to-date information on large farms than originally envisaged.
- The LTSP team is connected to the head of the LIU to discuss investment guidelines, and there appears to be the opportunity to influence the Tanzania Investment Act through this. However, two sets of guidelines are budgeted for and it is unclear that there is a significant difference between the two types of guidelines. It appears that they are directed at different types of investors.
- Benefit sharing models: the PID team has prepared ToR and identified a consultant. There is solid work that has already been done on benefit sharing models and compensation for land in Tanzania funded by USAID[3] that could provide a shortcut or greater value for money for the LTSP.
  [3] Approaches to Agricultural Investment Models, Valuation and Support for Local Communities in Tanzania, September 9, 2014
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A – no recommendations were made in the first Annual Review.
Recommendations
Logframe revision:).
- Identify more milestones that are appropriate for Output 3.1 in current logframe that the LTSP team is using in order to reflect the ongoing process and the role that the LTSP has played in catalysing a more rigorous, systematic survey of large farms.
- Clarify the types of investment guidelines to be produced and revise timeline, to take into account delays in starting the LTSP, and identifying the link with the review of the Tanzania Investment Act.
- Revise milestones for output indicator 3.3 to take into account delays in starting the LTSP, and possible availability of good quality information on benefit sharing models.
Large farm survey: resolve issues blocking finance of the rollout of the large farm survey across Tanzania to ensure that this can be launched before the rainy season starts.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

Actual spending
Delayed programme implementation and slow procurement has meant that spending against forecasts has been low. From October 2015 - July 2016,[4] the spending on non-management activities has been 19% of disbursements made against forecasts for these activities. The largest area of spending overall and the highest budget items have been on management and administration.
[4] This covers the period since the last annual review. Financial statements for the latest quarter (July-September) are not available at the time of the review.

Top 5 cost items: all costs (October 2015 - July 2016)	Cost (US$)
Management company	359,997
Motor Vehicles	257,849
PIU Staff costs	106,303
Office running costs	124,536
Recruitment cost	25,080

Top 5 cost items: non-management costs (October 2015 - July 2016)	Cost (US$)
District Framework plans	51,273
Public Awareness (specific for CCRO)	31,973
System Development	20,638
Equipment and Data (imagery, software and material)	18,149
Linking field data to map (for large farm survey)	14,627

Spending on activities compared to management is expected to have increased over the most recent quarter (July – September 2016). However, ongoing delays in procurement indicate that spending will continue to fall short of forecast Year 1 spending in the programme budget.

Forecast spending
For Year 1 and subsequent years, the largest share of spending is on Component 1 activities (which contribute to Output 1). Over the three years, Component 1 activities account for around 49% of spending; Component 2 accounts for 13% and Component 3, 10%. Administration and management account for the remaining 25%.

Within Component 1, the budgetary value earmarked for delivering CCROs is around 35%. This is the highest overall budget category. Activities leading to the production of Village Land Use Plans account for 11% overall. Since all VLUPs will be delivered in Year 1, 27% of the Year 1 budget spent on VLUPs compared to 20% of CCROs.

The cost of adjudicating between parcels of land and issuing CCROs is the highest cost activity within the programme and therefore represents a major cost driver.
Within this, the systematic adjudication activity will cost around TZS16 million for a village with 1,500 parcels, or around 50% of the total activity (see Figure 1 below).

Figure 1: Costs associated with adjudication for CCROs in villages

VfM performance compared to the original VfM proposition in the business case

Overall VfM proposition for LTSP is to improve efficiency in the MLHHSD by reducing operating costs across their services that will lead to reducing cost of the participatory land use planning and titling process in line with international benchmarks. However, due to delayed delivery and limited spending, the programme’s ability to deliver value for money against major spending categories remains untested and unproven.

Given the delays in setup and delivery, during the nine months since the last annual review (October 2015 – June 2016) 85% of PIU spending has been on administration and management[5], with 15% on activities. Spending on activities is expected to have picked up in the last quarter but is still restrained given delays caused by discussions on the programme’s direction and procurement issues.
[5] Administration cost include technical company charges and procurement of 4 field vehicles

The PIU has yet to formally identify and track VfM indicators for activities and outputs, and this should be considered an important priority for the programme given part of its objective is to deliver land parcel adjudication, demarcation and certification at low cost. Examples of where the programme has achieved VfM in the activities to date include:
- The PIU negotiated down the costs for carrying out village boundary surveys with the MLHHSD’s Department for Surveying and Mapping. The major change to specification included putting placing beacons every 1500m instead of 500m. The Program Coordinator also highlighted that Ministry (rather than project) vehicles are being used for activities in Dar es Salaam, which has saved costs to the programme. Ministry vehicles were used for the exercise (six out of nine vehicles).
- Through tendering instead of direct procurement, the PIU has reduced the cost of purchasing sensitisation material, including copies of the land laws.
- Villages have to either build their registry or renovate it to a certain standard before receiving money from programme to complete the renovation; this guarantees a level of commitment from the villages and effective use of resources.
- The PIU also plans to reduce costs in future activities through combining some activities in the field, or reducing reliance on Ministry-level expertise and relying instead on district level officials as these become trained and familiar with processes.
- While the current plan is to deliver the first phase activities using existing methodologies, and then seek to reduce these costs for future phases, there are some areas where the PIU could trial lower cost approaches immediately.

Exploring lower cost methodologies for parcel adjudication / As discussed in the section above, adjudication and demarcation of parcels represents a major cost driver for the programme. One of the major cost items within this activity is the high number of days of land officers and other government staff are remunerated with additional allowances for their time in these activities, either in the field or in the office. Under baseline estimates, adjudication of an average village involves around 252 person days for official staff (from districts or the Ministry). The costs for transporting these staff members to and from villages each day also represents a substantial direct (16%) and indirect cost. Although the PIU estimates costs for these activities will fall over time as teams become familiar with the process and junior adjudicators are trained, it is yet to model how these costs will fall over time. / Modelling testing methodologies for adjudicating and demarcating parcels should be considered an immediate priority for the PIU, given this is one of the programme’s main original aims and an action flagged in the programme’s risk assessment. It will important to develop VfM indicators around this, and monitor and report against these.

Assessment of whether the programme continues to represent value for money
The programme has underspent compared to forecasts at the time of the last annual review and after the inception period. However, Program is expected to deliver value for money in line with the original proposition rate of spend has picked up since last quarter (June - September) due to increases of field activities. In addition, district-specific information is now obtainable for some of the variables that underpin the VfM proposition (level of conflicts, agriculture value added etc), it is suggested that the programme update its VfM analysis and projections.
Quality of financial management
The inception review identified concerns regarding the state of the programme’s budgeting and forecasting which raise concerns over the PIU’s ability to maintain accurate records of the programme’s financial position. As the LTSP uses the government financial management systems and these receive periodic reviews and audits, neither the inception review nor the current annual review looked in depth at the financial management systems and processes.. On 29th July, the GOT Controller and Auditor General conducted a spot check of LTSP’s cash management in the year to 30th June. The spot check uncovered no irregularities. DP are discussing the most appropriate timing for any fGOTher analysis of the financial management systems.
The review of the inception period found concerns over preparation of the programme’s main budget, which shows spending to date and forecasted expenditure, and which is discussed at management meetings. . The version of the budget that was presented to the team contained substantial errors. For example, during the inception review it came to light that expenditure incurred before the programme’s official start (including rent and staff costs) had not been included into the overall budget, and forecasted costs for office running costs were well in excess of actuals. This was rectified quickly. The inception review included specific recommendations to improve budgeting, and recommended a mini-audit was carried out on the PIU to identify where improvements are needed in systems and processes. As discussed above, a CAG audit found the systems for cash management were in order.
The annual review found that while recent changes have improved the programme budgeting, the budget continued to exhibit problems suggesting the PIU needs to sustain attention to ensure this serves as a solid basis for discussions of the programme’s planned activities and performance. Practices that continue to frustrate effective communication over budgets include unclear explanations for changes to budgets, sending of budgets later than agreed in advance of meetings and without explanations of proposed changes to budget items, and lack of record keeping of previous versions of budgets The Programme Coordinator is aware of these challenges and has sought to address these through deputising preparation of budgets and quarterly financial reports to the Team Leader for PD. This is a welcome interim measure, but the situation should be monitored to ensure this responsibility is not a burdensome distraction from the PD Team Leader’s core responsibilities

Date of last narrative financial report	June 2016
Date of last audited annual statement	None to date.

E: RISK (½ page)

Overall risk rating: High

Overview of programme risk

The programme is judged to be of high risk. The risk assessment and mitigation strategy set out in the LTSP business case identifies 17 risks to successful programme implementation. Key risks includes delays due to slow procurement, disputes in areas of field operations, the availability of spatial infrastructure the programme could use and input data into, such as the new geodetic network and Integrated Land Management Information System (ILMIS). The review noted 12 risks mitigations has been partly implemented , 2 mitigation risks has not been implemented at all, while 2 risks are no longer valid. However, while the programme has gained from strengthened delivery mechanisms and gained good political buy in from the government, the program risk is still deemed as medium, the AR has highlighted a new number of challenges and risks facing LSTP, and offers recommendations that seek to mitigate those risks.
- Protracted lack of clarity over the programme's objectives delay progress and undermine attempts to establish M&E objectives
- Poor budgeting and unclear communication over the budget leads to delay activity approval and undermines confidence in the PIU's capacity

Outstanding actions from risk assessment
The risk assessment still contains a number of outstanding actions that DFID should urge the programme to undertake. There is need to continue to monitor key risks and the effect of mitigating actions.
F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is behind its planned timeframe according to both the original DFID logframe used in the last AR and against the more recent timeframe established in the Inception Report.
Against the most recent version of the work plan (September 2016) certain activities that were planned to have commenced have yet to start, including public awareness, imagery acquisition, GPS tool acquisition, and under this work plan, work on adjudicating and demarcating plots for CCROs will start in January 2017 and finish in June 2017.
Severe delays in delivering against the original logframe mean that the LTSP will not achieve expected outputs by June 2017, the original end date in DFID’s Business Case.
Performance of partnership(s)

DFID and GoT
The partnership between DFID and the Government of Tanzania is working well in general; The DFID team is in regular contact with the LTSP team including participating in the field visit to LTR sites in September 2016. There may be a need for closer engagement and scrutiny over financial budgeting and planning of activities. Some issues have been created by unexplained or unexpected changes in the LTSP budget presented to DFID and the other DPs involved; this has undermined trust in the PIU leadership.
DFID, SIDA and DANIDA:
There have been some very recent signs of improved coordination between the DPs – particularly with the involvement of Heads of Cooperation – but this is an area where substantial improvements could be made. There is some evidence indicating that the three DPs do not operate in close coordination with each other, with different rates of response to documentation coming from the PIU, and different positions with respect to particular aspects of the programme (see discussion on the relative weighting of VLUPs and CCROs). This creates difficulties for the PIU in terms of understanding where DPs priorities lie and who the main point of contact is for the DPs. In similar programmes with basket funding, the DPs are represented by a lead DP in order to prevent this occurring and this is something that could be considered in this case. However, in order for this to happen, the DPs will need to agree a common position on VLUPs and CCROs, and on the issue of salaries to PIU staff.
Technical advisors, MLHHSD and DPs:
The international programme management company has been in place since January 10, 2016. The Senior Technical Advisor (STA) to the LTSP resigned in July 2016, citing problems with the working conditions and the relationship with the Project Coordinator in the PIU. A new STA joined the LTSP in August and there are indications that this relationship has improved. The TA and core PIU staff appear to work well together with a friendly yet professional atmosphere in the PIU office. As mentioned above, the PIU would benefit from greater interaction with Head Office staff from LEI who can bring a range of international experience to complement the experience and knowledge in the PIU TA.
Asset monitoring and control
All assets are procured as per the annual procurement plan and government procurement regulations. PIU is following instructions in the Program operation Operational Manual for monitoring assets which requires Fixed Assets Register to be updated annually .In addition PIU office is not part of the Ministry, there is a low risk that programme assets are mixed up with those in the ministry.

G: CONDITIONALITY (½ page)

The MoU between DFID and Government of Tanzania requires ongoing commitment by the Government to Partnership Principles namely
- Reducing poverty and achieving the MDGs;
- Respecting human rights and other international obligations; and
- Strengthening financial management and accountability, which reduces the risk of funds being misused through weak administration.
- A commitment to strengthening domestic accountability

In the context of this programme, particular attention is on respect for the legal, economic, social and cultural rights of poor landowners, and women. Based on this Annual review, there was no deterioration on partnership principles.
H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
CCROs and access to finance
Evidence from a new journal article (Stein et al. 2016) confirms the weak linkages between issuing CCROs and access to additional finance. Reviewing the two main systematic titling efforts undertaken in Tanzania in the mid-2000s — MKURABITA and the World Bank's PSCP programme — the authors found that, although these programmes' public awareness campaigns promised access to finance as one of the benefits of a CCRO, there is no evidence that banks accepted any of the CCROs alone as collateral.
The authors found that "As a prerequisite to obtaining a loan, an applicant must be able to demonstrate that he or she has had a savings account at a bank for at least six months, with a minimum balance of Tsh 100,000 (= USD$65 at the time of interview). In addition, the applicant must undergo two property value assessments (both an internal and outside assessment), must produce cash flow and asset statements following a visit by a loan officer to his or her property, and produce a business plan".
The continued existence of these conditions was confirmed in the AR mission through interviews with NMB bank managers in Kilombero (Ifakara) and with NMB's Head of Business Lending in Dar es Salaam. Stein et al.'s (2016) findings indicated that rural households in the target areas researched had low access to formal savings (around 4.2%), and thus failed to meet the first condition. Among their sample, farmers that have accessed loans have been richer, more commercially oriented (e.g. employing farm labourers), and grow cash crops. Discussions with the Ifakara NMB manager confirmed that lines of credit exist for organised out growers with confirmed buyers.
These findings do not undermine the original rationale of the business case or the design of the programme, which did not consider access to credit a likely outcome or impact from the programme. Nor does the cost-benefit analysis in the business case assume additional access to credit in its calculations of benefits.
However, these findings suggest it is imperative that the programme tightly controls all messaging during public awareness campaign on the benefits of CCROs. The programme should seek to ensure that all communications on the programme accurately convey that, unless villager meet the bank's other set of conditions, they will be unable to access additional finance using CCROs.
CCROs and conflict
Underpinning the rationale of the LTSP is the assumption that CCROs will increase individual security of tenure and that this will reduce the likelihood of conflict. This has the combined effect of encouraging landholders to invest more in their land, confident in the expectation that they will continue to hold the land, while reducing the frequency and severity of disputes, itself a drain on landholders’ time and resources. Testing this assumption through the impact evaluation study is key to measuring the outcome and impact of this programme, and to deciding the relative weighting of resourcing VLUPs and CCROs.
Planned evaluation
During the inception period, the LTSP team introduced an additional activity — a baseline survey and subsequent impact evaluation. While this had been part of the original discussions for the programme design, it was felt at the time that this would need to be resourced independently, and it is to the credit of the LTSP team that they recognised the need for this and allocated resources to it.
While the procurement process meant that this activity was going to be delayed, the LTSP team negotiated the possibility of procuring a pilot bridging exercise to be able to start the baseline survey, using staff and students from Ardhi University, with oversight by senior officials from the MLHHSD. So far, the baseline survey is underway in 37 villages of the three target districts, and the evaluation of bids for the rollout of the survey is nearing completion.
There has been good progress in the field with the baseline survey, and fieldwork is due to be completed on October 3, 2016. A review of the questionnaire indicates that it covers a wide range of relevant issues. However, it would benefit from some strengthening to capture adequate measures of perceived tenure security, the complex link between CCROs and access to finance, and the full extent of disputes. The Annual Review team has made some recommendations in this regard and will connect the evaluation team to other initiatives monitoring these issues. The team will also need to ensure consistency between the design and methodology used for this pilot and that which the successful tender applicants develop for the rollout of the survey.
Monitoring progress throughout the review period

This review was completed by two ODI staff, both specialists in land tenure and governance, and overseen by DFID’s Senior Responsible Officer for LTSP. . This team has followed the progress of the programme since its launch, carrying out the first Annual Review and a subsequent review of the inception period. The review included document reviews and meetings in Dar es Salaam, and a three-day field visit to the districts of Kilombero and Ulanga, the main sites of the LTR activities.

Along with the annual review, the program is closely supported by program Management Committee that meet quarterly to review quarterly work plans, cash flow forecasts and the progress of Programme implementation against log-frame indicators, quarterly plans and budget. Permanent secretary -MLHHSD, chairs the Management Committee and it comprises a representatives of the Programme Implementation Team, District Land Officers from to pilot districts of Kilombero and Ulanga, Commissioner for Lands, Director for Surveys and Mapping, Director for Rural and Town Planning, Director for Policy and Planning and representatives of the DPs (DFID, SIDA and DANIDA).