BUSINESS CASE ADDENDUM FOR WORK IN BORNO STATE

SUMMARY INFORMATION
Project Name	Solar Nigeria Programme
Country or region targeted	Nigeria
Type of cost extension (if applicable)
Original project budget	£53.8 million (ASI component £4.765 million)
Original project start and end dates	2014 – 2020
Cost extension value (if applicable)	£4.2 million
New project end date (if applicable)
Business Case Quest Document No.	4643400; 5502319

INFORMATION
What is the project’s purpose?
Solar Nigeria’s purpose is to strengthen markets for solar photovoltaics (PV) generated energy in Nigeria, and in doing so improve the lives of poor Nigerians and reduce carbon emissions and the carbon intensity of Nigeria’s development path. / The programme targets both solar usage to improve the quality of public services and interventions to speed up the development of solar markets in Nigeria. The programme has made good progress in both areas, with electrification of 11 primary healthcare centres in Lagos is Nigeria’s largest solar installation to date, and companies supported by Solar Nigeria providing solar systems or devices to almost 50,000 households in the first quarter of 2016.
What is the objective of the cost extension or other changes?
The cost extension is to fund pilot installations of solar systems in health facilities in Borno State, where the Boko Haram conflict has had a devastating effect on healthcare provision. These planned installations in three general hospitals outside Maiduguri will improve health outcomes both by improving the quality of energy supply and by releasing funds currently used for buying diesel to run generators to improve staffing. They include one large, one medium sized and one small general hospital. / As well as providing immediate health benefits, the installations will also increase the resilience of energy supply, by making energy for key installations, and therefore the provision of health services, independent of grid power and diesel deliveries which are both vulnerable to conflict. / The specific locations to be electrified in the recommended option are: / Biu General Hospital. This was designed as a 250 bed hospital and is the largest hospital in Southwest Borno (185 km Southwest of Maiduguri). It is the largest hospital in the state outside Maiduguri. It is currently operated as a 300 bed hospital due to additional needs created by the closure of other hospital, including that at Damboa. / Benisheik General Hospital (75 km West of Maiduguri). This is a 100 bed hospital that was destroyed by Boko Haram. It has been reconstructed and is about to be formally reopened. / Dikwa General Hospital (90 km East of Maiduguri). This is a 50 bed hospital that was badly damaged by Boko Haram and is currently being repaired. It is expected to reopen later this year.
What is the additional and total support the UK will provide?
The funding requirements for each component are outlined below and further detailed in this section. / Location Amount / Installation of solar system at 250 bed hospital in Biu, Borno State (60-70% of total load) £ 1,724,000 / Installation of solar system at 100 bed hospital in Beinisheik, Borno State £ 987,000 / Installation of solar system at 50 bed hospital in Dikwa, Borno State £ 618,000 / 6.5% Administration fee to ASI, electrical retrofit work, technical assistance, solar module RfID tagging, M&E, Gender equality and Social Exclusion (GESI) assessment and first year maintenance and contingency £ 933,373 / Total additional £4,262,373 / Detailed breakdown / Activity / Sub-contract for installation of 3 hospital systems £3,329,000 / Electrical retrofit work at 3 hospitals, including security chipping of solar panels plus contingency £332,900 / ASI charges for administration of sub-contracts £238,023 / M&E contract including baseline studies £70,000 / Technical assistance £126,000 / One year maintenance support £166,450 / Total £4,262,373
What are the expected results?
In energy terms, the expected results are 24 hour power being supplied for critical load to 3 general hospitals in 3 locations in Borno. The hospitals represent one large system, one medium sized system and one small system, and one hospital in each of Borno's three senatorial districts. / This approach works well for a pilot as it means that we will be able to collect and compare information on the energy performance and impact on services of each of the three standard system sizes that have been designed for Borno. Doing installations in three locations also means that DFID will gain information on the operating environment and security situation that is relevant to a significant part of the state (as well as avoiding any perception that districts are being favoured in terms of reconstruction effort). / There is also an appropriate balance between supporting a large number of patients, with Biu being the largest hospital in the state outside Maiduguri, and the restoration of health services to areas most affected by conflict with Benisheik and Dikwa both being facilities closed and destroyed by Boko Haram that are now being reopened. While Biu is not a location that was overrun by Boko Haram, it takes many patients from areas such as Damboa that were overrun and where secondary healthcare facilities were destroyed and have not yet been reconstructed. / The design team has been able to visit the 3 locations and has measured actual energy use to design appropriate systems. The ultimate results will be improved healthcare outcomes, with increased patient attendance and greater willingness of healthcare workers to work in these locations. A more detailed assessment of expected health outcomes will be possible once a baseline study has been completed.
What is the approach to implementation?
Experience from recent procurement for Kaduna has shown limited market appetite for installing systems in conflict affected areas of Nigeria (the killing of Shia protesters impacted the Kaduna tender and only one compliant bid was received). There were also challenges from having an installation process overseen by a procurement specialist that had limited capacity on the ground in North. / Given the security challenges in Borno it is essential that those implementing the intervention have the capability to do so successfully in a conflict setting. ASI as a company has worked extensively in conflict environments for DFID. It's Nigeria Team Leader and Social Component Leader both have experience delivering projects in conflict zones. / The company that Lagos State used to install DFID funded systems in Lagos (EmOne Ltd.) has demonstrated strong technical capability and by chance did a lot of work in Borno prior to the recent insurgency. They have done the design work for the health systems in Borno, and worked well with Borno State counterparts to obtain information, and quickly got their design team out to all of the locations where work is proposed (Biu, Benisheik and Dikwa). / The implementation approach that offers the greatest probability of success with the least risk is to combine ASI's conflict experience with EmOne's solar expertise and experience of working in Borno. The design work and costing undertaken included 3 system sizes for secondary hospitals and 3 sizes for primary healthcare centres (PHCs). The PHC system costs have been benchmarked against costs for Kaduna, with respect to Levelized Cost of Electricity (LCOE); COE represents the cost per kWh of building and operating a generating plant over an assumed financial life and duty cycle. Key inputs to calculating LCOE include capital costs, fuel costs, fixed and variable operations & maintenance (O&M) costs, financing costs, and an assumed utilization rate for each plant type. Solar Nigeria estimates that Borno represents a 10% improvement in LCOE costs compared with Kaduna due to the use of a hybrid system and the higher solar irradiance in Borno. This appears to offer strong VfM compared with the incremental costs DFID has incurred in other conflict areas such as Afghanistan, Iraq and Somalia. / Implementation would be through a costed extension to the DFID’s contract (PO 5595) for Solar Nigeria services with Adam Smith International (ASI). They in turn would subcontract a local company EmOne Ltd. to install systems. ASI will charge a 6.5% mark up on the sub-contract, which is calculated to recover costs but not make a profit from the contract. / Compliance with International Development (Gender Equality) Act 2014 / Improving the quality of public health provision will benefit both men and women, but is expected to bring particular benefit to female populations through improvement to maternal healthcare. Detailed information on current services for the locations concerned is not available, but Borno counterparts identified general hospitals as their priority in part on the basis that they are currently providing a large share of primary services as well as secondary care due to the disruption of health facilities by conflict. Data collected on the impact of solar systems installed in Lagos indicates that mothers and young children form a significant component of the population benefitting from better services. / The budget for the intervention includes funding for both baseline studies on service delivery and a GESI assessment. The assessment will particularly inform discussion with Borno state government on the alternative use of savings from reduced use of diesel to run generators. / Key risks that we perceive include: / Boko Haram attack during installation that causes loss of life or injury. / Risk type: External / DFID Nigeria risk appetite: Severe / DFID would not have duty of care for the contractor, but minimising this risk has nonetheless been a key factor in deciding installation locations. / Biu has been is one of the few towns in Borno not to have been captured by Boko Haram, and the route to it through Gombe has remained relatively secure throughout the conflict. / Benisheik is on the main road from Maiduguri to Damaturu, which is the most secure major road route in the state. / Travel to Dikwa has been approved by UN OCHA, though military escort is needed. The contractor visited all three locations as part of the design process. / Borno remains an insecure environment, particularly outside Maiduguri, and any travel or activity there involves some risk even after mitigation. / Likelihood after mitigation: Minor / Impact: Severe / Boko Haram destroying DFID funded equipment after installation. / Risk type: External / DFID Nigeria risk appetite: Severe / The steps taken to select locations involving relatively low risk have been described above. For Boko Haram to take Biu, Benisheik or Dikwa would require the security situation to worsen very substantially. A conventional attack on an installation as large as one of the general hospitals situated in large towns would be more ambitious than any recent attack, and a suicide bombing would be unlikely to destroy the solar system. / Likelihood after mitigation: Minor / Impact: Severe / Boko Haram stealing and using DFID funded equipment. / Risk type: External / DFID Nigeria risk appetite: Severe / Boko Haram is known to use solar panels to supply energy needs, and the risk of DFID equipment falling into their hands would carry significant reputational risk. The hospital sites will be protected by the Nigeria Security and Civil Defence Corp (NSCD) and the nature of the installations mean that stealing panels or other equipment would not be easy. All the solar panels will be chipped, meaning they could be tracked if they were removed. / Likelihood after mitigation: Minor / Impact: Major / Poor performance by the installer leading to poorly performing systems. / Risk type: Delivery / DFID Nigeria risk appetite: Major / The importance of a first intervention in Borno being well implemented is recognised, and the delivery approach greatly reduces this risk. ASI has extensive experience of working in conflict zones, and the Team Leader and social component lead have both worked in conflict areas. The sub-contractor has worked with Solar Nigeria before and has the confidence of both ASI and DFID. The company worked extensively in Borno prior to the insurgency, and knows the locations and counterparts. / Likelihood after mitigation: Minor / Impact: Major / Fraud involving loss of UK funds / Risk type: Fiduciary / DFID Nigeria risk appetite: Minor / The use of ASI to manage the procurement gives significant assurance as they have well developed fraud avoidance systems. They have worked with the sub-contractor before and have confidence in that company. No funds would go through government systems. Even so, vigilance is necessary as Nigeria is a high-risk environment for fraud. / Likelihood after mitigation: Minor / Impact: Major
Describe any key changes to the original business case?
The proposed additional interventions are fully in line with the original Solar Nigeria business case, which included the electrification of health facilities in Lagos and the ambition to extend similar work into Northern Nigeria