Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: West African Food Markets Pilot Programme (WAFM)
Programme Value: £15 million		Review Date: 15 March 2017
Programme Code: / 200239	Start Date: / 26 Mar 2013	End Date: / 26 Mar 2019

Summary of Programme Performance
Year	2013-14	2014-15	2015-16	2016-17
Programme Score	B	A	A	A
Risk Rating	High	High	Major	Major

Summary of progress and lessons learnt since last review

Over the past year, the programme has made good progress, with the following highlights:

- Grantees from Round 1 are beginning to report significant results. Four of the five targets for output 2 have been exceeded: the year saw a 112% increase in grantees’ production levels of staple foods (against a target of 40%) and over 61,000 smallholder farmers were reached with goods and services (seeds, machinery hire, credit, storage). Cross-border trade targets were also exceeded for this stage of the programme;
- The second round of the Challenge Fund (CF) was successfully completed and five new awards were made. Round two saw an increase in agri-businesses financed in Burkina Faso (three out of a total of nine) and the grants awarded are expected to benefit a large number of farmers next year due to the significant outgrower networks in their business models. The programme is making a valuable contribution to the DFID Sahel strategy as WAFM is the only DFID programme delivering grant investments to agri-business in the Sahel;
- On policy reform, the programme has improved on the low base reported in the last annual review and made progress this year in analysing the regional trade policy environment. The team is well positioned to deliver on this area in the next reporting period, including through a partnership with a new subcontractor. DFID expects a gear-shift over the next 12 months and will continue to push the team to translate analysis and planning into improvements in regional trade policy or its implementation;
- 2016 – 17 has been a year of substantial consolidation for the WAFM Programme Management Unit (PMU). The Project Management Unit (PMU) has built a more stable, enlarged, and linguistically-balanced team, which will be further strengthened by senior technical resource.

The main lessons learnt:

If the programme is to deliver on its design – which combines a challenge fund model with policy work informed by grantee priorities - it needs to maximise the resource invested in policy influencing and focus on increasing the connections between Challenge Fund work and Policy Facility strategy. Plans are being implemented to enable the PMU to do this and a Policy Facility Manager has been recruited during the reporting period.

The review visit flagged issues with data quality being held by the PMU about grantees’ predicted results. Issues were resolved in the period immediately following the visit and grantee numbers included here have now been fully verified. Going forward the PMU will give renewed focus to ensuring the team is on top of portfolio progress by interrogating grantee result projections, regular site visits and results verification every quarter.

Finally, it should be noted that the programme is seeking to increase women’s participation by addressing gender-specific barriers. One example of this is grantee Psaltry, which provides boreholes in its contract farming communities to reduce the time burden facing female farmers who also bear responsibility for household water-collection. A further example is the decision made in Round 2 of the Challenge Fund to request applicants to focus applications on five areas of intervention, of which one was businesses offering aggregation services to informal female cross-border traders operating across the Nigeria – Niger corridor. The WAFM Business Case predates the Gender Equality Act.

Summary of scores / performance:

Overall Output score – A – Outputs met expectations

- Output one (20%): Policy Facility is established to generate evidence, identify policy interventions and deliver implementation of these for better functioning cross-border trade markets achieved an A rating.
- Output two (40%): Better business models for production of staple foods achieved an A+ rating.
- Output three (40%): Better business models for marketing of staple foods achieved a B rating.

Summary of recommendations for the next year:

WAFM should learn lessons from the mid-term evaluation of the sister programme, FoodTrade East and Southern Africa (ESA), which concluded recently and recommended that the programme’s impact level indicators be revised “to reflect the scope and realistic influence the programme can have at a regional level within the timeframe remaining”. As a resultant, two additional impact indicators have been added to ESA. WAFM should also adopt these two additional indicators (slightly revising this in the case of impact indicator 1.4 to make this relevant to the particular WAFM programme investments), to enable comparison between programmes;
- The PMU should consider tailoring the fourth piece of policy work on market supply to the Nigerian food shortages in the North East, so the programme is poised to assist in negotiating a less expensive, market-friendly emergency response;
- The PMU should engage closely with the Policy Dialogue and Influencing Study beginning March 2017 for the FoodTrade East and Southern Africa (ESA) programme which will analyse the effectiveness of the programme’s approaches to policy influencing. This could prove an extremely useful resource to WAFM given similarities;
- With improved analytical capacity now in place, the PMU should consider developing an intelligence / briefing offer on its prioritised regional trade issues or bulletin on food prices / stocks that can be shared with DFID country offices in West Africa and inform relevant DFID work with other partners. This will not only increase awareness of the programme but could also help build opportunities and alliances for agreed policy intervention strategies;
- The PMU must focus on how it will deliver against the final policy milestone (demonstrating improvements to regional trade policy / its implementation) in the remaining two years of the programme, as achievement here will be critical to success.
Monitoring of active Challenge Fund grants and verification of grantees results should be regularised and strengthened further over the next 12 months. The PMU should regularly interrogate grantees’ result projections, including conducting site visits and results verification every quarter.
While the PMU team has been strengthened in the past reporting period, it will be strengthened further by a senior technical post to focus on grantee reporting, flag challenges and achievements and focus on increasing the connections between Challenge Fund grantee needs and Policy Facility strategy.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202577/
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202577/documents

Regional context

The key features of the region set out in the WAFM Business Case continue to prevail. West Africa remains one of the poorest regions in the world with an incidence of hunger, malnutrition and poverty of over 70% in some areas. The worst-affected areas tend to be rural and typified by dependence on smallholder farms[1]. Agriculture remains the dominant livelihood for approximately seventy percent of West Africa’s population, yet growth in agricultural productivity has not kept pace with population growth[2]. Despite significant agricultural potential, West Africa has a high degree of dependence on global food imports to meet consumption needs, importing food from Asia or Latin America is often cheaper than importing the same product from a neighbouring country[3].This situation is compounded by the Sahel’s susceptibility to drought, which exacerbates food insecurity.
[1] WAFM Business Case, Quest No: 3859293, p2.
[2] The population of West Africa is predicted to rise to 516 million by 2030 and 815 million by 2050. Source: UN (2013). World Population Prospects, The 2012 Revisions, The United Nations (UN) Department for Economic and Social Affairs, New York in GRM WAFM Inception Report to DFID, p 4
[3] Source: GRM WAFM Inception Report to DFID, p 4

Despite the high poverty prevalence however, key agencies like the Food and Agriculture Organisation (FAO) and the Africa Development Bank (AfDB) have stated that market opportunities for West African food producers are on the rise due to a combination of population and economic growth, urbanisation, and dietary diversification, which are contributing to an increased demand for processed and nutritionally-enriched product. In late 2015, FAO and AfDB observed that “Food demand [in West Africa] is transforming from undifferentiated bulk commodities towards food products with differentiated quality attributes such as nutritional and health characteristics, packaging, and ease of preparation, offering important opportunities for value addition.”[4] The grantee approvals made to date substantiate this trend, with four of the nine businesses supported conducting fortification and vitamin-enrichment of staple food products during processing, a trend which fits well with DFID’s increased focus on interventions that enhance nutritional outcomes.
[4] pXVIII of Agricultural Growth in West Africa: Market and Policy Drivers AFDB and FAO, 2015 http://www.fao.org/3/a-i4337e/index.html

Changes to regional context in the past year

In terms of the broader political and economic context in programme countries, in Nigeria, the optimism that accompanied President Buhari’s election in early 2015 diminished during the reporting period. Falling global oil prices and macro-economic policy resulted in the devaluation in the Naira and the restriction of foreign exchange respectively, the latter being seen to damage regional and international trade as well as restrict the supply of inputs needed for agriculture. In North-East Nigeria, increasing control by militant groups over territory and escalation of conflict with government forces gave rise to extreme food insecurity and famine predictions, challenging the presumption in the programme’s Business Case that production in coastal states (Nigeria and Ghana) would be likely, over the programme’s life, to meet food shortages that would occur in the Sahel. Over the next 12 months, the programme may need to step up in assisting the humanitarian response to the crisis in North East Nigeria by ensuring local private-sector food supplies form a large part of the response and are not displaced by World Food Programme / humanitarian food supply.

The Economic Intelligence Unit (EIU) predicts that militant activities in Mali and Nigeria have high potential to spread to the border areas of western Niger and Burkina Faso, the programme’s two Francophone countries. The EIU notes that standard security measures in the region are weak and compounded by the geographical diversity of the terrain which makes the threat difficult to contain. Despite this, Burkina Faso has not seen a return to the levels of political violence which marked 2015 in the form of an attempted coup d’état. Contrary to expectations, the second round of the Challenge Fund has run very successfully in Burkina Faso, attracting an increased number of successful applicants, particularly in seed production and crop-buy back, which promise to reach large numbers of beneficiary farmers and which make a valuable contribution to DFID’s Sahel strategy.

In Ghana, peaceful elections were held in December 2016, ushering in an administration regarded as business-friendly but which is yet to demonstrate its capacity to deliver on campaign promises to improve the investment climate. High inflation, high domestic costs of borrowing and a crowding of the market with government bonds mean that financing needs of agri-business continue to be poorly served by private sector finance, with interest rates being offered by banks for investment in agri-business as high as 45%[5].
[5] Informed by interviews with AgDevCo and the PMU.

Outline of the programme

The UK is providing £15 million to support a pilot programme to develop regional staple food markets in West Africa over five-years (2013 - 2019). The West Africa Food Markets (WAFM) programme is designed to positively impact on food security in the region by increasing food availability via increased trade in food staples across two corridors: Ghana / Burkina Faso and Nigeria / Niger. Specifically, the programme seeks to increase staple crop food trade via the establishment of a Challenge Fund (CF) and a Policy Facility (PF). The Challenge Fund supports innovative applications from private sector actors seeking to trade staple foods across these borders, and the Policy Facility aims to support private and non-profit actors seeking to remove policy barriers preventing food trade across borders.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
It is still too early to report progress against outcomes at this stage. Over half of the programme grants have been active for one farming season at most and some grantees contracted in the second round were only contracted in last 2016. The Mid-Term Evaluation, which will be conducted over the next 12 month period, will make an assessment of programme progress against outcome statements.

Overall output score and description
- Output one: Policy Facility is established to generate evidence, identify policy interventions and deliver implementation of these for better functioning cross-border trade markets achieved an A rating and was weighted at 20%.
- Output two: Better business models for production of staple foods achieved an A+ rating and was weighted at 40%.
- Output three: Better business models for marketing of staple foods achieved a B rating and was weighted at 40%.

Given the cumulative weighting of outputs two and three, which is 80%, this programme gets an overall output score of A.

Key Lessons:
If the programme is to deliver on its design – which combines a challenge fund model with policy work informed by grantee priorities - it needs to step up the resource invested in policy influencing and increase the connections between Challenge Fund work and Policy Facility strategy. Plans are underway to assist the PMU to do this and a Policy Facility Manager has been recruited during the reporting period.

Key actions:
- The mid-term evaluation of the sister programme, FoodTrade East and Southern Africa, concluded recently and recommended that the programme’s impact level indicators be revised “to reflect the scope and realistic influence the programme can have at a regional level within the timeframe remaining”. Resultantly, two additional impact indicators have been added. WAFM should adapt these two additional indicators (slightly revising this in the case of impact indicator 1.4 to make this relevant to the particular programme investments), to enable comparison between programmes.
- The Mid-Term Evaluation of WAFM will be delivered by the Evaluation Management Unit (EMU) over the next twelve months. The PMU should see this as a unique opportunity to both showcase good work undertaken to date, and to improve programme performance. Key elements of the Foodtrade Mid Term Evaluation, recently completed, should be studied by the PMU team to learn lessons contained here.

All other actions are covered in the summary sheet under recommendations. Where more detail on each of these was considered necessary, this has been included in the recommendations section under each output below.

Has the log frame been updated since the last review?
Yes. In line with the recommendations of the last annual review, a revision of the programme’s Theory of Change (ToC) and logical framework has taken place. There were several strong arguments for this: the original Theory of Change in the business case rested almost exclusively on a food security rationale which missed significant additional justifications for the programme such as improved wealth and job creation and improving market functionality and access. Additionally, some top-level log-frame indicators were inappropriate as the data on which they depended is neither available nor reliable[6]. The monitoring framework for WAFM is therefore significantly improved as a result of work done in the reporting period.
[6] For example formal trade data on staple food volumes traded across borders, which is of limited reliability.

Following the log-frame revision completed in the previous period however, milestone indicators for the final two years of the programme are yet to be agreed. This needs to be done as soon as possible and appropriate indicators should be suggested by DFID, agreed with the supplier, and published on Dev Tracker.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Policy Facility is established to generate evidence, identify policy interventions and deliver implementation of these for better functioning cross-border trade markets.
Output number per LF		1	Output Score	A
Risk:		Severe	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Progress	Progress
Number of achievable regulatory and policy changes identified for which a dedicated influencing strategy is developed and agreed. / Target: 3 / Result: 3	MET In August 2016 the PMU contracted a partner organisation with a track record in gathering political, economic and market intelligence for large corporate and trade actors. It has used this analysis to develop realistic, well-grounded strategies on the three areas of regulatory and policy change seen as some of the most significant regional trade barriers by grantees. / The three areas identified for regulatory and policy change work are: / examination of export bans, specifically in Nigeria and Burkina Faso where they are most routinely and regularly applied; / investigation of the actual regime of tariffs and para-tariffs affecting grantees and; / training of grantees to improve their knowledge of legitimate cross-border processes. / In October 2016, a fourth area was added to the Policy Facility work plan. Drawing lessons from the 2016 El Niño response in Southern Africa, WAFM Programme Steering Committee members agreed the importance of the programme: / mapping regional staple food traders supplying the four WAFM countries as well as the rough volumes being brought in and out to ensure that trade patterns are broadly understood and the programme therefore well-placed, in the event of food shortages, to ensure that any emergency food response is transparent and does not displace private suppliers and traders. In a context of increased concern in early 2017 about famine in North-East Nigeria, this work could move up the Policy Facility’s priority list.
Number of achievable regulatory and policy changes identified for which a dedicated influencing strategy is being implemented. / Target: 2 / Result: 3	EXCEEDED Influencing strategies for three of the policy change areas set out above have got underway: / For export bans, detailed Political Economy Analysis (PEA) was shared in October analysing the specific application of export restrictions on staple foods in Burkina Faso and Nigeria. A four-pronged intervention approach was approved by the Steering Committee in December 2016 and implementation is beginning. Interventions focus on: a) Supporting grassroots associations and cooperatives to better represent producers’ / processors’ / traders’ interests either on a national scale or in northern Nigeria (Nigeria) and nationally (Burkina Faso); b) launching a more convincing counter-narrative against export bans regionally; c) lobbying for removal or simplification of the main tools used for export bans (the Export License Scheme for grain exporters in Nigeria and Authorisation Speciale d’Exportation (ASE) in Burkina) and d) improving the transparency of harvest data collection. / For tariffs and para-tariffs, work has been commissioned which gathers evidence of grantee experience across the two programme border crossings and the range of additional and informal fees demanded. This work reports in late February 2017 and will make recommendations on whether intervention options are feasible and, what these look like if so. / For cross border training, training sessions have been held in French and English by Borderless Alliance setting out legitimate cross-border processes with grantees. Participants have identified quality and phytosanitary standards (SPS) as areas for further training. An evaluation exercise in May 2017 will assess whether grantees perceive that the training and resulting greater knowledge of correct border processes has resulted in their speedier / cheaper border crossing and reduced exposure to illegitimate practices. / For regional staple food trade mapping a terms of reference has gone to market, with an estimated start date of March 2017 for the work.
Number of improvements to regional trade policy / its implementation to which Policy Facility-led activities contributed. / Target: 1 / Result: 0	NOT MET Despite significant improvements in analysis and planning, this has not yet translated into tangible improvements in regional trade policy or its implementation.

Key Points

While in the early years of the programme, delivery against this output was slow, the past year has seen the West African PMU make significant progress in improving the quality of regional trade policy analysis and intelligence available to it and in defining and beginning future work in this area.

If the programme is to deliver on its design – which combines a Challenge Fund model with policy work informed by grantee priorities - it needs to step up the resource invested in policy influencing and increase the connections between Challenge Fund work and Policy Facility strategy. Plans are underway to assist the PMU to do this and a Policy Facility Manager has been recruited during the reporting period.

Recommendations:
- The PMU should consider tailoring the fourth piece of work on market supply to the Nigerian food shortages in the North East, so the programme is poised to assist in negotiating a less expensive, market-friendly emergency response;
- The PMU should engage closely with the Policy Dialogue and Influencing Study beginning March 2017 for the FoodTrade East and Southern Africa (ESA) programme which will analyse the effectiveness of the programme’s approaches to policy influencing. This could prove an extremely useful resource to WAFM given similarities;
- With improved analytical capacity now in place, the PMU should consider developing an intelligence / briefing offer on its prioritised regional trade issues or bulletin on food prices / stocks that can be shared with DFID country offices in West Africa. This will not only increase awareness of the programme but could also help build opportunities and alliances for agreed policy intervention strategies;
- The PMU must focus on how it will deliver against the final milestone (demonstrating improvements to regional trade policy / its implementation) in the remaining two years of the programme, as achievement here will be critical to success.
Recommendations from previous annual report:
The recommendations under the relevant section of the previous annual review – to consider focusing on policy reform in Francophone programme countries and to revise milestones relating to advocacy events and publications which had become a poor fit with the agreed Policy Facility strategy – were both addressed. The export ban work focuses on Burkina Faso as one of its two countries of interest, and indicators and milestones have been revised for this output as part of the over-arching Theory of Change and Log-frame review.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Better business models for production of staple foods
Output number per LF		2	Output Score	A+
Risk:		Major	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Progress
Number of female and male smallholder farmers who have received goods or services from grantees (such as supply of modern inputs, increased storage and aggregation facilities, market price information, warehouse receipts and related-credit, mobile wallets/ payment and banking facilities). / Target: 45,072 / Result: 61,513 / (Male: 46,142 and Female: 15,371)	EXCEEDED This target has been over-reached by 136%. Results against this output come from three of the grantees supported under Round 1: AFEX (Nigeria), Fagri (Burkina Faso) and Psaltry (Nigeria). / Of the 61,513 farmers reached, Fagri has supplied 19,538 farmers with extension services and inputs (seeds, and tractor and shelling equipment rental), AFEX reached 15,000 farmers across 8 states with its Grain4Fertiliser input programme, 2,143 with over the counter transactions, 7,500 with loans and 16,262 with storage services as a result of selling through its platform. This brings AFEX’s share of the total to 40,905. Psaltry has provided 1,070 farmers with at least one of the following: tractor hire, stems, inputs (herbicides and fertiliser) soft-loans, market information or e-wallets. Note that the herbicides, fertiliser, and tractor-hire services are provided on a product-backed credit basis (the debt is recorded and when farmers’ product is sold, the debt is deducted from payments made to farmers’ bank accounts). / There is some way to go to achieve gender-equity in beneficiary terms, but given the significant barriers to commercial farming facing women in West Africa (most notably unequal access to credit, land and unequal division of domestic labour), a target of almost 25% female beneficiaries is not insignificant.
% annual change in production levels of staple foods (maize, millet, sorghum, cassava / gari) for direct beneficiaries of the challenge fund (disaggregated by crop and country). / Target: 44% / Result: 112.33%	EXCEEDED The milestone target for the reporting period has been exceeded by almost three times. All reporting grantees (the same as for the above indicator), overshot projected product aggregation targets from smallholder farmers. / AFEX also fared very well in this period despite an adverse macro-economic climate in Nigeria and being a relatively new entrant to the Nigerian market. The company provided a significant new market for smallholders’ staple food produce while reaching a large number of farmers with services and inputs. This demonstrates the programme’s ability to find, select and support promising firms able to positively impact the region’s food markets.
Total volume of staples traded cross-border as a result of grantee business models. / Target: 2,906 MT / Result: 3,577 MT	EXCEEDED The milestone target has been exceeded. AFEX reported cross-border transactions of 3,300 MT, of which sorghum transactions with the World Food Programme formed 3,000 MT and were financed through the electronic warehouse system. Fagri reported sales of 277 MT of maize to Niger (with an additional 800 MT planned for February and March 2017 - not be included in this report). Psaltry did not report x-border sales to the end of January, but has orders on its books for 210 MT of Vitamin A fortified-Gari to go to Niger in March 2017.
Total value of staples traded as a result of grantee business models. / Target: £700,000 / Result: £4,255,889	EXCEEDED The total value of staples traded has very significantly exceeded predictions. We are currently reviewing the target with a significantly higher level of ambition for the last two years of the programme.
% of total staple food production of grantees sold through cross-border trade. / Target: 25% / Result: 16%	NOT MET: This is the only target against this indicator which has under-reported, a fact due partly to the very significant scale of AFEX’s domestic operations in Nigeria, which makes attaining a cross-border percentage of sales of 25%, which is a challengingly high-figure in grantees’ early years of operation.

Key Points:

The second Challenge Fund round was conducted in this period, and in line with the recommendation of last year’s AR, saw a visible improvement in the quality of shortlisted proposals as well as an increase in awards to businesses based in Burkina Faso, possibly due to stakeholder awareness workshops being held in Ougadougou and at the AGRA Innovate West Africa Fair. Burkinabé grantees promise delivery of big beneficiary numbers in future years due to the businesses selected for support using seed and crop buy-back models which involve large numbers of smallholder farmers producing seed and crops which are then sold back to the company for processing or aggregation. The PMU has now contracted the five round two grantees, bringing the total Challenge Fund portfolio to nine businesses and the total grant amount committed to £5,604,640, about 78% of the total Challenge Fund budget.

Recommendations:

Monitoring of active Challenge Fund grants and verification of grantees results should be regularised and strengthened further over the next 12 months. The PMU should regularly interrogate grantees’ result projections, including conducting site visits and results verification every quarter.

While the PMU team has been strengthened in the past reporting period, it will be strengthened further by a senior technical post to focus on grantee reporting, flag challenges and achievements and focus on increasing the connections between Challenge Fund grantee needs and Policy Facility strategy.

Summary of responses to issues raised in previous annual reviews
Last year’s recommendations – that the programme strengthen co-operation with USAID’s Africa LEAD and Finn-Gap programmes to maximise use of business advisers trained under these programmes and that the programme improve in-house processes to ensure that errors, gaps and omissions are spotted in documents in advance of submission – have both been addressed.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Better business models for marketing of staple foods (including e.g. storage).
Output number per LF		3	Output Score	B
Risk:		Major	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Progress
Number of female and male smallholder farmers who have received goods or services from grantees (such as supply of modern inputs, increased storage and aggregation facilities, market price information, warehouse receipts and related-credit, mobile wallets/ payment and banking facilities). / Target: 45,072 / Result: 61,513 / (Male: 46,142 and Female: 15,371)	EXCEEDED As reported for Output 2, Indicator 1, this target has been over-reached by 136% (note that the same indicator is used for Output 2.1 and Output 3.1 as many of the goods or services received by smallholder farmers allow them access new markets with their product).
Number of male and female farmers selling product to grantees. / Target: 70,950 / Result: 42,444 / (Male: 28,437 and Female: 14,007)	NOT MET: Delivery against this target was significantly lower than predicted. This is due to target figures being provided by the supplier for the wrong time-frame (April 16 – March 17 and April 16 – June 17 in the case of some of the target data provided). This review can only consider data for the timeframe April 16 – February 17 and grantee-reported data must be verified by the supplier. / The time-frame discrepancy was discovered by DFID during the review visit. Review expectations have now been clarified with the supplier. Data for the correct time-frame will be supplied to DFID by the supplier for the next review period.
Volume of staples purchased from smallholder farmers by grantees. / Target: 79,856 MT / Result: 51,127 MT	NOT MET: Again, delivery was significantly down against this target for the reason given above. The time-frame discrepancy was discovered by DFID during the review visit and expectations have now been clarified with the supplier. Data for the correct time-frame will be supplied to DFID by the supplier for the next review period.
Value of staples purchased from smallholder farmers by grantee / Target: £12,854,189 / Result: £7,875,197	NOT MET: Again, delivery was significantly down against this target for the reason given above. The time-frame discrepancy was discovered by DFID during the review visit and expectations have now been clarified with the supplier. Data for the correct time-frame will be supplied to DFID by the supplier for the next review period.

Key Points

It is noteworthy that achievement against the targets has been negatively affected by the technical time restriction DFID places on the provision of target figures for the period April 2016 to end March 2017. While the review covers this time-frame, the annual reporting process must be completed by the end of February to allow figures to be verified and the review to be compiled and completed. The timing of the harvest at the end of December has exacerbated this, as the months of January – March are when the greatest results would occur for all three under-reported indicators.

Recommendations
Monitoring of active Challenge Fund grants and verification of grantees results should be regularised and strengthened further over the next 12 months. The PMU should regularly interrogate grantees’ result projections, including conducting site visits and results verification every quarter.

Summary of responses to issues raised in previous annual reviews (where relevant)
Last year’s recommendations – that sex-disaggregated data be provided for output 3 indicators and that there is a revision of the Theory of Change and the logical framework - have both been addressed.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers of the WAFM programme are the costs of the PMU to set up and manage the Challenge Fund and the Policy Facility. It is likely that additional investment in the PMU will be required to conduct and coordinate research and networks to inform Policy Facility interventions. DFID is currently in discussion with the PMU on this.
In August 2016, the programme agreed Value for Money (VFM) indicators to be used for the programme’s mid-term evaluation, based on those used in the FoodTrade ESA programme to encourage VFM comparability between programmes. Updates are provided against these below, up to December 2016.
WAFM Value for Money Indicators
#	Metric	VfM Dimension	Description	Progress (up to December 2016)
1	Fund management cost ratio	Economy	The ratio of direct fund management costs to the total grant funds committed by WAFM	Direct fund management costs for the period April – December 2016 was £789,445.60 against a total grant fund currently committed by WAFM of £5,604,460. This ratio (14%) is expected to improve as the programme commits the next round of grant funds.
2	Consultancy average unit cost	Economy	The average cost per consultant hired by PMU (total consultancy cost divided by number of consultancy days, per year and for programme duration).	The average cost per consultant for this period was approximately £350. This includes consultants billed through the Technical Assistance Facility (excluding Palladium contributions through TAF) and Borderless Alliance billed through the Policy Facility.
3	PMU Staff component economy	Economy	Number of PMU staff employed per £1m of programme funds	Approximately 9 staff per £1 million of programme funds spent during this period. Programme funds includes all reimbursable expenses.
4	Administrative cost ratio	Economy	Total admin + fund management costs to total grant funds committed by WAFM	The total spend for April – December 2016 on admin and fund management was £789,445.60, and the total grants committed was £5,604,460 (14%).
6	Portfolio-wide leverage ratio	Efficiency	Ratio of matched contributions mobilised by WAFM grantees to WAFM total grant amount committed.	WAFM currently has £5,604,460 in committed grants, and grantees have committed to match £7,662,338. This indicator highlights that for every £1 million of WAFM grant funding, approximately £1.3 million of matched funding is expected to be mobilised over the grants’ life.

Assessment of whether the programme continues to represent value for money

The programme’s progress to date indicates that it continues to represent good value for money. As outlined in the monitoring and evaluation section (section H below), independent research continues to underline the importance of getting regional food markets functioning more effectively in West Africa to increase economic growth and regional security, as well as to increase regional food security in a vulnerable and poverty-stricken part of the world.

DFID’s experience with the El Nino response in Southern African in 2016 has also shown us that better functioning regional markets allow food to flow from areas of surfeit to areas of deficit, leading to less – and to cheaper - humanitarian response. The FoodTrade ESA programme was able to intervene in the Southern African response to ensure that the emergency food approach was made more transparent and that private suppliers and traders experienced minimal displacement. The WAFM programme is uniquely placed to offer similar benefits to the 2017 crises anticipated in Northern Nigeria. The fact that mapping of regional staple food traders supplying the four WAFM countries is already underway in the programme demonstrates one of the ways it can be part of an efficient response to a possible emergency.

Quality of financial management
Programme spend is on track against the agreed 2016/17 budget. Spend at the point of writing was £2.5m against a budget of £3.3m and is expected to meet the £3.3m target by March 2017. The PMU provides DFID with detailed time sheets each month which set out the number of days each team member has spent on the programme and the assignments contracted. The PMU’s financial and forecasting management continues to improve and DFID’s programme management staff work closely with Palladium’s financial management team to improve forecasting via monthly catch up meetings. In June 2016, further measures were taken to improve financial management and monitoring. Accuracy has improved significantly since that point. In addition, the PMU has moved to monthly invoicing which has also improved forecasting accuracy.

The provision of annual audited statements is not a requirement for programmes contracted through procurement services. However, the PMU has agreed to provide annual audited statements for the programme.

Date of last narrative financial report	12 January 2017
Date of last audited annual statement	26 June 2016

E: RISK (½ page)

Overall risk rating: Major

Overview of programme risk
A detailed analysis of the key risks was included in the Business Case (BC)[7]. The largest risk factor for identified in the Business Case risk matrix was a decline in security in the region, for which DFID had put in place the following four mitigation measures:
[7] WAFM Business Case, Quest No: 3859293, p 48-50.
- Duty of care policy clarified to potential bidders;
- Flexibility to switch operations to different locations in West Africa.
- Contractual break clauses if performance measures are not met; and
- Mechanisms to enable the programme to be scaled down or expanded, based on performance and / or provision for DFID to terminate for convenience.

This review agrees that a worsening security situation continues to represent the most significant risk to the programme. As noted in the context section above, there has been an increase in insecurity in North-East Nigeria in the past year, contributing to acute food insecurity and predicted famine which may require the programme to adapt its activities. Despite this, food trade is currently continuing along the Nigeria /Niger corridor on which the programme focuses.

By contrast, the security situation in Burkina Faso improved in the past 12 months, following an attempted coup d’état in the 2015-16 period. The programme will continue to work on its four focus countries and two focus corridors, adapting processes to fit to local security conditions where necessary – as done this year in Burkina Faso – and with a readiness to switch operations to different corridors as a more drastic measure, if necessary.

The second most significant risk identified in the BC was that political economy considerations prevent the success of programme aims (seen as high probability and medium risk). Further Political Economy Analysis work undertaken this year examining beneficiaries and opponent of export bans in Burkina Faso and Nigeria (the two countries in which these are most routinely applied) have helped the Steering Committee to identify discreet activities that the programme can undertake to seek to improve the regional trade export regime. The success of these activities remains to be demonstrated of the remaining two year period.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
A one-year no-cost extension was granted to WAFM in the 2015 -16 reporting year to offset the significant delay in approving the original contract with the PMU. Lessons from the FoodTrade East and Southern programme shows that in complex and high-risk programmes such as these, implementation should not be rushed and thus, a no-cost extension was considered better Value for Money to DFID than trying to compact the time available for programme delivery.

Performance of partnership (s)
The formal partnership between the PMU and the Evaluation Management Unit (EMU) is working effectively: the EMU has conducted a review of the PMU’s data-collection systems and made recommendations to it. The two organisations also worked together to present the revised ToC and log-frame during this reporting period. The PMU began a new partnership in August 2016 with providers of Political Economy Analysis to inform policy intervention options and design. As set out in section C, output, this partnership has functioned well in laying the groundwork for policy intervention design.

Asset monitoring and control
Not applicable.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not relevant[8].
[8] The four Partnership Principles (PPs) are: I. A commitment to reducing poverty and achieving the Millennium Development Goals (MDGs)2 The commitment of the partner government to addressing the enablers and constraints to poverty reduction and progress against the MDGs (and successor goals). II. A commitment to respecting human rights and other international obligations3 The commitment of the partner government to respecting human rights, and in particular the economic, social and cultural rights as well as civil and political rights of poor people. III. A commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption4 The commitment of the partner government to strengthening the management of public finances and fighting corruption. IV. A commitment to strengthening domestic accountability5 The commitment of the partner government to enabling people to hold the government and public authorities to account for delivering on their commitments and responsibilities.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Changes in evidence and implications for the programme
Several publications make the case for continued support to regional integration of Africa’s food markets, while recognising the important role that increased regional trade in food staples can play in promoting growth and security more broadly, as well as food security in the region. These include:

- “Africa Competitiveness Report 2013: Connecting Africa’s Markets in a Sustainable Way” (May 2013), World Economic Forum concludes that efforts to foster trade through regional integration will be critical for Africa to diversify its economies and increase the region’s competitiveness. Holds that increased cross-border trade can lead to a virtuous cycle of more competition in domestic markets that—coupled with the exploitation of economies of scale—lowers the costs and therefore, argues that African countries are losing out on billions of dollars in potential trade because of the region’s fragmented regional market.
- “Barriers to trade in food staples in West Africa: an analytical review”, Jakob Engel and Marie-Agnes Jouanjean, Overseas Development Institute, 2013 concludes that facilitating intra-regional trade in inputs and food staples could address high trade costs and large price differentials between producing and consuming regions in West Africa, and that regional integration efforts should support supply as well as demand-side bottlenecks.
- “Connecting Food Staples and Input Markets in West Africa: A Regional Trade Agenda for ECOWAS Countries”, Jean-Christophe Maur and Ben Shepherd, World Bank (Forthcoming: currently in draft form only).

All research material outlined above adds to the evidence supporting WAFM’s objectives, underlining the importance of the trade integration agenda and the need to stimulate cross-border food markets to improve food security.

Theory of change and programme design

The original Theory of Change and logical framework were set up around the food security rationale for the programme, stressing that increasing levels of staple foods traded between the Sahel and Coastal areas would increase food availability and diversity, as well as capitalise on the different topographies’ harvest cycles and crop availability.

Less attention was paid in the ToC and logical framework to the likely market strengthening impacts of supporting agri-processing or the positive impact on jobs, livelihoods and nutrition that increased trade in processed and fortified staple foods, as well as raw staples, can deliver. For this reason, the ToC has been reworked during the reporting period in-keeping with the recommendation of the previous Annual Review. Indicators have been added to capture positive impacts accruing to farmer and consumer incomes and productivity. The monitoring framework for WAFM is therefore seen to be significantly improved as a result of work done in the reporting period and the revised log-frame can be viewed on Development Tracker at https://devtracker.dfid.gov.uk/projects/GB-1-202577/documents.

Monitoring and Evaluation activities throughout the review period

Monitoring activities by DFID include weekly phone calls with the supplier and review and approval of quarterly reports prepared by the PMU. DFID has also reviewed the Evaluation Management Unit’s (EMU) Design Report – which sets out the approach that the EMU team will take to the Mid-Term Evaluation (due March 2018). The EMU has also provided a quality assessment to DFID following their review of quantitative data being collected for monitoring and evaluation purposes by the PMU.

The quarterly Programme Steering Committee meetings chaired by DFID are a further means to monitor progress of activities of both the PMU and EMU, and are attended by advisers from DFID Ghana and Nigeria, as well as a representative of the West Africa Department of the World Bank.

The annual review process

This annual review was conducted by the DFID Food Markets Policy Adviser in the Africa Regional Department (ARD) in January / February 2016. It was conducted via documentation review and a six-day visit to Ghana (Accra and Kumasi) where interviews with project stakeholders were conducted.

Other key ARD staff have inputted to the document. Staff from both the Project Management Unit and Evaluation Management Unit also had sight of the document to enable factual corrections to be made and to ensure the review contains faithful and accurate reporting on PMU and EMU activity.

Representatives from the following organisations were interviewed in Ghana and the UK:

- AFEX – Palladium Office, Ghana.
- Africa Practice – Palladium Offices, Ghana.
- AgDevCo – Kumasi, Ghana.
- Borderless Alliance – Accra, Ghana.
- DFID Ghana (Livelihoods Adviser) – DFID Ghana offices.
- Fagri International – Palladium Office, Ghana.
- Kedan Ltd – Palladium Office, Ghana.
- NAFASO International - Palladium Office, Ghana.
- Psaltry International – Accra, Ghana
- Premium Foods Ltd – Kumasi, Ghana
- Programme Management Unit, Palladium - Accra, Ghana. .
- USAID West Africa Regional Trade Team – US Embassy, Accra, Ghana.