Annual Review - Summary Sheet

Title: Ghana Oil and Gas for Inclusive Growth (GOGIG)
Programme Value: £17,250,000		Review Date: 21/11/2016
Programme Code: 204330	Start Date: 2/03/2014 / Contract Start Date: 8/12/2014	End Date: 31/03/2019

Summary of Programme Performance
Year	2014	2015	2016
Programme Score	B	A	A
Risk Rating	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review

Despite a slow start to the implementation phase, the Ghana Oil and Gas for Inclusive Growth (GOGIG) programme has achieved fourteen of its fifteen Output milestones in the last year, and some have been exceeded. Programme expenditure is on target based on a pro-rata spend throughout the project lifetime.

The pace of implementation was slow for the first half of the year. Delays in signing Memoranda of Understanding in late 2015, acknowledged in the last Annual Review, contributed to this, but for the most part can be attributed to weaknesses in programme management. Oxford Policy Management (OPM) have responded quickly to concerns but changes in the programme manager have impacted on programme performance. Enhanced programme management capacity and increased back-stop support from OPM, as well as the recruitment of a new programme manager with experience in Ghana’s extractives sector should enable smooth future programme operations.

GOGIG has made good progress in establishing relationships with key beneficiary partners, creating networks with key supplier partners, enhancing understanding through political economy analysis (PEA), and developing plans for capacity development and institutional reform. In line with the project objectives, work in 2016 was delivered across two key elements: 1) strengthening systems to improve state institutions’ capacity to deliver on their mandates to manage the oil and gas (OG) sector, and 2) maintaining pressure and scrutiny from civil society organisations (CSOs) to promote accountability. Both activities have yielded results that GOGIG can leverage for further change as it moves into the second year of implementation.

Highlights of overall progress made over the period include:

- Strengthening the legislative framework for the sector. GOGIG facilitated the inclusion of technical experts and civil society in the deliberation process for: the Exploration and Production Bill, the development of regulations for the Petroleum Revenue and Management Act (PRMA) 2015 and the Income Tax law 2015[1];
  [1] Which covers Petroleum income tax.
- Facilitating Policy Development Process: GOGIG completed the first stage of preparatory work for the development of a petroleum policy for Ghana, including stakeholder consultation, and workshops to establish policy positions[2];
  [2] From Africa Center for Economic Transformation (ACET)/Prof Amoako Tuffour & GOGIG Adviser to the Minister.
- Establishing clarity in sector institutional arrangements: GOGIG has mapped the institutional arrangements within the sector, including highlighting areas of conflicts, overlaps and gaps. GOGIG will leverage this mapping work to engage other sector agencies on improving sector coherence;
- Institutional Strengthening and Capacity Building: The Bank of Ghana (BoG) and Ghana Revenue Authority (GRA) have been supplied with industry-standard software and relevant training to strengthen their capacity in sector management. The Petroleum Commission (PC) has received training on their preferred software (Petrel and Landmark suite), which should enable the PC to better assess oilfield appraisal programmes, but a key user of the software explained he was still awaiting purchase of the license for ongoing use[3];
  [3] The GOGIG team explained the license had been purchased, and provided evidence of this. The review team considers it important to note that a key user was unaware of this fact.
- Support for Identification of additional tax revenue: Additional revenue of GHC 7million was recovered by the GRA’s Transfer Pricing and Petroleum Units (PU) as a result of discussions at a GOGIG/Natural Resource Governance Institute (NRGI) workshop on Transfer Pricing. The multi-stakeholder format of the training facilitated dialogue and ultimately led to the identification of this additional revenue;
- Supporting the Public Interest Accountability Committee (PIAC) to fulfill its mandate of creating platforms for citizen country-wide engagements.

Lessons learned which have informed programme delivery include:
- The visibility of the “oil money” provides an opportunity for dialogue on broader issues of efficiency and good governance of Public Financial Management (PFM);
- There is a need to balance partner agencies’ preference for long-term planning with GOGIG’s flexible and adaptive approach, which they are not used to; collaborating with partners during their work-planning process can help with this;
- Clear evidence-based analysis is effective in informing debates on key sector issues;
- Combining strong relationships with analytical clarity is effective in overcoming differences in partner institutions’ business set-ups, cultures and approaches – this will provide a solid foundation for GOGIG to respond to new opportunities and demand for reform which may emerge post-election.

Summary of recommendations for the next year
- By January 2017: GOGIG should clarify and re-assess the role of the special adviser in discussion with MoP and PC.
- By January 2017: GOGIG should review the volume of material shared with Steering Committee (SC) members and timing for sharing this.
- By January 2017: GOGIG should finalise a portfolio approach to the development and management of projects, with a clear approvals process with timeframes.
- By February 2017: GOGIG should formalise information sharing with WRCF. The Review Teams suggests monthly contact, with quarterly meetings, including 1-pager information sharing on most relevant topics.
- By March 2017: GOGIG and DFID should revise the Logframe and agree on baselines. Specific recommendations for strengthening the Logframe in the upcoming revision are highlighted in relation to each Output, but should include:
  - Output 5 should be strengthened to ensure effective on-going project management. Suggested indicators could include: timeliness of project approvals process
  - The project expects to work with further government agencies. The project should cover this work in the Logframe. An indicator regarding sector coherence could track progress on the important mapping piece GOGIG has undertaken in 2016
  - Where the Logframe assesses capacity building in partner agencies, include measures of client satisfaction and client progress against their own work plans.
- By March 2017: GOGIG should convene key policy discussions with partners to continue momentum with government partners and harness opportunities post-election.
- By March 2017: DFID and GOGIG should consider how to better align the annual reporting with the annual review and to align GOGIG’s work with partners’ planning cycles; GOGIG’s programme year should match the timing of the annual review and be aligned to the calendar year/government operational year.
- By March 2017: GOGIG should define clear roles and responsibilities between Programme Director (PD)/Programme Manager (PM)/Team Leader (TL) and communicate this to partners, including the relationship with the DFID Lead Adviser.
- By March 2017: GOGIG should outline its capacity building strategy. This should consider capacity development activities that go beyond the individual being trained e.g. improving institutional memory beyond a specific team (BoG), and developing manuals.
- By March 2017: GOGIG should consider its contribution to DFID’s Climate Change agenda, and define a process for tagging spend by relevance to Climate Change agenda.
- By March 2017: GOGIG has had a successful meeting with management at Ghana National Petroleum Corporation (GNPC), and should seek to further strengthen this relationship to assess overlaps in regulatory responsibility with the PC and ease process of transfer of responsibilities towards the PC.
- Continuous: GOGIG should seek opportunities to liaise with DFID’s Extractive Hub and Partnerships projects for two-way information sharing.
- Continuous: DFID should include discussion on progress against the Logframe in quarterly progress meetings.
A. Introduction and Context

DevTracker Link to Business Case:	http://bit.ly/2gcjbEK
DevTracker Link to Log frame:	http://bit.ly/2gcjbEK

The Ghana Oil and Gas for Inclusive Growth (GOGIG) programme is a five year programme launched in January 2015 to support Ghana in maximising its oil and gas resources for inclusive growth. The expected outcome is “Effective management of oil and gas resources”. The programme intends to achieve this outcome through the delivery of five inter-related outputs.

The programme is organised in three components:
1. A dedicated programme team, contracted to the service provider Oxford Policy Management (OPM), that manages the technical support to government institutions responsible for the governance of oil and gas resources, as well as to accountability actors active in the sector;
2. Two accountable grants – to the Natural Resource Governance Institute (NRGI) and the African Centre for Energy Policy (ACEP) for specific advocacy related activities;
3. A dedicated Advisor to the Minister of Petroleum with extended support to the Petroleum Commission and other institutions.

A key part of GOGIG’s engagement with government is the Steering Committee (SC), which provides the forum for representation of government priorities for the programme and deliberations on the programme’s contribution to its Inclusive Growth objective. Each of GOGIG’s key partner agencies - Bank of Ghana (BoG), Ghana Revenue Authority (GRA), Ministry of Finance (MoF), Ministry of Petroleum (MoP), Petroleum Commission (PC) - are represented on the Steering Committee. This provides the SC legitimacy for engagement with official agencies that an outside programme would otherwise lack and has fostered a strong degree of government ownership of the programme objectives, priorities and activities.
Management of the two accountable grants to ACEP and NRGI has transitioned from DFID to OPM/GOGIG. This process is on-going, with MOUs signed, and contracts expected to be signed towards the end of 2016.

In the last year, there have been a number of significant changes in the wider context within which the programme operates:
- The sustained low oil price has reduced government revenues from oil and contributed to a record trade deficit. This has also contributed to a further slowing of the economy, which was already weighed down by a worsening fiscal situation and a difficult energy crisis.
- The passage of the parent law of the industry, the Exploration and Production bill by Parliament in August 2016 presents an opportunity for GOGIG to work with both government and civil society to understand the implications and work on implementation and sensitisation. GOGIG has already begun discussions with the Ministry of Petroleum to assess the implications for existing petroleum agreements.
- Although GOGIG does not directly work on downstream issues related to energy provision, there is an important rationale for greater focus on this area. Domestic gas production is increasingly being used to support the energy sector. This means that the plans and developments in the energy sector have a direct impact on how the petroleum sector contributes to inclusive growth.
- The initial high expectations associated with the discovery of oil and its potential contribution to the economy have given way to realism. The enthusiasm and incentive for transformational reform has shifted to an appetite for mainly transactional improvements. The high visibility of the sector and the post-election period however present opportunities for some strategic reforms.
- Lastly, the result of the 2016 elections could have significant implications for GOGIG’s work. GOGIG should prepare to be as supportive as possible and to maximise arising opportunities.
B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The programme’s outcome is “Effective management of oil and gas resources” as measured by:
- Resource Governance Index (RGI) scores;
- The Petroleum-Transparency and Accountability Index (P-TRAC); and
- The value of additional oil revenues.

Data for the RGI have not yet been released as a result of the postponement of NRGI’s launch to May 2017. The Institute of Economic Affairs (IEA) has been unable to assess the P-TRAC result for Ghana due to the upcoming elections. GOGIG and DFID are following developments with both indices.

The programme is able to highlight contributions to an important element of the RGI: improvements in the institutional and legal setting of the sector. Support has been provided in the form of the development of critical laws and regulations such as the Exploration and Production (E&P) Bill; the Petroleum Revenue Management Act (PRMA); and Income Tax regulations. In the case of the E&P Bill, GOGIG – through its CSO partners – succeeded in the uptake of key accountability provisions such as open and competitive bidding, and disclosure provisions such as the publication of reasons surrounding the use of the minister’s discretionary powers.

Regarding the third outcome indicator, an additional GHS 7 million[4] has been recovered by the GRA as a result of discussions at a GOGIG/NRGI technical session on Transfer Pricing. The process is on-going to collect an additional GHS 3 million. GHS 10 million would represent the 20% increase in oil and gas revenue the project forecast to be captured by October 2016.
[4] Approximately 1.8 million US Dollars

In summary, the project is working on areas that contribute to its outcome. It is on track to achieve targets in at least two of the three outcome-level indicators. It is currently not possible to make an assessment of the third, as the NRGI is yet to release RGI data for the oil and gas sector in Ghana, but this should be available before the next review.

Overall output score and description: A. The main programme components are generally on track against the logframe, and in some cases performing above expectations (e.g. Output 1, Output 4, and Output 5).

Key lessons

See summary sheet.

Key actions
- Consider the implications for the composition of the Steering Committee of extending work with government to additional agencies.
- Finalise the Logframe and baselines by March 2017 to enable the logframe to be used as a programme management tool. Ensure Logframe indicators are clear and ambitious. The review team understand RGI data will not be available at this point, and so the Logframe will need to update targets at this level when this is available.
- Work closely with government counterparts in December 2016 during their work-planning process to align GOGIG work plan with theirs where shared priorities are clear, but be ready to adapt to changes post-elections.

Has the logframe been updated since the last review?
Yes. Following recommendations from last year’s annual review, revisions to the logframe were finalised and accepted by the DFID Results Advisor in August 2016. This late agreement meant the annual review took place only three months after the Logframe edits had been finalised, which is the minimum time-frame allowed between revisions and project review. For this reason, the review team emphasises completing Logframe edits earlier this year.
C: DETAILED OUTPUT SCORING

Output Title	Regulatory mandate and policy coherence of the oil and gas sector enhanced
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
1.1 Number of actions taken to address policy gaps, conflicts and overlaps in mandates	Areas of legislative and institutional overlaps established	Achieved: Gaps and overlaps in oil and gas sector governance identified and validated by the Ministry of Petroleum
1.2 Number of initiatives implemented to advance the strategic priorities of the Ministry of Petroleum, Petroleum Commission and other relevant sector institutions	4	Exceeded: 12
1.3 Petroleum Commission's capability in sector regulation	Organisational capacity gaps established and capacity building interventions commenced	Achieved: PC’s capacity development needs identified, and capacity building commenced.

Key Points

The impact weighting for this output was reduced from 30% to 25% to accommodate a new output on programme management. All three milestones have been achieved with that of Indicator 1.2 exceeded. The review team recommend changing indicator 1.2 to something more informative regarding the capacity of partner agencies e.g. progress against their workplan and client satisfaction with GOGIG work.

Findings from mapping the institutional landscape of the sector have provided the evidence base for the MoP’s engagement with other sector agencies e.g. in planning interventions to address overlaps and gap, and will continue to inform do so.

GOGIG’s technical support to the PC and the MoP has improved their day-to-day operational functioning and supported them in meeting key priorities for the year. For example, economic and financial analyses of the Field Development Plan informed analysis of the Gas Master Plan and provided the Ministry with recommendations for the development of the gas policy and gas law.

Technical assistance supported improved implementation of the local content policy, as well as the development of key frameworks and templates e.g. the economic model for gas pricing; a capacity and competence building framework for local universities running oil and gas courses; and templates for IOCs, service companies and local companies engaged in the upstream petroleum sector to support succession strategies for the local population.

Support for everyday tasks such as the vetting of localisation plans and the review of reports and permits from IOCs, have resulted in the identification and submission of missing reports by IOCs as well as the securing of slots for Ghanaians to understudy expatriates.

Summary of responses to issues raised in previous annual reviews (where relevant)

The project team has responded to the majority of the recommendations raised in the previous Annual Review. See Annex 1 for details.

Recommendations
- By January 2017: GOGIG should re-assess the requirement for the Special Adviser going forward: feedback from MoP and PC suggested support should be tailored to their current needs. In the case of the MoP, this would require an organisational change expert.
- By March 2017: GOGIG and DFID should revise the logframe to strengthen indicators:
  - Include a client satisfaction indicator for work with MoP and PC.
  - Indicator 1.1. Could reflect progress made against work plan for coordinating the sector.
  - Indicator 1.2. Could reflect progress made by MoP and PC against their own work plan and staffing requirements.

Output Title	Systems of oil and gas revenue capture improved
Output number per LF		2	Output Score	B
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Ghana Revenue Authority's capability in revenue capture	Organisational capacity gaps established and capacity building interventions commenced	Achieved: Capacity building areas identified for PFM partners in 7 core areas and activities commenced.
2.2 Systems put in place to facilitate revenue capture	Computerised Assisted Audit Techniques put in place / Regulations for Income Tax Law drafted	Achieved: Computerised assisted audit techniques software procured and installed. / Income tax regulations drafted, laid before Parliament and passed.
2.3 Ghana Revenue Authority’s scope of tax audits	Adoption of computerised approach to audits	Not achieved: Transition from manual to computerised system in progress.

Key Points
Two out of three of the milestones have been achieved, with the last milestone (2.3) in progress.
A needs assessment has identified capacity building (CB) areas for PFM partners in 7 core areas: management development to enhance performance management; financial analysis and modelling of oil and gas projects; petroleum economics/fiscal regimes – negotiating oil and gas contracts; oil and gas industry knowledge; petroleum taxation law issues & auditing; fiscal metering & measurement; and sovereign wealth investment and risk management. Capacity building has commenced in exploration and production accounting and in understanding international petroleum law.

GOGIG worked to strengthen the policy framework in developing the Income Tax regulations. This is a positive example of GOGIG utilising the flexible approach it has adopted to respond to opportunities and use oil and gas as an entry point to improve governance more broadly. GOGIG also strengthened the systems for revenue capture through the installation of an automated audit system for the GRA. The installation of the IDEA Computer Assisted Audit Tool (CAAT) software is particularly significant because of the advantage it offers the Petroleum Unit with an increased coverage and scope of investigations, which cannot be done manually, and ultimately making the Unit more efficient by saving time in identifying exceptions. It aligns the GRA’s audit approach more closely with the accounting and financial management systems of the IOCs by changing it from manual to electronic.
As an indicator measuring a system changeover, factors outside the control of the programme affected the full achievement of Indicator 2.3 (travel, conflicting training schedules). GOGIG is however engaged with the service provider and the Unit to support this transition process.
Summary of responses to issues raised in previous annual reviews (where relevant)

GOGIG responded to all previous Annual Review recommendations. See Annex 1 for details.

Recommendations

By February 2017: GOGIG and DFID to consider including in the logframe:
- an indicator reflecting GRA Petroleum Unit’s progress against its own work plan – suggest this replaces current Indicator 2.2.
- an indicator reflecting client satisfaction with GOGIG work.
- By March 2017: In addition to identifying additional revenues, GOGIG should also consider approaches to reducing revenue losses. This might include exploring collaboration with the STAAC programme, which intends to focus on corruption in the oil and gas sector.
- By March 2017: The Petroleum Unit audit manual should be reviewed in light of computerisation to instil institutional capacity over the long-term. GOGIG should discuss this with GRA.

Output Title	Oil and gas revenue management improved
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Capability of key institutions (Bank of Ghana (BoG), Ministry of Finance (MoF)) engaged in revenue management	Organisational capacity gaps established and capacity building interventions commenced	Achieved: Capacity building (CB) areas identified for PFM partners in 7 core areas and capacity building activities have commenced.
3.2 Systems put in place to facilitate fiscal oversight and investment decisions	PRMA regulations drafted / Automated market trading systems put in place	Achieved: Petroleum Revenue Management Regulations drafted and submitted to the Attorney General's Department. / Bloomberg software has been procured and installed for the BoG and in use.
3.3 Number of research outputs made available by the Energy, Oil and Gas Unit to inform decision making on revenue management	2	Achieved: 2

Key Points
All three of the milestones have been achieved. As with Output 2, GOGIG collaborated with the MoF and the BoG to ensure that specific legal gaps in regulations and institutional shortcomings were addressed.

For the MoF, capacity building has commenced in relevant areas, including introductory training on financial modelling. For the BoG, capacity building has commenced in Sovereign Wealth investment and risk management and financial market analysis. Practical training on contract negotiation, which involved both the MoF and GRA as well as other key institutions, has also served to improve coordination.

GOGIG facilitated the inclusion of technical experts and civil society in the deliberation process for: the Exploration and Production Bill, regulations for the PRMA 2015, and Income Tax law 2015.
Another key area of progress is the installation and use of Bloomberg’s Asset and Investment Management application by the BoG’s Ghana Petroleum Funds Secretariat.

The growing maturity of the relationship GOGIG has developed with the MoF is reflected by an agreement for GOGIG to fund three key pieces of research rather than a full-time consultant. The agreed approach demonstrates value for money (VfM), and has introduced the MoF to a new more collaborative approach to working. Two research reports have been submitted to the MoF for review. A third report is in draft, due by end of November 2016.

Summary of responses to issues raised in previous annual reviews (where relevant)

GOGIG responded to all previous Annual Review recommendations. See Annex for details.

Recommendations
- By February 2017: Regarding the Logframe, GOGIG and DFID should consider the following:
  - Develop a tool for measuring capacity.
  - Include a client satisfaction measure for MoF and BoG counterparts on the Logframe.
  - Include a measure of agencies’ progress against their own work plan on the Logframe.
- By March 2017: Baselines to be agreed for with DFID Logframe indicators.
Output Title	Oil and gas sector oversight enhanced
Output number per LF		4	Output Score	A+
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Capacity building interventions that facilitate oversight functions of accountability actors	8	Exceeded: 11
4.2 Number of analyses, monitoring and advocacy initiatives that seek to hold government to account on oil and gas fiscal management	40	Exceeded: 75
4.3 Percentage of step change actions achieved by the Public Interest and Accountability Committee (PIAC)	ACEP: 80% / PIAC: 70%	Exceeded: / ACEP: 100% / PIAC: 100%
4.4 Number of engagements between government, accountability actors and citizen groups on key sector issues	4	Exceeded: 8

Key Points

GOGIG has surpassed expectations on all four indicators for this Output.

GOGIG delivered capacity building interventions targeting PIAC, media organisations, and members of parliament in the form of training workshops, orientation courses and technical roundtables. Focus areas included: governance of oil, gas and mining revenues; legal framework for Ghana’s petroleum revenues; amendments to the PRMA; and open data and extractive data analysis.

PIAC undertook a total of 60 citizen-focused advocacy initiatives to enhance its engagement with the public on the management and use of oil revenues. ACEP undertook seven analyses to scrutinise government actions in managing petroleum resources. Additional advocacy initiatives centered mainly on provisions to be amended in the E&P Bill and funding to PIAC.
Both ACEP and PIAC have made significant progress in achieving all planned milestones that contributed to their organisational development e.g. strategic plan, HR and finance manuals. This is significant for PIAC that has been beset with challenges that have affected its growth since its inauguration in 2011. Challenges remain, which have led to a 6-month extension to support. There are some question marks around PIAC being fully operational, however this is expected to be the case in 2017.

GOGIG is increasingly leveraging its partnerships and work with both government and CSOs to convene multi-stakeholder platforms for deliberations and learning on key sector issues. These have included facilitating cross-government engagements and between government and civil society. As a result, the Petroleum Unit and the Transfer Pricing Unit have begun joint audits together, and the GRA and the PC have begun collaborations to assess key audit risks specific to the sector.

Summary of responses to issues raised in previous annual reviews (where relevant)

GOGIG responded to all previous Annual Review recommendations. See Annex 1 for details.

Recommendations

- By February 2017: GOGIG should revise the logframe to further clarify the “step-change” definition. For this review, it was interpreted as meaning significant changes in operations, as demonstrated by the implementation of new procedures based on the GOGIG team’s own assessment, supported by ACEP and NRGI’s confirmation that there had been good support for operational changes.
- By February 2017: GOGIG should finalise reporting and contractual arrangements with NRGI/PIAC and ACEP. This is a good opportunity to review the scope of work for the partners. The review team recommends DFID meet with partners to discuss.
- Improved effort could be made to monitor the beneficiaries of GOGIG partner work around civil society engagement – this information could provide powerful input to GOGIG and DFID story-telling around the outreach activities of the programme, especially if disaggregated by sex, age, and other variables.

Output Title	Quality of programme management deliverables
Output number per LF		5	Output Score	A
Risk:		Minor	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

Indicator(s)	Milestones	Progress
5.1 Extent to which programme management outputs align with strategic priorities	80%	Exceeded: 100%
5.2 Extent to which VFM is integrated into programme	VFM framework developed / Capacity of programme team built to deliver VFM / VFM framework tested and finalised	Achieved: VfM framework developed, tested, and finalised. / Programme team aware of need to consider VfM in their day-to-day.

Key Points
This is a new output in response to DFID’s request for indicators to measure programme management to be included in the programme.

The project management team have developed a number of outputs to support the work of the project team, including a VfM framework, an Inclusive Growth framework, and an overview of the upstream gas sector in Ghana, amongst others. These are all in line with GOGIG’s strategic priorities. In meeting with the project management team, the review team mentioned that it would have been expected that 100% of these outputs aligned with strategic priorities. The project management team appeared to be in agreement with this.

An inclusive process of developing the framework contributed to building the team’s capacity. The team demonstrated a clear understanding of VfM in their initial presentation to the Review team, and interviews with partners provided substantial evidence that GOGIG communicate the need for VfM to partners. Examples include the selection of appropriate capacity building interventions that deliver the most VfM, supporting research papers rather than full-time consultants, and sharing costs with partners.

The VfM framework was finalised in August 2016 and is in line with the VfM indicators outlined in the Business Case.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable – newly created Output.

Recommendations
- GOGIG should finalise a portfolio approach to the development and management of projects, to include:
  - Demonstration of linkages and synergies between projects within each portfolio.
  - Timeframes for all approvals along the chain (GOGIG team / Oxford Policy Management (OPM) project management / DFID / Steering Committee). The recommendation is for batched approvals on a quarterly basis. Timing across the approval chain should be tracked, and the number of successful / unsuccessful request.
  - Demonstration of how each project contributes to the Logframe.
- By February 2017: GOGIG should formalise information sharing with WRCF. Suggest monthly contact, with quarterly meetings, including 1-pager information sharing on most relevant topics.
- By February 2017: GOGIG and DFID should consider the following Logframe revisions:
  - Review weighting of Output 5. Programme management is key to GOGIG functioning smoothly. 5% seems low.
  - Include a Logframe indicator around timeliness of approvals.
  - Include a Logframe indicator on the quality of financial management, such as timeliness of reporting and accuracy of forecasting.
  - Review Programme Management indicator and 80% target. It is unclear why this would not always be expected to be 100%. Consider what progression would be.
  - Strengthen targets for VfM integration – instead of ‘achievements reported’ suggest ‘targets met’.
  - Include a Logframe indicator to measure the extent to which political economy analysis (PEA) has informed the programme to better capture the programme approach.
- By March 2017: GOGIG should define clear roles and responsibilities between Programme Director (PD)/Programme Manager (PM)/Team Leader (TL) and communicate this to partners, including the relationship with the DFID Lead Adviser.
- GOGIG is currently assessing internal procedures for project management and information sharing, and could also include looking at lesson-learning with similar projects in other countries.
D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The lead cost driver between September 2015 and September 2016 was provision of support to partners (53% of total spend). This includes delivery of trainings, workshops, procurement of software and research pieces. The second largest programme cost over this time period was programme management (38%). Disbursement of the Flexible Responsive Fund (FRF) has increased in the months from June to September 2016. By the end of 2016 GOGIG will have reached the expected pro rota rate of spend for the whole programme.

Programme Expenditure Profile and Projection

VfM performance compared to the original VfM proposition in the business case

The Business Case was approved on the basis of an estimated return of £5.50 for every £1 invested. The severe drop in oil price since this was written has made this target more challenging. However, the programme’s shift to more strategic areas of work such as broadening its points of engagement for revenue capture to include minimising losses and its early gains in this area suggests an opportunity to improve VfM. The programme’s emphasis on leveraging the visibility of oil for improved overall efficiency of Ghana’s PFM, and increased dialogue on inclusive growth has the potential to further improve VfM.

The programme has developed a VfM framework since the last Annual Review. The framework contains a number of useful indicators for measuring progress, which are in line with the measurement indicators in paragraph 104 of the Business Case.

Equity: GOGIG’s VfM framework focuses on mainstreaming Gender and Social Inclusion. Improved reporting from GOGIG accountability partners e.g. beneficiaries from outreach work, disaggregated by sex, would support the project team in reporting their impact on this VfM measure.
Effectiveness: Indicators outlined in the Business Case include raised revenue, scrutiny of contracts, improved management of the heritage fund, and engagement of civil society. GOGIG has made good progress against all of these indicators, including identifying additional revenue of GHS 7m.
Efficiency: Indicators outlined in the Business Case refer to institutional capacity building and improved collaboration between partner agencies. GOGIG has made good progress against both indicators.
Economy: The key indicator in the Business Case relates to how GOGIG benchmarks its costs. Overall, the total cost savings made on projects within the reporting period amounted to a total of £126,883. Of this, £43,317 was derived from savings made on project activities against agreed GOGIG benchmark standard rates, based on competitive market costs. Further cost savings were made in negotiating procurement agreements, using pro bono services for some delivery, and leveraging funds from GoG for payment of per diems.

Assessment of whether the programme continues to represent value for money

It is too early to assess whether the programme continues to represent value for money. Significant investment to date has been required to build relationships within partner agencies, the value of which cannot be easily quantified.

A significant element of GOGIG spend to date has been on the Special Adviser, whose role is being reviewed at the end of the current contract. Assessing whether his work continues to represent value for money will be a key factor in considering whether or not to continue, and if so in what form.

Quality of financial management

OPM has been quick to address challenges related to programme and financial management over the review period and has demonstrated commitment to continuously improve. An expenditure verification exercise conducted by DFID and a review by Internal Audit early in the implementation phase, raised concerns around programme management capacity and the quality of the financial and operations manual. OPM responded by bringing in a new Programme Manager. The manual was strengthened and GOGIG identified an experienced consultant to quality assure it. A new team structure was developed to enhance programme management capacity, resulting in an increase in the contract ceiling. OPM again responded quickly to performance concerns in September 2016, changing the Programme Manager again. The annual audit commissioned by DFID (delayed from June until August due to procurement delays), did not identify any significant issues. Progress is still underway in addressing some of the areas highlighted for improvements identified from the audit.

These changes were not without causalities, however: there was delay to an ACEP request for technical support being approved, which led to the opportunity falling through due to it no longer being relevant. Similarly, when the accountable grant with DFID was terminated at the end of September, OPM were not prepared to issue contracts with the ACEP and NRGI partners and they have been operating without a contract until the time of the review. Funds have been spent on projects on two occasions without approval from DFID being in place. Review team recommendations to clarify roles and responsibilities and develop a Service Level Agreement for partners will go a long way to addressing these issues.

Generally, costs have been well managed. At the beginning of implementation, the programme changed from a Payment by Results (PBR) modality to a hybrid approach of actuals for fees and expenses, and PBR for the Flexible Response Fund (FRF). It was quickly apparent that the PBR approach for the FRF was not appropriate and did not incentivise risk-taking as the programme is intended to do. As a result, programme activity (FRF) costs were billed by the Supplier based on actuals (using the allowance for 10% of FRF activities to be billed as actuals) while a ‘dry-run’ alternative hybrid approach was being tested. The new hybrid modality of 90% actuals and 10% milestones, based on up to three suitable outputs per quarter, was agreed in September 2016 as the payment modality for GOGIG projects funded out of the FRF. The team were delayed in submitting suggestions for suitable deliverables for the first formal quarter during the changeover in Programme Manager. There remain concerns that the new modality will be cumbersome to implement and will not drive performance given the risk that it creates additional work that does not genuinely add value to the programme. Agreeing a rolling programme of deliverables that mature in different quarters will help, and it will be important going forward that GOGIG and DFID continually assess what value it adds and revisit annually.

DFID has robustly scrutinised invoices and timesheets and where discrepancies have been identified ensured that these have been rectified by OPM before payments were made. OPM have shown improvements over the year in submitting financial information and supporting documents in a timely manner. Forecast performance has also improved, and for the last two months has been within the acceptable threshold of +/-10% (6.5% in September and 6.7% in October).

Date of last narrative financial report	31/10/16
Date of last audited annual statement	30/06/16

E: RISK

Overall risk rating: Moderate

Overview of programme risk

The programme continually assesses and manages risks at both the overall programme level and at individual project levels. The overall level of risk for the programme has not changed since the Business Case was written.

The programme has set up internal control systems to manage fiduciary risks associated with its grant-making. This has included the conduct of due diligence assessments and the identification of mitigation strategies to address risks, as well as measures put in place to manage partners’ disbursements and spend.

The Business Case identified the main risks as being in two clusters - political support and institutional incentives. So far the programme has managed this well by strengthening its relations with its government counterparts, regularly updating the project PEA, and leveraging the right incentives to deliver its objectives. The programme has also balanced its neutrality with political parties through its engagement in the elections.

In response to the risks identified around a slowdown of government business and the possibility of a change in government with the election, the programme has developed a line of work for early next year that allows it to maintain the momentum of its work and (re)establish relations with new Ministers and/or a new Government.

There is a risk to the credibility of the project team in working with two sectors that are often in conflict: government and civil society. Further risk stems from having ‘two masters’ in the form of the Steering Committee and DFID. The project team is aware of both difficulties – the latter issue is in no part unique to the GOGIG programme in DFID programmes working with partner governments. However, a change of government or the operating environment could significantly impact both of these points. The project mitigates against this by conducting PEA and building strong relationships at the highest level within government, below political appointees.

Outstanding actions from risk assessment

No outstanding actions.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The programme started slowly. The lengthy procurement of the implementing partner and extended period to approve inception phase deliverables were covered in the last annual review. The implementation phase was also slow to start, pending agreement and signatures of the DFID-Government MoUs at the end of 2015. There were further delays at the start of 2016 due to gaps in programme management, highlighted earlier. Delivery has accelerated since June; this increase in the pace of delivery is welcomed and encouraged to continue over the coming 12-month period. The programme has delivered the majority of its Output milestones and GOGIG spending is on track in terms of a pro-rata projection by end of 2016.

Performance of partnership (s)

GOGIG has built trust and strengthened its relationship with its government counterparts. GOGIG has broadened relationship with GoG to include engagement with the Ministry of Health as part of the work on contributing to inclusive growth.

GOGIG’s partnership with DFID remains strong. The Team Leader, Project Manager, Project Director and DFID adviser have regular and effective meetings to catch up on the progress of the programme.

GOGIG had a productive meeting in Takoradi with WRCF in July 2016, where specific areas for potential collaboration were identified. However, the partnerships between the two programmes – which together make up one of DFID’s largets investments in the extrcatives sector - could be strengthened. The project team identified a list of synergies between the projects, and have shared this with both teams and recommends formalising the relationship.

Relationships with ACEP and NRGI/PIAC urgently require formalising to smooth approvals process and management structures going forward.

Asset monitoring and control

Since the last review, the programme’s assets register has been updated and passed a compliance check from DFID firstly in February and then in August 2016. DFID also checked the assets of PIAC in October 2016 and those of ACEP in February 2016.

G: CONDITIONALITY

Update on partnership principles (if relevant)

The GOGIG programme does not provide financial aid directly to the government. However, the programme is well-positioned to support progress against the partnership principles, particularly in the areas of concern, e.g. strengthening financial management and domestic accountability.

The partnership principles were assessed in January 2016. The Government of Ghana upheld all four partnership principles. However, the assessment notes continuing concerns about genuine political commitment to macroeconomic management, fiscal discipline, public financial management reform and fighting corruption. Performance in relation to the IMF programme will be monitored carefully as a means of assessing GoG commitment to the partnership principles.

H: MONITORING & EVALUATION

Evidence and evaluation

The Logframe has been updated since the last annual review. The update reflects a strengthening of the approach to capacity assessment for government institutions, although the capacity assessment tool is yet to be developed, significantly delaying assessment of the baselines for reporting. Given that the project is currently revising the Logframe, this will soon be made available and will be an important tool in monitoring and evaluating project progress, as would efforts to capture client feedback and VfM targets.

GOGIG is carrying out some excellent strategic work across GoG in a sector that is currently under the spotlight. The project team appears to be internally well-coordinated, with regular meetings to assess project proposals. The team is currently assessing internal procedures for project management and information sharing, and could also include looking at lesson-learning with similar projects in other countries.

Monitoring progress throughout the review period

The Annual Review was undertaken by two Adam Smith International (ASI) consultants - an extractives expert and an M&E expert. The review took place alongside that of the WRCF programme and consisted of a desk review of documents submitted by the programme team and DFID followed by 10 days in country. This included initial briefings from the programme teams and interviews with partners and stakeholders. The draft Annual Review was quality assured by a DFID Senior Governance Adviser.

ANNEX 1: REVIEW OF RECOMMENDATIONS FROM LAST ANNUAL REVIEW

Output 1

The project team has responded to the majority of all recommendations raised in the previous Annual Review:

Recommendation: Support the PC in developing a sustainable financial framework, and explore using wider GOGIG networks funding options so that they are not dependent on internally generated funds such as from licence fees.
Response: This was not considered feasible. GOGIG held discussions with the PC on its Financing Strategy. The discussion revealed clearly that the PC had already given extensive consideration to this issue and had developed a framework for financing which could bring in substantive revenues to the PC. Review team conversations with the PC confirmed this.

Recommendation: MOU for the PC signed as soon as possible. The GOGIG team should consider recruiting a Programme Manager.
Response: MOU signed 14 March 2016. The team structure was revised and approved by DFID Ghana, alongside a budget increase to account for additional associated costs.

Recommendation: By March 2016: Agree the definition of inclusive growth. Clarifying how policy related activities link to inclusive growth. This could be underpinned by conducting a strategic analysis of the development needs of the country, and the sector needs, and developing priorities for e.g. local content. The team could review the development of Ghana’s 40-year plan and party manifestoes.
Response: Definition of Inclusive Growth agreed with Steering Committee. Work on the strategic analysis is to follow now that the definition has been agreed. The Vice Chairperson of the National Development Planning Commission was on the panel at a dialogue on Inclusive Growth organised by GOGIG.

Recommendation: Develop a strategy for lobbying or engaging with Government on how oil and gas revenues are utilised, and consider support to sector ministries to enable better understanding of the PRMA, how funding is allocated, and entry points for them to engage on how it is used.
Response: GOGIG supported a sensitisation workshop for stakeholders on PRMA revisions. Allocations of ABFA was not considered a priority when compared to ensuring ministries spend petroleum revenues in line with the budget. GOGIG is also investigating work on management of petroleum funds such as working with Ministry of Health to develop ToRs on sustainable financing that considers petroleum funds. ACEP and other CSOs have worked on tracking oil revenues e.g. ouroilmoney.org. The project is also working to advocate streamlining the number of sectors and projects in which oil money is used to improve transparency.

Recommendation: GOGIG team should review the Logframe, with support from the DFID:
  - Indicator 1.1: the logframe should note whether or not the target is cumulative;
  - Indicator 1.2: consider moving from percentages to absolute figures;
  - Indicator 1.3: consider how to assess the capability assessment; a more tailored approach preferred to a generic approach
Response: Further explanations provided in the definition sheet of the Logframe to clarify the programme’s approach to capability assessments (Indicator 1.3) and to specify that the target for Indicator 1.1 is cumulative. For Indicator 1.2, the indicator statement and calculation was revised from “percentage” to “number” of initiatives implemented as recommended.

Output 2

Recommendation: Ensure VfM in procurement of accounting and audit systems by coordinating GOGIG support to the GRA Petroleum Unit with wider GRA or GoG plans. Ensure complementarity with DFID’s support to GRA delivered through HMRC and other similar donor efforts, e.g. Norad providing input to the GRA Tax Unit.
Response: GOGIG liaised directly with other DFID-supported programmes to GRA in a bid to seek VfM in procurement of accounting and audit systems and has a clear understanding of the role of Norad at the GRA.

Recommendation: Logframe changes as follows:
- For indicator 2.2, milestone 5 and the target should be completed, or an explanation provided as to why it is unnecessary (the same applies to the similar indicator for output 3).
- For indicator 2.3, the logframe should clarify whether the milestones are cumulative or not, and explain the lack of change between milestone 5 and the final target.
Response: Further explanations were provided in the definition sheet of the logframe to clarify the programme’s approach to capability assessments (Indicator 2.1) and to specify that the target for Indicators 2.2 and 2.3 is cumulative. All milestones are complete for all indicators, although the review team recommends further strengthening of these indicators.

Output 3

Recommendation: Synchronise GOGIG internal efforts e.g. with Public Interest Accountability Committee (PIAC), and link externally with other relevant DFID programmes, e.g. WRCF.
Response: DFID support to NRGI for PIAC has moved under the umbrella of the GOGIG programme. This has created enhanced opportunities to align GOGIG and PIAC. Efforts have been made to increase the linkages with WRCF and other DFID projects e.g. STAAC, however the project team recommends the relationship with WRCF to be formalised to capture the full advantage of the synergies between projects.

Recommendation: Increase GOGIG awareness of broader contextual issues, such as the public finance management framework, the macro-economy and the IMF support programme and ensure that these are reflected in Quarterly reports to DFID.
Response: GOGIG developed a paper on Ghana’s debt and the risk to compliance to the PRMA. GOGIG has also been engaged in wider PFM discussions and convened a stakeholders’ dialogue on PFM governance.

Output 4

Recommendation: Further develop plans to use the upcoming elections as an opportunity to build sustained civil society support around key issues, in conjunction with the DFID STAR II programme.
Response: The project has conducted work with civil society actors across traditional media and social media to place OG issues in the debate in the run-up to elections.

Recommendation: Pursue options to work with political parties to offer balanced and neutral technical support for better understanding of the sector to inform party manifestos.
Response: The programme has leveraged opportunities to engage the political parties in discussions that brought attention to OG issues as part of the elections campaign discourse. As part of the election projects, GOGIG partners have engaged with representatives of the political parties at both the national and sub-national levels on oil and gas issues, e.g. ACEP presented the citizen’s manifestos to the political parties individually and highlighted the issues of concern.

Recommendation: The GOGIG team, working with DFID, should revise the Logframe as follows:
- For indicators 4.1, 4.2, and 4.4, the logframe should clarify whether the milestones are cumulative or not.
- For 4.3, the logframe definitions could explain the advantage of tracking the percentage of step change actions rather than the number.
- For 4.4, the baseline should be completed, and an explanation added for the dips in 2017 and 2019.
Response: Further explanations were provided in the definition sheet of the logframe to clarify the advantage of using percentages for Indicator 4.3 and whether targets for Indicators 4.1, 4.2 and 4.4 were cumulative or discrete. For 4.4, the baseline is now complete (0) and there are no dips in milestones.