Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	March 2017

Title: Enhancing Nigeria's Response to HIV/AIDS
Programme Code: / 114206	Start Date / January 2009	End Date: / December 2016
If programme was closed >1 month early please describe in a few words why.

Summary of Programme Performance

Year of AR	2010	2011	2012	2013	2014	2015	2016
Programme Score	75%	A+	A	A	A+	A	A+
Risk Rating	M	M	M	M	M	Major	Major

Financial Position

Original Programme Value	£100,000,000
Extensions/ amendments	No cost extension shifts end date from December 2014 to December 2016
Log-frame revisions (with dates)	New DFID logframe format, merger of output 4 with output 1 (September 2012) / No-cost extension logframe (December 2014)
Total programme spend	£98,977,031.42 (excluding programme income spend)

Follow up actions required following closure
1. Conclude closure audit.
2. Formalise transfer of remaining assets.
3. Conduct dissemination of lessons from ENR social marketing component.

List of abbreviations / ANC	Ante-Natal Clinic
AR	Annual Report
ARVs	Anti-Retroviral drugs
CDP	Capacity Development Plan
CSO	Civil Society Organization
DFID	Department for International Development UK
DP	Development Partner
ESSPIN	Education Sector Support Programme in Nigeria
FBOs	Faith Based Organisations
FMoH	Federal Ministry of Health
FRA	Fiduciary Risk Assessment
FSW	Female Sex Worker
GFATM	Global Fund for AIDS, Tuberculosis and Malaria
GMS	Gender Management System
GoN	Government of Nigeria
HAD	HV/AIDS Division of Federal Ministry of Health (formerly NASCP)
HAF	HIV/AIDS Fund
HCT	HIV Counselling and Testing
HERFON	Health Reform Foundation of Nigeria
HIV	Human Immunodeficiency Virus
HPDP2	Second HIV/AIDS Programme Development Project (World Bank)
IBBSS	Integrated Biological and Behavioural Surveillance Survey
IDU	Injecting Drug User
IPC	Interpersonal communication
JAR	Joint Annual Review
JFA	Joint Financing Agreement
LACA	Local Action Committee for AIDS
LGAs	Local Government Authorities
M&E	Monitoring and Evaluation
MARPs	Most At Risk Populations
MDA	Ministry, Departments and Agencies
MoT	Mode of Transmission
MSM	Men who have Sex with Men
MTSS	Medium Term Sector Strategy
NACA	National Agency for the Control of AIDS
NARHS	National AIDS and Reproductive Health Survey
NASA	National AIDS Spending Assessment
NASCP	National AIDS and STI Control Programme
NGO	Non-Governmental Organization
NHOCAT	National Harmonized Organizational Assessment Tool
NHRC	National HIV/AIDS Resource Centre
NNRIMS	Nigeria National Response Information Management System
NSF	National Strategic Framework
NSP	National Strategic Plan
OCA	Organisational Capacity Assessment
OCAT	Organisational Capacity Assessment Tool
OPM	Oxford Policy Management
PADEF	Partnership Assessment and Development Framework
PATHS2	Partnership for Transforming Health Systems Phase Two
PEP	Peer Education Plus
PLACE	Priority Local AIDS Control Effort
PR	Primary Recipient
SACA	State Agency for Control of AIDS/State Action Committee for AIDS
SASA	State AIDS Spending Assessment
SASCP	State AIDS STI and AIDS Control Programme
SAVI	State Accountability and Voice Initiative
SFH	Society for Family Health
SHARHS	State-specific HIV/AIDS and Reproductive Health Survey
SMOE	State Ministry of Education
SMOH	State Ministry of Health
SPARC	State Partnership for Accountability Responsiveness and Capability
SSP	State Strategic Plan
STAR	Society Tackling AIDS through Rights
STI	Sexually Transmitted Infection
TA	Technical Assistance
TW	Transport Workers
TWG	Technical Working Group
UOP	Unified Operational Plan

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	N/A
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5372572.xlsx

Outline of programme and what it has achieved

The Enhancing Nigeria’s Response to HIV&AIDS (ENR) was an innovative two phase eight year, integrated HIV prevention and institutional strengthening programme. The first phase (2009-2014), focused on institutional strengthening of government and civil society organisation/networks, a National Commodity Social Marketing strand with a condom market modulation element was implemented nationally (working with the National Agency for the Control of AIDS; Federal Ministries of Health, Education, and Women Affairs; and Civil Society organisations). A state level component focused on system strengthening and strategic behavioural change was implemented across eight high priority states (working with the State Agencies for the Control of AIDs; State Ministries of Health, Education, Women Affairs and with Civil Society organisations). The second phase (January 2015 – December 2016) took the market modulation element of the programme one more notch, by working to transition the hitherto subsidised commodities element of the Commodity social marketing component to a full cost recovery regime, with the goal of ensuring long term sustainability of condom access for Nigeria HIV&AIDS and Family Planning efforts, ensuring high net value for money to DFID and the Nigerian people. This report summarises the results, lessons learnt and key innovations applied over the eight years of the programme.

ENR significantly strengthened the organizational capacities and systems of the National and State AIDS Control Agencies and enabled them to analyse, strategically plan, coordinate and manage the national and state AIDS responses. ENR also strengthened the Civil Society Organizations in their planning and management processes and capacities and enabled them to play a substantial role in implementing prevention interventions at community level. ENR also built the capacity of the Ministry of Health at national and state levels in streamlining data collection, data management and data use. The National and State Aids and Reproductive Health Surveys (NARHS and SHARHS) supported by ENR have been of huge value for the HIV response in Nigeria; the Modes of Transmission (MOT) studies championed by ENR was a game changer for the HIV response in Nigeria – facilitating an evidence based shift in focus toward the general population from the initial focus on traditionally defined key populations at risk. Through direct intervention ENR has increased the knowledge about HIV among the population and has contributed to reduction of stigma. Anti-Stigma laws were promulgated in at least 7 ENR states. The proportion of people in ENR supported states with non-stigmatising attitudes doubled from 27% to 53% (men) and 24% to 52% (women).

ENR has been the major driver in shaping the condom market in the country, distributing over 1.4 billion condoms over eight years, with a deliberate focus on rural and underserved areas. This is estimated to have provided 12,000,000 couple years of contraceptive protection, averted 3,300,000 unintended pregnancies, preventing 77,000 maternal deaths and averted 14 million disability adjusted life years (DALYs). During this time, the proportion of rural areas where people can buy a condom increased from 50% to 91%, and condom use at last high risk sex increased from 56% to 78% (men) or 40% to 57% (women). In the final two years, the project implemented a transition from a DFID subsidised social marketing to a full cost recovery social enterprise model. Subsidies on the mass market Gold Circle condom brand were reduced from 76% to 58% (despite serious macroeconomic headwinds during the period), and are on track to be eliminated completely by 2019. SFH has pursued four main strategies to achieve the goal of becoming self-sustaining by the end of 2019 – restructuring, cutting costs, raising price and introducing new products. The DFID supported Gold Circle brand has now become part of a portfolio of health products (such as bednets, the morning-after pill and oral rehydration Salts and Zinc (ORS-Zinc), as well as condoms) marketed by SFH’s new Social Business Enterprise (SBE) unit, which will become a self-sustaining social enterprise delivering public health good indefinitely without donor support.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

The Outcome of the programme is to improve the access of those most vulnerable to infection to effective HIV and AIDS prevention, treatment, care and support information and services.

Indicator 1: Percentage of males and females aged 15-49 years who received HIV counselling & testing and got results in ENR states: There were considerable increases in HIV Counselling and Testing (HCT) uptake from 13% (2007) to 49.5% (2014, target 18%) in females; and from 15% (2007) to 43.7% (2014, target 20%).

Indicator 2: Percentage of the population with access to condoms (disaggregated by urban and rural locations): This has remained stable in urban areas at around 95% throughout the period. In rural areas, there was a considerable increase from 50% (2007) to 93% (2016 – target 85%).

In the final years of ENR SFH made a major push to get Gold Circle condoms into shops in rural areas in the 8 ENR states, with impressive results. By 2014 90% of local government areas (Nigeria’s smallest administrative unit) had at least one shop which stocked them.[1] This level of coverage was maintained during the two years of the extension, despite SFH cutting back on its sales-team and merchandisers.
[1] This is measured in SFH’s Measuring Access & Performance (MAP) survey of a sample of Local Government Areas (LGAs). Starting at the centre-point of the LGA (as specified by the National Statistical Agency), the researcher asks where the shops are, and then finds (or does not find) at least one shop stocking Gold Circle within 15-minutes walking time from the centre. If no such shop is found, the LGA scores zero; if one shop is found, people in that LGA are deemed to ‘have access’. In 2016 just 9% of the sample of LGAs had no shop stocking Gold Circle condoms.

With much less money to spend on promotion, and with the retail price of one Gold Circle condom in 2017 more than double what it was in 2014, it remains to be seen whether consumer demand will be enough to persuade these shop-keepers to continue to stock the product. Luckily SFH will be continuing to monitor this, because its regular surveys of distribution are paid for by donors which are funding the social marketing of other products.

Indicator 3: Percentage of 15-49 year old female and male involved in high risk sex who used condom at last risk sex in ENR states: condom use at last high risk sex increased in men from 56% (2007) to 78% (2016, target 67%) and in women from 40% (2007) to 57% (2016, target 52%).

The long-term rise in this key indicator has continued, so that by the end of the NCE in 2016 at least three-quarters of men and more than half of women in the 8 ENR states used a condom when having what UNAIDS calls ‘high-risk sex’. This percentage has more than doubled since 2007 before ENR started, when the figures were 35% and 23% respectively. During the two years of the NCE the percentage of men reporting that they used a condom rose from 69% in 2014 to 78% in 2016, while the percentage of women reporting that their male partner used one remained much the same (56% in 2014 and 57% in 2016).[2]
[2] The DHS figure for female respondents is always lower than that for males, for various reasons - men are more likely to know and to recall using a male condom, and if more men than women report having sex with more than one partner, the chances of the sample including such men is higher.

It is always difficult to work out how much change can be attributed to a specific intervention, but in this case we do have a basis for estimating the impact of ENR, at least up to 2012, as SFH commissioned an independent evaluation of change in this and other ENR indicators between the two Demographic and Health Surveys in 2007 and 2012.

The analysis compared four of the eight ENR states with four states where ENR had not operated. This found that ‘the likelihood of condom use in the last non-marital sex among males was 1.36 (95% CI = 1.03 – 1.80) and in females 1.73 (95% CI = 1.11 – 2.70) for ENR states compared to non-ENR states’.[3] So for every hundred men using a condom in the non-ENR states in 2012, 136 did so in the areas covered by ENR; and for every 100 women who reported that their male partner used one, 173 did so in the areas covered by ENR.[4]
[3] Independent Cross Sectional Assessment of ENR States Evaluation Report, Meldsak Resources Ltd, Abuja, November 2013, pp3-4.
[4] It is difficult to interpret the much higher figure for women. It would be useful if USAID, if it goes ahead with its planned Total Market Approach to condoms, repeated this analysis after the next DHS.

On this basis, outcome performance is assessed to be A+: Outcome moderately exceeded expectation

Output Score and Description

A+ Outputs moderately exceeded expectation

Output	Description	Score	Weighting	A+
1	Strengthening stewardship for sustainable and effective multi-sectoral and evidence -informed HIV prevention response by federal and state government	A+	25%
2	Improved institutional and technical capacity of civil society to engage in HIV and AIDS prevention and care and support interventions	A+	15%
3	Improved knowledge, change in attitudes and availability of commodities conducive to safer practices for effective HIV&AIDS prevention	A+	60%

Lessons and how these have been shared

Co-location was a valuable strategy: ENR co-located in 7 states except Lagos with the SACAs. This not only proved to be a cost-saving strategy as the programme did not have to pay for rent and other related expenses but also enabled a very cordial relationsip between the ENR state teams and their respective SACAs. The SACA benefitted immensely from the presence of technically sound professionals in the same location and that not only helped streamline many technical issues but also enabled capacity development in more practical forms of working together, mentoring and learning by doing.

Working directly with State Ministry of Health (SMOH) and State Ministry of Education (SMOE): Initially ENR state teams worked with state ministries of health and education only at the behest of SACAs, which also meant that ENR neither proactively sought ways of assisting SMOHs and SMOEs nor reached out to these partners to assist them in their existing roles. After the Annual Review of 2011/12 ENR changed this strategy and engaged directly with both SMOHs and SMOEs and helped them streamline their institutional processes and built the capacity of their personnel. The result is visible in the dramatic improvement in the institutional capacities of these stakeholders. The strategy has worked well and the lesson is that in a multi-setoral intervention it is important to identify the most critical sectors and extend assistance to help these sectors in improving their organizational processes and capacities so that they can play their roles effectively in the larger cross-sectoral strategies.

Evidence seeking and utilization: Up until 2011 most attention was being paid to key populations at risk for implementing interventions for prevention and control of HIV transmission. However in 2011 ENR conducted a Modes of Transmission study across all states which revealed that the mode of transmission in Nigeria was largely due to heterosexual behavior among the general population. This revelation had a deep impact on the thinking and nature of HIV response in the country. The lesson is that international experience and examples are important to learn from but seeking evidence and basing strategies on factual realities is critical to success of programmes such as HIV-AIDS control programmes.

Institutional strengthening: Organized, planned and standardised institutional capacity assessment, gap analysis and capacity development are critical elements for any long term response that needs orchestrated and coordinated functioning of various partners. Unless the key government institutions and stakeholders have established mechanisms to plan, program, budget, resource, implement and monitor, issues like HIV-AIDS cannot be effectively addressed.

ENR had three main components – institutional strengthening of government and civil society, prevention interventions and demand-supply for testing and condoms. In terms of sequence, the most critical element in longer term strengthening of national and state responses is to build the capacity of national/local institutions responsible for planning and implementing the interventions to prevent and control HIV-AIDS. Therefore ENR’s attention to strengthening the capacity of NACA, SACAs and at federal and state levels: MOH, MOE and Technical Working Groups, was an extremely valuable investment. All these forums have shown excellent development and maturity and there is promise that the responsible institutions in the country have the ability to plan and implement HIV response in the country.

ENR proved through championing the NHOCAT tool and ensuing capacity development process that the strengthening of government institutions is both possible and effective. It is recommended that future programs include a clear integrated component of institutional strengthening so that the government counterparts have adequate momentum and capacity to continue the essential elements of the required response which the programme had itself been a part of.

Counselor-Tester strategy: ENR’s intervention to raise awareness using community-based counselors was successful in increasing the knowledge and awareness among masses about HIV. This led to demand for testing. ENR trained their counselors to perform rapid testing at community level. This step created a workforce of community based counselor-testers who not only created demand for testing but also met the demand by providing testing services: a unique combination of demand and supply. Given the dearth of health workforce who are trained in testing, other partners can take up this good example and lesson of combining the demand creation and supply provision for HIV testing as it is both effective and efficient.

Start with the end in mind. Develop the exit strategy from the initial design, and work towards this throughout implementation.

Free condoms: The paid-for market (subsidised socially marketed and full-price commercial) has to compete with free condoms provided through the public sector. Despite the economic turbulence of the last 2-3 years, the paid-for condom market is actually fairly ‘orderly’, where the numbers sold rise and fall with little volatility, reflecting well-understood factors such as competition, price and the level of promotion. It is the free distribution which is ‘disorderly’ – unplanned and unco-ordinated in equal measure. There does not appear to be much evidence one way or the other that condom use by Most At Risk Populations (MARPS) in Nigeria is or is not increased by them being free, or that price is a significant barrier to use among the clients of female sex-workers.[5] Given the potential for free distribution to disrupt the commercial market, this approach should be based on more hard evidence that it produces better results.
[5] There are certainly many social marketing programmes around the world which target brothels and hot-spots such as truck-stops as places where they can sell condoms.

Developing a healthy market: The market for paid-for condoms in Nigeria is strong, dynamic and competitive. DFID played a big part in creating and developing this market. DFID supported the market (through a series of programmes, the last of which is ENR) from very small beginnings more than a decade ago – setting up the Gold Circle brand targeted at the bottom of the market, making substantial investments in demand creation and behaviour change, and expanding distribution reach to rural and hard to reach areas. This opened market space for a variety of other commercial players to develop and market differentiated brands, with the result that total market size increased dramatically, with Gold Circle’s share of the market dropping from around 95% to 70% in 2014. From 2015, the gradual removal of subsidies on the Gold Circle brand has seen its volumes slightly diminish, but new entrants such as DKT and other players have increased their market share. Competition is good for everyone – for government and for donors as they have a choice if they want to influence the market; for those who work for social and commercial marketing companies, as it keeps them on their toes and stops them getting complacent; and most of all for consumers.[6] It is very important that the currently competitive nature of the condom market is maintained.[7]
[6] For an early warning of the threat of social marketing monopolies, see ‘Social marketing brands – who owns them and does it matter’, Futures Group 2002. http://www.eldis.org
[7] For a recent review of this topic, see Achy & Joekes, eds, Competition policies and consumer welfare: corporate strategies and consumer prices in developing countries’, Elgar, 2016.

Need for a Market Shaping Intervention before transitioning subsidised products and services to cost recovery: Transitioning heavily subsidised products to cost recovery requires long term preparation. DFID’s over ten year market shaping intervention was central to the core ambition of transition to the social enterprise model. In the Promoting Sexual Reproductive Health and HIV Reducation (PSRHH) programme and even more in the Enhancing Nigeria’s Response to HIV&AIDS Programme, the investment in extensive generic condom promotion contributed in no small measure to reduce the entry barriers to the condom market for private sector actors. This resulted in the growth and expansion of the Nigeria condom market with about 200 brands and associated variants flooding the market. The massive promotion also resulted in commodification of condoms such that they became acceptable as a lifestyle product and widely expanded the channels of distribution and sales. An extension to Gold Circle the SFH socially marketed brand was pursued with the objective of using product enhancement and higher packaging aesthetic to wean some of the beneficiaries of the subsidy on the “classic” Gold Circle to this new Flex variant. This lesson is important as there are ongoing debates on transitioning other family planning products to cost recovery. Without the market shaping intervention over the long haul, it is doubtful if the ongoing success in transitioning condoms to cost recovery would have been possible.

Beware of standard indicators: The catch-all definition of ‘high-risk sex’ is too broad to be useful as a grouping of people who may or may change their behaviour. SFH defended using this on the grounds that it is a UNAIDS’ definition, which is true, but that does not mean it is useful for programming. It is obviously far too broad to do any form of target marketing, which is why SFH itself segmented its audience further – it just did not include any indicators to show its impact on the different segments. The lesson is for DFID to learn, that having too few or too high-level logframe indicators risks having indicators which are not actually an indication of anything.

ENR conducted a series of dissemination events in 2015 to share the lessons learnt from the first phase of the programme. A similar dissemination event to share the lessons from the second phase is planned to take place by May 2017.

Gender Mainstreaming
ENR’s objectives have largely been focused to empower women to play a more meaningful role in their own and other women’s lives with a specific focus on HIV prevention, stigma reduction, and their ability to make relevant informed, rational and independent choices. ENR’s Gender Mainstreaming strategies have been aimed to reach these objectives.
Gender has become a part of the Policy and Advocacy Technical Working Groups in all ENR states except one state where a separate Gender TWG is functioning. These Gender (Policy & Advocacy) TWGs are functioning and meeting regularly with clearly agreed and understood TORs. Additionally all SACAs, CSOs, LMs and all TWGs have dedicated Gender Focal Persons. The state strategic plans and operational plans are being reviewed with a Gender lens to assure that Gender is mainstreamed in these plans. ENR’s assistance has deepened the understanding of policy makers and programme implementers on using Gender lens in analysing, interpreting and using data in programme planning and allocative decision making. One of the most significant developments with respect to Gender empowerment is the appearance and growing acceptance of the female condom marketed by SFH.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthening stewardship for sustainable and effective multi-sectoral and evidence -informed HIV prevention response by federal and state government
Output number per LF		1	Output Score	A+
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Capacity of national, state and selected sector MDAs to provide gender-responsive policy, planning and coordination of the HIV prevention response.	The federal and at least 5 ENR states has an OCA threshold of 60%	Milestone exceeded with all 3 MDAs at Federal level and in all 8 States achieving an OCA threshold of 60% and all aggregate scores equal to or above 70%: 70% (Federal), 73% (Enugu & Ogun), 74% (Akwa Ibom), 75% (Kaduna), 77% (Cross River), 78% (Nasarawa), to 80% (Benue and Lagos)
1.2 National, States and selected MDAs harmonizing and coordinating the HIV & AIDS response	7 ENR State SACA with a Unified State Operational Plan	Exceeded with State Unified Operational Plans developed by all 8 ENR States
	NACA and 7 ENR States producing programme reports	Achieved with NACA and 7 States: Akwa Ibom, Benue, Cross River, Enugu, Kaduna, / Nasarawa, Ogun
	NACA and 5 ENR state producing Financial reports	Exceeded with NACA and 7 States: Akwa Ibom, Benue, Cross River, Enugu, Kaduna, / Nasarawa, Ogun
	The Federal and 6 ENR states have functional Prevention, M&E and Policy & Gender TWGs	Exceeded with Federal and 8 States: Akwa Ibom, Benue, Cross River, Enugu, Kaduna, / Lagos, Nasarawa, Ogun
1.3 Use of disaggregated (sex and others) data from Nigeria National Response Information System NNRIMs, / National Surveys and other sources to inform HIV prevention at all levels	NNRIMS and other relevant study data used for evidence and informed decision making		Achieved: National and 8 states
	NHRC established as a national resource base for information storage, retrieval and management		Achieved: Established at National
	NSP/ENR state operational plans reflect areas of need as identified by available reports (ERPS, MoT, NDHS, NARHS, IBBSS etc.)		Achieved: National and 7 states
	Eight focal ENR states produce issue based policy briefs and fact sheets using MOT and other sources of Evidence		Achieved: National and 7 states
	Seven ENR states use the Incidence modelling and / epidemiological synthesis studies, other studies used for designing prevention strategies		Exceeded: National and 7 states

Key Points: ENR achieved 5 and exceeded 5 of the 10 milestones under this output with State capacity now existing for continued progress.

Summary of responses to issues raised in previous annual reviews (where relevant)
The NHOCAT has been simplified and made cheaper. It uses a traffic-light system for grading and avoids duplication by development partners. PMTCT Plans have been developed in 6 states by SMOHs. ENR has also prioritized support to Policy, Advocacy and Gender TWG, to Preventop TWG and to M&E TWG. The NACA-SACA-LACA operations manual had been developed but not yet domiciled in an organization or in use. Gender focal persons had been installed in all MDAs, adequate progress is yet to be seen. ENR had also promoted the use of Gender lens to examine policies, plans and budgets however more effort needs to be put in to make the HIV response more Gender responsive.

Recommendations for future programmes
1. ENR proved through championing the NHOCAT tool and ensuing capacity development process that the strengthening of government institutions is both possible and effective. It is recommended that future programs include a clear integrated component of institutional strengthening so that the government counterparts have adequate momentum and capacity to continue the essential elements of the required response which the programme had itself been a part of.
2. Gender audit of policies, plans, programmes and budgets or any other intervention for HIV-AIDS needs to be done so that specific issues can be identified and progress against planned actions can be assessed.

Output Title	Improved institutional and technical capacity of civil society to engage in HIV and AIDS prevention and care and support interventions
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	15%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of States in which at least 10 SACA verified CSOs are equipped with skills in evidence informed prevention methodologies [8][9][10]	7 states have at least 10 CSOs with required skills [11]	Exceeded: In 8 states: 245 SACA verified CSOs trained; 107 equipped with tools and 135 both trained and equipped on use of appropriate HIV prevention interventions
2.2 Number of States with Legislation to protect the rights of people living with and affected by HIV&AIDS	5 ENR states have anti stigma legislation to protect the rights of PLWHA	Achieved: 7 states have anti-stigma legislation - Kaduna, / Nasarawa and Cross / River, Benue and Ogun. Lagos and Enugu had at baseline. Akwa Ibom’s bill has passed 2nd reading at the Legislature.
2.3 Number of ENR CSO Grantees with demonstrable Organizational capacity for effective HIV programming	15 CSO grantees	Exceeded: 20 out of 25 CSO grantees demonstrate organizational capacity for effective HIV programming with a score of 4 and above in PADEF
[8] “Skilled in evidenced informed HIV prevention methodologies” means the CSO has received training and is competent in the implementation of either PEP among MARPs, PLACE, STAR and General Population IPC intervention.
[9] This is a new indicator introduced May 2012 in response to 2011 OPR recommendations
[10] Verified implies that the SACA CSO mapping process for the HAF fund has established that the CSO is an authentic organisation performing developmental work as a representative of the civil society in the state and registered with a state body”
[11] 2012 and 2014 milestones were introduced as result of introduction of new indicator in 2012 based on 2011 OPR recommendations

Key Points
CSOs were producing and implementing organisational strategic plans and annual operational plans and were found to be much more confident and were planning for Private–Sector resource tapping for continuity of their HIV prevention programmes. They have also started to use the ENR initiated prevention methodologies mentioned above in other donor (UNICEF, USAID, WB) funded programmes. A large proportion of ENR supported CSOs had also been successful in receiving HAF 2 funds and ENR provided mentoring and support to these HAF2 grantees to ensure effective implementation. ENR had widely disseminated the Anti-Stigma law among stakeholders and CSO-networks have started to assume a watchdog role for rights violations of People Living with HIV-AIDS, maintaining Stigma Diaries with violations being reported to national level. The PADEF process of CSO capacity assessment and consequent capacity development has been adopted by many donor partners.

Summary of responses to issues raised in previous annual reviews (where relevant)
Having achieved the targets, ENR had revised the indicators to accommodate the change and had also increased the targets for indicators 2.1 and 2.3. ENR had developed a CSO strengthening toolkit however the institution where the CSO toolkit would eventually be domiciled and used had not been clarified till the time of this review.
Recommendations for future programmes
1. A formal reporting process to SACA should be developed for the cases reported under the Anti-Stigma Laws and the Annual Programme Reports should include a section on these cases without revealing identities of parties.
2. NACA to disseminate and legitimize the CSO Management Manual/toolkit with CSOs in the sector.

Output Title	Improved knowledge, change in attitudes and availability of commodities conducive to safer practices for effective HIV&AIDS prevention
Output number per LF		3	Output Score	A+
Risk:		Major	Impact weighting (%):	60%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)		Targets		Progress
3.1 Proportion of females and males in ENR states with accurate knowledge of HIV/AIDS prevention using the UNAIDS prevention knowledge indicator		ENR states / M 44% / F 33% / Source: NARHS; SHARHS, NDHS, NPC		Sex % Progress / M 47% Exceeded / F 45.1% Exceeded / Source: SHARHS 2016
3.2a Proportion of females and males in ENR states with non stigmatising attitudes towards PLWHA. (ENR stigma indicator) / 3.2b Proportion of females and males in ENR states with non-stigmatising attitudes towards PLWHA. (Adapted UNAIDS stigma indicator)		ENR states / M 40% / F 38% / Sex ENR states / M 19% / F 14%		Sex % Progress / M 53% Exceeded / F 51.7% Exceeded / Source: SHARHS 2014 / Sex ENR states Progress / M 20.8% Exceeded / F 15.5% Exceeded / Source: SHARHS 2014
3.3 Number of commodities distributed nationally	Male condoms 130 million, 44% of cost subsidised / Gold circle Flex and other variants 2 million, cost recovery		Male condoms 122 million , 58% of cost subsidised Not achieved / Gold Circle Flex and other variants 4 million, cost recovery Substantially exceeded

Key points
After remaining flat during the early years of ENR (not shown in table above) there was a steady increase in accurate knowledge of HIV prevention from 2013-15 among both men and women, plateauing among men in the final year but continuing to increase among women so that by the time of SFH’s 2016 survey women (45%) were nearly as knowledgeable as men (47%) on this.[12] Note that this indicator is a ‘strict’ one, so-called ‘comprehensive knowledge’.[13] On the separate items of knowledge, in 2016 90% of respondents has heard of HIV/AIDS, and of those 85% knew there is no cure. Of the ways to prevent infection, 57% said ‘staying with one faithful uninfected partner’, but only 41% said ‘using a condom every time’, 17% said ‘avoiding sex with people who have many sexual partners’, 14% ‘avoiding sex with commercial sex-workers’ and only 10% said ‘reducing the number of sexual partners’. On all these indicators, younger people aged 15-24 knew less than adults did.
[12] State-Specific Survey of HIV/AIDS, Reproductive and Child Health Survey 2016 (SHARCHS 2016), Jan 2017 draft from SFH Research, Measurement and Results Directorate.
[13] The UNAIDS definition of this indicator specifies that respondents who have comprehensive knowledge of HIV & AIDS are those who correctly identify the two major ways of preventing the sexual transmission of HIV (using condoms consistently and staying with one faithful uninfected partner), who reject the two most common local misconceptions about HIV transmission and who know that a healthy-looking person can have HIV. Being a composite indicator, respondents were required to have answered all the five questions correctly to be considered as having comprehensive knowledge of HIV/AIDS.

ENR’s 5/5[14] campaign and the associated stigma reduction 4/4 campaign have been particularly successful in creating the change in knowledge. 3651 Inter-Personal Communication/Health Promotion agents were trained of which 2274 were engaged by ENR and 1377 were engaged by MDAs. These efforts are also strengthened by mass media messages.
[14] After the results of the NARHS 2012, which showed lower than expected figures in a number of states including Nasarawa, Ogun and Akwa Ibom, ENR reviewed its strategy both in terms of scope but also with the aim to achieve scale. It developed a strategy to reach persons in these states within their homes which called the “house-to-house 5by5 campaign”. This was carried out in Akwa Ibom and Nasarawa States. During the programme it reached over 1.7 million people in these 2 states with appropriate information of HIV and AIDS. In Ogun State ENR linked the activity with the Insecticide Treated Net (ITN) distribution campaign. This has paid off as these are the same states with significant increases in level of knowledge and accepting attitude.

SFH’s proposal to DFID in 2014 projected sales of 140m Gold Circle (GC) and 1m of the higher-priced Flex in 2015, the first year of the No Cost Extension NCE (ENR phase 2) and 130m GC and 2m Flex in 2016, the second year.[15] These went into the NCE logframe as a 2015 milestone and a 2016 target.[16] Because SFH was entering uncharted waters with the NCE, the GC projections were much rougher estimates than the targets set during previous years, when it could be more confident about its projections. In the event, GC sales were lower (and Flex sales higher) in both years than SFH had anticipated back in 2014. This was because the price rise in January 2015 led to initial falls in purchases by wholesalers which were sharper than SFH expected (sales more than halved in the first month after the price rise, compared to the average of the previous 3 months), before recovering to about 75% of previous monthly levels.
[15] We presume that by 2015 Gold Circle sales volume will drop from 180 million per year to about 140 million, drop further in 2016 to 130m unit and settling at about 120 million per year in 2017. SFH No-Cost Extension Proposal to DFID, undated, p7.
[16] Cells G89 and H89 in the Logframe dated Nov 4 2014

This was partly because the other social marketing agency in Nigeria, DKT[17] was offering wholesalers especially good terms if they bought its ‘Kiss’ brand, the nearest direct competitor to Gold Circle;[18] partly because the recession in Nigeria reduced available spending power, so demand was weaker; and partly because SFH under-estimated the effect of the first price-rise in 3 years. One thing which did work in the poorer customer’s favour, however, was that the lack of coins available in the market means retailers tend to keep items priced at N50 at that price (the lowest denomination note) even if they are having to pay a bit more for them at the wholesaler.
[17] DKT International is named in honour of a pioneer of family planning in India, D.K.Tyagi. The organisation uses the initials of his name but never spells them out, it is called ‘DKT International’.
[18] We saw plenty of cartons of DKT’s ‘Kiss’ in the wholesalers which we visited in Lagos. DKT not only gave wholesalers credit (SFH only sells for cash) but had earlier done a ‘two-for-price-of-one’ offer.

Judging how consumers will respond to price rises is a tricky judgement at the best of times. SFH actually got the overall impact about right – they predicted they would lose about 25% of GC sales and they did, but it took longer than expected for sales to recover from the two price increases. SFH had little experience to go on – its predictions in future will likely be more accurate, given they have now raised prices twice.

Despite the price increases, subsidies on the Gold Circle brand only reduced to 58%, not achieving the planned 44% by 2016. This was due to the serious impact of Naira currency devaluation in 2016 (the currency lost more than 50% of its value in 2016). If exchange rates had remained at their 2014 level, the subsidy on Gold Circle would have met its 2016 target. SFH have adapted by cutting costs even deeper than planned, and extending the timeframe for full cost recovery from 2018 to 2019.

SFH’s higher-priced Flex condom, which it launched in January 2015 and re-tweaked in 2016 for launch in 2017 in new packaging, has sold better than anticipated (4m pieces in 2016 compared to the 2m target). This has helped to make the cost-recovery which SFH anticipated from the two brands together better than it would otherwise have been.

Equity
In its NCE proposal to DFID, SFH expected ‘some knock-on effects on equity’, predicting that raising the price to N50-60/pack might cause ‘at most 25%’ of poorer customers to stop buying Gold Circle. SFH could not know whether these people would switch to free condoms or stop using altogether, but they took comfort in what they foresaw as a big increase in the availability of free condoms which occurred during the NCE.[19] These may have been taken up by some or all of the former Gold Circle buyers. SFH suggested in its proposal that ‘equity of access may not be overly damaged‘, though it did not set up any specific monitoring for this so unfortunately we do not know the impact on equity. (ENR never had a logframe indicator for equity).
[19] A possible shortage of condoms at the lower end of the market was avoided because, starting in 2014 there was a spike in the availability of free condoms, due mainly to a one-off procurement of 150m by the World Bank on behalf of the FMOH, and slow distribution by NACA of 50m from GFATM.
SFH’s 2016 survey[20] captured condom brand by wealth quintile. This had not been collected before so we can only compare it to the 2013 NDHS, which asked a different question.
[20] SHARCHS 2016, see footnote 7 above.

Table 4. Men reporting condom use at last or recent sex, 2013 & 2016, by wealth quintile*
% men who reported they used a condom	Wealth quintile (1 = poorest, 5 = richest)*
who used Gold Circle	1	2	3	4	5
At last sex (NDHS 2013)[21]	79%	89%	86%	85%	74%
Most often in last 3 mths (SHARHS 2016)	71%	78%	74%	73%	65%
[21] Nigeria Demographic and Health Survey 2013, National Population Commission & IFC Macro, June 2014, p.101.

* Each quintile is 20% of households, equivalent to 20% of the adult population

The differences between the quintiles are small, but the pattern of both surveys suggests that, as we might expect, the richest 20% of condom users are slightly less likely to use Gold Circle (as they are buying more expensive brands such as Rough Rider or Durex), while the poorest 20% are also less likely to use Gold Circle (almost certainly because they are using either free condoms, or one of the very cheap Chinese brands).[22]
[22] The 2013 NDHS survey did not ask about free condoms as such or identify these as a ‘brand’, but none of the other 21% of users in the poorest quintile reported using a more expensive brand such as Durex or Rough Rider, while the great majority of the richest quintile not using Gold Circle reported using one of the two more expensive brands

The draft report of SFH’s own SHARCHS survey in 2016 shows a similar pattern, though the percentages using Gold Circle are lower, ranging from 65% for the richest and 71% for the poorest quintiles, and 73% for the second richest and 74% and 78% for the third and fourth. The figures are lower than in 2013 presumably because sales of Gold Circle had started to decline in 2016, following an increase in its price.

The age-group of condom users with the highest use of Gold Circle was the youngest, the 15-19 year-olds. This may be because they do not have good access to free condoms, and do not have the money to buy more expensive brands. It may also be a result of SFH deliberately keeping the price low while marketing Gold Circle as an ‘aspirational’ brand, this combination being particularly attractive to younger consumers.

Summary of responses to issues raised in previous annual reviews (where relevant)
#### Previous recommendations to SFH
Improve in-store displays of the Gold Circle brand and positioning. SFH to also include promotional materials in their condom packaging.
SFH has acted on the first of these, and has distributed 20,000 improved point-of-sale displays in 2016 with a further 20,000 planned for 2017.

Strengthen operations research to provide total market information on condom programming.
SFH commissioned Taylor Nelson Sofres (TNS) to analyse consumers’ brand preferences, and continues to use market research from FPwatch[23] (for which SFH is the main Implementing Partner (IP) in Nigeria) and other sources such as the ‘condom landscaping’ exercise which USAID has commissioned and which is ongoing.
[23] FPwatch is part of the monitoring for FP2020. See http://www.actwatch.info/

Develop an aggressive marketing and brand promotion model.
Despite spending less than planned in 2016 on trade marketing (£500K compared to the £850K budgeted) SFH continued to actively market its products, especially Flex. They also used digital media (one of the Flex spots on TV was trending for about two days on Twitter) and road-shows as well as having its existing staff of merchandisers working directly with wholesalers.

Develop a comprehensive and clearly articulated Draft Exit Strategy by June 2016.
SFH presented an updated Summary Business Plan 2017-19 to DFID in September 2016. This took account of the considerable macroeconomic shocks and risks experienced between 2015-2016, with updated stragetgies to mitigate them (such as lengthening the expected timeframe for full cost recovery from 2018 to 2019).

#### Previous recommendations to DFID
The last AR also recommended that DFID:
- intensify coordination with USAID on the Behaviour Change and Communication (BCC) agenda. In the event, DFID’s dealings with USAID in 2016 have been more to do with the latter’s plans for a ‘Total Market Approach’ (TMA) to condoms.
- reiterate DFID’s role in the ENR and ensure partners understand the strategy for ENR’s transition to full cost recovery. DFID has done what it can to achieve this, though stakeholders pay less attention to donors who are not putting money on the table.
- Continue the ongoing transition of procurement of condoms to SFH during the no-cost extension to strengthen in-house capacity for procurement management. DFID eventually brokered an MOU between Crown Agents and SFH to jointly procure 200m condoms, which will arrive in phases during 2017. This helped SFH to improve their procurement capacity and give them more procurement options, which will come in very useful when they face the challenge of replacing the condoms with a new procurement in 2018 and 2019.

Recommendations for future programmes

For Society for Family Health (SFH)

Manage change actively and be clear on your objectives
1. Maintain the things which have made SFH so successful - being responsive, nimble, motivated, thoughtful, interesting, transparent (and a pleasure to work with).
2. Be clear on the trade-off between making on impact on health and building and maintaining a sustainable business.[24] Be especially clear what you mean by terms such as ‘cost-recovery’ and ‘cross-subsidy’ and about what timeframe you are talking about.[25]
  [24] How you calculate this and how you use the calculations to make decisions are not the same thing - make sure everyone, including the board, is clear on both.
  [25] Working without donor funding requires quick decisions about the next 6-12 months, not leisurely decision-making about the next 3-5 years.

The loss of donor funding exposes SFH to new risks. Manage risks more robustly than ever before
1. Be prepared for shocks which you could withstand when you had DFID funding for condom social marketing but which will be tougher now (such as key staff leaving, or a donor dumping 50m free condoms).
2. Be prepared for some tough situations (such as Gold Circle sales declining to 50m pa, or Flex never getting above 5m pa[26]) and tough choices (such as letting go of loyal staff – or even pulling out of the condom market). Don’t be complacent, especially about competitors.[27]
  [26] Competition in the higher-priced market will be much fiercer than it has ever been for Gold Circle.
  [27] SFH staff said several times during the review that DKT is ‘dumping’ Kiss on the market. They are not – they are just competing with Gold Circle in a way any new player would.

Know your market much better
1. Really understand the condom user – and share most of that knowledge in a way which becomes the ‘common understanding’. Make SFH the go-to agency for anyone seeking information on the condom market and condom use.
2. Stop using ‘high-risk sex’ as currently defined – it is useless as a way of targeting any ‘behaviour change’ and harms your credibility as a serious player in HIV prevention. Adopt a segmentation of ‘risky sex’ which makes sense not just to you but also to less sophisticated stakeholders who are not familiar with the maths behind MoT or PSI’s models.
## For other programmes

Take account of the lessons from this programme highlighted on pages 6-8 of this report.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
Since 2012 SFH has reported ENR and now the NCE’s VFM with five indicators.
1. Efficiency - Overheads as % of total budgets compared to a DFID benchmark.
2. Efficiency - Overheads as % of total spend compared to a DFID benchmark.
3. Effectiveness - Cost per person reached by mass media messages
4. Impact - DALYs averted.
5. Cost-effectiveness - Cost per DALY averted compared to a WHO benchmark

Value-for-Money Indicators 2012-2016
Indicator	Benchmark	2012	2014	2015	2016
1. Overheads (OH) as % budget	22%	14%	12%	15%	15%
2. Overheads (OH) as % spend	22%	16%	8%	12%	9%
3. Cost/person reached by mass media	N50	N41	N28	N28	NA**
4. DALYs averted					12,076,367 (total)
5. Cost/DALY averted	£13-130		£10	£5	£4

** Not Applicable, as 2015 SFH now uses digital media, not comparable to mass media

All the annual reviews of ENR have concluded that SFH runs a ‘tight ship’, keeping good control of costs and taking account of VFM when making decisions.

Evidence from SFH’s decision-making during the NCE supports this conclusion. For example, in 2014 it launched a pilot scheme in Lagos to extend distribution of Gold Circle by having its salesforce visit smaller wholesalers. The last AR commended SFH for doing this and recommended taking it to scale. However, SFH rightly tested it first. As the ENR National Sales Manager explained to the review team during the visit to Lagos, ‘although the pilot did increase sales, when we looked at what it was costing us, it was clear that the benefits of additional sales were out-weighed by the costs. We had to hire extra staff, and the average sale they made was smaller than those of our regular sales-force who sell into bigger wholesalers, so the cost-of-sales was higher. It just did not add up’.[28]
[28] Nkiru Anonyuo, speaking to the review team in Lagos on Jan 12th 2017.

The decision to test it, rather than just go straight to scale; measuring how much it cost and comparing it to the benefits; and then deciding to scrap it; all these decisions are evidence of SFH management paying close and proper attention to VFM. Discussions with SFH managers during the review suggested that they were very conscious of other cost-drivers, such as packaging condoms by hand at the warehouse in Ota. Being aware of the things which drive costs, and being able to monitor them and take decisions accordingly, will become increasingly important to SFH’s new Strategic Business Enterprise as it seeks to become self-sustaining.

VfM performance compared to the original VfM proposition in the business case
This programme was designed before the business case system was instituted. A comparable VFM business case proposition is not available to make a useful comparison.

Assessment of whether the programme represented value for money
With a cost/ DALY of $4/DALY averted, this programme represents excellent value for money compared to all available benchmarks.

Quality of financial management during programme
SFH has maintained the high standards of financial management for which it has been praised in previous annual reviews. This is all the more commendable given the very difficult economic circumstances in Nigeria during this period.

Date of last narrative financial report	December 2016
Date of last audited annual statement	December 2016

E: RISK (½ page)

Quality of risk management over the life of the programme
Overall risks have been well managed during this programme. Risks around the condom social marketing component increased markedly during the second phase, with the main risks around the following:

1. Condom subsidy withdrawal & rise in prices leads to reduced condom use, particularly by the poor and high risk groups.
2. Commodities cannot be procured from program income using existing CA’s procurement route.
3. Exchange rate fluctuations undermine sustainability of the new social enterprise model (currency risk).
4. Free condom distribution undermines the commercial market for commercial condoms.
5. DFID exit from bilateral HIV support undermines credibility of DFID commitment to HIV in Nigeria.
6. Corruption leads to diversion of project funds and commodities

These were well managed using a comprehensive risk register. Mitigation measures were implemented and proved effective up to the end of the programme. Additional risks identified during this review for SFH (as well as Nigeria’s government) to manage over the longer term include:

1. Significant numbers of people might stop using condoms due to higher prices.
2. With the loss of donor funding, SFH may find it difficult to maintain rural distribution at existing levels.
3. Transition to the new strategy may be unexpectedly difficult (change).
4. Further weakening of the economy and foreign exchange difficulties undermine implementation.
5. Lower investment in generic demand creation leads to lower demand, particular in youth who have not been exposed to the heavy demand creation investment in previous years.
6. Perception of the risk of HIV declines and condoms become less desirable, particularly as options such as emergency contraception and medical abortion become increasingly available.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The project delivered according to its planned timeframe

Performance of partnership (s)

ENR has been implemented by a consortium comprising ActionAid Nigeria, Population Services International (PSI), BBC WST, Options Consultancy Services, Benguela Health Pty, Population Council, and Crown Agents. The Society for Family Health (SFH) is the Managing Agent. The quality of partnership between the members of the consortium, the Nigerian government, DFID, other development partners, civil society and the private sector to implement this programme has been excellent.

Asset disposal and value obtained by DFID

A number of programme assets were disposed of in 2015 and 2016, after the closure of the institutional strengthening phase of the programme and state offices in the supported States. Most assets were transferred to civil society and government partners, but residual assets were sold, from which DFID obtained value of £100,422.28.

DFID intends to transfer the remaining assets, including the commodity stock (condoms) and the balance in the programme income account to the Society for Family Health to enable the continued transition to the full cost recovery social enterprise model for condoms, which should continue to deliver development results indefinitely after the close of this programme. DFID has commissioned a closure audit (ongoing) which will quantify and assess these assets ahead of formal transfer.

G: CONDITIONALITY (½ page)

Partnership principles assessment

The programme was designed prior to the development of the Partnership Principles, so no role was envisaged for the Principles in the management and monitoring of the programme.

DFID Nigeria has now completed a Partnership Principles Assessment for Nigeria. The assessment indicates that the programme approach of working with government and other partners to improve health systems and service delivery, but not passing any funds through government systems, remains appropriate.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The theory of change has generally held true through out the programme. Except for the assumptions on macroeconomic stability during the second phase, the assumptions in the programme have held true. Modifications were made to the logframe to capture changes in targets and refocus of attention to priority areas but no fundamental modifications in the design of the programme was necessary during the first phase. In the second phase the programme strategy was adapted significantly to implement the transition to the full cost recovery social enterprise model for condoms.

The programme invested heavily in improving the evidence base for HIV prevention in Nigeria, and responded well to changes in evidence. For instance, the Modes of Transmission study stimulated a shift in the programme from a focus on Most At Risk Populations (MARPs) towards the general population. Sex, age, urban/rural and state based disaggregated evidence was constantly in use by the programme and formed the basis for programme management decisions as well as national response direction.

Monitoring progress throughout the programme

The ENR programme routinely monitors performance against logframe and non-logframe indicators and is able to analyse and present the data clearly. Data are collected through a combination of routine programme tracking and periodic programme-specific and national surveys. One weakness identified during this PCR is that the programme had only one indicator of condom use, when a more disaggregated picture would have been much more useful to monitor the condom market and take timely decisions. Although the first annual review highlighted this recommendation, it was not implemented up to the close of the programme.

This Project Completion Review was carried out by Dr Ebere Anyachukwu, Health Adviser and DFID Senior Responsible Owner for the ENR programme, with contributions from Ogechukwu Omeribe, Private Sector Adviser; Ededem Hogan, Programme officer; and Olatunji Ogunbanwo, Deputy Programme Manager, between January and March 2017. It draws heavily on work carried out in previous reviews of the ENR programme, particularly by Simon Azariah, Ojobo Atuluku and Alex Jones in the 2014 ENR annual review (which included a PCR of the public sector and civil society institutional strengthening components of the project); and by Bruce MacKay in the 2017 review of the ENR social marketing programme.

The review process included the study and analysis of relevant evidence, including surveys, reports and other information; interviews with relevant stakeholders, and visits to project sites, market participants, and competitors.

Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMPas part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised throught the duration of the programme which were not forseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process