Project Completion Review

Review Date:	31 March 2017

Title: Central African Republic (CAR) Humanitarian Funding to Central Africans, IDPs and Refugees 2014-2016
Programme Code: 204852	Start Date: 17 July 2014	End Date: 31 December 2016
If programme was closed >1 month early please describe in a few words why.			N/A

Summary of Programme Performance

Year	AR 2014/15	AR 2015/16	PCR 2014-17
Programme Score	A	A+	A
Risk Rating	High	Severe	Severe

Financial Position

Original Programme Value	£35 million
Extensions/ amendments	£ 5 million cost extension / (Business Case Amendment: 1 February 2016)
Log-frame revisions (with dates)	Original:12 December 2014 / Revised: 7 January 2015 / 6 July 2015 / 22 July 2016
Total programme spend	£39,711,508.77

Follow up actions required following closure

- Obtain overdue final reports from FAO
- Consider asset disposal requests in line with Smart Rules
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204852/documents / Business Case 5084736 / Business Case Addendum 5401581
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204852/documents / Logframe 5518518

This project completion review has been completed by members of the Sahel and West Africa, Humanitarian and Resilience team in the Africa Regional Department, and is informed by quarterly and interim reporting from partners, drawing on programme visits to CAR and Cameroon.

Outline of programme

The CAR Emergency Response programme was approved in 2014 and provided a package of support totalling £40 million. The programme addresses life-saving and protracted needs of conflict-affected populations in CAR and of CAR refugees in Cameroon and Chad who have fled the violent conflict since December 2013.

Agencies - CAR response	Total	Description
Common Humanitarian Fund (CHF)	£6m	Emergency multi-sectorial assistance
International Committee of the Red-Cross (ICRC)	£2.2m	Emergency and protracted assistance and protection
Food and Agriculture Organisation (FAO)	£6.1m	Livelihoods assistance
International Medical Corps (IMC)-led consortium*	£4.7m	Basic healthcare
Solidarities (SI)-led consortium**	£3m	Livelihoods and protection support
Agencies - CAR refugees
UN High Commissioner for Refugees (UNHCR) Cameroon and Chad	£9.5m	Emergency multi-sectorial assistance
World Food Programme (WFP) Cameroon	£4m	Food and nutritional support
MSF Cameroon	£1m	Emergency healthcare and nutritional treatment
START network***	£3m	Emergency multi-sectorial assistance
M&E	£0.5m
TOTAL	£40m

*NGO consortium led by the International Medical Corps providing healthcare.
**NGO consortium led by Solidarités International providing livelihoods and protection assistance.
***NGO consortium under secretariat of Save the Children UK.

Two annual reviews of this programme were conducted in July 2015 and July 2016 scoring an “A” (QUEST 5194121) and an “A+” (QUEST ID 5532542). UK funding has helped agencies provide a successful response to refugee needs and bring assistance up to minimum standards. Significant mortality drivers such as malnutrition have been brought under control thanks to DFID and other contributions. On that basis we assessed that the programme is achieving its outcome.

Expected Results

Impact: To save lives and reduce suffering of the population affected by the ongoing crisis in CAR, including refugees in the region. The target is to reach 1,460,735 individuals with DFID humanitarian assistance in CAR and CAR regional in 2014/2016.

Outcome: Central Africans access essential services through multi sectoral relief effort.
- Target 1: 993,728 individuals reached with DFID humanitarian assistance in CAR.
- Target 2: 467,007 CAR refugees reached with DFID humanitarian assistance.
- Target 3: Crude mortality rate in prefectures of intervention does not increase.

It should be noted that DFID calculates beneficiary reach for some partners as a proportion of funding against the overall appeal (ICRC) or against all funds received that year (CHF). ICRC’s mid-term review led to a minor drop in overall budget, so that by the end of 2015, DFID’s contribution represented 8.9% against the total appeal and we have calculated that 8.9% of beneficiaries reported in the ICRC annual review were DFID-attributable. By the end of 2015,	DFID’s contribution to the CHF represented 36.6% (after the release of surge funding to address needs in September 2015). We have therefore calculated our beneficiary reach as a 36.6% proportion of the CHF total reach. Additionally it is important to note that as the CHF’s coverage is country-wide, some double counting of beneficiaries with our other partners is possible.

Context in which UK support is provided

From 2013, violence in CAR took a sectarian turn with increasing inter-communal incidents and violence by self-defence militias (anti-Balaka) systematically targeting Muslim populations. The conflict forced the displacement of more than a million people, of which 420,000 are still internally displaced and 470,000 are refugees. Since September 2014, a 12,000-strong UN peace-keeping operation (MINUSCA) has endeavoured to stabilise CAR. Armed and sectarian violence continue however to threaten the population and humanitarian actors and hinder economic recovery.

Presidential and legislative elections took place in 2016 ending the transition that began in 2013. President Touadera was successfully inaugurated in March and nominated a Prime Minister and government in April. Despite this progress, needs remain extremely high and food insecurity affected 50% of the population in 2015. The health system is reliant on humanitarian organisations and the country’s gross national product is still 30% lower than in 2012. CAR’s refugee population were welcomed in Cameroon, Chad and the DRC, with needs in Cameroon proving particularly serious and acute malnutrition reaching 30-40% of children in some locations in 2014.

The UK has so far provided £82 million in humanitarian aid to CAR and CAR refugees since 2013 (and £2.5 million in development funding through central programmes), making the UK CAR’s third largest humanitarian donor in 2016. In 2016, DFID approved a multi-year business case that provides £36 million in assistance to CAR populations and refugees from 2016 until March 2019, and plans for a £24 million contingency reserve to address surges in needs.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

Impact

Under this programme, DFID reached 2,401,765 people with humanitarian assistance (including double counting across agencies[1]) compared with the initial target of 1,460,735. This includes Central Africans in CAR, Central African refugees as well as other vulnerable people affected by the crisis including Chadian returnees and vulnerable host communities.
[1] This means that one person might have benefited under multiple programmes and have been counted multiple times.

Outcome

Outcome 1: Cumulative number of Individuals reached with DFID humanitarian assistance (food, health, cash, agricultural inputs) in CAR in 2014/2016.
- Target: 993,728
- Final result: 1,582,422

Outcome 2: Cumulative number of Individuals reached with DFID humanitarian assistance in CAR regional in 2015/2016.
- Target: 467,007
- Final result: 819,343

Outcome 3: Crude mortality rate in prefectures of intervention does not increase
- Target: Crude Mortality Rates in 3.14 (Ouham), 3.34 (Nana Gribizi), 0.82 (Basse Kotto), 0.75 (Haute Kotto), <1 (Bangui)
- Final result: Unfortunately we are unable to report on this outcome as there has not been a national SMART survey conducted in 2015 as was the original plan. According to UNICEF they have organized instead specific Nutrition SMART surveys in IDPs and Muslims enclaves sites to complement the findings from the last nationwide SMART survey done in 2014 (used by DFID as baseline above). From the data available for these surveys, crude mortality does not appear to have been estimated as is sometimes the case in extremely insecure settings as this adds significantly to the time spent on the ground by the survey teams. Additionally, these surveys did not use the same geographical boundaries as the 2014 national survey (baseline) and hence the results would not have been comparable. As DFID was not providing funding for these surveys we were not consulted regarding the survey methodology or geographical coverage. A new nationwide SMART survey is planned to be carried out May-June 2017.

Output Score and Description

This project has scored an A – outputs moderately exceeded expectations. The breakdown per output is below.

CAR
- Output 1: Livelihoods and Food security A – outputs met expectations
- Output 2: Health and Nutrition B – outputs moderately did not meet expectations
- Output 3: Protection A – outputs met expectations
- Output 4: Performance of system and humanitarian coordination A – outputs met expectations

CAR refugees
- Output 5: Food Security A – outputs met expectations
- Output 6: Health and Nutrition A+ - outputs moderately exceeded expectations
- Output 7: Multi-Sector (UNHCR) A++ - outputs substantially exceeded expectations
- Output 8: Multi-Sector (START) A+ - outputs moderately exceeded expectations

Lessons and how these have been shared

DFID field visits continue to be critical in capturing the experience of beneficiaries receiving assistance and in highlighting programme quality issues. This information is not always captured in partner reports but has enabled DFID to remain sighted and support quality assurance.

Great advances have been made in encouraging partners to improve monitoring and procurement. However, pipeline breaks and stock-outs continue to be an issue for many partners and therefore require further monitoring by DFID. Fraud reporting amongst partners has also improved now they have a better understanding of DFID’s definition of fraud.

Maintaining access to intervention areas continues to be an issue for many of our partners due to the challenging security situation. DFID monitoring and partners efforts need to continue on ensuring that security management processes are ongoing and effective and that contingency plans are in place in order to reduce impact when access is temporarily lost.

The scale and severity of refugee needs in this crisis led DFID to make the decision to start funding in a new country. The success of the intervention so far in providing life-saving assistance in the targeted areas justifies this decision to intervene.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Livelihoods and food security. The agro-pastoral production in the targeted areas is improved and reinforced
Output number per LF		1	Output Score	A
Risk:		Severe	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Target	Final reach
Number of people reached through general food distribution and cash transfers by ACF/DRC/SI	480	570
Number of people reached through livelihood assistance by ACF/ DRC/ SI	158,750	150,978
Proportion of the targeted population improving their Coping Strategy Index Score	50% - June 2016	DRC – 86% / SI – 33%
Number of people reached through general food distribution, cash and voucher (GFD) by the ICRC	8,932 - March 2016	6,347
Number of people reached with livelihood assistance by ICRC	4,015 - March 2016	6,582
Number of people reached in food security/livelihood sector by CHF	3,540 - March 2016	8115
Number of people who have received livelihood assistance through the FAO	372,060	585,500
Proportion of FAO project beneficiaries that are not induced to resort to negative mechanisms at least for six to eight months	95% - March 2016	60%

Key Points

This output started in April 2015 with some aspects lasting until December 2016.

ICRC reviewed its targets and objectives at the mid-term review point in 2015, leading to a slight decrease in budget and in turn a higher beneficiary share for DFID (8.9% of overall appeal value instead of 6.6% at onset of the programme). ICRC completed their seed assistance operation in 2015. Their overall livelihoods reach proved higher than planned (by 22%) while their food and voucher assistance ended up much lower (52%), reflecting changing needs. Positively, ICRC provided substantial assistance in Bangui in the form of cash. Due to the changing context/security ICRC had to refocus their food security and livelihoods intervention towards the end of 2015 to focus on more straightforward food and non-food items (NFI) assistance (including some emergency food distributions end of 2015) and had to put some of the more longer-term activities on hold. This illustrates well the organisation’s capacity to adapt to a changing and difficult context and ensuring their activities are relevant. Insecurity also impacted the 2015 post-harvest monitoring (PHM) which could not be carried out. ICRC launched a wave of cattle vaccination that was successfully carried out.

FAO part one was completed in June 2016 and part two finished in November 2016. There were initial challenges in 2015 due to delays with the signing of the grant which resulted in the seed multiplication activity having to be run through other funding instead of through DFID. Meanwhile, FAO was able to sign many agreements with partners that entailed in-kind donations only and were complemented by other funding sources to cover support costs. This enabled FAO to make savings, which were used to reach additional beneficiaries. This led to a reach almost twice as high as initially envisaged. Due to issues around targeting criteria, FAO have planned on refreshing partner training on this topic in order to increase adherence to the selection criteria.

The post-harvest survey results for the 2015 agricultural campaign were positive. However, the data collection was weak and the methodology allowed for some overrepresentation of under-served areas which FAO strived to address in 2016 by piloting a new method by which a random selection of beneficiaries were given a booklet at the beginning of the planting season to complete and return after harvest. Unfortunately this method proved difficult to implement as response rate was only around 50%. The same method will be tried again next year but with reinforcements to promote a higher response rate.

Overall the activities towards the agricultural season in 2015 were implemented on time but some seeds had a lower germination rate than expected. This was most likely due to the heavy load of the trucks leading to damaged seeds and to suppliers mixing higher and lower quality seed supplies. Following this FAO tightened their quality check protocols in 2016 which in turn led to higher germination rates. The piloted seed fairs in 2016 proved to be very effective and encouraged local producers of seeds in the area as well as giving the farmers the choice of what they wanted to cultivate on their land. However, due to the rapid roll out of this pilot there was a poor understanding among some of the retailers on the voucher system which led to inflation in the price on some of the more popular seeds. Additionally there were problems around the payment processes taking a long time due to issues with the bank. The plan for 2017 - under the 2016-2019 Central African Republic Humanitarian and Recovery Programme ‘CHURP’ - is to scale up this activity to 5,000 beneficiaries as the results overall last year were very beneficial however this year it will be restricted to only semi-urban areas with a functional banking system.

The vegetable gardening project progressed with some delay due to surges in violence in September/October 2015 and further incidents in Bambari, and required a no-cost extension. Beneficiary feedback has been positive however there is a need for the intervention to incorporate a more nutrition sensitive approach in future as mothers complained of difficulties getting time to feed their children due to spending long hours in the field and requested more information on how best to feed their children with the food they were producing. On staffing, the monitoring and evaluation (M&E) capacity is still limited and is constrained mainly by the decline in funding. To reduce the impact of this on the quality of programming staff based at headquarters (HQ) are “loaned out” during post-distribution monitoring (PDM) and PHM time. They are now well represented for field-level staff and able to carry out their work at scale.

The Solidarités International (SI)-led Consortium experienced many difficulties in implementation of the programme. Security was a big issue as the consortium operates in a highly insecure area. Frequent clashes meant that access was lost on major axis leading to delays in implementation resulting in two no-cost extensions.

During the programme the consortium experienced difficulties in harmonising beneficiary targeting methods as well as the timeline for activities. This, and the tools for monitoring, have now been addressed though some flexibility is still required due to the differing contexts of the consortium members. Additionally the consortium faced difficulties in its agricultural activities due to the late arrival of seeds from the FAO as well as poor germination rate likely due to poor storage and transport prior to the delivery of the seeds. For next year’s programme local procurement options will be explored in order to avoid this issue. This also led to a lower proportion of beneficiaries actually sowing their seeds due to the planting season already being well underway and hence some agricultural groups pulled out of the activities. For next year’s programme a larger component of cash will be considered.

A local market assessment has been carried out to serve as a baseline. On vegetable gardening, good progress was made but there were some difficulties linked to procurement delays (caused by insecurity) and some crops not resisting the heat as well after a late delivery. In the future more attention could go into harmonising the design and strategy among consortium partners and where possible adapting procurement to the season. All the construction/rehabilitation of infrastructure of value to production such as markets, access bridges, cassava drying areas and multi-sectorial platforms were completed. Due to the insecurity and risk of looting however, at the time of the end of this project, the infrastructure built by DRC has not yet been effective and has not benefitted the target populations. DRC, who are present in the area, will follow up on this activity during 2017.

In terms of livestock, the purchasing process took longer than expected for both SI and DRC leading to a no-cost extension for three months for DRC. Both partners had to take into account the origin of the suppliers to ensure they were accepted by the recipient community and were not perceived to have links to armed groups. SI and ACF completed their livestock vaccination operation. DRC had issues with breakdown of fridges leading to a lower beneficiary reach than expected. A do no harm study was also carried out which helped identify key hurdles and led to a shift in activities to focus instead on support to small businesses.

The CHF reached approximately 22,173 DFID-attributable beneficiaries with food security and livelihoods programmes during the year. This total is eight times higher than planned targets, which DFID extrapolated based on reach in 2014. This increase reflects a drastic increase in livelihoods interventions to support returnee and displaced populations.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID to monitor SI consortium endeavours to reinforce income-generating activities (IGA) sustainability.
Income diversification is a key adaptation strategy for households to support their families when their main income sources are threatened. Therefore, the project gave special attention to stimulating and diversifying households’ subsistence activities. Throughout the project, more than 4,000 households adopted this strategy, which suggests that people have understood the value of income diversification. Nevertheless, monitoring of these activities has shown that almost half of these activities still suffer from poor management, which limits their sustainability and potential for growth. This issue will need to be addressed further in any future programming.

DFID to monitor FAO 2016 Post-distribution monitoring (PDM) and post-harvest monitoring (PHM) to assess overall results and seed qualities.
The PDM showed that 85% of the beneficiaries found the seeds provided to be of good quality however 15% of the beneficiaries did find rotten seeds particularly in the groundnut bags and therefore had to discard these leading to a lower yield. Additionally some beneficiaries found the quantity of seeds provided to be too low to be able to cultivate their whole land. This appears to be indicative of the relative calm in some of these areas which enabled beneficiaries to be able to go back to their abandoned land. The beneficiary satisfaction with the seeds from the piloted seed fair was slightly lower at 71% however the average area sown be each household was higher likely due a lesser diversification of crops allowing larger areas to be sown.

Recommendations

- Follow up with FAO on new pilot method of PHM to ensure higher response rate after 2017 harvest season.
- Follow up with FAO on incorporation of nutrition sensitivity in vegetable gardening activities
- Follow-up for future programming with SI consortium on strategies employed to counteract poor management of IGA’s and its impact on sustainability

Output Title	Health and Nutrition. Affected population have an improved access to healthcare
Output number per LF		2	Output Score	B
Risk:		Severe	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Target	Final reach
Number of beneficiaries reached in the healthcare sector by ICRC	30,422 – March 2016	4,670
Number of beneficiaries reached in the healthcare sector by CHF	120,888 – March 2016	110,690
Number of beneficiaries reached in the healthcare sector by the IMC consortium	269,354 - Sep 2016	317,755
Health service utilisation rate (based on number of beneficiaries reached with new consultations)	1/person/year - Sep 2016	0.46
Number of acute malnutrition cases from the targeted areas that gain access to treatment	1795 – Sep 2016	3431
2.6. Cured rate among children treated for MAM and SAM	>75% - Sep 2016	SAM:98.9% Haute Kotto , 72% Basse Kotto / MAM: 100% Haute Kotto
Number of health facilities with access to sanitation with a ratio of 1 latrine/ 20 users	10 - June 2016	10

Key Points

This output started in April 2015 and is contributed to by three partners (CHF, ICRC and IMC consortium). ICRC and CHF finished their activities at the end of 2015. The IMC-led consortium were granted a cost extension and completed their programme in September 2016. All partners continue to be funded by DFID under the CHURP business case.

In addition to supporting primary health centres and community-based malaria treatment activities, ICRC continued running the hospital in Kaga Bandoro and the war-wounded programme at the hospital in Bangui. The partnership had to be partially frozen several months with the Kaga Bandoro hospital after challenges with the local health authority, but was resolved in 2016. Across the country, ICRC focused on a communication campaign around acceptance of humanitarians and particularly around respect for the medical mission after several incidents in September last year. Due to increasing instability, ICRC refocused their activities on life-saving projects and preparedness for war-wounded and mass casualty situations. ICRC’s overall reach proved much lower as the catchment areas for health centres assisted in 2015 turned out to be half the size of those of 2014. (DFID’s results were extrapolated based on 2014 catchment areas.) ICRC also covered two health centres fewer in their activities than had been planned under their appeal.

Over 2015, the CHF reached in total 112,341 beneficiaries with nutrition services and 190,092 beneficiaries with health services. The DFID share represents 110,690 people, slightly below the extrapolated target for 2015.

For the IMC Consortium utilisation rates were impacted by limited access due to worsening security. For this reason, a network of healthcare workers was set up to be able to diagnose and provide treatment in the community for most common childhood diseases (Integrated Community Case Management - ICCM). Access to the health facilities continued to be an issue due to insecurity forcing IMC to temporarily shift its area of operation from two of the mobile medical units (MMU) to different localities also hosting a number of internally displaced persons (IDPs). Since January 2016, IMC had a psychiatrist working with them to reinforce their management of mental, neurological, and substance use disorders. This has proved challenging as, even with training, government staff did not have the capacity to carry out these activities and IMC therefore had to employ and train their own mental health staff to carry out case management according to Mental Health Gap Action Programme (mhGAP) protocols.

During the reporting year one of the partners in the IMC-led consortium, Save the Children (STC), decided to pull out their operation in the areas of CAR covered by the consortium and handed over their activities to INGO Cordaid which commenced operations in April 2016. Oxfam GB was also replaced by Oxfam Intermon, from the same Oxfam network. These transitions were overall organised cooperatively, however in the case of Coraid this did lead to some pipeline breaks. For all the consortium partners, stock-outs of essential drugs were a recurring issue – see below.

Throughout the programme there has also been concerns around lack of harmonisation on approaches used by the different partners. DFID therefore engaged in thorough discussion to ensure that future programming involves a solid technical platform and adequate harmonisation of partner approaches and tools etc.

More details on consortium partner’s performance are included in QUEST 5524222.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID to monitor IMC consortium stock levels of essential drugs and follow up on barrier analysis
Insecurity on the transport axis, delays in international shipping, poor stock management capacity and poor adherence to treatment guidelines were found to be major barriers to avoiding stock-outs. In terms of insecurity, the consortium partners have worked to put in place measures to mitigate the impact of loss of access on the axis such as providing alternative safe locations to meet for resupply. On the issue of international orders, this is a necessity for all actors operating in CAR as there is no central pharmacy and this creates a bottleneck with the internationally pre-approved vendors such as the International Dispensary Association (IDA). Unless a central pharmacy is set up in CAR, these issues are likely to continue despite the best efforts of our partners. In terms of stock management and adherence to guidelines, some training has already been carried out to improve on these aspects but as the education level and capacity of most staff is quite low more will need to be done to ensure their capacity is built to an acceptable level.

DFID to follow closely the implementation under new partner Cordaid, their plans on coverage expansion, and the potential roll out performance based management system.
Cordaid has faced some initial challenges in implementation due to issues in the handover process from STC which led to stock outs of drugs and medical materials in many of the supported health facilities. During the last quarter of the project (3 months after the handover from STC), Cordaid assessed the quality of the services provided in the supported health facilities. The results of the assessment highlighted several critical areas where improvements were necessary. In discussions with Cordaid they report that these issues have now been addressed. Due to security concerns, DFID staff have not yet been able to conduct a field visit to directly monitor the programme implementation under Cordaid however such a visit is being planned under the new programme. The geographical area in which Cordaid operates remains one of the most neglected areas and even prior to the crisis had some of the worst health indicators in the country. This explains some of the difficulties they are facing in operating in this area and also highlights the importance of maintaining a health programme in this area.

Recommendations for future programmes

- DFID to monitor partner efforts to analyse and improve utilisation rates and stockouts of essential drugs under 2016-19 project.
- DFID to follow up with Cordaid and the MENTOR consortium to do a more thorough assessment of the implementing partners implementation under the new programme as a follow up to the final assessment under this programme
- DFID to carry out field monitoring visit of Cordaid programme in Alindao under 2016-19 programme
- DFID to monitor and follow up on the progress of setting up a technical committee to ensure a cohesive approach amongst IMC/MENTOR consortium partners under 2016-19 project.

Output Title	Protection - Central Africans enjoy an improved protection environment
Output number per LF		3	Output Score	A
Risk:		Severe	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N

Indicator(s)	Target	Final reach
Number of beneficiaries supported in the protection sector by the CHF	43,080	137,381
Number of beneficiaries supported in the protection sector by the SI consortium	74,600	Final reach: 48,496
Increase in the % of people who have perceived an improvement in their protection and safety situation	+25%	64%
Number of GBV survivors who access remedial services through IMC, DRC and ICRC.	N/A	IMC 271 / DRC 261 / ICRC - 20

Key Points
This component started in April 2015. CHF and ICRC completed their activities in December 2015. IMC and SI consortium completed their activities in September 2016. All partners continue to be funded by DFID under the CHURP business case.

CHF reached 375,360 beneficiaries with protection interventions during the year. This amounts to 165% of the planned target, demonstrating a trend in the humanitarian coordination system to prioritise protection (seen as the overarching problem in this crisis). The Office for the Coordination of Humanitarian Affairs (OCHA) and the CHF developed a protection mainstreaming guidance for its partners shared for each allocation. In addition, training for all partners has been organised by the CHF with the ProCAP on protection mainstreaming in projects which took place in March 2016 after an initial delay due to insecurity. A gender specialist has supported clusters and partners in developing their proposals and has been working with the CHF to strengthen their gender M&E. A first round of sensitisation on protection mainstreaming was organised for CHF partners. The CHF will need to further develop its M&E and capacity building in this area in 2016-17 to continue strengthening partners’ capacity.

SI Consortium partner Danish Refugee Council (DRC) has formed protection committees tasked to progressively take over protection monitoring. Security incidents such as robberies and attacks on villages have forced the project teams to suspend their activities several times in different areas of the project. Such incidents caused a delay in the committees becoming fully functional. As a result some new groups had to be trained as well as some existing groups had to refresh their training before starting. As a result, the peace committees only began identifying and resolving conflicts in March 2016 which represents a delay of four months in the functioning of the committees. To overcome this gap, the teams focused on providing training and sensitisations on protection and social cohesion first, in order to achieve sufficient progress in the implementation of these activities, and then started to implement other activities once the situation became more stable.

In Batangafo the consortium faced a land dispute when building their listening centre for survivors of gender-based violence (GBV) which resulted in the construction having to be temporarily abandoned. This delay meant that the beneficiary reach was a lot lower than planned. In the meantime, a listening centre was built on a new piece of land. It was inaugurated in October 2016 and now provides psychosocial support and individual protection assistance to beneficiaries. Negotiations regarding the original site have since continued and the consortium remains hopeful that also this centre will be able to be completed and utilized for its intended purpose.

All other listening centres and the child friendly spaces are functional and in order to ensure that both Christian and Muslim youths have access to them DRC developed a non-aggression pact between Christian and Muslim youths prior to the opening. The youth centre management committee is comprised of a mix of representative youth leaders from both Muslim and Christian communities who were democratically elected during the General Assembly in March 2016. They lead the centre’s activities together supported by the Elder committee and the Sous-Prefet who support them during any difficulties or tensions.

The IMC Consortium worked with a limited team to do some protection monitoring and deliver GBV services. IMC also launched a series of public health education sessions on sexual and gender-based violence (SGBV) and female genital mutilation (FGM) among other topics. Additionally 12 community members were trained on providing psychosocial support to survivors of GBV. MENTOR Initiatives also conducted sensitisation on SGBV to heads of health centres and midwives to ensure referral to adequate services. STC also conducted training for the health staff on medical referrals of SGBV and skills training on empathetic listening. Oxfam implemented protection mainstreaming activities into their community mobilisation activities. For future programming the partners have agreed on a structure to better promote sharing of expertise among partners which will benefit those consortium members with relatively less experience in the field of GBV to improve and harmonise their programming.

ICRC’s approach to SGBV in Nana Grebizi has shifted the evidence burden, from requiring proof that there is an SGBV problem to start a psycho-social response, to starting a psycho-social response and requiring proof that there is no SGBV problem to stop it. Integrating the programme in wider healthcare provision has also been beneficial, enabling lower profile and easier access to the services. Additionally, improved information gathering has also fed into the organisation’s sessions on International Humanitarian Law (IHL) to armed groups.

ICRC’s protection work in prison was affected by events in September (which culminated in a prison break) but resumed thereafter. The ICRC is also looking to get support from an armed forces delegate in country and from a regional delegate to strengthen their work with internal security services. Some CAR authorities were sent to a regional workshop to help set up a cross governmental platform for management of mortal remains. Family reunification activities have continued but with some delay due to insecurity.

ICRC organised training in community-based protection (CBP) and is beginning to pilot this approach in CAR. Starting from the premise that populations are experts of their own lives, this approach aims to map with populations their problems, threats and coping mechanisms. Communities identify leading priorities, which can then inform programming in risk education, self-protection measures, risk reduction activities, protection engagement, community self-organisation and so on. Though this approach is in its early days, it is a positive example of participation and accountability in action and should be monitored and supported.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

- DFID to follow up on protection mainstreaming in CHF funded projects.
- DFID to monitor results and impact of ICRC community-based protection.
Output Title	Performance of the system and coordination - The CHF actively contributes to strengthened humanitarian coordination and response
Output number per LF		4	Output Score	A
Risk:		Major	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Target	Final reach
4.1. Percentage of overall funding received from all donors by 30 June 2015 is allocated before 31 December 2015/ received by 31 December 2015 and allocated before 30 June 2016.	> 80% - March 2016	82.8%
4.2. Percentage of projects monitored through field visits within their project duration	40% - March 2016	39%

Key Points

This component was completed in December 2015.

In 2015, US$ 27.74 million was transferred to participating organisations through the CHF, and US$ 25.90 million was reported in expenditure. With a delivery rate of 82.8% this is a solid indicator of the CAR Common Humanitarian Fund’s robust financial performance. In 2015 DFID contributed US$ 9,132,207 to the CHF which totals to 36.6% of total CHF funds for 2015. 77% of funding was channelled through NGOs and 23% to UN agencies and the International Organisation for Migration (IOM), making the CHF a solid channel to support NGO partners. Reflecting widespread needs, projects were fairly evenly allocated across sectors, with protection, health, food security, early recovery and WASH (water, sanitation and health) taking the bulk of funding.

Source: CHF annual report 2015
During the year 39% of the projects were visited for monitoring purposes. Targets are still at 40% making this year only slightly below target. The CHF began strengthening their M&E team and planned in 2016 to expand it and rely more heavily on OCHA. The CHF also started strengthening the gender and protection monitoring aspects in 2016.

The CHF management team focused heavily in 2015 on developing a solid partner performance and risk management system. Those were up and running and fully rolled out by end of 2015, and began informing funding decisions. The CHF also diligently followed up on incidents and losses affecting projects after the September 2015 events in Bangui. By mid-2016, the CHF presented the final CAR CHF guidelines to their advisory board for validation, which will ensure that partner risk management systems are understood.

Summary of responses to issues raised in previous annual reviews (where relevant)

None

Recommendations

- Continue monitoring that partner performance system is used and informs allocations and M&E.
- Ensure that CHF reports to board changes in their analysis on partners’ risk levels, and other relevant points including losses and fraud.

Output Title	Food security - Central African refugees receive basic food assistance in Cameroon.
Output number per LF		5	Output Score	A
Risk:		Major	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Target	Final reach
5.1 Number of people reached through general food distribution (GFD) in Cameroon.	145,567 – December 2015	154,000 – December 2015

Key Points

The WFP programme aimed to deliver urgent food (general food distribution or GFD) and nutrition commodities (blanket and targeted supplementary feeding) to meet the basic food and nutrition needs of CAR refugees in Cameroon. DFID support to WFP ran between July 2014 and December 2015. WFP continue to be funded by DFID under the CHURP business case.

In Cameroon, WFP’s response was implemented in the East, Adamawa and North regions and targeted CAR refugees who arrived in 2014 as well as CAR refugees who arrived and settled prior to the conflict and are still identified as severely food insecure. Vulnerable host populations were also targeted through nutrition programmes. In 2015, WFP provided monthly GFD to refugees in seven established UNHCR refugee sites, border entry points and in local villages, scaling up over time as new refugees arrived. WFP has scaled up its nutrition programme from 8,700 beneficiaries per month in early 2014 to more than 60,000 in 2015.

For the nutrition component, the operation focused on refugee populations located along border regions of CAR (East, Adamawa and North regions) providing general food distribution. Children and pregnant and lactating women amongst refugees and host populations alike received nutrition support aimed at preventing and treating moderate acute malnutrition. Additionally, WFP supported malnourished individuals living with HIV. Around 25,000 malnourished women and children received treatment for moderate acute malnutrition (MAM) in 2015. Among the beneficiaries the global acute malnutrition prevalence decreased from 17% in May 2014 to below 5% in 2015 and less than 1% at the end of 2015 (far below the 15% emergency threshold).

In Cameroon, the PDM carried out in December 2015 indicated improvements in the food security situation of refugees targeted through food assistance. Since April, the proportion of households with poor food consumption has decreased by seven percent. Through nutrition programmes implemented at scale and along other partner activities, WFP managed to reverse an alarming nutrition situation which prevailed at the onset of the crisis. Global Acute Malnutrition (GAM) rates of over 30% registered at the early stage of the crisis dropped to below 5% among beneficiaries receiving assistance. Monthly screening using mid upper arm circumference (MUAC) indicated less than 1% GAM in several sites in December 2015. Furthermore, a steady decline in the number of newly admitted moderately malnourished and severely malnourished children was registered in health centres, from over 200 registered per month in January to below 100 in December. The cure rates for women and children in target supplementary feeding programme (TSFP) were 71.2% which is slightly lower than Sphere minimum standards (>75%) but still an improvement from last year. Defaulter rates (patients leaving the programme before being cured) were high at 26% (Sphere standard <15%). Mortality rates were well below sphere standard at 0.2% however due to high defaulter rates this figure may not be reliable. Non-response rate was at acceptable levels well below target 2.5%.

Supply chain challenges constituted a major hindrance for WFP's operations during the first half of the year, resulting in pipeline breaks from March to May. A complete break in May delayed WFP from performing food distributions during the month. Refugees’ difficult living conditions combined with breaks in assistance coincided with anecdotal evidence of a rise in negative coping mechanisms. However, WFP ensured GFD support through the remaining 11 months of the year and augmented nutritious rations to compensate for the reduced food support. Nutrition activities in east Cameroon continued without interruptions through the year. Monitoring evidence also suggested this positively impacted refugees’ ability to avoid negative coping mechanisms. While treatment programmes were prioritised over prevention, major efforts were made to scale up blanket supplementary feeding from initially 25 sites to 60 sites in the East, Adamawa and North regions. Under TSFP, 35 outreach sites were created to adequately provide MAM treatment packages to beneficiaries located in remote villages.

WFP’s operations face regular challenges due to chronic underfunding, which will continue to require regular monitoring and where possible adequate DFID response.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID to prioritise engagement in country with WFP on overall pipeline management and opportunities for local procurement and cash assistance. DFID to monitor challenges for delivery likely to result in ration reductions and pipeline breaks and opportunities to help address these challenges.
According to WFP reports, a series of initiatives put in place by WFP and partners succeeded in improving the situation and supply chain procedures went smoothly through the second half of the year during which no breaks in the pipeline were registered. The challenges encountered in 2015 led WFP to reflect on the importance of combining food assistance projects with cash and voucher modalities for a more efficient response. Consequently, in 2016, WFP will introduce cash-based programmes for the first time in Cameroon. According to WFP reports, augmented nutritious rations were given to compensate for the reduced food support.

Recommendations

- DFID to work with WFP to look at strategies for decreasing defaulter rates in the nutrition programme.
- DFID to continue monitoring WFP pipeline management to ensure there are no ruptures in supplies.
- DFID to work with WFP to ensure M&E adequately tracks increases in negative coping mechanisms.

Output Title	Health and nutrition - Central African children in Cameroon receive treatment for acute under-nutrition.
Output number per LF		6	Output Score	A+
Risk:		Moderate	Impact weighting (%):	5%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target	Final reach
6.1. Rehabilitation recovery rate (%) for children suffering SAM who have received MSF Community Based Management of Acute Malnutrition.	September 2014: 65%. / October 2014: 75%.	September 2014: Garoua Boulai 97% and Batouri 80% (MSF areas of intervention). / October 2014: Garoua Boulai 97% and Batouri 93%.
6.2. Number of people reached with MSF health interventions.	30,000.	30,000.

Key Points

The MSF programme aimed to deliver emergency healthcare and therapeutic treatment for severe acute malnutrition. MSF was the first INGO to respond to the crisis in 2014 by setting up mobile clinics and providing medical care on refugee sites complemented by water and sanitation activities to address the crisis.

MSF has met and exceeded agreed targets by reaching 30,000 people with urgent health interventions[2] and exceeding the final 75% recovery rate for children with SAM.
[2] The overall beneficiaries for MSF programme for Central Africans in Cameroon is 50,000 (30,000 people reached with UK funding).

Central Africans generally arrived in Cameroon in an extremely poor condition with very high rates of malnutrition: GAM reached up to 25-30% and SAM rates 10% in June 2014. The baseline recovery rate for children suffering SAM was 59% in Garoua Boulai and 61% in Batouri at July 2014. By September MSF had exceeded their 65% recovery rate for children suffering SAM. MSF’s overall programme objective was to stabilise and reduce mortality and morbidity rates amongst Central Africans. Mortality rates were reduced to acceptable levels across the MSF area of intervention to 0.1 - 0.3 by October (against a target of under 5 mortality rate <1). A small cholera outbreak occurred in November 2014. However a multi-partner response plan was immediately implemented with MSF leading on health and the outbreak was successfully contained.[3]
[3] MSF reporting to DFID.
While the immediate emergency phase has passed, MSF has noted that attention is still needed to ensure the stability and quality of healthcare. At the end of the DFID funded MSF programme the number of patients in the intensive therapeutic feeding centres remained high and with a still unstable situation in Central African Republic, MSF has extended its operations in Cameroon to at least the end of 2015, but these aspects of the programme are not funded by DFID.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID to monitor MSF handover to more development orientated partners over 2015.
DFID has monitored the handover the UNHCR partners and after some adjustments, UNHCR has made ACF the lead to maintain quality of care.

Recommendations
None.
Output Title	Multi-sectorial (UNHCR) - Central Africans arriving in Cameroon and Chad as refugees have their most basic needs met, including shelter and water and sanitation.
Output number per LF		7	Output Score	A++
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Target	Final reach
3.1. Average supply of water per person per day in the 7 refugee sites reaches a minimum of 15 litres per day in Cameroon (WASH).	>15 – March 2016	18 litres per person per day
3.2. Number of emergency shelters provided in Chad (Shelter).	636 – March 2015	3,386
3.3. Number of people reached with UNHCR multi-sector assistance in Chad.	56,000 – March 2015	72,068
3.4. Number of people reached with UNHCR multi-sector assistance in Cameroon.	68,704 – March 2016	107,760

Key Points

UNHCR and its partners have been implementing a multi-sectorial response on and off sites for CAR refugees and host communities and for returnees in Cameroon and Chad in 2014/15. The UNHCR programme in Cameroon aimed to ensure the protection of refugees, including through registration, the provision of shelter and non-food items, access to water, sanitation and hygiene as well as healthcare. UNHCR also supported access to education through the rehabilitation and construction of school buildings. UNHCR in Cameroon continues to be funded by DFID under the CHURP business case. In Chad, the programme supported the needs of refugees and ‘returnees’[4] across sectors, including shelter and infrastructure, water and sanitation and protection.
[4] Returnees are people of Chadian nationality who have had to flee CAR during spikes of sectarian violence in 2013-14. Many are second or third generation migrants and no longer have family or social ties in Chad.

In 2015/16, UNHCR received DFID support to continue its multi-sectorial response. UNHCR are implementing multi-sectorial activities in East, Adamaoua and North mainly in biometric registration, self-reliance and livelihood activities, and support to local authorities through capacity building, in order to respond to the identified needs linked to the protracted displacement of CAR refugees.

In terms of WASH in refugee sites, 115 boreholes and 3,450 latrines have been built resulting in provision of water at 19l/p/d and an average of 20prs/Latrine, only 66 boreholes have been built in refugee-hosting villages.

With the aim of improving services to beneficiaries UNHCR in Cameroon introduced a biometric registration system in late 2015 with financial support from DFID to cover the first phase of the exercise. It consisted of the setting up of the main registration centres, the purchase of main biometric registration equipment, and trainings and workshops of the staff on the methodology/features of biometric registration. The switch to biometric registration has so far given a much more accurate picture of the number of refugees and is expected to have a wide range of key protection impacts, including continuous access to asylum.

UNHCR Cameroon has prioritised self-reliance and livelihoods as one of the main pillars of intervention in the assistance to CAR refugees in the East, Adamaoua and North regions. In 2015 the intervention targeted various groups of refugees supporting livelihood activities such as: (a) agricultural extension and distribution of agricultural tools-kit and food seeds, seed-kit market gardening; (b) Income-Generating Activities; (c) capacity building for IGA groups and organisations; (d) training in profitable trades and first starter kits to the training participants.

DFID funds also provided vehicle and assets to Cameroonian authorities to improve their capacity to respond and facilitate the operation assistance in the East, Adamaoua and North.

There have been improvements in coordination but these improvements only apply to the livelihoods sector while all other sectors leave much to be desired. Additionally the partnership situation appears to be deteriorating as UNHCR partnership management has proved insufficiently cooperative, poorly communicated and some NGOs have raised concerns about the length of the contracting process. These concerns were already identified in 2014 and call for drastic improvements in partnership management.

Despite exceeding logframe targets UNHCR has been administratively weak. Their specific final project report was due on 30 June 2016 however was significantly delayed and not received until November (more than six months after the completion of the project).

Summary of responses to issues raised in previous annual reviews (where relevant)

Continue to monitor UNHCR delivery in Chad and in Cameroon including funding pipelines and UNHCR’s ability to achieve coverage of assistance across operations and sectors.
Underfunding continues to be an issue. There remains a very strong need for DFID to continue monitoring the situation and supporting the response.

Continue to monitor the situation of refugees both inside and outside of the camps in Cameroon including any arising assessments on nutrition and specifically the potential causes of under-nutrition, e.g. limited water and sanitation.
This remains part of ongoing monitoring using nutrition surveys.

Recommendations

- DFID to follow up with UNHCR both at country level and at HQ level to ensure that they step up in terms of improved coordination and partnerships.
- Continue to monitor UNHCR delivery in Chad and in Cameroon including funding pipelines and UNHCR’s ability to achieve coverage of assistance across operations and sectors.
- DFID to discuss UNHCR’s reporting delays with CHASE and UNHCR HQ.

Output Title	Multi-sectorial (START) - Central Africans receive multi-sector assistance both in refugee camps and outside of camps in communities in Cameroon
Output number per LF		8	Output Score	A+
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (March 2016)	Progress
4.1. Number of people reached with multi-sector humanitarian assistance with START network activities.	179,526 people (91,196 female, 88,330 male)	455,515 (249,842 Female, 202,137 Male) No double counting
4.2. / Network mechanisms deliver rigorous decision-making for selecting projects and learning.	June 2015. Decisions made by the Project Selection Committee are well-documented in meeting minutes and transparent selection criteria are used. Decisions are based on needs analyses, evidence of the project’s engagement with affected people and the technical strength of proposals. / March 2016. Lessons learned have been documented with evidence of adjusting programmes in response to emerging needs analyses, engagement with affected people and the findings of their technical teams. Programmes are course-corrected if needed.	Project selection was clear and documented but technical criteria for project selection not always clear and decisions only moderately based on evidence. Learning Workshop took place in August 2015 to reflect on inception period and strengthen collaboration between stakeholders. / Problems were documented and there is some evidence that adjustments were made where needed.
4.3. Proportion of beneficiaries (5481) who report an increase in vegetable production and acceptable food consumption score at the end of the project.	At least 80% beneficiaries report increased vegetable production and have an acceptable Food Consumption Score at the end of the program. – March 2016	80.6% report an increase in vegetable production / 91% have an acceptable FCS by end of the programme.

Key Points

A Memorandum of Understanding (MOU) was signed with the START network in April 2015 to conduct activities for the CAR refugee crisis in the East and Adamawa states of Cameroon covering a period between 01 April 2015 and 31 March 2016. DFID did not disburse the funds to START until late May. Following this there was a delay of more than two months until full implementation was initiated in August which can not entirely be explained by late transfer of funds from DFID. This led to several of the partners suffering severe delays in their project implementation. Most of these delays were overcome by the beginning of 2016 but they may still have impacted the sustainability of some activities.

Additionally there were serious concerns raised on the issue of the monitoring, evaluation and learning component within START as it was more focused on processes rather than proper implementation and did not substantially contribute to improved overall management. A lesson learning workshop was organised by DFID and START to take stock of areas requiring improvements for future collaboration, including in contracting, project selection process, M&E, staffing and in deciding the localisation of START staff.

The lessons learned exercise gave some clear recommendations for both the START network and DFID. START was making changes to their Standard Operating Procedures to formalise exit strategies, payment plans, capability assessments of partners and review of projects. DFID and START both committed to agree a more formal model of partnership in any future collaboration, including regular calls and communications. The full lesson learning document is saved on QUEST 5534027.

In terms of project implementation, most outputs were met, and some exceeded, indicating an overall positive performance of the programme. START were particularly successful in significantly exceeding targets for sessions on WASH, nutrition, education and protection. START only met 53% of their target to deliver primary health care consultations through IMC due to delays related to security concerns and poor road conditions during the rainy season (July 2015 - November 2015). START also acknowledged the slow launch of health services was due to delays in signing the agreement between IMC/PLAN and the START network; this also led to delays in developing an agreement with the local Ministry of Health representatives to facilitate the provision of health services to refugees.

Key successes reported by Start Network implementing partners centred on advocacy work with community leaders, local authorities, government bodies and UN agencies, which fostered their cooperation, notably on protection and gender-based violence issues. Support from community leaders was particularly beneficial for smooth programme implementation. There were several programmatic adjustments such as developing an integrated approach for WASH and nutrition activities that demonstrate the programme’s successful adaptation to the needs of the targeted populations and the programme context.

Some of the specific key successes included:

- Changes in hygiene practices with the implementation of community-led total sanitation activities.
- Securing access to health by providing services for the most vulnerable communities (refugees and host communities).
- Mitigation strategies to compensate for shortages of therapeutic food by focusing on preventative measures and orientated programming on Infant and Youth Child Feeding (IYCF).
- Collaborative farming projects where 10 to 15 farmers would farm on one piece of land with members learning and coaching their peers.
- Focussing on income generating activities where household groups could gain income from farming and business activities.
- Successful advocacy campaigns to draw attention of UNHCR and government representatives on the importance of integrating child protection.
- Increasing awareness and access to GBV prevention and response services.
- Advocacy against discrimination towards girls and women through the promotion of girls’ access to schools.
- Positive coping mechanism among children through Child Protection Officers.
- Integrating parenting education as part of the education curriculum in Cameroon, with endorsement of the Ministry of Education.

Some of the key challenges included limited access to target communities, especially in the north due to security. Access was also a challenge to populations in constant displacement outside the refugee camps; impeding targeting and meaningful community involvement in specific activities. It was reported that the status of affected people and their living conditions (weather, insecurity and constant displacement across hard-to-reach areas) was a recurrent challenge during implementation. The increasing size of the displaced population also impacted on project delivery. Finally, ensuring the sustainability of specific activities was challenging due to the short programme timeframe.

Summary of responses to issues raised in previous annual reviews (where relevant)

Monitor impact of delays at DFID, START and partner level on operations and review process of integration of lessons learned into the START network’s processes.
START lesson learning workshop was carried out in August 2015 and a wider lesson learning event was carried out in June 2016.

Recommendations
It is the recommendation based on this review that future DFID funding on longer-term response should be conditioned by the implementation of lessons learnt agreed at the June 2016 workshop.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The primary cost drivers in CAR are poor capacity, insecurity and location. As the Business Case indicated, the location of CAR alone makes it an expensive place to operate as a landlocked country bordered by a number insecure countries. The ongoing security situation, the associated high risk of fraud and loss, and the remoteness of much of the displaced and conflict-affected populations also significantly increases costs. In addition, transportation costs are very high due to poor infrastructure, insecurity, and the quasi collapse of the private and transportation sectors. High operational costs are less prevalent in Cameroon.

Since the last Annual Review in July 2016, CAR experienced an upsurge of violence in the last four months of the year including several robberies and lootings of humanitarian partners’ offices and warehouses. Over 53,000 people were displaced and 171 civilians died (OCHA, December 2016). Despite this further insecurity and a few incidences of fraud and loss, the remaining activities of this project – under the Solidarités Consortium, IMC-led Consortium and FAO – were able to conclude with just one no-cost extension of one month for IMC.

VfM performance compared to the original VfM proposition in the business case

The Business Case followed DFID’s approach to VfM, ‘the 3Es model’ of economy, efficiency and effectiveness. It also addressed equity and the metrics of speed/timeliness, quality/appropriateness and cost in accordance with humanitarian planning in rapid responses.

Economy (spend less)

The Business Case stressed the high operational costs in CAR, which are less prevalent in Cameroon. The operational cost of scale-up in particular is very high given the challenges of the context.

An important balance to strike was the speed of the response to high levels of need while also sustaining operations with predictable procurement. FAO beneficiaries noted an improvement in the pace of delivery in 2016 although there was room for improvement which could be achieved by DFID and FAO signing a partner agreement earlier. DFID and FAO signed the partner agreement for 2016-19 on 1 December 2016, one day after the end of the FAO 2016 agreement. Partners also endeavored to do more local procurement where possible, for example in livelihoods, although this led to some complaints about deliveries in 2015. FAO strengthened its quality check systems in early 2016 to address this. Beneficiary feedback on the distribution process at the end of 2016 showed that 55% of farmers said that while they received their seeds too late for the March to July crop cycle, they did receive them in time for the August to November crop cycle.

In terms of human resourcing, partners knew that inadequate experience and poor support would lead to poor quality implementation and increase fraud risks of their operations. They therefore worked to avoid staffing gaps, to recruit staff of adequate seniority and establish solid systems to ensure continuity of operations and allow for appropriate economic decisions. The CHF in particular strived to strengthen its systems and staffing and FAO set up an M&E team to consolidate their monitoring and evaluation processes.

The location of most projects constrained the possibility of providing cash and voucher assistance in due to poor market absorption capability. ICRC and the Solidarités-led Consortium endeavored to channel aid (food support and income-generating activities) through cash and/or vouchers where possible, which was particularly beneficial to the resumption of trade. In 2016, FAO also piloted a seed fair with positive initial results, which DFID and FAO have agreed to scale up in the 2016-19 project to increase beneficiaries’ choice.

Efficiency (spend well)

According to the beneficiary reach, most partners either met or exceeded their targets with the exception of the Solidartés-led Consortium on protection, FAO on negative coping mechanisms, and ICRC on health and food assistance.

The START Network substantially exceeded their targets. While savings did enable an expansion of activities the main reason for the significant project reach appears to be due to the very large number of water points disinfected (an activity implemented at a very low cost) rather than more efficient delivery.

The IMC-led Consortium was slightly below its target. Achieving the target of one consultation per person per year was a challenge. Although the health services were operational, the findings were that the population was not using them to the extent that would be expected. The underlying reasons are not clear but likely the cost-recovery strategy imposed by some of the health facilities is creating a barrier of access for some in the target population. Partners used M&E and accountability tools to monitor these trends, which were also monitored by DFID.

DFID’s value for money guidelines consider the average output cost and fluctuations to be good reflection of efficiency. The cost per beneficiaries[5] were approximately: £22.33 for MSF, £25 for the Solidarités-led Consortium, £5.50 for the IMC-led Consortium, and £2.19 for the START Network. The average cost per beneficiary was approximately £12.76. The cost per beneficiary was much higher for MSF and the Solidarités-led Consortium. While MSF met their beneficiary number target, the cost per beneficiary was high for the £1m funding it received which was the smallest allocation under this programme. The relatively high cost per beneficiary is mainly attributable to the very high quality of care that is provided by MSF. For the Solidarités-led Consortium, the Kabo to Kaga-Bandoro transport axis was one of the most insecure areas for operation for our parTners. They experienced not only conflict from armed groups but were also in the path of the transhumance which was increasingly an additional source of conflict. This deterioration in security and access, together with the implementation challenges faced by the consortium contribuTed to the increased the final cost per beneficiary.
[5] See partners’ final reports

Speed and equity of distribution is also important in order to assess whether aid is reaching the right beneficiaries in time and leaving no one behind. Some partners, notably ICRC, MSF and the IMC consortium, repeatedly adapted their response to address surges in needs, with dramatic lifesaving results in the case of MSF. In Cameroon, the pace UNHCR and WFP interventions was also crucial in saving lives in 2014.

Effectiveness (spend wisely)

The evidence collected from DFID partners during field visits in 2015-16 found that the assistance provided through the Solidarités Consortium was considered to be very relevant by beneficiaries in terms of targeting and type. Anecdotally, DFID could see that the combined impact of activities was leading to a revival of trade in some areas covered. FAO’s assistance was also greeted as more timely and of better quality in 2016 as a result of earlier contracting and improved quality control processes. When speaking to beneficiaries of the home gardening activities these were praised as very effective at providing both a source of income as well as nourishment for the beneficiaries. Assistance provided by the IMC-led Consortium was also met positively, with MENTOR Initiative’s beneficiaries in particular hailing the programme as life-saving in their region which had been entirely deprived of healthcare access.

Close collaboration between IMC-led Consortium partners and other humanitarian stakeholders enhanced the effectiveness of the projects’ activities by increasing complementarity and information sharing on referrals and security matters.

The ‘do no harm’ principle of effectiveness proved less than straightforward in such an insecure environment with deep social divisions and upsurges in violence. Having said that, UNHCR and WFP gave much attention to this, in particular towards negative coping mechanisms among beneficiaries. ICRC’s practice is designed so that protection and assistance actions are complementary and their launch of community-based protection in 2016 further contributes to helping to foster positive coping mechanisms. CHF’s efforts to start strengthening protection mainstreaming in 2016 also helped to ensure its partners do no harm.

The Solidarités-led consortium implemented do-no-harm studies for some of their activities with great diligence. The Danish Refugee Council (DRC) in this consortium also tried to tailor their protection and assistance activities to reinforce each other but the Annual Review in 2016 assessed that they may have been too quick in pushing for concrete outputs under their social cohesion project before having a complete grasp of the situation. DRC operates in a very difficult area of agro-pastoral disputes and it was noted that their social cohesion work would still need reinforcing in the long term to try to address underlying factors.

Gender and equity

There was a significant variation in how gender was considered between partners. This will require greater attention in future programming for example tracking and reporting of gender-disaggregated data by partners wherever possible.

Partners’ teams are gender imbalanced in part due to poor overall capacity in country combined with uneven access to education for women. In terms of beneficiary targeting, most partners had fairly gender-sensitive policies with some livelihoods activities (income-generating activities, resilience) targeting women. However, future livelihoods activities specifically targeting women should also take greater care to ensure no unintended negative consequences, for example on child feeding, are incurred. In particular, although local committees usually include female representation (in addition to youth, religious leadership, local authorities, economic stakeholders etc.); in practice females are frequently under-represented due to the lack female local leaders. Partners could have imposed targets to try to address this but this sort of social bias is difficult to correct through programmes. To ensure that isolated women, the elderly, handicapped people and so on benefit, it is important to sustain conversations on tools and mechanisms to ensure no one is left behind.

Another challenge of equity is ensuring that sedentary and pastoralist populations in need are all catered for. Within CAR this is made very difficult by poor access with pastoralist populations for example choosing to remain in forest areas for their protection. Some partners endeavored to monitor this. For instance, in Basse-Kotto, the IMC-led Consortium worked with the religious platform to analyse obstacles to access to care for Peuhl populations. The ICRC, FAO and the Solidarités-led Consortium all undertook cattle vaccination campaigns that provide entry points to assess the needs of pastoralist populations, whilst responding to a priority need identified by them.

The Solidarités-led Consortium also funded a useful assessment in June/July 2016 to better understand the needs and challenges of pastoralist populations, which was shared through the Food Security Cluster and is now online. The results of the assessment were used as a source of information to actualise the Integrated Food Security Phase Classification (IPC) for 2017.

Assessment of whether the programme represented value for money

In the circumstances, it is remarkable that the programme met all but one of the output targets and exceeded many. The programme represented good value for money overall considering the challenges to the economy, efficiency and effectiveness of activities that were presented during implementation. Partners operated in an outstandingly difficult context to deliver DFID assistance and were frequently forced to adapt their approach to respond to insecurity and had three contingency plans for their procurement. The fact that the programme did not see big staffing gaps is a reflection of the professionalism of our partners, given the incredible difficulty in recruiting staff to work in CAR.

Quality of financial management during programme

Funding was provided through memoranda of understanding and accountable grants. Payments to ICRC, UNHCR and the CHF were made to appeals, and therefore (as is standard) DFID did not receive individualised finance reporting. NGO partners – MSF, the START Network, IMC-led Consortium and Solidarités-led Consortium - were required to show expenditure and forecast of the tranche to be made. Financial statements were received and reviewed along with progress reports before payments were made according to the agreed schedules. The Start Network underspend of £1,096 which was shown in final report and referenced in the 2016 Annual Review was returned to DFID. IMC returned unspent funds of £105,761 to DFID in March 2017.

In general, partners provided financial reporting on time, with accurate forecasts and explanations where reallocations were required. This allowed DFID to make timely disbursements. However, DFID was required to follow up with some partners on late reporting during the course	of the programme and following its completion. Agencies provided DFID-attributable results but this was challenging in practice for some UN partners as their internal procedures do not demarcate DFID from other donor funding against specific projects in their operations.

The projects with FAO, the Solidarités-led livelihoods consortium and the IMC-led health consortium each finished after the date of the last Annual Review in July 2016. Final narrative and final narrative reports have been received for all partners except FAO. DFID is pursuing receipt of these reports as a matter of urgency.

Date of last narrative financial report
WFP	6 April 2016
UNHCR	14 August 2016
MSF	05 February 2015
START Network	20 July 2016
Solidarités-led Consortium	14 February 2017
CHF	31 May 2016
FAO 2015	23 November 2016 (narrative). Awaiting financial report
FAO 2016	27 March 2017 (narrative). Awaiting final financial report
ICRC	12 May 2016
IMC-led Consortium	31 December 2016
Date of last audited annual statement
WFP	7 March 2016
UNHCR	25 July 2016
MSF	2015
Solidarités International	2015
CHF	31 July 2016
FAO	16-20 May 2016
ICRC	30 June 2016
IMC	30 June 2016

E: RISK (½ page)

Quality of risk management over the life of the programme

A comprehensive risk register was developed as part of business case process which was approved in 2014 and updated in 2015. DFID amended its Risk Management Framework in 2016 from low, medium and high ratings to minor, moderate, major and severe. This project was rated “high” risk and is now rated severe overall due to the components of the programme operating inside CAR. For the components supporting refugees in Cameroon and Chad, where the operating environment is much less insecure, the risk rating is better described as major/moderate.

Implementation risks proved the greater problem including insecurity in all its forms, hindering access, operations, M&E, delivery, recruitment of staff willing to be deployed to remote areas. Mitigating measures were in place to reduce risk and DFID quarterly monitoring visits and a greater focus on due diligence and UK engagement in CAR and the region also contributed. However, partners were only able to implement activities because they accepted a very substantial residual security risk. Partners also endeavoured to address associated stress (regular leave, debriefings), take measures when staff are subjected to incidents (psychological support etc) and foster a supportive atmosphere amongst staff.

Strategic risks and in particular underfunding remain a key concern., DFID regularly engaged across the donor spectrum in Cameroon and CAR to try and see this addressed and attended the Brussels Donor Conference on CAR in November 2016. In light of the protracted nature of the crisis, DFID has begun a three-year programme (CAR Humanitarian and Recovery Programme or ‘CHURP’) to help sustain the humanitarian response from 2016 to 2019.

Fraud risks affecting financial and operational losses have also been a concern. DFID allocated substantial capacity to note and review partners’ due diligence processes and compliance mechanisms with DFID’s counter-fraud unit. After a push from DFID, partners reported more cases of suspected fraud and did so in a timelier manner. This indicated a better understanding of DFID’s definitions, systems and procedures around reporting and management of suspected cases and that partners were dealing with suspected fraud transparently and appropriately. Additionally, partners have proven they have strong systems in place to prevent and mitigate the impact of fraud and loss due to for example robberies and looting.

Where challenges arose, a professional plan was devised and fully implemented. For example, the IMC consortium conducted compliance checks among its partners, the CHF rolled out of a full risk management framework, and the FAO started developing a similar tool in 2016. NGO partners in CAR also worked together to discuss and try to address the risks arising from difficulties with MINUSCA. Partners also systematically rolled out sensitisation sessions on fraud where cases were detected creating a better space to talk about these problems. The ICRC noted for instance that repeated sessions led to improved HR dialogue over any kind of problem. Where FAO’s operations are concerned, they did not hesitate to share concerns at the cluster level and across their bases, to ensure all were sensitised where risks were identified.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The overall programme was delivered against the planned timeframe, including the cost extensions to the CHF, IMC-led Consortium and FAO. During the programme, five no-cost extensions were granted to WFP (1), UNHCR (1), Solidarités-led Consortium (2) and IMC-led Consortium (1) respectively.

Performance of partnership (s)

A lesson from this programme is the importance of flexibility in DFID’s programme management and strong relationships with the partners to manage and adapt to the challenges they face in carrying out their activities in such a fragile context. Partners need to provide realistic workplans at the outset of a project taking into account constraints and update them regularly over the duration of the project. DFID should take care to maintain good relationships with partners and ensure robust but flexible management for future programmes like this.

The performance of the NGO Consortiums are also heavily dependent on the strength of understanding and collaboration between consortium partners, and the strength of the consortium lead to manage and monitor its partners. DFID will work closely with the health consortium as it transfers leadership from IMC to MENTOR Initiatives in the next phase of the programme.

As the security situation is deteriorating in some of the areas in the country, loss of assets due to theft and robbery is likely to continue to be an issue for many of our partners. In order to continue to be effective at reaching the most vulnerable with life-saving interventions in these areas, our partners may need to consider taking greater risks with some commodities in order to prevent stock-outs and improve the quality of the services. As such, any future DFID funded programme will also need to consider accepting this increased risk of loss as an acceptable cost of being able to provide life-saving assistance in this very complex and challenging setting.

Asset disposal and value obtained by DFID

All assets will be dealt with as per DFID’s asset disposal guidance in the Smart Rules during the closure of the project. DFID’s procedure for dealing with assets after a programme ends is for our partners to send a request if they wish to retain the assets purchased with a list of the items, mainly if they have a useful life of more than one year and the cost of the assets is in excess of £1,000 or equivalent in local currency. DFID requires assurance from the organisation that they will be put to good humanitarian use and used for the purposes under the terms of the transfer.

DFID received a request from Solidarités for authorisation to continue using the assets on a food security programme which continues with the activities implemented under this DFID-funded project. A request was also received from Cordaid, under the IMC-led Consortium, to transfer ownership of assets such as an ambulance and generator purchased under this DFID-funded project to the District Hospital of Alindao. These requests will be considered by the Senior Responsible Officer for the programme, in accordance with DFID’s Smart Rules guidance.

G: CONDITIONALITY (½ page)

Partnership principles assessment

Not applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Partners have shared with DFID good evidence informing their programmes. Such evidence includes robust monitoring and evaluation frameworks, post-distribution monitoring reports, post-harvest monitoring reports and evaluation reports. Partners have provided evidence that they have disaggregated data by sex and where most relevant, by age. There is evidence that other needs have been considered, for example by UNHCR in supporting people with specific needs – an activity expanded from the target of those with physical disabilities to older people, children at risk of school dropout and patients with medical specific needs. The programmes have also responded to changes in the caseload and needs of people affected by the crisis in Central African Republic. Overall this programme has provided useful insights and evidence on implementing effective programming in an extremely complex and insecure setting where access remains challenging.

The theory of change remained relevant to the project design and did not require review. The project design did not require any major modifications during the course of the programme. No external evaluation of the programme was planned or conducted. However, DFID received project evaluations from the START Network, CHF and IMC with their final reports.

In summary:

START Network evaluation
- Overall the programme was relevant and effective; meeting unmet needs of both refugees and host communities with good performance against targets.
- Collaboration between agencies significantly influenced its performance.
- Activities in areas with mixed interventions were considered to be of great added value
- Beneficiaries praised the complementarity of activities but this could have been more systematic
- Sustainability successes can be attributed to the direct involvement of beneficiaries and local authorities at every stage

CHF evaluation
- The CHF proved its added value by blending emergency and resilience to fill gaps
- Allocated funds contributed meaningfully to the collective humanitarian efforts in CAR
- Funds were provided flexibly as the situation changed
- Funds were used for life-saving interventions and for priority humanitarian actions that were not otherwise funded
- Gender markers played an important role in project assessment but needed to influence implementation and impact more
- Added value is the quality of prioritisation and allocation processes but could further improve speed of disbursement for interventions

IMC evaluation
- The programme was very relevant and allowed access to basic health care for the most vulnerable
- All expected results were achieved as planned
- The action was efficient considering the enormous challenges of the operating context.
- Recommend improving improve coordination, harmonisation and standardisation between consortium partners in next programme.

Monitoring progress throughout the programme

DFID does not have a country office in CAR, Cameroon or Chad. DFID engaged a humanitarian adviser based in Yaoundé in 2015 to provide oversight of programmes in the region. Between 2014 and 2016, UK based staff completed quarterly visits to programmes in CAR and Cameroon to check project progress. Visits to CAR and Cameroon included meetings with beneficiaries and other stakeholders, national government officials, DFID partners and other humanitarian agencies. DFID also held calls with partners on a regular basis and when field visits were not possible.

Direct beneficiary feedback has been an important element of the programme, including with women, with men, and young people. For example, the Solidarités Consortium was found by a DFID monitoring visit to be considered very relevant by beneficiaries in terms of targeting and type, the timeliness and quality of FAO’s assistance was improved following beneficiary feedback surveys, and MENTOR Initiative’s beneficiaries within the IMC-led Consortium hailed the programme as life-saving in their region which had been entirely deprived of healthcare access.

Partner performance was monitored, reviewed and captured in Intervention Review Sheets for due diligence compliance before financial allocations were made. Both Annual Reviews were conducted thoroughly and on time, rating the programme at an A in 2015 and an A+ in 2016.

ANNEX – List of abbreviations
ACF	Action Contre le Faim
AFEB	Association des Femmes Évangeliques de Bossangoa
CAR	Central African Republic
CBP	Community-Based Protection
CHF	Common Humanitarian Fund
CHURP	Central African Republic Humanitarian and Recovery Programme 2016-2019
DFID	Department for International Development
DRC	Danish Refugee Council
ECHO	EU Civil Protection and Humanitarian Aid Operations
FAO	Food and Agriculture Organisation
FGM	Female Genital Mutilation
GAM	Global Acute Malnutrition
GBV	Gender-based violence
GFD	General Food Distribution
HQ	Head Quarter
IDA	International Dispensary Association
DIP	Internally Displaced Person
ICE	Integrated Community Case Management
ICRC	International Committee of the Red-Cross
IDs	Internally Displaced Persons
IGA	Income-generating activities
IHL	International Humanitarian Law
IMC	International Medical Corps
INGO	International non-governmental organisation
IYCF	Infant and Youth Child Feeding
M&E	Monitoring and Evaluation
MAM	Moderate Acute Malnutrition
MH GAP	Mental Health Gap Action Programme (MH GAP)
MINUSCA	United Nations Multidimensional Integrated Stabilisation Mission in the Central African Republic
MUM	Mobile Medical Unit
Mohr	Ministry of Health
MOU	Memorandum of Understanding
MUAR	Mid-Upper Arm Circumference
NFI	Non-food items
NGO	Non-governmental organisation
OCHA	Office for the Coordination of Humanitarian Activities
PCR	Programme Completion Review
PD.M.	Post-Distribution Monitoring
PH.C.	Public health care
PH.M.	Post-Harvest Monitoring
SAM	Severe Acute Malnutrition
SIB	Sexual and Gender-Based Violence
SI	Solidarities International
SC	Save the Children
SIB	Sexual and Gender-Based Violence
SI	Solidarités International
TSP	Targeted Supplementary Feeding Programme
UNHCR	United Nations High Commissioner for Refugees
VFM	Value For Money
WASH	Water, Sanitation and Hygiene

Annual Review 2015 Summary Sheet

Review Date:	July 2015

Title: Central African Republic (CAR) Humanitarian Funding to Central Africans, IDPs and Refugees 2014-2016
Programme Code: 204852	Start Date: 17 July 2014	End Date: 31 December 2016
Programme Value: £35 million (including £7m contingency activated on Ministerial approval)

Summary of Programme Performance

Year	2014/15
Programme Score	A
Risk Rating	High

Summary of progress and lessons learnt

The 2015/16 £35 million Business Case for responding to the Central African Republic (CAR)[6] Humanitarian Crisis was approved in 2014 and included two outcomes focusing on refugee populations in Cameroon and Chad and on affected populations inside CAR. Outcome 2 (refugee programmes of £10 million in 2014 and £4.5 million in 2015) were the first to be implemented from July 2014 to July 2015 and form the major focus of this Annual Review. Programmes under outcome 1 for populations inside CAR began later (start up in April 2015) as funding was until that point provided through a previous Business Case (DevTracker 4408472). A brief assessment is made in this Annual Review of their progress in starting up.
[6] This and all further abbreviations are referenced in the annex.

Overall the programme has made good progress and achieved its stated outcome of significantly reducing suffering and saving lives among CAR refugees.

The cumulative number of people reached under the programme is 250,068 vs. a target of 352,100. The original target was not achieved as it was based on a UNHCR planning figure for the number of refugees expected to arrive in Cameroon in 2014 (higher than the final number of people who arrived) and following changes in the beneficiary counting methodology. UK funding has helped agencies provide a successful response to emerging needs and bring assistance up to minimum standards. Significant mortality drivers such as malnutrition have been brought under control thanks to DFID and other contributions. On that basis we assess the programme is achieving its outcome.

By the end of 2014 with the support of DFID and other donors, assistance in refugee sites in Cameroon started to reach minimum emergency response standards in water, food and emergency shelter.[7] Among people reached with food and nutrition assistance, Global Acute Malnutrition prevalence dropped to below emergency thresholds. The recovery rate for children suffering acute malnutrition was brought up to higher than target levels. Of particular concern were food and nutrition pipeline breaks in Cameroon in 2015. While the situation in camps has improved, there are still significant gaps due to serious under-funding. These included limited sanitation (latrines), durable shelter and livelihoods opportunities. In Chad the total Central African refugee population has been profiled but there have been gaps in assistance coverage.
[7] Programme information from WFP project report for EMOP 1200689, MSF and UNHCR project reporting to DFID.

Recommendations:
- DFID to follow up with partners on the use of cash and local procurement to deliver food in Cameroon and to closely monitor the food and nutrition pipeline.
- DFID to continue to coordinate closely with other donors on programme funding and prioritisation and continue to undertake quarterly field visits.

Annual Review 2016 Summary Sheet

Review Date:	July 2016

Title: Central African Republic (CAR) Humanitarian Funding to Central Africans, IDPs and Refugees 2014-2016
Programme Code: 204852	Start Date: 17 July 2014	End Date: 31 December 2016
Programme Value: £40 million

Summary of Programme Performance

Year	2014/15	2015/16
Programme Score	A	A+
Risk Rating	High	Severe

Summary of progress and lessons learnt since last review

Overall the programme has made good progress and achieved its stated outcome of significantly reducing suffering and saving lives among the population in CAR as well as refugees in Cameroon. The cumulative number of people reached to date under the programme is 1,422,854 vs the target of 1,460,735 indicating that already 6 months prior to the conclusion of this program the target number of beneficiaries have already almost been reached. UK funding has helped agencies provide a successful response to emerging needs and bring assistance up to minimum standards. Based on this we assess the programme is well on its way to achieving its outcomes.

In terms of progress made within the reporting year, clear achievements have been made in terms of strengthening of monitoring and evaluation as well as procurement systems. Though further push is needed in terms of pipeline management as well as gaining a better understanding of the barriers to access to healthcare, we believe that the current partners will be able to successfully deliver the desired program outcomes and we will continue to ensure that the gains made thus far are not lost. Additionally after a push from DFID partners are now reporting more cases of suspected fraud which indicates a better understanding amongst partners of the DFID definition of fraud as well as the systems and procedures around reporting and management of suspected cases and also indicates that partners are dealing with suspected fraud in a transparent manner. To date the experience has been that partners are dealing with suspected fraud cases in a timely and appropriate manner.

Summary of recommendations for the next year

CAR
- Monitor Solidarities International (SI) consortium endeavours to reinforce income generating activities (IGA) sustainability.
- Monitor Food and Agriculture Organisation (FAO) 2016 post-distribution monitoring and post-harvest monitoring to assess overall results and seed qualities.
- Monitor partner efforts to analyse and improve health service utilisation rates under the 2016-19 CAR Humanitarian and Recovery Programme (CHURP) project.
- Monitor International Medical Corps (IMC) led consortium stock levels of essential drugs and follow up on barrier analysis.
- Follow closely the implementation under Cordaid, including their plans on coverage expansion and the potential roll out performance based management system.
- Monitor progress of setting up a technical committee to ensure a cohesive approach amongst IMC consortium partners.
Follow up on protection mainstreaming in Common Humanitarian Fund (CHF) funded projects and ensure that CHF reports to board changes in their analysis on partners’ risk levels, and other relevant points including losses and fraud.
Monitor results and impact of International Committee of the Red-Cross (ICRC) community based protection.
Ensure that the CHF performance system is used and informs allocations and monitoring and evaluation (M&E).

Cameroon
- Work with World Food Programme (WFP) to look at strategies for decreasing defaulter rates in the nutrition programme and to ensure M&E adequately tracks increases in negative coping mechanisms.
- Monitor WFP pipeline management to ensure there are no ruptures in supplies.
- Follow up with UN High Commissioner for Refugees (UNHCR) both at country level and at HQ level to level to ensure that they step up in terms of improved coordination and partnerships.
- DFID to discuss UNHCR’s reporting delays with CHASE and UNHCR HQ.
- Continue to monitor UNHCR delivery in Chad and in Cameroon including funding pipelines and UNHCR’s ability to achieve coverage of assistance across operations and sectors.
- Future DFID funding to START on longer-term response should be conditioned by the implementation of lessons learnt agreed at the June 2016 workshop.

Risk
- Update the risk register in line with DFID Risk Management Framework.
- Monitor FAO’s development of a risk management framework.