## Template
PROJECT TITLE | Saving Lives at Birth
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 2015 | Milestone 2 2016 | Target 2017 | New knowledge generated is seen as acceptable to low-middle-income countries; scaling has intended impact on maternal and newborn health (Theory of change)
Reduction in maternal and infant mortality | Maternal and infant mortality rates (geographically relevant), partners to agree metrics after prioritisation exercise | Planned
Achieved
Source
Agreed common metrics from the prioritisation exercise. These will likely be combined into a compendium for review with innovators at the start of each program awarded through SL@B.
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 2015 | Milestone 2 2016 | Target 2017 | Assumptions
New technologies, service delivery models and strategies to generate demand that have shown evidence in improving maternal and infant health outcomes are implemented in low- and middle-income countries. | Cumulative number of pregnant women, mothers and newborns who accessed innovative products and/or services | Planned |  |  |  |  | Innovations might take longer to come to fruition than might originally be thought - for a wide range of reasons. Due to the high risk nature of this endeavour, it is acknowledged that only a proportion of seed grants will show proof of concept and only a proportion of transition grants will prove feasible; grantees comply with Global Access Policy; assume institutions/organizations/governments/ investors have interest and funds necessary for scaling up
|  | Achieved |  | 763334 | 1516130 | 1717943
Source
Results-based Management and Accountability Framework (RMAF) & innovator program evaluation reports
| Outcome Indicator 2 |  |  | Milestone 1 2015 | Milestone 2 2016 | Target 2017
| Cumulative numbers of MNH policies adopted and implemented at scale attributable or partially attributable to SLAB innovations | Planned
|  | Achieved |  | 1 | 1 | 1
Source
Results-based Management and Accountability Framework (RMAF) & innovator program evaluation reports
| Outcome Indicator 3 |  | Baseline | Milestone 1 2015 | Milestone 2 2016 | Target 2017
| Cumulative number of health workers and other intermidiaries accessing new products or services | Planned
|  | Achieved |  | 31856 | 51900 | 55239
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline 2012 | Milestone 1 2015 | Milestone 2 2016 | Target 2017 | Assumptions
Output 1: Funded projects that tackle maternal and newborn health in the domains of science & technology, service delivery and demand creation. | Cumulative number of seed, validation and transition grants successfully awarded since inception of SLAB in 2011. | Planned |  |  |  |  | Funding continues to be available from all partners. Successful seed grants are identified and innovators submit good transition grant proposals which are funded; recognizing that not all seed and transition grants will show proof of concept and feasibility once tested in the field.
|  | Achieved | 39 | 91 | 140 | 128
Source
RMAF & Application data
| Output Indicator 1.2 |  | Baseline 2012 | Milestone 1 2015 | Milestone 2 2016 | Target 2017
| Cumulative number of transition to scale grants successfully awarded since inception of SLAB in 2011 (sub total of above). | Planned
|  | Achieved | 0 | 14 | 16 | 18
Source
RMAF & Application data
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline 2012 | Milestone 1 2015 | Milestone 2 2016 | Target 2017
50% |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline 2012 | Milestone 1 2015 | Milestone 2 2016 | Target 2017 | Assumptions
New knowledge and learning produced and disseminated on innovative ways to to improve maternal and newborn health outcomes. | Number of papers published in peer reviewed journals | Planned |  |  |  |  | Innovations might take time to come to fruition and some will fail.
|  | Achieved | 0 | 5 | 62 | 94
Source
SLAB programme assement/RMAF/GCC & USAID media report?
| Output Indicator 2.2 |  | Baseline 2012 | Milestone 1 2015 | Milestone 2 2016 | Target 2017
| Number of media coverage outputs that mention Saving Lives at Birth portfolio each year | Planned
|  | Achieved |  | 540 | 320 | 336
Source
Meltwater report
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline 2012 | Milestone 1 2015 | Milestone 2 2016 | Target 2017
25% | Cumulative number of Innovative prototypes, service delivery models, drug reformulations and drug delivery systems developed. | Planned
|  | Achieved |  | 34 | 77 | 108
|  | Source |  |  |  |  | RISK RATING
|  | RMAF |  |  |  |  | Major
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline 2012 | Milestone 1 2015 | Milestone 2 2016 | Target 2017 | Assumptions
Diverse community of innovators engaged and supported to accelerate learning and build capacity. | Percentage of applicants each year from LMICs across the entire portfolio of grants | Planned |  |  |  |  | Partners will work with this community to foster learning across component solutions and move toward integrated solutions that address key roadblocks preventing healthy pregnancies and birth outcomes.
|  | Achieved | 48% | 55% | 54% | 50%
Source
Application data
| Output Indicator 3.2 |  | Baseline 2012 | Milestone 1 2015 | Milestone 2 2016 | Target 2017
| Percentage of grantees each year from LMICs across the entire portfolio of grants | Planned
|  | Achieved | 13% | 20% | 30% | 7%
Source
Application data
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline 2012 | Milestone 1 2015 | Milestone 2 2016 | Target 2017
25% | Cumulative percentage of awards with a female project lead | Planned
|  | Achieved |  |  | 30% | 37%
|  | Source |  |  |  |  | RISK RATING
|  | Application data |  |  |  |  | Major
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)