SNG Annual Review 2017 - Summary Sheet

Title: Sub-National Governance programme
Programme Value: £38.1 million		Review Date: 27 February – 10 March 2017
Programme Code: 202367	Start Date: 8 April 2013	End Date: 31 May 2018 (contract with OPM ends 30 Sept 2017, contract with DA ends 31 May 2018)

Summary of Programme Performance
Year	2014	2015	2016	2017
Programme Score	A	A	A+	A+
Risk Rating	Severe	Severe	Major	Major

Summary of progress and lessons learnt since last review
The Sub-National Governance programme (SNG) is DFID Pakistan’s flagship programme supporting public financial management, planning and local government reform in the provinces of Punjab and Khyber Pakhtunkhwa (KP). Now in its fourth year of delivery, SNG has been focused on consolidating and embedding key reforms and building the capacity of government systems to take evidence-based decisions and improve health and education outcomes. Some of the key achievements include:

- Delivering major increases in funding for health (37%) and education (19%) at the district level in Punjab through the interim Provincial Finance Commission (PFC) award.
- Establishing an expenditure tracking system for three (and soon six) districts in health-care in KP, allowing PKR715 million to be traced to health units, centres and hospitals. The Government of KP (GoKP) have announced that the system is to be rolled out across the province.
- Supporting continued improvements to budget transparency in both provinces, with Citizen Budgets now being formulated and published by governments.
- Nine pilots, financed by the SNG District Delivery Challenge Fund across both provinces, are being adopted and scaled up by government, including innovations to improve vaccination coverage and monitor communicable diseases.
- Creation of new specialised units, including a Tax Policy Unit, Debt Management Unit and Corporate Finance Wing, in Punjab’s Finance Department.
- Strengthening the Performance Management and Reforms Unit in the office of the Chief Secretary of KP to institutionalise performance monitoring of departments and districts.

A number of key lessons were learned through the programme in its fourth year:
- Close relationships with government and a flexible programming approach are essential if external actors want to shape and accelerate reform when opportunities arise.
- To be sustainable, government ownership of reforms is essential.
- By ensuring that activities are interlocking and coherent, governance programmes can have an impact that is more than the sum of its parts.
- By bringing government into decision-making around challenge or innovation funds early, donors can improve the chances of successful pilots being adopted and scaled up.

Summary of recommendations for the next year
- SNG should ensure that reforms that have been successfully trialled are institutionalised, according to a schedule agreed with respective provincial governments.
- That SNG use the next six months to systematically reflect on lessons learned over the course of the programme, and disseminate to influence wider development practice.
- That DFID explore how to improve linkages and synergies between larger health and education programmes and the public financial management (PFM) and planning reforms introduced by SNG.

Acronyms / AR Annual Review NFC National Finance Commission / ADP Annual Development Plan OBB Output Based Budgeting / DA Delivery Associates OBI Open Budget Index / DDCF District Delivery Challenge Fund OPM Oxford Policy Management / DEA District Education Authority P+DD Planning and Development Department / DFID Department for International Development PETS Public Expenditure Tracking Survey / DHA District Health Authority PFC Provincial Finance Commission / DLI Disbursement Linked Indicators PFM Public Financial Management / FATA Federally Administrated Tribal Areas PHC Primary Health Care / GIS Geographical Information System PKR Pakistani Rupee / GIZ Deutsche Gesellschaft für Internationale Zusammenarbeit PLSM Pakistan Living Standards Measurement / PMRU Performance Management Reform Unit / GoKP Government of Khyber Pakhtunkhwa PRA Punjab Revenue Authority / GoP Government of Pakistan SDPF Strategic Development Partnership Framework / GoPb Government of Punjab SMU Special Monitoring Unit / IAS Integrated Ambulance Service SNG Sub-National Governance programme / IDS Integrated Development Strategy SSU Strategic Support Unit / KP Khyber Pakhtunkhwa TA Technical Assistance / M&E Monitoring and Evaluation VCNCs Village Councils and Neighbourhood Councils / MDGs Millennium Development Goals VfM Value for Money / MTBF Medium Term Budgetary Framework WB World Bank

A. Introduction and Context
DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202367/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202367/documents/

DFID Pakistan’s £38.1 million Sub-National Governance programme (SNG) is supporting provincial and district governments in Khyber Pakhtunkhwa (KP) and Punjab to improve the delivery of basic services, especially health and education. The programme works in 12 districts, six each in KP and Punjab. By building the finance and planning capacity of government, the programme aims to improve service delivery, and thereby contribute towards stable democracy in Pakistan. The Oxford Policy Management (OPM) led consortium is the key implementing partner and provider of technical assistance. DFID’s contract with OPM ends on 30 September 2017. In Punjab, Delivery Associates (DA) is providing strategic support to improve performance in priority areas. DFID’s contract with DA ends on 31 May 2018.

SNG Theory of Change
(summarised from VfM framework)

More stable democracy in Pakistan through increased trust in Government
Improved access to, and citizen satisfaction with, government health and education services
Increased funding and efficiency savings for basic service delivery, targeted to the needs of the population
Reforms to PFM, planning and performance monitoring at provincial and district-levels

In 2010, Pakistan’s National Assembly passed the 18th amendment to the Constitution which, among other changes, transferred significant powers to the four provinces: Punjab, Sindh, Khyber Pakhtunkhwa and Balochistan. This decentralisation enhanced provincial responsibility for delivering basic services such as education and health. Nevertheless, Pakistan continues to perform poorly with respect to human development outcomes, failing to meet the targets set by the Sustainable Development Goals. Therefore, SNG’s support for governments in KP and Punjab, which account for 118 million people and well over half of the country’s population, is crucial. Elections are due to take place in mid-2018.

Punjab is Pakistan’s largest province and economic engine, where the ruling Pakistan Muslim League (Nawaz) party has been in power since 2009. Under the Chief Minister’s leadership, there has been a concerted focus on health and education, underpinned by reforms to financial management and budgeting. Public administration is characterised by a powerful civil service, but with decentralisation to district and lower levels of government proceeding more cautiously.

In contrast, KP’s location on the border with Afghanistan and daily security-related attacks have undermined governance and development outcomes. Widespread militancy has destroyed livelihoods and infrastructure and increased unemployment. The Pakistan Tehreek e-Insaf party won elections in KP in 2013, and has been seeking to improve political oversight of the civil service whilst embarking on radical fiscal decentralisation to new local government structures.

Over the course of the programme, SNG has been taking forward four linked activities:
1. Public financial management: Supporting the delivery of reforms to the budget process, including evidence-based budgeting, transparency, allocation and execution.
2. Governance and planning: Facilitating the transition to new local government systems and structures, and supporting the development and alignment of Annual Development Plans (ADPs).
3. Innovation: Establishing the District Delivery Challenge Fund (DDCF) to finance innovative service delivery pilots, and rolling out Geographical Information System (GIS) technology to improve evidence based policy making.
4. Strategic oversight of delivery: Building the capacity of units in the centre of Government to track performance of key priority areas and remove obstacles to delivery.

In its fourth year, SNG has focused on consolidating and institutionalising reforms introduced earlier in the programme. A key challenge has been the decision to suspend SNG activities in KP between June and September 2016, due to security concerns with the use of GIS technology. Fortunately, this disruption did not significantly impact on delivery of activities, with the exception of school rectification.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The outcome statement for SNG, as set out in the results framework, is that ‘poor people in Punjab and Khyber Pakhtunkhwa report that services are better meeting their needs’. This is to be measured through: (1) household satisfaction with basic health and education services; and (2) access to improved health and education services, focused on immunisation coverage for children under five, and net enrolment rate of girls in primary education. Data on both the above indicators is collected by the Pakistan Bureau of Statistics through the Pakistan Social and Living Standards Measurement Survey (PLSM), though this has not been consistent over the course of the programme[1]. However, a limitation of using this data is that there is a lag of two years. Therefore, data reported for the March 2017 milestone is drawn from survey results in 2014-15.
[1] Methodology and sampling of PSLM was changed during the course of the programme. The logframe indicators were updated to reflect this. However, the data for immunisation and net enrolment is also triangulated with the provincial databases on education and health, making it more reliable and relatively more current.

Outcome indicator	Baseline – March 2013	Milestone – March 2017 (based on 2014-15 survey)	Progress – March 2017 (based on 2014-15 survey)
Household satisfaction with basic health and education services	Punjab / Basic Health Unit (BHU) = 29% / Schools = 63%	BHU = 39% / Schools = 73%	BHU = 65.84% / Schools = 96.23%
	KP / BHU = 45% / Schools = 94%	BHU = 53% / Schools = 95%	BHU = 49.73% / Schools = 92.77%
Access to improved health and education services	Punjab / Immunisation = 65% / Net enrolment = 73%	Immunisation = 75% / Net enrolment = 77%	Immunisation = 70% / Net enrolment = 67%
	KP / Immunisation = 57% / Net enrolment = 60%	Immunisation = 62% / Net enrolment = 62%	Immunisation = 78% / Net enrolment = 62%

Given the lag, and shift towards different data sources, it is not possible to draw conclusions regarding progress at outcome level, nor SNG’s contribution to them. A key focus of the final year should be to revise indicators and milestones so that they are stretching and focused on continuous improvement, and continue to be underpinned with a consistent method of data collection and analysis.

Overall output score and description
Overall, SNG scored an A+ for its fourth year of delivery, moderately exceeding expectations:

Log frame output	Punjab	KP	Risk
Output 1: Public financial management and planning systems improved (30%)	A+		Moderate
1.1 Institutional capacity of government departments in public finance	A+	A
1.2 Improvement in Provincial Open Budget Index (OBI) score	A+	A+
1.3 Availability of resources to finance services	A	A
1.4 Strengthened provincial planning processes	A+	A+
Output 2: Devolved systems, processes and budgets better focused on improved service delivery (30%)	A+		Major
2.1 District budgets based on evidence of peoples’ needs	A	A
2.2 Improved flow of funds to districts and service delivery units	A++	A+
2.3 Strengthened capacity of local governments to deliver services	A+	A
Output 3: Support innovative experiments, some of which sustainably improve service delivery (30%)	A+		Major
3.1 Service improvement pilots are evaluated and successful pilots are adopted by provincial governments	A+	A+
3.2 Government uses GIS to monitor and plan quantity and quality of services	A	A+
3.3 Rectification of construction flaws in schools	n/a	B
Output 4: Strategic support improves performance in priority areas (10%)	B		Major
4.1 Improved pace and quality of strategic reforms	n/a	B
4.2 Technical assistance provided to four roadmaps	B	n/a

Key lessons
- The momentum behind reform is primarily a product of factors in the local political economy. However, the right combination of strong relationships, politically aware engagement and flexible technical assistance can shape and accelerate reforms where opportunities arise. Groundwork laid in the first two years of SNG was vital in pushing improvements when political appetite increased over the last 18 months.
- Formal rules, systems and institutions can be used to lock in reforms that may have emerged through informal interactions. This process can make reform less easy to reverse, when political conditions shift. For instance, SNG’s support for needs-based budgeting in the Punjab has now been embedded in new local government processes.
- By building linkages between workstreams, and ensuring overall coherence, governance interventions can have an impact that is greater than the sum of their parts. For instance, linking Annual Development Plan formulation at a provincial level with needs-based budgeting at a district-level, and involving citizens in the budget making process[2] have been mutually reinforcing reforms.
  [2] At the provincial level it is called ‘Budget Jirga’ (Pre-Budget Consultation) and the same process takes place in all 6 SNG districts. At both levels community organisations participate.
- In order to scale innovations and ensure government ownership, government needs to be brought in at the beginning of the process, with continuous engagement throughout. This has underpinned the success of the DDCF.
- The time and energy required to consolidate, embed and transfer ownership of reforms, in the final phase of programming, should not be underestimated. This entails difficult decisions about dropping activities that are either not gaining traction, or are sufficiently completed.

Key actions
- That SNG prepare a revised work-plan for the next six months which focuses on areas where reform can be consolidated prior to the 2018 elections, and define recommendations which could be taken forward by a successor programme.
- That SNG, as part of the above prioritisation, targets its support to local government institutions in Punjab and KP to facilitate the transition to new systems and structures (resulting from the decentralisation of tiers of government).
- That SNG, also in relation to the above, considers how the programme can accelerate improvements in budget execution, especially at district level.
- That SNG reviews its risk management strategy to ensure emerging political risks associated with 2018 elections are reflected.
- That SNG formalises and systematise its lessons learning routines to capture successes and failures and add to the body of evidence around public sector reform. These lessons will inform the design of a successor programme.
- That DFID Pakistan and SNG review the logframe outcome indicators and milestones in order to track service delivery and build a better understanding of SNG’s contribution.
- That DFID Pakistan review its coordination between SNG, and the health and education programmes, to ensure technical assistance is mutually reinforcing and delivering better PFM and governance.
- That Delivery Associates strengthen relationships with the Strategic Management Unit in Punjab to agree a transition plan that allows for exit.
- That DFID Pakistan conduct a review of the strategic support being offered to the Chief Minister of KP to improve links with performance monitoring by the Chief Secretary and improve links with DFID sector programmes in health and education.

Has the logframe been updated since the last review?
Yes, the logframe was updated in July 2016 (and the weightings of indicators within the logframe were also revised) to reflect recommendations made in the previous annual review and focus SNG activities on reforms to be institutionalised and consolidated.

## C: DETAILED OUTPUT SCORING

Output Title	Public Financial Management and planning systems improved
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Punjab Indicators	Milestones	Progress
1.1 Institutional capacity of government departments in public finance	Three units established and operational: Corporate finance, Debt management and Tax policy	Moderately exceeded (A+): All three units have started to perform functions. A draft Debt management strategy prepared and additional capacity-building support provided.
1.2 Improvement in Provincial Open Budget Index (OBI) score	Score 65 (18% improvement over baseline of 55)	Moderately exceeded (A+): OBI score increased to 68, almost 25% higher than the baseline
1.3 Availability of resources to finance services	Expenditure saving/ revenue raising activities deliver efficiency savings of £15m (cumulative)	Achieved (A): Savings of £2.48m realised from payroll audit taking cumulative savings up to £15m. Further potential savings of £6.7m identified but not yet realised[3].
1.4 Strengthened provincial planning processes	Revised ADP guidelines approved for preparation of ADP 2017-18 (approx. USD 5 billion)	Achieved (A): Guidelines approved.
[3] Discussions are taking place between the Punjab and Federal Governments about debt swaps (swapping expensive federal loans with cheaper provincial loans). If agreed, these debt swaps will generate an estimated £5.1m of savings for the Punjab Government. Additionally, a survey to identify new taxpayers has been completed. If taxes are collected from these new tax payers this will generate an estimated £1.59m of revenue per annum.

KP Indicator(s)	Milestones	Progress
1.1 Institutional capacity of government departments in public finance	PFM reform strategy approved and oversight mechanism operational	Achieved (A): PFM reform strategy endorsed by Chief Minister, and oversight committee meeting bi-monthly.
1.2 Improvement in Provincial Open Budget Index (OBI) score	Score 60 (36% improvement over baseline score of 40%)	Moderately exceeded (A+): OBI score increased to 66, with 50% improvement over baseline.
1.3 Availability of resources to finance services	Medium term resource mobilisation proposal prepared by government	Achieved (A): Proposal has been developed and being presented to next Sectoral Coordination Committee
1.4 Strengthened provincial planning processes	Over 80% of the annual development budget aligned with SDPF/IDS	Moderately exceeded (A+): 94% of the annual development budget aligned with SDPF/IDS

Summary
This output is intended to improve public financial management and planning systems. The fourth year of SNG has seen substantial progress towards the institutionalisation of sound public finance and planning systems in Punjab and KP, with reforms being escalated according to the political agenda of government. In Punjab, progress on PFM has been faster overall, reflecting the higher institutional capacity in that province, and combined leadership of the Minister and the Secretary of Finance. Support for the planning system is at a less mature stage, but momentum for reform has accelerated in the last 12 months. In KP, SNG is starting from a lower base on PFM and planning, but the approval of a PFM Reform Strategy and shrinking fiscal space has focused political attention.

Key Points
This output scores an A+, meeting expectations across all the indicators in both provinces, and exceeding expectations on improving open budgeting.

- Institutional capacity of government: In Punjab, the three specialised units, working on debt management, corporate finance and tax policy, have been rapidly absorbed into the Finance Department. In addition the SNG team have developed a handbook for staff, updated the Financial Rules, conducted a training needs assessment of the Finance Department and streamlined processes to release development funds. In KP, the PFM Reform Strategy has received political support, providing a road-map for the government. Whilst the oversight mechanism has started meeting, it will need to be further embedded (although the approval of the strategy by Cabinet on 4th April 2017 is a positive step). In both provinces, the key institutional challenge will be improving budget execution[4].
  [4] A common problem is several government departments is their inability to fully spend the money that they receive as annual budget which negatively affects service delivery. SNG has been working with the provincial governments of Punjab and KP to improve departments’ capability to efficiently spend the allocated amounts.
- Fiscal transparency: The provincial OBI scores have improved in both provinces, exceeding the milestone in the logframe. The sustainability of SNG supported budget transparency reforms is evidenced by the fact the Citizen’s Budgets are owned and published (on the internet[5]) by government in both provinces, providing assembly members and ordinary citizens with important and accessible information on public expenditure[6]. Pre-budget consultations have also been introduced. In the longer-term, there may be opportunities for DFID to support initiatives by the Government of Pakistan (GoP) on transparency; for example Pakistan’s recent membership of the Open Government Partnership.
  [5] Citizen Budget Punjab - https://finance.punjab.gov.pk/Citizen_Budget, Citizen Budget KP - http://kp.gov.pk/page/citizen_budget_2016_17
  [6] However, the Punjab citizens’ budget is only available in English. The KP citizens’ budget is available in Urdu and English.
- Resource mobilisation: While the focus of SNG activities has been on the budgeting and expenditure side, teams in both provinces have supported revenue mobilisation. In Punjab for instance, SNG supported a survey for the Punjab Revenue Authority (PRA) which identified a further 25,000 new potential tax-payers. However, in order to realise the tax potential, PRA will need to register and issue tax notification orders. Furthermore, a payroll audit has resulted in Finance Department directing the Accountant-General to stop unauthorised payments worth £2.48m each year. In KP, a resource mobilisation proposal should help create additional fiscal space, though more work is required to ensure full ownership by government. This should also help leverage greater World Bank (WB) support. SNG has played a significant role in support of the KP Revenue Authority since its creation in 2013, and has been advising them on rolling out a tax survey across the province.
- Provincial planning: Planning processes have been strengthened in both provinces. In Punjab, beyond the publication of ADP Guidelines, SNG has helped the Planning and Development Department (P+DD) develop an ADP Formulation Strategy to streamline projects and improve the quality of economic appraisals. The team have also trained 203 P+DD officials on improved planning processes. In KP, 94% of the annual development budget is now aligned with the SDPF/IDS (Strategic Development Partnerhip Framework/Integrated Development Strategy), increased from 86% a year previously, ensuring that district development budget bids are in accordance with high-level strategy. However, more work is required to track this allocation through to budget execution.

Summary of responses to issues raised in previous annual reviews (where relevant)
As noted in the last annual review there remains scope for further mutual lesson learning between both provinces on areas such as PFM strategy, and support to devolution.

Recommendations
That SNG considers measures to leverage existing PFM reforms and support budget execution at a district and provincial level.
- That SNG engage in a dialogue with Finance Minister in both provinces on the PFM reform strategy and identify a small number of focus areas on which substantive progress can be made in the coming year.
- That DFID consider how it might support the Government of Pakistan (especially at sub-national level) to take forward elements of the Open Government Partnership to increase fiscal transparency.

Output Title	Devolved systems, processes and budgets better focused on improved service delivery
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Punjab Indicators	Milestones	Progress
2.1 District budgets based on evidence of people’s needs	System of budget execution and reporting developed and implemented for primary health care (PHC) in six Districts	Achieved (A): New system in place in six focus Districts for PHC budgets, with data presented simply and objectively.
2.2 Improved flow of funds to Districts and service delivery units	Provincial Finance Commission (PFC) Award approved, resulting in increase in non-salary budget allocations to health and education by 1%	Substantially exceeded (A++): The PFC award was approved by Government with non-salary allocations for health and education increased by 19% and 37% respectively.
2.3 Strengthened capacity of local governments to deliver services	Financial management and governance reforms mainstreamed in devolved rules, systems and processes	Moderately exceeded (A+): Local government Rules of Business, Budget and accounts have incorporated financial management and governance reforms. In addition, rules have been notified and published.

KP Indicators	Milestones	Progress
2.1 District budgets based on evidence of people’s needs	Six District budgets prepared based on needs assessments	On track (A): Six District (Buner, Haripur, Karak, DI Khan, Lakki Marwat and Nowshera) budgets have aligned with guidelines on needs assessments and been approved.
2.2 Improved flow of funds to Districts and service delivery units	Expenditure tracking system established for one department in six districts (by July 2017)	On track (A+): Haripur, Karak and DI Khan have implemented expenditure tracking. Processes for roll out in the remaining three districts (Laki Marwat, Nowshera and Buner) are advanced, and will be established by July 2017. Additionally, expenditure tracking replicated by Department of Education in Karak.
2.3 Strengthened capacity of local governments to deliver services	District governments execute budget for service delivery more effectively than control districts.	Achieved (A): The average budget execution rate in focus districts was 24% compared to zero execution in control districts.

Summary
This output is intended to devolve systems, processes and budgets so that they are better focused on improved service delivery. Both provincial governments in Punjab and KP have embarked on governance reforms aimed at devolving responsibilities for delivery of essential services to district and village/neighbourhood levels of government. In 2015, GoKP implemented radical changes with the establishment of Village and Neighbourhood Councils (VCNCs), and devolution of 30% of the development budget to local governments (i.e. district, tehsil and VCNC levels[7]). The Government of Punjab (GoPb) has moved more cautiously, but in January 2017 created new District Health Authorities (DHAs) and District Education Authorities (DEAs) to manage budgets and deliver services.
[7] Of this 30%, the division between district, tehsil and VC/NC is 30:30:40 respectively

Whilst these reforms are welcome, there is a concern that decentralised tiers of government lack financial resources and administrative capacity to manage and deliver services. This resulted in poor planning, budgeting and monitoring of service delivery – with women and vulnerable groups most severely affected. SNG has been supporting districts in improving planning and PFM capacities and facilitating the transition to a new local government system.

Key Points
This output scores an A+, meeting expectations across all the indicators in KP, and on evidence-based budgeting in Punjab, with significant successes in relation to the PFC Award increasing funding to district-level health and education.

- Evidence-based Budgeting: In the fourth year of the programme, SNG has been focused on institutionalising an evidence-based budgeting process. In Punjab, SNG have supported consultation, formulation and execution of PHC budgets, including ensuring allocations of funds for medicines in the Essential Package for Health Services, and repair and maintenance of equipment and buildings. However, the creation of DHAs in early 2017 has created a challenge in terms of embedding these systems in the new institutional architecture. In KP, SNG has made progress in spite of the suspension of activities between June and September[8]. In focus districts missing facilities were provided to 305 schools with an investment of PKR189m.
  [8] Between June and September 2016 SNG activities in KP were temporarily suspended whilst the Government investigated the support being provided by SNG to GIS cells. The investigation fully vindicated the approach of SNG and their activities were resumed in October 2016.
- Increased fund flows: In Punjab, SNG led detailed analysis to develop the formula for the PFC award, and worked closely with the Minister of Finance to finalise it. It was made effective from 1 January 2017. This is a major achievement, and a result of politically astute engagement and a considerable investment of analytical effort. In addition to extra funds flowing to health and education, the award will increase funds for municipal services from PKR17bn to PKR43.2bn and bring transparency and predictability to the fiscal transfer system. In KP, expenditure tracking introduced budgeting, accounting and reporting processes to 97 Basic Health Units, 13 Rural Health centres and 11 civil hospitals with a PKR715m traceable budget. A diagnostic study, piloted by SNG and now owned by GoKP, has identified critical capacity gaps at VCNC level.
- Improved Local Government capacity: The delay in establishing the new health and education authorities in Punjab has made it difficult to engage in direct capacity-building. The SNG team has been focused on developing business processes and rules for all tiers of local government, and these rules are now posted on the GoPb website. In spite of this success, there remain significant challenges in establishing new roles and lines of accountability in local institutions, especially between Deputy District Commissioners and the new DHA and DEAs. While local government structures in KP have been in place longer, budget execution remains very low. However, it is clear from the evidence that SNG focus districts are performing better on average. SNG has also helped establish a dashboard in the Local Government Department to monitor and report on budget execution across districts.

Summary of responses to issues raised in previous annual reviews (where relevant)
The current logframe captures budget execution in its milestones, though more could be done to embed this in next year’s work-plan.

Recommendations
- SNG follows up its success on the PFC Interim Award with support for the permanent award, and builds capacity in the Finance Department in both Punjab and KP.
- SNG shift the balance of its effort in Punjab towards embedding new business processes and systems in local government, with a particular focus on helping GoPb address concerns around roles and accountabilities of the new DHAs and DEAs, and improve budget execution.
- SNG carry out a diagnostic of capacity gaps in new local government structures in Punjab, drawing on the methodology of the VCNC diagnostic conducted in KP.

Output Title	Support innovative experiments, some of which sustainably improve service delivery.
Output number per LF		3	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Punjab Indicators	Milestones	Progress
3.1 Support innovative experiments, some of which sustainably improve service delivery.	Four pilots recommended by programme steering committee for adoption benefitting 240,000 people with a focus on women, girls and marginal groups. Integrated health governance & service delivery model developed.	Moderately exceeded (A+): Four pilots recommended for adoption, with two pilots already scaled up and another two in the process of being scaled up. 1,105,309 beneficiaries including 557,910 females.
3.2 Government uses Geographic Information Systems (GIS) to monitor and plan quantity and quality of services	GIS operational in six districts, in sectors other than health and education, and with sex disaggregated data. Substantial evidence of use of GIS in decision making	Achieved (A): GIS cells fully operational in six districts and used for planning, decision making and monitoring, with sex disaggregated data.

KP Indicators	Milestones	Progress
3.1 Support innovative experiments, some of which sustainably improve service delivery.	Four pilots recommended by programme steering committee for adoption benefitting 240,000 people with a focus on women, girls and marginalised groups	Moderately exceeded (A+) / Five pilots recommended for scale-up and one for partial scale-up. Two of these pilots are at advance stage of adoption by government. 257,000 beneficiaries, including more than 140,000 women.
3.2 Government uses Geographic Information Systems (GIS) to monitor and plan quantity and quality of services	GIS operational in six districts, in sectors other than health and education, and with gender disaggregated data. Substantial evidence of use of GIS in decision making.	Moderately exceeded (A+) / KP GIS component has been operationalised, completed and handed over to government. GIS rolled out to further 8 non-SNG districts through the government allocations of PKR57 million with provincial GIS hub established.
Output indicator 3.3: Rectification of construction flaws in schools	Rectification work completed in 190 schools	Moderately underachieved (B): / Rectification work slightly behind schedule with 91 schools completed.

Summary
This output is intended to support innovative experiments, some of which sustainably improve service delivery. In its fourth year, SNG has continued to successfully showcase the importance of innovation in public policy-making and service delivery. Beyond the immediate benefits of the activities in the logframe, the enduring value of SNG has been the extent to which it has helped provincial and district governments embed innovation in its own planning and delivery mechanisms. As an example, the GoPb is establishing a £3 million Punjab Population Innovation Fund, and has sought SNG advice on replicating the successful DDCF (District Delivery Challenge Fund) model.

Key Points
This output scores an A+, either meeting or exceeding expectations on the adoption of DDCF pilots and GIS technology, but not meeting expectations on rectification of construction flaws.

District Delivery Challenge Fund: The DDCF provides funding for innovative pilots in health and education sectors. After two rounds of accepting applications which funded a total of 14 pilots, the remaining funding has been redirected to other SNG priorities in agreement with DFID. To date, nine pilots have been recommended by the Programme Steering Committee of the DDCF, which includes government representation, for adoption and scale-up. There has been continuous lesson learning. After a relatively less successful first round in KP, the team have adapted the DDCF to attract public sector actors and bring government into decision-making earlier. Some of these pilots include:
  - Learning Boost is at an advanced stage of roll-out in Punjab as a teacher training programme working in 4882 schools with over 14,400 teachers and 700,000 students.
  - Har Zindagi has been adopted by the GoPb to improve coverage of the existing electronic vaccination programme, following testing of a new card with 10,500 babies.
  - Integrated Ambulance Service (IAS) is seeking to reduce maternal mortality with faster ambulance response times, and following the district-level pilot is being rolled out across the province through Ufone.
  - D-Talk has developed a toolkit for doctors and paramedics to screen people for diabetes in health-care facilities, and increase early detection and intervention. A government committee has been formed to identify means to replicate D-Talk across KP
  - Integrated Disease Surveillance and Response System is bringing together different health information systems in KP to monitor and report on communicable diseases. 21 outbreaks have been detected and responded to since April 2016.
- Geographical Information Systems: SNG funded piloting of Geographical Information Systems in 12 districts – six each in KP and Punjab. These cells are now fully operational in all 12 districts and are being used for planning, decision making and monitoring, primarily in health and education, but also covering other key sectors. For example, district government in Sheikhupura has used GIS to increase revenue collection by improved marking territory marking of urban areas. Similarly, education department in Haripur have been able to triangulate their school enrolment data with proximity of the school locations leading to better resource planning. Therefore, SNG has been able to successfully exit from management and providing technical support to these cells. Progress in KP has been more substantial, with GIS being rolled out across the province, and a central unit created in the Chief Secretary’s office. GoKP reacted quickly when SNG activities were suspended in June 2016[9], and greatly facilitated the resumption of work, at least partly because of the success of GIS. The SNG team in Punjab are in discussions with P+DD to take forward GIS mapping at a provincial level.
  [9] See footnote 8 (above)
- Rectification of school construction flaws: GoKP is being supported to improve primary education infrastructure through construction of additional classrooms and provision of missing facilities, such as boundary walls. The overall progress of rectification work under conditional grants has been slow due to issues identified in the schools survey report, leading toward improvements being made in the engineering construction plans. Construction was also delayed as activites were suspended between June and September 2016. Rectification has since resumed with all 190 schools due to be completed by mid-2017.
- For the remaining 401 schools, DFID is discussing a possible transfer of funds as earmarked Financial Aid to the education department to carry out the rectification work and involving Parent-Teacher Councils in this process. This will be subject to third party monitoring as well as standard audit compliance by the GoP. This will ensure that the GoKP takes complete ownership of the remaining rectification work and that appropriate management and fiduciary safeguards are also in place.

Recommendations
- SNG and DFID facilitate a lesson learning exercise with colleagues working on larger education and health challenge funds to identify the key success factors which might be replicated. The ability of DDCF to secure government buy-in for adoption and scale-up at a political level is a key issue for study.
- SNG work with the GoPb to embed GIS mapping in the P+DD at the provincial level, building on success in KP.
- SNG accelerates progress on school rectification in focus districts of DI Khan and Nowshera to complete and handover by mid-2017.

Output Title	Strategic support improves performance in priority areas
Output number per LF		4	Output Score	B
Risk:		Major	Impact weighting (%):	10
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	Y

Punjab Indicator	Milestones	Progress
4.2 Technical assistance provided to four roadmaps	i) Technical assistance / provided on four roadmaps / ii) SMU transition plan developed	Moderately underachieved (B) / Delivery Associates provided significant technical assistance for the development and launch of two new roadmaps (Water and Solid Waste Management), significant support on secondary health and some support on primary health (family planning specifically). With support from Delivery Associates, the SMU conducted four rounds of stocktakes in June, July, and November in 2016 and Feb 2017. The milestone for an SMU transition plan being developed has not been met.

KP Indicator	Milestones	Progress
4.1 Improved pace and quality of strategic reforms	Regular ‘stocktakes’ conducted with political leadership, with evidence of obstacles removed in at least three priority reform areas’	Moderately underachieved (B) / SSU conducted two rounds of stocktakes during the review period and there is limited evidence of contribution to unblocking.

Summary
This output aims to provide technical assistance and capacity building support to the Strategic Support Unit (SSU) in KP and the Special Monitoring Unit (SMU) in Punjab in delivering government objectives in priority sectors[10] whilst ensuring the long-term sustainability of these institutions. Both the units are operational; however there remain challenges around sustainability. In KP particularly, the SSU needs to be more closely integrated with the Performance Management Reform Unit (PMRU), which is also supported by SNG, collecting data on service delivery which could be raised at a political level.
[10] KP priority sectors: Health, Education, Local Government, Energy and Chief Minister KP’s special initiatives Punjab priority sectors: Health, Education, Water and Solid Waste Management

Key Points
This output scores a B, falling below expectations in both Punjab and KP.

- Special Monitoring Unit: the SMU was established in mid-2014 to support the Punjab Chief Minister’s roadmaps in education and health sectors. DA provided technical assistance to the SMU to prepare and execute roadmaps in primary health (specifically family planning to complement Acasus’s work leading in the other areas), secondary health, water and solid waste management. DA provided significant technical assistance to develop and launch the Water and Solid Waste Management roadmaps over this period, and to support the development of a tax reform plan, though this has not been turned into a roadmap following a steer from the Finance Department. Progress against existing roadmaps that DA supports has largely been successful over the period: for example with SMU interventions helping to ensure hospitals were maintaining minimum stocks of medicine, and improving the cleanliness of hospitals from 22% in May 2016 to 44% in October being assessed as ‘clean’.
- Underpinning technical assistance on these roadmaps, DA has made progress on the workplan to build the capacity of the SMU for phase 1 of the contract, and delivered on the critical pieces of work for the period of this annual review: (a) undertaking a perception survey to set the baseline for how the SMU’s capacity is viewed in government, (b) undertaking a baseline capacity assessment of the SMU; and (c) developing a data action plan which sets out data management systems to ensure that stocktakes contain rigorously tested information. This output needs final sign-off by the SMU.
- Under the second phase of the contract, DA is building capacity of staff through ‘deliverology’[11] trainings. We recommend that these are clearly linked to the areas of need identified in the capacity review. The milestone in the logframe for March 2017, of developing a workplan for transition of education and primary health roadmaps to the SMU has not been met. This is partly due to the transition of leadership in the SMU (a new Head was recruited and joined in December 2016 after a 6-month period for the SMU without leadership) and difficulty in developing a jointly shared vision of the SMU’s future role with different branches of government during this period. This will need to be a key priority moving ahead. In addition, the SMU could consider models for delivering training and capacity-building that are more fully embedded in Punjab’s institutional framework (for example, through the Management and Professional Development Department).
  [11] Deliverology is a term that refres to Sir Michael Barber’s model of reform. He published Deliverology 101 in 2011 to serve as a comprehensive guide to education system reform and delivery. Governments and large public organisations adopted elements of the 'deliverology' approach. Additionally, a number of international organizations including the Organization for Economic Co-operation and Development (OECD), the World Bank, DFID, and the International Monetary Fund have sought his advice and guidance.
- Strategic Support Unit: The SSU was established in September 2015 to accelerate delivery of government priorities and remove blockages for the Chief Minister of KP. It has been fully staffed since inception through SNG KP support. Four rounds of stocktakes have been conducted over this time period including two in the review period. However, the terms of reference for the SSU need to be more clearly defined, including how its role sits with related functions exercised by parts of the civil service bureaucracy such as the PRMU. This has resulted in SSU staff being pulled in multiple directions. Whilst it is clear that the services of the SSU are in high demand, further evidence is required to make a firm assessment of their contribution to removing delivery obstacles. Moreover, as with SMU, a transition plan should be developed as a matter of high priority to show how the capacities of the staff will be institutionalised and made sustainable. The SNG contract with the SSU, which comes under the overall TA contract for SNG with OPM, is set to expire in September 2017.

Recommendations
- DA to substantially strengthen its relationship with the Head of SMU, through more regular meetings, to agree a vision for the SMU, and a transition plan for DFID support.
- SNG to work with the SSU to develop a clear work-plan of activities and process for collecting evidence of impact, with a stronger focus on sustainability and ensuring a joined-up approach to performance monitoring including creating stronger links with DFID’s sector programmes in health and education.
- DFID to carry out a mapping of the centre of government functions in KP, with a view to providing more coherent support to the Chief Minister.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
The SNG programme has spent £20.4 million from its total budget of £38.1 million. The most significant driver of costs in the programme has been technical assistance, including the cost of external consultants and core programme staff. With the additional costs of the DDCF and GIS technology, this makes up 78 percent of all expenditure. Remaining costs relate to the financial aid to government for school rectification (13%), externally financed outputs through the WB (8%) and design and monitoring (1%). DFID is looking to extend the programme however, some funds from the total programme budget may remain unspent and DFID will explore how these funds can be used most effectively.

VfM performance compared to the original VfM proposition in the business case
The appraisal case in the Business Case for SNG estimates monetary value of benefits (not discounted) to be £49.9 million. At the time of drafting, the Business Case did not seek to quantify the welfare gains from a strengthened public sector delivery of health and education. This has been made possible by subsequent analytical work in the SNG VfM framework. Nevertheless, it is clear that VfM performance of SNG has substantially exceeded expectations in the Business Case.

Assessment of whether the programme continues to represent value for money
Following the 2015 and 2016 annual reviews, a full independent assessment of SNG has been carried out based on a framework for measuring results and VfM. This assessment found that the programme either meets or exceeds expectations across all VfM criteria.

Expenditure on education and health in Punjab and KP was £729.32m higher between 2016/17 and 2013/14 after allowing for growth and inflation. SNG has been integral to securing additional resources towards priority sectors and ensuring increased expenditure is used effectively.

Higher expenditure on health and education at provincial and district levels is taking place in the context of increasing commitment by Punjab and KP to social sectors and an increase in the allocations going to provinces under the 8th National Finance Commission (NFC). DFID’s use of disbursement linked indicators (DLIs) to incentivise increased and well-balanced expenditure has supported this process. SNG’s role in securing this increase in priority expenditures in the past year include:

- The establishment of three specialized units in Tax Policy, Debt Management and Corporate Finance at the Finance Department in Punjab, with SNG and WB support. These units have helped build analytical and technical capacity of the Finance Department in these three critical areas. In addition, SNG work supported: i) Finance Department in leading Punjab's PFM Reforms, ii) revision/ updating of Financial Rules, iii) training needs assessment of officials of Finance Department and development of training plan, and iv) streamlining the process with the release of development funds.
- Revenue increased by PKR3.00 billion and brought efficiency savings of PKR4.22 billion through a tax survey that identified 25,000 new potential taxpayers, and a payroll audit of all provincial government departments in Punjab.
- A needs based transparent formula for transfer of funds to new local governments, will bring transparency and predictability into the fiscal transfer system and enable local councils/governments to plan sustainably. This came into effect in January 2017. It also brings substantial increases in allocation of resources for local service delivery. The PFC Award increased non-salary budget allocations for health by 37%, education by 19% and other local governments by 164% in Punjab.
- SNG continues to provide support to the Medium Term Budgetary Framework Cell in the KP Finance Department which is essential for MTBF/output based budgeting (OBB) implementation.

Based on transparent and illustrative attribution assumptions (set at 10% of additional budget allocations and utilisation):
- For every £1 invested by DFID in SNG to date, the programme has already achieved £3.57 worth of increased allocations to health and education in Punjab and KP.
- For every £1 invested by DFID in SNG to date, it is estimated that the programme will achieve £3.11 worth of increased utilisation of health and education resources in Punjab and KP in 2016/17.

Economy: The independent VfM assessment judged that the SNG team manages programme resources economically, buying inputs at the appropriate quality at the right price, achieving savings that either met or moderately exceeded expectations. The most significant operating costs (staff, travel, equipment) have decreased from £439,900 in year 2, to £299,100 in year 4. Examples of these savings include:

- The average cost of technical assistance has mostly been kept below the budgeted amounts. For instance short-term technical assistance has been negotiated to a rate that is 31% less than the budgeted amount.
- SNG has used the premises of District Government Sheikhupura for its North Cluster Office, provided rent-free due to effective relationships of the SNG team with the district government. This is estimated to have saved £7,015 in rent and utilities over the last year, and £21,046 over the life of the programme to date.
- As a result of the Annual Review 2016 recommendation, significant economies have been achieved in 2016 through the co-location of the Islamabad SNG office with OPM’s Islamabad office and transfer of most of the previously centrally located programme management capacity to Lahore and Peshawar. There have been significant savings in rent/utilities and in the cost of support staff.

Conversely, the cost of delivering the challenge fund has been higher than expected. It costs approximately £400,000 in terms of fees and overheads to deliver £1,000,000 of challenge fund grants, which is relatively high. Also, the consultancy fee rates in the reporting year have been slightly higher.

Efficiency: The independent VfM assessment examined the extent to which SNG inputs were converted into outputs and concluded that deliverables for the last year moderately exceeded expectations.

Out of 39 key deliverables in the annual work-plan, 29 have been completed successfully, with a further 5 on track for completion in accordance with original timelines. Other activities are either not due for completion, or have been postponed, dropped with agreement or await government action. The quality of deliverables was judged based upon government uptake and movement towards instiutionalisation. In addition to the work-plan commitments, additional work has been accomplished such as support for enhanced fiscal space in KP, and support for the creation of an internal audit function in Punjab.

Effectiveness: The assessment examined how well the outputs being delivered by SNG are achieving the desired outcome in relation to reforms to PFM, governance and planning, and service improvement pilots. Again, it was found that SNG had moderately exceeded expectations, based on a preliminary assessment of progress towards achieving significant milestones. For instance, significant improvements in budget openness and transparency have been fully adopted by government, such as the Citizen’s Budget, and district governments in SNG focus districts have adopted evidence-based budgeting. Over 480,000 beneficiaries have been directly impacted by the DDCF pilots, of whom 79% are women children or marginalised groups. There is also strong evidence to suggest that PFM reforms are increasing fiscal space for provincial governments, and leading to larger allocations and expenditures in key service delivery sectors. In Punjab, SNG supported the establishment of a debt management unit which is enabling the Government to swap expensive debt for lower interest loans, bringing initial efficiency savings of PKR2.2 billion (£16.7 million)

In the coming months, it will be important to strengthen the evidence base in relation to the budget execution and revenue realisation, in order to support the judgements on VfM outlined here. An independent impact evaluation should validate the effectiveness of the reforms which have been supported by SNG, and provide robust contribution and attribution analysis on (a) what has been materialised in the life of the programme and can be verified; and (b) what is on track to be materialised in the foreseeable future.

Quality of financial management
The programme has demonstrated strong financial management controls for downstream partners with continuous monitoring, spot checks and audit process in place. Invoicing quality is maintained. However, there is room for improvement around the quality of forecasting, which has been overly optimistic in some of its assumptions. Invoices are supported by a narrative report along with the budget tracker and support documents which are reviewed by DFID before processing the disbursement. Cost efficiencies are achieved through continuous negotiation between DFID, OPM and downstream partners.

Date of last narrative financial report	March 2017
Date of last audited annual statement	August 2016

E: RISK

Overall risk rating: Major
The programme has been rated as Major risk due to the difficult operating context and complex political economy of reform in both Punjab and KP. The risk rating has not changed since the last annual review, however the risks have been reassessed and it is important that the programme remains responsive to the changing context. Good risk mitigation measures are in place.

Overview of programme risk
The main risks are:
- Complex political economy and the potential lack of political buy in: The SNG teams have good relationships with both provincial governments and have adopted a politically-sensitive approach. However, as 2018 elections approach the programme should be mindful of the changing dynamics and the impact this may have on delivery. This can be mitigated through ongoing political economy analysis, and close engagement with key stakeholders.
- Sustainability: In the final year, the programme should continue to focus on ensuring government ownership and institutionalisation of reforms. The programme should carefully prioritise a small number of specific workstreams which can be delivered in the coming months and support technical assistance with capacity building.
- Uncertainty around the changes in local government structures: This risk is especially acute in Punjab, where changes have been introduced relatively recently, and some of the new local government institutions need to be embedded. This is a risk to programme delivery, and SNG should continue to engage at the district and sub-district level to ensure the programme adapts.
- Fiduciary: Fiscal decentralisation in both provinces has increased the potential fiduciary risk. Many finance, audit and procurement functions are yet to establish deep roots. This should be mitigated through detailed expenditure tracking to identify any potential points of leakage, as has been demonstrated through the KP public expenditure tracking survey of the KP health-care sector[12].
  [12] The survey highlighted system weaknesses which were vulnerable to leakage and recommended mitigating actions which the KP health department has agreed to implement.

Outstanding actions from risk assessment
Monthly and quarterly review discussions between SNG, DFID and Government are important opportunities to discuss risk and assess whether mitigations are sufficient. These discussions should continue.

F: COMMERCIAL CONSIDERATIONS

This programme has two commercial contracts. The first with OPM which ends on 30 September 2017, and the second with DA which ends on 31 May 2018.

Delivery against planned timeframe
Delivery against the work plan is monitored and reported on a monthly basis using monthly DFID-OPM meetings and dashboard reports. This provides an opportunity to look into the upcoming challenges, identify risks and real time solutions. Quarterly progress reports help monitor the log frame milestones. The programme activities were halted due to a temporary suspension imposed by the provincial government on SNG KP between June to September 2016. Whilst the programme remains on track overall, the temporary suspension had an impact on the school rectification work under the conditional grant component. Revised timelines have been agreed.

Performance of partnership(s)
Performance of technical assistance and innovations contract:
OPM is consistent and proactive in delivering the programme outputs and objectives and responded to the recommendations of the 2016 annual review. Coordination and communication between governments’ departments and SNG has been regular and effective. The review team also found the Punjab and KP teams are effectively sharing information and lesson learning, for example on the DDCF and M&E framework. The steering committees, chaired by government counterparts and attended by DFID, are key governance mechanism to review programme progress and take key decisions.

Coordination with other programmes
SNG is a cross cutting programme and has developed linkages with budget support and demand side programmes on education and health. One of SNG’s objectives is to create synergies between all these programmes and build better coordination. SNG has established routines of coordination with other DFID funded programmes in education, health and voice and accountability sectors in both the provinces. However, this coordination could yet be strengthened, especially between different technical assistance teams working on health and education. Both the offices are closely working with other donors including WB and Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) around the broader agenda of governance.

Asset monitoring and control
A random spot check was conducted during the review period in Lahore and Hafizabad district. Asset spot checks are also a regular feature of DFID and SNG teams’ field visits throughout the year. The OPM team maintains a robust asset register with all assets properly reflected and coded. Spot checks of procurement documents and vehicle log books were also found that adequate controls are in place. OPM maintains a record of bids, quotations and award processes. This provides a comprehensive audit trail and also enables Value for Money analysis.

Recommendation
That DFID develop stronger coordination mechanisms within the DFID office to ensure improved coherence between technical assistance teams working on health and education and SNG.

G: CONDITIONALITY

Update on partnership principles (if relevant)
The majority of the UK’s support for SNG is delivered through technical assistance to the Governments of Punjab and KP, with an additional small element of earmarked budget support to KP for the rectification of schools. However, SNG is part of a wider aid relationship between the UK and Pakistan which is based on an assessment of Government’s commitment to our Partnership Principles.

These principles cover issues relating to human rights; financial management and corruption; and strengthening domestic accountability. DFID Pakistan regularly conducts the Partnership Principles Assessment with the EAD at the federal level and the text is shared every six months. The Assessment was discussed most recently in December 2016 during our Bilateral Aid Talks. DFID Pakistan’s view is that the Government is demonstrating a credible commitment to the four principles. For example, on public financial management the direction of travel shows some improvements in the areas of budget transparency and progress on audit and procurement. DFID can therefore continue to deliver SNG programme activities as all of the work falls within the remit of the Partnership Principles.

H: MONITORING & EVALUATION

Evidence and evaluation
A mid-term evaluation of the programme was completed in 2015. An independent evaluation will be commissioned as the programme approaches its end. This evaluation will assess the overall results and impact which have been achieved by the programme. SNG maintains a comprehensive tracking system of evidence against key deliverables and outputs. This evidence demonstrated a general shift towards consolidation of reforms and institutionalisation. The findings of the evaluation as well as the evidence generated throughout the programme will be used to inform the design any successor programme.

Monitoring progress throughout the review period
Following the 2016 annual review, the logframe was revised to reflect consultations with SNG.

SNG maintains a robust monitoring, evaluation and reporting framework, which is structured around: (i) progress monitoring against work plan deliverables; (ii) progress verification and process monitoring; (iii) outcome monitoring to track impact of activities; and (iv) assessment of progress against logframe indicators/milestones.

The development of a VfM framework for SNG allowed the programme to establish, test and validate the link between activities with outputs, intermediate and final outcomes. The VfM framework now captures SNG Programme dimensions, including economy, efficiency, effectiveness, cost-effectiveness, equity as well as learning and adaptation. DFID AR team reviewed the VfM report, validated some of the assessments, and collected evidence on which to base these judgements.

Quarterly and annual progress reports are provided by the SNG team to DFID, capturing progress against milestone targets in the logframe. SNG has provided DFID with full access to their knowledge management system, which includes evidential documents against each of the logframe indicators/ milestones and work plan deliverables. Evidence has been quality assured by OPM Oxford and the government counterpart departments. The programme has actively disseminated its learning on innovations through a Challenge Fund Position Paper. SNG also used case studies and workshops to share evidence and lesson learning across sectors – in particular education and health.

Recommendations:
- That SNG and DFID agree on revisions to the logframe, setting milestones for the final year of the programme, which are stretching and also based on a prioritisation of work-streams aimed at consolidating reform progress.
- That SNG and DFID commence discussions on the terms of reference for the final impact evaluation to draw robust and evidence-based conclusions on the outcome and impact of the programme. This exercise should also focus on drawing out key lessons learned which might be more widely disseminated to inform governance programming and development practice.