## Revised 2016
PROJECT NAME
IMPACT | Impact Indicator 1 |  | Baseline (2013/14) | Milestone 1: 2014/15 | Milestone 2: 2015/16 | Milestone 3: 2016/17 | Target: May 2018
|  | Planned | 8% | less than 8% | 10% | less than 8% | less than 8%
Improved macroeconomic stability and resilience | Average annual inflation rate | Achieved |  | 7.7%
Source
Ethiopia Central Statistics Agency website, NBE Quarterly Bulletin
| Impact Indicator 2 |  | Baseline (2013/14) | Milestone 1: 2014/15 | Milestone 2: 2015/16 | Milestone 3: 2016/17 | Target: May 2018
|  | Planned | 8% | 7.5% | 6% | 7.5% | 7.5%
| Annual GDP growth | Achieved |  | 8.7%
Source
IMF World Economic Outlook/Article IV Staff reports
| Impact Indicator 3 |  | Baseline (2013/14) | Milestone 1: 2014/15 | Milestone 2: 2015/16 | Milestone 3: 2016/17 | Target: May 2018
|  | Planned | B1/B/B | B1/B/B | B1/B/B | B1/B/B | B1/B/B
| Sovereign debt rating for Ethiopia (Moody's/Fitch/S&P) | Achieved |  | Moody's: B1 Fitch: B S&P: B
Source
Websites of Moody's, Fitch and S&P
OUTCOME | Outcome Indicator 1 |  | Baseline (2013/14) | 2015-06-01 | 2016-06-01 | 2017-06-01 | Target: May 2018 | Assumptions
Increased use of evidence in macroeconomic and high level economic policymaking | Evidence that macro fund outputs have led to an improvement in GOE economic policy making | Planned | NA | 5 policy initiatives, strategies or laws showing cleat evidence of significant influence of macro fund outputs. | a) Clear evidence that EPAU has had a positive impact on GTP 2 b) Clear evidence that work with IGC has had a positive influence on the policies and operation of the EIC | Macroeconomic reporting from NPC is informing the decisions of the economic council Key NBE officials have established an understanding of the operations and management of the secondary market | Ethiopia has established a secondary market for securities based on the advice of the IMF Support from IGC to EIC relationship building programme results in the percentage of firms converting from pre-operational to operational increasing from 29% to 50% | - A benign international economic environment and absence of domestic economic shocks. - Sufficient domestic revenue collection to fund government policy programmes - Improved policies are actually implemented GoE officials
|  | Achieved |  | As activiites have just got underway it is not possible to judge the influence on policy-making. | a) Achieved. EPAU’s Technical Oversight Committee confirmed that EPAU prepared the macroeconomic framework for the GTP2. b)The Relationship Building programme is successfully embedded within the EIC. Initial evidence suggests that there has been an impact on how quickly and effectively issues are being dealt with.
Source
Desk review and stakeholder interviews by Fund Manager/Lead Adviser
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
|  | 4.5 | 0.5 | 0.8 | 5.8 |  | 77.59%
INPUTS (HR) | DFID (FTEs)
0.5
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2013/14) | Milestone 1: May 2015 | Milestone 2: May 2016 | Milestone 3: May 2017 | Target: May 2018 | Assumption
Effective policy support to the Ethiopian Investment Commission | Delivery of technical support in investment promotion and export promotion workstream | Planned | N/A |  | Interim report received by DFID in April 2016 detailing significant progress within the EIC reationship building programme. The delivery of a report of the One Stop Shop service of EIC. | Interim report provides evidence of significant progress of the relationship building programme including transfer of principles of programme to industrial parks; extension of file sharing system; induction of new staff; and embedding of processes within organisation | Over 90% of participants in the relationship building programme consider themselves well-serviced by the programme. | - Research and technical outputs are of high quality and relevance. - Capacity is developed to ensure appropriate uptake of research findings - Evidence is brought to the attention of users - Ideologically or politically driven policymaking does not dominate over the use of evidence.
|  | Achieved |  | Development and introduction of new file sharing system for relationship building programme Delivery of report to ERCA on recommendations on the process for importing inputs for manufacturing | i) Achieved. Report received, which clearly set out evidence of progress on the relationship building programme. Report on one stop shop delivered to Head of EIC.
Source
Internal Fund Management documents; reports from implementing agencies
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline (2013/14) | Milestone 1: May 2015 | Milestone 2: May 2016 | Milestone May 2017 | Target: May 2018
20% | Feedback from high level officials within GOE | Planned | N/A |  | Director General of EIC and/or PM's adviser on industrialisation rate the support as highly valuable | Director General of EIC and/or PM's adviser on industrialisation rate the support as highly valuable
|  | Achieved |  | Not measured | Very positive feedback received from PM’s advisor on industrialisation.
|  | Source | [5 empty] | RISK RATING
|  | Discussions between DFID staff and GOE officials | [5 empty] | med
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
|  | 0.43 |  |  |  |  | 100%
INPUTS (HR) | DFID (FTEs)
0.05
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1: May 2015 | Milestone 2: May 2016 | Milestone May 2017 | Target June 2018 | Assumptions
|  | Planned | NA | 5 | 10 | 15 | 15 | - Research and technical outputs are of high quality and relevance. - Capacity is developed to ensure appropriate uptake of research findings - Evidence is brought to the attention of users - Ideologically or politically driven policymaking does not dominate over the use of evidence. - Additional funding from others donors is found to fill remaining financing gaps
Effective implementation of the Prime Minister's Economic Policy and Analysis Unit (EPAU) work plan | Number of Policy Papers, White Papers, programme evaluations and research products produced by EPAU (per year). | Achieved |  | 4 major outputs | 12
Source
EPAU bi-annual reporting.
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline | Milestone 1: May 2015 | Milestone 2: May 2016 | Milestone May 2017 | Target June 2018
30% | Feedback from the EPAU Technical Oversight Committee and senior GoE policymakers on the quality and effectiveness of EPAU's outputs. | Planned | NA | In general strong, some recommendations for improvements | Strong with clear reference to quality of outputs and impact. | Strong with clear reference to quality of outputs and impact. | Strong with clear reference to quality of outputs and impact.
|  | Achieved |  | Feedback has been strong althugh problems in hiring and retaining key staff crea risks for maintaining the quality of the outputs | EPAU Technical Oversight Committee happy with the performance of EPAU. EPAU is consulted before any economic policy is implemented and has received very good feedback from senior officials in Government.
|  | Source | [5 empty] | RISK RATING
|  | Informal stakeholder survey and feedback received though day to day contact with GoE counterparts | [5 empty] | med
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
|  | 0.8 | 0.2 | 0.6 | 1.6 |  | 50%
INPUTS (HR) | DFID (FTEs)
0.1
Output 3 | Output Indicator 3.1 |  | Baseline | N/A | Milestone 1: May 2016 | Milestone 2: May 2017 | Target: December 2017 | Assumptions
Effective delivery of technical assistance to the National Bank of Ethiopia on secondary debt markets | Delivery of planned outputs against IMF project proposal | Planned | N/A | N/A | Terms of reference agreed between IMF and NBE At least one short term mission by IMF staff | Long term adviser in place Review of policy environment undertaken Capacity building activities from NBE staff taken place - both on the job training and at least one study tour to either India, Kenya or Uganda | Preparation of proposal on development of secondary debt market At least two study tours completed as well as formal and on the job training for NBE staff | - Research and technical outputs are of high quality and relevance. - Capacity is developed to ensure appropriate uptake of research findings - Evidence is brought to the attention of users - Ideologically or politically driven policymaking does not dominate over the use of evidence. - Additional funding from others donors is found to fill remaining financing gaps
|  | Achieved |  |  | Terms of reference agreed; Letter of understanding (LOU) signed; disbursement made. Short term mission is currently underway.
Source
IMF reporting
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline | N/A | Milestone 1: May 2016 | Milestone 2: May 2017 | Target: December 2017
20% | Feedback from senior NBE offiicals on the quality and effectiveness of EPAU's outputs | Planned | NA |  | NBE offcials rate the support as highly valuable | NBE offcials rate the support as highly valuable | NBE offcials rate the support as highly valuable
|  | Achieved |  |  | Deputy Governor of NBE confirmed that DFID support is highly appreciated given that establishment of the long-awaited secondary debt market is a key priority under GTP2.
|  | Source | [5 empty] | RISK RATING
|  | Discussions with NBE officials | [5 empty] | med
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
|  | 0.5 | 0 | 0 | 0.5 |  | 100%
INPUTS (HR) | DFID (FTEs)
0.05
Output 4 | Output Indicator 4.1 |  | Baseline | Milestone 1: May 2015 | Milestone 2: May 2016 | Milestone 3; May 2017 | Taget: June 2018 | Assumptions
The macroeconomic support fund is a useful resource for GOE policy makers | Ad hoc requests linked to macro economic policy making are delivered on time and to a high quality | Planned |  |  | a) Research on Ethiopia's tax policy delivered and accepted by Government b) Framework for macro economic reports produced; monthly, quarterly and semi-annual report produced; training provided to NPC on macroeconomic reporting | TBC based on demand | TBC based on demand | - Research and technical outputs are of high quality and relevance. - Capacity is developed to ensure appropriate uptake of research findings - Evidence is brought to the attention of users - Ideologically or politically driven policymaking does not dominate over the use of evidence. - Additional funding from others donors is found to fill remaining financing gaps
|  | Achieved |  | Support to design work of PPP framework Training on natural resource management delivered | a) The Tax policy TA was successfully completed. MoFEC officials confirmed that the TA was delivered as per their expectations b) Framework for macro-economic reports prepared; semi-annual macroeconomic report prepared, discussed & finalized and draft nine-month macroeconomic report prepared. Training on macroeconomic reporting and analytical skills delivered. NPC confirmed that the quality of output has been very good and in line with agreed TOR.
Source
Individual recipients/beneficiaries of macro fund utputs feedback to DFID
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline | Milestone 1: May 2015 | Milestone 2: May 2016 | Target June 2017
10% | Level of awareness and use of outputs of Macro Fund among Government and development partners | Planned | NA | Some partners aware of fund | Evidence used regularly in partner discussions | Evidence used regularly in partner discussions | Partners regularly using evidence produced by macro fund outputs in press or public forums, or in developing their own analyses
|  | Achieved |  | There is a good level of awareness of DFID's ability to support macroeconomic policy making among GOE officials | Evidence mixed
Source
Feedback from GOE officials
| Output Indicator 4.3 |  | Baseline | Milestone 1: May 2015 | Milestone 2: May 2016 | Target June 2017
| Annual number of requests from GoE officials for policy support on macro and high level economic policy advice | Planned | NA | 5 | 8 | 10 | 12
|  | Achieved |  | 7. This is in addition to the pieces of work supported through the fund's core funding to EPAU | 8
|  | Source | [5 empty] | RISK RATING
med
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
|  | 0.8 | 0.2 | 0.6 | 1.6 |  | 50%
INPUTS (HR) | DFID (FTEs)
0.1
Output 5 | Output Indicator 5.1 |  | Baseline | N/A | N/A | Milestone 2: May 2017 | Target: June 2018 | Assumptions
Delivery of high quality expertise on trade logistics | Use of DFID-funded TA in design of new World Bank programme on trade logistics | Planned |  |  |  | Bank project dealing with key constraint in trade logistics sector approved by board | N/A | - Research and technical outputs are of high quality and relevance. - Capacity is developed to ensure appropriate uptake of research findings - Evidence is brought to the attention of users - Ideologically or politically driven policymaking does not dominate over the use of evidence. - Additional funding from others donors is found to fill remaining financing gaps
Achieved
Source
World Bank/IFC contacts
| Output Indicator 5.2 |  | Baseline | N/A | N/A | Milestone 2: May 2017 | Target: June 2018
| Delivery of high quality support to Ethiopian Maritime Affairs Authority | Planned |  |  |  | Logistics Transformation Office established | LTO is fully functional and evidence that capacity has been built.
Achieved
|  | Source | [5 empty] | RISK RATING
med
IMPACT WEIGHTING (%) | Output Indicator 5.3 |  | Baseline | N/A | N/A | Milestone 2: May 2017 | Target: June 2018
20% | Extent to which Ethiopian Government is able to take more informed decision on its policy on the Berbera corridor. | Planned |  |  |  | Corridor diagnostic report delivered and findings presented to Joint Operating Committee (EMAA and BPA) | Evidence this report has been used to form a policy position or take action on the Berbera corridor
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
|  |  | 0 | 0 | 0.5 |  | 0%
INPUTS (HR) | DFID (FTEs)

## LF 2014
PROJECT NAME
IMPACT | Impact Indicator 1 |  | Baseline (2013/14) | Milestone 1: 2014/15 | Milestone 2: 2015/16 | Milestone 3: 2016/17 | Target: May 2018
|  | Planned | 8% | less than 8% | less than 8% | less than 8% | less than 8%
Improved macroeconomic stability and resilience | Average annual inflation rate | Achieved
Source
Ethiopia Central Statistics Agency website, NBE Quarterly Bulletin
| Impact Indicator 2 |  | Baseline (2013/14) | Milestone 1: 2014/15 | Milestone 2: 2015/16 | Milestone 3: 2016/17 | Target: May 2018
|  | Planned | 8% | 7.5% | 7.5% | 7% | 7%
| Annual GDP growth | Achieved
Source
IMF World Economic Outlook/Article IV Staff reports
| Impact Indicator 3 |  | Baseline (2013/14) | Milestone 1: 2014/15 | Milestone 2: 2015/16 | Milestone 3: 2016/17 | Target: May 2018
|  | Planned | B1/B/B | B1/B/B | B1/B/B | Ba3/BB-/BB- | Ba3/BB-/BB-
| Sovereign debt rating for Ethiopia (Moody's/Fitch/S&P) | Achieved
Source
Websites of Moody's, Fitch and S&P
OUTCOME | Outcome Indicator 1 |  | Baseline (2013/14) | Milestone 1: 2014/15 | Milestone 2: 2015/16 | Milestone 3: 2016/17 | Target: May 2018 | Assumptions
|  | Planned | NA | 5 | 5 | 5 | 5 | - A benign international economic environment and absence of domestic economic shocks. - Sufficient domestic revenue collection to fund government policy programmes - Improved policies are actually implemented GoE officials
Increased use of evidence in macroeconomic and high level economic policymaking | Number of policy initiatives, strategies and laws showing clear evidence of significant influence of Macro Fund outputs (per year). | Achieved
Source
Desk review and stakeholder interviews by Fund Manager/Lead Adviser
| Outcome Indicator 2 |  | Baseline (2013/14) | Milestone 1: 2014/15 | Milestone 2: 2015/16 | Milestone 3: 2016/17 | Target: May 2018
| Level of awareness and use of outputs of Macro Fund among Government and development partners | Planned | NA | Some partners aware of fund | Evidence used regularly in partner discussions | Evidence used regularly in partner discussions | Partners regularly using evidence produced by macro fund outputs in press or public forums, or in developing their own analyses
Achieved
Source
Possible stakeholder survey, minutes of Macro SWG
| Outcome Indicator 3 |  | Baseline (2013/14) | Milestone 1: 2014/15 | Milestone 2: 2015/16 | Milestone 3: 2016/17 | Target: May 2018
| Annual number of requests from GoE officials for policy support on macro and high level economic policy advice | Planned | NA | 5 | 8 | 10 | 12
Achieved
Source
Fund Manager/Lead Adviser
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
|  | 4.5 | 0.5 | 0.8 | 5.8 |  | 77.59%
INPUTS (HR) | DFID (FTEs)
0.5
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2013/14) | Milestone 1: May 2015 | Milestone 2: May 2016 | Milestone 3: May 2017 | Target: May 2018 | Assumption
|  | Planned | 0 | 5 | 10 | 12 | 15 | - Research and technical outputs are of high quality and relevance. - Capacity is developed to ensure appropriate uptake of research findings - Evidence is brought to the attention of users - Ideologically or politically driven policymaking does not dominate over the use of evidence.
Production of effective and policy relevant evidence and analysis that strengthens knowledge base and economic policy making processes within GoE. | Number of research and analytical products, and pilot initiatives provided by the Fund (per year). | Achieved
Source
Internal Fund Management documents; reports from implementing agencies
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline (2013/14) | Milestone 1: May 2015 | Milestone 2: May 2016 | Milestone 3: May 2017 | Target: May 2018
50% | Weighted average of project outputs delivered scoring "good" or "excellent" as per DFID's internal scoring system | Planned | 0 | 75% | 80% | 85% | 90%
Achieved
|  | Source | [5 empty] | RISK RATING
|  | Scoring system to be developed as part of the regular review process | [5 empty] | med
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
|  | 2.25 | 0 | 0 | 2.25 |  | 100%
INPUTS (HR) | DFID (FTEs)
0.4
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1: May 2015 | Milestone 2: May 2016 | Milestone 3: May 2017 | Target: May 2018 | Assumptions
|  | Planned | NA | 5 | 5 | 5 | 5 | - Research and technical outputs are of high quality and relevance. - Capacity is developed to ensure appropriate uptake of research findings - Evidence is brought to the attention of users - Ideologically or politically driven policymaking does not dominate over the use of evidence. - Additional funding from others donors is found to fill remaining financing gaps
Production of effective and policy relevant capacity building initiatives that strengthen economic policy making processes within GoE. | Number of capacity building exercises (e.g training, workshops) provided by the fund (per year) | Achieved
Source
Partcipants feedback; technical reports from implementing agency
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline | Milestone 1: May 2015 | Milestone 2: May 2016 | Milestone 3: May 2017 | Target: May 2018
20% | Weighted average of project outputs delivered scoring "good" or "excellent" as per DFID's internal scoring system | Planned | 0 | 75% | 80% | 85% | 90%
Achieved
|  | Source | [5 empty] | RISK RATING
|  | Informal stakeholder survey and feedback received though day to day contact with GoE counterparts | [5 empty] | med
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
|  | 1.45 |  |  | 1.45 |  | 100%
INPUTS (HR) | DFID (FTEs)
0.1
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1: May 2015 | Milestone 2: May 2016 | Target June 2017 | N/A | Assumptions
|  | Planned | NA | 5 | 10 | 15 |  | - Research and technical outputs are of high quality and relevance. - Capacity is developed to ensure appropriate uptake of research findings - Evidence is brought to the attention of users - Ideologically or politically driven policymaking does not dominate over the use of evidence. - Additional funding from others donors is found to fill remaining financing gaps
Effective implementation of the Prime Minister's Economic Policy and Analysis Unit (EPAU) work plan | Number of Policy Papers, White Papers, programme evaluations and research products produced by EPAU (per year). | Achieved
Source
EPAU bi-annual reporting.
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline | Milestone 1: May 2015 | Milestone 2: May 2016 | Target June 2017
30% | Feedback from the EPAU Technical Oversight Committee and senior GoE policymakers on the quality and effectiveness of EPAU's outputs. | Planned | NA | In general strong, some recommendations for improvements | Strong with clear reference to quality of outputs and impact. | Strong with clear reference to quality of outputs and impact.
Achieved
|  | Source | [5 empty] | RISK RATING
|  | Informal stakeholder survey and feedback received though day to day contact with GoE counterparts | [5 empty] | med
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  | DFID SHARE (%)
|  | 0.8 | 0.2 | 0.6 | 1.6 |  | 50%
INPUTS (HR) | DFID (FTEs)
0.1