Annual Review

Title: Humanitarian Emergency Procurement Programme (HEPP)
Programme value: £12.5m		Review date: 31/10/16
Programme code: 203416	Start date: 09/05/2012	End date: 30/06/2017

Summary of programme performance
Year	2013/14	2014/15	2015/16
Programme score	A	A	A
Risk rating	Medium	Low	Minor

Summary of progress and lessons learnt since last review

Period of reporting April 2015 – April 2016
- Responding to the Nepal Earthquake[1] with over 230 tonnes of Non Food Items (NFI’s) transported by air and 115 tonnes by road, including over 23,000 shelter kits, 1,700 solar lanterns and nearly 2,000 Life Saver Cubes, plus the Air Cargo Handling Equipment (ACHE).
  [1] Funding was provided from DFID Nepal
- Responding to migrant crisis in Europe[2] with over 800 tonnes of aid delivered including over 174,000 blankets, 30,000 sleeping mats, 12,000 sleeping bags and nearly 4,000 tents.
  [2] Funding was provided from Migration Department programme.
- Provision of NFIs for Yemeni refugees in Djibouti, and blankets in Iraq[3].
  [3] Funding was provided from MENAD programmes.
- Procurement to meet the shelter needs of up to 75,000 people.
- Establishment of Framework Agreements[4] for solar lighting and sleeping mats; and new contracts agreed for aviation services, hygiene kits, and ACHE and storage at Doncaster airport.
  [4] The renewal of a number of Framework Agreements put on hold pending the outcome of the new CHASE Operations Team (OT) contract.
- Provision of armoured vehicles for Nigeria and Ukraine, and boats in Sierra Leone[5].
  [5] Funding was provided from relevant Country Programmes.
- Opening DFID’s Stockpile to Rapid Response Facility (RRF) NGOs, allowing them to access it during an RRF activation, meaning quality items are distributed, quicker and cheaper.
- Research and testing to take advantage of new developments and technologies in the sector, such as fire retardant plastic sheeting, new water filtrations devices, and deployment communications.
- In collaboration with DFID’s IT department, upgraded the deployment platform to ensure it is taking advantage of the latest developments in IT and communications equipment.

Summary of recommendations for the next year
- Dedicate part of a CHASE Humanitarian Adviser to the HEPP project.
- Set-up a new Framework Agreement for camping items, such as sleeping bags.
- Review and update the ACHE with the World Food Programme, as required.
- Continue to engage in and influence the humanitarian community to improve the quality and accessibility of global stockpiles by offering UK support and expertise.
- Improve HEPP financial management, particularly the accuracy of forecasting, to HRG.
- Improve HEPP annual reporting of activities to HRG.
- Staff to routinely join monitoring missions where a new item or approach has been used for the first time or large amounts of NFI’s have been used to assess performance, as was piloted in Ethiopia, and obtain feedback.
- Conduct/commission an asset check within six months following this Annual Review.
- Further improvements to the deployment platform so that a field team can operate in all forms of weather conditions, particularly IT and communications.
- Update the logframe to the end of programme (June 2017).

A. Introduction and context

The UK government’s humanitarian policy ‘Saving lives, preventing suffering and building resilience’ recognised humanitarian need is likely to continue to grow. One of the seven goals it set for improving the effectiveness of UK humanitarian support was to reinforce the UK Government’s own capacity to respond to humanitarian crises. In doing so, it recognised that carefully targeted bilateral support provided a valuable contribution to the international response and the UK has a strong reputation for its humanitarian work in rapid-onset disasters and in fragile and conflict-affected states.

The HEPP is DFID’s operational Stockpile, and is part of the global humanitarian community’s preparedness toolkit that can be mobilised rapidly when a disaster occurs. DFID has held a stockpile of emergency NFI’s for many years, but following publication of the HERR (Humanitarian Emergency Response Review), the ICAI (Independent Commission for Aid) review of Typhoon Haiyan response, and requests from Ministers, the size and composition of the Stockpile has increased over time. In 2015/16, the Secretary of State approved an additional £0.5m for the HEPP to respond to the European migrant crisis.

The programme’s aim is to ensure NFI’s can be delivered to people in need in humanitarian emergencies. To meet these needs, DFID holds a stockpile that can be drawn upon at short notice for a response. DFID has developed a network of suppliers who can supplement these items when needed. The Stockpile works in parallel with a similar Stabilisation Unit (SU) support package and shares warehousing, labour and maintenance services. To keep the Stockpile appropriate and relevant, DFID undertakes a process of reviews to test the performance of materials and products to take advantage of latest innovations and developments in the sector.

## B: Performance and conclusions

Outcome assessment: A
The intended outcomes of the programme are to enable: DFID to respond quickly, effectively and appropriately to humanitarian emergencies; the international system to be better prepared to respond quickly, effectively and appropriately to humanitarian emergencies and their changing nature and scale; and innovations in shelter materials and NFI’s to be assessed properly and brought into use as part of a response. Stockpile equipment, materials and logistical expertise have been used to respond to humanitarian emergencies in Nepal, Ukraine, Djibouti, Europe and Iraq. The table below shows the quantity of NFI’s distributed for each response.

Response	Items	Quantity
Nepal Earthquake	DFID Shelter Kits / Solar Lanterns / LifeSaver Cubes / Body Bags / 2.1 tonne All Terrain Forklift	13,176 / 1,728 / 1,980 / 180 / 2
Nigeria (UNDP)	Armoured vehicles	4
Ukraine (OCHA)	Armoured Vehicles	4
Djibouti Migrant Crisis	DFID Shelter Kits / 14 tre buckets (Oxfam spec) / Synthetic Blankets / Kitchen Sets (IFRC spec) / Pole and peg sets	367 / 840 / 2,300 / 567 / 167
Iraq	50% Wool Blankets	33,120
Europe Migrant Crisis	High thermal synthetic blankets / DFID Family Tents / DFID Atlantic Tents / 2.4 tonne Forklift	151,525 / 2,121 / 1,846 / 2

CHASE has also taken part in various meetings to encourage improvements in the international system for managing stockpile items globally, including:
- taking part in preparatory work and consultation between WFP, UNHCR (United Nations High Commissioner for Refugees), UNICEF (United Nations International Children’s Emergency Fund) and OCHA for the DFID Preparedness Programme;
- representation at the Logistics Cluster meetings held in Split, Brindisi, Rome and Lyon; and
- participation in Working Groups following the Logistics Cluster meetings, in particular the Emergency Supply and Pre-positioning (ESUPS) Working Group.

Has the logframe been updated since the last review?
The logframe has been updated. It will be updated again following this Annual Review to ensure milestones remain valid to the end of programme in June 2017.

## C: Detailed output scoring

Output	DFID humanitarian stocks and agreements with suppliers ensure UK can meet the needs of affected communities across a wider range of humanitarian emergencies.
Output number		1	Output score	A
Risk		Minor	Impact weighting	50%
Risk revised?		Yes	Impact weighting revised?	No

Output Indicator 1.1 UK stockpile (quality, content, and volume) is kept under review to ensure it able to meet humanitarian needs on an ongoing basis and respond to emerging needs

Milestone 2: The holdings of solar kits, water filters, sleeping mats and hygiene kits will all be complete to a level that is enough to meet the needs of 75,000 people. The holding of Aircraft Handling Equipment will be complete, with a call down process agreed between DFID and WFP

Ministers requested the stockpile was increased in size to meet the needs of 75,000 people. This target has been met. Stock holdings of solar kits, water filters, sleeping mats and hygiene kits have been increased to meet targets. The table below shows the items and quantities procured. The ACHE module is now ready, and was successfully deployed in Sierra Leone and Nepal. DFID and WFP have in place an ACHE MOU, which may need to be revised in future to ensure it remains fit for purpose. A full list of items held in the Stockpile at April 2016 can be found at Annex A.

Item	Procured 2015/16	Stock April 2016
Shelter kits	15,000	40,000
Family tents	1,000	7,500
Hygiene kits	15,000	15,000
Solar lanterns	7,500	12,500
Solar lights	15,000	15,000
2.5T fork lift	1	5
7/8T forklift	2	2
Boats with engines	4	4

Output Indicator 1.2. Effective links made with private sector suppliers and public sector / NGO’s that enables rapid access to goods, equipment, materials not held in UK stockpile. Links made with potential private sector suppliers and innovators on international humanitarian products.

Milestone 2: The new frameworks with new suppliers have been utilised to make significant increases to the UK Stocks, as the Stockpile Uplift nears its formal completion.

Framework Agreements allow DFID to undertake rapid procurement to supplement stockpiles during an emergency and also reduce timescales for replenishment. They also allow DFID to secure competitive pricing through mini-competitions run between suppliers, setting the terms and conditions under which the goods will be procured, helping ensure good value for money. The table below shows all requests made through Framework Agreements.

A new tender was run in 2015/16 for a Framework Agreement for Aviation Services. The new Aviation Services Contract now expires in February 2018 and is made up of four components: cargo, passengers, helicopters and emergency passenger deployments. A new Clothing framework was also put in place to cover CHASE deployment kit and Stabilisation Unit’s Police Store Clothing, and includes polo shirts, boots and top layer cold weather clothing. DFID’s Migration Response required a large number of sleeping bags, so it is recommended a Framework Agreement is set-up to cover camping items, including sleeping bags. A full list of current Framework Agreements can be found in Annex B.

Item	Procured for uplift	Procured for responses	Procured for replenishment	Total procured
Blankets	0	61,899	135,825	197,724
Tents	1,000	0	4,135	5,135
Shelter Kits	15,000	10,000	47,027	72,027
Lifesaver Cubes (water filtration)	0	0	0	0
Buckets	0	0	26,734	26,734
Kitchen Sets	0	0	20,535	20,535
Solar Lanterns	7,500	1,680	1,728	10,908
Armoured Vehicles	0	0	8	8
K Loader (aircraft main deck loader)	0	1	0	1
2.1t All Terrain Forklift	0	1	2	3
2.5t Forklift	1	1	2	4
7/8t Forklift	2	0	0	2

Summary of responses to issues raised in previous annual reviews
- Complete the tender process for solar lights and lanterns, hygiene kits, sleeping mats, cook stoves and toilet systems. Complete, apart from cook stoves and toilet systems which are on hold.
- Continue to explore and research new and innovative equipment to enhance the quality, safety and comfort of items in the Stockpile and deployment kit. Ongoing.
- Continue to test the market and use competition to drive value for money. Ongoing.

Output	DFID’s Stockpile appropriately located and complements the international system’s own stockpile. Implementation of agreed recommendations to support, improve and replace existing international systems.
Output number		2	Output score	A
Risk		Minor	Impact weighting	20%
Risk revised?		Yes	Impact weighting revised?	No

Output Indicator 2.1. That the UK is assured that the location of the items in the stockpile are optimally located to reduce suffering and morbidity, offer value for money and are resilient.

Milestone 2: A comprehensive review of stockpile locations will be undertaken to understand alternative options that exist. Evidence based decision made on the location of Global Stockpiles. Recommendations made and plans in place for any regional stockholding to be established.

A review of the location of the Stockpile was undertaken in 2014/15, and CHASE has taken forward the recommendations from this review to ensure stocks remain stored in strategic locations, that are cost effective and logistically efficient. The locations chosen are based on DFID’s regions of interest, transport and warehouse hubs, proximity to at risk countries, value for money, flexibility and knowledge of our business area. DFID’s Stockpile is split across four sites[6]. Doncaster was added as a key storage location for NFI’s and ACHE to improve the speed at which a response could be mounted from UK airports.
[6] Kemble, East Midlands and Doncaster Airports, India and Dubai (Jebel Ali Free Zone).

In January 2016, CHASE introduced a Warehouse Management System (WMS) at Kemble to ensure international regulations for the storage and shelf life of pharmaceuticals were followed. In the future it is planned that this system will be used for all HEPP stocks, with the system adapted to include other parts of the supply chain and other geographical locations, linking it to the CHASE Procurement System.

Output Indicator 2.2. DFID held relief items linked effectively with DFID air service provider operations and those of other logistics / transport providers to ensure a seamless supply / deployment process.

Milestone 2: Conduct and “Industry Day” for Airlines and Air Brokers where innovative solutions to Air Charter can be discussed and considered. Also engage directly with major airlines to build relationships that can be utilised to access aircraft during a major emergency. Use knowledge gained from Industry Engagement in order to establish a new Air Broker Agreement.

In July 2016, CHASE held an Industry Day for airlines and air brokers to discuss and present ideas about how DFID’s air logistics requirements could be best met. The aim of the day was to ask the industry to present new and innovative solutions that would allow DFID to mount faster, more effective and efficient responses by air. The findings from the Industry Day were used to inform the re-tendering of a new Air Broker Agreement. The new contract was designed to meet DFID’s needs to be able to quickly and reliably deliver relief stocks. The new contract came into operation in February 2016, and includes agreements with seven providers chosen on basis of specific skills, aircraft capabilities and geographical coverage. The agreement includes some airlines that allow DFID to contract services directly through them, rather than having to go through brokers, saving time and cost.

Output Indicator 2.3. Support the development of a system that ensures all members of the international community can quickly identify and access NFIs and deployment equipment held by individual organisations in the community.

Milestone 2: Conduct a review and provide recommendations to support/improve/replace existing international systems, using DFID influence to promote better compliance/practice direct bilateral support for systems development, personnel secondments. Implementation of agreed recommendations with key stakeholders to develop and improve systems.

The CHASE review of the NFI’s held by the international community highlighted a number of challenges that hampers the effective and accurate mapping of the global stockpile. These include:
- a lack of global buy in, meaning not all partners’ stock is mapped;
- no common standard for the specification of items;
- a lack of up-to-date real time information, making it difficult to determine accurate stock levels; and
- no real system to enable inter-agency access and use of different stockpiles.

CHASE has been working with OCHA and the Logistics Cluster to try and make progress with the following.
- Emergency and Supply and Prepositioning (ESUPS – participation in this Working Group aims to address the issue of inefficiency in global stockpiles of emergency supplies. CHASE is actively engaged and part of the ESUPS Steering Group.
- OCHA Pre-positioning Review – involvement in OCHA’s global review of the international system for stockpiling.
- Preparedness Programme – to strengthen participating agencies' capacities to ensure the centrality of protection, accountability to affected populations and to provide timely, appropriate and cost effective humanitarian response.
- Collaboration with USAID – regular meetings between CHASE and USAID to share each other’s approaches to stockpiling and global logistics, and develop closer working relationships.
- Using DFID’s Stockpile to Support Partners – opening up DFID’s Stockpile to RRF partners during an RRF activation, enabling them to access and distribute better quality items, quickly and more cheaply. Linked to this, an online website catalogue has been developed of DFID’s NFI’s so partners can see the status of stock.

Summary of responses to issues raised in previous annual reviews
- New improved air brokerage contract agreed that delivers DFID better integrated response capacity, making greater use of scheduled airlines. Complete.
- Complete DFID review and engage to shape and influence OCHA Stockpile Mapping Review, offering UK support and expertise as needed to drive process forward. Ongoing.

Output	Implementation of agreed recommendations on standards and dissemination and compliance
Output number		3	Output score	A
Risk		Minor	Impact weighting	15%
Risk revised?		Yes	Impact weighting revised?	No

Output Indicator 3.1. Effective system in place to establish and monitor minimum acceptable standards for shelter materials and NFI’s provided in response to emergencies

Milestone 2: Recommendations made on any changes that are required to the funding policies or process to enable the quality and standardisation to be improved.

The range of commodities held in the stockpile has been developed from extensive experience and is limited to those items that are proven to have been most urgently and frequently required in disasters and are cost effective to store and transport.

CHASE monitor the quality of NFI’s held in DFID’s Stockpile to ensure items held meet DFID and international organisations’ standards and specification.. From regular coordination with partners and stakeholders DFID ensures its own stock meets and often exceeds these accepted standards and specifications.

CHASE OT undertake detailed lab testing, sampling, batch inspection and in-country monitoring to ensure that goods procured are up to standard. All goods are benchmarked against relevant standards and pharmaceuticals must adhere to MHRA licensing requirements. Areas such as health and safety law and Sphere and Euopean and British standard must also be complied wth. Items are also regularly rotated so shelf life is not exceeded.

A routine inspection of Life Saver Cubes revealed some batches had a reduced filtration capability, only providing a protective level of filtration, rather than the desired WHO level of highly protective. Following independent laboratory testing and consultation with partners it was decided to refurbish the Cubes to meet WHO certification of highly protective rather than disposing of them.

An important aspect of the HEPP is to take advantages of new technology and developments that can improve the comfort and living conditions of people. As the costs of solar products have reduced a decision was taken to upgrade 12,500 solar lanterns with new models that have greater solar panel efficiency and longer battery life. The number of solar lights was increased to 20,000. These lights can be easily included in distributions of other NFI’s and help provide protection to vulnerable groups at night such as women and girls.

CHASE commissioned research and testing with a number of suppliers into a number of commodities to determine improvements or to take advantage of new developments and technologies in the sector. This included the fire retardency of plastic sheeting, new transitional tent concepts, new water filtrations devices, and latest in deployment communications.

Summary of responses to issues raised in previous annual reviews
- Continue to research and field test NFI’s for the Stockpile, developing new standards where they don’t exist, sharing the findings with the rest of humanitarian community to drive improvements. Ongoing.
- Explore how new technological advances such as Quick Response (QR) labels and Active Radio Frequency Identification (RFID) tracking might be used to track the performance of NFI’s in the field, with feedback informing continual improvement. On hold.

Output	DFID held stocks support the deployment of DFID staff (and/or those of partners’ specialist teams) into a range of environments for up to three simultaneous deployments.
Output number		4	Output score	B
Risk		Minor	Impact weighting	15%
Risk revised?		Yes	Impact weighting revised?	No

Output Indicator 4.1. DFID has the equipment and resources in place to enable the immediate deployment of up to 20 people to a range of environments and which can be scaled up in line with changing UK response capability. Instigate on-going review and testing of innovations and emerging technology in deployment platform holdings to ensure they are properly assessed and, where appropriate, brought into standard stock holdings – and referred to relevant actors in the international humanitarian community and UKTI as appropriate.

Milestone 2: Work with DFID IT to ensure that all new deployment hardware is fully integrated with the DFID IT systems to ensure a seamless system that allows staff to work in the DFID Field Office when deployed with full DFID IT functionality.

CHASE worked with DFID’s IT department to ensure the deployment platform is taking advantage of the latest developments in IT and communications equipment when located in the field managing an emergency response. This included:
- Very Small Aperture Terminal (VSAT) – recommending the procurement of new Ka Band VSAT Technologies, that are not only more compact than DFID’s current model, but are also quicker and easier to set-up, and have greater bandwidth making them ideal for use by field teams in the early days of a response.
- ECHO (global network for voice and data services) Phones – working with Vodaphone and DFID IT to integrate the VSAT with DFID’s ECHO telephone network so DFID staff mobile phones can be used while connected to the VSAT, dialling normal DFID extension numbers, and making calls made at lower cost.
- ISAT Hub – (a satellite Wi-Fi device) working with Inmarsat to encourage firmware and software upgrades to the ISAT Hub to enable it to work at higher levels of encryption, making it compatible with DFID laptops.
- Deployment Equipment – identification of new items to be added to the personal deployment kit given to staff operating in the field. A Framework Agreement was established for the production of DFID polo shirts given to staff working emergency response situations.
- Packaging Materials – undertaken research into new lighter cardboard pallets that allow the amount of cargo loaded on to air charters to be maximised and minimising the amount of packaging.

It is important following Triplex 2016 (a civilian-run multilateral humanitarian response field emergency simulation), for this module to be improved, with areas for development rectified to ensure a field team can operate in all forms of weather conditions. Further improvements to kit, particularly IT and communications are needed.

## D: Value for money and financial performance

Key cost drivers and performance
The principle cost drivers for the programme are the costs of the additional items added to the Stockpile associated with the uplift and the costs of storage, warehousing and maintenance. Where new or increased quantities of NFI’s have been required open competitions have been run to test the market and ensure value for money is obtained. CHASE has undertaken these competitions at no additional cost to DFID[7]. The cost of warehousing in Dubai varies depending on the amount of goods stored. This means following a sizeable response savings can be achieved when stock levels are low. Options are also being explored, and taken, to store goods with manufacturers/suppliers, thereby minimising storage costs[8].
[7] Costs being met from the Humanitarian Emergency Operations Support Services contract.
[8] High Thermal Synthetic Blankets now stored at the Supplier’s premises in New Delhi.

Value for money assessment
CHASE has worked to optimise value for money for NFI’s procured through HEPP, either through the use of Framework Agreements or competitive procurement. A selection of some the savings achieved are listed below:
- 40% discount from Go Outdoors for 5,000 sleeping mats - saving £60,000
- VAT and duty free import of 32,000 blankets - saving £27,000
- Maximise airfreight load of tents and blankets - saving £30,000
- EU rebate on RAF humanitarian flights - saving £55,000
- Recertification of 25 sets of body amour rather than buying new - saving £22,000
- Splitting hygiene kit award to multiple bidders - saving £58,000
- Reduction in cost against Framework Agreement price for kitchen sets - saving £156,000
- Reduction in cost against Framework Agreement for replenishment of four armored vehicles for Nigeria - saving £119,000
- Donation of 170 tents from Ebola Response to Ukrainian Government - saving £154,360

Assessment of whether the programme continues to represent value for money
The programme’s continues to represent value for money but a further assessment will need to be conducted within the next six months as the successor programme to the HEPP is designed. It must be recognised that holding a large stockpile is not cheap, with significant monthly costs associated with warehousing, maintenance and storage, plus the need to refresh stock to ensure it is not held beyond its expiry date. Following the award of the new Operation’s Team Contract, which parts of this programme will be subsumed into in the future, a more cost-effective approach to stockpiling may be identified.

Quality of financial management
The team meets on a regular basis to discuss the performance of HEPP, including expenditure. Total programme expenditure to date is approximately £10m. Monthly expenditure and forecast reports are produced and these form the basis of DFID’s forecasting. These reports do however need some refinement to meet DFID’s needs, which will be actioned after this Annual Review. The monthly meetings provide an opportunity to discuss any changes to the previous months’ forecast and agree options for reallocating funds if savings or overspends have been identified.

E: Risk

Overall risk rating: Minor. HEPP builds on a series of previous programmes (Stockpile programmes 1–5), and Crown Agents Procurement and Logistics Team are very experienced in delivering humanitarian supplies in emergency situations. Improving the quality of procurement in the overall humanitarian system should become a focus for activity and influencing as DFID’s own internal stockpile uplift is finalised.

F: Commercial considerations

Delivery against planned timeframe
The increase in the size of the Stockpile to meet the shelter needs of 75,000 people triggered an extension to the programme, which now runs until the end of June 2017. Good progress has been made with the target met for stockholdings of shelter kits, tents, blankets, kitchen sets, buckets, water filters, small solar lights, solar lanterns, hygiene kits and sleeping mats.

Asset monitoring and control
DFID plans to undertake a check of the assets held in the Stockpile in early 2017.

G: Conditionality

Not applicable.

H: Monitoring and evaluation

Monitoring progress throughout the review period
The team meets on a regular basis (at least monthly) to discuss the performance of HEPP. These meetings provide an opportunity to run through all current issues related the Stockpile. The meetings also provide an opportunity for authorisation to purchase new or innovative equipment to be provided, and test out new approaches. Goods held in the Stockpile are inspected and monitored to ensure they remain fit for purpose and that expiry dates are not exceeded. DFID is able to mark its NFI’s allowing them to be tracked and monitored in the field, assisting in feedback to manufacturers and learning lessons. A recent recommendation, is that CHASE staff should routinely join all monitoring missions when large quantities of NFI’s have been accessed from the Stockpile (or a new item or approach has been used for the first time) to assess performance in the field and obtain feedback from beneficiaries.

Annex A
Items held in the Stockpile at April 2016.
Item	Target Stock	Stock April 2016	Status
Shelter Kits	35,000	40,000	Target Met
Tents	7,500	7,300	Target Met
Blankets	75,000	75,000	Target Met
Kitchen Sets	15,000	15,000	Target Met
Buckets	40,000	40,000	Target Met
Water Filters	15,000	14,500	Target Met
Small Solar Lights	15,000	15,000	Target Met
Solar Lanterns	12,500	12,500	Target Met
Hygiene Kits	15,000	15,000	Target Met
Sleeping Mats	30,560	30,560	Target Met
Cook stoves	0	0	On hold
Toilet System	0	0	On hold

Annex B
Current Framework Agreements, with start and end dates.
Name	Start Date	End Date
Humanitarian Relief Blankets	31/5/2014	31/4/2017
Humanitarian Relief Tents	31/5/2014	31/3/2017
Humanitarian Relief Shelter Kits	31/5/2014	31/3/2017
Armoured vehicles	8/12/2014	7/12/2016
ACHE for Airports	20/11/2014	19/11/2016
Hygiene Kits	16/3/2015	15/3/2017
Solar Kits	16/3/2015	15/3/2017
Sleeping mats	16/3/2015	15/3/2017
Buckets and kitchen sets	26/7/2013	31/3/2017
Aviation services	18/2/2016	18/2/2018
Clothing	20/6/2015	25/6/2017