## IMMANA logframe_V2SK
Title: Innovative Metrics and Methods for Agriculture and Nutrition Actions
| Indicators | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Milestone 6 | Target | Assumptions and Risk Assessment
|  |  | August 2014- March 2015 | April 2015- March 2016 | April 2016- March 2017 | April 2017- March 2018 | April 2018- March 2019 | April 2019- August 2019
Impact
To create a step change in the generation of high quality and coherent scientific evidence base linking agriculture, nutrition and health which will underpin effective policy and investments | Agriculture policies and programmes use high quality evidence for their decision-making | Mapping and scoping reviews undertaken by DFID, LCIRAH and other literature |  |  |  |  | Updated mapping and scoping review of use of evidence, including IMMANA methods & metrics, in academic, policy and programme literature |  | At least 8 major international and national policies and programmes have drawn on robust evidence, including the methods and metrics developed by IMMANA | Continued interest by policy and programme decision-makers in evidence-based actions
Source: Literature reviews and project/policy documents; mid-term and endline evaluations
Outcome
A strong portfolio of innovative methods and metrics to strengthen the evidence base on agriculture-nutrition research widely available to researchers and practitioners | 1. New methods/approaches and metrics in agriculture-nutrition research developed and made available to researchers and practitioners |  |  |  | 6 publications submitted to peer-reviewed journals | 14 publications submitted to peer-reviewed journals | 14 publications submitted to peer-reviewed journals | 6 publications submitted to peer-reviewed journals | 40 publications submitted to and published by peer-reviewed journals (assumption: will be published in time to report on); A pool of researchers trained/engaged. | A strong interest by researchers with high scientific capability in interdisciplinary research on agriculture-nutrition linkages, who would apply for competitive research grants and early career fellowships.
Source :Documentation on Grants and Fellowship awards; deliverables from Grants and Fellowships
| 2. The Agriculture, Nutrition and Health Academy accelerates sharing and learning relevant to methods and metrics in agriculture-nutrition research | Stakeholder consultations in Africa and South Asia to assess demand for the platform and mechanisms for engagement |  |  |  | 50 % of IMMANA stakeholders report IMMANA as a key contributor to improved methods and metrics in agriculture-nutrition research |  | 50 % of IMMANA stakeholders report IMMANA as a key contributor to improved methods and metrics in agriculture-nutrition research | 50 % of IMMANA stakeholders report IMMANA as a key contributor to improved methods and metrics in agriculture-nutrition research | Academy members, especially the current research programmes and consortia, are willing to engage with the Academy and the other mechanisms established to learn and share.
Source: Anual monitoring report of collaborations reported by stakeholders; Mid-term and endline evaluation report
Outputs
Output 1
Competitive research grants develop new methods/approaches and metrics | 1. Competitive research grants awarded and implemented to develop new methods and metrics |  | Call for research grants and fellowships disseminated | 8 research grants awarded | 8 research grants awarded | 5 research grants complete development of methods and metrics | 11 research grants complete development of methods and metrics |  | 16 research grants develop methods and metrics | The Grantees are able to conduct their proposed research successfully and in a timely manner Risk Assessment: Low - it is anticipated that 100% of the grantees will be able to deliver quality & timely research and 80% would be able to deliver on the innovative component.
Source: Documentation on Grants awards; Grant project reports
Impact weighting output 1: | 60%
Output 2
Research fellowships develop or adapt new methods/approaches and metrics | 1. Early Career researchers awarded fellowships and mentoring to develop or adapt new methods and metrics |  | Processes to award grants and fellowships established | 6 fellowships awarded | 6 fellowships awarded. 6 fellowships on methods and metrics completed | 5 fellowships awarded. 6 fellowships on methods and metrics completed | 5 fellowships awarded. 6 fellowships on methods and metrics completed | 6 fellowships on methods and metrics completed | 22 fellowships adapt or develop methods and metrics | The fellows are able to conduct their proposed research successfully and the host and the home mentors invest their time in the mentoring process Risk Assessment: Low/Medium - The potential risk of selected IMMANA Fellows not furnishing their deliverables remains very low. The risk of Home and Host Mentors providing poor mentorship, which would affect the standards of the research delivered, exists but remains low, as Mentors were also reviewed as part of the IMMANA Fellowship selection process. It is therefore anticipated that 100% of the fellows will be able to deliver their outputs. However, it is anticipated 75% of the fellows would effectively develop their scientific capability and deliver high-quality research by the end of their fellowship.
Source: Documentation on Fellowship awards; Fellowship reports
Impact weighting output 2: | 25%
Output 3
Platforms and mechanisms are in place to facilitate sharing of methods and metrics | 1. The Agriculture, Nutrition and Health Academy is established |  | 5 planning meetings and 5 stakeholder presentations convened | 4 regional stakeholder consultations and one online (global) consultation convened; Academy launched; meeting of major agriculture, health and nutrition initiatives convened | Academy membership grows by 10% | Academy membership grows by 10% | Academy membership grows by 10% |  | 250 institutions are members of the Academy | The research community is willing to volunteer their time to deliver webinars, offer trainings and participate in working groups. Risk Assessment: Low/Medium - the risk on the successful establishment and operations of the network is very low as it is led internally by IMMANA funded staff. However, the extent and quality of the content shared as part of the network is member-dependant and could therefore be rated as medium risk. Lastly, the effectiveness of the working groups are dependant on time and technical contributions from experts who contribute to IMMANA on a voluntary basis on top of their high-level commitments, and therefore present a level of risk rated as medium.
Source: Documentation on the Academy; Annual programme reports
| 2. Mechanisms established to facilitate learning and sharing of methods and metrics amongst the global community engaged in agriculture-nutrition research |  | IMMANA webpages and Twitter presence established; draft Academy concept developed | 3 webinars; microsite and online knowledge management portal launched; 3 working groups convened; | 4 webinars; one Academy conference convened; one Learning Lab at Academy conference; one policy working group and 2 technical working groups convened; one policy brief and 2 technical briefs released | 4 webinars; one Academy conference convened; one Learning Lab at the Academy conference; one policy working group and 2 technical working groups convened; one policy brief and 2 technical briefs released | 4 webinars; one Academy conference convened; one Learning Lab at the Academy conference; one policy working group and 2 technical working groups convened; one policy brief and 2 technical briefs released | 4 webinars; one Academy conference convened; one Learning Lab at the Academy conference; one policy working group and 2 technical working groups convened; one policy brief and 2 technical briefs released | 4 Academy conferences held; At least 18 webinars provided to research community; at least 4 learning labs convened at the annual Academy conference; At least 8 technical briefs disseminated; At least 4 policy briefs produced and disseminated
Source: Documentation on the Academy; Annual programme reports
Impact weighting output 3: | 15%