Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Palestinian Market Development Programme to Strengthen the Private Sector in the Occupied Palestinian Territories (OPTs)
Programme Value: £20.8 million (UK £15m, EU £5.8m)		Review Date: 31/03/2017
Programme Code: 201828	Start Date: 21/10/2013	End Date: 31/11/2019

Summary of Programme Performance
Year	2013	2014	2015	2016
Programme Score	C	A++	A++	A
Risk Rating	Medium	Medium/High	Major	Major

Summary of progress and lessons learnt since last review
During the reporting period (January-December 2016), PMDP met its yearly targets overall and scored A. The below table summarises the 2016 Annual Review scoring.

	Output	Impact weight %	Score
1	Improved private sector skills and innovation	65%	A+
2	Market system failures addressed in specific sectors	15%	A
3	Strengthened trade and investment linkages with international markets	20%	B
	Overall output score		A

Key findings of the review:
1. Business environment remains challenging: Instability persists as a result of continued deadlock in the peace process. Consequently, economic growth remains static and key economic indicators, such as unemployment, worsened during the year. PMDP remains flexible in its approach to addressing overarching economic impediments.
2. Shift in approach focusing on job creation for women and youth initiated: The programme responded to the high unemployment rates by initiating a shift in approach to focus on job creation for women and youth. The programme also initiated changes to its grants windows and beneficiary selection processes.
3. Job creation results substantially overachieved expectations: Jobs targets for the year were exceeded by 600 mainly due to the overachievement of the Gaza Back to Business (B2B) component which recreated an estimated 810 jobs that were lost as a result of the 2014 conflict. Consequently, cumulative job results have become very close to end-of-programme targets and hence end-of-programme targets will need to be readjusted. B2B remained weak in terms of creating jobs for women as the majority of jobs created were in traditionally male dominant sectors, such as industry and construction, where most jobs were lost.
4. Support to marginalised areas remained weak: The programme struggled to reach potential beneficiaries in marginalised areas including Area C[1], Seam Zone[2], Jordan Valley and East Jerusalem due to the small size of companies, companies’ unofficial registration status, and their need for support in capital and hardware as opposed to technical assistance. The introduction of a dedicated sub-window for marginalised areas in 2017 is anticipated to enhance outreach and tend to the needs of companies operating in marginalised areas.
  [1] Area C refers to West Bank territory administered by Israel. It includes the Jordan Valley and consists of 60% of the West Bank.
  [2] Seam Zone refers to areas in the West Bank located east of the Green line and west of Israel’s separation barrier.
5. Investments facilitated in a number of key sectors: With support from PMDP, the Palestinian Investment and Promotion Agency (PIPA) facilitated 14 new investments worth £7.4 million in tourism, health, agriculture and industry creating 347 direct jobs.
6. Commercial Trade Representatives (CTRs) component launched: The first CTR was placed in the Palestinian diplomatic mission in London in November and recruitment for remaining selected countries has been finalised with most CTRs expected to be placed by May/June 2017.
7. Good value for money continued: The programme continued to present good Value for Money (VFM) with most VFM indicators improving compared with 2014 and 2015.
8. PMDP has effective safeguard measures in place: PMDP has robust safeguards against the risk of fraud and diversion of funds to illicit organisations. It also has stringent vetting, procurement, contracting procedures in place and includes regular third-party monitoring and evaluation by an independent party.
Progress against previous recommendations
Recommendation	Progress
Adjust PMDP to include specific components focusing on women and youth employment	During 2016, PMDP carried out a major review exercise to examine its current portfolio and the appropriateness of its various grant funds, resulting in a new approach on processing applications more efficiently as well as a new Women and Youth Employment (WAYE) initiative targeting specific constraints facing women and youth owned enterprises and stimulate employment. This shift included changing the definition of women owned and managed businesses to ensure that women play an active rather than passive role within their organisations. It also led to increasing targets for women and youth employment. For example, women and youth are now expected to fill 35% and 50% of end-of-programme job targets, respectively. In addition, out of the total number of assisted firms, 35% will be women owned /managed businesses (an increase from 20%). There has also been a review of the programme’s gender strategy. The new direction was rolled out in the first month of 2017.
Establish a robust methodology to assess and capture indirect jobs created by the programme	PMDP has contracted Steward Redqueen (SRQ), a specialised consultancy that advises on impact and sustainability, to develop a methodology for measuring magnitude and quality of indirect job creation through programme implementation. SRQ is presently in the process of conducting its assessment.
Strengthen analysis dissemination and coordination with other donors	This year saw good analysis dissemination and donor coordination from the programme. Examples of this are stated below: / Analysis and dissemination: Example of this includes PMDP’s work with Mercy Corps and AWEF to produce a study on ‘Online Freelancing for Women in OPTs’, / Coordination: Example of this includes PMDP’s participation in the Food Security Cluster and coordination with JICA on strategic interventions in Gaza.

Summary of recommendations for the next year
General recommendations:
PMDP and DFID will increase end-of-programme direct job targets from 2450 to 3020 jobs and amend the milestone accordingly by May 2017.
- PMDP will fill vacant programme positions in Ramallah and Gaza, particularly in the area of Monitoring and Evaluation by July 2017.
- PMDP to develop a methodology to assess the quality of jobs created through the programme.
- PMDP to improve ways of tracking and analysing the impact of interventions.
- PMDP to develop VFM effectiveness indicators for outputs 2 and 3.

Output specific recommendations:
Output 1:
1. PMDP to increase its outreach in marginalised areas and establish realistic targets in 2017.
2. PMDP to monitor the effectiveness of new grants windows in creating jobs for women and youth in 2017.

Output 2:
1. PMDP to develop facilitation strategies for the furniture and services sectors by September 2017.
2. PMDP to devise and initiate interventions for tourism, furniture and services sector in 2017 based on the study recommendations, while ensuring interventions are spread out more evenly throughout the year.
Output 3:
1. PMDP to finalise placements of remaining CTRs and assess performance level, impact, and VfM.
2. On quarterly basis, PMDP and DFID to continue to monitor PIPA’s political will to embrace necessary change to implement its objectives.
3. PMDP will continue to engage with other public and private institutions with the aim of improving investment and trade.
4. PMDP to launch a branding initiative in line with National Export Strategy (NES) and Palestinian Export Council (PEC) objectives.
5. PMDP to help PIPA to effectively engage with other national organisations in the area of branding, Business Enabling Environment (BEE) and diaspora engagement in 2017

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3598717.doc
DevTracker Link to Log frame:	Need to add updated logframe to DevTracker

Programme outline
What need are we trying to address? The Palestinian economy continues to suffer from low growth and high unemployment as a result of ongoing political instability due to protracted conflict. Restrictions on movement and acess across the OPTs, both for goods and people, continue to be a major stumbling block in unlocking the full potential of the Palestinian economy.
In 2016, growth was 4% (3% in West Bank and 7.5% in Gaza according to the IMF) and was mainly driven by private consumption and reconstruction. The IMF assesses that the Palestinian economy needs to grow at an annual rate of 7-8% in order to trigger meaningful economic growth and recovery. Investment in the OPTs remained low as international businesses continue to deem the Palestinian business environment as high-risk, unsteady, and unreliable.

Unemployment rates remained critically high rising to 28% in 2016. In Gaza, unemployment exceeded 40% where around two-thirds of young people were jobless. Unemployment among women in the OPTs reached 44.7%. With the Palestinian economy unable to create sufficient job opportunities, labour force participation stood at a meagre 45.7%. In the medium term, growth is expected to persist at 3-3.5%. Should a political resolution to the conflict be found, evidence suggests that the economy would grow at the required levels. In the meantime, there is a need to develop a dynamic, productive and competitive private sector to enhance growth and job creation prospects.

What are we doing to address the problem? By October 2019, the UK will have provided up to £15 million for the Palestinian Market Development Programme (PMDP) to strengthen the competitiveness of the private sector in the OPTs and create jobs. The EU is co-funding the programme with £5.8 million, through a delegated agreement with DFID, bringing the total programme budget to £20.8 million.

PMDP has three main components: 1) Provision of matching grants and technical assistance to Palestinian businesses to mitigate risks associated with doing business in a fragile context; 2) Carrying out market analysis to identify and address market failures in key economic sectors; 3) Strengthen inward investment and commercial linkages with Diaspora Palestinians and enhance know-how of Palestinian institutions in the area of trade and investment. All three components are in line with commitments outlined through our Operational Plan to increase long-term growth and employment by addressing government and market failures.

PMDP met its objectives for the year. In 2016, DFID urged PMDP to review its approach to focus more on creating jobs for women and youth to address high unemployment rates. This has been reflected in the future targets of the programme.

Expected results following PMDP’s review:
By 2019, PMDP is expected to:
- Assist 810 Palestinian firms (35% managed or owned by women) through matching grants and technical assistance to develop 300 new/existing products and enter 321 new markets;
- Create over 3,020 direct jobs and 3,020 indirect jobs[3] (6,040[4] overall)
  [3] Indirect jobs relate to jobs that have been created not directly as a result of a PMDP intervention but rather as a result of economic growth resulting from a PMDP intervention. Based on our evaluation supplier’s assessment, for every one direct job created under PMDP, an indirect job is created resulting in a ratio of 1:1.
  [4] The target of 6,040 direct and indirect jobs is a result of this review’s findings/recommendations. It will be confirmed with PMDP in due course.
- Leverage a minimum of £155m in additional attributable sales (£100m through TA and £55m through B2B)
- Assist 120 companies to increase exports;
- Enable 120 companies to start using their own funds to develop and sustain their businesses;
- Assist 380 companies in improving their annual business performance;
- Assist 256 companies who experienced damage due to the 2014 conflict in Gaza to get back to business (B2B);

Who implements support we provide? Development Alternatives Incorporated Europe (DAI Europe) implements the programme. Galway Development Services International (GDSI) is the evaluation supplier. DFID uses Reuter Thompson’s World Check to carry out online vetting of beneficiaries against international terrorism and sanctions lists and checks the system’s effectiveness routinely. The Programme Steering Committee consists of DFID, the EU and the Palestinian Ministry of National Economy (MoNE).

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)
Annual outcome assessment
The programme’s objective as outlined in the outcome statement is to ‘improve competitiveness of the Palestinian private sector’. The table below summarises progress in this regard covering the period January-December 2016. To date PMDP has assisted 585 companies, created 2,450 direct jobs (substantially exceeding this year’s cumulative target of 1,850), and contributed £74 million in additional sales attributable to the programme. The programme is on track to reach its 2019 programme objectives.

DFID funding is 72% of the overall budget so when quoting 'DFID attributable’ the 72% should be applied to the figures below.
Outcome indicator	2016 Cumulative Planned	2016 Cumulative Achieved	2019 / Cumulative / Planned	Description and percentage attained to date
Number of enterprises reporting improved annual performance[5]	230	198	380	Moderately did not meet expectations and underachieved by 32 enterprises. This may be attributed to limited economic growth in the OPTs, lag in impact, and overambitious target for 2016. Out of the 198 firms, 23% were women owned or managed (46). PMDP on track to achieve 2019 targets, which include ensuring that 35% of all supported enterprises (133) are women owned/ managed. Percentage attained to date: 52%
Number of enterprises reporting increased exports or first-time exports	75	90	120	Moderately exceeded expectations with an additional 15 enterprises for 2016. Percentage attained: 75%
Number of net jobs created	1,850 / TA: 550 / B2B: 1,300	2,450 / TA: 833 / B2B: 1,617	2,750 / TA: 1,150 / B2B: 1,300	Substantially exceeded expectations by 600 jobs for 2016. Jobs were derived from: / Technical Assistance: 833 (including 386 youth, 248 women). / Gaza Back to Business (B2B): 1,617 (including 44 women). The B2B component was devised to address post-conflict recovery in Gaza and has mainly focused on sectors that are traditionally male-dominant such as construction, furniture, metal and other industries. Percentage attained: 89% due mainly to effective job creation under B2B. Due to the high attainment rate, targets will be revised upwards.
Value of additional sales attributable to PMDP (£m)	60 / TA: 30 / B2B: 30	74 / TA: 33 / B2B: 41	155 / TA: 100 / B2B: 55	Substantially exceeded expectations by £14 million overall. Percentage attained: 47%
Number of new domestic and international markets entered	255 / TA: 180 / B2B: 75	368 / TA: 228 / B2B: 140	396 / TA: 321 / B2B: 75	Substantially exceeded expectations by 113 markets. Percentage attained 93%. Due to the high attainment rate, targets will be revised upwards.
Number of foreign and domestic markets entered by women owned/managed firms	60	66	112	Moderately exceeded expectations by 6 markets. Percentage attained 59%. On track to meet 2019 targets.
Number of improved products and services developed	400 / TA: 200 / B2B: 200	479 / TA: 343 / B2B: 136	500 / TA: 300 / B2B: 200	Substantially exceeded expectations by 79 products. Percentage attained 95.8%. B2B is expected to reach 2017 target.
Number of new or improved products developed by women owned/managed firms	60	90	105	Substantially exceeded expectations by 30 products. Percentage attained 86%. Due to the high attainment rate, targets will be revised upwards.
Number of enterprises using own funds to pay for Business Development Services	60	85	120	Substantially exceeded expectations by 35 enterprises. 23 of 85 enterprises were women owned/managed. Percentage attained 71%. On track to reach 2019 targets.
Percentage of initiated programme interventions accepted and implemented by targeted groups	50%	74%	50% per year (2017-2019)	This indicator under Output 2 is meant to measure the percentage of PMDP-devised interventions adopted and implemented by partners to address key market failures. Set targets are yearly. The 74% adoption rate indicates wide-ranging beneficiary buy-in of PMDP analysis and interventions. Annex of interventions available at end of programme.
Extent of improvement in PIPA’s capacity	3	3	4	Measurement is based on a scale where 1 indicates ‘very low’ on a performance scale and 5 indicates ‘very high’. The 3 score indicates ‘moderate’ improvement in PIPA’s capacity. PIPA’s progress is measured against a checklist of predefined milestones in three areas: 1) Proactivity; 2) Business Environment; 3) Increased Investments. See Annex X.
Number of investments facilitated by PIPA	15	14	TBD	Moderately did not meet expectations by 1 investment. End of programme targets will be determined through discussions with PMDP team. PIPA organised several roadshows across the OPTs to promote its services and encourage Palestinian companies to apply for incentives. / PIPA’s investment portfolio includes 14 projects in tourism, health, agriculture and industry with a total value of £7.36 million. In 2016, 347 jobs were created by these projects. The largest concentration of investment was located in Hebron (7 projects, £3.745 million, 167 jobs) followed by Jericho and Jordan Valley (2 projects, £857,762, 46 jobs); Bethlehem (2 projects, £1.17 million, 60 jobs), and Ramallah and Bireh (3 projects, £1.54 million, 74 jobs).
Performance level of CTRs	2	2	4	Measurement is based on a scale whereby 1 indicates ‘very low’ on a performance scale and 5 indicates ‘very high’. The 2 score indicates ‘low’ performance levels. This is primarily the result of a delay in employing CTRs, with the first CTR only beginning work in November 2016 allowing insufficient time to assess performance.
Number of initiatives designed and launched by partner organisations (to attract Palestinian diaspora)	7	9	13	Moderately exceeded expectations by 2 initiatives in 2016. These relate to initiatives designed and launched by partner organisations such as the Palestinian Trade Centre (PalTrade) and the Palestinian Information Technology Association (PITA) to attract investment
[5] 'Improved performance' includes increased sales, reduced costs, increased income, entry to new markets, introduction of new products, and improvement of existing products due to PMDP intervention.

Summary of Progress
Overall output score and description
	Output	Impact weight %	Score
1	Improved private sector skills and innovation	65%	A+
2	Market system failures addressed in specific sectors	15%	A
3	Strengthened trade and investment linkages with international markets	20%	B
	Overall output score		A

PMDP remains one of the largest and most effective private sector development programmes in the OPTs. PMDP marked strong performance under Output 1, which moderately exceeded its targets. Output 2 and Output 3 met and moderately did not meet their targets, respectively. Overall, the programme met its targets for the year.

The programme also underwent a major review which culminated in commitment to increase focus on job creation for women and youth starting in 2017. PMDP introduced a more robust definition of women owned/managed firms and increased the end of programme target of women-owned/managed enterprises to represent 35% of all enterprises assisted (original target was 20%). The programme will also introduce new grants windows and change the way it processes applications to become more efficient and cover more ground. PMDP will monitor the effectiveness of the new shift in approach, especially in awarding grants and increasing job targets with a particular focus on the Women and Youth Employment (WAYE) and Marginalised Areas grant components.

The programme continues to deliver good Value for Money with key VFM indicators, including the cost of creating a Full Time Employment (FTE) job, improving compared with last year. Effective VFM indicators will be developed for Output 2 and Output 3. The programme will also be developing and implementing robust methodologies to measure indirect jobs to better reflect PMDP’s economic impact. Safeguards employed by the programme for vetting, anti-fraud, anti-corruption, contracting, and procurement were found to be effective and are regularly and independently assessed by the evaluation supplier.

Programme visibility, outreach and communications were limited due to DFID’s programme examination which is yet to conclude.

Key actions
Key actions are listed in the summary section above.

Has the logframe been updated since the last review?
Yes, the following additions were made to the logframe:
- New outcome and output indicators for Output 3 were added after last year’s EU scale up
- New target and milestones for direct jobs created were introduced. This included targets and milestones for women and youth – 35% and 50% of all jobs created by end of programme should be allocated to women and youth, respectively.
- Indicator 1.1: number of firms assisted has been increased to 810 from 710 by the end of the programme. This was also reflected by increasing yearly milestones.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved private sector skills and innovation
Output number per LF		1	Output Score	A+
Risk:		Major	Impact weighting (%):	65%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

DFID funding is 72% of the overall budget so when quoting 'DFID attributable’ the 72% should be applied to the figures below.

Indicator(s)	2016 Milestones	Progress
1.1 Total number of enterprises assisted	570 / TA: 314 / B2B: 256	585 / TA: 329 / B2B: 256
1.2 Number of women owned or managed enterprises assisted	80 / TA: 80 / B2B: No Target	84 / TA: 84 / B2B: No Target

Key Points
  1. This programme output moderately exceeded its cumulative target for the year assisting a total of 585 companies including 256 companies in Gaza which continued their recovery from the 2014 conflict. The moderate exceeding of targets was still possible even after an increase of the milestones on this indicator from 480 to 570 last year. Companies receiving support through the TA window created 528 jobs and added £14.8 million in additional sales bringing the cumulative total under TA to 833 jobs and £33 million in additional sales. Companies in Gaza receiving support through the B2B window created 810 jobs and added £26.3 million in additional sales bringing the cumulative total under B2B to 1,617 job and £41 million in additional sales. Programme support under this output in 2016 included:

Receiving 228 new TA applications (187 in the West Bank and 41 in Gaza) bringing the cumulative total to 672. Out of the received applications, 77.2% came from the services, manufacturing, ICT, and food industries. Companies based in the Middle West Bank region were the highest applicants representing 38% of all applications.

Example of success story in 2016
Two PMDP beneficiaries, Hawash Sons Case Stone and Palestine Organisation for Safes, attained ISO 9001:2008 certifications focused on meeting customer expectations and delivering customer satisfaction. ISO certifications helped both companies expand their client base and penetrate new markets.

The Gaza B2B component has now closed with assistance continuing through TA and other new grants windows which will start in 2017. In 2016, PMDP struggled to reach potential beneficiaries in marginalised areas including Area C, Seam Zone, Jordan Valley, and East Jerusalem with only one grantee in East Jerusalem receiving support during the year. The main reason for this was the limited number of prospective clients in Area C with the size of most companies being very small and they were typically unregistered officially. In addition, the needs of companies in marginalised areas were mainly focused on support in areas of infrastructure, building, equipment and machinery, which were outside PMDP’s mandate. PMDP will aim to address this shortcoming through the newly developed grants window for marginalised areas in 2017. The grants window will be flexible enough to respond to specific needs of companies operating in marginalised areas.

  1. The programme assisted 84 women owned/managed companies in 2016 moderately exceeding its target of 80. While the 80 target may be viewed as a reduction from the original target, this is due to the change in the way the programme defines women-owned[6] and women-managed[7] companies. This represented 14% of all enterprises assisted in 2016 and is expected to be 35% by end of programme. The programme will be deploying a new Women and Youth Employment (WAYE) sub-component in 2017 which aims to assist women and youth owned enterprises tackle specific business constraints.
    [6] New definition with additions bolded: A woman-owned business is a legally registered business concern in which a woman is listed among the owners and is also active in the day-to-day operation of the business.
    [7] New definition with additions bolded: A woman-managed enterprise is a legally registered business concern in which a woman has a managerial/supervisory role and day-to-day decision-making responsibilities with regard to its finances and/or operations.
Summary of responses to issues raised in previous annual reviews (where relevant)
Increase coverage in Area C: PMDP launched a comprehensive assessment of Area C businesses in cooperation with the Federation of Palestinian Chambers of Commerce, Industry and Agriculture (FPCCIA). The aim of the assessment was to get a better understanding of the number of companies operating in Area C and where their needs lied. PMDP has developed a dedicated grants window for marginalised areas which is expected to increase programme coverage and provide support in Area C, Seam Zone, Jordan Valley, Gaza and East Jerusalem.

Increase gender and youth targets and improve grants outreach and effectiveness: PMDP will be launching a shift in approach to generate jobs for women and youth in 2017. Job creation will become an additional outcome level objective for the programme. PMDP also increased gender and youth targets while also launching dedicated grants windows to reach out to women and youth, including a Women and Youth Employment (WAYE) sub component. In addition, PMDP will be shifting its grants approach under Output 1 from a first-in first-served approach to a batches approach which is more focused, more time-sensitive, and with higher-impact opportunities. PMDP will also launch a Results-Based Fund focusing on sectors and investments with greatest potential for creating jobs for women and youth.

Recommendations
- PMDP to increase coverage of marginalised areas in 2017.
- PMDP to monitor effectiveness of the new approach especially under Women and Youth Employment (WAYE) sub-component to reach women and youth enterprises and create more jobs.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Market system failure in specific sectors addressed
Output number per LF		2	Output Score	A
Risk:		Minor	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

DFID funding is 72% of the overall budget so when quoting 'DFID attributable’ the 72% should be applied to the figures below.

Indicator(s)	2016 Milestones	Progress
2.1 Number of market system studies completed	13	14
2.2 Number of interventions based on completed market system studies	13	19

Key Points
2.1 This programme output met its targets for 2016. Four new studies designed to identify and address market failures in key sectors were conducted in 2016 bringing the cumulative total to 14 compared to the milestone of 13. Follow up interventions were subsequently designed to address identified failures with effectiveness to be determined throughout 2017. Below is a table of studies conducted in 2016:
Study	Description
Fruit and Vegetable Seedlings in Gaza	Investigated the causes of underperformance in the seedlings market system in Gaza. The main failure is sub-optimal quality of fruit and vegetable seedlings which reduces on-farm yields
Veterinary Services in the OPTs	Investigated constraints preventing effective veterinary care from reaching small herders in the West Bank and Gaza
Online Freelancing for Women in the OPTs	Carried out in cooperation with Mercy Corps and the Arab Women Enterprise Fund. Identified constraints (including access and agency issues) limiting the expansion of online freelancing amongst women in OPTs and recommended growth strategy
Furniture Sector in the OPTs	Studied this leading export sector to identify growth and employment generation opportunities

PMDP has made considerable effort in 2016 in stepping up from the identification and analysis of market constraints to the development of a strategic framework for remedial actions. Output 2 has produced comprehensive sector facilitation plans for IT, agriculture, and tourism and launched specific interventions in two target sectors. In addition, clearer result chains between market analysis and intervention plans were introduced and a more robust monitoring and reporting framework was created to track results.
2.2 While the 2016 milestone was moderately exceeded with PMDP initiating a total of 9 interventions in 2016 bringing the cumulative total to 19, most interventions were initiated towards the end of the year and are still in the planning stages with implementation expected in Q1/Q2 2017. Six of the interventions were carried out in the IT sector and three were carried out in the agriculture sector. Only two interventions offered concrete progress in 2016. The first was the ICT/Web skills boot camp which trained 20 students between October-December on design verification of software programmes, with 12 becoming full time employees in the IT sector. The second was Josoor (Bridges) programme which rolled out two teams in June and a third in September to study the disconnect between the IT industry and academia in the OPTs with findings being used to design appropriate interventions. There were also delays in initiating planned interventions in the Tourism and Services sectors. The impact of implemented and planned interventions will be clearer during 2017 and will be covered in next year’s annual review.
Summary of responses to issues raised in previous annual reviews (where relevant)
Business Service Providers (BSPs) involved in analysis of market failures: PMDP has engaged local experts and consulting firms in carrying out a number of studies of market failures in key economic sectors. In addition, PMDP plans to conduct a training in market systems analysis for local consulting firm and individual consultants in 2017.
Develop sectoral facilitation plans: During Q1 2016, Output 2 developed sector facilitation plans for IT, agriculture, and tourism sectors which have high economic growth and employment generation potential. These plans have served as a mechanism to synthesise information about target sectors, prioritise systematic constraints and articulate appropriate intervention strategies. Facilitation plans were developed with inputs from Output 1 and Output 3 and in coordination with other donor activities in focal sectors. Plans are reviewed on a quarterly basis to assign priorities, scale up successful efforts and scale back unsuccessful interventions.
Recommendations
- PMDP to develop facilitation strategies for the furniture and services sector in Q2.
- PMDP to continue to share facilitation plans, studies, assessments, and findings with other active donors and programmes.
- In 2017, PMDP to devise and initiate interventions for tourism, furniture and services sector based on the market studies’ recommendations, while ensuring these interventions are spread out more evenly throughout the year.
- PMDP to assess by 2017 the extent of its interventions in unlocking identified market failures.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Strengthened trade and investment linkages with international markets
Output number per LF		3	Output Score	B
Risk:		Major	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	Y

DFID funding is 72% of the overall budget so when quoting 'DFID attributable’ the 72% should be applied to the figures below.

Indicator(s)	2016 Milestones	Progress
3.1 Number of activities completed by PMDP within the framework of support provided to PIPA and key market institutions	20	21
3.2 Number of people trained on trade and investment promotion	10	0
3.3 Number of women trained on trade and investment promotion	2	0
3.4 Number of CTRs placed	2	1
3.5 Number of Diaspora engaging activities conducted	17	18

Key Points
3.1 This programme output moderately met its targets for 2016. A total of six activities were carried out in support of PIPA bringing the total number of activities to 21. Through PMDP interventions, PIPA was able to obtain required approvals from the Palestinian General Personnel Council for organisational restructuring and consequently redeployed its staff to positions in three directorates and departments. Examples of support activities include hiring an Organisational Development Expert to enhance PIPA’s organisational structure, including trimming down the number of departments from 9 to 3, and organising local road shows on the Investment Promotion Law in Jenin, Nablus, Jericho, and Bethlehem. Additionally, PMDP assisted PIPA in offering capacity building opportunities to 20 of its staff and facilitating 14 new investments in the tourism, health, agricultural and industrial sectors creating an estimated 347 new direct jobs.

3.2 and 3.3 The programme has not reported any trainings on trade and investment, including for women, in 2016 and hence has substantially not met its targets in this area. These trainings were meant for Commercial Trade Representatives (CTRs) which were delayed in being hired. The training is planned for early May 2017 when all CTRs are expected to be in place. The training will also be extended to others from ministries and trade institutions.

3.4 The programme launched the CTRs component by placing the first CTR in the UK in November. The programme also finalised contracts for a CTR in Saudi Arabia who is yet to be placed. In addition, the programme identified five additional placements for CTRs for Russia, Kuwait, the Netherlands, Germany and the United States. As a result, the programme has met its targets for the year.

3.5 PMDP also enhanced its engagement activities with Palestinian diaspora during 2016. Examples of engagement activities include a mission to the US which organised 40 one-on-one business meetings and 4 group meetings resulting in 10 business leads currently in PMDP’s pipeline. Other examples include the launch of a Diaspora Conference in Bethlehem and support to Invest Palestine (IP), a youth initiative owned by a private company of consultants in Santiago, Chile. Through PMDP’s support to IP, two memorandums of understanding (MOUs) estimated to be worth £800,000 were signed between a Chilean Palestinian investor and two Palestinian pharmaceutical companies, Beit Jala pharmaceuticals and Pharmacare. The programme has met its target for the year.

Summary of responses to issues raised in previous annual reviews (where relevant)
Following the EU’s €2 million add-on in December 2015, PMDP expanded the mandate of Output 3 in mid-2016 to include work on Business Enabling Environment (BEE) and the National Export Strategy (NES). Over the remainder of the year, PMDP made good progress overseeing the signature of a subcontract with the Palestinian Export Council (PEC) for the implementation of key activities under NES. PMDP also proactively engaged with the World Bank to improve the OPTs ranking in the World Bank’s Doing Business report. As a result of the expansion of Output 3’s mandate, the following indicators were added to the programme logical framework and will now become part of next year’s annual review. Progress on some of those indicators was already made in 2016.

Indicator(s)	2016 Milestones	Progress
3.6 Number of gaps and impediments to trade and investment based on NES, Investor Needs Assessment and Output 2 analysis	5	6
3.7 Number of engagements with relevant stakeholders	1	1
3.8 Capacity building activities for relevant stakeholders	0	1
3.9 Number of laws or bylaws facilitated and TA provided to improve the regulatory environment	1	1
3.11 Creating action plan and activating Doing Business Committees (Yes/No)	Yes	Yes
3.12 Number of TA provided to MoNE and other institutions to tackle issues relating to Doing Business report	0	1
3.13 Number of WAY related gaps and impediments identified	1	2
3.14 Number of engagements with relevant stakeholders on WAY-related issues	0	0
3.15 Number of capacity building activities of relevant stakeholders to address WAY-related issues	0	0
3.16 Agree with PEC on action plan (Yes/No)	Yes	Yes
3.17 Number of policy recommendations for the PEC plan implemented/in process	0	0
3.18 Branding strategy developed	No	-
3.19 Branding pilot implemented	No	-

 Recommendations
- PMDP to finalise placements of remaining CTRs and assess their performance level, impact, and VfM
- On quarterly basis, PMDP and DFID will continue to monitor PIPA’s political will to embrace necessary change to implement its objectives.
- In 2017 PMDP will continue to engage with other public and private institutions with the aim to improve investment and trade
- PMDP to launch a branding initiative in line with NES and PEC objectives by…..
- PMDP to help PIPA to effectively engage with other national organisations in the area of branding, Business Enabling Environment (BEE) and diaspora engagement in 2017
- PMDP, DFID, and the EU to review newly added indicators and ensure they are specific, measurable, agreed upon, realistic and time-related (SMART).
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)
Key cost drivers and performance
The main cost drivers of the programme are staff costs, running expenses, and matching grants. These cost drivers have been identified in the original business case and are not expected to change. In addition to the implementer’s costs, the programme covers evaluation supplier expenses, vetting expenses, and the salary of a DFID B2 Programme Office embedded with the programme.
VfM performance compared to the original VfM proposition in the business case
VFM assessments follow the 3Es methodology of checking the economy, efficiency and effectiveness of programme implementation with the programme performing well across the various VFM indicators. The following analysis and finding is based on the independent monitoring supplier’s annual assessment.
Economy: Based on the values against economy indicators, the programme is performing well. PMDP has strict bidding procedures in place for purchasing quality inputs at the right price. Inputs procured have a direct link to programme outputs. PMDP staff are involved in assessing quality of deliverables provided by Business Support Providers (BSPs).
The share of management staff of total staff cost was 33% in 2016 (48% in 2014; 41% in 2015)

Efficiency: PMDP is making efficient use of its resources overall, maintaining high standards of programme management in a difficult operating environment. The programme has trusted systems in place for financial management, tracking of grants, procurement and tracking of implementation. The ratios of administrative/management staff costs versus total programme costs and technical staff costs versus total programme costs are good. PMDP is delivering its outputs efficiently and remains on track to achieve end-of-programme targets.
- The share of technical staff of total programme costs was 21% in 2016 (35% in 2014; 17% in 2015)
- The share of management staff of total programme costs was 10% in 2016 (32.6% in 2014; 11.7% in 2015)
Effectiveness: PMDP measures the cost per outputs produced and is providing strong monetary information under Output 1. There is presently no VfM effectiveness assessment data for Output 2 and Output 3 which require further attribution analysis before gaining an understanding of costs and results.
- Cost to create a new Fixed Term Employment (FTE) job was £3,150[8] in 2016 (£6,764 in 2015)
  [8] This was the cost of developing a FTE job in 2016. The cost of developing a FTE job since the start of the programme is estimated at £3,159.
- Cost per new market entered was £22,169.74 in 2016 (£41,899.32 in 2015)
- Cost per existing product improved was £12,594.92 in 2016 (£18,823.40 in 2015)
- Cost per £1 in generated sales was £0.09 in 2016 (£0.10 in 2015)
Recommendation:
- Design and develop VFM effectiveness indicators for outputs 2 and 3.
- Design and develop VFM indicators to measure the quality and sustainability of jobs created.

Assessment of whether the programme continues to represent value for money
Overall, PMDP presents good Value for Money based on data collected against 26 VfM indicators. Values against most indicators have been steady between 2015 and 2016 with significant improvement against all values compared with 2014 data when the programme expended multiple upfront costs for start-up.
Quality of financial management
DAI provides quarterly financial reporting and expenditure forecasts as well as monthly invoices. The total sp
end during the reporting period was £4,622,528 with breakdown presented below:
PMDP finances during reporting period January-December 2016
Item	Spend
Implementation Supplier (DAI Europe)
Fees & Expenses	£1,737,005
Grants	£2,723,842
Evaluation Supplier costs	£92,512
Vetting costs	£22,471
DFID B2 Programme Officer embedded in project site	£46,698
Total	£4,622,528

This brings the total programme spend from the start of the project to £11,011,722

Date of last narrative financial report	31 Jan 2017
Date of last audited annual statement	30 Sept 2016
Date of next audited annual statement	1 June 2017

No post-audit follow up actions were required.

E: RISK (½ page)

Overall risk rating: Major
The overall risk rating for the programme remains major given continued instability resulting from political deadlock in peace negotiations between Israelis and Palestinians and the political context in Gaza. This means that occasional flare ups in violence are more likely, which could impact programme operations and deliverability.

Overview of programme risk
The risk register (annexed) is regularly monitored on a quarterly basis. In addition to monitoring risks identified through the programme, the below risks have been identified and are monitored regularly:

The political context, particularly in Gaza, raises the risk that funds may indirectly or unintentionally be diverted for use by illicit and unauthorised organisations. Safeguards employed by the programme for vetting, anti-fraud, anti-corruption, contracting, and procurement were found to be effective, which was also confirmed by the programme’s independent evaluation supplier. Safeguards are monitored regularly.

Outstanding actions from risk assessment
There are no outstanding actions from risk assessments.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The programme has met its targets for the year and remains on track to deliver its end-of-programme targets in 2019.

Performance of partnership(s)
DAI Europe (implementation supplier) and GDSI (evaluation supplier) continue to meet commercial partnership requirements.

Asset monitoring and control
PMDP keeps an updated track of the programme asset record which DFID monitors on a quarterly basis. The last two asset checks were conducted in December 2016 and April 2017.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
The PA Ministry of National Economy is a member of the Steering Committee of the programme. In addition, PMDP works closely with the Ministry on the Commercial Trade Representatives component as well as the Business Enabling Environment (BEE) component. Finally, PMDP supports the Palestinian Investment Promotion Agency (PIPA) to improve its capacity and attract investments.

The Partnership Principles are relevant to the management and monitoring of this programme given it works directly with the PA.  We  assess the Palestinian Authority’s commitment to DFID’s Partnership principles on a regular basis, most recently in March 2017. The Partnership Principles are also discussed through a formal meeting with the PA annually. This was last undertaken in June 2016 where we acknowledged progress by the Palestinian Authority against a number of indicators in particularly challenging circumstances.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
Evidence and Theory of Change
Evidence collected throughout 2016 confirms the validity of the Theory of Change (ToC). Nonetheless, the ToC has been updated after PMDP instituted a new shift in approach, introduced new grants windows, and expanded the mandate of Output 3 to include new activities as a result of the EU’s add-on. The programme’s evaluation supplier, GDSI, organised a workshop in February 2017 to review the ToC and changes were agreed between stakeholders during and after the workshop. The updated ToC (annexed) now explicitly mentions job creation at the outcome level. Below is a list of changes introduced to the ToC:

Level of Change	Previous Statement	New/Additional Statement
Impact (supplementary statement)	Client and non-client firms increase productivity, employment and profits	Client and non-client firms/beneficiaries increase productivity, employment and profits
Outcome (main statement)	Improved competitiveness of Palestinian private sector	Improved inclusive competitveness of Palestinian private sector and job creation
Outcome / (supplementary)	Underperforming market system improve productivity	Productivity and employment increase through strengthened market systems
Outcome / (supplementary)	Firms produce higher quality and/or lower cost products and services	Firms/beneficiaries produce higher quality and/or lower cost products and services and/or expand
Output 3 / (supplementary)	PIPA better equipped to promote and look after investment	PIPA and other organisations better equipped to promote and look after investments
Output 3 / (supplementary)	Effective CTRs deployed	Effective CTRs deployed and modality available for continued use
Output 3 / (supplementary)	N/A	Enabling environment improved for doing business in/with OPTs, including PEC’s activation and moving the NES forward
Output 2 / (supplementary)	BSPs to invest to imrpove and innovate their businesses	Identify market failures in sectors with high potential to create jobs
Inputs/Interventions / Output 1	Technical assistance, matching grants to firms	Technical assistance, matching grants to firms/beneficiaries and partnership with co-facilitating organisations
Inputs/Interventions / Output 2	Market analysis, facilitation activities	Market analysis, facilitation activities and partnerships to unlock market systems failures
Inputs/Interventions / Output 3	TA and systems development for PIPA, research and build Diaspora linkages and train commercial trade representatives	TA and system development for PIPA and other trade and investment organisations, research and build Diaspora linkages and train commercial trade representatives and TA to support BEE

In addition to the above changes, the programme updated the definitions of firms/beneficiaries and co-facilitators. Firms/beneficiaries now refer to enterprises, cooperatives, startups, and entrepreneurs and include youth and women businesses. Co-facilitators now refer to organisations with particular access to and experience with and supporting women and youth.

Monitoring progress throughout the review period
The programme falls under the OPTs Economic Development pillar and is managed by a Project Officer, Senior Programme and Policy Officer, Private Sector Adviser, and the Team Leader who is also the Senior Responsible Owner (SRO). The team monitored progress in 2016 as follows:
- DFID embedded a Project Officer at the programme site three days per week to monitor progress and provide day-to-day support.
- DFID’s Senior Policy and Programme Officer met with PMDP management on a monthly basis, called PMDP management on a weekly basis and corresponded on PMDP-related issues on a daily basis.
- DFID’s programme team also met regularly with the EU Project Manager and Head of the Economic Development Unit separately and together with DAI Europe.
- DAI Europse submitted monthly performance sheets, quarterly progress reports, and quarterly financial reports.
- DFID held occasional meetings with PA Ministry of National Economy at both ministerial and technical levels.
- PMDP organised quarterly Steering Committee meetings.
- GDSI provided regular assessments quarterly and annually and have improved programme efficiency. For example, GDSI recommended a change in definition to women owned/managed businesses which was taken on by the programme.

Evidence and data collected are sex disaggregated where possible and gender-specific indicators were included in the logframe.

Annual review
The annual review for 2016 has been completed by DFID’s Economic Development Pillar’s Senior Programme and Policy Officer and Private Sector Adviser in Jerusalem with input from relevant DFID advisers. DFID’s Deputy Head of the OPTs programme based in Jerusalem quality assured the review. The annual review deduced most of its information from the annual report submitted by the implementing partner DAI Europe as well as the annual assessment prepared by the evaluation supplier GDSI.
ANNEX 1: PMDP amended logframe

PMDP logframe: updated on December 2016

ANNEX 2: Initiated interventions accepted and action taken by target group

ANNEX 3: Value for Money Analysis

ANNEX 4: Risk Register

ANNEX 5: PMDP Asset List