Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the Programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the Programme.

Review Date:	23rd February – 20th March 2017

Title: POST CONFLICT DEVELOPMENT PROGRAMME (PCDP)
Programme Code: 200250	Start Date: 15TH June 2009	End Date: 31st December 2016
If Programme was closed >1 month early please describe in a few words why.	-

Summary of Programme Performance

Year	2011	2012	2013	2014	2015	2016	PCR (2017)
Programme Score	3 / QN -3304683	Deferral from 2.Dec.2012 to 30th June 2013 / QNs -3568546, 3627269, 3986341.	B / QN – / 4036196	A / QN – / 4542198	A / QN - / 5061519	A / QN – / 5495688	A
Risk Rating	Moderate		Moderate	Moderate	Moderate	Moderate	Major

Financial Position

Original Programme Value	£100.5m – total value / Programme Memorandum, 13 November 2009 (QN 2449087) / To build a peaceful, vibrant northern Uganda, with increased opportunities for the people of northern Uganda and reduced poverty for all of Uganda. / The purpose was to create economic, social and political opportunities that improve the lives of people affected by conflict.
Extensions/ amendments	A no-cost extension and a re-allocation of £33.92m, (22 June 2011,QN 3100442) from within the Programme’s total budget of £100m to reflect Ministerial priorities on results and delivery mechanisms used to achieve the Programme’s purpose. / A rationalisation of Programme outputs from 6 to 4 to align better with the Government of Uganda’s results matrix. / A no-cost extension of the Programme by one year to March 2015 to bring the timescale in line with DFID Uganda’s Operational Plan and with the UK spending round.
	£90m – reduction in total value / Submission to Ministers, 29 July 2013 (QN 4081381) / A reduction in the allocation for PCDP from £100m to £90m. / A reallocation of £16m between the four main outputs of the PCDP.
	A no-cost extension from March 2015 to December 2016, (QN 4512561) / A re-allocation of £9,659,902 between the four main outputs of the Programme reflecting the changes in results and instruments of delivery.
Log-frame revisions (with dates)	Logframe Original – 13 November 2009 (QN 2449095)
	Revised logframe – June 2011 (QN 2967884)
	Revised logframe – July 2013 (QN 4079558)
	Revised logframe – November 2013 (QN 4246048)
	Revised logframe – August 2014 (QN 4605368)
	Revised logframe (Youth outputs) – February 2015 (QN 4968538)
	Revised logframe – July 2015 and July 2016 (QN 5061544)
Total Programme spend	£ 90,111,933.27 (unspent figures to be reduced on ARIES through a Submission Note and PROJB process - £10,403,614.73)

Human Resource Inputs for PCDP
INPUTS (HR) / (100%)	DFID (FTEs)
	17% Senior Governance Adviser /TL (SRO) / 20% Conflict and Recovery Adviser / 10% Governance Adviser / 3% Economist / 15% Private Sector Adviser 5% Social Development Adviser / 10% Health Adviser 5% Results Adviser 10% Dep. Programme Manager 5% Programme Officer

Follow up actions required following closure
The key remaining action is to disseminate the independent evaluation of the youth skills components. The evaluation report was quality assured positively by DFID's evaluation review service EQUALS. Further lesson learning opportunities will be explored through, for example, the DFID skills working group.

The DGF should support the development of a political economy analysis during 2017 to inform the direction of the DGF.

Take forward the lessons learned indicated below on pages 2-4 and recommendations documented in various reviews and independent evaluations (outlined below) to inform policy influencing and engagement.

  - External Evaluation of the Youth Development Programme and Northern Uganda Youth Entrepreneurship Programme, September 2016.

  - UNHCR Assessment report on Joint Durable Solutions for Northern Uganda, 2011.

  - Formative Evaluation of WFP’s livelihood programme in Karamoja, July 2012.

  - Impact Evaluation report, Transparency, Accountability, Anti-corruption component /NUSAF, April 2016.

  - Evaluation of Results Based/Health Financing.

  - Democratic Governance Facility, phase 1 Evaluation Report, November 2016.

  - Advisory Consortium on Conflict Sensitivity Review Report, June 2014.

Lessons learned:

The configuration of the PCDP – as one large umbrella programme with many distinct components and delivery partners programme management was challenging, as was measuring progress towards the outcome. As a result, this project completion review focuses on the PCDP-level logframe indicators, but has also been informed by detailed individual reviews and evaluations on each output.

PCDP was designed with a high level of flexibility to respond to changing contexts and assessments of risk. This proved to be very useful given the changes required following the misappropriation of funding in 2012/13. However, the multiple changes to the programme mean that the original theory of change and plans to holistically support the PRDP were not realised. Value for money has however been pursued through the impact and effectiveness of the individual components.

In programmes of this nature, the overall DFID Senior Responsible Owner in practice must rely on and be supported by ‘sub-SROs’ for each component who are closer to the day to day work, delivery chain, and decision making.

Output 1: Local Government Capacity for Equitable Service Delivery and Management Is Strengthened

It’s crucial to embed public and social accountability into the design of a stronger service delivery mechanism mainstreamed within government systems.

The impact of small components such as the technical assistance provided to Gulu and Lira local governments can be significant. DFID recognised its impact and replicated the same approach under the Governance, Accountability, Participation and Performance programme (GAPP) component of the Strengthening Uganda’s Anti-Corruption and Accountability Regime (SUGAR) programme.

Output 2: The most vulnerable conflict-affected communities are rebuilt and empowered

Robust monitoring of quality of care should be incorporated into future RBF payment formula. A lesson learning review showed that the quality of infrastructure, medical supplies and management processes improved in the RBF health facilities but that the quality of care was poor in both sub-regions.

Increasing productivity and beneficiary livelihood security through conditional transfers was effective. Implicit in the NUSAF II (WFP) objective was behaviour change, reflecting a move away from dependency on food aid to sustainable approaches to livelihoods. In the short period since food/cash for work was introduced by Karamoja Productive Assets Programme (KPAP), 2,010 people in Karamoja have proven that they are willing to work and that the issue for the future is one of opportunity rather than dependency. Their willingness to work is evident by the large numbers who participated in community gardens and dam and road construction-- many activities were over-subscribed.

Output 3: The private sector is revitalised and accessible employment opportunities are created

The key lesson of the business grant scheme relates to the costs and risks of this type of programming, and the very significant oversight and management systems required to manage them well. Should similar schemes be proposed in the future, the designers should look closely at established challenge funds (such as Africa Enterprise Challenge Funds or ABiTrust) to copy management systems and learn lessons.

A key lesson on youth skills training is the level of effort and capacity required to ensure data quality. While large amounts of data are available on over 25,000 youth, data cleansing and checks by independent evaluators revealed quality and content gaps that limited the strength of conclusions that could be drawn from the projects. This was despite a very significant effort by implementing partners to ensure strong monitoring and data systems.

The assumption that training schemes in developing economies deliver ‘decent jobs’ is weak. Although economic benefits are likely to have outweighed costs, ‘decent’ jobs are extremely hard to deliver in an informal economy. One of the original selected measures of a ‘decent job’ (based on ILO guidance) for youth was the average income level in the region. This was over ambitious because youth will take many years to reach the average level of income and the target was thus reduced by 50%. Targets could perhaps be better calibrated by asking potential beneficiaries about their expectations and prospects in the economy, with and without training. Even better would be randomised control trials (RCTs) to enable clear comparison of trained youth with non-trained youth.

The youth components are not sustainable and replicable at scale. Although almost 30,000 have been trained, with a likely positive net cost/benefit ratio, funds are not available to support the 700,000 young people coming onto the labour every year in Uganda – the core problem of youth under-employment requires a different approach if it is to be comprehensively addressed.

Meaningful and cost effective indicators are extremely hard to operationalise in a very poor, informal economy; much more work is required on tracking perceptions of economic opportunity.

Output 4: Government, civil society and communities can engage actively in peacebuilding and reconciliation

Constructive engagement: Taking a non-confrontational approach by partners has enabled responsiveness on the part of officials in MDAs. There was more traction for investments where DGF partners and state partners worked collectively.

Programme design should embed agility, flexibility and capacity to adapt to changing context: This was demonstrated in a number of ways but most important was when the Anti-Homosexuality Act was passed and later nullified.

Technology-based innovations have a catalytic effect in promoting access, engagement and drawing in citizens. This should be explored as a tool for addressing marginalisation, exclusion and responsiveness of leaders to citizen concerns.

The DGF Legal Aid Programme contributes to closing an important and critical gap in the formal justice system but there are critical systemic gaps within the criminal justice sector chain that need to be addressed for the effectiveness of legal aid.

The Legal Aid Programme (LEAP) is challenged by a lack of sustainability. Most partners are solely funded by the DGF and the whole legal aid system could collapse if DGF did not continue. The issue of sustainability within the justice system needs to be addressed at a strategic level.

Problem-Driven Iterative Adaptation (PDIA) approach is considered appropriate for a democratic governance programme of this scale and complexity; and the approach should be central to the future design of the Democratic Governance Facility (DGF). DGF implementation and governance structures will need to be tailored accordingly.

Integrating conflict sensitivity within large government programme is a highly political endeavour (rather than a technical fix). NGOs can play an important role, however, concerted messaging, monitoring and buy-in to the approach amongst stakeholders and drivers of change is necessary from the earliest design phases.

Perceptions of neglect arising from poor service delivery and under-developed infrastructure cannot be resolved in the absence of post-conflict truth, reconciliation and transitional justice processes through which the relationship between state institutions and the people can be repaired.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	2449087
DevTracker Link to Log frame:	5061544

Outline of programme and what it has achieved

The UK’s five year Northern Uganda Post-Conflict Development Programme (PCDP) approved £100,515,548 million to support recovery in post-conflict northern Uganda. However, a number of the activities and components ended prior to its programme natural end and the budget was reduced to £90m accordingly, the pace of implementation across components varied and PCDP underwent two time extensions. The first to March 2015 and a second to December 2016 to allow the Programme to: (a) to align funding for the Rights, Justice and Peace (RJP) component of Democratic Governance Facility (DGF) to the DGF end-date; (b) to give the re-programmed youth development Programme an additional six months to complete planned activities; and (c) to support a one-year extension of the Northern Uganda Social Action Fund II (NUSAF) to August 2015 to complete the houses. Delivery mechanisms were changed during the project, reflecting the UK’s withdrawal from budget support following a corruption scandal, reorienting from GoU delivery to NGO and private sector delivery.

The goal of PCDP is to build a peaceful, vibrant Northern Uganda with increased opportunities for the people of the North and reduced poverty for all of Uganda. The outcome is to create economic, social and political opportunities that improve the lives of people affected by conflict.

Originally, the PCDP was delivered under six outputs:

  1. Strengthening the ability of local government to deliver services through the construction of houses for health and education workers.

  1. Fostering private sector led growth through an economic recovery analysis for northern Uganda and a grants scheme for small enterprises.

  1. Building skills for young people through a literacy, vocational skills and apprenticeship Programme.

  1. Supporting extremely poor and vulnerable people returning from camps by providing shelter, livelihoods opportunities and cash transfers.

  1. Supporting the implementation of the Juba peace agreement, in particular institutional mechanisms including an Equal Opportunities Commission.

  1. Increasing the capability of the Government of Uganda to monitor results and conflict sensitivity.
In June 2011 this was reduced to four to better align with the Government of Uganda’s results matrix for Northern Uganda, in parallel the logframe indicators were adjusted at purpose and output level to better measure progress. New indicators to monitor the impact on peacebuilding ensured DFID Uganda’s work on service delivery was linked to reducing the drivers of conflict. Other factors that informed the redesign included:

Scale back on-budget support for local government service delivery: re-focused to improving services through a World Bank Programme and a new results-based aid pilot in the health sector.

Significantly increasing support to the most vulnerable communities. WFP supported to provide livelihood opportunities in Karamoja and extended support to UNHCR to help IDP returns.

Increased support to the private sector development, including through a small grants scheme to businesses and vocational training for young people; and

Support to national reconciliation.

Key achievements include:

1. Local government capacity for equitable service delivery and management strengthened: construction of 1,738 homes for health workers and teachers, improved governance to reach minimum standards in 21 sub-counties, and community-level project Monitoring and Evaluation (M&E) tracking systems in 485 sub-counties.
2. Vulnerable conflict-affected communities rebuilt and empowered: 3,500 extremely vulnerable people accessing social services, shelter and livelihoods in Acholi and Lango; 24 million labour hours on food/cash for work projects in Karamoja and 9,878 food transfers; and an evidence base for results-based financing in healthcare, through 20 results-based health facilities and 10 input-based facilities, targeting 333,719 consultations and treatments.

3. Private sector revitalised and accessible employment opportunities created: The Private Sector Foundation Uganda (PSFU) approved grants for 426 businesses (under target) before it was ended in 2012. Strong performance from the Youth Development Programme (YDP) and the Northern Uganda Youth Employment Programme (NUYEP) ensured PCDP surpassed the targets of 15,400 (15,875) youth trained in vocational skills and 13,377 in business start-up. However, Peace and Conflict Surveys revealed declines in the perception of access to increased economic opportunity across all districts and regions.

4. Government, civil society and communities engage actively in peace building and reconciliation: influencing the GoU’s Peace, Recovery and Development Plan (PRDP) interventions to make them more conflict sensitive; legal aid services to 4,975,184 in 79 districts; and conflict analysis in PRDP districts areas for 4 key conflict drivers (land, sexual and gender based violence, transitional justice and youth). The latter framed a shared discourse on key conflict issues amongst state, non-state and political actors at the national, district and community level.

In addition, PCDP also funded important policy work with the Office of the Prime Minister. The ‘Economic Recovery Analysis’ was a major review of the Northern economy, establishing for the first time a set of economic accounts, modelling likely growth patterns, and recommending key intervention priorities. It was based on a wide-scale survey of business in the region. The final report, produced by Oxford Policy Management, was launched by the Prime Minister and First Lady at the bi-annual PCDP monitoring conference in April 2015. This followed a low quality report from Uganda Investment Authority, who’s contract was terminated. The report’s key findings were:

- The North remains highly disadvantaged in infrastructure, poverty prevalence, and in number of private businesses.
- Northern businesses are typically isolated, trading within their own districts.
- Northern Uganda would have to grow at over 10% a year for 25 years to catch up with the rest of Uganda.
- Northern Uganda does have key advantages in terms of land, geographic location to markets, and minerals, which represent significant economic potential.
- Achieving the potential will require massive, coordinated and risky investments by government and private sector.

The report provided a strong basis both to justify Uganda’s continued focus on the Northern region, and to shape it towards a development and growth orientation, rather than relief. It is reflected in the second major piece of work, to produce a design document for the Government of Uganda’s third PRDP programme. While not formally launched, the PRDP III design document has driven improved principles of sustainability, oversight and economic development into the PRDP 3 programme.

## PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

PCDP aimed to increase economic, social and political opportunities and improve the lives of people affected by conflict in Northern Uganda. The outcome was to create economic, social and political opportunities that improve the lives of people affected by conflict. PCDP was aligned behind GoU’s Peace Recovery and Development Programme (PRDP) and the Poverty Eradication Action Plan (PEAP) (later replaced by the National Development Plan). Under PRDP, the proportion of people living in poverty in Northern Uganda reduced, but only slightly, from 46.2% in 2009/10 to 41.8% in 2012/13 – while the national average declined from 24.5% to 19.7% (National Poverty Status Report, 2014). Perceptions that the North is marginalised by the GoU persist, with the 2014 Peace and Conflict Indicators (PCI)[1] Survey indicating a decrease in perception that Government is doing enough to breach the gap between north-south (56% in 2013 to 47% by 2014).
[1] Peace and Conflict Indicators (PCIs) were used to track the interactions of the PCDP/PRDP (led by International Alert), which also saw the further development and use of the Conflict Analysis to influence programming (led by Saferworld).

Progress against the expected outcome was assessed through four outcome level indicators: No <5s tested and appropriately treated for malaria; number of youth with decent jobs; and satisfaction with basic socio-economic services; and responsiveness of local government to community needs. Each component produced sound results, however the targets at the outcome level were not all fully met.

In the Uganda National Household Survey 2012/13, the percentage of respondents who had never attended school was largest in the Northern region with 13.6% while the national average was only 7.6%.Secondary school enrolment in Northern Uganda is half that of the national average (21.9%) and the lowest in the country at 10.9% (12.9% male; 8.6% female). Youth skills and enterprise programmes aim to address these inequalities through vocational and entrepreneurship training schemes. However, skills development programmes suffer their inability to generate employment as they are said to be ‘showing little impact on poverty or stability, especially to programme cost’[2]. These programmes are found to have high failure rate often due to their large nature and absence of informed market realities. Evidence supports arguments that greater success for youth and returns on investment are found in capital injection centred programmes that for example provide cash transfers, in-kind capital (livestock or tools) or subsidised credit.
[2] The External Evaluation of YDP and NUYEP Programmes: Final Evaluation Report, September 2016.

Peace and conflict outcomes were modest due to political barriers, as established by the DGF phase 1, Evaluation report, November 2016.

Outcome Indicator 1	Baseline April 2011 to March 2012	Target 2015/16	Progress
Number of under-fives presented with fever that are tested for malaria and appropriately treated in the 31 PNFP facilities (disaggregated by gender)	21 RBF HF=25,854 10 IBF HF=9,531 Total =35,385	21 RBF HF = 32,965 10 IBF HF =12,197 / Total = 45,162	Achieved / 21 RBF HF = 43,660 / 10 IBF HF = 17,332 / Total = 60,992 / Lessons from the evaluation of the RBF Programme were disseminated at a national event in September 2015.

Overall there was an increase in under-fives tested and appropriately treated for malaria in all 31health facilities. This is largely attributed to improvements in knowledge and skills of the health workers following training and supply of treatment guidelines. A more significant increase in the RBF facilities suggests that the link between performance and payments incentivised improvements in management of fever cases

Outcome Indicator 2	Baseline 2009	Target (2016)	Progress
Number of YDP youth with decent jobs (employed or self-employed in the formal or informal economy) (attributable to DFID)	0	11,000 / (50% female) / Based on 71% of overall trained beneficiaries target	Missed target. / The independent evaluation of the relevant component estimated that only 39% of beneficiaries met the criteria of ‘decent job’, covering both a monthly income target of UGX 85,000 and the prospect of being in employment for more than 6 months. Only 21% hit a target of UGX 141,000 per month which had been the original criteria before a downward revision.

The target of 71% of beneficiaries with decent jobs was not met. The low figure underpins important challenges to assumptions linking training packages to employment outcomes. However, given the informal nature of the economy and the youth of participants, the project still secured positive results, and it can be argued that the target was set too high, and that significant income and economic benefits were generated both by YDP and its sister project NUYEP. An independent evaluation provided a very cautious estimate that the two projects together delivered an economic return - based on income effects - of a little over 1.4, or £14.95m of benefits for the £10.5m project costs. The benefits used in this calculation also excluded many additional social benefits arising from measured increases in social engagement, life skills, and capacity building within the technical colleges supported through the project. This form of evaluation measurement - a benefit/cost ratio – is likely to be more useful for future similar projects than a target based on decent jobs.

Outcome Indicator 3	Baseline (2008)	Target (2013)	Progress
Level of satisfaction among targeted population with quality of basic socio-economic services	73%	90%	Missed target / 85%

A Citizens Report Card implemented under NUSAF II in 2013 (through which PCDP funded staff housing) covered 24 of NUSAF’s 55 districts and reported that 85% of respondents were satisfied that NUSAF II investments had improved their access to education, health and safe water. However, it is important to note that it is not possible to identify how far this can be attributed to increased numbers of houses for teachers and health workers. Furthermore, there isn’t more recent data, showing whether the levels of satisfaction has either increased, decreased or remained static over the last three years.

Outcome Indicator 4	Baseline (2011)	Target (2014)	Progress
% of respondents assessing that local government is responsive to community needs (ACCS PCI 2: Local government responsiveness to community needs)	Acholi: 44% [M:23%, F:21%]; Lango: 44% (M: 22%, F:22%]; West Nile: No data available; Karamoja: No data available.	Acholi 59% / Lango 59% / West Nile 62% / Karamoja 57%	Missed target / Acholi 58.1% / Lango 51.4% / West Nile 55.3% / Karamoja 71.6%

This indicator tracks whether investments under PRDP, to which PCDP contributes, expanded economic opportunities for people across Northern Uganda. Annual Peace and Conflict Impact (PCI) surveys across Northern Uganda gathered baseline data gathered for Acholi and Lango sub-regions in 2011, and for West Nile and Karamoja in 2014.

Notwithstanding the marked improvements noted in Karamoja sub-region in local governments’ responsiveness to community needs, in focus group conducted during the PCI discussions, respondents reported government leakages of funds through corruption thereby undermining perceptions of local governments being responsive to community needs.

Factors that influenced positive perceptions (under outcome indicator 4) were:
- An impression of the community’s active engagement in service delivery and budget prioritisation. This was seen as a direct result of the local government participatory planning structure used to incorporate community needs from village up to district levels.
- However, such an impression was not supported by the (lower local) community-level PCI survey, where respondents reported having never participated in local government planning activities because they had never been invited. Only 16.3% of the aggregated respondents at the lower-local level reported having provided and sought information in local government planning meetings.

Factors that influenced negative perceptions were:
- Insufficient community mobilisation for, and engagement with, the planning process at lower levels.
- Inadequate staffing, not being well equipped and long distances were supported by arguments advanced in the panel discussions relating to resource and funding restrictions.
- Limited budget allocations from the central government resulted in feelings of marginalisation among the respondents. Service delivery was characterised as being centrally dictated, rather than a demand-driven provision.

## C: DETAILED OUTPUT SCORING

The table below indicates the summary performance of the PCDP four outputs.

Output	Performance score
Output 1 - Local government capacity for equitable service delivery and management is strengthened.	A
Output 2 - The most vulnerable conflict-affected communities are rebuilt and empowered.	B
Output 3 - The private sector is revitalised and accessible employment opportunities are created.	A
Output 4 - Government, civil society and communities can engage actively in peacebuilding and reconciliation.	A+

OUTPUT 1: LOCAL GOVERNMENT CAPACITY FOR EQUITABLE SERVICE DELIVERY AND MANAGEMENT IS STRENGTHENED

Score: A - Outputs met expectation
Overall Risk: Medium
Impact Weighting: 25%

Under PCDP Indicator 1.1, DFID provided a £24m ($35m) grant to the World Bank (WB) Northern Uganda Social Action Fund (NUSAF) II programme. This included £21m to build 1,738 houses for teachers and health workers; £2.2m for overhead costs, and £.8m for Inspectorate of Government (IG) to improve transparency, accountability and anti-corruption (TAAC) of NUSAF II which was supported under indicator 1.3. Under indicator 1.2, PCPD aimed to build the capacity of the Gulu and Lira District local governments and Lower Local Governments (sub-counties) to improve service delivery through the provision of technical assistance. The total support for technical assistance was £57,265 for two years.

The Northern Uganda Social Action Fund (NUSAF) was co-financed by World Bank’s International Development Association (IDA) and DFID with US$ 100 million and £24 million respectively.
The project built on the experiences of NUSAF 1, scaling up the pilot on public works and Vulnerable Group support components to produce a broader livelihoods response that addresses household income enhancement mechanisms for the poor. It also provided support to communities to improve public infrastructure in order to have better access and utilisation of basic services in under-served communities. The project was supported through three components: (i) Livelihood Investment Support; (ii) Community Infrastructure Rehabilitation; and (iii) Institutional Development.

Indicator 1.1: Number of houses for health workers and teachers constructed by NUSAF2 (DFID attributable)

Output Indicator 1.1		Baseline 2009	Target (2015)	Achieved
Number of houses for health workers and teachers constructed by NUSAF2 (DFID attributable)	Planned	0	1,738 / (869 units each unit containing 2 houses)	Achieved / 1,738
	Source: World Bank NUSAF2 annual reviews; Impact Evaluation of TAAC/NUSAF
Output Indicator 1.2		Baseline 2009	Target (2015)	Achieved
Number of sub-counties in target districts meeting minimum governance conditions	Planned	4	21	Achieved / 21
	Source: MoLG Annual Assessment Process of Local and Lower Local Governments
Output Indicator 1.3		Baseline 2009	Target (2015)	Achieved
Percentage of sub-counties with operational community-level project M&E tracking systems	Planned	0	100% (485/485)	Achieved / 100%
	Source: World Bank NUSAF2 annual reviews

The NUSAF Project was approved by Parliament on November 25, 2009 and officially launched in February 2010 with the project development objective to improve access of beneficiary households in Northern Uganda to income earning opportunities and better basic socio-economic services. The project was initially covering 40 districts and was later scaled up to cover 55 districts covering the sub-regions of West Nile, Acholi, Lango, Karamoja, Teso, Elgon and Bukedi, and parts of Bunyoro.

DFID’s support was targeted at building 1,738 houses for teachers and health workers as an incentive package to attract and retain local government staff in order to improve social services in the health and education sector. DFID also supported the transparency, accountability, and anti-corruption efforts within the NUSAF programme as well as the project’s technical support team (TST). Under the PCDP, part of DFID’s interests included improving access to key social services in especially health and education through building houses for teachers and health workers as an incentive package for the North and tackling extreme poverty and vulnerability as poverty levels in Northern Uganda stood at 46.2% above the national average that stood at 24.5% at the start of the PCDP in 2009. This meant that Northern Uganda lagged behind the rest of the country on all service related MDGs and the region had difficulties in attracting and retaining local government staff.

The houses were equipped with solar panels, enabling teachers to do lesson planning, mark students’ homework, charge their phones and remain in touch with District officials. Community participation in construction supervision strengthened adherence to technical specifications and ensured quality control.

All projects under NUSAF II were identified and implemented by communities – an innovative model for a large scale project. As a result, a key strength of NUSAF II was its strong engagement of communities in sub-project implementation – however the focus on community participation and rigorous WB accounting resulted in slow build times.

There is no specific end of project evaluation that provides evidence on the impact of houses constructed on education and health outcomes. Consequently, there is no evidence that building teachers and health workers led to staff retention and improved service delivery.

This aspect of the project was exposed to risk as a result of weak social safeguards. The project implementation support mission (sept 2013) noted that various social risks had not been appropriately considered during design and so mitigations were not being taken forward during implementation (including by contractors). As a result, the project integrated local government monitoring and reporting and established a grievance redress mechanism. At the sub-county level, designated environment Focal Persons were identified to monitor and escalate social safeguard concerns.

Lessons learned:

The NUSAF project highlights the need for a conscious effort to root development interventions in conflict mitigation. In this way, the experience of NUSAF not only offers lessons for donors concerned with development prospects of Northern Uganda but also the design and implementation of comparable social action funds in post-conflict conditions. NUSAF was an appropriate approach highlighting the importance of integrating project management with local government planning and administrative systems and building community level capacity for planning and monitoring micro-projects in a post-conflict state.

There is value in a co-ordinated response by donors and recipient governments on the most appropriate forms of intervention in conflict and post-conflict environments. Although structures were put in place, it was difficult to ascertain if there was a targeted recruitment and retention strategy for teachers and health workers (to ensure the structures are filled through-out). In addition, maintenance of the houses was not factored in the design process. It was difficult to conclude if the houses were indeed an incentive to retain teachers and health workers in Northern Uganda and if the project subsequently contributed to health and education outcomes.

To improve M&E functions at the implementation levels (i.e. district level and below), high level political commitment was key e.g. by the PS of the Ministry of Local Government (MoLG) that heightened the engagement and monitoring of NUSAF II by MoLG.

Pooled funds ‘may’ allow for greater economies of scale by (a) reducing the risk of duplication (as different donors fund the same types of initiatives) and (b) registering low transaction costs for DFID (WB took charge of 80% of the project overhead costs).

Indicator 1.2: Number of sub-counties in target districts meeting minimum governance conditions

This project was delivered through the Uganda Local Government Association (ULGA) with funds of £417,423 between 2010 and 2012, until fiduciary risk ruled out a second phase. DFID then provided 2 year contracts to the Technical Assistants to the Chairperson of Gulu and Lira Local Governments, and conducted a scoping study to identify the potential for scaling-up support.
Key outcomes of the project was noted in PCDP’s annual reviews and confirmed by interviews with local officials and chairpersons during a review visit in February 2014. These included:
- Lira District Chair scored most performance improvement (90%) (LG Council Scorecard) in 2014,
- Lira Local Government became the most improved district in the country.
- Lira had the highest percentage improvement in performance of any district assessed.
- Improved communications helped resolve misinformation and improved transparency and inter-party relations.
- Council Resolutions were documented, implemented and followed-up.
- Gulu held a consistently high score (2nd and 1st)
- Transparent master plans to increase revenue were developed
- A citizens advice bureau was constructed and is fully operational
- A staff incentive scheme improved time keeping and attendance by local government staff.

Lessons and how these have been shared:

Embedding TAs in each District was not sustainable but was highly effective. Lessons were integrated into the Governance Accountability Participation and Performance (GAPP) programme, jointly funded by DFID and USAID.

Indicator 1.3: % of sub-counties with operational community-level project M&E tracking systems

In 2014, all sub-counties had operational community-level project M&E tracking systems. The system (which was managed by Community Development Officers and NUSAF II desk officers in the Districts) tracked and analysed sub-project processes, outputs and intermediate outcomes at the sub-county levels. Data collection was strengthened through the introduction of sub-project tracking templates, but timeliness and regularity in data collection remained an issue. It was also decided that District and Sub-County personnel were required to provide the technical support, and the monitoring approach was amended to rely less on community reporting. While NUSAF reported inadequate operational funds for field-based activities including monitoring they were able to reach all sub counties with the tracking systems, and the target was met.

The UK’s support to NUSAF also provided for a Transparency, Accountability and Anti-Corruption (TAAC) component managed by the Inspectorate of Government (IG). TAAC’s objectives included strengthening transparency and accountability in implementing the broader NUSAF programme and supported the creation of 625 Social Accountability Committees (SACs) at sub-project level, with 40,000 members trained. 12,000 spot messages and talk shows were delivered through 18 regional radio stations, and 2000 NUSAF related cases of corruption were received via SMS, telephone calls and letters. Of these reports, 426 cases were deemed actionable, of which two were taken forward for prosecution.

The IG developed a remote monitoring tool which used a mobile phone system. The trainees and regional managers fed into this system which also linked with the Global Positioning Satellite system (GPS) to confirm that the training was conducted.

According to the Impact Evaluation report of Transparency, Accountability, and Anticorruption (TAAC (QN 5681586), it increased the intensity of community monitoring which delivered observed improvements in the quality of community projects. The Social Accountability and Community Monitoring (SACM), training led to an increase in overall community monitoring, including in communities producing accountability reports or monitoring reports. The intervention led to a particularly strong increase in the intensity of monitoring by the Social Accountability Committees that became more active: they undertook approximately 40% more monitoring activities compared to committees that were not assigned to the SACM training. Social accountability committees produced more written monitoring reports and increased monitoring project implementation and material usage. As such, the absolute increase in community monitoring is moderate.

Additionally, the component implemented anti-corruption prevention activities through the IG, such as public awareness through radio talk shows, sensitisation workshops and training of NUSAF II Social Accountability Committees. A free corruption reporting hotline with a code 6009 was set-up to ease reporting of complaints to the IGG.

Lessons and how these have been shared

The 2016 impact evaluation of the TAAC component was disseminated to GoU and DPs. Lessons from implementation of the NUSAF II TAAC sub-component and SACM intervention have already had broader policy influence, including the design of the NUSAF III TAAC sub-component. For instance, in line with the approach in the SACM training, the Community Monitoring Groups (CMGs) have replaced the Social Accountability Committees (SACs) and have been given an expanded mandate. At the same time, training of these communities will build upon the SACM curriculum. In addition, the experience of the TAAC sub-component has already been emulated in social protection programmes in Liberia and Sierra Leone. The experience of the NUSAF II TAAC sub-component is also mentioned as an example in the World Bank new strategic framework for mainstreaming citizen engagement (World Bank, 2014). Other lessons include:

- When there is adequate support and guidance, communities (including those affected by conflict) can participate effectively in local development.
- It is crucial to embed the promotion of public and social accountability in the design of a stronger service delivery mechanism which are mainstreamed into existing government systems.
- The incentives for community members to engage in project monitoring should be clear.
- Due consideration should be given to long term sustainability of projects of that nature e.g. maintenance of assets created.

OUTPUT 2: The most vulnerable conflict-affected communities are rebuilt and empowered

Output 2 score and performance description:

B - Outputs moderately did not meet expectation
Overall Risk: Medium
Impact Weighting: 25%

OUTPUT 2	Output Indicator 2.1	Baseline 2009	Target (2010)	Achieved
The most vulnerable conflict-affected communities are rebuilt and empowered	Numbers of EVIs/PSNs lacking access to social services, shelter & livelihoods in areas to which they return, resettle or reintegrate	10,190 (total); 3,748 (M); 6,442 (F)	3,110	Achieved. / 3,500 (Total); 2,205 (F); 1,295 (M)
		Source: UNHCR monthly and quarterly performance reports
	Output Indicator 2.2	Baseline 2009	Target (2015)	Achieved
	Number of labour hours worked on food/cash for work projects in Karamoja (attrib. to DFID)	0	28m (14m F)	Partially achieved 23.9m
		Source: WFP / NUSAFII annual reviews
	Output Indicator 2.3	Baseline 2009	Target (2015)
	Conditional food transfers received by NUSAF II participating households in Karamoja (metric tonnes, attributable to DFID)	0	14,964	Missed target / 9,878
		Source: WFP / NUSAF2 annual reviews
	Output Indicator 2.4	Baseline 2012	Target (2015)
	Number of OPD consultations and treatments in the 31 PNFP facilities per year (disaggregated by male/female , and by age-group)	21 RBF HF =210,708 10 IBF HF = 78,032 Total= 288,740	21 RBF / HF=252,975 / 10 IBF / HF=92,500 / Total=345,475	Partially achieved / 20 RBF / HF = 253,919 (107,093 M, 146,826 F) 10 IBF / HF = 79,800 (31,005 M, 48,795 F) Total=333,719
		Source: DFID Northern Uganda healthcare component implementing agent

Output Indicator 2.1: Numbers of EVIs/PSNs lacking access to social services, shelter & livelihoods in areas to which they return, resettle or reintegrate

DFID provided UNHCR with £5,720,000 for the achievement of durable solutions (return, reintegration and settlement) for internally displaced persons (IDPs) in Northern Uganda in 2011 within the framework of the PRDP, UNHCR and its partners worked to deliver:

- Protection monitoring and advocacy based on the Framework for Durable Solutions with focus on supporting the national system and its institutions; and
- Coordinated support to strengthen resettlement and reintegration in return areas.

By December 2011, all (3500 (2,205, Female and 1,295, Male), Extremely Vulnerable Individuals (EVIs) and Persons with Specific Needs (PSNs) previously living in camps were successfully resettled and provided with shelter and livelihoods support. This was lower than the original estimate of 10,190 as many of the PSNs and EVIs had voluntarily moved out of the IDP camps, the target was adjusted to 3,110 per annum, but the target to establish and assist 120 common interest groups was increased to 190 to provide impoverished communities with sustainable options to support their EVI/PSNs.

2,692 (87%) shelter units (huts and latrines) and household start up kits were provided out of the total 3,110 initially targeted. Reintegration of each beneficiary was supported by community/family networks. Prior to shelter units (hut and latrine) construction, a community/familial care-taking network was established and/or strengthened around each individual beneficiary. This activity ensured that the return/reintegration of the beneficiary remained sustainable.

459 PSNs were technically assessed for special mobility assistance with support from the National Union for Disabled Persons in Uganda (NUDIPU) and the Gulu Youth Development Association (GYDA). UNHCR assisted all 459 PSNs which represented an increase in the number of PSNs assisted by 109 (131%), compared to the initial target of 350. The assistance included provision of devices to improve their mobility (tricycles, wheelchairs, white canes and crutches) and they were also trained on how to use and maintain the devices.

Lessons and how these have been shared

In 2011, UNHCR finalised a report on the joint Durable Solutions Assessment for Northern Uganda (QN 3564771). The assessment was conducted in partnership with District authorities, as well as humanitarian and development partners. This report was summarised in UNHCR’s end of IDPs Operation report in December 2011, which was shared with UN OHCHR, UN Country Teams, Local Government Authorities in northern Uganda and the GoU.

Lessons drawn from the report have fed into DFID Uganda’s current multi-year Business Case on protracted crises.

Output Indicator 2.2: Number of labour hours worked on food/cash for work projects in Karamoja (attributable to DFID)

From 2010 to 2013, DFID provided £14m DFID to the World Food Programme (WFP), for the NUSAF II livelihoods Karamoja project. This aimed to improve the access of 77,000 moderately food insecure households with labour capacity (approximately 50% of the population in the Karamoja sub-region) to income-earning opportunities and better socio-economic services. It was expected to alleviate pressure on household budgets by providing temporary employment during the periods of greatest stress ; and to create socio-economic assets in and around communities which, in turn, would help build social and ecosystem resilience.

It consisted of three components: i) a Public Works Programme - providing food or cash transfers in exchange for unskilled labour. ii) a Household Income Support Programme (HISP) - providing inputs and training to individual and or small groups of poor households. This was intended to enhance productivity within the household’s principal livelihoods systems and iii) Institutional development - This was intended to enable the necessary skills to be transferred to Government (at the district and sub-county level) and to communities. The project was a response to the WFP strategic shift from food aid to food assistance implemented by WFP through 11 implementing partners.
WFP introduced, within a short space of time, a dramatic shift in the type of programming used in Karamoja at a very large scale providing livelihood and economic opportunities to 76,360 households – this reflected the move from free food distribution to other forms of programming: public works programmes (PWPs) and household income support programmes (HISP).
NUSAF II (WB) provided cash payments in return for public works participation at a rate of Ush 4,000/= (£1) per day. The number of hours worked for food/cash for work projects in Karamoja (attributable to DFID) were 23.9m short of the PCDP logframe target of 28m labour hours. This was due to (a) delays in transfers - There were considerable delays in delivery of food (by several months) undermining the objective of providing food during the hungry months; the cash transfer process was characterised with administrative problems causing extensive delays causing work to stop (b) Completion of existing PWPs – Whilst the PWP funded by NUSAF offered UGX 4,000 per day, the EDF funded Karamoja Livelihoods Programme (KALIP) offered UGX 7,000 per day for public works. Thus, different rates gave rise to competition for KALIP work and over time witnessed an increased uptake of KALIP PWP by the able-bodied and the less able-bodied working with NUSAF II, hence the milestone registered.
Based on wide international experience, it is likely that men will dominate where there is good remuneration (e.g. KALIP) while women will remain working for lower value food transfers and it is understood that KALIP will pay about 7,000 Ush in order to fulfil the commitment by that programme to providing local liquidity. Depending on the understanding of purpose of NUSAF 2 (WFP), it can be argued that the KALIP rate may in fact be more efficient at enabling people to accumulate assets and, ultimately, begin to move out of poverty When assessed against the PCDP log frame the programme does not meet the cumulative target. Funding from PCDP for this programme ended in FY 2013/14. From FY 2014, the programme was rolled into the broader DFID ICF programme in Karamoja.

The project also faced challenges of long delays to cash (and to a lesser extent food) transfers: a direct result of inadequately designed and trailed cash transfer mechanism. There is no data available on how cash was used, and market price data was not mapped to distributions. The technical capacity required by Implementing Partners was underestimated, and has relied on inputs from district officials rather than developing the capacity of districts.

The June 2012 Evaluation report of the WFP Livelihoods programme, (QN 3711926) noted the following lessons learned of the programme:

- Assets created, provided employment opportunities, however the evaluation noted that the PWP programme reflected a series of disconnected projects rather than being based on and informing a local-level livelihoods strategy.
- The programme was judged innovative with good quality targeting and an appropriate balance between food and cash. The programme was primarily a government-designed programme being implemented by WFP.
- Public Works and Household Income Support Programmes are an essential element of a recovery effort. Based on the findings of the evaluation and the context of Karamoja, this review concludes that there was merit in the broad approach taken by NUSAF II (WFP). The project reached a large target group of the moderately food insecure in a relatively efficient way and the food and inputs distribution.
- Notwithstanding the achievements, both food and cash transfers experienced delays and undermined trust in the programme. Delays undermined the objective of providing food during the hungry months.
- The evaluation findings underscore the need to take into account risks of unintended consequences in the design of programmes, Cash transfers exposed women to greater risks of gender-based violence. Additionally, there was evidence that some polygamous households were being excluded from transfers. There was no clear evidence that the programme had a gender strategy and that there was no linkage with targeted income generation opportunities for women and youth.
- The Evaluation also established that any form of shock in Karamoja is likely to quickly undermine any gains made, in what remains a very fragile environment.

It is on this basis, that this evaluation recommended a re-design with a sharper focus, greater analytical and technical capacity and attention to quality if the potential value of the three year investment, as part of the wider GoU led strategy on Karamoja, is to be realised.

Output Indicator 2.3: Conditional food transfers received by NUSAF II participating households in Karamoja (metric tonnes, attributable to DFID)

A total of 9,878 metric tonnes of conditional food transfers were received by participating households in Karamoja, against a cumulative target of 14,964. However, the evaluation found this milestone to be overly ambitious due to (a) challenges of unpredictability - The food transfers were not predictable. Six cycles of work were planned in each location but in practice only four happened. There were break points in public works in December 2011 and works only commenced after April 2012 (b) The work was undertaken on a project-by-project basis which took time to design, plan and attain approval (rather than a pre-determined list of projects whose implementation is sequential) and (c) Targeting – NUSAF II was not able to absorb newly identified vulnerable people onto the eligibility list (targeting was conducted in 2010) e.g. new widows, the recently orphaned households, households that are caring for orphans, some polygamous households.

The component evaluation determined that increasing productivity and beneficiary livelihood security through conditional transfers was effective. Implicit in the NUSAF II objective was behaviour change, reflecting a move away from dependency on food aid by the people of Karamoja to developing sustainable approaches to livelihoods. In the short period since food/cash for work was introduced by people in Karamoja demonstrated that they are willing to work and that the issue is opportunity rather than dependency.

Lessons and how these have been shared

- Polygamous households require disaggregation in targeting. A man may have as many as six wives with each are responsible for her own household; polygamous wives do not share amongst themselves so it cannot be assumed that all family members of that household are benefiting.
- Communities were insufficiently involved to address exclusion e.g. if you weren’t home when the first survey was completed, were a recently returned IDP, recent orphans, or those whose circumstances had recently deteriorated. Working primarily with local councils was also perceived as politicising the process.
- Facilitating behavioural change is a complex, time-consuming process, especially among a population that has such a low literacy rate (10%). Government capacity was too limited to implement an approach which required time, good communication, and considerable field work.
- Trade offs between livelihood investments must be considered. For example, where land is brought in to agricultural production it reduces land traditionally available for grazing in stress periods.
- Community gardens are productive assets but much more time needs to be invested in transferring skills that are learnt in community gardens to the household plots.

Output Indicator 2.4: Number of OPD consultations and treatments in the 31 PNFP facilities per year (disaggregated by male/female, and by age-group)

Health Partners International (HPI) and Montrose Ltd were contracted to design and manage a programme (NUHealth) to incentivise improvements in health results through a results based financing mechanism. DFID’s total contribution was £12.1m between 2011 and 2015. The objectives of NUHealth were:

- to improve the availability of essential medicines in private-not-for-profit health facilities;
- to improve the quality and quantity of services provided by private-not-for-profit health facilities; and,
- to test a new way of financing private-not-for-profit health facilities.

The facilities were divided into a “treatment” group of 21 facilities receiving results-based financing (RBF) and a “control” group of 10 facilities receiving traditional input-based financing. Payments to facilities in the treatment group were increased if there were improvements to the quality and quantity of maternal and child health care provided, whereas the control group was financed irrespective of the services provided.

NUHealth produced good process learning for the Ugandan context on implementation of a Results Based Financing RBF, and delivered significant health services. The project improved the skills of district health offices to supervise and measure service delivery in a systematic way and the implementing partner contributed important policy inputs to key debates. The project attracted international attention and is documented as a case study in DFID’s Payment by Results Strategy.

Key achievements were:

- separation of roles and responsibilities of purchaser, provider and verifier of health services improved accountability;
- some behavioural change in the RBF group: considering new ways to attract patients, including dissemination of information and reduction of user fees for key services;
- Delivered of significant health services with reduced or eliminated user fees.
- Close supervision resulted in significant gains in quality and quantity of health services and encouraged innovation. Stock-outs of essential medicines in the facilities in the pilot have fallen and the management of medicines by health facilities has improved.
- Policy inputs to the debate on national health financing and results-based financing of health services.

Key challenges included:

Difficulty in incentivising RBF health facilities where other, non-RBFresources were available.
- Input-based funding may prove to be less effective than results based funding but also less costly to manage. Predicting the costs of managing results-based funding at scale is difficult.
- Staff attrition and turnover has led to a constant need to refresh understanding of how the facilities are reimbursed. The poor financial skills of new staff have led to poor compliance by facilities, which has resulted in these facilities either losing funding or having to re-submit reports.
- Poor data collection by health facilities made results verification time-consuming.

Lessons learned and how these were shared:

Lessons from the programme were disseminated at a national event in September 2015, and across DFID. The learning will serve as a good basis for design and implementation of RBF, particularly in the health sector. These lessons include greater transparency and analysis of value for money questions, especially focused around the costs of managing the results-based financing component of the.

Recommendations for future programming included:

- Implement a smaller trial in a new region(s) in lower-level health facilities with a mixed IBF/RBF where inputs would include a credit-line for drug supply and clinical care interventions (training/ continuing professional development/ supportive supervision/ monitoring in clinical care).
- Scale the lower-level facility model up into several regions nationally and with strong M&E framework for adaptive programming (verification data makes RBF ideal for adaptive programming).
Random Control Trial: larger scale-up with more rigorous RCT model matching facilities and then randomising to different implementing models (RBF/IBF/mixed).

OUTPUT 3: The private sector is revitalised and accessible employment opportunities are created.

Output 3 score and performance description:

A - Outputs met expectation
Overall Risk: Medium
Impact Weighting: 25%

OUTPUT 3	Output Indicator 3.1	Baseline 2009	Target (2010)	Achieved
The private sector is revitalised and accessible employment opportunities are created	Number of applications for small grant scheme received and approved	0	1,200 (received) 1,000 (approved)	Not Achieved / 626 (received) 426 (approved)
		Source: PSFU management records; Independent Evaluation Report on Youth components, 2016
	Output Indicator 3.2	Baseline 2009	Target (2015)	Achieved
	Number of YDP youth trained in a core vocational skill(s) relevant to local market opportunities	0	15,400 (50% female)	Achieved / 15,875 / (49.7% women) / 6% with disabilities / (Reached by April 2016)
		Source: PSFU management records; Independent Evaluation Report on Youth components, 2016
	Output Indicator 3.3	Baseline 2009	Target (2015)	Achieved
	Youth trained in Business Enterprise Start up Tool (BEST)	0	10,000, revised up from 8400 in July 2015	Achieved / 13,377 youth / (a total of 15,920 trained, of whom women, 6,841) / Reached by April 2016
		Source: Independent Evaluation Report on Youth components, 2016
	Output Indicator 3.4	Baseline 2011	Target (2015)	Achieved
	Percentage of respondents perceiving they have access to increased economic opportunity [disaggregated age/gender]	Acholi: 32% [M: 17%, F:15%]; Lango: 27% [M: 13%, F:14%]; West Nile: No data available; Karamoja: No data available.	Acholi: 62% / Lango: 57% / West Nile: 44% Karamoja: 39%	Missed: / Acholi: 38.4%; / Lango: 38.8%; / West Nile: 22.7%; Karamoja: 34.5%
		Source: Advisory Consortium on Conflict Sensitivity

DFID’s total support under Output 3 was £18,688,370: for a grant scheme to businesses, two youth training schemes targeting 29,000 youth, and a survey on perceptions of access to economic opportunity. The business grant scheme (Output 3.1) was suspended early in 2012, linked to the OPM corruption scandal, and subsequently cancelled in 2013 following a negative review of its progress to that point. The two youth training schemes (Outputs 3.2 and 3.3) were completed successfully in 2016, and included capacity improvements delivered to over 30 training institutions, as well as 29,000 people trained. The findings of an independent evaluation were positive, estimating a return of £15m for the £10.5m spent, excluding ‘social’ benefits. The fourth component was dropped in 2015 after the perception tracking methodology was assessed as unreliable and expensive to collect.

Indicator 3.1: Number of applications for small grant scheme received and approved

The purpose of the grant scheme was to support the creation and expansion of new businesses to drive job and income growth in Northern Uganda. Matching grants (requiring an equivalent 50% investment from the firm) were given to business enterprises to enable them to pursue investment opportunities in a region recovering from conflict. An external review of the component identified weaknesses in beneficiary selection, and process management, and limited impact, on which basis the decision not to restart the component was taken. The project and its funds were managed by the Office of the Prime Minister in partnership with PSFU.

The programme was suspended in November 2012. Activities were reactivated briefly under the direct management of the Private Sector Foundation of Uganda (PSFU) in July 2013 to cover only outstanding commitments to beneficiaries, before final closure. A total of £4,489,011.07 was disbursed in grants out of a planned total of £10.5million, and £986,706 was spent on management and administration costs. The final payment of £1,347,037 was approved in April 2014.The total cost of DFID’s contributions to PSFU was £5.8 million (Small grants scheme + payment of liabilities incurred prior to the funding freeze to the Office of the Prime Minister)[3].
[3] This figure comprises a total disbursement of £6.996m, but of which PSFU returned 7.939 billion Uganda shillings due to early closure of the project. This returned amount was never re-converted into GBP but re-disbursed to other projects from DFID Uganda’s local Uganda shilling account. The GBP value of the retuned amount is calculated as £1.950m, based on the exchange rate of the days on which the returned monies were received.

The 2014 annual review noted that PSFU had given grants to many businesses with insufficient assessment of their business expertise or the viability of the enterprise, and that monitoring and evaluation of had not yet produced strong evidence of efficacy or impact. Results in terms of jobs created were reported by the implementing partner but were found not to be credible by the 2015 annual review. Equipment purchased through the project had in some cases not been utilised due to problems with land disputes and electricity connections.

Lessons learned and how these were shared:

The key lesson of the business grant scheme relates to the costs and risks of this type of programming, and the very significant oversight and management systems required to manage them well. Should similar schemes be proposed in the future, the designers should look closely at established challenge funds (such as Africa Enterprise Challenge Funds, or ABiTrust, both relevant to Uganda) to copy management systems, learn lessons, or even distribute funding through them rather than create a new vehicle.

Subsequent to the 2014 Annual Review, PSFU published an End of Project Report (QN: 4939970) which reported that the project created 97,430 indirect jobs. However, the results figures are not credible as they rely only on estimates provided in grant applications by firms (see below for validation exercise during a field visit. The report noted the following lessons:

- Upfront financial contributions from beneficiaries improved commitment and success compared to those made in kind.
- Working through government (civil servants and politicians) threatened to derail the project.
- Conflict assessment was required to avoid precipitating conflict drivers.
- Business Development Services were important to build the capacity of enterprises to operate competitively.

The report also made some strong recommendations with regard to management of the suspension. These included the need for the implementing agencies’ reputation to be safeguarded in the event of suspension, for example, by including clauses in PSFU/grantee agreements with regard to the possibility and impact of suspension of funding.

DFID Uganda undertook a field visit in April 2015, to some assess the impact of the grants. The following conclusions were drawn:

- All five beneficiaries had somewhat credible business plans, and there was no evidence of misappropriation – equipment purchases were verified in place.
- Four out of five had suffered as a result of poor implementation and planning (both by themselves and by project implementers) – in respect of receiving delivery of equipment before other elements to operationalise it were in place (such as land title and electricity).
- Two whom received equipment had not yet operationalised it, indicating substantial risk of future benefit, and invalidating the results reported based on their grant applications.

Indicator 3.2: Number of YDP youth trained in a core vocational skill(s) relevant to local market opportunities

Following the suspension of financial aid to Uganda in 2012, DFID reprogrammed PCDP’s Youth Development Programme (YDP). It was subsequently delivered through Volunteer Service Overseas (VSO). Strong performance from YDP ensured PCDP surpassed the targets of 15,400 (15,875) youth trained in vocational skills.

A key issue was whether or not the skills provided are ‘market-relevant’. Overall, interviews with beneficiaries suggest that they are, and significant steps have been taken with Vocational Training Institutes to build their understanding of how to identify and respond to ‘market relevance’ in choice of course and curriculum, and in the delivery of ‘entrepreneurship’ skills.

Key Lesson learned:
A key lesson on youth skills training is the level of effort and capacity required to ensure data quality. While large amounts of data are available on over 25,000 youth, data cleansing and checks by independent evaluators revealed quality and content gaps that limited the strength of conclusions that could be drawn from the projects. This was despite a very significant effort by implementing partners to ensure strong monitoring and data systems, which were in many respects better than usual.

Indicator 3.3 (Youth trained in Business Enterprise Start up Tool (BEST)

The Northern Uganda Youth Entrepreneurship Programme (NUYEP) implemented by Enterprise Uganda (EUg) in partnership with Youth Business International (YBI). The NUYEP programme selected people who were willing to invest an initial amount of their own money to receive the Business and Enterprise Start-up Tool (BEST) training before subsequently implementing a self-selection process through which the ‘high flyers’ received more intensive levels of support. This component indicator surpassed the target of 10,000 with 13,337 youths trained, including 6,841 women.

The External Evaluation report of YDP and NUYEP Programmes (5698969) noted the lessons learned as indicated below:

In addition to the lessons learned documented on pages 2-4:
The review points to much greater potential for cross-project comparison with other existing similar projects. Best practices can be identified and usefully shared, delivered through the high quality and innovative work undertaken by implementing partners. Work on technical college board governance, data collection, management information systems and disability deserves wide recognition and replication.
- Future grants projects should be very carefully considered, and will require substantially stronger design and implementation systems. Alternative approaches to delivering capital to key sectors or regions should be considered instead – such as market development approaches, or by incentivising or subsidising the financial sector to target problems instead.
- Carefully consider whether a skills training approach will add value, given costs and issues of replicability and sustainability, and the scale of the problem to be tackled. Ensure that low cost options are fully explored. These might involve models delivering volunteer mentoring to businesses (such as the ‘Grow Movement’ and elements of the Enterprise Uganda model), or setting up school business clubs (see the ‘Educate!’ model).
- If a skills training programme is to be established, it is likely amenable to a Randomised Control Trial evaluation. Given the lack of quality data and evidence on the additional, and attributable value of skills training, an RCT approach is strongly recommended. Project designers should demand stretching targets on gender and inclusion.

Indicator 3.4: Percentage of respondents perceiving they have access to increased economic opportunity [disaggregated age/gender]

This result is monitored by the ACCS (a consortium of three organisations; Safer-World, International Alert and Refugee Law Project) whose mandate was to develop Peace and Conflict Indicators (PCIs), to measure the peace dividends accruing to the implementation of the PRDP and the PCDP. Key among the PCIs was the ‘Percentage of respondents perceiving they have access to increased economic opportunity’. DFID signed an Accountable Grant with the Refugee Law Project (RLP) in May 2010 for £2 million. In October 2011 the total amount of funding was adjusted to £2.875 million, and in September 2013 a further revision was agreed taking the total amount of funding available to £3,641,539 with an end date of March 2015.

The PCI (2014) noted that an average of 33.6% of all the survey respondents in the four regions of Acholi, Lango, West Nile and Karamoja did not have access to increased economic opportunities. This percentage was highest in Lango (38.8%); followed by Acholi (38.4%); Karamoja (34.5%) and lowest in West Nile (22.7%).

Positive drivers:
The largest number of respondents who had access to increased economic opportunities attributed it to increased business activities in their localities (39.7%), followed by local government initiatives (17.4%), while improved security (17.1%) was also mentioned as a driver. However, it should be noted that the majority of respondents from all surveyed regions (54.1%) rated the level of business vibrancy in their communities as low. Only 7.5% of the respondents overall rated the level of business vibrancy in their communities as high.

In the qualitative evidence, positive perceptions of increased economic opportunity were also limited. However, according to the narratives, strong potential was commonly observed in agricultural activities, influenced by a sense of abundant land and favourable conditions for livestock and crop farming. This was supported by community-level survey results showing that the most common economic opportunities were agricultural (30.9%). Moreover, a large majority of respondents (72.9%) from all regions reported having access to land that they owned, while 12.8% had access to rented land, and only 10.3% had none. Indeed, the most common current income activity was stated as crop farming (39.7%), followed by business in market stalls, kiosks or roadside vending (13.1%) and selling of casual labour (12.5%).

Negative drivers:
Even among those respondents who reported that there were sufficient economic opportunities in their communities, 46.7% felt that not everyone was able to take advantage of them. Failure to access credit was the reason most advanced (24.5%), followed by laziness/alcohol (16.8%) and lack of qualifications (13.2%).

In the qualitative evidence, the primary reasons advanced for a lack of access to increased economic opportunities were: dissatisfaction with government interventions due to inappropriate guidelines and funding restrictions; and lack of agricultural sector development despite widespread perceptions of its economic potential.

Lessons learned how these were shared:
The key lesson from this relatively minor sub-component focused on tracking perceptions of economic opportunity is that meaningful and cost effective indicators are extremely hard to operationalise in a very poor, informal economy; much more evidenced-based work is required before attempting something similar.

- When functioning well, consortia can strengthen programme performance in a variety of ways. However, there are a number of key criteria for effective functioning of a consortium, which if absent, can undermine performance. These include: a shared understanding of the programme scope, foundational concepts, theories of change and benefits of consortium working amongst members; clear lines of accountability for performance and robust management structures (including financial management) and oversight.
- The PCI methodology was thorough but offered relatively poor Value for Money (VFM) and should have been accompanied by a more robust and targeted advocacy strategy (as should other ACCS products).

OUTPUT 4: Government, civil society and communities can engage actively in peacebuilding and reconciliation.

Output 4 score and performance description:

A+ Outputs moderately exceeded expectation
Overall Risk: Medium
Impact Weighting: 25%

OUTPUT 4	Output Indicator 4.1	Baseline 2009	Target (2016)	Achieved
Government, civil society and communities can engage actively in peacebuilding and reconciliation	Number of interventions and systems under PRDP modified to make them more conflict sensitive	0	4	Achieved / 4 (clustered around four conflict areas of land and natural resource conflicts, transitional justice, youth disenfranchisement, and sexual and gender based violence)
		Source: Advisory Consortium on Conflict Sensitivity PCI report 2014, External Review report of ACCS, June 2014
	Output Indicator 4.2	Baseline 2010	Target (2016)	Achieved
	Number of men and women reached by legal aid service supported by DGF in PRDP districts (DFID attributed)	679,273 women and men reached by the Legal Aid Basket Fund partners over a five year period (2004 -2009)	2,000,000 women, children and men reached (direct) / [376,000 attributed to DFID = 18.8% contribution to RJP component] / (additional 6,000,000 reached by PLA’s media outreach work). / [1,128,000 attributed to DFID =18.8% contribution to RJP component ]	Achieved / Cumulatively, 4,975,184 men and women have been reached by DGF legal aid partners by December 2016. / Direct beneficiaries – 468,490 (100,868 – Female; / 367,622 – Male) / Indirect beneficiaries – 4,506,696 / Total - Attributable to DFID (18.8%) – 935,334.59 / Direct beneficiaries attributable to DFID (18.8%) – 88,076.12 / In-direct beneficiaries attributable to DFID (18.8%) – 847,258.85
		Source: Evaluation of the LABF Report (2010); JLOS Semi-Annual and Annual Performance Reports; DGF Periodic reports and Implementing Partners Reports; Mid-Term Review report, 2014, Thematic Evaluation of RJP, April 2016
	Output Indicator 4.3	Baseline 2011	Target (2016)	Achieved
	Number of traditional conflict resolution informal groups and institutions supported by DGF partners in Northern Uganda	Selective provision of support to institutions in Northern Uganda and conflict-prone regions	10 trainings and 43 institutions	Achieved. / 15 trainings and 67 institutions / Additional 50 formal and informal institutions were strengthened through 8 different trainings.
		Source: JRP, AYINET, RLP, CEWIGO and ACCS reports
	Output Indicator 4.4	Baseline 2012	Target (2015)	Achieved
	Proportion of respondents perceiving decrease in levels of competition and grievance between PRDP region and between north and south	Acholi:34% [M:18%, F:16%]; Lango 40% [M:22%, F:18%]; West Nile: 34% [M:19%; F:15%]; Karamoja: 30% [M:20%, F:10%]	Acholi 45%; Lango 50%; West Nile 45%; Karamoja 40%	Missed target / Grievance between PRDP region / Acholi 28.8% / Lango 22.2% / West Nile 27.8% / Karamoja – 43.1%
				Grievance between North and South / Acholi 30.6% / Lango 29.9% / West Nile 39.5% / Karamoja – 32.2%
		Source: Advisory Consortium on Conflict Sensitivity PCI 2014 (QN 5019016); External Review report of ACCS, June 2014

Indicator 4.1: Number of interventions and systems under PRDP modified to make them more conflict sensitive

This result is monitored by the ACCS (a consortium of three organisations; Safer-World, International Alert and Refugee Law Project) whose mandate was to make PCDP conflict sensitive and in so doing make PRDP achieve peace-building aims. The project budget was £3,619,962 over six years (2010-2015).

ACCS had three major objectives: monitoring the extent to which interventions under the PRDP, particularly those funded under DFID’s Post-Conflict Development Programme (PCDP), succeed or fail in achieving peacebuilding aims (International Alert); contextual analysis of the overall recovery process (conflict indicators, issues and dynamics) to provide early warning as and when necessary (RLP); and evidence-based advocacy, targeted recommendations, and technical support to improve the recovery and peacebuilding impact of the Office of the Prime Minister (OPM) and other PRDP stakeholders (Saferworld). Each consortium agency led on one output, supported by the other partners.

The freezing of UK Aid in late 2012 had major impacts on the operations of the PCDP and, as a consequence, the ACCS, had challenges in engaging with the OPM. Effective dialogue and interactions with the OPM were almost impossible since the breaking of the 20102 OPM corruption scandal.

The ACCS final external review, June 2014 (QN 5170989) recognised that outcomes were most evident at the local level. ACCS was found to have contributed to an understanding, responsiveness and engagement amongst District Local Governments and other key stakeholders in relation to four key conflict drivers highlighted in the Conflict Analysis (land, youth, gender and transitional justice), and an increased understanding of the principles of conflict sensitivity.

ACCS engagement with national level policy frameworks and efforts to build linkages between national and local level stakeholders also gained some traction. For example, ACCS contributed to an increased emphasis on youth and conflict within the National Youth Policy and a broader understanding of Transitional Justice (TJ) issues within the TJ Policy. How far policies will translate into actual implementation and change, however, remains unclear.

In general, the Conflict Analysis was found to have been influential in framing a shared understanding and discourse on the key conflict issues (in particular the four key conflict drivers) amongst state, non-state and political actors at the national, district and community level. The PCIs also contributed to the evidence base on peace and conflict issues and trends in Northern Uganda and their relationship to development interventions. However, PCI reports are dense with recommendations of variable quality and specificity. In general, the external review noted that ACCS research products were insufficiently accompanied by a robust advocacy and communications. These factors, along with delays in producing the reports tended to reduce their value, relevance and potential.

Engagement at a national level on land conflict issues has increased commitment to addressing local land issues in a conflict sensitive manner amongst a range of national level stakeholders (Uganda Wildlife Authority (UWA), Ministry of Land, key investors). Specifically, Saferworld supported the ability of key stakeholders in Nwoya and Otuke to manage land issues in a conflict sensitive manner with some evident success in reducing tensions. Their accompaniment approach has been valued for being collaborative and pragmatic, placing local government in the lead and helping them build trust with communities and engage relevant stakeholders In Apaa (Amuru district), Saferworld’s intervention has shifted the attitudes and behaviour of a range of stakeholders, encouraging actors from both sides of the border to work together with a positive and consultative approach to border demarcation.

However, ultimately success has been limited. This was in part due to Saferworld’s inability to sustain support and monitor the situation as events unfolded (border demarcation) in order to build confidence amongst key communities. However, Saferworld also required a deeper understanding of the key drivers of conflict and dynamics among factors and key actors (including those entrenched political interests at a national level who use violence for political ends) and broad range of approaches to addressing these. A conflict sensitivity approach is not sufficient. Longer term engagement is required to bring about significant change on land issues and the time was too short to make a sustained difference. Any gains remain fragile.

The external review also found that progress in particular in the first two years of implementation was limited, not living up to its potential or expectations. This is largely attributed to delays in producing a foundational conflict analysis, insufficient traction gained with key stakeholders including OPM, and an unclear functional division of labour including a management model that did not include clear lines of accountability. The OPM case in 2012 further complicated the picture, with significant changes in many PCDP interventions as a result of the aid suspension and suspension of many PRDP and PCDP projects. The external review also notes that in its initial phase, the ACCS partners International Alert, Refugee Law Project and Saferworld, did not hold a common understanding of the concept of conflict sensitivity, or indeed the theories of change behind the intended programme outcomes/impact.

Over its project period, the ACCS project underwent a number of adjustments to reflect:
- Changes in priorities in the Northern Uganda recovery process;
- The transformed relations between development partners and GoU following the 2012 OPM corruption scandal; and
- A re-focusing of the work of the Consortium following the completion of a Conflict Analysis in 2013.

A key challenge that the Consortium faced was the ability to exert influence on national level institutions. This is partly due to the lack of PRDP coordination by OPM following the suspension of financial aid. It was also due to the increased constraints on NGOs space.

Indicator 4.2: Number of men and women reached by legal aid service supported by DGF in PRDP districts

This indicator is drawn from the Rights, Justice and Peace (RJP) component of the Democratic Governance Facility (DGF), which is a multi-donor basket fund. The total development partner contribution to RJP component was £35,092,100. UK’s total contribution to the DGF basket fund was £ 6,600,000 (representing 18.8% of contribution to the component) covering the period 2011-2016. The purpose of this component is to support civil society organisations to provide legal aid services to the poor and vulnerable people as well as to work with Government of Uganda on the development of the National Legal Aid Policy and Law.

DGF led by DANIDA conducted an evaluation of DGF phase I, November 2016 (QN 5648055), although an EQUALS quality assurance process downgraded this from an evaluation to an internal review.

The review recommended that a legal aid strategy should be developed in which legal aid continues but is clearly targeted to vulnerable groups especially indigent women, and at the same time a commitment to lobby government and eventually phase out the support. It further highlighted that like other DGF partners and programmes, the Legal Aid Programme (LEAP) is challenged by a lack of sustainability. The National Legal Aid Policy (NLAP) is still pending after four years. The LEAP contributes to closing an important and critical gap in the formal justice system and is thus highly relevant to the GoU and the political economy. However, there are critical gaps within the criminal justice sector chain, such as constrained police resources and performance in investigations, lack of prosecutors and judicial officers and continued backlog of cases and perceived corruption and mistrust of a number of the JLOS institutions. Prisons also continue to be underfunded by the GoU, hence overcrowded with almost no correctional services and little prospects of prisoners’ rehabilitation. The review notes that there is therefore a need to address the root causes of the weaknesses within the formal justice system. The issue of sustainability within the justice system (formal and informal) needs to be raised at a strategic level, by the DGF Board (Heads of Mission).

Key achievements include:

By June 2016, 4,975,184 poor, vulnerable and marginalised people accessed legal aid services from across 79 districts.
Legal aid contributed to reducing the prison remand population, through support to Legal Aid partners and Paralegal Advisory Services. DGF support also facilitated LEAP partners’ work around the release of 18,155 from police custody and prison. This included assistance to obtain police bond, court bail and assistance to get community service orders in lieu of imprisonment. An addition of 79,000 remand inmates has been released since 2012 with the support of DGF partners.
Significant improvement in Partners’ coordination, capacity, service quality and accessibility: The partners have become better organised and collective under their umbrella coalition, the Legal Aid Service Providers’ Network (LASPNET), leading to higher standards in service provision.
Improved Government Capacity (Uganda Law Council): ULC used DGF support to build its capacity through training and additional staff to enforce accreditation requirements, standardisation and establishing para-legal regulations. Prison de-congestion: They also caused the recovery of UGX 429,188,974 on behalf of poor and vulnerable persons for child support and maintenance, whilst unpaid wages, compensation for unfair termination, terminal benefits amounting to UGX 959,770,756 were recovered on behalf of poor and vulnerable workers.

Much more than just legal aid: The RJP component through which legal aid outreach has been delivered was broader covering two other objectives of promotion and protection of human rights as well as transitional justice.

Human rights:
Support to the Uganda Human Rights Commission (UHRC) resulted in community sensitisations that reached over 6 million people across Uganda. DGF supported 338 schools and universities to form human rights clubs to cultivate a culture of respect for human rights and tolerance targeting young people as the next generation of leaders. The International development Fund (IDF) funded sub-grantees were able to refer more than 2,000 cases to the relevant authorities and to access legal aid. Human rights NGOs reached a total of 8,260,000 Ugandans with human rights knowledge. Since 2012, UGX 4,185,092,000 has been awarded to human rights abuse victims. In the same period, 36,347 cases of human rights violations were handled by the UHRC and EOC but only 43% have been resolved. There are concerns around failure by the UHRC to play an effective watchdog role. Another concern is around GoU’s failure to pay awards ordered the human rights tribunal in favour of victims of violations.

On the advocacy side, DGF supported NGOs such as the African Centre for Torture Victims (ACTV) that worked together with UHRC for the passage of the Anti-torture law. Another group of Human Rights Defenders, Chapter 19 successfully petitioned for the nullification of the Anti Homosexuality Act (AHA) of 2014.

Transitional Justice:
DGF partners initiated mediation meetings and talk shows led by eminent persons, including religious and political leaders in the Rwenzori region. Through these efforts, evidence based information was generated and used for engagements and the call for peace, reconciliation and promoting peaceful co-existence. As a result of DGF support to the RLP, under TJ, 4,582 LRA war victims were profiled with 2,979 receiving medical repair and psycho-social support and leaders were trained in conflict sensitive leadership to better respond to the needs of the people in Northern Uganda. The results achieved under RJP can also be attributed to joint donor efforts that together with the UK provided a total of £35,092,100 to implement RJP. The UK burden share to the RJP component stands at 18.8%.

Indicator 4.3: Number of informal/ traditional conflict resolution informal groups and institutions supported by DGF partners in Northern Uganda

Progress against this indicator is measured against information provided by the RJP partner reports.

In 2011, DGF partnered with Ker Kwaro Acholi (KKA) – the traditional cultural institution comprising clan chiefs but headed by a Paramount chief in Acholiland, Northern Uganda. DGF supported training of cultural leaders in conflict mediation and dispute resolution to play a natural role as mediators, pacifiers and bastions of justice in post conflict Northern Uganda. The support also focused on gender education to increase gender and security sensitivity among the cultural leaders. However, in 2014 DGF took a decision to cease support to KKA when it failed to fully account for our funding.

DGF redirected delivery against this output indicator by supporting NGOs to work with selected clan leaders in Northern Uganda without channelling money directly to the KKA. For example, one RJP partner, the Centre for Women in Governance (CEWIGO) has implemented a project to monitor Uganda’s UNSCR 1325 commitments and ensuring it accounts for commitments on women’s peace and security in the region. CEWIGO worked with four district local governments to and help them develop clear strategies and Local Action Plans to promote women’s rights and women’s peace and security in traditional set-ups.

Notably, over the years, there was a noted a decline in satisfaction with traditional institutions in Lango and Acholi, and an increase in the level of satisfaction with those in Teso and West Nile. The DGF attribute the decline in the level of satisfaction in Acholi and Lango to the internal clashes in the cultural institution cultural institution KerKwaro Acholi (KKA) and in the Lango Cultural Foundation (LCF). KKA has faced considerable criticism internally and from external stakeholders alleging mismanagement of funds (DGF has ended its partnership with them over this issue). Internal troubles have reduced the credibility and respect for the respective institutions within their constituents. The declining satisfaction with the role of traditional institutions in the transitional justice process may be related to a declining trust in traditional institutions overall.

ACCS also launched its Compendium of Conflicts: the first attempt in Uganda at a definitive compilation of conflicts to inform the debate and healing process.

There have been challenges reported associated with political pressure on CSOs especially those working on sensitive issues at national and district level, which in recent months has become more acutely clear with developments regarding passing of the NGO Act in November 2015 which introduces more checks, controls and tighter monitoring of CSOs. DGF-funded interventions should work more closely together to monitor any constraints in the operating environment and seek high level engagement from DGF and its donors where necessary.

Indicator 4.4: Proportion of respondents perceiving decrease in levels of competition and grievance between PRDP region and between north and south

The ACCS Conflict Analysis report (QN 5703659) provided a comprehensive analysis of conflict drivers that have the potential to undermine development and peacebuilding efforts and these include:

Regional instability and border conflicts (e.g. Uganda-DRC, Uganda - South Sudan, Somalia, CAR).

Perceptions of North-South economic and political divide that have not been addressed (e.g. ‘National cake’ vs Equal opportunities). The PCI demonstrates that 63.7% of people in 21 districts in the North (PRDP region) perceived other regions to have more benefits and investments from Government than their own regions. PCI 2014 shows decrease in percentage of respondents reporting that Government is doing enough to breach the gap between north-south (56% in 2013 to 47% by 2014).

Communities consulted by ACCS believe that the politicisation of PRDP implementation by districts and community leaders is to blame for the conflicts and tensions, which have undermined solidarity and cooperation between communities in the North. Growing North-South Poverty Gap: Northern Uganda growing poorer by the day. 44% of people in Northern Uganda live below the poverty line compared to 20% national average. The number of people living in poverty in northern Uganda has risen in the last 2 decades from 2.4 million in 1992 to 3.6 million in 2013 against a decrease in national poverty headcount (Oxford Economics – Northern Uganda Economic Recovery Analysis Phase II, Nov. 2014).

Lessons learned:

Perceptions of neglect arising from poor service delivery and under-developed infrastructure cannot be resolved in the absence of post-conflict truth, reconciliation and transitional justice processes through which the relationship between state institutions and the people can be repaired. They are being deepened by emerging conflicts over natural resources and property (notably oil, forest and minerals), land and boundary disputes in areas of return, and a proliferation of new districts, a process that appears to weaken governance rather than bringing it closer to the people.

The inadequacy of disarmament, demobilisation and reintegration programmes, when juxtaposed with high levels of youth unemployment and disenfranchisement, gives rise to widespread fears that this sector of the population may engage in armed violence. Moreover, the rapid socio-economic changes that the region has undergone since the cessation of hostilities in 2006 impacted upon gender relations, as shifting roles have contributed to high levels of domestic violence and SGBV, which in turn continue to drive conflicts within families and communities.

Increasingly militarised and violent resource competition was/is fuelling conflicts in different parts of the country (e.g. land-grabs in Amuru, gazetting of game reserves (Lakang & Apaa), Mabira Forest, oil exploration-related displacement, Otuke district, etc.).

Poor governance and democratic deficits are fuelling tensions within and between government institutions (e.g. 2016 Elections/contested Electoral Reforms 2015, Term & Age limits debate, political gerrymandering, Intra-party conflicts, emergency of militia/vigilante groups, South Sudan refugees influxes).

Growing politicisation of ethnic identity (e.g. Bakiga-Banyakole tensions, creation/demand for new districts e.g. Karamoja, Bunyoro/Masindi, MP attempted suicide 2015 etc.) is fuelling tension.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Output 1:
For NUSAF II, the Aide Memoire Mid-term report of OPM/NUSAFII (QN 5709364) highlighted increases in administration costs due to: (a) creation of more 15 independent administrative units (districts and sub counties) by Government thus increasing the number from 40 to 55 district in the project area; (b) recruitment of 55 Engineering Assistants to support the capacity of the districts and supervision of construction works at the communities; and (c) additional staff to meet the needs at the NUSAF2 Technical Support Team. The major costs drivers under output 1 included: trainings, management fees, staff costs, office administration overheads, travel expenses, programme evaluation costs, conferences/workshops, office equipment, information and technology equipment, and construction of houses.
It is worth noting that during the course of 2012, the contract with HPI/Montrose to implement the PNFP programme increased from £6.5m to £10.5m. The reason cited for the increase was the unexpectedly complex nature of the programme (which was amended to include a control group, in order to allow a robust impact evaluation of results based financing to take place) as well as the lower than expected capacity of the PNFPs in Northern Uganda.

Output 2:
The key cost driver was cash grants. NUSAF II (WB) provided cash payments in return for public works participation at a rate of Ush 4,000/= (£1) per day. The number of hours worked for food/cash for work projects in Karamoja (attributable to DFID) were 23.9m short of the PCDP logframe target of 28m labour hours. The shortfall in target was due to competition of existing PWPs funded by KALIP, EDF funded PWP. KALIP programme paid UGX 7,000/= (£1.20).

Output 3:
Youth: Key cost drivers in the youth skills components relate largely to the expenses of training, driven by numbers of trainees. The cost performance was strong, as the output targets of numbers of beneficiaries trained were revised upwards throughout the project by both VSO and, particularly Enterprise Uganda. This was partly to do with lower than expected costs, but also good planning to exploit sunk costs to achieve greater numbers at low marginal costs.

Output 4:
RJP: Key administrative (PMU) costs: office rentals, assets procurement, in-country travel for monitoring and evaluation and vehicle maintenance costs. Other cost drivers include, capacity development of partners and audit fees. DFID is one of eight partners contributing towards the administrative costs of the DGF. A total of 7% of DFID’s grant was allocated to administrative costs. These costs have been judged to be good VfM and compare favourably with other implementing partners used by DFID such as the UN or World Bank.

Key DGF Partner costs: Under RJP, legal aid work presented the highest costs. Specifically, drivers include: support for capacity building; human resource to deliver legal aid and other running costs including rent, stationery and fuel expenses. However, support to legal aid partners to increase the geographical scope of their services has contributed to bringing legal aid services nearer to beneficiaries and reduced the cost and time for accessing justice which in turn reduces the potential for escalation of disputes and attendant effects, including turning disputes into criminal cases. Whereas legal aid service delivery is expensive, the benefits related to empowerment and legal support especially for poor and vulnerable people exceeds the cost.

Other costs include investments in research and development of regulatory framework for legal aid which are intended to enhance standards in delivery of legal aid services.

VfM performance compared to the original VfM proposition in the business case
The original Programme Memorandum made the assumption that the total investment of £100m would deliver economic benefits worth 2.5 times the cost of the programme, based on the following assumptions:

1. Improvements to health and education outcomes due to construction of health workers and schoolteachers houses
2. Improvements to governance conditions (reduced leakage through corruption)
3. Jobs created through private sector grant scheme
4. Increased employability and opportunities for young people
5. Social support provided to the extremely vulnerable

Table 1: Cost benefit analysis (Original Programme Memorandum)
	Costs / (£ m)	Discounted Costs	Discounted Benefits	Benefit : Cost Ratio	Indicator
Total Benefit			647.7		GDP
Education
Health	27.20	22.9	59.7	2.6	Primary school years
Governance	27.20	22.9	64.0	2.8	DALYs - Disability Adjusted Life Years
Grant Scheme	9.80	8.2	31.0	3.8	Diversion reduced
Youth Development	15.00	10.9	28.7	2.6	ERR
Social Protection	12.15	10.2	22.7	2.2	ERR
Other	4.00	3.4	8.1	2.4	Marginal income utility
Indirect Benefits	4.65	4.5
Total	100.00	83.0	214.2	2.5

Without revisiting the detailed cost benefit analysis it is clear that some of these assumptions changed, whilst others remained valid.

On Assumption A (above) – improvements to health and education due to construction of health workers and school teachers houses – There isn’t evidence to support assumption A and therefore this project completion review is not in position to affirm that this assumption still stands because there was no specific impact evaluation carried out on the NUSAF houses for teachers and health workers. An impact evaluation would have tested the assumption that increasing the number of houses for health workers and school teachers really does result in improved health and education outcomes (e.g. reduced absenteeism of health workers and teachers, an improved learning environment, increased literacy levels, etc.). The evaluation (QN 5574787) provided some limited evidence that RBF was effective in small health facilities but due to the design of the study the evaluators were unable to control for other influencing factors. On work with PNFPs, the project completion review is unable to conclude that the improvements in access and infrastructure in small health facilities were purely results of RBF.

On B – improved governance conditions (reduced leakage through corruption) -

The governance environment in Uganda is considered to be challenging. There is a downward trend on corruption and accountability benchmarks, as evidenced by Transparency International’s Uganda’s Corruption Perception Index (see Table A). This reflects continued weakness in governance, particularly, perceived low levels of accountability and responsiveness of the Government to the people.

Table A
Country	2016 / Global ranking	2015 Global ranking	2014 / Global ranking	2013 Global ranking	2012 Global ranking	2011 / Global ranking	2010 / Global ranking	2009 / Global ranking
Uganda	151/175	139/168	142/175	140/177	130/176	143/183	127/178	130/180

Source: Transparency International Corruption Index

However, there is quantitative and qualitative evidence that the technical assistance DFID supported at local level (through ULGA) did make a significant impact in improving governance, government performance and management of finances (in the case of local government). The Technical Assistance given through ULGA, at just over £400,000 for three years, provided hands on support to lower district governments in financial management, for example through the Output Based Budget Tool. This tool has led to timely budgeting and development of local government plans, procurement plans  and activities.

On C – jobs created through private sector grant scheme - the original assumption was that the grant scheme would create 9,800 jobs over five years, 5,400 of which will be attributable to DFID funding, and the rest to co-funding from partners. The Youth Development Programme (YDP) it was assumed would generate 500 jobs per annum, amounting to 2,500 jobs over the period with an annual benefit of £1.1m. DFID would directly support the creation of 7,900 jobs in total. PSFU has to-date approved grants for 426 businesses, leading to the creation of a total of 15,875 jobs. Given that the PSFU expenditure between 2010 and 2013 was 29.9% of its original budget, (before reallocation of funds), this component represented value for money in line with the criteria in the original programme memorandum. In addition, Voluntary Services Organisation, youth training programme provided the pathway for 15,875 young women and men (49.7% female) to find decent jobs (including through self-employment) at a cost of £7.8m. Also through the Northern Uganda Youth Entrepreneurship Project delivered through Youth Business International and Enterprise Uganda, the project created and/or expanded 13,337 youths (6,841 young women) and family-owned enterprises, of which savings and investment clubs were reported with over UGX 150m (£35,000) raised. 11 clubs opened up accounts at financial institutions and benefit 350 people (around 5% of the total number of beneficiaries).

An independent evaluation report (QN 5698969) of the Youth skills projects assesses a cost/benefit ratio of 0.9 for VSO’s intervention, and a rate of 3.1 for Enterprise Uganda. However, as well as caveats related to data quality and methodological weaknesses, it is important to note that the VSO project involved the most excluded populations in Northern Uganda, while Enterprise Uganda included a far more enterprising, urban group. It is important to consider the ‘raw material’ being trained when calculating costs and benefits of training programmes. A negative rate of 0.9 might represent good value for money in the context (especially given that lifetime benefits and social benefits were not included), and the VSO approach and beneficiary group maybe suitable candidate for the public subsidy implied by the negative rate of return. Overall, and heavily caveated, the report suggests project benefits of £14.95m, after an expenditure of £10.5m

A further indicator of VFM was through comparing the two sub components to other Uganda skills initiatives, which was undertaken by the independent reviewers. Although data is high level and not easily comparable, the comparison shows the two components in a relatively strong light. The main cheaper projects were noticeably focused on far higher capacity target beneficiaries (secondary school students and existing entrepreneurs).

On D – increased employability and opportunities for young people. The assumption in the PCDP revised submission to SoS in 2011 was that 100,000 young people would receive vocational training at a cost of £12.5m, roughly £125 per student. Expenditure by the Northern Uganda Youth Development Centre (NUYDC) to-date amounts to £2.5m, whilst 16,894 young people have received training. Notably, training through VTIs was on track on costs while it was moderately above originally envisaged costs for NUYDC. Overall, the cost of delivering training to each student in 2012 and 2013 was £148. The high cost of delivering training was particularly driven by the more labour and resource-intensive nature of the training provided (residential courses, lasting between 1 – 2 years) at NUYDC. However, value for money for the more intensive residential courses offered by NUYDC vis-à-vis the shorter term courses offered by the other VTIs is difficult to determine without statistically significant data on employment patterns among graduates as NUYDC was unable to develop a graduate tracking system.

The reprogramming and subsequent delivery of the NUYDC through the Northern Uganda Youth Enterprise Programme (NUYEP) delivered by YBI and Enterprise Uganda was judged by the independent evaluation as delivering VfM. The unit costs for the different modalities of NUYEP support was used to estimate the opportunity cost of providing the different levels of support provided to NUYEP participants; Business Enterprise Start-up Tool (BEST) training only, BEST plus one additional follow up specialised training, BEST plus two or more follow up or specialised trainings, and BEST plus counselling or mentoring. The weighted cost per participant for the different modalities was UGX 297,146 (£ 65.6), whilst 13,377 youth received training. NUYEP participants with more intensive support did have estimated net income from reported sales that exceeded the benchmark figure estimated on the basis of net income for youth involved in business in Uganda by UGX 58,800 (£ 12.9) per month for participants attending BEST and 2 or more follow up trainings; and by UGX 121,200 (£26.7) per month for those attending BEST and receiving business counselling. This results in an estimated average additional monthly income per programme participant of UGX 26,816 (£5.9).

E – social support to the extremely vulnerable people - this assumption, which relates to the work undertaken by UNHCR to resettle extremely vulnerable individuals and persons with special needs from IDP camps back into their communities and improving access to income-generating opportunities to moderately insecure households in Karamoja, remains unchanged.

Assessment of whether the programme represented value for money

VfM assessment is mixed but also more difficult to measure largely due to the more dynamic and challenging political-economic-social context and the level of ambition set for the different indicators.

Output I: NUSAF: This was a large investment (£24m) by DFID but there is little evidence around the direct impact. The Aide Memoire of the Joint Project Implementation Mission, September 2013 (QN 5709623) established that the houses were built to a high standard; they were extremely popular with the staff that benefitted from them, who according to the Annual review 2013, anecdotally informed DFID that the teachers and health workers previously struggled to find local accommodation in many of the areas in which they have been built; and they were popular with local communities, who see it as a positive measure of support to health workers and teachers who are – usually – respected by the local communities. Follow up visits to some of the houses however reveal that maintenance after they were handed over has not always been done consistently and effectively. It should be noted that the operational costs (incurred by the project and the World Bank) rose over the programme period. The main reason for this was the decision to enhance the intensity of technical assistance on construction standards provided to the districts with a responsibility to oversee the building work. This resulted in a significant increase in costs, but due to exchange rate gains, the per-unit cost of the houses built turned out the same (in £) as originally planned; and the units are extremely high-quality as a consequence of the technical assistance on construction standards – far better quality than much public infrastructure in Uganda, without being inappropriately over-specified.

An important caveat is that the cost to benefit ratio of the Social Accountability and Community Monitoring (SACM) is not fully established. A key question relates to the value-for-money of the SACM intervention itself. Due to challenges in contracting, the scope of the training, and the fact that the implementing NGO/CSO was a consortium of various partners, the Programme was relatively expensive to implement. The impact evaluation of TAAC established that the cost of the training per community is estimated at approximately is US $850, (£681). Still, the increase in the quantity of outputs delivered to projects is not the only benefit from the programme, and most likely represents a lower bound. For instance, the SACM intervention also led to improvements in the quality of output.

Output 2: NUSAF II (WFP): A Public Works Programme (PWP) providing food or cash transfers in exchange for unskilled labour. The modality of using of Implementing Partners (IPs) is efficient in terms of reaching and addressing vulnerability across all villages in Karamoja, and overheads are low. However, there are inefficiencies in the contracting process between WFP and IPs, and between this programme and that of other programmes in terms of coherence and coordination. IPs have good structures to get down to community level but the challenge is the quality of work due to time and technical constraints. Considering reputational implications, we would have expected to see the development of a much clearer communications strategy to keep stakeholders informed about; expected delays, what the reasons are for these delays, and how WFP are working to resolve the situation.

The key cost driver was cash grants. NUSAF II (WFP) provided cash payments in return for public works participation at a rate of UGX 4,000/= per day (£1). However, it was understood that the EU funded KALIP programme paid UGX 7,000/=. Thus, it is likely that members of the same household will work on different projects at different rates. Different rates may have given rise to competition for KALIP work and over time may see a widening of the poverty gap between community members with the more able bodied working for KALIP and the less able bodied working with NUSAF II.

PNFPs/RBF: An independent evaluation was not sufficiently methodologically robust to draw confident conclusions about the attribution of RBF or input based financing (IBF) to any changes in health facility services or population health/utilisation. The evaluation provided some limited evidence that RBF was effective in small health facilities but due to the design of the study the evaluators were unable to control for other influencing factors. This project completion review is unable to conclude that the improvements in access and infrastructure in small health facilities were purely a result of RBF and that RBF should therefore focus on this type of facility in future.

Output 3: Private Sector/Youth components: Output indicators: small grant schemes (3.1) and respondents perceiving they have access to increased economic opportunity (3.4) were not assessed as representing value for money, leading to early closure which limited losses. Losses were not absolute, as the 2015 AR notes – examples of equipment purchase and technical assistance provided to businesses created some value.

Output indicators YDP/VSO, youth training skills (3.2) and BEST - YBI/EU (3.3) were successful in delivering outputs at a level higher than originally agreed. The section above notes the positive overall VFM assessment. However, there are two key caveats to this. The first is that data, although voluminous was not of the very high quality required to draw conclusions with confidence, and a randomised control trial could have delivered far stronger VFM conclusions. The second is that the ultimate impact of the components is weak beyond the direct beneficiaries, and the number of direct beneficiaries (although impressive at almost 30,000) is a very small proportion of the number requiring support – indicatively 700,000 young people enter the labour market each year. The sub-components can, however, point to sustainable impacts driven by capacity improvements in the 36 technical colleges, and plausibly the wider economic impacts of several thousand entrepreneurs growing their businesses. Such impacts are very hard to measure however.

The independent evaluation report assesses a cost/benefit ratio of 0.9 for VSO’s intervention, and a rate of 3.1 for Enterprise Uganda. However, as well as caveats related to data quality and methodological weaknesses, it is important to note that the VSO project involved the most excluded populations in Northern Uganda, while Enterprise Uganda included a far more enterprising, urban group. It is important to consider the ‘raw material’ being trained when calculating costs and benefits of training programmes. A negative rate of 0.9 might represent good value for money in the context (especially given that lifetime benefits and social benefits were not included), and the VSO approach and beneficiary group maybe suitable candidate for the public subsidy implied by the negative rate of return.

Output 4: PCIs/ACCS: A review of the ACCS programme found that the methodology of data collection and reporting results (particularly the PCIs) was high-cost. Compounded with the lack of a clear set of lessons drawn out of each iteration of the PCIs, or a broader advocacy and communication strategy, the assessment is that this area of the ACCS programme did not offer good VFM. The ACCS end of project review noted that peacebuilding work can justify a relatively high expenditure if found to be effective. This is because of the high costs associated with conflict and therefore the value that can be placed on preventing this happening. However, VfM in relation to peacebuilding is very difficult to measure, particularly given the challenges of attribution and measuring outcome level change.

RJP: Under RJP (Component indicator 4.2), legal aid work presented the highest costs. Specifically, drivers include: support for capacity building; human resource to deliver legal aid and other running costs including rent, stationery and fuel expenses. However, support to legal aid partners to increase the geographical scope of their services contributed to bringing legal aid services nearer to beneficiaries and reduced the cost and time for accessing justice which in turn reduces the potential for escalation of disputes and attendant effects, including turning disputes into criminal cases. Whereas legal aid service delivery is expensive, the benefits related to empowerment and legal support especially for poor and vulnerable people exceeds the cost. Legal aid has enabled poor widows to retain control of their husbands’ land, thus ensuring care for their children; prevention of hunger and destitution as well as added nutritional value to prevent disease. Access to justice has contributed to reducing the rate of prison population growth. Through police and prison decongestion programs, about 30,000 people are released each year, including juveniles. However, there is increasing recognition to ensure holistic access to justice programs that also address the drivers/causes of poverty and vulnerability. There is need for social and economic empowerment programs to be run alongside access to justice programs.

Other costs include investments in research and development of regulatory framework for legal aid which are intended to enhance standards in delivery of legal aid services.

The DGF I review[4], November 2016 noted that systematic VfM assessment was limited and relied more on a qualitative and subjective assessment of VfM. The evaluation established that the overhead costs of the DGF are around 4% which is considered significantly below similar governance programmes which often charge 5-10%. Considering the relatively low overhead and administrative costs of running the PMU the DGF, according to the Evaluation report, can be considered more cost-efficient than other bilateral DP governance programmes. The report further notes that It is however difficult to assess and verify this statement due to limited results monitoring and in particular limited disaggregated financial data.
[4] DFID’s EQUALS team, quality assured the DGF I Evaluation report and judged it as a ‘Review’ and not an evaluation.

In comparison to donor’s own separate governance programmes the DGF ‘may’ allow for greater economies of scale (by pooling funds together) and reduces the risk of duplication (as different donors fund the same types of initiatives and even governance actors). According to the review report, It is not possible to assess whether the DGF has influenced how the Government of Uganda is providing greater support to its governance priorities (as laid out in the National Development Plan) so as to reduce dependency on aid.

Equity as understood as the DGF’s ability to reach most vulnerable groups – is limited by the absence of disaggregated data. Equity is a focus and target of the DGF, but whether the DGF is applying a better value for money equity approach compared to individual or bilateral governance programmes cannot be verified due to the absence of baseline and disaggregated project data. There is however clear evidence that DGF-funded projects have reached vulnerable and marginalised groups in Uganda.

Quality of financial management during programme

The programme was exposed to high fiduciary risk which materialised with the OPM corruption scandal in 2012. Following this, a number of the components under the PCDP were reprogrammed and funding was channelled through different delivery channels. DFID reprogrammed PCDP’s youth development programme which was subsequently delivered through Volunteer Service Overseas (VSO) and Youth Business International (YBI) through its partnership with Enterprise Uganda (EUg). Whilst it was originally intended that PCDP should provide budget support through OPM for the Government of Uganda’s PRDP, the fiduciary risks of doing so were judged to be too high. Additionally, support through the Private Sector Foundation Uganda (PSFU) was phased out, and technical assistance to OPM was ended. Work delivered through the Northern Uganda Youth Development Centre (NUYDC) was terminated.

Under RJP, DGF operated in a high fiduciary risk environment. DGF and DANIDA (as lead donor) closely monitored fiduciary risk and coordinated with contributing donors on mitigation strategies. DGF developed a whistle-blower mechanism with a confidential hotline and email to report and escalate exposure of risk.

There was regular monitoring of programme delivery by implementing partners and DFID to ensure that funds were used for intended purposes and as per approved work plans and budgets.

Audits: All components under PCDP underwent financial audits. RJP under DGF received an unqualified audit opinion. Regular audits were conducted on the use of DFID funds by implementing partners (VSO Uganda, YBI, DGF, UNHCR, ACCS).

The audits focused on both the managing agents e.g. DGF (PMU) of the components and the implementing partners. Overall, the DGF audits pointed out the PMU as a managing agent for RJP has put in place an internal control environment that can enable management to prevent, detect and correct material errors in the Funds Accountability Statement, ensure compliance with the terms and conditions of the Funding Agreements and regulations and ultimately safeguard for assets and resources from loss and misappropriation. In spite of the above, the DGF audit reported that there were some instances of non-compliance with pre-grant assessment (due diligence) procedures, unreported foreign exchange gains/losses by implementing partners and recommended strengthening internal scrutiny. DGF has addressed all these Audit issues to our satisfaction.
VSO were operating in a very high risk environment for financial management, particularly in relation to their vocational college partners. VSO’s openness, oversight, willingness to challenge and be challenged were all instrumental in ensuring risks were well managed.

Funding flows were closely managed. Project funds (comprising 90% of the overall budget) were paid either monthly or quarterly in advance (depending on financial aid instrument). All partners were required to open a separate account for each project. Disbursement was approved on the basis of agreed work-plans, verification of project progress was through field/site visits by DFID and specific project staff, and receipt of accountability of 80% of the previous tranche of disbursements before the next disbursement.

Whilst it was originally intended that PCDP should provide budget support through OPM for the Government of Uganda’s PRDP, the fiduciary risks of doing so were judged to be too high. The programme was on track against the financial forecast until the OPM corruption scandal of 2012 which led to freezing of DFID funds for the grants scheme and re-programming of the youth development programme and the termination of the technical support to OPM. However, the suspension of financial aid to Government of Uganda meant PCDP would have a significant under-spend, particularly during the financial year 2013/2014 as the youth training was reprogrammed, the grants scheme was rolled into the financial services programme (outside of PCDP), and the proposed PRDP budget support for Northern Uganda did not go ahead.

PCDP revised budget spend by output
	PCDP Outputs	Spend	Balance
1.	Output 1 - Local government capacity for equitable service delivery and management is strengthened	24,474,689.55	-
2.	Output 2 - The most vulnerable conflict-affected communities are rebuilt and empowered	34,804,188.15	1
3.	Output 3 - The private sector is revitalised and accessible employment opportunities are created.	18,688,370.64	1
4.	Output 4 - Government, civil society and communities can engage actively in peacebuilding and reconciliation	10,219,962.00
5.	Supporting components (across components – Design, procurement, research and evaluation)	1,924,722.93	1
6	Unallocated	-	10,403,611.73
	Total	90,111,933.27	10,403,614.73

PCDP Budget spend by component
Component	Budget Revised	Spend	Balance

Design & Appraisal of Post-Conflict Development Programme for northern Uganda	458,629.11	458,629.11	0.00
NUSAF II World Bank - resource spend for administrative reform	10,325,138.00	10,325,138.00	0.00
Advisory Consortium on Conflict Sensitivity - Accountable Grant	3,619,962.00	3,619,962.00	0.00
NUSAF II World Food Programme - Karamoja	14,000,000.00	14,000,000.00	0.00
UNHCR support for Extremely Vulnerable Individuals in Northern Uganda	5,720,000.00	5,720,000.00	0.00
Uganda Local Governments Association - strengthening Gulu & Lira councils	474,689.55	474,689.55	0.00
Private Sector Foundation Uganda - Small Grants Scheme for Northern Uganda	4,489,011.07	4,489,011.07	0.00
Peacebuilding and Reconciliation in Northern Uganda	6,600,000.00	6,600,000.00	0.00
Grant for Government of Uganda Peace, Recovery & Development Plan	10,401,308.95	-2,302.78	10,403,611.73
NUSAF II World Bank - capital spend for public worker housing in northern Uganda	13,674,862.00	13,674,862.00	0.00
Advisory support, research and evaluation for northern Uganda	1,371,386.32	1,371,385.32	1.00
Youth skills and employment in northern Uganda - off-budget spend	942,609.63	942,609.63	0.00
Uganda Investment Authority - economic analysis in northern Uganda	1,842,222.33	1,842,222.33	0.00
Youth skills and employment in northern Uganda - on-budget spend	1,245,613.82	1,245,613.82	0.00
Improving access to healthcare in northern Uganda	12,170,827.82	12,170,827.82	0.00
Direct procurement of goods for recovery in Northern Uganda	97,011.28	97,011.28	0.00
Youth Development Programme - Voluntary Services Overseas	7,897,249.42	7,897,249.42	0.00
Design of the Nodding Disease Syndrome Project	60,000.00	60,000.00	0.00
Response to the Nodding Syndrome outbreak in Northern Uganda	1.00	0.00	1.00
Support to the Office of the Prime Minister	1.00	0.00	1.00
Impact evaluation of a DFID programme to improve access to healthcare in northern Uganda	1,011,138.00	1,011,138.00	0.00
Northern Uganda Youth Entrepreneurship Programme (NUYEP)	2,738,984.00	2,738,984.00	0.00
Payment of Liabilities incurred by Private Sector Foundation Uganda prior funding freeze to the Office of the Prime Minister	1,374,902.70	1,374,902.70	0.00
Total	100,515,548.00	90,111,933.27	10,403,614.73

E: RISK (½ page)

Quality of risk management over the life of the programme

The overall risk of the project in the original Programme Memorandum document was medium. By 2016 the residual risk for the programme was judged as medium-high albeit with solid development return. PCDP’s risk rating has slightly changed since in the 2015 review, given the changes in the contextual and fiduciary risk environment as indicated below.

All components had in place approved risk registers with the various identified categories of risk. Risk registers were updated on a quarterly basis and risk was part of the quarterly programme management discussions with managing partners.

Since the suspension of financial aid to GoU and changes in the delivery of PCDP components, the relevant risks to the programme are assessed below:

Risk	Status and mitigating action	Rating
The absence of final peace agreement between LRA and the GoU and the likely return of the LRA in Uganda	DFID monitors the attitudes of both LRA and GoU through ACCS and news media. ACCS conflict analysis concluded that it is highly unlikely that the LRA will return to Northern Uganda.	Low
Conflict emerges in Northern Uganda	While ACCS peace and conflict analyses identify some key conflict drivers in the north, the evidence suggests that a resumption of widespread conflict remains unlikely. ACCS analysis reveals key findings that remain the most serious threats to long-term peace across the PRDP: Conflicts over land and other natural resources (including oil, grazing, forest and other reserves);Changing gender relations during and after the conflict, which have contributed to high levels of domestic and sexual and gender-based violence; Youth unemployment, disillusionment and lack of opportunity, which create a risk of violent activities – whether criminal or political – and of continued economic and social disparity between the PRDP regions and the rest of the country and Incomplete or inadequate transitional justice, reconciliation and return processes that leave people depressed, in conflict with each other, their neighbours and authorities, and with a sense that the war is still not completely ‘over’.	Low
The uncertain status of peace, security and stability in South Sudan/DRC and Kenya leading to unstable northern Uganda.	The break-out of conflict in South Sudan led to the influx of South Sudanese refugees in Northern Uganda. To-date, more than 700,000 refugees from South Sudan have crossed into in Uganda (UNHCR/RIMS system). However, this has not resulted into any large scale instability of Northern Uganda. There are however local level tensions between host communities and the arrivals from South Sudan. The political situation in South Sudan continues to evolve with GoU playing an important stabilising role. DFID Uganda has scaled up its support to the humanitarian crisis resulting from the conflict in South Sudan. The political situation in South Sudan continues to evolve with GoU playing an important stabilising role There was an unrest in Burundi in 2015, following announcement of the President’s re-election for a third term. Hundreds fled Burundi into Uganda, however, that did not pose any immediate threat to Uganda. After the peaceful elections in Kenya 2013, and terrorism threats in Kenya did not pose immediate threat to the security of Uganda as a whole. DFID Uganda continues to monitor the situations in South Sudan, Burundi, DRC and Kenya.	High
Lack of political will within central government to support local government institutions	The 2012 OPM corruption scandal and the suspension of financial aid to GoU by donors resulted in GoU having less resources with which to support local government institutions. As a result, the credibility of central government has been undermined at LG levels that increasingly believe that OPM role under PRDP be limited to monitoring and not include implementation.	High
Corruption remains a risk but will be mitigated through the provision of TA to support demand and supply side governance. This will be complemented by our broader accountability programme. The GoU is making real progress on the management of public sector standards and systems and this programme will assist this process.	Following the 2012 OPM corruption scandal, a number of the components under the PCDP were reprogrammed and funding was channelled through different delivery channels. DFID reprogrammed PCDP’s youth development programme which was subsequently delivered through Volunteer Service Overseas (VSO) and Youth Business International (YBI) through its partnership with Enterprise Uganda (EUg). Whilst it was originally intended that PCDP should provide budget support through OPM for the Government of Uganda’s PRDP, the fiduciary risks of doing so were judged to be too high. Additionally, support through the Private Sector Foundation Uganda (PSFU) was phased out, and technical assistance to OPM was ended. The Northern Uganda Youth Development Centre (NUYDC) was previously responsible for the implementation of the youth development plan (for youth skills component) and funds were channelled through the OPM. NUYDC awarded contracts to a network of 42 training institutions through a competitive bidding process. Delivery through the NUYDC was terminated following the suspension of financial aid in 2012. Under RJP, DGF operated in a high fiduciary risk environment. DGF and DANIDA (as lead donor) closely monitored fiduciary risk and coordinated with contributing donors on mitigation strategies. DGF developed a whistle-blower mechanism with a confidential hotline and email to report and escalate exposure of risk. DFID regularly obtained advice from Counter Fraud and Whistle-Blowing Unit (CFWU) on fiduciary risk management.	High
Supplementary resources from GoU are inadequate and OPM does not use DFID funds for intended purposes	DFID does not provide support to Northern Uganda through GoU systems. Suspension of financial aid to GoU by donors meant that GoU has fewer resources available to support post conflict recovery in Northern Uganda through PRDP grants to the districts.	Low
Failure of youth development programme to secure employment creates tensions and resentment	The programme was redesigned to improve livelihoods and train youth in skills relevant to labour market demands, including self-employment. Delivery was delivered through VSO and YBI/EUg. Testimony from beneficiaries suggested existence of unintended risks relating to the programme. Firstly, youth who participated at trainings without follow-up support opportunities, were exposed to losing assets through unsuccessful attempts to start a business. Secondly, women and older girls in particular were exposed to domestic conflict when husbands or other male relatives were resistant to their enterprise.	Medium
Private investors do not respond to grants scheme due to fear of socio-economic tension and instability / Private investments does not create the intended socio-economic outcome / Grants scheme is politicised	As a result of the OPM corruption scandal and the Annual Review, 2013 recommendations and DFID suspended financial aid to GoU and closed this component of the programme. DFID settled liabilities with SMEs that arose from the implementation of the component prior to aid suspension through an Accountable Grant with PSFU.	Medium
Uganda Investment Authority (UIA) economic recovery analysis is inaccurate and misguides economic recovery	When the quality of the first phase of the economic recovery analysis was unsatisfactory, DFID terminated the contract with UIA in 2012. The second phase of the work has been contracted to Oxford Economics through competitive bid. The report was presented to OPM and MoFPED.	Low
Building of houses for teachers and health workers causes health and environmental damage	World Bank/NUSAF2 project hired environmental specialists who provided oversight and guidelines so that environmental and social safeguards are put in place for every sub-projects under the project. In August 2016, the World Bank approved a new environmental and social framework (ESF) that makes advances in areas such as transparency, non-discrimination, social inclusion, public participation, and accountability – including expanded roles for grievance redress mechanisms.	Low
The physical progress on teachers and health workers houses do not reflect the level of funds disbursed from DFID	The project has accounted for all funds. The original target of 1,000 units attributable to DFID was revised down to 869 units (each unit containing 2 houses). Target was met. However, there was no specific evaluation that provides evidence on the impact of houses on the education and health outcomes.	Medium

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

A number of PCDP components had slow start up and implementation: ACCS, youth development programme, grants scheme, economic recovery analysis, advisory consortium on conflict sensitivity, and NUSAF II. Two components of the programme had late start ups: health work with PNFPs and peace building and reconciliation work through DGF. Four components of the programme started on time: resettlement and reintegration of EVIs/PSNs with UNHCR, Karamoja livelihoods programme, capacity building of the Local Governments of Gulu and Lira districts, and technical support by PWC to OPM. Of the various components of the programme, the Northern Uganda grants scheme, cash transfers and youth development programme were off track in terms of set targets. The reasons for this are: a) weak institutional capacity of NUYDC and PSFU to effectively implement their components of the programme, b) delayed disbursement of funds from OPM to NUYDC and PSFU which affected implementation of programmes.

Performance of partnership (s)

PCDP projects were implemented through downstream partners managed at two levels: DFID Uganda - with the managing partners; then Managing partners with downstream partners. DFID maintained close working relations with the different managing partners through monthly meetings and regular communication on email and phone calls that have helped timely resolution of emerging issues during programme implementation. DFID was also responsible for overall management of the programme and for reporting on outputs and impact, but specific components of programme delivery are outsourced to the GoU, NGOs and technical assistance providers.

Office of the Prime Minister (OPM): The partnership was strained during the project, due to the corruption scandal and DFID’s decision to suspend all budget support through the Ministry. DFID and OPM subsequently worked hard to rebuild relationships and found different approaches to delivering the results.

Partnerships with Private Sector Foundation Uganda (PSFU); Northern Uganda Youth Development Centre (NUYDC); and PriceWaterhouseCoopers (PWC); were challenging due to the suspension of financial aid to GoU; all technical and other support provided by these partnships was subsequently terminated during the project.

World Food Programme (WFP): responsible for delivering the NUSAF II programme in Karamoja. Used a range of implementing partners to deliver the programme, including national and international NGOs. There were concerns with of the the high overhead cost of the programme, given it’s nature of food anc cash transfers.

Uganda Local Government Association (ULGA): Provided good technical support to the district resource pools of Gulu and Lira districts, however, had challenges in their financial management systems. As a result DFID has opted to fund the TA to Gulu and Lira districts directly, rather than renewing our partnership with ULGA.

World Bank (WB): By working together, World Bank and DFID delivered more houses for teachers and health workers in Uganda. However, the lack of an evaluation meant the opportunity to learn lessons or understand the real impact of these houses on service provision was missed.

Democratic Governance Facility/Rights Justice and Peace Component: DFID cultivated a good relationship with DGF through representation on the Steering Committee and the DGF Board. DFID was able to use its influence to drive the financial management, results and VFM agendas within the multi-donor programme. The Steering Committee engaged on scrutiny and approval of Screening Notes and the approval of corporate reports, the Communication Strategy and Programme policy engagement proposals. The Annual Partnership Conferences attracted more than 150 participants from DGF’s Partners, the PMU, the Steering Committee and the Board enabled networking, synergy and building of strong linkages in the DGF Partnership, as well as enlightening partners on DGF’s plans during the extension period (DGF 1+).

Advisory Consortium on Conflict-Sensitivity (ACCS) – The Consortium comprised of three partners: International Alert, Safer World and Refugee Law Project. The project suffered from inefficiencies and poor coherence, including flaws in the consortium’s management model and functional division of labour; a lack of understanding and agreement over programme scope, foundational concepts and theory of change amongst consortium members. This led to delays in delivering on the outputs. There were difficulties in achieving buy-in amongst key stakeholders managing the PRDP (including OPM), and PCDP/PRDP implementing partners. The failure to address these issues was largely due to a lack of sustained leadership within the Consortium.

Health Partners International/Montrose: implemented the results-based financing pilot involving 31 PNFPs in Acholi and Lango sub-regions. Management costs escalated since the programme was designed, representing almost 40% of project costs. This is largely due to the experimental nature of the project, which involves separate arrangements for an “intervention” and a “control” group, as well as the cost of seconding 10 health officials to the district health teams..

Asset disposal and value obtained by DFID

The youth skills project asset register was updated in December 2016. As part of the end of project reporting requirements, both YBI and VSO were asked to report on the status of the assets that they have purchased. A final asset spot check was undertaken in July 2016. Asset disposal was otherwise focused on achieving maximum value for assets purchased through the project, and largely involved handing over to project partners who will continue to use them in related activities.

Under DGF/RJP, the Programme Management Unit (PMU) maintains an asset register for both Partner and PMU Assets. Fixed assets and their value were verified during DGF’s audit for the period ending 30 June 2015. DGF/RJP submits asset registry updates to DFID and the latest Asset Register submitted was for June 2016. PMU partners, as part of the progress reporting requirements, report on the status of the assets that they have provided. DFID conducted a spot check in Western Uganda on three downstream partners in May 2015 and findings revealed that asset registers were in place and spot-checks conducted on a semi-annual basis.

G: CONDITIONALITY (½ page)

Partnership principles assessment
PCDP conditionality was restricted to GoU compliance with Development Partnership Arrangement (DPA) commitments to poverty reduction, protection of human rights and improved financial management and accountability. This conditionality was attached to the delivery of components of the programme through the GoU systems.

Following the 2012 OPM corruption and the suspension of financial aid to GoU DFID stopped delivery of any component of the PCDP through GoU. While no component of PCDP was then delivered through GoU, implementing partners were required to demonstrate consistent strong financial management and accountability. All aspects of the management of the programme sit outside of GoU systems, but the office continues to monitor the relevance of the Partnership Principles to programme, particularly those close to government even though the Partnership Principles were not used to make decisions on disbursements.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

DFID Uganda in November 2016 conducted an external review on assessing the use of evidence in PCDP (QN 5633880). The external review considered how lessons learned and evidence informed the development and delivery of results in the Post-Conflict Development Programme and how they should inform DFID’s continued programming in the Northern Uganda. See Annex A for detail by project. Below were the key findings:

Programme design was informed by best practice and lessons-learned from DFID post conflict recovery programmes; DFID experience of working in Uganda; and consultation with development partners. In neither the programme memorandum by Coffee International nor the DFID business case is any evidence (in the form of studies or political economy analysis) directly referred to. Programme design was also informed by the DFID white paper 4 and various aspects of the Uganda National Development Plan in accordance with the Accra Agenda and Paris Principles. The extent to which these documents are based on evidence needs to be discussed further. However, it does raise questions about the compatibility of evidence based policy and development policy aligned to national development plans. Likewise, programme design of individual components of PCDP were informed by best-practice rather than rigorous evidence.

The Theory of Change outlined in the PCDP Programme Memorandum is very basic. It does not explain how inputs translate into outputs, nor how these outputs interact with one another and go on to translate into outcomes and impact. Crucially, the key assumptions of the programme are not stated. This makes it very difficult to test the programme in a way that generates evidence with external validity.

The OPM was in charge of M&E with DFID support. When DFID funds directed away from direct support to the OPM, the PCDP was left without a cohesive M&E strategy. This meant that monitoring and evaluation largely depended on implementing partners with a high degree of variation. DFID commitment to flexibility and M&E meant that adaptability and learning were neverless achieved in many cases. For example:
- The substantial re-design of the programme in 2012/13 wasan opportunity to stop or reform non-performing components of the PCDP
- DFID’s general working culture was identified by partners as a key factor in adaptive programming
- Several independent evaluations of varying quality were carried out

Monitoring progress throughout the programme

- Independent evaluation and reviews.
- Conducted extensive field and focus group research.
- Reviewed and updated the risk management framework for each project
Review of the overarching ToC (e.g. for DGF)
- Annual reviews conducted
- Adjusted PCDP logframe following Annual Review Reports - aligned to partner interventions and more datasets obtained for better results monitoring and recording
- Robust field monitoring resulting in increased compliance and partner awareness of results documentation and reporting
- Financial and audit spot checks conducted
- Provided capacity development to IPs to conduct peer to peer evaluations.
- Semi-annual and annual reporting.

Logframe changes
Outcome Indicators: Two outcome indicators were revised to reflect direct contributions that are being made through the investments of PCPD components: the Northern Uganda Health and the Youth Development Programme implemented by VSO. An additional output indicator was moved to an outcome indicator so that the programme now has four outcome indicators.

Outcome indicator 1: Changed from Proportion of U5s with fever receiving malaria treatment within 24 hours (PRDP districts) to Number of under-fives presented with fever that are tested for malaria and appropriately treated in the 31 PNFP facilities (disaggregated by gender).

Outcome indicator 2: Changed from Number of trained young people retained in formal employment for six months or more (attributable to DFID) to Number of YDP youth with decent jobs (employed or self-employed in the formal or informal economy) (attributable to DFID)

New Outcome indicator 4: The output indicator which was moved to outcome level to become outcome indicator 4 is, Percentage of respondents assessing that local government is responsive to community needs.
Output Indicators: The following changes were made to output indicators:
- Output indicator 1.1: milestone was changed from 4000 to 1,738 houses built. The original target of 4000 houses was due to a misunderstanding about what is meant by a ‘house.’ NUSAF2 ‘houses’ are duplexes (i.e. they contain two houses). DFID had originally understood that c. 2000 duplexes would be built but this target has now been reduced down to 869 duplexes with 1,738 houses; this revision reflects the actual number of houses that DFID funds would build.
- Output indicator 2.4: indicator was changed from: Number of additional consultations and treatments in PNFP health centres in Acholi region to Number of OPD consultations and treatments in the 31 PNFP facilities per year (disaggregated by male/female, and by age-group). This change was required in order to reflect results that can be measured through investments in both Acholi and Lango sub-regions under the Northern Uganda Health Programme. The earlier indicator would not reflect the investments in both input-based and results based financing health facilities in Acholi and Lango sub-regions.
- Output indicators 3.2 and 3.3: indicators were changed from: Jobs created (under the grants scheme programme) and Number of youth trained by DFID-funded programmes in targeted vocational and micro-enterprise skills to Number of YDP youth trained in a core vocational skill(s) relevant to local market opportunities and Youth Trained in Business Enterprise Start Up Tool (BEST). The earlier indicators were drawn from NUYDC and PSFU implemented components of the programme that were managed by OPM. With the termination of funding to NUYDC and OPM, cancellation of the grants scheme, and the reprogramming of the youth programme it became necessary to change these indicators in order to reflect new results that would be delivered through VSO and YBI/Eug.
- Output indicators 4.2 and 4.3: Indicator 4.2 was changed from Progress of parliamentary legislation on reconciliation to Number of men and women reached by legal aid services supported by DGF. Indicator 4.2 was changed to reflect results that would be delivered through DGF-funded activities. The progress of legislation in the Ugandan Parliament depends on a number of external factors beyond activities funded under the remit of DGF. Results under the revised indicator directly relates to DGF supported interventions.
- Output indicator 4.3 is a new indicator: % of Ugandan women and men satisfied with the role of traditional institutions. Indicator 4.3 was added to the log frame to reflect additional results from more resources that DFID will provide to DGF under the programme component.