Project Completion Review

Title: SUPPORTING ECONOMIC RECOVERY IN SOMALIA (SERS)
Final Programme Value £ (full life): 69.4M	Review Date:	August 2020
Programme Code: 204313	Start Date 2014	Final End Date: March 2020

Summary of Programme Performance
Year	2014/15	2015/16	2016/17	2017/18	2018/19	2019/20
Programme Score	A	A	B	A	A	A
Risk Rating	High	Major	Major	Major	Major	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204313/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204313/documents

A. Summary and Overview (1-2 pages)

The Supporting Economic Recovery in Somalia (SERS) programme funded the World Bank (WB) managed Multi Partner Fund (MPF), established in 2014, to provide pooled funding in support of Somalia’s economic reconstruction needs. It provides expert knowledge, skills and resources in support of (a) core government functions, (b) improved management of the economy, (c) public financial management and (d) private sector development. The MPF supports a broad portfolio of projects designed around the Somali government’s economic development priorities and operates under Somalia’s aid coordination architecture, the Somalia Development and Reconstruction Facility (SDRF).
The UK is the second largest contributor to the MPF after the EU, providing 30% of MPF funding to date. The MPF is funded by eleven donors and is intended to run up to 2024.
The UK’s funding through SERS was not primarily earmarked for any specific programme, with two exceptions: £2.4m to enhance integrity and security of the UK-Somalia remittance corridor; and £5m (in 2017) for a new International Finance Corporation (IFC) managed Trust Fund (IFCTF) to accelerate private sector development in Somalia.

What has the programme achieved
From a starting point, where the World Bank had no presence in Mogadishu, the MPF has delivered substantial outputs on technical reform and knowledge production in a difficult political context. There has been some progress in establishing and facilitating a regular political dialogue between the Federal Government (FGS) and Federal Member States (FMS) on important issues of federalism. Key achievements include;
- Strengthened core state institutions. Under the first two outputs, achievements include expansion of civil service salaries to all FMS; commitment by the Government to take on the financial responsibility of Capacity Injection Mechanism (CIM) recruits (expert civil servants), demonstrating increased fiscal responsibility and further consolidation of the Somalia Financial Information System (SFMIS), through which all Public Sector non-security sector salaries and payments are now made.
- Improved financial management and accountability systems. For example, the MPF-supported oversight mechanism (Financial Governance Committee - FGC) has provided 28 confidential assessments of government concessions and procurement contracts. Of these, 15 were either stopped or cancelled and others were recommended for re-negotiation. This shows both a strength and weakness of the work to date. On the one hand,the much-needed work of the FGC provides a useful oversight function. On the other, , the substantial work and need of the committee in challenging processes highglights there is still a long way to go in improving Public Financial Management in Somalia .
- Supported the federal government in meeting the benchmarks of the International Monetary Fund Staff Monitoring Programmes (SMP), which were critical to enabling Somalia to reach the Decision Point for the Heavily Indebted Poor Countries (HIPC) debt relief process. This has enabled Somalia to normalise relations with the World Bank, African Development Bank (AfDB) and International Monetary Fund (IMF) and ensured its eligibility for substantial funding from these institutions. This is a huge achievement for Somalia (and faster than expected), while increased IFI flows could lead to a step change in the pace of development. The MPF has also helped establish the ground work for International Development Assistance (IDA) programming, with the majority of initial IDA programmes being follow-on programmes to MPF projects. At the individual Trust Fund programme level, the MPF has made significant progress in several areas, including those directly contributing to milestones in the New Partnership for Somalia’s (NPS) Mutual Accountability Framework (MAF) between the donors and the Somali government.
- Financed fiscal transfers for service delivery - e.g. health and education through inter-governmental financing system. The MPF’s support in inter-governmental dialogue on natural resource management and resource-sharing has seen some limited success (e.g. fisheries licenses), although a more conducive wider political context is required to ensure these endure. Given the political context it has been operating in, it may be unreasonable to expect much more could have been delivered in this area.
- Helped build the basic foundations to support economic development. The Central Bank has issued licenses to the Banking Sector and Money Transfer Businesses, carrying out independent supervisions. Some important pieces of legislation have been approved, although many remain stuck between the Lower and Upper Houses of Parliament. Private enterprises have been supported through grants, leveraging additional private and family finance. And, finally the IFC supported Private Public Dialogue between government and major private sector players in key sectors has opened an important avenue for the Government and the private sector to communicate and prioritise reforms to support economic growth. However economic marginalisation particularly for women and youth remain a major issue. This work on private sector growth has laid the ground work for future DFID funded work – both through further support to the MPF and our own bilateral programme.
- The MPF has also marked good progress in ways of working, in particular the number, frequency and quality of engagement of the Bank with the donors has gone up significantly. For example, the MPF Consultative Group meetings have happened regularly and have involved qualitative consultations involving the Federal Government of Somalia (FGS), WB and donors in key challenges and opportunities facing the MPF. The Bank has involved donors in shaping the recommendations of its Mid Term Reviews (MTR) in 2017/18 of key MPF projects.
- With the MPF having disbursing $255m by end of 2019, compared to an initial disbursement of $10m in 2014, this expansion shows the confidence donors have had in the MPF delivering development support, with economies of scale driving its effectiveness. However, several contributors continue to “preference/ ear-mark” their contributions, and while it is the biggest development fund in Somalia, only around 10% of overall aid to Somalia flows through the MPF. This suggests that donors did not fully buy into the original ambition of the MPF to “serve as the centrepiece for the partnership between the government and international community”, with the World Bank (and FGS) failing to turn the MPF into the driver for coordination that was originally attended. This partly reflects a reality of how donors fund development (globally as well as in Somalia).
- All of the above has been achieved against an extremely challenging backdrop; Al Shabaab remain a significant threat restricting access and increasing the costs of operating throughout Somali, the country has suffered numerous droughts, floods and most recently swarms of locusts. The political settlement is fragile with the roles and responsibilities of the different levels of government strongly contested. The nascent work to help develop the private sector, the establishment of public institutions and some limited support on political dialogue on the federal agenda is thus fairly remarkable against such a backdrop.
- These outputs have translated into impressive achievement on many of the outcomes; revenue collection of the FGS increased from $113m in 2016 to $230m in 2019, while on the expenditure side, it has successfully regularised salary payments for over 4,000 civil servants. On the private sector side, over 5,000 new jobs will be created over the next two years by some 110 grantees in manufacturing, agriculture and fisheries sectors.
- Overall the programme is scored as an A (met target). All 4 outputs have been judged to have delivered against expectations (A). While some sub-outputs have fallen short of the target, these have been offset by a number that have exceeded the target. At outcome level, milestones have either been met or exceeded. While there is still a long way to go in building the institutions of Somalia, the programme has delivered significant state-building in a challenging context.

Summary of lessons learnt and recommendations for future programming
General
- The WBG and donors should continue to work together to prioritise and promote a more open collaborative culture, incentivising donor engagement and actively seeking out new partners. DFID should push the World Bank to replicate the MPF local governance and coordination structures for IDA programming and explore how these structures can be strengthened. On key areas of donor overlap (e.g. PFM), there should be more joint dialogue between donors, the FGS and FMS.
- Due consideration of the benefits and risks of different donors supporting similar areas of technical assistance (e.g. on PFM) to different levels of government is needed. The design process for future PFM support will therefore involve substantial consultation with the Somali authorities as well as close coordination with other donors in this space.
- Make provision for robust monitoring, evaluation and learning throughout intervention delivery, including potentially for clients. The MPF should work with all stakeholders to improve evidence available on substantive project level outcomes (e.g. creation of productive new jobs) and the quality of the indicators used to monitor progress. Where practicable, beneficiary views should be incorporated into monitoring reports to help understand how projects are perceived by affected communities.
- The MPF should enhance the utility and value of knowledge products through more structured dissemination.

Accountable Government
- The Effective, Accountable Government portfolio demonstrates that constructive inter-governmental relations are possible in the midst of an evolving political climate when framed around a solid technical agenda; we should look to identify such technical areas for cooperation and dialogue (in Somalia and beyond) to help make progress on politically challenging issues.
- The current work has helpfully facilitated the regular flow of resources, and investments in good practices and procedures to the FMS. Future work will need to focus on shifting the FMS (and other tiers of government) to actually increase its spending on social sectors and areas with a tangible benefit for the Somali population.

Economic Development
- Build in practical political economy analysis, particularly where activities are dependent on state regulation. The weak regulatory environment means that even when laws are passed, they are insufficiently implemented. Such political economy analysis should consider how best to incentivise businesses to change; for example by highlighting the benefits of more formalised businesses and a more predictable regulatory environment. Consideration should also be given to identifying regulation that goes beyond the state e.g. could be best delivered through self-regulation or private entities. This should take more of a sector/problem driven approach, and scan sectors to see which actors are best positioned to work
- Future programmes should consider how to work with and strengthen financial institutions; there is a need to identify more critical interventions beyond lending to banks.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Strengthened fiscal and public finance management capacity
Output number per LF		1	Output Score	A
Impact weighting (%)?		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
O1.1. Federal government finances an increased share of its civil service wage bill (non-security sector)	70%	A+ / FGS taking over an increasing share (now 80%) of its non-security wage bill and including responsibility for Capacity Injection Modality (CIM) recruits
O1.2 Fiscal federalism dialogue facilitates FGS- FMS agreements. / (i) # of annual intergovernmental fiscal dialogues and knowledge sharing events / (ii) Evidence provided of FGS-FMS decisions and agreements made at fiscal dialogues (qualitative)	(i) 3 / (ii) qualitative	A / 3 meetings held: All meetings led to decisions and agreements being made, although not yet clear how long these will last.
O1.3 Foundations for fiscal federalism strengthened as demonstrated by increased inter-governmental transfers. / (i) # of FMS receiving transfers / (ii) % increase in total volume of transfer compared to previous years outturn	(i) 5 / (ii) 50%	B / All (5) FMS received transfers / While total transfers only increased by 6% over the past year, Recurrent Cost and Reform Financing Project (RCRF) transfers to FMS increased by 48%.
O1.4 Improved treasury management, budget execution and procurement in FGS, regional member states and SL	i) register for moveable fixed assets included in annual financial reports / ii) Integration of core banking system with SFMIS	B / i) Partially met – included in financial reports but not integrated with SFMIS / ii) Not yet complete

Given all four sub-outputs are broadly of equal importance, and there has been an over-achievement on one sub-output, under-achievements on two, and one target has been met, an overall score of A is considered appropriate.

Output 1: Strengthened fiscal and public finance management capacity (Recurrent Cost and Reform Financing Project, RCRF II)
O1.1. Federal government finances an increased share of its civil service wage bill (non- security-sector)
There is now a predictable payment of civil service salaries in all FMS through a functioning payroll. This has complemented parallel EU and UK programmes on public resource management in Somalia (notably the DFID-funded Public Resource Management in Somalia - PREMIS programme) and through a consolidated Somalia Financial Information System (SFMIS), which is now applied to all non-security public sector payments.

As a result of successfully increasing domestic revenue and ownership of the payroll, FGS is taking over an increasing share (now 80%) of its non-security wage bill and responsibility for Capacity Injection Modality (CIM) recruits.

O1.2 Fiscal federalism dialogue facilitates FGS-FMS agreements
This programme has managed to facilitate substantial dialogue at the technical and Finance Ministerial level between the FGS and FMS. This is impressive considering the wider tensions in the relationship between the FGS and the FMS .

Inter-governmental fiscal coordination between the FGS and FMS improved substantially in the second half of 2019, including; a strong joint commitment from Finance Ministers to re-invigorate regular inter-governmental fiscal forum meetings, an approved Inter-Governmental Fiscal Transfers Policy Paper (an RCRF reform benchmark), and an agreement to improve routine sharing of fiscal reports, as well to work on the development of a data sharing system between the Ministries of Finance. Such data sharing is important in giving World Bank shareholders (including the UK) the confidence to provide World Bank budget support (starting in June 2020). There were also initial steps to agreeing a common customs tariff between the FGS, Jubbaland and Puntland.
It is possible that some of the agreements may not endure over time. For example,Puntland has already signified that they do not recognise the Baidoa agreement on sharing of oil revenues. Further time is needed to see how sustainable the agreements facilitated by the SERS programme will be.
[note] In addition to the MPF supporting the inter-ministerial dialogue between FGS and FMS finance ministers, the World Bank provided technical assistance on the implementation of revenue and resource-sharing agreements in the natural resources sector. $0.5m of additional funding for technical assistance was also provided from the World Bank’s Extractives Global Programmatic Support Trust Fund.

O1.3. Foundations for fiscal federalism strengthened as demonstrated by increased inter-governmental transfers

Transfers through the MPF to the FMS increased from just over US$2m in 2014 to over nearly $29m in 2018. Given that many FMS were non-existent or not reachable when the MPF commenced this gradual rise represents an achievement.

The wider fiscal transfers between the FGS and FMS presents a more complex picture. Although overall transfers have increased over the years, there was a strong slow-down in 2018 in the increase of (non-RCRF) transfers to the FMS: The overall picture of these transfers remains inequitable, and there is no agreed or transparent formula or model for distribution in place. The politicisation of such transfers remains a key concern and DFID will use diplomatic channels and push for the inclusion of this issue in the benchmarks of multilateral institutions (e.g. World Bank, AfDB and EU budget support and IMF instruments) to seek a resolution.

The MPF has pushed forward various processes across different sectors to try to improve the approach and support policy dialogue on this fundamental resource allocation issue, for example:
- The MPF-supported Financial Governance Committee (FGC) joined several FGS/FMS meetings in 2018, with practical recommendations on the topic. These were reflected in an initial Fiscal Transfers Policy Paper by the FGS, discussed with FMS in November 2018, but that seems to have lacked sufficient wider political support (related to FGS-FMS relations) to produce a tangible outcome;
- On revenue sharing, for petroleum, the MPF supported a consultative process that led to an agreement. Achieving consultation and ordered dialogue on this topic is a result in itself but unfortunately due to low capacity in the Ministry, it did little to shape the legislation put earlier this year to Parliament - which is now stuck in the lower house and, we heard from key informants, generally criticised as incapable of implementation. The FGC have already underlined the risks associated with inappropriately designed revenue-sharing agreements, particularly in the petroleum sector;
- Agreement has been reached on fisheries, but this is limited to a one year rolling basis.

The picture has been one of poor progress on a subject of fundamental importance. Plainly the topics of revenue sharing and fiscal transfers are highly sensitive and are tricky areas for the international community to engage in without adversely affecting some existing relationships. . Current FGS-led discussions appear stalled and in any event seem unlikely to dispel perceptions of unfairness. It remains to be seen how far the requirements for agreements and system-building included in the benchmarking for HIPC decision point will achieve breakthrough.

O1.4. Improved treasury management, budget execution and procurement in FGS, regional member states and SL

While there has been significant improvement in the overall treasury management and budget execution (see outcome section), the two technical milestones for this sub-output have not been delivered.

The project has supported the development and deployment of the Financial Management Information systems which, have been used for their Budget execution and most transactions are processed through this system including payroll (covering the security sector as well). International Public Sector Accounting Standards (IPSAS) basis of accounting and Treasury Single Account (TSA) have been adopted in FGS and are now being adopted in Puntland and Somaliland. PFM Legislations have been enacted in FGS, and even though Puntland and Somaliland have their Acts, these are being revised. An independent Audit bill for FGS has stalled for several years and with limited domestic political appetite, is likely to require efforts on the part of partners to engage government on this for progress to be made. There has been limited activities for procurement except some limited capacity building activities and working with EU to help set up a website.

The provision of donor funds directly to line ministries, agencies and Federal Member States means not all funds are included in government financial reports. The government, with support from UNDP are developing templates for reporting information using the Aid Information Management System (AIMS). The second step will then be an engagement that will bring such support through the TSA and eventually give the government ability to include these in the annual financial reports. Donors also need to take responsibility in ensuring all their support is reported to the FGS.

The fixed assets are reported in financial reports (as an annex) but assets are not automatically registered on SFMIS as previously discussed. As a result, the fixed asset reporting is being done manually.

Integration of Core Banking system with SFMIS; The successful installation of the banking system and its integration with the SFMIS is still not complete. Independently these 2 two systems are operating but integration has yet to be completed and does not seem to be making progress. The accountant general’s office has not received the required TA support from their existing consultants and continues to have challenges in gaining access to available technical assistance. Under another World Bank funded project, a new systems’ integrator has been engaged for the office to focus on this assignment. It is not clear when this task will be complete or whether the current people involved have the technical knowledge to do so.

Lessons identified this year linked to this output and recommendations for future programmes

Implementing partners and donors acknowledged the good coordination between the MPF and the DFID and EU-funded PREMIS programme which is supporting PFM in the FMS. It was noted that coordination could be improved in this area (including with the IMF and AfDB) through the establishment of more formal mechanisms and that there should be more formal joint dialogue on the issue of PFM between donors, the FGS and FMS. Such dialogue has already commenced and will be stepped up in the coming months as the successor to PREMIS is designed.

With PREMIS and the MPF both providing PFM support in Somalia, this has inevitably led to beneficiary comparisons between the two delivery models and partners. In some ways this has helpfully highlighted aspects we can look to replicate across the support – for example. the need to have clear lines of accountability so that beneficiaries are clear who should be contacted when things go wrong. However, in other ways beneficiaries have differences in approach, at times on mundane aspects such as the provision of Per Diems. Due consideration of all these issues will be needed in the design of future PFM support in Somalia.
Output Title	Strengthened public sector management capacity
Output number per LF		2	Output Score	A
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
O2.1 Staff appointed to key positions in FGS and regional member states through approved CIP procedure (cumulative, % women)	FGS: 210 / PL: 110 / (20%)	A [see justification below] / FGS: 110 (28% women) / PL: 104 (29% women)
O2.2 Ministries/agencies with operational HR functions	FGS: 7 / PL: 7	A+ / FGS: 7 / PL: 9
O2.3 Improved civil service management functions / [more qualitative to capture TA activities]	Civil Service Pay Policy and phased plan for implementation developed and submitted for Cabinet approval	B / Plans not yet submitted to Cabinet
O2.4. Transparency & Accountability: / i) # of monthly payroll reports published on the MoF Website. / ii) # of fiscal summary reports published on the MoF Website	i) 12 / ii) 12	A [See justification below] / i) 0 / ii) 12
[note] A ministry/agency is considered to have an operational HR and FM function in place when at least three of the four criteria below are met: i) organogram developed, ii) Unit staffed (at least 60%), iii) Unit staff trained, iv) produces key outputs (e.g., financial reports, HR records).

Provide supporting narrative for the score

Sub-outputs 2.2. and 2.3 are probably the most important elements. With one sub-output exceeded (A+), one falling short (B) and two meeting the milestones (A), an overall score of A is considered appropriate.
O2.1. The Capacity Injection Project (CIP) builds civil service capacity and works to improve transparency and efficacy in public service recruitments. While CIP struggled to get off the ground due to security issues, the project is now performing better and has Completed recruitment, filling critical positions across the FGS and Puntland, with pay in line with an approved, harmonised pay scale. Given fiscal constraints there has been a decision by FGS not to consider future hires as CIMs, instead integrating them into the mainstream civil service pay and grading system. As such, the World Bank revised (in April 2019) their future target for CIP recruits down to 110 for the FGS. The failure to meet this target is therefore a reflection that the FGS is giving due regard to fiscal sustainability [output 1.4], rather than a recruitment failure, and we have scored this output an A, despite failing to meet the numerical target. Puntland met the target for recruitment but numbers have dipped slightly as a small number of CIP staff have resigned and yet to be replaced.
O2.2 The government has completed organizational reviews for all MDAs to pave the way for streamlining mandates and functions, and appropriate skills alignment. All common function positions (including Human Resources and Financial Management) have been filled and financial reports are produced, and HR records are in place and available from the Civil Service Commission and the MDA HR Departments.
O2.3 , FGS is concluding procurement of the Technical Assistance and Puntland is about to validate the final outputs of the pay and grading assignment which includes the pay and grading policy. However, the timeframe for these to be submitted to cabinet is uncertain given Covid-19.
FGS has completed the organizational reviews for all 48 MDAs. An inter-agency government team has been formed to incorporate additional; technical comments in the organizational review reports. Puntland State of Somalia (PSS) has completed organizational and modernization assessments for all the 43 MDAs and Government organizational ordinance has been developed to provide more clarity on mandates, vision, mission, functions, accountabilities, structures, staff complement and establishment ceilings for these MDAs.
PSS has now rolled out the approved Administrative rules, procedures and regulations that have were developed from the HR policies. In FGS, an inter-agency government team has been constituted, led by the Ministry of Labour and Social Affairs, to prepare administrative rules, procedures and regulations for the HR policies that have been developed.
Several human resource policies including merit-based recruitment, promotion, performance management, career management, competency management, coaching and mentoring, etc. have been developed. These policies will be implemented in the broader civil service to broaden impact on public administration.

O2.4. Transparency & Accountability: (RCRF & FGC payroll and fiscal reports)
The MPF has invested in key Public Financial Management (PFM) systems, bringing about increased capacity, transparency, and sustained reforms as well as a strong technical collaboration between the Federal Ministry of Finance and the Ministries of Finance in the Federal Member States. These investments are providing the foundations for donor engagement in other sectors, which rely on strengthened country systems for recipient execution. Working through country systems is improving federal and subnational governance and intergovernmental relations, as illustrated in the quality and ambition of the policy environment and fiduciary control. The shift towards greater transparency and accountability was demonstrated by the Federal Ministry of Finance’s (MoF) website, which includes information on all government revenue and expenditure data reported under the Financial Management Information System (FMIS).
Note that while there is excellent transparency through the MoF website, in 2018 the frequency and form of financial reporting was changed; with quarterly reporting on a more detailed and user-friendly basis. As such, while the target was not strictly met, the degree of transparency is such to score this indicator an A.

Lessons learned
The Effective, Accountable Government portfolio demonstrates that constructive inter-governmental relations are possible in the midst of an evolving political climate when framed around a solid technical agenda. Future work should focus on identification of technical areas to drive progress on these political issues..

Output Title	Enhanced economic and sectoral policies and enabling environment for economic development.
Output number per LF		3	Output Score	A
Impact weighting (%)?		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
O3.1. Operationalisation of the Somalia Business Catalytic Fund (SBCF) and Small Medium Enterprise Facility (SMEF): / (i) grant applications received; and / (ii) awarded, by region / (iii) Private sector investment (committed as co-payment) by Catalytic fund recipients / SBCF operated from July 2016 - January 2019 and SMEF operated from July 2016 - April 2019.	(i) South-Central:500 Puntland: 500 Somaliland: 500 / (ii) Granted: 201 / (iii) $6,000,000	A / (i) SC 522; PL 476; SL 752 / (iii) 101 grantees / (iii) US$6.5 million in private capital mobilized by Small & Medium Enterprises (SMEs) supported by SBCF was higher than target despite disbursing approx. 50% of allocated funds to business (US$5.3m disbursed of $10m allocated).
O3.2 Training: / i) # of individuals receiving subsidized BDS, TVET or other forms of training financed by the SCORE project / ii) Total annual increase in revenue of firms supported by SBCF and SMEF that received training and advisory services	i) 1500 / ii) 15 – subsequently determined not the correct measure and replaced with % increase.	B / (i) SMEF trained 1,175 individuals (75% of the target) through 45 trainings. (ii) Increase in average quarterly revenue across all firms per region: Somaliland (194%), Puntland (527%), South Somalia (61%)
O3.3 Improvements in the regulatory environment for private sector development / i) # of diagnostic reports on legal, regulatory, institutional and infrastructure setting aimed at supporting private sector development (cumulative)	i) 8	A / (i) 10 diagnostic reports. Substantial gains were made drafting and adopting laws and regulations to improve the business environment.
O3.4 Supervisory capacity within the remittance sector: Trusted Agent operations, including # Money Transfer Businesses (MTBs) supervised (on or off-site)	i) 8	A+ / Project helped to kick-start formal regulation and oversight of all 12 money transfer businesses (MTBs) by the CBS. / .
O3.5. Greater contribution of Information Communications and Telecoms (ICT) sector (through taxes and license fees) to public treasury enabled.	Regulatory Authority described in the Communication Act established and regulatory framework drafted including tax regime	B / While the regulation of telecommunication companies improved with the passing of the Communications Act, companies are still negotiating contributions to the treasury rather than being held to a tax regime, resulting in potential loss of revenues.
O3.6 Feasibility and preliminary design studies for specific urban investments completed.	Studies completed on; / Primary roads in Mogadishu and Garowe; secondary roads in Mogadishu; solid and liquid waste in Hargeisa).	A / Feasibility studies, preliminary engineering designs, and safeguards instruments have been completed for the rehabilitation of urban secondary and tertiary roads in Mogadishu and Garowe to improve people’s access to basic services. Activities were completed by December 2018.
O3.7 Total number of direct jobs created in enterprises supported by the Somali Core Economic Institutions and Opportunities (SCORE) project (Cumulative) / i) Total / ii) Women / iii) Youth	i) 2000 / ii) 650 / iii) 800	A+ / i)Total: 2,217 (exceeded by 11%) / ii) Women: 634 / iii) Youth: 1,343
[note] The target number of grants awarded should have been revised downwards as the scale of grants was revised after the SCORE MTR – WB MPF target is 85. Of 101 selected, 19 dropped out as they couldn't meet performance-based conditions

This output has developed a wide-ranging portfolio of projects aimed at creating an enabling environment for economic growth, spurring growth in productive sectors, and increasing access to finance and sustained remittances. Supporting development of urban infrastructure and inclusive resource sharing arrangements were increasingly important associated aims.

By and large where the delivery of outputs was directly in the hands of WBG targets were exceeded/met, but where delivery depended upon implementation by the Federal Government of Somalia progress has been slower to materialise, particularly when parliamentary approval of legislation has been required.

Key achievements include:
- Drafting and approval of key pieces of legislation to include the Mobile Money Regulation which came into force in February 2020 and the FGS Companies Bill approved by the Upper House in December 2019.
- The establishment of Public Private Dialogue (PPD) mechanisms between the Government and the private sector (initially in Mogadishu and in Hargeisa) surveying opinions on ease of doing business and helping prioritise reforms to support economic growth. In Hargeisa, the PPD is reported to have facilitated an agreement between the public and private sector on electricity supply reform, though it is too early to take a view on the impact of the PPD’s initial activity.
- The development of the regulatory capacity of the Central Bank of Somalia (CBS) to tackle structural issues not least the supervision of MTBs. Technical assistance to the CBS was designed to complement other activities tackling key deficiencies affecting broader and longer-term financial sector development in Somalia; not least the UK / World Bank 'Safer Corridor Initiative' (focusing on the UK-Somalia remittance corridor). While these proposals were initially geared towards developing contingency mechanisms in case of severe disruption of remittance flows between the UK and Somalia, they evolved towards tackling the more structural issues impacting remittance flows to Somalia in general.

Key challenges:
- In the early days of at least one of the projects, changes in the management of the Project Implementation Unit (PIU), as well as frequent changes in Ministers, caused a series of delays to implementation. Unpredictable financing from donors also made project planning difficult.
- Slow pace of drafting and approving key pieces of legislation. For example: the Somalia Bureau of Standards Bill still awaits a first reading in the Lower House; The Investment Law and Electricity Act have still not yet been published, and; The Company Law has yet to be enacted. The challenges in enacting these may be linked to a general challenge of the ex-post public regulation of purely private sectors.
- Lack of coordination between international partners in the sector. The Financial and Private Sector Development Forum (November 2018) found that this was resulting in significant duplication of activities, such as for example between DFID business development activities and the MPF SCORE grants schemes. This was part of the motivation for scaling back and refocussing SCORE and for establishing key fora such as the Somalia Remittances Stakeholder Advisory Council co-chaired by the FGS and the World Bank.

Lessons identified this year linked to this output and recommendations for future programmes
Build in practical political economy analysis, particularly where activities are dependent on state regulation. The weak regulatory environment means that even when laws are passed, they are insufficiently implemented. The Telecommunications Act is a good example of this. Such political economy analysis should consider how best to incentivise businesses to change; to date businesses have not been supportive of enhancing the regulatory environment, even when this could benefit them.

Future programmes should consider how to work with and strengthen financial institutions; there is a need to identify more critical interventions beyond lending to banks.

Consider the sustainability of interventions particularly those directly delivered by the World Bank Group. This was a critique raised by the SCORE Mid Term Review, which resulted in the Somalia Business Catalytic Fund (SBCF) being scaled back in order to focus efforts building foundations for market-based financial intermediation thereby supporting enterprise growth, jobs, and livelihoods on a sustainable basis. In order to do that, the commercial case for reform needs to be carefully made.

Make provision for robust monitoring, evaluation and learning throughout intervention delivery, including potentially for clients. The review point was key to adjusting the SCORE programme towards a more sustainable, systemic approach. the analytical work on women’s access to microfinance and microfinance providers has informed sector-wide activities. Stronger analytical frameworks and increased capacity would have generated more robust evidence, for example on jobs numbers, and provided insights into the relative impact of approaches.

Output Title	MPF is effectively managed
Output number per LF		4	Output Score	A
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
O4.1 Implementation of an effective MPF wide approach to risk management [revised] / i) # of quarterly reports and corresponding donor briefing sessions by Monitoring Agent / ii) Evidence of risk management response to issues raised / iii) External review of Joint Risk Management Strategy (JRMS) conducted / iv) DfID and World bank work collectively to improve strategic implementation of JRMS (qualitative)	i) 4 / ii-iv) qualatively assessed	Score: B / i) 2 / ii) – iv) see text below
O4.2 MPF disbursement and commitment ratios of signed project grants (signed more than 4 months prior to the end of the calendar year. / i) Disbursement ratio of signed project grants (signed more than 4 months prior to the end of the calendar year) including RCRF/ Excluding RCRF / ii) Commitment ratio of paid in donor contributions (transferred more than 4 months prior to the end of the calendar year)	i) 60%/ 50% / ii) 50%	Score: A+ / i) 65% [including RCRF] / 51% [excluding RCRF] / ii) 85%
O4.3. Consultation and transparency / i) # of consultative group meetings held with both donors and Minister of Finance / ii) Publicly available documents available on the MPF website / iii) # of annual consultative group meetings with donors addressing fund, sector or project-level issues / iv) Annual consultation on the quality of dialogue and fund management between World Bank and donors hosted and minuted by DfID (Introduced in 2018)	i) 2 / ii) / iii) 12	Score: B / i) 2 / ii) The MPF website has migrated to the core Bank external website infrastructure and all documents available . / iii) All MPF projects have been consulted with relevant Working Groups during design, and 11 MPF Consultative Group meetings were held in 2019 alone. / iv) Held in November 28, 2019 to discuss the MTR findings and present the MPF repurposing in light of IDA. In addition, several Performance Learning Review meetings were held to discuss adapting the portfolio.
O4.4 MPF portfolio is gender and conflict sensitive / i) % of RE projects with WB gender flag and accompanying justification / ii) % of MPF projects that utilize conflict analysis to inform project management, going beyond basic World Bank requirements for project preparations	i) 80% / ii) 100%	Score: A / i) 75% / ii) 100%

O4.1; The MPF deploys the full WBG repertoire of policies and procedures for managing fiduciary and other risks related to implementing the Fund’s projects and is managing risk ‘satisfactorily’ according to the WBG measurements. As noted by the MPF Monitoring Agent in its analysis of the portfolio, the MPF is “outperforming” the global World Bank portfolio (average of 3.5 vs. 3.4 for progress towards achievement of Project Development Objectives and 3.7 vs 3.2 for implementation progress) in spite of its higher level of risks. The MPF MTR questioned whether the risk management structure and system are sufficiently granular and reactive for Somalia, where sub-national systems are still weak. Some of the tools to manage higher-level risks at portfolio level require remedial attention (such as the moribund Risk Management Group established under the Joint Risk Management Strategy for the three Somalia Development and Reconstruction Facility (SDRF) Funds). The Group received only little support from Donors (including DFID), and these lessons have been shared with Development Partners for improvement as part of the external review of the JRMS. Unfortunately, no substantive improvements have resulted from the review and the Groups has been inactive for almost two years.

O4.2: As a result of working predominantly through in-country systems, the Bank have increased absorbtive capacity. This, combined with pacing commitments in line with donor contributions and absorbtive capacity (choosing to employ monthly disbursals for the RCRF), has enabled disbursement ratios to increase.

O4.3 – While consultation with donors has been strong, in several areas, the coordination, particularly on programme design could have been improved through the establishment of more formal coordination mechanisms. The Mid-Term review noted that the WB should engage donors much earlier in the design process. This appears to have happened at a sectoral level (e.g. health, urban) – with a noticeable improvement in programme design. The World Bank acknowledged that there is still scope to improve discussions around additional financing (e.g. IDA) with the wider support that donors are providing. There is also room to improve the quality of engagement at the portfolio level, which remains challenging due to the varying degrees of interest from donors.

Lessons identified this year linked to this output and recommendations for future programmes

There are some areas where performance could be enhanced. In particular, the emergence of an integrated IDA-MPF portfolio intensifies the need for more effective communication, coordination and consultation between the MPF, its donors and other international stakeholders. The changing context requires all stakeholders to work even more closely and collaboratively to meet their shared objectives to ensure the reconstruction of Somalia.

In summary:
1. The WBG and donors should continue to work together to prioritise and promote a more open collaborative culture, incentivising donor engagement and actively seeking out new partners. As programming shifts from the MPF to IDA; DFID should push the World Bank to replicate the MPF local governance6 and coordination structures for IDA programming [they have already made encouraging steps in this area], and explore how these structures can be strengthened.
2. The WBG should work with international partners and potentially synergetic programmes to clarify expectations on the key strategic and political issues requiring negotiation and agreement. In parallel, the MPF should create opportunities for greater outreach to FGS and FMS leadership on such issues. This process should build further on the FGC model of targeted technical work combined with analysis and open discussions to help drive progress.
3. The MPF and development partners could arrange more collaborative and engaging approaches to risk and ensure that risk management includes cross-portfolio risks, analysis of residual levels of risk, plus escalation processes for when risk rises above acceptable tolerances. Gender-based violence (GBV) risk prevention should be strengthened as well as precautionary responses to such issues.
4. The MPF should work with all stakeholders to improve evidence available on substantive project level outcomes (e.g. creation of productive new jobs) and the quality of the indicators used to monitor progress. Where practicable, beneficiary views should be incorporated into monitoring reports to help understand how projects are perceived by affected communities.
5. The MPF should enhance the utility and value of knowledge products by improved codification, dissemination. In parallel, it should work closely with donors and other stakeholders to identify lessons, including from Monitoring Agent reports, and integrate them into existing and future programming.
## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES (1-2 pages)

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The table below outlines progress against the impact and outcomes in the logframe.

	Target / (December 2019)	Progress (December 2019)
IMPACT
1. Real GDP growth per annum	6.0%	2.9%
2. Nominal value of domestic revenue collection at federal and regional member state level	FGS: $153m	FGS: $230m
OUTCOMES
1. Government demonstrates progress on key governance reforms and benchmarks, as demonstrated by achievement of an increased % of RCRF annual review benchmarks.	75%	Target exceeded / 86% (6 of 7 achieved).
2. Federal government demonstrates improved fiscal discipline, revenue generation and cash management, as evidenced by more regular salary payments. / (i) # of months of civil service salary payments outstanding at the end of year / (ii) average days between payments during year	(i) 2 / (ii) 30	Target exceeded / (i) 0 / (ii) 30
3. Increased uptake of Financial Governance Committee (FGC) recommendations. / (i) # of contracts/concessions reviewed by FGC (cumulative). / (ii) increased #/% of FGC confidential assessments with evidence of FGC recommendations being implemented (Cumulative)	(i) 32 / (ii) 21	Target exceeded / (i) 49 / (ii) 29
[note] Previous logframes had an impact target for nominal GDP. Given the substantial ex-post revision of historic GDP estimates over the lifetime of this programme, this target is not considered meaningful and has not been reported against.
[note] Some FGS civil servants (c. 20%) are paid from the RCRF Designated Accounts (DA). Payments from the DA are in some cases later than those made of the Treasury account, due to a lack of liquidity in the DA. For the months of May and November 2019, and for January 2020, payments to those civil servants were made in the following month, on June 3 2019, December 12, 2019 and 3 February 2020 respectively.

The programme achieved some noticeable success, with all targets either met or exceeded. The exception was the impact target related to GDP growth, which was not met. Such a target was unrealistic given the persistent droughts and dependence on agriculture in Somalia.

As the programme has focussed on establishing the institutions and processes of the Somalia state, with some systems and processes difficult to circumnavigate, much of the progress made should endure regardless of the direction Somali politics takes. However this does not apply across all outcomes; there is a risk that a more corrupt government could drive lower compliance and weaker public finance management in some areas. Thus parallel work to help support a stable and accountable government are needed to ensure the sustainability of outcomes.

Theory of change & lessons learned
The SERs programme was designed on the assumption that Somalia’s low level of income and wide-spread poverty is down to low levels of investment. This, in turn, is due to a dysfunctional state, weak governance, poor security, unregulated private sector, low-level of human capital, and inefficient financial intermediation. The programme assumes that a capable and well-functioning state is the single most important precursor to Somalia’s economic stability and prosperity.

The results chain and key assumptions depicted in the diagram below illustrate how activities related to: (i) improved core state functions, (ii) public finance management, (iii) capacity building for economic policy formulation and implementation. (iv) enhanced public institutions for enforcement of laws and regulations, and (v) better ability of the private sector will contribute to the objectives of increasing domestic resource mobilisation, investment, income generation, and creation of more and better jobs.

SERs Theory of change (from 2017 business case extension)

The World Bank conducted a Systematic Country Diagnostic in 2018 which allowed a more dynamic understanding of the the constraints facing development in Somalia and the more complex assumptions linking institutional reform to effective states. This identified both a fragility trap and resilience trap that one should look to address (further details provided in 2019 SERS Annual Review). While this work improved the depth of understanding, the assumptions in the theory of change remain broadly valid;

On (i) and (ii), technical assistance has strengthened key institutions, with significant gains made on public financial management. The recruitment of advisers through the Capacity Injection Model (who are viewed by Ministers as Government rather than WB advisers) should lead to a more professional civil service, although further work on areas such as a pensions policy is required to make this truly sustainable. These interventions have been complemented by the work of the FGC which has sought to ‘police’ public financial management through the continuous reviewing of contracts and processes. The FGC has also helpfully linked with donors and allowed the latter (including DFID) to use our diplomatic dialogue to help drive progress. At times, the wider political discourse has not always resulted in the passing and implementation of effective policies, with legislation getting stuck in parliament, or processes being followed (e.g. on petroleum) against the advice of the technical experts. A greater consideration of the political economy, along with engagement with a wider range of political actors, may improve the chances of success, although it should be noted that progress in some areas will always be challenging.

On the area of economic development, while outputs have been delivered, the failure to test assumptions in the Theory of Change makes it difficult to assess whether these have directly driven the desired outcomes and impact. Future programming in this area will need to shift from a focus on model policy and regulatory structures to those that are actually going to be implemented - based on political economy analysis. The MPF has produced some interesting Political Economy Analysis, and the future challenge will be to ensure this is fully shaping the programme design. Consideration should also be given to identifying regulation that goes beyond the state e.g. could be best delivered through self-regulation or private entities. This should take more of a sector/problem driven approach, and scan sectors to see which actors are best positioned to work

In seeking to enhance the legitimacy and accountability of federal and regional governments in Somalia, the programme has effectively facilitated sustained technical dialogue on areas such as fiscal transfers and revenue sharing and a harmonized customs regime. Achievements in this area have been against a backdrop of tensions in the political relations between the FGS and FMS. Future work will be needed (supported by the MPF, PREMIS programme and others) to getting beyond the regular flow of resources, and investments in good practices and procedures to shifting the FMS (and other tiers of government) to actually increase its spending on social sectors and areas with a tangible benefit for the Somali population.

Key to the success of a portfolio approach such as this one is a strong theory of change and framework with which to verify and test results. This approach leans heavily on output and outcome measures that are not best placed to tell the story of whether interventions are helping to unlock elements of the development trap that Somalia finds itself in. Future programming should therefore give more consideration as to whether an approach to M&E that allows for a more problem-driven-adaptive (PDA) approach is possible within the context of the Multi-Partner Fund. Alternatively, donors should give more consideration to which programming is most in need of a PDA approach and should therefore be delivered outside of the MPF.

There is also a gap in monitoring the assumptions which is putting achievement of outcome level goals at risk. The WB is operating at an operational level, not always engaging in policy discussion. If we also assume that this is happening and being effective, when it is not, we risk not achieving outcomes.

Explain major changes to the logframe in the past year (1/2 page)

There have been no major changes to the logframe over the last year.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme (1 page)

The main cost drivers for the programme were staff costs, security, travel, and procurement. DFID Somalia and the Bank sought to contain these costs, by developing a harmonised approach to pay of advisers placed within externally funded projects

On economy, the breakdown of spend is as follows;

		US$ Millions	% of total
Administration	MPF Administration	$11	2.8%
Management	Monitoring Agent & Preparation	$14.5	3.7%
	Supervision	$15	3.8%
Delivery	Bank Executed Grants	$47.9	12.3%
	Recipient Executed Grants	$302.5	77.4%

Thus 89.7% of expenditure was on grants (either receipient or bank executed) with only 2.8% on administration and 7.5% on management (preparation, monitoring and supervision)..

These administrative costs remain comparable to other administrative fees charged by multilaterals. The Investment income from the MPF has broadly netted out the total fees paid by donors and is expected to exceed fees in coming months based on the pace of accumulated interest. In addition, the MPF continues to achieve economies of scale by investing in services at the fund level, such as the monitoring agent and security and logistics platform.

The MPF has provided a mechanism to pool donor resources and coordinate policy dialogue across donors with the Government. This has driven value for money by ensuring efficiencies from economies of scale.

Efficiency is measured by the Funds disbursement ratio which has improved over time, reaching 75% in 2019 (or 62% not including the RCRF) compared with 73% in 2017 (or 58% not including the RCRF). This demonstrates an improvement particularly for the RCRF which represents the bulk of MPF payments.

Effectiveness has been improved by the pooled nature of the programme. This has effectively reduced fragmentation of donor efforts and achieved greater economies of scale. The MPF has also been helpful in supporting coordination between the partners working with Government or within Somalia’s private sector. In some cases, strong partnerships have been forged that have led to the development of joint/ synergized policy/programming work, notably on SCALED UP and Financial Institutions Development Project (FIDEP).

On effectiveness the MPF has achieved progress on the state-building agenda, particularly in building the systems able to process payment of civil salary wages through country systems. There has also been important progress on building the institutions to regulate Somalia’s critical financial sector, work on mapping out investments in urban areas to stimulate urban economies However given the breadth of the Fund’s focus and its expansive activities, it is difficult to aggregate the Fund’s impact and develop a meaningful unit cost indicator to represent the Fund’s portfolio, especially given the lack of meaningful comparators. In terms of internal measures, the WB’s internal project-level scores find that 100 % of active operations have been rated moderately satisfactory or higher.

On equity, the fiscal transfer component of the MPF, although relatively small at this stage, has helped in progressing equity considerations, especially the MPF’s outreach to different Member States of Somalia. Fiscal transfers to the regions have scaled-up significantly through WB resources (RCRF and Surge support) from US$ 6.7m in 2017 to US$11.8m in 2018, representing a 75% increase. The issue of clan (and the risk that development support drives inter-clan conflict) is significant in Somalia. It is not clear whether the World Bank are actively monitoring this, and any future programming will need to address this issue more pro-actively.

The CIP recruits targeted the recruitment of women, with 29% of recruits being female (up from 23% in 2016). This is impressive in the context of Somalia, which has high levels of gender inequality on most indicators.
E: RISK (½ page)

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

Despite the changing nature of the programme and evolving risk environment. The overall risk rating of the programme is Major, with the risk appetite of the programme remaining at major.
  . Operational, reputational, financial and political factors inhibit achievement of project purpose in this highly fragile context in which this programme operates. Enhanced controls applied to the management of this programme have worked to bring the overall level of risk down. Some of the key control measures include (e.g. third-party monitoring, RCRF payment on reimbursable, monthly donor consultation groups where administrative agreements are discussed as well as risk mitigation).

Overview of programme risk

DFID used to maintain a risk matrix specific to SERs, however given that many of the risks are those identified in the DFID Somalia portfolio-whole risk matrix, the two were merged. DFID used to be an active member of the Multi-Partner Risk Working Group led by the WB and the UN. However due to a lack of quorum from the donors, this group has not met since mid-2017. Despite a request from DFID to re-establish the group, once again there was a lack of availability from other donors. Along with the mid-term review the WB has agreed to discuss how to take forward the recommendations from the Third-Party Monitoring Agent’s (TPMA’s) risk assessment and incorporate into monthly Consultative Group meetings. A summary of these are below.

At project-level. The MPF mid-term report finds that: on average MPF projects outperform global programmes implemented by the WB in terms of implementation and progress towards development project objectives; and despite higher risk ratings, fewer problems are reported in the Somalia portfolio than compared to Africa portfolio. The fiduciary risk of both project financing and financing directly through Government systems is managed through policy design and tight structures and systems in place. In addition, ex-post reviews of transactions have been used to identify issues with project expenditure, demanding repayment from government where necessary, but also identifying areas in need of improvement.

At a portfolio level the report highlights four other types of risks:
- Delivery risk, given WB standard procedures and the shift away from strategic design to managing fund flows once projects move to implementation. The WB’s institutional constraint to continue policy dialogue during implementation is particularly risky in a difficult and complex environment such as Somalia. In some cases, projects have found ways of actively engaging with delivery, actively guiding and advising government on the implementation of programmes. But this is not standardised across projects and not always addressed.
- Dependency risk – as in not making the most of the positive impact projects can have on another – this is most relevant institutional development projects.
- Physical infrastructure projects. The institutional risk is currently managed through PIUs and tight controls, but procurement procedures have presented challenges, which will only increase as projects go to larger scale. Issues include verifying business information, track records and ownership, as well as environmental and social risks as Government frameworks are insufficient
- Expanding scope of social protection. Comes with heightened risks also: limited data to monitor discrimination and long-run conflict and violence impacting behaviour, and minima public trust in state mechanisms for addressing grievances, especially for issues of sexual exploitation and gender-based violence.
Partnership Principles
With nearly 75% of the MPF’s funding allocated to projects implemented by the Somali government, consideration of the partnership principles has been important in managing this programme.
The most recent Partnership Principles assessment (2018) noted that “government had made important High-level commitments through the New Partnership for Somalia to accelerate peace, state building processes and economic recovery and reconstruction”. The trajectory since this assessment (with regard to state building and poverty reduction) has been broadly positive, with the development of Somalia’s 9th National Development Plan (NDP) in 2019.
The objectives and priorities of the MPF are aligned with the NDP and the MPF is accountable to the Somalia Development and Reconstruction Facility (SDRF) co-chaired by the Prime Minister. The development of the Mutual Accountabilty Framework (MAF) also provides a framework and forum to drive progress on the Partnership Principles, although its effectiveness at doing so has been relatively mixed.
With the strong approach to fiduciary risk management from the World Bank, DFID considers the risk of misuse of funds is at an acceptable risk level, particularly given the programmes explicit objective to strengthen state institutions and financial management systems and practices.
The direction of travel against respecting human rights and domestic accountability is more mixed. The current political instablility (with the Prime Minister removed in July 2020) and the upcoming elections present a new set of risks and we will need to consider these issues, along with ongoing tensions between the FGS and FMS in the next partnership principles assessment and in the future aid modalities we use in Somalia.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Financial performance

The budget was made up of contributions to two trust funds: £64.4m for the World Bank multi-partner fund and £5m for the IFC trust fund. An Administrative Arrangement had scheduled dates of various disbursement and all were met. Payments were done bi-annually after satisfactory expenditure reports were presented. WB utilised internal accounting system which ensured each contractor and project activities were clearly outlined.

The breakdown of spend by component during the project lifetime is as below:

Component Description	WB Multi- Partner Fund for Somalia	WB - Multi-Partner-Safer Corridor Initiative Project to support remittance flows to Somalia	WB - Multi-Partner Fund - Capital Expenditure	IFC	Total
Budget per component	60,600,000.00	2,400,000.00	1,400,000.00	5,000,000	69,400,000
Spend per component	60,600,000.00	2,400,000.00	1,400,000.00	5,000,000	69,400,000
% of the total for the overall programme	87.30%	3.45%	2%	7.20%	100.00%

Quality of financial management

World Bank provided six monthly reports to compare actual spend against the planned spend. A statement of assurance was completed for the MPF in February 2019, which found that although the risks remained high, the WB was making progress to strengthen the Governments Systems through which the majority of the MPF funds are executed. The recommendation from the due diligence carried out in March 2019 indicated that online financial reports were not updated in real-time with the commitments made and hence affecting reliance on the same for DFID internal reporting on the project. DFID continually monitored the change of on the online financial reports and ensured funds were fully utilized as per commitments and that prepayments amount was reduced.
The WB has taken measures to ensure good financial management. These include: regular financial management supervision missions, use of externally staffed External Assistance Fiduciary Services (EAFS) to prepare withdrawal applications, reimbursements and procurements, fund held in separate designated account in central bank and risk unit review payments and risk level on regular basis.
Advance thresholds are based on risk assessments. Expenditures are deemed eligible for reimbursement based on actual amounts expensed. Use of external audit firm to conduct audits has led to better transparency. Asset management was carried out under the WB management policies of asset management. This was monitored by the third part monitor who undertook asset verification to ensure project assets are safeguarded. The asset database was managed by the WB and disposal made as per the WB policies.

Date of last narrative financial report(s)	June 2019- Vault Number 32329827
Date of last audited annual statement (s)	September 2019. No particular issues raised in this audit statement

Partner performance

DFID Somalia’s relationship with the WB has been good through the life of the programme. DFID was the first and largest donor to the MPF and has a lot of relevant technical expertice and therefore a strong voice among donors. The SRO and the Lead DFID Advisor for each project have good relaships with the counter WB officials and there is regular informal information sharing at each level ie at donor consultationa and sub-workign group meetings. SERS has been entirely implemented through the World Bank Group. In addition to the quality of fund management, outlined in Output 4, DFID has also directly engaged with the Bank at different levels, including through;
- DFID Somalia’s Senior Leadership Group, to shape the strategic focus as well as performance of the Fund. For example, two meetings have been held bringing Senior Leadership Teams from WB and DFID and key programme leads to discuss the WB Country Partnership Framework (CPF) and future direction given IDA.
- MPF Consultative Group Meetings (some involving the Somali government), organised by the Bank around the MTRs of the various MPF projects and the WBG’s Systematic Country Diagnostic and CPF.
- Focal points at the project level to cover technical areas of the portfolio, and in some case thematic working groups such as the Health Group, led by the WB that brings together the various donors working on Health.

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

The MPF’s results are measured through a compilation of indicators drawn from project-level reporting by the Bank.
More could be done to improve the quality of the indicators that are being measured. For example, it is not enough to monitor jobs created without an understanding of what a quality job is, are these truly additional, sustainable and who is benefitting. The key issues such as economic marginalisation and gender are not readily monitored in a meaningful way. With a deeper understanding of the dynamics that contribute towards marginalisation, it could then be possible to define indicators that measure change in these dynamics, and a sense of progress towards overall outcomes. Similarly, there should be some attempt to ensure activities and achievement of outputs is not leading to harm and say more entrenched marginalisation.

Systematic reporting requirements are also in place to monitor financial management, quality, progress and risks. The financial information related to the MPF can be accessed through the Bank’s Clients’ Page, including periodic audit statements. The Bank provides detailed annual progress reports setting out areas of achievements, challenges and emerging priorities.

MPF uses an external third-party monitor to complement the Bank’s internal supervision of the MPF projects. Third Party Monitoring has allowed the bank to monitor risks, identifying weaknesses in the system and in turn use this analysis to feed into the design of Government systems. The agent is directed to report on how MPF funds are executed by the Somali authorities, confirm utilization for the purposes specified in MPF grant agreements, and monitors the flow of MPF funds from the World Bank through the government systems. The monitoring agent also advises the World Bank on trends, developments, and emerging issues that relate to the MPF portfolio.

Evidence
The MPF has a knowledge production component which has been used to provide the High-frequency survey covering key socio-economic indicators for Somalia. While hugely important to further our collective understanding of the context and state of development in Somalia, the WB has been very slow to secure approval from the Government and release results. This may in part be due to the approach taken by the WB, which did not build ownership (of evidence), collaboration or capacity within the Government. Future work in this area and the wider area of statistics should place a greater emphasis on capacity building and national ownership.

In addition, the Third-Party Monitor is commissioned on a quarterly basis to provided discrete analytical pieces, such as the risk assessment report covered in the risk section. In the period under review most of these reports have been used to advice internal WB operations and have not been shared publicly. As the risk report recommends - knowledge production and dissemination should be a higher priority and an analytical component should be included in every project. DFID should encourage the WB to engage with the donor working group on Third Party Monitoring to assist in this area.

A greater focus on monitoring and evaluation would make an important contribution to the relatively weak body of evidence of the context and development initiatives in Somalia. In some cases, such as with Private Sector Development initiatives, greater monitoring and evaluation capacity would have strengthened the weight of the evidence produced, for example the reliability of jobs numbers, and provided insights into relative impact in terms of productivity and added value of the elements of support provided. Further consideration is needed to understand how such M&E can best be strengthened; an independent M&E contract (like the production of the Mid-Term Review) would provide a more objective assessment, but building capacity within the programme at the WB may result in a better integration of evidence with programme design.

Learning
There have been dissemination events to share learning from TPM reports, but more could be done to discuss learnings with donors, but also to ensure that learnings are internalised into project design. In some cases, there has been evidence of shifting project implementation according to learnings, for example, a second round of grants from SCORE did not go ahead because it was identified that others, such as USAID’s Government, Enterprise, Employment and Livelihoods (GEEL) and DFID’s Promoting Inclusive Markets (PIMS) were delivering strong projects in this space, and that the Bank’s comparative advantage was in providing policy and regulatory support.

Lessons identified this year, and recommendations for the year ahead linked to this output
1. DFID will work with the WB project-level team to build on their evidence work. Generating evidence will also be built into conversation about future collaboration as a potential opportunity where DFID and WB can work closer together.
2. DFID should use the lessons identified in this PCR along with those from the World Bank and other development partners as the basis for a discussion on how the design and implementation of the future MPF and IDA portfolio (along with other development partner support) can be improved.

This PCR was conducted by the SRO of SERS in close collaboration with colleagues from DFID Somalia and the delivery team at the World Bank. The Federal Government (as the main beneficiary) were consulted. The report relied heavily on the independent Mid-Term Report of the MPF conducted by Aleph Strategies and completed in September 2019.