Annual Review - Summary Sheet

Title: Democratic Governance Support Programme / DIALOGO – Dialogo Local para a Boa Governacao
Programme Value: £ 9,484,658.76		Review Date: April 2017
Programme Code: 201958-102	Start Date: Implementation from March 2013	End Date: December 2017

Summary of Programme Performance
Year	2013	2014	2015	2016	2017
Programme Score	A	A	A	A+	A+
Risk Rating	Medium	Medium	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review

The Democratic Governance Support Progamme - DIALOGO - aims to improve decentralised governance and accountability between citizens and municipal governments. The project is implemented in five municipalities of Mozambique: Maputo, Nampula, Tete, Beira and Quelimane. It operates in a context where the decentralisation of powers is still being contested between the government (FRELIMO) and RENAMO, its main opposition. While municipalities continue to operate in an autonomous manner, their roles and responsibilities, in particular around service delivery remain unclear.

This is the last Annual Review of the Project covering 5 years of implementation. The project was extended in March to December 2017 for 10 months to further strengthen the project’s influencing capacity, to broaden its impact and consolidate its impact in the five focus municipalities.

The objective of this programme is to bring municipalities and communities together to address communities’ concerns and issues such as sexual violence, land rights, lack of infrastructure (eg. bridges and roads), access to water, etc.

The focus of the last year of the project for the civic engagement component is to deepen and measure the sustainable impact of civic groups by supporting them to reach out and involve a wider range of citizens in their work. In practice, this is done by disseminating best practices and ways of working among other non-Dialogo beneficiaries. The project has in the last year reached out to 33 new neighbourhoods and targeted a total of 69 new civic groups and organisations. Success stories include better waste management in Quelimane and Tete, joint solutions for primary health care in Beira and electricity and water management and participatory budgeting in Nampula.

One of Dialogo’s success story is the media component. Throughout the project, this has been a great tool to communicate and discuss issues mainly through local radio stations and newspapers, and also educate and empower citizens and municipalities to come together. The project has focused in the last year on strengthening the media business model so that radio stations can be self-sustainable after the closure of the project. Another priority was to strengthen journalists’ competencies to improve the coverage of municipal governance issues.

The third component of this project prioritises municipal engagement mainly by engaging with and demanding more transparency and responsiveness towards citizens’ needs and demands. The priority this year will be to institutionalise best practices and ways of working with communities after the closure of the project and to focus on long term strategic changes in municipal level engagement and coordination. The participatory budgeting tool will continue to be used . This can can be easily monitored and has gained traction this last year in Nampula and Quelimane. The Project is working with the World Bank and ANAMM (Municipalities’ National Association) to set up a national network for participatory budgeting and to implement it in all municipalities.

The project will end in December 2017 and priorities and recommendations, as established in the 2016 MTR and last Annual Review for the extension phase of the project will remain the following:

- Communicate lessons and dessiminate these through Exchange Events
- Continue to support the development of solutions to core municipality issues such as land rights, security concerns, and water shortage
- Consolidate ongoing activities around civic engagement and handover of participative tools that have helped build the confidence of communities and CSOs to interact with municipal governments
- Step up the policy engagement at national level particularly around the process of decentralisation and the role of municipalities play in reducing poverty

The programme has also introduced new activities in 2016 and a new approach to consolidate what works in the final year of implementation. These include in particular a new gender strategy and implementing more gender inclusion and youth targeting across all participative activities. Some of the activities include: gender budgeting in Beira, training on gender violence in Nampula and training on Women and Leadership and Communication in Maputo for all five target and non-target municipal assemblies. The Project is also improving its linkages with other donor organisations working in the same field and collaborating more effectively with Prodem (Municipal Development Programme) and the German Development Coopeeration GIZ (Deutsche Gesellschaft fur Internationale Zusammenarbeit).

Summary of progress against previous recommendations

Recommendation April 2016	Actions as of April 2017
Generate and measure the sustainable impact of civic groups. This will mean a) assessing their impact beyond the direct membership; b) supporting them reach out and involve a wider range of citizens in their work (e.g. through closer collaboration with media); and c) identifying and then consolidating their key capabilities.	Ongoing. A) The analysis of the sustainable impact of the civic groups (civic engagement in DIÁLOGO's approach) will be measured in the final evaluation. B) DIÁLOGO, following the MTR recommendations has employed a ripple effect strategy that reaches out to a wider range of local groups and citizens to engage in municipal governance; and ) DIÁLOGO is holding exchange workshops and interacting with new groups to expand impact; and c) CESC (Centro de Aprendizagem e Capacitacao da Sociedade Civil) is working on consolidating capabilities and leading a development capacity plan for civic groups to continue to use the most effective participatory tools.
Tackle the harder issues that are most important to citizens e.g. sexual violence and livelihoods.	Met. The programme remains demand driven and relies on the local partner groups and municipalities to share their concerns and commitment to work together to resolve them. All hard issues continue to be a priority for communities: Sexual violence, water and sanitation, industrial pollution, land tenure, revenue collection, and urban resettlement are among the top issues being addressed by DIÁLOGO partner coalitions across the target municipalities over the current implementation year. DIÁLOGO's Gender and Social Inclusion Strategy will introduce the "Safe and Inclusive Cities" approach that aims to sensitise the municipal institutions on specific security problems that women face in urban areas.
Balance the shorter terms results with an increased focus on long term structural/strategic changes based on a more coherent approach. This will involve: a) increased municipal level co-ordination (rather than via PMU) to clarify roles and enhance joint working. b) More analysis of and action to influence the key blocks to participatory governance in each municipality to address the structural causes.	Ongoing / Municipal facilitators are coordinating more together. / More analysis is underway: CESC is undertaking various assessments to unlock some “thematic” challenges. Currently the programme is looking at the following issues: / Maputo – resettlement problem / Tete – water management / Quelimane – waste management
Gender and inclusion: Responding to the detailed findings of the MTR set out an inclusion strategy that covers all strands of the programme. Steps will include: • recruitment of a gender/inclusion expert with international experience; • Identifying the priorities for women and youth in municipalities; • Identifying what prevents women and youth from participating meaningfully in governance issues at municipal level including economic, social and cultural barriers; • Within these groups (‘women’ and ‘youth’), identifying who are the most vulnerable and excluded; • Analysing how the programme can address these issues directly and by working with others; • Link with BBC media	Partial progress The PMU hired a gender consultant, and has finalised a Gender Strategy. which includes interventions for each component of the programme (civic engagement, media and municipal engagement); / •The PMU identified potential resource partners to support the implementation of the strategy's goals, and is currently partnering with CAPAZ and Blue Horizonte given their ongoing work in the municipality. / •The programme has so far trained: / 26 leaders (councillors and directors) and members of the municipal assemblies of the five municipalities in gender based leadership and communication; / 20 municipal planning officers on budgeting from a gender perspective / • The programme has not carried out a formal study to identify the most vulnerable and excluded groups. DFID will once more recommend that DIALOGO takes this pending recommendation forward. With the new gender strategy in place, partners such as the Youth Parliament and CAPAZ (who work on youth related issues with youth parliaments in Maputo and Tete ), are taking actions to reach out to as many vulnerable people as possible which is a key focus of the Gender Strategy. / • The programme has focused on increasing the municipalities’ understanding of gender and youth issues. The programme has not been linked with BBC media as of yet. DFID considers it too late to initiate a new activity given that the project is closing in 8 months.
Build sustainability into the media element by supporting media partners build links with other media organisations and sources of funding.	Met and ongoing: A media training package focused on sustainability and consolidating the training and knowledge was implemented in 2016/2017. A main focus has been on finalising business plans for current media partners. Some of the capacity building and networking work includes the following: • Malasha (Tete) and Whampula Fax (Nampula) newspapers have a new modern and attractive lay-out for both electronic papers. • IREX developed new Digital Media Platforms (website and mobile apps) for eight DIÁLOGO radio partners, plus Whampula Fax. • Three managers from DIÁLOGO’s media partners participated in the IREX conference on community media leadership. • 17 journalists from all DIÁLOGO media partners attended two trainings on how to cover municipal governance related issues. • 17 journalists trained on gender and social inclusion related issues. • 18 journalists and media managers and 23 representatives of local organisations have attended two exchanges linking media and civil society organisations on municipal governance
Support stability more explicitly e.g. can programme provide TA to municipalities on how they respond to civil unrest to ensure an appropriate response that calms rather than fuels violence? Links to recommendation 2.	Not met and as agreed with the SRO was not considered possible. This is out of DIÁLOGO's mandate to provide TA to respond to civil unrest. The Programme is however monitoring the political situation.
Strengthen the work on learning and influencing. This will need a strategy to include: a) Influencing other municipalities and central government: b) Passing learning to and influencing other programmes in Mozambique. c) Internationally: going beyond Mozambique to share DIÁLOGO's innovative approach?	Met. / The programme is now implementing a new learning and influence strategy. DIÁLOGO is actively documenting and sharing its experiences within and across municipalities. / DIÁLOGO renewed its partnership with ANAMM to help influence other municipalities and the central government, and is very present in key decentralisation working groups at the central level, sharing experiences and influencing decisions. The programme is coordinating with PRODEM and CEP to share best practices. / DIÁLOGO, CEP and DFID are in discussion to share a final event for both programmes in October 2017. The agenda and work should start now to ensure that what happens in the event does not kick off ideas but instead cements them.–
Keep building the link with supply side programmes, particularly PRODEM	Met. DIÁLOGO has regular interaction with all donors active in municipal governance: PRODEM, World Bank, Cities Alliance and GIZ.
Value for Money: Set out a simple VfM strategy to drive the choice of indicators, assessment approaches, data collection and documentation. This should include: a) Addressing the recommendations in the MTR; b) Shifting the focus from economy and efficiency to effectiveness, including equity and sustainability. DFID to consider how to use and share lessons learnt from VFM analysis and findings of the MTR.	Met and ongoing: An updated draft VFM strategy was submitted with the Y4Q2 Quarterly Report. The SRO, Economist and Programme Manager will work with Dialogo to help improve the vfm strategy by June, the next Quarterly Report.
Financial management: PMU to suggest how to complement grant making with other approaches to funding activities if feasible at this stage in the programme.	Met. The project signed two new MoUs to help support local organisations. At this stage the SRO and Dialogo agreed that it was not feasible to change the approach of grant making.
Contract management: DFID with PMU to consider if IDS should be contracted directly rather than through DAI.	Met. DFID and the PMU agreed that IDS will remain contracted through DAI.
Logframe: a) add outcome and output indicators on learning and influencing; b) disaggregating output 2; c) reduce outcome indicators while keeping the balance between perception and fact.	Met. The logframe was updated in September 2016.

Summary of recommendations for the next year

Recommendation	Responsible	Timelines
Final evaluation of the project to be carried out by IDS	PMU	Report due to DFID on 1 November
DIALOGO to provide a close down plan with clear proposal of asset disposal and work with DFID on financial reconciliation of invoices	PMU	30 September
PMU to measure and report on the impact of gender trainings. PMU to report on any stories of what was done differently as a result of the training.	PMU	June and September quarterly reports
In relation to the ongoing work to sensitise the municipal institutions on the security problems that women face in urban areas: Assess whether other partners can take forward the work as part of making the project sustainable.	PMU	September quarterly report
With respect to the final DFID DIALOGO Event: PMU to produce a ToR for this event within the next 6 weeks to give the right time and space for inputs to make this relevant. Consider merging the event with DFID CEP	PMU	30 May
PMU to inform DFID SRO and DFID PM on event planning so that other DFID programmes can benefit from DIALOGO and better link on cross-sector issues such as on gender and youth.	PMU	By 30 May
DAI to improve documentation sharing and discussions of lessons learnt with DFID in view of DFID’s new Communication Strategy. PMU to consider hiring a short-term expert Communication Adviser to showcase the positive changes and human stories of the project.	PMU and DFID	Updated fact sheets and human stories by June quarterly report
DAI to report against the Gender Strategy logframe in their next quarterly report while highlighting what prevents women and youth from participating meaningfully in governance issues at a municipal level. The analysis should also look at who are the most vulnerable and excluded and explain how the programme is addressing these issues.	PMU	June quarterly report
DIALOGO to consider forming some strategic partnerships in these last months with, for example, Eduardo Mondelane University (UEM), where learning and case studies can be incorporated into research and teaching.	PMU	Ongoing
PMU to produce a Gender Based Budgeting Guide	PMU	TORs currently being drafted; Final Guide ready by 30 July
See vfm section for specific related recommendations	PMU	June Quarterly Report and Final DIALOGO Report

Annexes
Annex 1: DIALOGO Logframe
Annex 2: Value for Money Matrix
Annex 3: Risk Matrix

## A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201958/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-201958/

DIALOGO aims to contribute to improved governance, accountability and responsiveness at the municipal level in Mozambique. It is a five year programme implemented by DAI in partnership with COWI. Further subcontracted partners of this consortium include the Institute for Development Studies (IDS) in charge of the monitoring and evaluation component, CESC (Centro de Aprendizagem e Capacitacao da Sociedade Civil) working mainly with civil society organisations and providing the key community facilitators on the ground, and IREX focusing on media.

The main outcomes of the project aim to empower citizens, civil society, the local media and municipal government to address and engage on local issues. DIALOGO advocates for a more open and participatory dialogue based on issues raised by communities.

Implemeting municipal governance has been confronted with persistent obstacles, with many of these obstacles arising from political economy sources. While there has been increased national policy attention to improving municipal governance in recent years, the difficulty of translating this policy momentum into results at local level remains. Government remains highly centralised and the municipal mandate is still not rolled as a result of the lack of implementation of the 2006 decentralisation policy which remains one of the main sources of contestation for the opposition. What it means on the ground, municipalities have limited capacity and mandate to intervene and address all sector issues.

The project works in five municipalities and each have had different degrees of success in civic engagement with municipal institutions. Overall the project has pushed for social change in municipalities like Nampula and Quelimane where a real motivation of society to engage with municipalities has been observed. The project has also worked best in those municipalities where there is a strong municipal leadership and commitment to engage with communities.

The challenges for this project continues to be the current political situation and political engagement of municipalities to push forward a more inclusive and participatory agenda. The project has been adaptive and flexible using various tools to engage at all levels through the local media, local stakeholders, youth groups, associations and communities. The project has stepped up its efforts to link up more with other donor programmes on the ground. It has also increased its lessons learning and influencing through its policy engagement with ANAMM, media outreach both on the ground and in Maputo, and stepping up event planning/studies in coordination with other civil society organisations working with municipalities.

The project will also continue to face local realities such as weak capacity of municipality to respond, difficulties for CSOs to agree on a common agenda and competition for funding. It is too early to say whether sustainability of municipal engagement will be achieved. Some municipalities look more promising in particular those that have a clear political will to push for greater citizen engagement.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The project is on track to achieve its outcomes and meet its output indicators. Throughout all five target municipalities, DIÁLOGO is achieving most of its targets. Indicators around citizen engagement with municipalities and around the media promoting public debate have been fully met. Those around the municipal institutions engaging differently have not been met under sub-outcome 3: “Municipal institutions engage different stakeholders into municipal governance”. This is because of lagging results in Nampula and Beira participatory budgeting and planning were suspended and as a consequence, less meetings and events were organised by the municipalities. To balance out this result there was more engagement meetings led by municipal councils in all five municipalities. Of all three components, municipal engagement is the most challenging component in terms of data collection from municipal institutions which this component heavily relies on.

Overall output score and description

Overall output score for the programme is an A+. The Programme has received an A+ in Civic Engagement (40%), an A+ in Media (30%) and an A in Municipal Engagement (30%).

Key lessons

The focus of this programme is to bring municipalities and communities together to address concerns and issues raised by the community, such as sexual violence, land rights, lack of infrastructure (eg. bridges and roads), access to water, etc. The focus of the last year of the project for the civic engagement component is therefore to achieve a ripple effect via the dissemination of best practices and ways of working among other non-Dialogo beneficiaries. The project in the last year reached out to 33 new neighbourhoods and targeted a total of 69 new civic groups and organisations. Success stories include better waste management for Quelimane and Tete, joint solutions on primary health care in Beira and electricity and water management and participative budgeting in Nampula.

The overall biggest success story is the media component. Throughout the project, this has been a great tool to communicate and discuss issues, and also educate and empower citizens and municipalities to come together. The project focused in the last year on strengthening the media business model so that it can be self-sustainable after the closure of the project. Another priority is to strengthen the journalists’ competencies to cover municipal governance issues which are a continuation of ongoing activities and capacity building efforts.

The third outcome of this project prioritises municipal engagement mainly by engaging with and demanding more transparency and responsiveness towards citizens’ needs and demands. The priority and challenge this year will be to institutionalise best practices and ways of working with communities after the closure of the project. One of the tools that may continue to be used is the participatory budgeting, which can easily be monitored and has gained traction in Nampula and Quelimane. The Project is building on WB and ANAMM (National Municipal Association) work to set up a national network for participatory budgeting and to expand it to all municipalities.

A final additional activity which was introduced last year as a result of the 2016 Annual recommendations was to step up the “learning for policy influence”. This initiative was consolidated with the Learning for Consolidation and Influencing Strategy which has three interlinked approaches:

- Learning for consolidation to document Dialogo best practices and lessons learnt,
- Learning for programme influence to target non beneficiaries and actors of the project working on municipal governance, and the
- Learning for policy influencing to step up and influence discussions around decentralisation and challenges of municipal governance. Given the relevance of the project and cross-sector work (on gender, water, policy work on decentralisation), the project would achieve a bigger impact if it provided its event planning ahead of time with DFID SRO and Programme Manager. The Fact sheets and results from the project also need to draw in an expert Communication Adviser to showcase the positive changes and human stories of the project.

An important recommendation from last year was to strengthen the gender and youth interventions. The Gender Strategy was finalised with much training invested into all above components of the project. So far 17 journalists have been trained on gender and social inclusion related issues. The project has also introduced, as a compulsory activity for each media partner, radio programmes on subjects that concern women, youth, and vulnerable groups. Live street radio programmes were introduced as a way to promote and increase the participation of women, youth and other groups (such as the elderly, disabled, etc.).
Key actions

DAI to improve documentation sharing and discussions of lessons learnt with DFID in view of DFID’s new Communication Strategy

DAI to report against the Gender Strategy in their next quarterly report

DIALOGO to consider forming some strategic partnerships in these last months with, for example, Eduardo Mondelane University (UEM), where learning and case studies can be incorporated into research and teaching.

Has the logframe been updated since the last review? Yes, following the 2016 annual review

The following indicators were no longer prioritised for 2017, most of them no longer valid and already met during the previous AR:

2.4 : # of media programmes and articles about electoral process from media grantees: Given the focus of the extension phase this indicator was not prioritised.

2.4 : # of investigative journalism pieces on priority issues reported by independent media: During the extension phase DIÁLOGO will not support investigative journalism pieces.

2.5 : # media outlets where ICT were set up. The Project agreed not to further expand ICT and new radio stations for the final year of the project and work with those that are already set up.

3.3 : % of implementations of Municipal Technical Support Plan:

The following indicators were added as recommended in the last Annual Review to focus on the implementation of the Gender Strategy as well as building sustainability to the project:

Indicator 1.2.: The project is expanding its civic engagement approach to new non-DIÁLOGO partners in new neighbourhoods and around new issues that are a real concern to citizens.

Indicator 2.6: # of interactive media transmissions and articles (radio, newspapers) disaggregated by gender and group ( women, youth and another vulnerable groups)

Indicator 3.5 # of municipalities initiatives prioritising vulnerable groups

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Civic Engagement: Mobilising, sensitising and supporting citizens to engage on municipal governance.
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1. # of civic groups and individuals assisted on engagement practices	150 groups and 2,226 individuals assisted on engagement practices: / Maputo:24/307 / Beira: 19/452 / Tete: 21/271 / Quelimane: 41/407 / Nampula:45/789	Milestone exceeded / 192 groups and 4,765 individuals assisted on engagement practices: / Maputo:29/826 / Beira: 36/587 / Tete: 21/375 / Quelimane: 55/1695 / Nampula: 51/1282
1.2. # of NON-DIÁLOGO partners informed on DIÁLOGO approaches, methodologies and adopting DIÁLOGO approaches	55 NON-DIALOGO partners trained and involved with DIALOGO: / Maputo: 19 / Beira: 23 / Tete: 1 / Quelimane: 3 / Nampula: 9	Milestone exceeded / 71 NON-DIALOGO partners trained and involved with DIALOGO: / Maputo: 22 / Beira: 23 / Tete: 3 / Quelimane: 8 / Nampula: 15
1.3. # of coalition/ synergies between municipal actors working around priority issues	84 coalition/ synergies between municipal actors working around priority issues: / Maputo: 19 / Beira: 14 / Tete: 12 / Quelimane: 25 / Nampula: 14	Milestone met / 83 coalition/ synergies between municipal actors working around priority issues: / Maputo: 20 / Beira: 12 / Tete: 12 / Quelimane: 23 / Nampula: 16
1.4. # of municipal actors that engage with municipal institutions on current priority issues (disaggregated by type of organization - youth and gender focused)	173 municipal actors engage with municipal institutions on current priority issues: / Maputo: 22 / Beira: 20 / Tete: 25 / Quelimane: 51 / Nampula: 55	Milestone exceeded / 198 municipal actors engaged with municipal institutions on current priority issues: / Maputo: 25 / Beira: 28 / Tete: 29 / Quelimane: 60 / Nampula: 56

Key Points

All output indicators were exceeded except for indicator 1.3.

Details

As shown by indicator 1.1, DIÁLOGO continues to promote a strong civic engagement around specific issues with several civic groups, NGOs and individuals. The project uses various accountability tools (such as community score cards and community action plans) to gather communities’ needs and provide advice on how to prioritise and address them.

Indicator 1.2: As recommended by the last Annual Review this indicator was added to generate sustainable impact of the current DIALOGO civic groups and encourages the civic groups to work more openly. The project is expanding its civic engagement approach to new non-DIÁLOGO partners in new neighbourhoods and issues that are a real concern to citizens.

Indicator 1.3: This indicator assesses the extent to which DIALOGO partners are working together. Although the number of coalitions was not achieved (only for Quelimane), indicator 1.4 has overachieved in that these coalitions increased the number of actors targeted.

Indicator 1.4 was added following the last AR recommendation to disaggregate data by gender/group focus.

Summary of responses to issues raised in previous annual reviews (where relevant)

The Project finalised a Gender Strategy that focuses on improving access to services, continuing women’s empowerment in raising issues and promoting women as leaders.

Recommendations

Report on the implementation of the Gender Strategy in the next quarterly report while highlighting what prevents women and youth from participating meaningfully in governance issues at a municipal level. The analysis should also look at who are the most vulnerable and excluded and explain how the programme is addressing thes concerns of these groups.

Output Title	Strengthen and Engage Media: Building capacity to promote media coverage, interaction and public debate around municipal governance.
Output number per LF		2	Output Score	A+
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1. # of interactive media transmissions and articles / (radio, television, newspaper) on municipal governance	350 interactive media transmissions and articles: / Maputo: 70 / Beira: 70 / Tete:70 / Quelimane:70 / Nampula: 150	Milestone exceeded / 524 interactive media transmissions and articles on municipal governance: / Maputo: 79 / Beira: 99 / Tete:80 / Quelimane: 69 / Nampula: 197
2.2. # of journalists trained on several issues (1st year on electoral process)	40 journalists trained on several issues	Milestone exceeded / 77 journalists trained on several issues
2.3 # of media programmes and articles about electoral process from media grantees	n/a ( Target measured during year 1 of the implementation of the programme)	n/a
2.4 # of investigative journalism pieces on priority issues reported by media	No milestone set this year	Milestones exceeded last year. Not monitored this year. Agreed to refocus last year’s project on gender training, capacity building and helping radio stations remain financially sustainable.
2.5 # media outlets where ICT were set up	No milestones set this year	Milestones exceeded last year. No new radio stations therefore no ICT introduced.
2.6 # of interactive media transmissions and articles / (radio, newspapers) on women, youth and another vulnerable groups issues	60 interactive media transmissions and articles / on women, youth and another vulnerable groups issues	Milestone met / 61 interactive media transmissions and articles / on women, youth and other vulnerable groups’ issues

Key Points

All indicators under this component were achieved and exceeded. The target number of interactive media-transmissions and articles on municipal governance issues was exceeded.

As per the 2016 Annual Review, media was seen to promote public debates around municipal governance but was not fully considered as a tool to resolve local problems. However as of 2017, media is clearly seen to promote an attractive space for citizens’ voice in order to put forward their demands and influence policy makers. For example in the case of Nampula, a DFID visit heard that various issues raised on the radio had quickly been resolved by municipalities.

Part of these interactive radio transmissions are done outside of the studio interacting directly with citizens on the ground. In order to stimulate women and young peoples’ voices, media partners are promoting specific debates around issues that are important to them.

A recommendation from last years’ Annual Review was to strengthen the capacity of journalists. DIÁLOGO has now trained 77 journalists on: journalism and gender inclusiveness, business management and digital platforms, to ensure sustainability, lesson learning and individual capacity building across this component.

Details

2.1 Exceeded. The target number was set for 350 interactive media transmissions and articles on municipal governance issues but was exceeded with 524 achieved transmissions. This is largely as a result of the capacity training initiatives with local radio stations and newspapers. Weekly one hour radio transmissions have been made which include live debates on municipal issues. These debates involve citizens, municipal authorities and other municipal actors and specialists. The project partners with 2 newspapers that produce weekly articles on municipal governance issues in which they showcase views and stories from citizens.

2.2 Exceeded. 77 journalists received training against the target of 40. The training was on radio editing, radio journalism, governance, social media and digital tools, and taught how to prepare a business plan and financial management. Journalists from all of DIÁLOGO’s media partners in the five target municipalities are currently benefitting from these trainings.

Following the MTR and programme’s extension, it was agreed to discontinue indicator 2.5. on Information and Communication Technology (ICTs) (# of media outlets where ICT was set-up). DAI and DFID agreed not to expand the existing media partners for the last year of the project. All current media partners already have ICT as of 2016 and the target was met last year.

2.6 Exceeded. The programme completed 61 media transmissions and articles (radio and newspapers) that were focused on women, youth and other vulnerable groups, exceeding the initial target of 60.

Examples of topics covered during radio transmissions and news articles include: crime and security concerns in neighbourhoods that affect women; lack of public toilets, which was said to affect women; lack of water and long distances required to fetch water; the municipality’s strategy to make the town more accessible for disabled people highlighting civic associations’ current support activities; living conditions of, and care for, elderly people and how the municipality is addressing this problem.

Summary of responses to issues raised in previous annual reviews (where relevant)

This component was seen as the weakest in terms of gender inclusion. A lot of effort was put in this year to include a shift in culture so that women participate in news making as well as more generally across all other components of the project. Capacity training was provided to ensure more equality and gender training in journalism.

The last AR recommended to explore linking with BBC Action but DFID considers it too late to start a new initiative when the project is closing in the next 8 months.

Recommendations

None

Output Title	Engagement of Municipal Institutions: Supporting municipal institutions on participatory governance and actor’s dialogue.
Output number per LF		3	Output Score	A
Risk:		Major	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1.# of communication initiatives to disseminate municipal institutions’ informations	17 communication initiatives to disseminate municipal institutions’ informations: / Maputo: 3 / Beira:2 / Tete: 1 / Quelimane:7 / Nampula: 4	Milestone met / 26 communication initiatives to disseminate municipal institutions’ informations: / Maputo: 5 / Beira: 0 / Tete: 0 / Quelimane:8 / Nampula: 13
3.2. DIALOGO Municipal Technical support Plans designed and agreed	5 Municipal Technical support Plans designed and agreed	Milestone Met / 5 Municipal Technical support plans were designed and agreed for the final year of the project.
3.3. # implementation of Municipal Technical Plans (% annual activities)		This milestone is no longer monitored. Met last year.
3.4. # of dissemination/advocacy activities on lessons learnt/best practices/ municipal studies / beyond target municipalities	12 dissemination/advocacy activities on lessons learnt/best practices/ municipal studies / beyond target municipalities	Milestone exceeded / 16 dissemination/advocacy activities on lessons learnt/best practices/ municipal studies / beyond target municipalities
3.5 # of municipalities’ initiatives prioritising vulnerable groups	At least one initiative	New Milestone – ongoing, will be measured at the end of the Programme

Key Points

At the aggregated level for each indicator, all have been met or exceeded. This output is about improving municipal government’s approach and responsiveness to citizens’ demands. In a way it is about introducing good governance and better service delivery practices through relationship building, raising awareness and educating municipalities on peoples’ rights to better services. The project has worked with municipal institutions - both councils and assemblies - to help them improve their governance approach. During the last year of the project, the aim is to continue disseminating: DIÁLOGO best practices; its tools and tactics for capturing citizen’s needs (e.g. participatory budgeting); as well as its lessons learnt, both for its target municipalities and other groups, including NGOs and media stakeholders working on municipal governance.

Details

3.1 Met. Activities under this indicator included the production and dissemination of the municipal activity plans, budgets and key legislation through the production of a municipal newsletter, website, and a hot line. DIÁLOGO helps municipalities increase their communications capacity in order to promote transparency and accountability to citizens, as well as to promote awareness campaigns on citizens’ rights and duties. In Quelimane, Nampula and Maputo, several communications activities were facilitated, such as a tax campaign to introduce revenue collections and pamphlets on participatory budgeting in Maputo and Nampula.

3.2 Met. The targeted number of Municipal Technical Support Plans designed and agreed upon was met (1 in each municipality[1]). These plans included actions such as support to improve the respective municipality’s communication capacity and their ability to deliver services including their work on participatory budgeting. This activity was largely supported with technical assistance.
[1] The plan for Tete was designed but not formally agreed yet. Activities have started.

3.4 Exceeded. This indicator captures DIALOGO activities that aim to disseminate lessons learnt and best practice studies in order to promote exchanges among target and non-target municipalities. Activities include workshops, meetings, publications, newsletters, and websites with resources for municipalities. In 2016, 16 dissemination/advocacy activities on municipal governance were carried out in order to share DIALOGO’s best practices with non-target municipalities and to encourage a dialogue with the national government and other involved stakeholders on municipal governance. Some examples include: the participation of DIALOGO in the OIDP Conference (Organização Internacional de Democracia Participativa); the organisation of the Urban National Forum (in partnership with GIZ and the Cities Alliance); a seminar on “Municipal Barometer” with IESE and MASC. DIALOGO also set gender and youth agendas at municipal level, such as a workshop on “Leadership and Communications” targeting female municipal assembly members and an Inter-Municipal Dialogue for Youth, with young people from several southern municipalities in partnership with Fundação Luso-Americana para o Desenvolvimento and the Associação comunitária de Mafalala.

Indicator 3.5 has been added following last year’s recommendations. This indicator measures the number of municipal initiatives that prioritise vulnerable people. Although some activities have already begun, the project will begin to see results from May onwards. Each target municipality should have at least one new initiative that prioritises vulnerable groups, such as the introduction of gender budgeting or women and youth quotas that benefit from urban poverty funds.

Some of the expected results for this year which are currently being worked on:

•	Include a quota for women and young people so that they too benefit from the Urban Poverty Reduction Fund in Quelimane and in Beira.
•	Develop a Safe Cities Plan in Nampula to reduce crime. This Plan involved various actors such as the police, municipal institutions and CSOs.
•	Produce a Gender Based Budgeting Guide for the 5 municipalities.
•	Good Neighbours Approach will be introduced by Horizonte Azul ONG partner in Maputo and Tete. Although this is a civil society initiative, it will require municipal government participation on introducing a gender lens.

Summary of responses to issues raised in previous annual reviews (where relevant)

n/a

Recommendations

1. PMU to inform DFID SRO and DFID PM on event planning so that other DFID programmes can benefit from DIALOGO and better link on cross-sector issues such as on gender and youth.
2. PMU to consider producing the Gender Based Budgeting Guide.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers of the programme have not changed from previous years and include:
- Direct and indirect staff – 58% (including TA)
- Grants – 16%
- Municipal learning workshops – 13%
- Administrative overheads – 10%
- Travel costs – 3%

The cost drivers are tracked since the Extension Phase contract was signed in September 2017 and are outlined in the Value for Money (VfM) monitoring (annex 2). These cost drivers are broken down below. Overall the project has performed well against respective targets.

VfM performance compared to the original VfM proposition in the business case
This section reports against the updated VfM strategy submitted with the Y4Q2 Quarterly Report. It is based on a number of quantitative and qualitative indicators at economy, efficiency, effectiveness and equity levels.

Assessment of whether the programme continues to represent value for money
Yes, the programme continues to represent VfM as it continues to perform reasonably well for most of the VfM indicators. Nonetheless, it was noted previously that DIALOGO’s management model appears to offer lower value for money when benchmarked with other similar programmes. This is something that will be looked at in more detail during the final evaluation.

Below is a discussion of the performance against the current VfM indicators. The complete VfM Matrix can be found in Annex 2.

Economy
Cost per major cost driver: 1) domestic RT airfare (per trip); 2) municipal learning workshops (per workshop); 3) PMU staff costs (as % of overall spending for period); 4) external consultant costs (total per day of consultancy); and 5) Maputo office administrative costs (as % of overall spending for period): The Indicators relating to the average cost rates of items associated with key cost drivers indicate that most are in line with targets – see table below.

Indicator	Target	Results
Domestic RT airfare (average per trip)	£500	£326.77
Municipal learning workshops (average per workshop)	£5,000	£4,742.20
PMU staff costs (as % of overall spending for period)	42%	35.8%
External short-term consultant costs (average per day)	£450	£240
Maputo PMU office administrative costs (as % of overall spending during period)	4.3%	5.1%

Office administrative costs reached 5.1% above the target of 4.3%. For the first 3 quarters the average was 4.4%, but in the 4th quarter office administrative costs were high due to some bulk office supply procurements to prepare for the Theory of Change workshop and exchange workshops. As the programme begins to wind down its operations in 2017, this metric should improve during the next quarter, bringing down the average administrative costs over the five years duration of the project.

The PMU continues to encourage best VfM for all its procurement and for all other indicators above. So far, it has performed better than the targets.

% of grants awarded on a competitive basis: This VFM metric is not used due to the programmatic decision to remove the Challenge Funds from the grant portfolio due to a lack of viable options of grantees.

Efficiency

Out of 4 metrics, 3 are performing and the last metric partially. It refers to the costs per citizens benefitting directly from improved practices of accountability and consultation which is heavily dependent on the municipality’s participation.

Cost per civic group supported, and per person participating in media space for citizen voice on municipal governance issues during the reporting period: The cost per civic group supported was £7,340 which is below the target of £10,000. The cost per person participating in media space for citizen voice on municipal governance issues, were higher in Year 4 than in the past due to refocused efforts based on the MTR and AR 2016 that included increased grants, more in-depth trainings and better and more expensive equipments. While this increased the number of grants signed with media partners, the average number of people per civic group supported decreased hence increasing the average cost per person. The change in approach is perceived as crucial to increase beneficiaries’ ability to reach a larger audience more efficiently and obtain better VfM. The improved results should be clearly visible in the coming months.

Number of days to process a grant (from announcement to first fund transfer, for Challenge Fund grants; from presentation of initial proposal to first fund transfer, for non-competitive grants): No new grants were awarded during the period covering this Annual Review. Instead DIALOGO is working to consolidate its ongoing interventions.

% of DIALOGO budget spent on direct programmatic support versus administration and other overhead costs: Following the MTR and AR 2016, DIALOGO increased its programme based spending consistently in Year 4 with an average rate of 75%, which is above the 67% target. This means that more of DFID’s funds are going directly towards interventions which should contribute to better results.

Cost per beneficiary per major objective included in annual municipal engagement action plans: The target is £12.50 per citizen benefitting from improved interaction and communication and this amount averaged £6.6 in Year 4. The target is £35 per citizen benefitting directly from improved practices of accountability and consultation. This amount has averaged £61.5 per citizen mostly because of high fixed costs of preparation and lower participation levels. DFID will be discussing all vfm indicator targets with DIALOGO in May 2017 to ensure they remain realistic and achievable for the last phase of the programme.

Percentage of activities developed in collaboration with complementary programmes / implementers: Historically the project developed 80% of its activities in collaboration with complementary programmes/implementers. During Year 4 the programme collaborated with many other organisations including the World Bank, ANNAM, GIZ, the National Urban Forum with Cities Alliance and the Governance Informal Group. Approximately 88% of activities were created in collaboration with complementary programmes/implementers, thus surpassing target of 48% by a healthy margin.

Effectiveness

% of grant-funded projects implemented successfully: DIALOGO performance was slightly below the target for the project implementation success rate indicator reaching an average score of 8. In spite of this, the programme has been showing steady improvements of scores. In Year 4, 11 grants were evaluated, with an average score of 7.4, steadily increasing from 6.8 and 6.6 in years 3 and 2 respectively. The main weaknesses shown by DIALOGO’s grantee partners are with financial reporting. DIALOGO is working with grantees to improve their record keeping, as well as their financial management, to help avoid any funding needs and delays in implementation.

Equity

After the MTR and AR in 2016 the programme has made efforts to ensure that equity was the top driver in programmatic decisions for the extension phase of the programme. The gender strategy was enhanced and lessons learnt were consolidated so that equity could be seen flowing through all of DIALOGO interventions in Year 4 and the extension phase. New indicators were added to the logframe around equity, and those will be reported on during the extension phase of the programme in 2017.

Recommendations:

The next seven months will be crucial to DIALOGO, as the programme approaches its closure it needs to achieve a broader impact and consolidate its gains in the five municipalities as well as refine its approach to sustainability. DFID has a role to play in this and will do so by supporting actions that can lead to sustainability.

Continue to follow up on previous recommendation from AR 2016 on considering equity further than just looking at women and youth still applies. More consideration needs to be given to how class, political affiliations and patronage relationships influence voice and the choice of priority projects and distribution of benefits.

DIALOGO to submit in their final report, in addition to the quarterly VfM information, the annual VfM assessment (totals and average of the 4 quarters).

In preparation for the PCR, DFID should work with DAI on improving the format to report against VfM indicators and clarify the details of how quantitative performance is calculated.

DIALOGO to include a review of the main weaknesses found in the implementation of grant-funded projects in their final report and report on how DIALOGO worked with them over the years to improve their performance.

Quality of financial management

DFID’s contract with DAI Europe was extended for an additional 10 months in September 2016, at a cost of £1,496,931. This has brought the total value of the contract to £9,484,127 over almost 6 years. The project now ends on 31 December 2017.

The contract model is ‘Milestone Based’. Payments are made against agreed milestones and the DIALOGO work plan. These are linked to the overall Project logical framework. This allows for more frequent tracking of progress.

The PMU and DFID agreed on a set of milestones in September 2016 and payments have been made based on achievement of these milestones. The payment frequency remains quarterly and the final payment is due one month of the expiry date of contract. DFID and the PMU agreed that all activities will be completed by 30 September 2017, so the bulk of the funds will be spent during the next seven months.

From October until December, the PMU will be wrapping up final activities and grants, delivering final municipal workshops and closing down the project. DFID and the PMU also agreed that the final payment deliverable will be a final report. The PMU has the responsibility to prepare financial statements and oversees DIALOGO’s financial cash flow. IDS remains contracted through DAI and will provide a final Evaluation Report in November 2017.

The PMU continues to maintain strong internal controls for procurement, expenditure recording, and inventory management.

Ernst and Young has been contracted out to conduct the programme’s audits for the whole duration of the project. The last audit was finalised in March 2017 and covered the period from 1 March 2016 to 28 February 2017. The recommendations from previous audits were all implemented.

The total contract value with DAI Europe is £9,484,127. During the financial year 2016/17, DIALOGO spent £1,643,010.45 (fixed portion - 1,407,658.76 and grants portion - £235,351.69) against a forecasted £1,789,034.61. To date the programme has spent £7,562,728.82 and spending is on track.

Following the AR 2016 the PMU was asked to suggest how to complement grant making with other approaches to funding activities. Given that the programme is running smoothly, both DFID and the PMU have not suggested a different approach for the final year of the project.

The PMU signed two new MoUs with Horizonte Azul and CAPAZ- two young women Associations- to integrate a transformative gender and social inclusion approach to DIALOGO civic engagement and its partners’ interventions.

Recommendation:

DIALOGO to provide a close down plan with clear proposal of asset disposal and work with DFID on financial reconciliation of invoices by 30 September

Date of last narrative financial report	March 2017
Date of last audited annual statement	27 March 2017

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk

The programme has an updated risk framework which is discussed on a regular basis with DAI. See annex 3. There are a number of major to moderate risks which pertain in particular to the political environment in which the Project operates and which are continuously monitored. Other risks relate to the financial crisis and of the municipalities’ reduced budget to cater for all needs. A new risk has been added which relates to the project ending this year and to the sustainability of the project’s results which the project is seeking to address.

The media component helps mitigate some of the risks around lack of engagement from municipalities to respond to civil society. A continuous risk that also affects the programme’s performance and impact, is the delay in the implementation of the 2006 Decree on decentralisation and competency transfer to municipal councils (for eg. Health care provision). The mandate of the municipalities and their capacity to address local problems remains as a result limited. The PMU is working with ANAMM to advocate for the implementation of the Decree and continue to raise the challenges faced by the freeze in the decentralisation process. This is a political challenge and very hard to predict however government and the opposition party are still debating on this very matter.

Outstanding actions from risk assessment

No outstanding actions.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme was extended in September 2016 taking the programme completion date from 28 February 2017 to 31 December 2017. The overall purpose of the extension was twofold: to ensure that the gains made by the programme would be sustainable in terms of participatory governance at municipal level and to inform any future governance programming by DFID or other donors. The programme is on track and progress is according to schedule.

Performance of partnership (s)

DIALOGO has been increasing its partnerships with various donor programmes active in municipal governance as well as civil society active on the ground.

An informal group has been established between MASC and CEP, two major non-governmental organisations active in local governance and capacity building, and DIALOGO to improve sharing of best practices. DIALOGO is also firming up its strategic links with MASC to see how some of DIALOGO’s interventions can be built into MASC, especially on civic and media engagement.

DIALOGO has strengthened its collaboration with donor programmes active in urban and municipal governance such as GIZ’s PRODIA II, the Cities Alliance country project, and with the World Bank decentralization programme. Several meetings were also held with PRODEM, a donor funded municipal programme, to assess areas for mutual collaboration. GIZ and PRODEM for example set up a National Urban Forum in March 2017 to discuss current policies around municipal governance.

Recently, DIALOGO has collaborated more proactively with ANAMM (Municipalities National Association) on various issues related to the decentralisation process and participatory budgeting together with the World Bank (WB). DIALOGO and WB have also been supporting the set-up of a national network for participatory budgeting with a view to expand it to all municipalities.
The PMU and DFID have updated the logframe following the last Annual Review, revised milestones to match the 2017 work plan, as well as kept payment profiles up to date. All of these have been implemented according to the timeline and delivered to a good standard. There is scope to improve the quality of these communications documents in particular the Fact Sheets, reporting on human stories and results of the project. DFID has discussed this with the PMU.

The Work plans, objectives and budgets continue to be shared openly and collaboratively with DFID.

Asset monitoring and control

The PMU submits asset registers as part of their regular reporting and assets spot checks are done annually by DFID Mozambique. The last spot checks were carried out in August 2016 and in March 2017. Following the August 2016 spot check, DFID approved the PMU’s request for early disposal of iPads and chairs and the write-off of stolen and damaged iPads. No issues have been identified in the latest spot check.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The UK Partnership Principles (PPs) are not applicable. The delivery mechanism for this Project is through a Service Providers and civil society and has a lower degree of proximity to government.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The Final Evaluation of the Programme has been contracted out by DAI and will be led by IDS. IDS conducted the baseline survey in 2012 and the MTR in 2015 which provide guidance and direction for the last year of the programme.

The planned evaluation by IDS is scheduled to be carried out from July to November in time to feed into DIALOGO PCR for the overall Project.

The Final Evaluation will generate findings on each of the key elements of DIALOGO Theory of Change (Civic Engagement, Municipal Engagement and Media Strengthening and Engagement). It will aim to identify key lessons learned not only on performance within each one, but also on how the elements have been combined to contribute to outcomes and impact at the organisational, neighbourhood, municipal and national levels. The Final Evaluation will also take a preliminary view on the likely sustainability of the changes to which DIALOGO has contributed at different levels.

Monitoring progress throughout the review period

DIALOGO has a Monitoring and Evaluation Learning Strategy which it prepared at the start of the programme. The PMU monitors the programme and collects output data through :

1. Regular project monitoring visits. Every quarter PMU managers carry out planned and unplanned field visits and interact with DIALOGO partners in order to collect additional information and monitor progress.
2. Partners’ quarterly progress reports which report against DIALOGO’s logframe.
3. Municipal seminars. The PMU conducts a Learning seminar each year in each of the target municipalities. The last one was carried out in September and October 2016. The objective is to measure progress and gather all stakeholdes to discuss progress based on partners’ reports, discuss data for each outputs, as well as reflect on changes related to the political and economic context and the programme’s assumptions and risks’ framework.

Last year’s Medium Term Review (MTR) also monitored progress at output and outcome levels and underpinned the activities for the last phase of the programme.

The PMU reports on progress every quarter to DFID by providing a narrative report which is discussed at quarterly management meetings with DAI, DFID and COWI. DFID SRO and DFID Programme Manager chair and attend all quarterly meetings with DIALOGO to monitor progress and regularly follow up on recommendations from Annual Reviews. Minutes and actions points are agreed at the meetings and followed up in the following meeting to ensure progress on agreed actions.

As part of this Annual Review, the DFID team conducted a visit to Nampula in February to meet Project stakeholders and see the results on the ground. When speaking with government and communities, they felt that engagement and good governance were key to introducing positive change in the community and towards a more responsive municipality. The visit gathered people from the community, the local youth association, two journalists, and municipal government officials who demonstrated their enthusiasm of community problem solving. Talking to the various associations, they felt empowered to engage with the municipality. The project demonstrated local community-municipal led initiatives and solutions such as: a waste disposal site and locally made big metal bins; a covered market with a public toilet; separate cooking and selling space; public toilets in the city; as well as hand-made tree baskets and other types of locally made trash bins.

The AR Review mission team also met with DAI to finalise additional inputs to this AR and conducted a desk-based review of all key documents (such as the Gender Strategy, DIALOGO Annual Report, and Vfm Strategy).

The AR was conducted during April 2017 by a core team of DFID staff including the SRO for this Programme (Governance Adviser), a Social Development Adviser, an Economist and Programme Manager from DFID Mozambique.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process