Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / China UK Global Health Support Programme (GHSP)
Programme Value: GBP 12 million		Review Date: 6-15 March 2017
Programme Code:	Start Date:Jan 2013	End Date: September 2017

Summary of Programme Performance
Year	2012	2013/4	2014/5	2015/6	2016/7
Programme Score		A	A	A+	A+
Risk Rating		Low	Low	Low	Low

Summary of progress and lessons learnt since last review

The China-UK Global Health Support Programme (GHSP) is a partnership based on China’s progress in improving health outcomes and its potential to make a greater contribution to global health. The business case is based on the assumption that China has experiences to share with other countries, and that a UK-China partnership will both enhance China’s effectiveness in the provision of development cooperation for health and increase China’s role in global health policy and governance. It takes place at a time of increasing attention to global health by the Chinese Government and the desire of both partners to increase their cooperation on global issues, including cooperation in health and development.

The review takes place more than three years into the substantive work of the project. Work under Output 1 (distilling and disseminating Chinese experience in improving health outcomes) is now complete and a final report was issued in November 2016. This output has resulted in an impressive body of research and policy advice from four Chinese partner institutions - working with around 15 local and 15 international partners - for around GBP 1.3 million (15. 3 Million CNY). Given the large audience that will be reached through published articles, books, training materials and policy briefs, work under this output represents very good value for money.

The research components of Output 2 (increased understanding of best practice in health and development) and Output 3 (enhanced contribution to global health policy and government) are similarly almost complete. As with output one, a significant body of analysis and research has been produced - at very modest cost - which has the potential to increase China’s understanding of the health and development policies of other countries and to influence China’s support for improving health outcomes in other countries. There is evidence - for example the role of PKU in advising the Chinese delegation on approaches to evaluating the reform of WHO - of how work funded by GHSP is directly influencing global health policy and practice. Key components of Output 3 are the development of China’s Global Health Strategy and the establishment of the China Global Health Network. The role of the PIA in the former has changed from generating research to drafting the strategy on behalf of the NHFPC. It now seems likely, however, that the GHS will be issued as an NHFPC document, with the endorsement of the Ministry of Foreign Affairs and MOFCOM. The Global Health Network held a successful first annual meeting after its launch last year with over 300 participants. It has been agreed that support to the CGHN will continue - through a no-cost extension - through to mid-2018.

There has been slow progress on the implementation of three pilot projects (in Tanzania, Myanmar and Ethiopia) under Output 4 and a further project implemented by China CDC has been added to the portfolio in Sierra Leone. It has recently been agreed that projects in Myanmar and Tanzania will continue as part of the no-cost extension to mid-2018. More detailed comments on each project are found in the body of thisreview. One of the three initial pilots has the potential to demonstrate improvements in health outcomes assuming that the final round of surveys is done at an appropriate time.

Lessons learned

Policy Briefs: 16 policy briefs have been published in English, mostly products of Output 1 based on China’s experience in public health. For the most part, they are of a quality equivalent to those produced by UK resource centres, but at much lower cost. Additional policy briefs are available in Chinese - many of which deal with issues around the effectiveness of Chinese aid in other countries. These briefs, which have not been reviewed, have the potential to be relevant to changing operational approaches; they include assessments of the effectiveness of Chinese medical teams and trends in international health development assistance. Reports from PIAs also recognize - in the words of a report from Fudan - the need for a greater understanding of the difference of the “contextual situation” in partner countries. The message from two Chinese members of the TAG is that the quality and relevance of policy briefs has improved over time - albeit more in terms of their technical content than their ability to communicate recommendations in terms that are likely to influence policy makers. A further observation is that briefs coming from institutions in Beijing, where there is a greater degree of interaction with government - show a greater awareness of current policy debates (for example on the efficacy of Chinese aid) and thus are more likely to have an impact.

Influencing policy and practice: The last AR noted a marked change in the quality, sophistication and openness of conversations held with PIAs around issues of aid effectiveness. This continues.

  - At the most basic level, respondents agree there is a need to broaden the scope of Chinese health cooperation, from medical services to disease control, maternal and child health and health system strengthening. Topics not covered in the original design of GHSP, despite their relevance to China and to the global health agenda - such as NCDs, health security, tobacco control food safety, and road safety - are still not prominent in the discussion.
  - At the next level, it is recognized that effectiveness depends on a better understanding of the cultural and institutional context in recipient countries, links to national policies and budgets (particularly given past problems with staffing and maintenance of Chinese built facilities) and that future progress requires a critical mass of professionals experienced in project management and implementation.
  - The next stage: moving from understanding to implementing changes in practice will take time and a more sustained link with MOFCOM. The pilots do not provide sufficient opportunities to put new understanding into practice.

Links with MOFCOM: The last review highlighted the importance of a stronger and more sustained relationship between the work of GHSP and MOFCOM. Links have been established through CNHDRC and through GHSP supported training courses for consultants and health aid managers, as well as technical advisory documents on health aid programmes, focusing particularly on health facilities and human resource development. MOFCOM is also represented on the Strategic Oversight Committee by the Department of International Trade and Economic Affairs (but not the Department for Foreign Assistance). The meeting between for the AR and MOFCOM was cancelled.

  - MOFCOM’s engagement with the issues raised by the project is critical in achieving the main outcome of GHSP. There are some promising signs. It is evident, for example, that MOFCOM is more closely engaged with the GHSP funded project run by China CDC in Sierra Leone. In addition, UNICEF has submitted a proposal to MOFCOM (through CICETE, a MOFCOM implementing agency) with NHFPC for strengthening MCH services in 8 African countries. WHO has also signed an MOU with the Government of the People’s Republic of China (not just NHFPC) on health sector cooperation under the Belt and Road Initiative. It thus appears that there is a real interest within MOFCOM to seek support and advice for how to programme China’s financial commitments to health in Africa and beyond.

Global Health Strategy: The expected output of this component is a research report with recommendations for the Government to consider when developing the GHS. The fact that the NHFPC quickly decided to use the research output to produce the NHFPC GHS is a notable and positive achievement. The Global Health Strategy itself has gone through several drafts in the last year. It now appears that it will be released as an NHFPC document, rather than a strategy for government as a whole endorsed by MOFCOM and the Ministries of Finance and Foreign Affairs, as was originally intended. The reasons advanced for this is that the time needed to secure buy-in across government would significantly delay release. At the same time, a document that only addresses the role and work of NHFPC suggests that the strategy will have a much more limited impact. AR and TAG interviews suggest that discussion of the role and financial contribution of MOFCOM and MOFA in the document have been “softened” and, of greater concern, that health security does not feature prominently in the GHS or in the Healthy China 2030 policy.

Pilot projects: Several key lessons emerge from the pilot projects. First, as noted previously, the main purpose of the pilots is to increase the exposure of Chinese institutions, experts and officials to the operational realities of international health cooperation through a learning by doing approach, particularly in countries with multiple development partners. Given that long-term engagement on the part of Chinese officials is clearly important - some of the pilots have been more successful than others in this regard. Second, in the context of a project exploring the potential for China-UK government-to-government partnership, there has been only limited engagement of DfID or the respective Chinese Embassies in pilot project countries. Thirdly, and leading on from the previous point, many of the countries involved have moved beyond the idea of donors working on multiple pilots and are keen to give greater emphasis to coordination among partners as a means of working to scale. The focus on pilots as part of GHSP thus risks perpetuating the notion that there is a straightforward trajectory between the successful completion of a pilot and more widespread implementation - an orthodoxy that in most parts of the world has had its day. Finally, a more positive lesson could emerge from the work of CDC in Sierra Leone - a country where China has strong engagement (as a result of work on Ebola) and one where MOFCOM has a clear interest in scaling up funding. The project will carry out a series of feasibility studies, which can be developed as proposals for MOFCOM funding. Whilst such funding is not guaranteed, this approach (using GHSP funds as a catalyst for proposal development in MOFCOM priority countries) may represent a fruitful approach in the future.

Sustainability: GHSP has been a successful catalyst - generating an interest in global health and in understanding best practice in development cooperation.

  - Pressure from PIAs has been successful in securing recognition for global health as an academic discipline (see last year’s recommendations) and there is no doubt that work stated as part of the project will continue. Indeed, many PIAs are already expanding their networks of national and international contacts and plans for further research, policy analysis and documentation are in the pipeline. Obviously, sustainability is enhanced by a favourable policy environment and the commitment of China to enhance its position as a major financier of international development. Nevertheless, GHSP has been an important instrument in helping to promote the production of a body of high-quality work that will provide a solid platform for the future. The decision to extend support for the Global Health Network, which currently relies heavily on GHSP funding, makes sense as it would otherwise be vulnerable. However, the organisers of the Network need to use the additional time to develop a sustainable resource mobilisation strategy.

  - Sustaining work started as part of the pilots beyond the project period appears unlikely. The value of the pilots needs to be seen instead in terms of lessons learned by Chinese individuals and institutions about new ways of operating and about how to overcome the many operational obstacles that have been encountered. It is vital that these lessons be properly documented.

China-UK partnership: The partnership between China and the UK is highly valued and among those interviewed there is unanimous support for finding a way of sustaining the relationship. A lesson that emerges from the review is that those activities where there is direct interaction between UK and Chinese professionals are perceived to be the most valuable. An example: while added to the GHSP following earlier work in China, the relationship between CNHDRC and NICE International addressed live issues on hospital cost containment in China and partner countries. Since the formal end of the project, work has flourished nationally and has been expanded by CNHDRC, attracting additional international funding, and enabling active involvement in global networks on health technology assessment. At policy level, the presence of DfID advisers at the First Global Health Network meeting was genuinely appreciated. Similarly, the involvement of internationally-known experts in consultancy training had a significant impact, and there remains an expectation that China-UK dialogues at health minister and higher levels will continue to be critically important in informing China’s role in global health and enhancing inter-ministerial coordination in China.

Summary of recommendations for the next year

MOFCOM: Translating the lessons learned and new approaches to health development cooperation on a large scale depends on further developing the relationship between project partners and MOFCOM. Specific actions include a better understanding of the modalities for implementing the South-South and other newly established funds administered by MOFCOM, and thus the channels by which the experience of the project can be utilised in practice. Additionally, the project should aim to build on recent experience from Sierra Leone such that feasibility studies can be developed as proposals for future MOFCOM funding. Action: SOC

Pilot projects: The no-cost extension in Tanzania will allow a final survey to take place (in June 2018) as this project has the potential to show health outcome associated with the introduction of a Chinese experience in malaria control. The main benefit of the pilot projects collectively derives from documenting lessons learned for the future of Chinese development assistance. It is recommended that work on documentation of experience become an explicit part of the rationale for the proposed extension of GHSP to mid-2018. Responsibility for analysis and dissemination should be included as part of the TORs for the Global Health Network. Action: SOC

Global Health Network: It is important that the GHN develops a role that goes beyond running an annual meeting. Current thinking is that it should seek to mobilise funds and award small research grants to its members either singly or for joint work. Part of the distinctiveness of the GHN, however, lies in its broader membership beyond the academic community. It is therefore recommended that the GHN be given responsibility by SOC to work on documentation of lessons learned in operationalizing new approaches to Chinese development assistance. This should draw on the experience of the pilot projects but, in addition, should take into account lessons learned by PIAs in conducting overseas research and analysis and the problem of placing secondees in international organizations. Resources should be allocated both for the synthesis of information, developing recommended solutions, but also for running dissemination workshops that include representatives from MOFCOM and the parts of government working on new approaches to foreign aid (see Policy Context below). Action: SOC, GHN

Synthesizing lessons from research and analysis: A significant body of research and analysis has been produced by GHSP. Bringing the findings together in synthesized form (particularly from Outputs 2 and 3) could become a very useful resource for the future. It is recommended that the members of the TAG collaborate to produce a suitable framework for the synthesis. Action: SOC, TAG, PIAs

Future China-UK health and development partnership: There is wide interest in sustaining a partnership between China and the UK that makes use of Britain’s experience in health and development cooperation. The form that such a partnership should take has yet to be defined. Given the rapid developments in the policy space around health and development (see Context below) a smooth transition to a subsequent phase is desirable, and should be an explicit agenda item at the forthcoming China-UK Health Dialogue. Action: SOC

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

The China-UK Global Health Support Programme (GHSP) is a partnership based on China’s progress in improving health outcomes and its potential to make a greater contribution to global health. The business case is based on the assumption that China has experiences to share with other countries, and that a UK-China partnership will both enhance China’s effectiveness in the provision of development cooperation for health and increase China’s role in global health policy and governance. It takes place at a time of increasing attention to global health by the Chinese Government and the desire of both partners to increase their cooperation on global issues, including cooperation in health and development foreign aid.
The GHSP seeks to strengthen China-UK collaboration and build capacity for China to increase engagement in global health. It aims to increase learning from China’s experience of improving health outcomes and reforming its health system and to increase China’s engagement in overseas health aid and in global health governance. It builds on a long history of DFID partnership with Chinese government and is a new phase in China-UK collaboration in health. Similar to a number of contemporaneous programmes, the GHSP gives support to China as a means to increase China role in global health and to increase south-south learning, as well as build a foundation for long-term China-UK partnership.
The project was initiated in September 2012 through a Memorandum of Understanding between the UK Department for International Development (DfID) and the Ministry of Commerce (MOFCOM). A project launch workshop took place in January 2013. Thereafter, over the course of 2013 and early 2014, the newly established Project Management Office (PMO), under the guidance of the Strategic Oversight Committee (SOC), co-chaired by the National Health and Family Planning Commission (NHFPC), MOFCOM and DfID, defined technical requirements, established management systems and conducted a bidding processes for consortia of Project Implementation Agencies (PIAs) that will carry out activities for the four main outputs of the project. A Technical Advisory Group (TAG) made up of experts from China and the UK supports the work of the PMO and SOC.

Impact: China-UK partnership that contributes to improved global health policy and outcomes.

Outcome: UK partnership helps China improve its contribution to global health and achieve the potential of its health cooperation.

Outputs:
Increased capacity to distil, disseminate and apply Chinese experience in improving health outcomes and strengthening health systems.

Improved understanding amongst Chinese officials and researchers of best practice in international health development cooperation (including bilateral and multilateral).

Enhanced capacity of Chinese officials/researchers to contribute to global health policy & governance.

Pilot partnerships apply China experience and international best practice in development cooperation in five developing countries that are preferably DFID priority countries and including cross border.

Policy Context

Recent developments point to increasing engagement by China in global health. Key initiatives are described in more detail in a recent report from the e-Pact evaluation group on China’s increasing global health engagement and emerging China-UK collaboration. In summary:

Healthy China 2030 framework (October 2016) issued by the Central Committee of the Chinese Communist Party and the State Council calls for strengthening of international exchange and cooperation through implementing China’s Global Health Strategy; developing new cooperation modalities; increasing people to people exchange; promoting health cooperation with neighbouring countries through the Belt and Road Initiative (BRI); strengthening south-south cooperation, particularly in Africa; promoting Chinese traditional Medicine internationally; and playing a full part in global health governance. Also within the strategy it is suggested that China should improve the competitiveness of its health industries. The inclusion of the Global Health Strategy in the 2030 framework is seen by NHFPC as a major achievement by NHFPC - in terms of dissemination the “concept” of the GHSP.

NHFPC workplans for 2017 include a similar list of priorities. They include a Healthy Belt and Road conference is scheduled for August 2017 (following a leadership summit in May, which will be attended by heads of State (and the WHO D-G Margaret Chan); increasing cooperation with the BRICS; a joint meeting with of central and eastern European Ministers of Health; and reforming the management of Chinese medical teams in Africa.

WHO Global Health Promotion Conference (November 2016). Premier Li Keqiang’s opening address stated that China will continue to promote global health issues while providing aid to other developing countries and called for strengthening policy dialogue around health systems strengthening particularly in relation to health security.

In January, the Chinese Government signed an MOU with WHO on health cooperation as part of the Belt and Road Initiative during the visit of President Xi to Geneva.

In September MOFCOM released a draft consultation document setting out plans for a South-South Cooperation Aid Fund, now said to be worth $2 billion over 5 years. Proposals for work in 8 African countries have been prepared by UNICEF and NHFPC.

Cooperation Policy (November 2016): The 32rd CPC Reform Committee Meeting, CPC central committee approved 4 important documents related to reform of China's foreign policy, including: Reform of Management Structure of the Central and Local Foreign Offices; Strengthening the reform of leadership structure, management system and monitoring of overseas representative offices; Opinions on reforming foreign affairs personnel; and Opinions about reforming foreign aid work. Specifically about reforming China's foreign aid, CPC spelled out four strategies to optimize strategic planning for foreign aid, improve fund and project management, reform foreign aid management system and elevate the effect of foreign aid.

In summary, the wave of political support for global health continues to increase in amplitude: with multiple geographical foci - China-Africa, the Belt and Road Initiative and the BRICS countries; and with increased engagement with global forums and institutions. While there arguably remains a gap between policy intent and the channels and systems for changing the approach to international cooperation in health, the need for new approaches (as evidenced by the November announcement on Cooperation Policy) signals that these issues are clearly on the agenda.

Acronyms

AIIB	Asia Infrastructure Investment Bank
AMR	Anti-Microbial Resistance
CAITEC	MOFCOM think tank (equivalent to CNHDRC for NHFPC)
CCUGH	Chinese Consortium of Universities in Global Health
CGHN	China Global Health Network
CNHDRC	China National Health and Development Research Centre
BRI	Belt and Road Initiative (the most current acronym see also OBOR)
DFID	Department for International Development
EVD	Ebola Virus Disease
GHS	Global Health Strategy
GHSP	Global Health Support Programme
GoC	Government of China
IET (e-PACT)	Independent Evaluation Team (Consortium)
MCH	Maternal and Child Health
MFA	Chinese Ministry of Foreign Affairs
MOFCOM	Chinese Ministry of Commerce
NHFPC	National Health and Family Planning Commission
NIPD	National Institute of Parasitic Disease
OBOR	One Belt One Road
PIA	Programme Implementing Agencies
PKU	Peking University
PMO	Programme Management Office
SOC	Strategic Oversight Committee
VFM	Value for Money
WHO	World Health Organisation

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

China - UK partnership helps China improve its contribution to global health and achieve the potential of its health cooperation

The outputs of the project show every sign of being achieved in their own terms. Although the pilot projects are an important part of the whole learning package, given the change in the policy context and the surge of interest in global health, the work done under outputs two and three has the potential to be influential in its own right. However, an outcome defined in terms of changes in development cooperation practice depends - to a very significant extent - on increased interest and demand on the part of MOFCOM. This, in turn, is likely to be influenced by growing pressures to show progress on implementing Presidential spending commitments - particularly in Africa.

Indicator 1: China is an active participant in a range of global health fora. The targets/milestones set for March 2017 in the log frame are framed in terms of numbers of Chinese officials appointed. A possibly more useful measure (particularly for WHO) is to take account of area’s of China’s influence. In the last year this includes support for the development of the WHO framework for engagement with Non-State Actors and approaches to evaluating WHO reform.

Indicator 2: The pilots have yet to be formally evaluated, nevertheless there are already important lessons to be learned. To date these lessons have not been well documented. An alternative approach is suggested in the recommendations.

Indicator 3: While the Global Health Network itself may not be the source of advice. It can act as a platform for the institutions and individuals that are members, and add value and consistency to the advice they provide. Moreover, the demand for advice is likely to grow.

Overall output score and description

The overall output score acknowledges successful achievement against specific logframe targets. An issue that needs to be addressed in the remaining part of the project is to seek a better synthesis of the wide range of deliverables produced by the PIAs. Despite last year’s recommendation (#6) the work of each output, for example in the final report of Output 1, is still presented separately for each PIA. The focus of the PMO has been primarily on timely and on-budget delivery. The need is now to complement this approach (as suggested by the TAG last year) such that it is possible to get a more holistic view of how the body of knowledge and skills generated by GHSP can be used to help maximise China’s contribution to global health and to inform an effective, strategic collaboration between China and the UK on health issues in the longer term.

Key actions/recommendations

MOFCOM: Translating the lessons learned and new approaches to health development cooperation on a large scale depends on seeking to further develop the relationship between project partners and MOFCOM. Specific actions include a better understanding of the modalities for implementing the South-South and other newly established funds administered by MOFCOM, and thus the channels by which the experience of the project can be utilised in practice. Additionally, the project should aim to build on recent experience from Sierra Leone such that feasibility studies can be developed as proposals for future MOFCOM funding. Action: SOC

Pilot projects: The no-cost extension in Tanzania will allow a final survey to take place (in June 2018) as this project has the potential to show health outcome associated with the introduction of a Chinese experience in malaria control. The main benefit of the pilot projects collectively derives from documenting lessons learned for the future of Chinese development assistance. It is recommended that work on documentation of experience become an explicit part of the rationale for the proposed extension of GHSP to mid-2018. Responsibility for analysis and dissemination should be included as part of the TORs of the Global Health Network. Action: SOC

Global Health Network: It is important that the GHN develops a role that goes beyond running an annual meeting. Current thinking is that it should seek to mobilise funds and award small research grants to its members either singly or for joint work. Part of the distinctiveness of the GHN, however, lies in its broader membership beyond the academic community. It is therefore recommended that the GHN be given responsibility by SOC to work on documentation of lessons learned in operationalizing new approaches to Chinese development assistance. This should draw on the experience of the pilot projects and, in addition, should take into account lessons learned by PIAs in conducting overseas research and analysis. Resources should be allocated both for the synthesis of information but also for running dissemination workshops that include representatives from MOFCOM and the parts of government working on new approaches to foreign aid (see Policy Context below). Action: SOC, GHN

Synthesizing lessons from research and analysis: A significant body of research and analysis has been produced by GHSP. Bringing the findings together in synthesized form (particularly from Outputs 2 and 3) could become a very useful resource for the future. It is recommended that the members of the TAG collaborate to produce a suitable framework for the synthesis. Action: SOC, TAG, PIAs

Future China-UK health and development partnership: There is wide interest in sustaining a partnership between China and the UK that makes use of Britain’s experience in health and development cooperation. The form that such a partnership should take has yet to be defined. Given the rapid developments in the policy space around health and development (see Context below) a smooth transition to a subsequent phase is desirable, and should be an explicit agenda item at the forthcoming China-UK Health Dialogue. Action: SOC

Has the logframe been updated since the last review?

No

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased ability to distil and disseminate Chinese experience in improving health outcomes and strengthening health systems that is relevant to Low Income Countries
Output number per LF		Output 1	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress *
Output indicator 1.1	10 institutions + 34 individuals	15 institutions + individual milestone significantly exceeded
Output indicator 1.2	200 publications/papers	c. 70
Output indicator 1.3	10 partnerships	15
Output indicator 1.4	10 research dissemination events	<10
Output indicator 1.5	2	4
Output indicator 1.6	2	4

* Based on Output 1 Final report November 2016. Numbers are approximate as the report does not tabulate deliverables by output indicators. It is also important to note that the logframe defines five categories and milestones of achievement under output indicator 1.2. As for the 2016 review, the table shows only an undifferentiated and approximate cumulative total of publications and papers.

Key Points
Financial data for Output 1 as of 8 March 2017 is shown in the table (RMB 10 000):
		2016/17			(RMB 10 000)
Output 1	PIA	Forecast	Actual	Total Contract Value	Accumulated Spending to date
GHSP-CS-OP1-01	National Institute of	9.07	99.01	344.15	331.93
Disease Prevention and Control	Parasitic Disease, China CDC
GHSP-CS-OP1-02	Global Health Institute,	11.34	32.44	378	342.03
Reproductive Health / Maternal and Child Healthcare	Fudan University
GHSP-CS-OP1-03	School of Public Health,	28.62	0	405.72	334.35
Health Systems Strengthening	Peking University
GHSP-CS-OP1-04	National Health Development Research Centre	0	115.27	599.68	525.75
The Practice and Experience Dissemination of China Integrated Care Pathway and Payment Reform

Findings

This part of the project is now complete and a final report has been issued which provides an account - for each PIA separately of work carried out. Savings from GHSP-CS-OP1-04, as anticipated last year, have been made available for other aspects of the project.

Summary of responses to issues raised in previous annual reviews (where relevant)

Training on preparing policy brief has continued as recommended. TAG members involved report improvements in quality. This is born out by the English language briefs now available.

Dissemination: The routes for dissemination have not significantly changed and depend on the PMO. PIAs report little feedback once policy briefs have been finalised.

Recognition of global health as an academic discipline has been achieved.

Recommendation

Synthesizing lessons from research and analysis: A significant body of research and analysis has been produced by GHSP. Bringing the findings together in synthesized form represents a very useful resource for the future. It is recommended that the members of the TAG collaborate to produce a suitable framework for the synthesis. Action: SOC, TAG, PIAs

Output Title	Improved understanding amongst Chinese officials and researchers of best practice in international health development cooperation (including bilateral and multilateral).
Output number per LF		Output 2	Output Score	A+
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress*
Output indicator 2.1	15 policy papers	15+
Output indicator 2.2	20 relevant research projects	20+
Output indicator 2.3	4 think tanks	4
Output indicator 2.4	50 consultants	Not determined

Key Points
Financial data for Output 2 to 8 March 2017approved by SOC and implemented by PIA are shown in the table (RMB 10 000):

OUTPUT 2	PIA	Forecast	Actual	Total Contract Value	Accumulated Spending to date
Centre of Excellence in HDA
GHSP-CS-OP2-01	School of Public Health, Peking University	79.05	36.40	399.92	362.85
GHSP-CS-OP2-02	China National Health and Development Research Centre	169.08	25.54	399.98	270.22
GHSP-CS-OP2-03	National Institute of Parasitic Disease, China CDC	157.80	75.39	399.50	307.09
Secondment	ZHUSONGSONG, SHIYUHUA, ZHANGYUN, ZHANGJIUQIN,HEQUN	56	45.12	107.56	77.32
HDA Training	National Health Development Research Centre	10	10.12	81.92	59.36
HDA Training	IDS	25	21.68	63.02	58.23

The semi-annual report (to September 2016) suggests that the milestones in the logframe have all been exceeded. Precise figures are difficult to ascertain from reports as the PMO does not record achievements according to log frame indicators. In relation to indicator 2.3 the groups at NIPD, PKU, Fudan (School of Public Health) and CNHDRC are all capable of acting as effective think thanks in relation to their respective areas of expertise. All of these institutions conduct consultancy and NIPD has developed a data base for consultants. The exact number of staff working as consultants is hard to ascertain and has little real meaning without some associated measure of competence and quality.

The number of secondments under GHSP has been less than expected and, as a result to the many difficulties encountered, the 8th Meeting of SOC suspended this aspect of the programme. Given the value of working experience in international organizations, it is important that the problems that hinder secondments are more fully understood with a view to finding structural solutions. This should be part of the documentation of experience suggested in Recommendation #3.

Recommendation
A significant body of research and analysis has been produced by GHSP. Bringing the findings together in synthesized form (particularly from Outputs 2 and 3 which are currently only available in Chinese) could become a very useful resource for the future. It is recommended that the members of the TAG collaborate to produce a suitable framework for the synthesis. Action: SOC, TAG, PIAs

Output Title	Enhanced ability of Chinese officials and researchers to contribute to global health policy and governance.
Output number per LF		Output 3	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Output indicator 3.1	GHSP-supported Network fully functioning, providing forum for discussion, development and mutual learning among PIAs and other concerned institutions	Successful first annual meeting held December 2016
Output indicator 3.2	Policy relevant research contributing to Global Health Strategy	Global Health Strategy in 7thdraft after extensive internal and external consultations. GHS to be issued as NHFPC document.
Output indicator 3.3	Joint (China-UK) work on global health issues of shared concern in global governance debates	UK-China Global Health dialogue postponed in 2016

Key Points

Financial data for Output 3 to 22nd January 2016 is shown in the table (RMB 10 000):

OUTPUT 3	PIA	Forecast	Actual	Total Contract Value	Accumulated Spending to date
GHSP-CS-OP3-01	School of Public Health, Peking University	159.32	48.42	492.28	443.41
GHSP-CS-OP3-02	School of Public Health, Fudan University	198.45	95.44	449.82	325.98
China Global Health Network (CGHN) related technical activities	PMO	80	24.03	N/A	24.03
CGHN international conference & annual meeting CGHN	PMO-CGHN	40	44.63	N/A	44.63
Health and Post MDG Roundtable	School of Public Health, Fudan University	39	5.07	77.85	45.4

Findings

China’s Global Health Strategy

The strategy has gone through several drafts and a series of consultations (within and beyond the NHFPC - with NDRC, CFDA and others including Chinese Traditional Medicine). Rapid acceptance of the research report represents a positive achievement of the project. Furthermore, high level support for the idea of a GHS is apparent from its appearance in the healthy China 2030 document and there is a reference to the implementation of the strategy in NHFPC 2016 work priorities. It will be important in subsequent reviews to assess the importance given to global health security as some interlocutors suggested that it does not have the prominence it deserves, particularly in the healthy China 2030 Healthy China document.

The Global Health Network
The first International Symposium on Global Health Development was convened by the China Global Health Network in November 2016 and attracted over 300 participants. DfID Asia health advisers meeting in Beijing at the same time took part as active participants.

In addition to the annual meeting the Network secretariat organized bids for research on local production of medicines in Africa by Chinese pharmaceutical companies; organized a meeting at the request of NHFPC DIC for 20 experts and scholars from 7 institutions under the rubric of the China Harvard Africa Network, effectively an extension of GHN; and publicised its activities on WeChat.

Work on by the Network has been extended to mid 2018.

Other aspects of OP3
No contribution has been made to China Africa Roundtable. The work on SDGs has continued in Fudan independently of GHSP with subcontract funding from the Gates Foundation.

The China-UK Health Dialogue was last held in September 2015. A further meeting is scheduled to take place in mid-2017.

Recommendations:

It is important that the GHN develops a role that goes beyond running an annual meeting. Current thinking is that it should seek to mobilise funds and award small research grants to its members either singly or for joint work. Part of the distinctiveness of the GHN, however, lies in its broader membership beyond the academic community.

It is therefore recommended that the GHN be given responsibility by SOC to work on documentation of lessons learned in operationalizing new approaches to Chinese development assistance. This should draw on the experience of the pilot projects but, in addition, should take into account lessons learned by PIAs in conducting overseas research and analysis and the problem of placing secondees international organizations. Resources should be allocated both for the synthesis of information, developing recommended solutions, but also for running dissemination workshops that include representatives from MOFCOM and the parts of government working on new approaches to foreign aid.

The GHN should use the extended period of GHSP funding to develop its own longer term resource mobilisation strategy.

Output Title	Pilot partnerships apply China experience and international best practice in development cooperation in Low Income Countries and cross border (probably to include in the first instance Malaria, Universal Health Coverage, Maternal and Child Health, Polio and Human Resources for Health).
Output number per LF		Output 4	Output Score	A/B
Risk:		Low	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Output indicator 4.1	2 pilot partnerships implemented	Project implementation has started in Tanzania (NIPD), in Myanmar and Ethiopia (Fudan) and in Sierra Leone (China CDC).
Output indicator 4.2	2 pilots incorporate international best practice and Chinese experience	Elements of Chines experience incorporated in Tanzania. Less evident in Myanmar and Ethiopia. Work in Sierra Leone in very early stages.
Output indicators 4.3	Improved Chinese engagement with international health cooperation	Relationships in pilot countries mainly confined to direct project partners. Potential for wider engagement in Tanzania and Sierra Leone

Key Points

Financial data to 8 March 2017 (RMB 10,000)

OUTPUT 4	PIA	Forecast	Actual	Total Contract Value	Accumulated Spending to date
GHSP-CS-OP4-D02	Malaria Pilot	1040.69	643.88	1700	890.15
GHSP-CS-OP4-D01	MCH Pilot	1461	282	2400	843.17
GHSP-CS-OP4-D03	China CDC	150	122.19	301.76	122.19

In addition to discussions with PIAs (Fudan, NIPD and CDC) more detailed observations on the pilot projects are contained in a report by the ePact Consortium submitted in February 2016.

Overall progress has been slow and several problems have been encountered.

Tanzania (partnership between NIPD and Ifakara Health Institute (IHI)): This is a complex and ambitious project with multiple components. IHI is experienced in dealing with overseas collaborators. It is not part of the government health system but has good relationships with the district and national authorities, thus offering the possibility that recommendations can have wider influence. The most distinctive elements of Chinese experience are to apply time limits to a WHO-defined test and treat regime. NIPD also is hoping to introduce new Chinese survey software. Chinese staff has worked on the project but each team is replaced after three months, putting a significant burden on IHI (the problem arises in part due to strict visa restrictions). Language skills have constrained learning in many instances. There remain concerns about the feasibility about introducing new software more widely. The main difficulty encountered this year has been a suspension of funding consequent on a failure by NIPD and IHI to secure prior approval of their procurement plan. Following an audit carried out by PwC in Tanzania the issue has been resolved satisfactorily. Both sides realised an error had been made and are committed to ensuring that it will not be repeated. A point of concern is that the project continues long enough to conduct a final survey in the high-transmission season (June 2018). Assuming this survey is carried out, there is a chance of showing a reduction in malaria transmission associated with the partnership.

Myanmar: In Myanmar and Ethiopia Fudan is working through Marie Stopes International an International NGO on improving MCH services is one Township close to Yangon. Kunming Medical University working with Myanmar Public Health University is responsible for conducting a baseline survey. Exposure of Chinese staff to working in Myanmar is limited. The project strategy has been to introduce international best practice in terms of removing economic barriers to facilitate institutional maternal care and childbirth. The extent to which this differs from the approach used by PSI and other INGOs working in Myanmar is not clear. Problems also appear to have arisen with regard to the needs of migrant populations that result from a failure to recognise significant difference between local and Chinese circumstances. Moreover, the overall approach is largely based on what MSI is doing in other townships with little change being introduced as a consequence of the partnership. Methodological problems with the proposed baseline survey appear likely to make it difficult to draw convincing conclusions from the pilot.

Ethiopia: A two-pronged project with one element following the same approach, working with MSI, as in Myanmar. The second element, added opportunistically by the PI from Fudan is to use the facilities of the Chinese Friendship hospital for midwife training. However, due to difficulties with procuring equipment the trainings have been held in Shanghai. Procurement difficulties seem to have been the dominant problem to date. Given the contractual relationship between MSI and the Regional Bureau in Ethiopia, failure to resolve difficulties around the agreed provision of equipment could lead to further problems. One Fudan staff member has been stationed in Ethiopia. The Ethiopia project will end in June 2017.

Sierra Leone: Less a pilot project and more an outcome of discussions at the China-UK Health Dialogue on collaboration in Sierra Leone post-Ebola. MOFCOM is supporting the establishment of Tropical Disease Research Laboratory in Freetown. GHSP is supporting the costs of a staff member in the P3 lab, a series of feasibility studies, the visit of 8 experts to China and 4 Chinese staff to Sierra Leone. An important possible outcome given the priority afforded to Sierra Leone by MOFCOM is that the feasibility studies lead to proposals for future MOFCOM financing, and proposals for UK and China collaboration in Sierra Leone. The original aim was that activities on the ground be carried out in partnership with Public Health England. This relationship has yet to be fully established.

In the first three pilots the relationship in countries is between Chinese institutions and local partners with little or no involvement of local UK or China Government representatives.

Recommendation

The no-cost extension in Tanzania will allow a final survey to take place (in June 2018) as this project has the potential to show health outcome associated with the introduction of a Chinese experience in malaria control. The main benefit of the pilot projects collectively derives from documenting lessons learned for the future of Chinese development assistance. It is recommended that work on documentation of experience become an explicit part of the rationale for the proposed extension of GHSP to mid-2018. Responsibility for analysis and dissemination should be included as part of the TORs for the Global Health Network.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Financial data 2016/17 as of 8 March 2017.

 	(GBP 10 000)
Financial Year 2016/17	Output 1	Output 2	Output 3	Output 4	Management	Governance	M & E	TOTAL
Forecast as of 31 March 2016	4.9	52.69	53.68	265.17	25.89	22.09	6.1	430.52
Actual as of 8Mar 2017	29.18	23.67	23.87	122.32	32.47	8.92	5.75	246.18

VfM performance compared to the original VfM proposition in the business case
The value for money proposition made in the original business case is based on the assumption that the different capacity building components of the project will result in improving the efficiency and effectiveness of China’s health cooperation. While the costs are relatively small at GBP12 million, the potential gains, while difficult to monetise, were predicted to be significant. Unit costs were to be controlled through project monitoring and through careful negotiation of performance based contracts with PIAs. All these assumptions remain valid.

Assessment of whether the programme continues to represent value for money
Experience to date suggests that the project represents even greater value for money than was expected in the business case. The reason is that the policy context has changed significantly (see section A). Thus for the same outlay the potential for influence is much greater.
The project logic no longer relies on building a case with government for changes in the form and content of Chinese aid, there is already a growing demand for advice, for example on how to programme health aid in Africa and as part of BRI. The likelihood of project partners being able to influence project outcomes has therefore increased substantially. While GHSP is not the only initiative that seeks to influence Chinese health and development cooperation it is seen as one of the most important and is likely to be copied by others and thus create further spin-offs.
Project governance and management continues to focus on value for money and efficiency. The production of policy briefs on the Chinese experience in global health illustrates how the project is achieveing value for money. The quality of the English language briefs is now roughly equivalent to those produced by a UK resource centre; the audience for such briefs is large in China; and there is also an appetite for understanding the Chinese experience globally. Had the production of these briefs been led by UK institutions working with Chinese partners (rather than vice-versa) costs would have been substantially higher. In addition, because contracting of UK and other international partners was managed by the PIAs, unit costs for external inputs were, for the most part, much lower than UK market rates.

Quality of financial management

The most recent audit was carried out in April 2016 by auditing all implementation activities that took place in calendar year 2015. There were no qualifications noted in the report.

Date of last narrative financial report	31 December 2015
Date of last audited annual statement	29 June 2016

E: RISK (½ page)

Overall risk rating:

Minor

Overview of programme risk

The PMO following a recent training course has produced a detailed Risk Management Register providing more detail on specific project related risks. Only 5 of the 19 risks identified are classified as moderate (there are no minor risks in the register). Six severe risks appear: political factors in pilot countries cause project termination; pilots are not completed; the innovative nature of pilot activities might not lead to expected objectives; the influence of changes in SOC membership; insufficient managerial experience on the part of PIAs leads to delays and mistakes; foreign exchange fluctuations reduce project funding.

The risks are realistic and some have been experienced. Most have been successfully managed and the cumulative risk to the project as a whole is rated as minor.

Outstanding actions from risk assessment

No action beyond the recommendations in this report are indicated

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Implementation of OP1-3 is on track. The pilots under OP4 have been delayed. The no-cost extension to allow completeion of selected activities is well justified.

Performance of partnership (s)

Partnerships operate at several levels within GHSP:

Between the Governments of China and the UK: Interlocutors interviewed during the AR all held this relationship to be valuable, and were all keen that ways be found to ensure that it is continued beyond the end of the project period.

Between PMO and the PIAs: The focus of the PMO is that workplans are approved and that activities are carried out on time and on budget. The partnership is primarily administrative rather than strategic in nature.

Between DfID, MOFCOM and NHFPC/DIC: this partnership operates primarily through bi-annual meetings of the SOC. Its influence on ensuring that learning from the project affects the work of both ministries is more limited.

Between the TAG and PIAs: The Chinese members of the TAG have influenced the quality of policy briefs. The UK members’ role has been more limited (effectively only coming into its own when attending meetings in China).

Asset monitoring and control

The programme does not involve purchase of significant assets but some computers, printer etc for the programme management office at the first year of the programme. There has been no change since then. Procedure for purchase, management and disposals of assets is set out in the programme management manual. The inventory list is attached in Annex 2.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Formal evaluation of the GHSP is the responsibility of the Independent Evaluation Team (IET). The final evaluation will now be delayed until 2018 in line with the project extension.

Monitoring progress throughout the review period

The annual review was conducted 6-15th March and included visits to all PIAs (with the exception of OP104). Some visits were conducted with a member of the IET.

Time		Agenda	Location	Contact Person and Others
Mar. 6th		Arrive in Shanghai
	09:00-12:00	Interview with PIA-NIPD (OP202, OP4D02) / PI Prof. Zhou Xiaonong周晓农	National Institute of Parasitic Diseases, China CDC (NIPD) / 中国疾控中心寄生虫病预防控制所	Ms. Guan Yayi官亚宜 / 13818987832 / Ms. Li Hongmei李红梅 / 13661583552 / Ms. Tang Yingjie汤滢洁 / 13651678523
	14:00-15:00	Interview with PIA-Fudan University (OP302) / PI Prof. Chen Wen 陈文	School of Public Health, Fudan University (OP302) / 复旦大学公共卫生学院	Ms. Huang Jiayan黄葭燕 / 13764258490
	15:30-18:30	Interview with PIA-Fudan University (OP4V01) / PI Prof. QianXu钱序	Global Health Institution, Fudan University(OP102, OP4V01) / 复旦大学全球健康研究所	Mr. Liang Ji梁霁 / 13621693855
Mar. 7th	10:00	Travel to Beijing
	14:00-15:00	Meeting with DFID China	DFID Office / DFID北京办事处	Ms.Ma Xiaochun马晓春 / 13801326676
Mar. 8th	09:00-10:00	Interview with TAG- Prof. Zhang Jianping张建平	商务部国际贸易经济合作研究院区域经济合作研究中心 / Center for Regional Economic Cooperation, Chinese Academy of International Trade and Economic Cooperation, Ministry of Commerce	Mr. Zhang Jianping张建平 / 010-64212175
	14:00-15:00	Interview with TAG- Prof. XuTongwu (in PMO) 徐彤武	PMO, CPSM, NHFPC / 国家卫生计生委项目资金监管服务中心	Mr. Chen Xun陈逊 / 13439401020
	15:00-19:00	Leader of PMO –Mr. Zhang Zhaoyang张朝阳	PMO, CPSM, NHFPC / 国家卫生计生委项目资金监管服务中心	Mr. Chen Xun陈逊 / 13439401020
		PMO team members
Mar. 9th	09:00-11:00	Interview with PIA-China CDC (OP403) / PI Prof. Liang Xiaofeng梁晓峰 / Mr. Wang Xiaochun 王晓春	China CDC / 中国疾病预防控制中心	Mr. Zhang Honglong张洪龙 / 13811336697
	14:30-15:30	Interview with TAG- Prof. Han Tieru韩铁如		Mr. Chen Xun陈逊 / 13439401020
	19:00	Interview with TAG-Stewart Tyson		Phone: +44 (0)17683 62327 / +44 (0)7557738156 / Skype: stewart.tyson1
Mar. 10th	14:00-15:30	Interview with PIA-Bejing University (OP201) / PI Prof. Meng Qingyue 孟庆跃	School of Public Health / 北京大学公共卫生学院	Ms. Ding Chaochao丁超超 / 18701386617
	15:30-17:30	Interview with PIA-Bejing University (OP301) / PI Prof. Liu Peilong刘培龙 / Key member Prof. Guo Yan 郭岩	School of Public Health / 北京大学公共卫生学院	Ms. Ding Chaochao丁超超 / 18701386617
	19:00	Interview with TAG-Laurence		Phone: +44(0)1225 446 261 / +44 (0)7748908915 / Skype: charlottelaurence
Mar. 13th	14:00-16:00	Interview with PIA-CNHDRC (OP203) / PI. Dr Yang Hongwei杨洪伟 / Key team member Dr. Wang Yunping 王云屏	China National Health Development Research Center / 卫生发展研究中心	Ms. Fan Xiaodan樊晓丹 / 18610568640
Mar. 15th	9:00-10:00	Interview with representatives of DICof NHFPC / Mr.NieJianggang (division director) 聂建刚	Department of International Cooperation, NHFPC / 国家卫生计生委国际司	Ms. Li Ying 李颖 / 13811906235 / Mr. Chen Xun陈逊 / 13439401020
	13:00-15:00	Debriefing meeting with DFID	DFID Office / DFID北京办事处	Ms.Ma Xiaochun马晓春 / 13801326676

Annex 1: Agenda for the 4th GHSP Annual Review
6-15 March 2017
Annex 2 Asset Inventory

No	Procurement	Item	Specification	Unit
1	GHSP-GS-01 Electronic office equipment	Desk-top computer	ThinkCentre M6400t	8
2		Lap-top computer	ThinkPad T440p 20AN002JCD	16
3		Mobile hard-drive	WDBY8L0020BBK-PESN	16
4		Color printer	Epson R3000	1
5		Portable printer and copy machine	HP 1213nf	1
6		Digital camera	Canon 60D	1
7		Web service	IBM X3300 M4（7382I01）	1
8	GHSP-GS-02 management software	Finance management software	GRP-U8	1
9	GHSP-GS-03 interpretation equipment	Portable transmitter	WT-080T	2
10		Portable receiver	WT-080T	20

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter:Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to betaken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process