Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: China UK Global Health Support Programme (GHSP)
Programme Value: GBP 12 million		Review Date: 11-19 January 2016
Programme Code:	Start Date: Jan. 2013	End Date: September 2017

Summary of Programme Performance
Year	2012	2013/14	2014/15	2015/6
Programme Score		A	A	A+
Risk Rating		Low	Low	Low

Summary of progress and lessons learnt since last review

Programme activities

The China-UK Global Health Support Programme (GHSP) is a partnership based on China’s progress in improving health outcomes and its potential to make a greater contribution to global health. The business case is based on the assumption that China has experiences to share with other countries, and that a UK-China partnership will both enhance China’s effectiveness in the provision of development cooperation for health and increase China’s role in global health policy and governance. It takes place at a time of increasing attention to global health by the Chinese Government and the desire of both partners to increase their cooperation on global issues, including cooperation in health and development.

The present review takes place following almost two years of substantive GHSP activities. Forecast annual expenditure for FY 2015/16 was GBP 5,137,100 with actual expenditures at 20 January 2016 of GBP 2,128,00 in respect of 203 activities. The work under Output 1 (distilling and disseminating Chinese experience in improving health outcomes) will be largely complete by the end of the current Financial Year. Activities being implemented by Project Implementing Agencies (PIAs) under Ouputs 2 and 3 (increased understanding of best practice in health and development and enhanced contribution to global health policy and governance respectively) are on track, and with some exceptions (discussed below) rates of implementation are broadly in line with overall plans. Contracts have been signed for two pilot projects in third countries under Output 4, but implementation will continue to be subject to significant delays. A futher area subject to delay has been the deployment of secondees to overseas agencies. While the obstacles to the overseas posting non-diplomatic Chinese personnel have been identified by the PMO, at the time of the semi-annual report only one person has been deployed out of 20 planned postings

The most significant achievements during the year have been the development of the Global Health Strategy (a third draft of which is currently under review) and the launch of the Global Health Network in December 2015.

The Project Management Office is increasingly effective and has established an on-line Programme Information System to streamline reporting. The SOC continues to provide oversight to the project. In January, however, the Director-General of the Department of International Cooperation of the NHFPC has left to take up a position in WHO Geneva. The Technical Advisory Group now has six active members.

Lessons learned

Progress over the 10 months since the last review has been impressive. Not just in terms of specific outputs, but in terms of the productive partnership that GHSP seeks to establish between the UK and China, and the importance attached to global health as a policy concern at the highest levels of the Chinese government. In this sense GHSP is more than the sum of its parts. Despite the specific delays noted above, overall progress suggests that the project will exceed initial expectations. This conclusion is reflected in the overall annual review rating.

Evidence from the interviews conducted for the Annual Review support this conclusion in several ways: the growing number of individuals exposed to issues in global health; the growing sophistication of the discourse on global health issues among PIAs and government officials, including a much greater degree of openness about the limitations of China’s current approaches to programming aid; a clearer understanding of what China can offer through its assistance, and a recognition that China needs to learn more about policy processes in developing countries; an acknowledgement of the importance of software and capacity building as well as hardware and construction in development assistance; an eagerness to pursue trilateral projects with the UK in future development assistance; the link established the Development Research Centre on global health issues through the flagship course and the Global Health Network; and the establishment of a growing network of international partnerships involving PIAs beyond those financed specifically by GHSP.

While the PMO is scrupulous in recording all GHSP financed activities, it is increasingly clear that there are a growing number of activities that are informed and influenced by the experience of the project that are not captured by formal reporting. Two examples illustrate this point: a) the role of Professor Qian Xu’s group in Fudan in advising the NHFPC on the design of maternal and child health projects in Africa, and b) the link between work in the National Institute of Parasitic Diseases supported by GHSP and NIPD’s influence on the work of China CDC in Africa, the establishmengt of an African CDC, and through CDC support to the African Union.

MOFCOM remains engaged with GHSP through the SOC. A link has also been established between China National Health Development Research Centre (CNHDRC) - supported by GHSP - and the equivalent think-tank (CAITEC) established to serve MOFCOM. At project level, the main link with MOFCOM has always been through the Department of International Trade and Economic Affairs. A key challenge as the China Global Health Strategy is further refined is to increase the engagement of the MOFCOM Department of Foreign Assistance if the proect is to increase its influence on the form and content of Chinese aid in the field of health and development.

Despite the delays in setting up the proposed pilot projects a number of lessons have been learned as a result of the project in terms of institutional obstacles and how to overcome them in deploying Chinese financial and technical assistance. These lessons will be useful in establishing new ways of working in other developing countries in future. It is critical that they are fully captured by the PMO and incorporated in the Global Health Strategy.

A point of discussion with all those interviewed was whether a) GHSP should be extended and b) whether there should be a new project on completion of the current one in 2017. On the question of extension, there was broad agreement among the PIAs directly involved and Ministry officials that an extension would be necessary to gain the maximum value from the proposed pilot projects (OP4), and that early termination would compromise lesson learning and would neither be in the interest of China or the countries in which the pilots are planned.

While it is premature to say anything definitive about the form or content of a possible GHSP 2.0, there was widespread support for finding ways of maintaining the partnership between China and the UK in global health - with the emphasis less on academic work and more on building the capacity of the Global Health Network and strengthening the links between the many agencies involved in China’s overseas assistance.

Summary of recommendations for the next year

Responses to the issues raised in the 2015 review are recorded in the relevant sections below. All recommendations and actions for this year are summarised below and set out in more detail under each Output.

Key actions/recommendations

Global Health Network: SOC should address at its next meeting how GHSP can best ensure the short and longer-term viability of the Global Health Network. This will include the issues related to the capacity of the secretariat, sustainable financing and wider membership outlined above. Funds available for reallocation within the GHSP budget should used to support the Network

Global Health Strategy: The key challenge is to institutionalise the relationship between the key governmental agencies involved in the further development and implementation of the strategy - particularly the relationship with the Foreign Assistance Department of MOFCOM.

Training for writing policy briefs: It is recommended that the training on preparing policy briefs - recognizing that different approaches are needed for Chinese government and international audiences - be continued and that the TAG member involved in organizing the course continue to provide critical feedback to the briefs prepared by PIAs.

Dissemination of policy briefs: Currently briefs are submitted to the PMO. They may then appear on the website and be submitted to SOC. It is recommended that PMO work with SOC to define more clearly the pathways by which briefs prepared under the project can reach a wider audience beyond NHFPC.

Recognition of global health: Many of the staff working in PIAs have to maintain their academic positions. Career progress and research funding requires publication and work on approved topics. Currently the National Science Foundation of China does not recognize “global health” as a topic for research. While approaches to the NSFC have been made in the past it is critical - for the sustainability of work in the universities on global health - that a further attempt be made to secure the required recognition.

Reporting at the Annual Meeting: In line with the suggestions from the TAG members (above), it is recommendd that PIAs report on progress toward overall outcomes at the next annual meeting. TAG members may consider facilitating the preparation of synthesis reports.

Pilot projects: In principle it is recommended that GHSP be extended to allow completion of the planned pilot projects. The length of the extension should be determined by a review of progress over the course of 2016.

Learning from current experience: Despite the delays in setting up the proposed pilot projects a number of lessons have been learned as a result of the project in terms of institutional obstacles and how to overcome them in deploying Chinese financial and technical assistance. These lessons will be useful in establishing new ways of working in other developing countries in future. It is recommended that these lessons are captured and written up by the PMO so that they can be incorporated in the Global Health Strategy.

Increasing Chinese representation in global health: A recommendation last year was made following the observation that several persons interviewed during the review would be eligible for international positions. The proposal was that GHSP consider holding a workshop on how to apply for work in global health organizations. This recommendation still stands.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

The China-UK Global Health Support Programme (GHSP) is a partnership based on China’s progress in improving health outcomes and its potential to make a greater contribution to global health. The business case is based on the assumption that China has experiences to share with other countries, and that a UK-China partnership will both enhance China’s effectiveness in the provision of development cooperation for health and increase China’s role in global health policy and governance. It takes place at a time of increasing attention to global health by the Chinese Government and the desire of both partners to increase their cooperation on global issues, including cooperation in health and development. foreign aid.
The GHSP seeks to strengthen China-UK collaboration and build capacity for China to increase engagement in global health. It aims to increase learning from China’s experience of improving health outcomes and reforming its health system and to increase China’s engagement in overseas health aid and in global health governance. It builds on a long history of DFID partnership with Chinese government and is a new phase in China-UK collaboration in health. Similar to a number of contemporaneous programmes, the GHSP gives support to China as a means to increase China role in global health and to increase south-south learning, as well as build a foundation for long-term China-UK partnership.
The project was initiated in September 2012 through a Memorandum of Understanding between the UK Department for International Development (DfID) and the Ministry of Commerce (MOFCOM). A project launch workshop took place in January 2013. Thereafter, over the course of 2013 and early 2014, the newly established Project Management Office (PMO), under the guidance of the Strategic Oversight Committee (SOC), co-chaired by the National Health and Family Planning Commission (NHFPC), MOFCOM and DfID, defined technical requirements, established management systems and conducted a bidding processes for consortia of Project Implementation Agencies (PIAs) that will carry out activities for the three main outputs of the project. A Technical Advisory Group (TAG) made up of experts from China and the UK supports the work of the PMO and SOC.

Impact: China-UK partnership that contributes to improved global health policy and outcomes.

Outcome: UK partnership helps China improve its contribution to global health and achieve the potential of its health cooperation.

Outputs:
Increased capacity to distill, disseminate and apply Chinese experience in improving health outcomes and strengthening health systems.

Improved understanding amongst Chinese officials and researchers of best practice in international health development cooperation (including bilateral and multilateral).

Enhanced capacity of Chinese officials/researchers to contribute to global health policy & governance.

Pilot partnerships apply China experience and international best practice in development cooperation in five developing countries that are preferably DFID priority countries and including cross border.

Policy Context

Global Health is increasingly high on the policy agenda in China. In part this is a function of the growing importance attached to involvement in global affairs more broadly on the part of the Chinese leadership, as evidenced by recent developments, including the establishment of the BRICS Bank, the Asia Infrastructure Investment Bank (AIIB) and the One Road One Belt Initiative. During 2015, the importance of health as a component of China’s foreign assistance has been further enhanced as a result of commitments made by the President at the UN and during his recent visit to Africa, where health is one of 10 major components in the announcement of overall support to countries in the continent worth USD 60 billion.

In the 2015 review it was noted that Chinese involvement in the outbreak of Ebola Virus Disease (EVD) had been a game changer. The Ebola response provided important lessons for China and GHSP partners in terms of a) the need for a more comprehensive response beyond the provision of doctors, that includes public health and laboratory facilities and liaison with other sectors, including military assets; b) a recognition that China has a valuable role to play in global health security beyond its own borders; and c) an awareness of the complexity of the policy, institutional and cultural dimensions involved in international support. Discussions with NHFPC and China CDC officials suggest that there have been further reflection on the lessons over the course of the year - including the practical difficulties to be overcome in establishing working relations with other bilaterals (for example in implementing the high level commitments to work jointly with partners from the UK in setting up laboratory services).

The key challenge now is to mainstream the lessons being learned from GHSP as China prepares to implement the commitments made by President Xi Jinping in Africa. The announcement made in Cape Town made reference to 100 hospitals - a term suggested by MOFCOM. However, it is generally understood that in practice the commitment is to improving health in Africa - through a range of different programmes including MCH, malaria control, primary care as well as through hospital construction. A lesson emerging from the analyses of current Chinese assistance concerns the importance of involving African officials in defining needs, and for China to be responsive to these demands. Increasingly this will involve dialogue in country beyond that currently conducted through the Commercial Counsellor in the Embassy. At present, however, there are relative few Chinese official in Africa with the relevant experience. The Chinese officials being posted to the African Union will help in this regard.

Acronyms

AIIB	Asia Infrastructure Investment Bank
AMR	Anti-Microbial Resistence
CCUGH	Chinese Consortium of Universities in Global Health
CGHS	China Global Health Strategy
CNHDRC	China National Health and Development Research Centre
DFID	Department for International Development
EVD	Ebola Virus Disease
GHS	Global Health Strategy
GHSP	Global Health Support Programme
GoC	Government of China
IET	Independent Evaluation Team
MCH	Maternal and Child Health
MFA	Chinese Ministry of Foreign Affairs
MOFCOM	Chinese Ministry of Commerce
NHFPC	National Health and Family Planning Commission
NIPD	National Institute of Parasitic Disease
PIA	Programme Implementing Agencies
PKU	Peking University
PMO	Programme Management Office
SOC	Strategic Oversight Committee
VFM	Value for Money
WHO	World Health Organisation

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

China - UK partnership helps China improve its contribution to global health and achieve the potential of its health cooperation.

It is reasonable to expect that the outcome of the project will be achieved.

There has been further progress towards the outcome over the course of the year. China has been active in the the development of health related Sustainable Development Goals at the UN; in WHO, on health security issues and the reform of WHO’s emergency response, as well as with global issues of particular concern to the UK such as anti-microbial resistance. China has also been involved in discussions about the reform of the governance of the Global Fund to fight AIDS, TB and malaria.

The discussion of aid commitments to Africa suggest that China has drawn on lessons from past experience and that the contribution that China will make in the future to health cooperation will improve as a result.

Indicator 1: On China’s contribution to Global Health institutions it will be important that the evaluation recognize that China is already very active in the institutions specified and to define the nature of the projects in which Chinese staff are involved in ways that capture current aid realities.

Indicator 2: It is too early to evaluate the pilot projects. However, already important lessons have been learned about the institutional obstacles inherent is setting up new ways of working with different partners in developing countrties. These lessons, if properly captured, can enhance the usefulness of the Global Health Strategy.

Indicator 3: The Global Health Network has now been established and the intention is that it will be used as both for coordination and as a source of advice. The concern (as outlined below) is to ensure its short and longer term sustainability.

Overall, the project is providing valuable learning for both sides and the high-level objective of UK-China cooperation is important for both parties.

Overall output score and description

In line with the reasoning in the summary of progress and lessons learned the outputs in combination are rated A+. However, the comment made in the summary of TAG Comments and recommendations made following the Annual Workshop in December is worth noting:

“The challenge now is to capitalise on this momentum by shifting the focus from delivering individual activities on time and on budget, to a more holistic view on how this body of knowledge and skills can be used to help maximise China’s contribution to global health, and inform an effective, strategic collaboration between China and the UK on health issues in the longer term.”

The summary note goes on to recommend that sessions at the next Annual Meeting be organized around outputs rather than individual workplans. This will require work beforehand between different PIAs working on the the same ouput to prepare a synthesis report. Facilitation by the TAG would be helpful in this regard. This recommendation is therefore included in the points that follow.

Key actions/recommendations

Global Health Network: SOC should address at its next meeting how GHSP can best ensure the short and longer-term viability of the Global Health Network. This will include the issues related to the capacity of the secretariat, sustainable financing and wider membership outlined above. Funds available for reallocation within the GHSP budget should used to support the Network

Global Health Strategy: The key challenge is to institutionalise the relationship between the key governmental agencies involved in the further development and implementation of the strategy - particularly the relationship with the Foreign Assistance Department of MOFCOM.

Training for writing policy briefs: It is recommended that the training on preparing policy briefs - recognizing that different approaches are needed for Chinese government and international audiences - be continued and that the TAG member involved in organizing the course continue to provide critical feedback to the briefs prepared by PIAs.

Dissemination of policy briefs: Currently briefs are submitted to the PMO. They may then appear on the website and be submitted to SOC. It is recommended that PMO work with SOC to define more clearly the pathways by which briefs prepared under the project can reach a wider audience beyond NHFPC.

Recognition of global health: Many of the staff working in PIAs have to maintain their academic positions. Career progress and research funding requires publication and work on approved topics. Currently the National Science Foundation of China does not recognize “global health” as a topic for research. While approaches to the NSFC have been made in the past it is critical - for the sustainability of work in the universities on global health - that a further attempt be made to secure the required recognition.

Reporting at the Annual Meeting: In line with the suggestions from the TAG members (above), it is recommendd that PIAs report on progress toward overall outcomes at the next annual meeting. TAG members may consider facilitating the preparation of synthesis reports.

Pilot projects: In principle it is recommended that GHSP be extended to allow completion of the planned pilot projects. The length of the extension should be determined by a review of progress over the course of 2016.

Learning from current experience: Despite the delays in setting up the proposed pilot projects a number of lessons have been learned as a result of the project in terms of institutional obstacles and how to overcome them in deploying Chinese financial and technical assistance. These lessons will be useful in establishing new ways of working in other developing countries in future. It is recommended that these lessons are captured and written up by the PMO so that they can be incorporated in the Global Health Strategy.

Increasing Chinese representation in global health: A recommendation last year was made following the observation that several persons interviewed during the review would be eligible for international positions. The proposal was that GHSP consider holding a workshop on how to apply for work in global health organizations. This recommendation still stands.

Has the logframe been updated since the last review?

The logframe was refined at outcome level with inputs from the Independent Evaluation Team (IET) and the Technical Advisory Group in 2015.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased ability to distil and disseminate Chinese experience in improving health outcomes and strengthening health systems that is relevant to Low Income Countries (LIC).
Output number per LF		Output 1	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress *
Output indicator 1.1	20 individuals + 6 institutes	>20 +6
Output indicator 1.2	59 publications/papers	c.72
Output indicator 1.3	6 partnerships	c.12
Output indicator 1.4	8 research dissemination events	>8
Output indicator 1.5	1	4
Output indicator 1.6	1	4

* Notwithstanding the point made above in relation to overall output achievement, the key point from the table is that the milestones, as defined in the log frame for 03/2016, have been achieved - some by a significant margin. However, the numbers derived from the semi-annual report 2015-16 (to September 30th 2015) are approximate and need to be confirmed as part of the data collection for the mid-term evaluation. It is also important to note that the logframe defines five categories and milestones of achievement under output indicator 2. As for the 2015 review the table shows only an undifferentiated cumulative total of publications and papers.

Key Points
Financial data for Output 1 as of 22 January 2016 approved by SOC and implemented by PIA is shown in the table (RMB 10 000):

Output 1	PIA	Forecast	Actual	Total contract value	Cumulative spending to date
GHSP-CS-OP1-01 / Disease Prevention and Control	National Institute of / Parasitic Disease, China CDC	111.9	145.33	344.15	232.92
GHSP-CS-OP1-02 / Reproductive Health / Maternal and Child Healthcare	Global Health Institution, / Fudan University	213.98	134.03	378.0	309.59
GHSP-CS-OP1-03 / Health Systems Strengthening	School of Public Health, / Peking University	219.14	140.54	405.72	334.35
GHSP-CS-OP1-04 / The Practice and Experience Dissemination of China Integrated Care Pathway and Payment Reform	National Health Development Research Centre	314.75	85.17	599.68	410.48

Findings

Much of the analytic work on distilling Chinese experience is now complete. The focus therefore turns to dissemination.

Out of the four components shown in the table above, the only one that is not expected to be completed by the end of the Financial Year is Component 4 on integrated clinical pathways and payment reform initiated in partnership with NICE International as part of an earlier World Bank project. Having started in 2009, this component predated GHSP but was incorporated into the project when GHSP began. The issues being addressed are relevant in China and the many other countries that are concerned to increase the efficiency and effectiveness of clinical care. However, progress has been slow and the scope of the reforms relatively narrow. Partnerships were formed with India and South Africa but have been difficult to follow up. Dr Zhao Kun’s group is now increasingly active in other networks (particularly in the area of health technology assessment). Through these links and following discussions with NICE International other sources of funding may become available (for example from the Gates Foundation). The WHO China office is also interested in collaboration as part of their work on health systems development. However, from the perspective of GHSP this component of the project should finish in March 2016, leaving an estimated RMB 1 million available for re-allocation.

Issues raised in previous annual reviews
A key finding in the 2015 Annual Review (relevant to OP1-3) was that many PIAs were working under the assumptions that peer-reviewed publications represent the main route for disseminating their findings. While this may hold true for an academic audience, decision makers in government require more concise policy-oriented briefs. This point had been made forcefully at several meetings of the SOC and the recommendation in the 2015 review was that the PMO, working with practitioners and policy makers, organize a workshop on the preparation of policy briefs. It was also recommended that NHFPC commission policy briefs on emerging research needs from PIAs - clearly specifying the format and content that they require.

Both recommendations have been acted on, and most of the PIAs are now focusing on preparing briefs in addition to their more traditional academic output. A training course on preparing briefs held in July organized by one of the new TAG members - Xu Tongwu - has been much appreciated. The same TAG member has also been reviewing briefs sent to the PMO by PIAs.

In a bid to increase quality of briefs the training course used examples of actual briefs submitted to the highest levels of government and included sessions run by a senior editor responsible for preparing such briefs. Xu Tongwu was of the opinion that the quality of briefs now being prepared by PIAs was improving but had some way to go to be of a standard that would guarantee influence. Nevertheless, progress has been significant.

Briefs for an English language audience are also now being produced - with 5 currently posted on the GHSP website (http://cps.nhfpc.gov.cn/ghsp)

Recommendations and actions

Training: It is recommended that the training on preparing policy briefs - recognizing that different approaches are needed for Chinese government and international audiences - be continued and that the TAG member involved in organizing the course continue to provide critical feedback to the briefs prepared by PIAs.

Dissemination: Currently briefs are submitted to the PMO. They may then appear on the website and be submitted to SOC. It is recommended that PMO work with SOC to define more clearly the pathways by which briefs prepared under the project can reach a wider audience beyond NHFPC.

Recognition of global health: Many of the staff working in PIAs have to maintain their academic positions. Career progress and research funding requires publication and work on approved topics. Currently the National Science Foundation of China does not recognize global health as a topic for research. While approaches to the NSFC have been made in the past it is critical - for the sustainability of work in the universities on global health - that a further attempt be made to secure the required recognition.

Output Title	Improved understanding amongst Chinese officials and researchers of best practice in international health development cooperation (including bilateral and multilateral).
Output number per LF		Output 2	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress*
Output indicator 2.1	7 policy papers	>10
Output indicator 2.2	12 relevant research projects	c.15
Output indicator 2.3	2 think tanks	3
Output indicator 2.4	30 consultants	10

*The numbers are derived from the semi-annual report (to September 2015) and are approximate. The figure for indicator 2.4, is almost certainly an underestimate given that PIA staff conduct consultancies that are informed by work under GHSP, but which are not all included in output reporting.

Key Points
Financial data for Output 2 to 22 January 2016 approved by SOC and implemented by PIA are shown in the table (RMB 10 000):

OUTPUT 2	PIA	Forecast	Actual	Total Contract Value	Accumulated Spending to date
Centre of Excellence in HDA
GHSP-CS-OP2-01	School of Public Health, Peking University	166.7	137.74	399.92	326.44
GHSP-CS-OP2-02	China National Health and Development Research Centre	224.4	118.2	399.98	244.68
GHSP-CS-OP2-03	National Institute of Parasitic Disease, China CDC	184.78	70.1	399.5	231.7
Secondment	LILIANG、YANGYAN、ZHANGYUN	105	32.2	40.41	32.2
HDA Training	National Health Development Research Centre	82	49.15	81.92	49.15
HDA Training	IDS	70	36.55	63.02	36.55

Findings

Judging by the successive interviews conducted for the three annual reviews there has been a marked change in the level of understanding among PIA staff on issues concerning global health and development. This is noticeable particulartly among staff who, as part of the research carried out for this output have been involved in field studies in developing countries, and those who have participated in events such as the World Health Assembly and WHO Executive Board.

Achievements of particular note include: an analysis of Global Health Strategies prepared by other countries, that emphasised that all countries seek benefits to their own populations (a concern raised in response to the first draft of the China Global Health Strategy); work by PIA staff on the strategy for the engagement of non-state actors with senior staff of the WHO’s Director-General’s Office; a detailed analysis of the successes and limitations of Chinese supported malaria control in Comoros, with findings to be applied in Malawi and Togo; proposals for changing current policies for the deployment of Chinese Medical Teams based in part on work in Uganda; analysis of cross-border work on malaria in Yunnan Province; and training in global health (particularly in the area of disease control) for a growing number of provincial officials.

An important point to note in relation to this output is that while progress in arranging formal secondments has been disappointing, GHSP has enabled a growing number of staff to increase their exposure to global health policy and practice through work on research and analysis, through training courses and extended visits to overseas institutions. Thus even without the secondments progress has been impressive.

This year has seen the first flagship training course held at the Institute of Development Studies (IDS) in the UK. While a more formal evaluation of the course will be conducted in due course, initial feedback has been positive. In addition to individual participant reactions, the course stands to be particularly important in terms of creating links between health and other key institutions involved in China’s development policy - notably the Development Research Centre. At an individual level, we heard several examples of how relationships built during the course have facilitated work across different institutions and branches of government.

Issues raised in previous annual reviews

The 2015 review contained several recommendations around capacity building, recognizing that many PIAs see capacity building as a key element of this project and that capacity building is too often seen in terms of training courses. The findings this year suggest that there is growing recognition both in NHFPC and in the PIAs that the most urgent need is for a greater number of Chinese officials with practical exposure to international working environments.

Specific recommendations last year in relation to the use of the flagship course as a means of building institutional and individual relationships appear to have been at least partially achieved. Other recommendations were designed to increase the number of opportunities for experience outside of Chian and to increase the awareness of GHSP among DfID advisers in other countries.

WHO has offered to find opportunities to take part in country reviews but to date they have received no takers. The proposal to hold a health advisers meeting in Beijing did not happen in 2015, but is still being considered for later this year.

Recommendations and actions

The recommendations on training and dissemination of policy briefs for OP1 are equally relevant for OP2.

One recommendation last year was made on the basis that several persons interviewed during the review would be eligible for international positions. The proposal was that GHSP consider holding a workshop on how to apply for work in global health organizations. This recommendation still stands.

Output Title	Enhanced ability of Chinese officials and researchers to contribute to global health policy and governance.
Output number per LF		Output 3	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Output indicator 3.1	Network delivering policy advice and training	Network launched December 2015
Output indicator 3.2	Policy relevant research contributing to Global Health Strategy	Global Health Strategy in 3rd draft after initial internal and external (to NHFPC) consultations
Output indicator 3.3	Information sharing and mutual understanding	Ongoing

Key Points

Financial data for Output 3 to 22nd January 2016 is shown in the table (RMB 10 000):

OUTPUT 3	PIA	Forecast	Actual	Total Contract Value	Accumulated Spending to date
GHSP-CS-OP3-01	School of Public Health, Peking University	230.11	154.35	492.28	394.99
GHSP-CS-OP3-02	School of Public Health, Fudan University	245.73	133.71	449.82	230.54
Global Health Dialogue	PMO	40	26.11	N/A	26.11
China-Africa Health Roundtable	China Chabmer of Commerce for Import and Export of Medicines and Health Products	18	63.83	79.22	63.83
Health and Post MDG Roundtable	School of Public Health, Fudan University	77.8	39.79	77.85	39.79

Findings

The Global Health Network

The GHN was launched on 6th December following a significant amount of preparatory work over the last year. It currently has 46 member institutions consisting of four tiers: core GHSP PIAs; partner institutions of PIAs; institutions that participated in the bidding for GHSP; plus other recommended institutions. Critically GHN extends beyond just universities and includes representatives from the Development Research Centre and the Association of Pharmaceutical Manufacturers. It will also have a link with the a network that is to be established between China, Harvard University and a number of African countries - and thus is already staring to make links with other international networks.

GHN has a 12 member board and the Secretariat, which will have no separate legal identity, will be hosted by different institutions on a 3-year rotating basis, starting with Peking University. The Network will be led by Professor Liu Peilong supported by one part-time staff member, Wang Yu.

GHSP funds have been used for the launch, but to date the network has received no additional funding.

The functions of the network, as previously agreed, are to act as a platform for coordination between institutions active in global health both in terms of their own work and the provision of advice and support to other parts of government.

Progress to date is exciting and there is a great deal of interest in the potential of the network. However, it is evident that the Network will need to overcome three key challenges:

Leadership and capacity: The network is fortunate to have an a leader who is able to represent the interests of the whole group and not just a single institution. However, to increase awareness of its work the network needs more capacity than it has at present - even just to maintain an information flow between members.

Finance: The Network will require financial support. In this regard, a way needs to be found to separate funding for PKU from funding for the GHN. The Innovation Fund that was discussed during last year’s review as a possible vehicle for supporting the Network has not been established. Nevertheless, discussions this year suggest that support for the network should be a priority for any funds available for reallocation (see under OP1). Beyond GHSP, it will be important to seek funding from other sources. Whether the pharmaceutical industry is the best place to start (as has been proposed by some members) needs careful consideration.

Membership: The impact of the network will depend on both deepening and widening membership. Deepening the expertise of the initial core with other institutions already active and experienced in global health, and widening to include more partners from other sectors and institutions new to global health.

Global Health Strategy

There has been significant progress in preparing China’s Global Health Strategy. The background research has been completed; a steering committee chaired by the Deputy Minister has been established; and internal and external consultation on initial drafts have been held; a third draft is currently iunder review. External consultations have involved the Ministry of Foreign Affairs, Ministry of Finance, MOFCOM, DRC, CFDA, and other institutions including those involved with international strategic issues, African development and Chinese Traditional Medicine.

Feedback on early drafts has stressed the need for the strategy to make clear the benefits that will accrue to China. In addition more work was said to be needed on health security issues.

Next steps include a further round of formal consultations within NHFPC and, subsequently, with a wider group of stakeholders. This will be followed a series of seminars to gain wider input and understanding of the strategy. These will be organized under the auspices of the Global health network.

While work on the Global Health Strategy has responded to many of the challenges noted in last year’s review, many still remain relevant:

On content: decisions will be needed as to: where China’s priorities should lie in global health; what objectives it should be aiming to achieve; what level of resources will be required to achieve these objectives; to what extent multilateral versus bilateral channels will be used; how and to what end China seeks to influence global health institutions; the role of non-state actors in health and development; China’s positions in regard to on-going global negotiations; what mechanisms are needed to support new ways of working in countries - particularly those that involve passing resources to non-Chinese institutions. With regard to the last point learning from oversease work under GHSP and, ultimately the pilot projects, will be important.

On process: The Global Health Strategy needs to be embedded in a broader debate on Chinese global development policy. Interest is growing both in MOFCOM, MOFA, the Development Research Centre of the State Council as well as other sectoral agencies who are now considering whether they should develop similar strategies. The ideas behind a global health strategy are thus gaining increasing traction. Neverthless work remans to be done to institutionalise relationship with other major players across government.

Other Components of OP3

China-Africa Roundtable: The 5th in the series of China-Africa Roundtables was held in March 2015 co-sponsored by Qinghua University and China’s Chamber of Commerce of Import and Export of Medicines and Health Products. Recommendations were passed to a subsequent ministerial meeting. GHSP contribution to the China-Africa Roundtable to date has been largely financial. Given the need now to move beyond broad statements about the priority to be given to health, and the establishment of a the Global Health Network with its potential links to networks in Africa, GHSP support may no longer be required.

Roundtable on Health and the Sustainable Development Goals: This component has been added to the GHSP portfolio as a result of a suggestion from NHFPC for more work on the significance of the SDGs for China’s. Consultations on the research protocol took 10 months to complete. While the Roundtable meeting led to interesting discussions about the future of China’s support to SDG related issues, it remains unclear as to the future of the specific research being conducted under this component.

Recommendations and actions

Global Health Network: SOC should address at its next meeting how GHSP can best ensure the short and longer-term viability of the Global Health Network. This will include the issues related to the capacity of the secretariat, sustainable financing and wider membership outlined above.

Global Health Strategy: The PMO should should aim to capture lessons learned from overseas work funded by GHSP as a contribution to the Global Health Strategy. At a more macro level, the key challenge is to institutionalise the relationship between the key governmental agencies innvolbved in the further development and implementation of the strategy.

Output Title	Pilot partnerships apply China experience and international best practice in development cooperation in Low Income Countries and cross border (probably to include in the first instance Malaria, Universal Health Coverage, Maternal and Child Health, Polio and Human Resources for Health).
Output number per LF		Output 4	Output Score	A
Risk:		Low	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Output indicator 4.1	2 pilot partnerships implemented	Contracts signed for pilots a) in Tanzania with NIPD and b) in Myanmar and Ethiopia with Fudan. Managememnt structures negotiated but implementation not started
Output indicator 4.2	2 pilots incorporate international best practice and Chinese experience	Two-way learning started in Tanzania
Output indicators 4.3	Improved Chinese engagement with internatonal health cooperation

Key Points

Contracts for the two projects under Output 4:.

OUTPUT 4	PIA	Forecast	Actual	Total Contract Value	Accumulated Spending to date
GHSP-CS-OP4-V02	Malaria Pilot / National Institute of Parasitic Diseases, China CDC	843.27	312.71	1700	246.27
GHSP-CS-OP4-V01	MCH Pilot, / Global Health Institute, Fudan University	1239.26	212.04	2400	354.81

Findings

Progress on developing the pilots - one in Tanzania on malaria initiated by NIPD and one each in Ethiopia and Myanmar initiated by Fudan Global Health Institute - has been slow for a variety of reasons. The two sets of pilots raise different issues.

Fudan Global Health Institute working on maternal and child health in partnership with an INGO (Marie Stopes International -MSI) in Myanmar and Ethiopia. The original intention had been for Fudan to work with partner countries with whom they are engaged through work on OP1 (Ghana, Lao and Vietnam). However, a decision by SOC that pilots should be only developed in LDCs required a change of plan. Contacts in MSI were approached and suggested partnerships in two countries where they are working. Much of the last six months has been taken up developing a complex management structure acceptable to all parties. While this is now agreed, several further uncertainties remain before work can begin. In Myanmar, the partnership with MSI requires a new MOU with government and the baseline study requires ethical approval. Given the change in government in Myanmar, it is unclear when either will be forthgcoming. Progress in Ethiopia is further advanced and preparatory and launch workshops have taken place in country.

The MSI partnerships raise several issues: the difficulty of Chinese personnel having sufficient time in country to learn from the project; issues relating to transfer and accountability for funds to a third party; the limited potential for introducing Chinese experience into pilot projects that have already been started. Nevertheless, while it is unlikely that the Government of China will want to replicate a model involving partnership with an INGO, there are important lessons to be learned from the work with MSI for others such as universities and other non-government partners that may wish to do so.

One further development of note in Ethiopia, following a country visit, the Principle Investigator, Professor Qiuan Xu, seized upon an additional opportunity not envisaged in the original proposal to work with the Chinese Medical Team in Addis to establish a training centre for local staff using Chinese expertise.

NIPD working with Ifakara Research Institute in Tanzania. This project is further advanced: baseline data have been collected and are being jointly analysed. The project has benefitted from the experience of Ifekara in managing externally financed research projects and the long-standing engagement of NIPD in WHO and other disease control networks. In other words it is developing along more familiar pathways than the Fudan projects.

At the same time, it is clear that the project has the potential for important lesson learning. Following the initial baseline study it is clear that translating Chinese experience directly into a radically different context is not going to work. Rather, a process of mutual adaptation is required from which both parties can learn. In contrast to other projects hosted by Ifekara where external researchers take data for analysis, all the work from the baseline has been handled jointly with Tanzanians coming to Shanghai.

At a broader level Professor Zhou Xianong defines three levels of collaboration: from basic sharing of knowledge, through sharing techniques, up to influencing policy. He is keen that the the pilot learn lessons for China and his institution on how to move from the first two to the third level.

Recommendations and actions

In principle it is recommended that GHSP be extended to allow completion of the planned pilot projects. The length of the extension should be determined by a review of progress over the course of 2016.

Despite the delays in setting up the proposed pilot projects a number of lessons have been learned as a result of the project in terms of institutional obstacles and how to overcome them in deploying Chinese financial and technical assistance. These lessons will be useful in establishing new ways of working in other developing countries in future. It is recommended that these lessons are captured and written up by the PMO, with support from the TAG, so that they can be incorporated in the Global Health Strategy.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Financial data for 2015/16 to 22nd January 2016 are set out in the table.
        (GBP 10 000)

Financial Year 2015/16	Output 1	Output 2	Output 3	Output 4	Management	Governance	M & E	TOTAL
Forecast as of 31 March 2015	86.08	83.29	61.16	218.25	22.3	17.2	25.43	513.71
Actual as of 20 January 2016	29.52	48.02	43.64	62.33	15.8	5.65	7.84	212.8

Fund implementation has improved but remains lower than expected. Slow implementation in relation to OP1-3 is due, according to the PMO, largely to delays in making payments from PIAs to their cooperating agencies. Despite these problems the PMO estimtes that the majority of core agencies will be able to complete their activities and fund payments according to the agreed schedule.

There will however be surplus funds in the order of 10% for OP101 and 20% for OP104 (discussed under OP1 above). Overall for OP1-3, the PMO estimates that currently there is likely to be a surplus of RMB 1.3 million.

Delays in relation to OP4 have been discussed in the main report. If the pilot projects were to be extended for 1 additional year, the PMO estimate there would still be approximately RMB 14 million, representing 12% of the GHSP budget that will remain unspent if not reallocated in the meantime (see Recommendation 1 Section B).

VfM performance compared to the original VfM proposition in the business case
The value for money proposition made in the original business case is based on the assumption that the different capacity building components of the project will result in improving the efficiency and effectiveness of China’s health cooperation. While the costs are relatively small at GBP12 million, the potential gains, while difficult to estimate, were predicted to be significant. Unit costs were to be controlled through project monitoring and through careful negotiation of performance based contracts with PIAs. All these assumptions remain valid.

Assessment of whether the programme continues to represent value for money
Decvelopments over the first two years of implementation suggest that the project represents even greater value for money than was anticipated in the business case. The reason for this is that the policy context has changed in significant ways: global health is a priority now at the highest levels of government and from commitments made over the last year and China’s spending on health in third countries (in Africa and through the One Belt One Road initiative) is likely to increase. Thus for the same outlay the potential for influence is much greater.
In addition, the project logic no longer relies on building a case with government for changes in the form and content of Chinese aid, there is already a growing demand for advice, for example on how to programme $60 billion more effectively in Africa. The likelihood of project partners being able to influence project outcomes has therefor increased substantially.
While GHSP is not the only initiative that seeks to influence Chinese health and development cooperation is is seen as the most important and is likely to be copied by others and thus create further spin-offs.
Project governance and management continues to focus on value for money and efficiency.
Overall, for a relative modest level of investment DfID can expect significant value from the partnership with China in the area of global health and more broadly in the field of global development. The approach adopted by GHSP is valued and may be adopted in other sectors.

Quality of financial management

The first audit by the China National Audit Office for expenditures in 2013 included a disclaimer opinion stating “the financial report was prepared in line with China’s accounting standards and accounting system as well as relevant requirements in the programme grant agreement in terms of all major aspects, which fairly reflects financial condition, financial revenue, programme implementation as well as revenue of the Special Account of DFID’s GHSP grant between 1 January 2013 and 31 December 2013.” This indicates that the financial management meets the requirements. However, auditors pointed out that in order to reduce potential financial risks, PMO reserve the original invoices/receipts when activities are entrusted to other institutions.

The CNAO audit opinion for 2014, issued in June 2015 includes no further disclaimer. The opinion states that….”the financial statements….present fairly, in all material respects, financial position of DFID Strategy for China-UK Global Health Support Programme as of December 31st 2014, its financial receipts and disbursements of the special account for the year then ended in accordance with Chinese accounting standards and system, and the requirements of the project grant agreement.

Date of last narrative financial report	31 December 2014
Date of last audited annual statement	29 June 2015

E: RISK (½ page)

Overall risk rating: Low

Overview of programme risk

Two risks previously identified: a) that the activities of some PIAs are not relevant to policy makers and b) that the Global Health Strategy will take place without significant GHSP inputs - have diminished significantly.

Outstanding actions from risk assessment

No further action recommended.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Implementation of OP1-3 is broadly on track in terms of originally specified products. The pilot projects lag behind schedule as do formal secondments to overseas institutions. Nevertheless there has been valuable learning from efforts to establish the pilots and a growing number of Chinese officals are being exposed to new working environments through other project mechanisms.

Performance of partnership (s)

The partnerships established by the GHSP are working well,

The recommendation made last year to reduce activity reporting to the PMO from quarterly to semi-annual has been acted upon and the on-line system for financial reporting is in place.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Formal evaluation of GHSP is the responsibility of the Independent Evaluation Team (IET). A mid-term report is currently under preparation. Interviews were conducted by the ITAD team in parallel with the Independent Annual Review.

Monitoring progress throughout the review period

The annual review was conducted from 11-19 Jamnuary 2016 and included visits to all PIA teams.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process