## Guidance
UK AID DIRECT LOGICAL FRAMEWORK TEMPLATE WITH ACTIVITY LOG A logical framework or logframe is required for all UK Aid Direct projects (at the proposal stage only) . Applicants invited to proposal stage will be asked to fully complete all sections of the logical framework and activities log tabs. IMPORTANT INFORMATION ON COMPLETING THE LOGFRAME • Each logframe must be saved as a separate file in Excel format (*.xls) • The logframe must not include any more than 6 (six) outputs • The logframe must not exceed a total of 155 spreadsheet lines • The font should be no smaller than Arial 9 when completed Logframes which do not conform to the above criteria will not be considered.

## Logical Framework
Logrframe update March 2020 See associated file note for change explanations | Modern energy cooking services (MECS)
Modern energy cooking services (MECS) Research
|  |  |  | 2019-09-01 | 2020-09-01 | 2121-09-01 | 2022-09-01 | 2023-09-01 | 2024-09-01
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
Access to modern energy cooking services (MECS) accelerated in Africa and Asia towards fulfilment of SDG 7. | Number of countries that have actively implemented policies and programs to increase access to MECS | Planned | 0 | 0 | 0 | 0 | 2 | 4 cumulative | 6 cumulative | 8 cumulative, (2025)
Achieved
Source
SDG 7.1 Global Tracking Framework reports/MTF reports, Global Alliance for Clean Cookstoves Annual Reports
| Impact Indicator 2 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Increased access to MECS in Africa and Asia as reported through the SDG tracking system | Planned | to be documented | baseline % increase | baseline % increase | baseline % increase | baseline % increase | baseline % increase |  | baseline % increase 2025
Achieved
Source
SDG 7.1 Global Tracking Framework reports/MTF reports, Clean Cooking Alliance Annual Reports
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date) | Assumptions
A market ready range of innovations (technology and business models) which lead to improved choice of affordable and reliable modern energy cooking services for consumers. MECS principles adopted in the SDG 7.1 global tracking framework. Participating countries incorporate modern energy cooking services in energy policies and planning. | MECS principles adopted in SDG 7.1 global tracking framework | Planned | Binary cooking fuel reporting in GTF 2017 | 0 | MTF report (1, 18mths) includes MECS principles | SDG meeting confirming MECS principles and indicator, tracking, and reporting arrangements (1, end yr. 3) | 0 | SDG 7.1 on cooking indicator tracking and reporting with MECS principles implemented (1, end yr. 5) |  | 2023 SDG 7.1 on cooking indicator tracking and reporting with MECS principles implemented (2023) | Adoption of the principles would be the incorporation of MECS as a speciifc element of energy access, with appropriate indicators. Policies and programs could be planned implementations by Government, Larger NGOs, Private Sector or some combination of all. Risk that the innovations and business models developed do not generate sufficient interest in government and private sector to meet output and outcome indicator targets
Achieved
Source
SDG 7.1 Global Tracking Framework reports/MTF reports, Document review and stakeholder consultations
| Outcome Indicator 2 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Number of countries with planned policies and programs to increase access to MECS | Planned | 0 | 0 | 0 | 2 | 6 Cumulative | 12 Cumulative |  | 12 cumulative (2023)
Achieved
Source
MECS research program progress report, evidenced by country plans (Government, Donor or Large NGO)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£)
| £18.8M + £21m |  |  | Est.£100M
INPUTS (HR) | DFID (FTEs)
TBC
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date) | Assumptions
Understanding Transition Pathways to MECS. Improved knowledge on factors driving transitions to MECS Output 1.b:- Additional transitions:- to apply the learning of MECS to cooking at scale. Output 1.c:- Additional transitions – to enable economies to transition to more pre-cooked food. | Systematic review of current knowledge on macro and micro factors driving transition pathways to MECS | Planned | None | Database of available knowledge (literature, operational reports, etc.) (1, end yr. 1) Review methodology developed (1, end yr. 1). Interim report of Modern Energy Cooking Services Transition Pathways. (1, end yr. 1) | Systematic Review (1, end 18 mths) |  |  |  |  | 1 (01/03/2020) | That key driving factors can be identified from the macro data and systematic review. This assumes that invisible factors are not significant. Generic research outputs require further streamlining or financial support to adapt to specific country contexts; policies and environments.
|  | Achieved |  | Yes
Source
MECS research program progress report and publications
| Output Indicator 1.2 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Case studies on key driving factors or in-depth assessment of selected thematic areas | Planned | None | None | Identification and initiation of Case studies on key driving factors (new technologies, supply-side constraints, demand adoption behaviour, public policies) (3, end yr. 2). Final draft of one case study report (1, end yr. 2) | Completion of Case studies on key driving factors (new technologies, supply-side constraints, demand adoption behaviour, public policies) (cumulative 3, end yr. 3) |  |  |  | 3 (01/09/2021)
Achieved
Source
MECS research program progress report and publications
| Output Indicator 1.3 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Specific recommendations on policy interventions accelerate transition pathway and country-specific action plan. | Planned | None | None | With the advent of CCF, there are specific policy recommendation actions (action plans) initiated in 3 countries by end year 2 | i) Country-specific action plan (3 cumulative by end yr. 3) and ii) Synthesis report and a set of knowledge notes (1, end yr. 3) |  |  |  | 3 (01/09/2021)
Achieved
Source
MECS research program progress report and publications
| Output Indicator 1.b |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Case studies on key factors enabling transitions to modern energy cooking services in places such as schools, clinics and humanitarian response | Planned | None | (dependent on 1.1) | Landscaping study for 1) institutional settings and 2) humanitarian responses considering key driving factors (new technologies, supply-side constraints, demand adoption behaviour, public policies) (2, end year 2) Draft of action plan for 1 humanitarian or institutional intervention in MECS (1 end year 2) | i) Action plans for institutional and humanitarian activities (3, end yr. 3) and ii) Action plans for small- scale institutional and humanitarian activities (3, end yr. 3) A set of knowledge notes on humanitarian and institutional MECS (1, end of year 3) | Action plans implemented (1, end yr 4) | i) Action plans implemented (3 cumulative, end yr 5) ii) Synthesis report and a set of knowledge notes (1, end yr. 5) |  | 3 (01/09/2022)
Achieved
Source
MECS research program progress report and publications
IMPACT WEIGHTING (%) | Output Indicator 1.c |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
15% | Case studies on key factors enabling transitions to increase pre-cooked food as a mechanism for enhancing modern energy cooking services. Specific recommendations on policy interventions accelerate transition pathway and country-specific action plan. | Planned | None | None | Landscaping study (considering key driving factors (new technologies, supply-side constraints, demand adoption behaviour, public policies) (1 end year 2) . Draft action plan for 1 pre-cooking intervention in MECS (1 end year 2) | i) Action plans for pre-cook interventions (3, end yr. 3) and ii) knowledge note on pre-cooking (1 end of year 3) | A set of knowledge notes on pre-cooking inclusive of MECS (1, end of year 4) | Action plans implemented (3 cumulative, end yr 4) Synthesis report and a set of knowledge notes (1, end yr. 4) |  | 3 (01/09/2023)
Achieved
|  | Source | [8 empty] | RISK RATING
|  |  | MECS research program progress report and publications | [7 empty] | Minor
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  |  |  | DFID SHARE (%)
£5.3M
INPUTS (HR) | DFID (FTEs)
TBC
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date) | Assumption
Technology and Business Innovation Research conducted on socio-economic and technical innovations in MECS | Technology and business innovations experiments designed, lab tested and piloted in selected countries | Planned | None | 3 MECS innovations (TRL 4-6) proposed and lab/field-tested (end yr. 1) | 6 MECS innovations proposed with appropriate lab testing and piloting (6 cumulative, end yr 2) | Piloting of MECS innovations (TRL 6, 7) (cumulative 8 innovations, end yr. 3). | 0 | Case studies on innovatiove MECS (5, end yr. 5) |  | 2023-09-01 | That the global trend which is lowering the cost of renewable energy (particularly Solar PV) and energy storage continues. Such reductions are based on the "learning rates" for the new technologies and should continue. That no major incidence, economic shock or shortages disrupt the global learning rate for the above technologies. That Governments, NGOs and Private Sector can translate a willingness to consider emerging technology into an active piloting, testing and experiential data gathering alongside consumer priorities. That some of the technical innovations do not reach viable system price points. That global changes in alternative fuel prices and/or system components/inputs make proposed MECS approaches and designs unaffordable.
|  | Achieved |  | Yes
Source
MECS research program progress report and publications
| Output Indicator 2.2 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Life cycle analysis and modelling undertaken for innovations | Planned | None | Framework for application of LCA ISO to MECS in place | Cradle to gate model complete for two iMECS (User stories) | Cradle to cradle model complete for two iMECS | LCA model refined and additional iMECS (user stories) evaluated | Generic guidelines for iMECS identified |  | 2023-09-01
|  | Achieved |  | Yes
Source
MECS research program progress report and publications
| Output Indicator 2.3 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Consumer preferences studies relating to MECS innovations documented and evidenced (with an increased focus on urban studies). | Planned | None | Studies conducted in 2 countries, draft analysis available | Studies either initiated or completed (5 cumulative, end Year 2) | Draft analysis and report available from fieldwork (5 end year 3). Field work initiated for 3 more studies (3 end year 3) | Studies conducted (8 + 2 cumulative, end yr. 4) | Analysis report and a set of knowledge notes (1, end yr. 5) |  | 2023-09-01
|  | Achieved |  | Yes
Source
MECS research program progress report and publications
| Output Indicator 2.4 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Innovation environment for priority countries mapped and engaged. | Planned | None | Studies on Innovations systems conducted in 3 countries (TRL 1 to 7 explored) | Innovation systems mapped (2 countries, end yr. 2) | Innovation systems mapped (5 cumulative countries, end yr. 3) | Discussions conducted with priority countries for ongoing innovation in MECS (6, end yr. 4) | Capacity for innovation strengthened (3 countries, end yr. 5) |  | 2023-09-01
|  | Achieved |  | Yes
Source
MECS research program progress report and publications
IMPACT WEIGHTING (%) | Output Indicator 2.5 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
40% | Innovation challenge (and accelerator) funds applied for energy storage, energy efficiency, alternative fuels, and distribution models. | Planned | None | Innovation proposals applied 1 initial round | Innovation call for proposals made (4 cumulative, end yr. 2) | Innovation call for proposals made (6 cumulative, end yr. 3) | Innovation call for proposals made (7 cumulative, end yr. 4) |  |  | 2022-09-01
|  | Achieved |  | Yes
|  | Source | [8 empty] | RISK RATING
|  |  | MECS research program progress report and publications | [7 empty] | Moderate
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  |  |  | DFID SHARE (%)
£11.4M + 5.8m
INPUTS (HR) | DFID (FTEs)
TBC
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date) | Assumption
Global Tracking: The Shift to Modern Energy Cooking Services | MECS conceptual framework defined with indicators and country examples | Planned | None | Draft MECS conceptual framework developed (1, 12 mths); Final Draft of 2020 ESMAP Global Review Report (1, 12 months) | MECS conceptual framework developed (1 report, 18 mths); Country-specific analysis (6 countries, end yr. 2) | Synthesis report and a set of knowledge notes (1, end yr. 3) |  |  |  | 2021-09-01 | That the MTF and MECS discussions find the practical and political space for insertion into the SDG processes. That adoption of the framework is not hijacked by groups with anti mitigation of climate change agenda.
|  | Achieved |  | Yes
Source
MECS research program progress report and publications
| Output Indicator 3.2 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Guideline, tools, and training conducted to mainstream MECS data collection | Planned | None | Guideline on MECS data collection methodologies developed (1, end yr. 1) | MECS data collection templates and tools developed (1, 18 mths) | Training conducted to mainstream MECS data collection in national statistics system (3, end yr. 3) |  |  |  | 2021-09-01
|  | Achieved |  | Yes
Source
MECS research program progress report and publications
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
5% | MECS principles incorporated into operational indicators for modern energy access under SDG7 | Planned | None | Stakeholder consultation and coordination: major global workshop (1, end yr. 1), workshop report (1, end yr. 1) | Draft framework for discussion and consensus building on the incorporation of MECS principles into the SDG 7.1 tracking system to complement the current binary indicator (1, end yr. 2) | MECS framework incorporated into operational indicators to complement the current SDG7.1binary indicator (1, end yr. 3) |  |  |  | 2021-09-01
|  | Achieved |  | Yes
|  |  | Source | [7 empty] | RISK RATING
|  |  | MECS research program progress report and SDG report | [7 empty] | Minor
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  |  |  | DFID SHARE (%)
| £0.9M |  |  | TBD
INPUTS (HR) | DFID (FTEs)
TBC
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date) | Assumption
Scaled-up Experimentations Relating the Transition Theory of Change (TToC) for MECS to planned programmes (Government, IDA, Large NGO) within which to trial MECS. 4b Leveraging investments from other MDBs to utilise emerging opportunities to increae the number and types of experiments at scale 4c Use Results Based Financing to test at scale 4d Accelerator funding to draw in 3-5 large modern energy cooking entities into the African and Asian markets 4e Seeding markets and finance to stimulte new finacing instruments | Technology, business, and policy innovation experiments designed and implemented in selected pilot countries | Planned | None | Internal opportunities report produced on how innovations fit the IDA pipeline (end yr 1) | Discussions held with IDA teams, and opportunities refined - updated opportunities report (end yr 2) | Pilot countries selected (6 + 2, end yr. 3) |  | Experiments implemented (3 + 2, end yr. 5) |  | 2023-09-01
|  | Achieved |  | Yes
Source
MECS research program progress report and publications
| Output Indicator 4.2 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date) | Assumption
| Monitoring and evaluation conducted and lessons drawn from experiments | Planned | None | (dependent on 4.1) | (dependent on 4.1) | M&E methodologies developed (1, end yr. 3) |  | Lessons learned from each experiment and synthesis report (3, end yr. 5) |  | 2023-09-01 | That the identified IDA programmes and other similar lending to be identified, can be suitably engaged such that they incorporate MECS experimentation on scaling into their programmes. That governments are convinced enough to approve large scale testing and experimentation on scaling. Risk that MECS solutions supported do not directly benefit the targeted population and improve the life of the poor (i.e. benefits are accrued to middle-income consumers, not the poorest).
Achieved
Source
MECS research program progress report and publications
| Output Indicator 4.3 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Operational models for scaling-up developed and priority countries engaged | Planned | None | (dependent on 4.1) | (dependent on 4.1) | Operational models developed (3, end yr. 3) |  | Discussions conducted with priority countries for scaling up (3, end yr. 5) |  | 2023-09-01
Achieved
Source
MECS research program progress report and publications
| Output Indicator 4b |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Leveraging investments from other MDBs to utilise emerging opportunities to increae the number and types of experiments at scale | Planned | None | None | Discussions held with other donors and opportunities refined - opportunities report (end yr 2) | (dependent on Yr2) |  | Lessons learned from each experiment and synthesis report (1, end yr. 5) |  | 2023-09-01
Achieved
Source
MECS research program progress report and publications
| Output Indicator 4c |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Use Results Based Financing to test at scale | Planned | None | None | Discussions held with RBF teams, and opportunities refined - updated opportunities report. (end yr 2) | (dependent on Yr2) |  | Lessons learned from each experiment and synthesis report (1, end yr. 5) |  | 2023-09-01
Achieved
|  | Source | [8 empty] | RISK RATING
|  |  | MECS research program progress report and publications | [7 empty] | Moderate
| Output Indicator 4d |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Accelerator funding to draw in 3-5 large modern energy cooking entities into the African and Asian markets | Planned | None | None | A strategy for engaging larger public and private entities with modern energy cooking services | (dependent on Yr2) |  | Lessons learned from each engagement and synthesis report (1, end yr. 5) |  | 2023-09-01
Achieved
Source
MECS research program progress report and publications
IMPACT WEIGHTING (%) | Output Indicator 4e |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
30% | Seeding markets and finance to stimulte new finacing instruments | Planned | None | None | Discussions held with social investment financiers - updated opportunities report. (end yr 2) | (dependent on Yr2) |  | Lessons learned from each instrument and synthesis report (1, end yr. 5) |  | 2023-09-01 | Assumptions
|  | Achieved | [8 empty] | Communication strategies and messaging are joined up and speak with one voice. GACC and ESMAP influence will enable all lead organisation representatives of the programme to access high level stakeholder meetings, SDG forums and decision boards. Communication products will utilise all media effective media sources -not just e-based. The stage gate reviews of 5.3 confirm forward strategy and these are budgeted for. In year 2 the coronavirus caused a global pandemic. March 2020, most face to face meetings are being cancelled, and air travel severely restricted. This will hamper the programme, especially stakeholder meetings - which are important for changing the narraticve and policy engagement. A key assumption for the programme is that by end 2020 the world reverts to normal working practice.
Source
MECS research program progress report and publications
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  |  |  | DFID SHARE (%)
| £3.6M + 8.5m |  |  | Access to Est.£240M IDA+ programming
INPUTS (HR) | DFID (FTEs)
TBC
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
Changing the narrative' Research Uptake, Knowledge disseminated, consultation conducted, stakeholders coordinated 5b Enhanced partnerships 5c Enhanced study on policy environments | Convening's, meetings, and workshops | Planned | None | Stakeholder meeting discussing MECS and SDG 7. (end yr 1) | Clean Cooking Forum 2019 MECS session (1, 18 mths) | Stakeholder meetings and workshops (6, yr. 3) |  | SDG7 meetings (6, yr. 5) |  | 2023-09-01
|  | Achieved |  | Yes | Yes
Source
MECS research program progress report and publications
| Output Indicator 5.2 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Communications and marketing materials/tools/media (brand, digital, storytelling) | Planned | None | Draft of major change of narrative report outlining MECS | Publication of the narrative report (end yr 2) | i) Clean cooking catalogue incorporating MECS principles (1, end yr. 3) and ii) Communication materials and tools (5, end yr. 3) |  | Dissemination of knowledge products (5, 2023) |  | 2023-09-01
|  | Achieved |  | Yes | Yes
Source
MECS research program progress report
| Output Indicator 5.b |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Enhanced partnerships | Planned | None | None | Significant engagement with key partners (3, end year 2) | Significant engagement with key partners (6 cumulative, end year 3) | Significant engagement with key partners (9 cumulative, end year 4) |  |  | 2023-09-01
Achieved
|  | Source | [8 empty] | RISK RATING
|  | MECS research program progress report | [8 empty] | Minor
| Output Indicator 5.c |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
| Policy environment studies | Planned | None | None | Responding to invited contributions to policy development (1, end yr 2) | Responding to invited contributions to policy development (cumulative 4, end yr 2) | Responding to invited contributions to policy development (cumulative 6, end yr 3) |  |  | 2023-09-01
Achieved
Source
MECS research program progress report
IMPACT WEIGHTING (%) | Output Indicator 5.3 |  | Baseline | Milestone 1, Yr1 | Milestone 2, Yr2 | Milestone 3,Yr3 | Milestone 4,Yr4 | Milestone 5,Yr5 | Milestone 6,Yr6 | Target (date)
10% | MECS research program monitoring, evaluation, and coordination | Planned | None | End of first year review (end 1 yr). MECS program M&E implementation framework developed and regular coordination mechanism established (1, yr. 1) | End of second year Review. MECS program M&E implementation framework developed and regular coordination mechanism ongoing (yr 2) | M&E framed review (stage gate - is TToC viable) (1, 30 mths) | M&E framed review (stage gate - Does WS4 need more time and further funding) (1, 54 mths) |  |  | 2023-09-01
|  | Achieved |  | Yes
Source
MECS research program progress report
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  | Total (£) |  |  |  | DFID SHARE (%)
| £1.6M + 2.7m |  |  | TBA
INPUTS (HR) | DFID (FTEs)
TBC
18.2

## Activities Log
|  | Proposed Lead Organization | Proposed Budget - LU | Proposed Budget- Alliance | Proposed Budget - ESMAP
OUTPUT 1 | ACTIVITY 1.1 | ESMAP |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Risks | Monitoring Officer
Understanding Transition Pathways to MECS. Improved knowledge on factors driving transitions to MECS | Systematic review of current knowledge on macro and micro factors driving transition pathways to MECS |  | 0 | 0
| ACTIVITY 1.2 | ESMAP |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| Case studies on key driving factors with cross-country data and evidence and on in-depth assessment across all key factors in selected countries |  | 0 | 0
| ACTIVITY 1.3 | ESMAP |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| Specific recommendations on policy interventions accelerate transition pathway and country-specific action plan. |  | 0 | 0
OUTPUT 2 | ACTIVITY 2.1 | LU |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Risks | Monitoring Officer
Technology and Business Innovation. Research conducted on socio-economic and technical innovations in MECS | Technology and business innovations experiments designed, lab tested and piloted in selected countries |  |  | 0
| ACTIVITY 2.2 | LU |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| Life cycle analysis and modelling undertaken for innovations |  |  | 0
| ACTIVITY 2.3 | LU |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| Consumer preferences studies relating to MECS innovations documented and evidenced |  |  | 0
| ACTIVITY 2.4 | LU |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| Innovation environment for priority countries mapped and engaged. |  |  | 0
| ACTIVITY 2.5 | LU |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| Innovation challenge funds applied for energy storage and energy efficiency. |  |  | 0
OUTPUT 3 | ACTIVITY 3.1 | ESMAP |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Risks | Monitoring Officer
Defining a Modern Energy Cooking Service. MECS framework defined, indicators developed, and measurement capacity improved | MECS conceptual framework defined with indicators and country examples |  | 0 | 0
| ACTIVITY 3.2 | ESMAP |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| Guideline, tools, and training conducted to mainstream MECS data collection |  | 0 | 0
| ACTIVITY 3.3 | ESMAP |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| MECS principles incorporated into operational indicators for modern energy access under SDG7 |  | 0 | 0
OUTPUT 4 | ACTIVITY 4.1 | ESMAP |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Risks | Monitoring Officer
Scaled-up Experimentations.Relating the Transition Theory of Change (TToC) for MECS to planned programmes (Government, IDA, Large NGO) within which to trial MECS. | Technology, business, and policy innovation experiments designed and implemented in selected pilot countries |  | 0 | 0
| ACTIVITY 4.2 | ESMAP |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| Monitoring and evaluation conducted and lessons drawn from experiments |  | 0 | 0
| ACTIVITY 4.3 | ESMAP |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| Operational models for scaling-up developed and priority countries engaged |  | 0 | 0
OUTPUT 5 | ACTIVITY 5.1 | LU |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 | Risks | Monitoring Officer
Changing the narrative' Research Uptake, Knowledge disseminated, consultation conducted, stakeholders coordinated | Convening's, meetings, and workshops |  | 0 | 0 | 0
| ACTIVITY 5.2 | LU |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| Communications and marketing materials/tools/media (brand, digital, storytelling) |  | 0 | 0 | 0
| ACTIVITY 5.3 | LU |  |  |  | Milestone 1 | Milestone 2 | Milestone 3 | Milestone 4 | Milestone 5 |  | Monitoring Officer
| MECS research program monitoring, evaluation, and coordination |  | 0
OUTPUT 6 | ACTIVITY 6.1
ACTIVITY 6.2
ACTIVITY 6.3