## Annual Review Template – from April 2020

Title: Strengthening Public Financial Management, Anti-Corruption and Accountability Institutions in Sierra Leone
Programme Value £ (full life): 22,200,000		Review date: September 2020
Programme Code: 300254	AMP start date: 28/09/2018	AMP end date: / 29/03/2024

Summary of Programme Performance
Year	2019	2020
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/39975011.odt
DevTracker Link to results framework:	http://iati.dfid.gov.uk/iati_documents/49041437.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The programme is designed to deliver a more effective executive that can raise, allocate and transparently use public resources to drive inclusive development and deliver services for the people of Sierra Leone. The programme will do this by providing strategic and technical assistance to Government institutions, including the Ministry of Finance, National Revenue Authority, Anti-Corruption Commission, Judiciary and Office of the Chief Minister, to support their reform efforts in relation to public financial management, revenue, anti-corruption and accountability. It will also support a range of civil society organisations (Christian Aid, the Budget Advocacy Network, Centre for Accountability and the Rule of Law, Restless Development, and Institute for Governance Reform under Phase 1) to hold the government to account and gather data against which to independently assess progress.

The programme was approved for an initial 18-month Phase 1 (September 2018 – March 2020; total budget £3.5m). Following a successful first year of delivery, demonstrated by an A in the 2019 Annual Review, Phase 2 of the programme was approved by Ministers in October 2020. In December 2020 a Business Case Addendum was undertaken in order to extend the end date and value of the programme to allow time to procure a Phase 2 supplier and deliver a smooth transition between the two phases.

Summary supporting narrative for the overall score in this review

The programme has met expectations, achieving a significant amount in the last 12 months and with some early indications that project activities are feeding through into outcome level results. In the past year substantial progress has been made on strengthening public financial management, through improving the integrity and oversight of the payroll, strengthening fiscal risk management, and improving the comprehensiveness of the budget and civil society oversight of this. Although revenue mobilisation has been negatively impacted by Covid-19, Phase 1 laid the foundations for reform progress around taxpayer engagement and strengthening tax compliance. Initiatives started by the TA have been reflected in the National Revenue Authority’s Covid-19 Business Recovery Plan and Phase 2 will continue to drive these forwards working closely with the Invest Salone programme, a partnership that was initiated under Phase 1. Under the anti-corruption workstream, the past year has seen the establishment of the anti-corruption court, which has now completed 17 cases, alongside strong progress in strengthening the administrative systems that underpin this. With support from the project, compliance with new asset declaration legislation has increased from 8% in January 2020 to 70% in June 2020. This is an important foundation to identify whether officials and political leaders are benefiting unduly for their time in office.

Major lessons and recommendations for the year ahead

- The flexibility and responsiveness of the TA aspects of the programme to GoSL priorities, and the strong relationships advisers have built with senior management teams, has enabled TA to participate in and influence management discussions. Whilst not easily measurable, this has ensured that the TA’s work has top level buy-in making it easier to secure the day to day engagement required from other Government staff.
- The balance between TA and complementary support needs to be kept under close review during Phase 2.
- Given the impacts of Covid-19 and constantly evolving political economy dynamics, the theory of change and logframe need to be reviewed going in to phase 2 to ensure these accurately capture key assumptions and better reflect the results that will be achieved under the programme, including during Phase 2 inception.
- The lack of a comprehensive VFM framework or a unified results framework across the programme makes it difficult to systematically track value for money or monitor how the different workstrands complement each other (and other aspects of the DFID SL portfolio) and map on to outcome level results. As these are developed in Phase 2 the focus should be on creating tools and mechanisms that intelligently capture relevant data, without creating a disproportionate reporting burden. We will begin working on strengthening the VFM narrative and more comprehensively reviewing the VFM of Phase 1 over the next 4-6 months.
- A redoubling of effort is needed to support stronger donor collaboration, especially in light of Covid-19 impacts and staff changes across institutions, which has led to all donor programming being adapted and, in some cases, key channels of communication being disrupted.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change set out in the Business Case argues that by providing:
- Mentoring to senior/technical leaders on PFM, anti-corruption and accountability reforms
- Ongoing institutional and political economy analysis to guide implementation
- Capability building of PFM institutions in revenue, payroll, procurement and budget credibility
- Capability building of a ‘basket’ of oversight institutions (e.g. Anti-Corruption Commission, Civil Society, Parliament, Audit Service), providing internal checks to the system against corruption
This will lead to:
- Improved revenue generation
- Public expenditure management systems strengthened
- Oversight and anti-corruption institutions strengthened in their abilities to deliver
Taken together, this will lead to a more effective executive that can raise, allocate and transparently use public resources to drive inclusive development, as indicated by:
- Agreement reached with IMF and a credible ECF programme is in place.
- Improved fiscal position of the Government of Sierra Leone.
- Actions taken on petty and grand corruption are increasingly effective.
- Views of ordinary Sierra Leoneans including women, vulnerable and excluded groups are represented in the way PFM, anti-corruption and accountability systems operate.
This remains the theory of change guiding the programme. The major negative external shock from Covid-19 has led to the IMF ECF programme being paused and replaced by Rapid Credit Facility arrangements and a deterioration in the Government’s fiscal position. However, at the current time it is expected that over the life of the programme the success indicators remain valid, albeit against an altered counterfactual that considers the macro-fiscal impacts of Covid-19. Government commitment to reform across the three focal areas remains in place, as tracked through our commitment matrix (Outcome Indicator 1.5). There have been no changes to outcome and impact indicators since the last Annual Review, which details changes since the Business Case.

As part of the inception phase for Phase II of the programme, we will review the theory of change and revise the logframe to ensure they better capture the results and influence intended to be delivered under the programme. This will include strengthening the links between this programme and the rest of DFID Sierra Leone’s portfolio. Phase II will increase the links between revenue generation work and efforts to create an enabling environment for private sector growth. It will also place an increased focus on public financial management reforms and anti-corruption work with direct links to service delivery (esp. health and education), for example through working on teacher workforce issues or supporting the systems for drugs procurement.

A Business Case Addendum in December 2019, increasing the programme value by £7m and extending the end date from September 2023 to March 2024 will strengthen the value for money of the programme by delivering improvements in efficiency and effectiveness through:
- Delivering additional output-level results and activities that will increase the level and likelihood of achieving outcome-level results.
- Creating greater complementarity with other DFID interventions, as noted above, improving results delivery across the portfolio.
- Strengthening the overlap between technical assistance to improve government capacity and civil society / parliamentary oversight, for example through the work on audit. In Phase II VFM will be enhanced by consolidating support under one contract This will increase complementarity between the two workstreams, something that has been found to work well in Phase I. This will also streamline management structures, reducing overhead costs and freeing up DFID staff time for policy engagement and influencing.
- Improving the quality of design of the World Bank’s future programme, and strengthening its value for money, through exploring potential partnerships through an externally funded output. This work has been delayed slightly due to the impacts of Covid-19, which have impacted both the timing of the UK’s Phase 2 and the Bank’s programme design. We will use the next few months to work closely with the Bank to revisit what a future partnership might look like.
The programme is highly adaptive, has responded well to new opportunities and stepped back from areas where we struggled to gain traction. Close engagement of DFID staff with the Government and CSO partners has helped to assess Government commitment and the reform space and respond to opportunities to influence the Government. For example, following Head of Office conversations with the Minister of Finance we have provided him with a special adviser, who has played an instrumental role in establishing the governance structures around the Covid-19 economic response. Phase 2 will retain this adaptive nature.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on-track against the majority of outcome and impact level indicators. There are 3 indicators where the programme is off-track. Two of these (IMF programme and revenue target) are off-course due to the macro-fiscal impacts of Covid-19 and disruptions due to mitigation measures, such as border closures and lockdowns. There is a high degree of uncertainty around the economic and fiscal impacts of the crisis, and future targets will need to be reviewed as part of Phase 2 inception to take account of this. We will continue to work with the Government and the IMF to ensure Sierra Leone remains in good standing with the Fund and is in a position to resume a programme at an appropriate point in time, and will look to work alongside the Fund and the Government to deliver against revised revenue targets. During Phase 2 inception, we will also review the focal areas to ensure the programme is targeting the most critical areas to deliver the outcomes and impacts, recognising the changed external context.

Although the Government is still displaying a moderately high degree of commitment to strengthening public financial management, revenue generation and anti-corruption there are some areas where progress has been relatively weak. These include: establishment of comprehensive governance structures around PFM reform, including effective monitoring mechanisms; procurement reporting by MDAs; comprehensiveness and publication of budget documentation, including information on enacted budgets and actual expenditure; and external audit follow-up. We will work alongside the European Union and other donors to strengthen PFM reform governance, focusing on dialogue and coordination mechanisms and a sequenced and prioritised approach to PFM reform, with effective oversight mechanisms. This will be a priority during Phase 2 inception.

Impact Indicator		Target		Achievement
1	GoSL is on track with an approved IMF programme.	March 2020	Second review successfully concluded.	On track. The Second Review was approved by the board on 17th April.
		Sept. 2020	Third review successfully concluded [subject to resumption of ECF - this has been temporarily put on hold given the macro-fiscal shocks relating to Covid-19]	Off track (due to C19). The ECF programme has been paused given the impacts of C19 on the macro-fiscal framework. Sierra Leone received an RCF disbursement in May 2020 and remains in good standing with the IMF.
2	Improved public perception of corruption	March 2020	Improvement	On track. 33/100 (2019) [Compared to 30/100 Baseline]
		Sept. 2020	-	-
Outcome Indicator		Target		Achievement
1.1	Revenue as a % of non-iron ore GDP	March 2020	-	-
		Sept. 2020	15 [to be updated in line with latest IMF targets]	Off track (due to C19): 13% [The estimate for the year of 13% given in the supplementary budget is in line with forecasts in the IMF RCF documentation, Jan-Jun collection was 6.4% of non-iron ore GDP]
1.2	PEFA, TADAT and Open Budget Index reports [exact timings TBD].	March 2020	Open Budget Index Score for 2019 (expected Jan) higher than 38/100	On track. 39/100
		Sept. 2020	No target for this period. Next PEFA due in 2021. TADAT timings TBD.	-
1.3	Implementation of the PFM Reform Strategy	March 2020	N/A - no further annual reporting expected since last milestone	-
		Sept. 2020	By end-June: Revised PFM reform strategy implementation plan in place, including monitoring mechanisms.	Off track. Strategy revision has not been fully rolled out. Monitoring mechanisms are not functioning.
1.4	Number of grand corruption cases investigated, and prosecuted by Anti-Corruption Commission, and adjudicated by the Anti-Corruption Court to completion.	March 2020	4	On track. Of the 43 cases inherited by the ACD in December 2019 upon its operationalisation, two (2) cases have been completed and rulings delivered in three (3).
		Sept. 2020	6	Exceeded. 5 additional cases were completed between March and June 2020, making 10 completed cases in total.
1.5	% of Commitment Matrix achieved	March 2020	70%, including 50% of the High Priority actions	On track. 46% RAG rated green and 42% amber. Of the high priority actions 75% are green.
		Sept. 2020	70%, including 50% of the High Priority actions	On track. 50% RAG rated green and 42% amber. Of the high priority actions 67% are green.
[note] Amber ratings were given where the Government has taken positive steps towards completing the action but where timelines have slipped slightly, meaning actions are likely to be achieved in the near future.

The Business Case set out key measures to assess the effectiveness / value of the programme:
- Improvements in revenue. In 2019 domestic revenue was 14.4% of non-iron ore GDP. Above the IMF target and up from 13.8% in 2018. In 2020 revenue was projected at 15.6% of GDP, however this has been revised down to 13% to take into account the impacts of Covid-19, which has led to the NRA agreeing deferrals of tax payments in an effort to support the private sector.
- Public Expenditure Management, specifically, improvements in the Open Budget Index score, percent of unqualified audit reports and procurement compliance scores. There has been a slight improvement in the Open Budget Index score and the Ministry of Finance has prioritised improving this further. In Phase I DFID has not provided support on audit or procurement.
- Increase in savings and payroll cleaning. During 2020 it is estimated that the project delivered £40,000 in payroll savings through removing dual assignment workers and a saving of £52,000 through identifying leave allowances incorrectly paid to employees on study leave. In addition, all of the 83,000 active workers on the payroll in 2020 have been biometrically verified against their NCRA records, except members of the political class. The value of the suspense account at NASSIT has reduced from Le16bn in 2019 to Le15bn in 2020, with the addition of university workers with high values of unreconciled records into the payroll offsetting some of the broader improvements.
- Increase in the number of recovered stolen assets from successful corruption cases, and a reduction in money stolen. As reported in section C, recovery of funds is expected to be slightly lower in 2020 than in 2019, due to a reduction in the backlog of historical cases. As of July 2020, £0.3m had been recovered, compared to approx. £0.9m in 2019 and £0.7m in 2018.

These value for money indicators will be reviewed as part of the development of a comprehensive value for money framework during Phase 2 inception. One area that needs to be better captured is the role the programme plays in developing our relationships with senior officials and Ministers in the key institutions, which has positive spill-over effects into our engagement on broader policy dialogues.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme is delivering against output targets and there is evidence of this feeding through into outcomes and impact. Efforts to restructure the programme as we move into Phase 2, changing the delivery model to bring together TA and CSO work under one supplier and strengthening linkages with the broader DFID Sierra Leone (and HMG) portfolio, will improve value for money. The programme is an important part of delivering the x-HMG strategy in Sierra Leone and supporting the longer-term sustainability of our investments in human capital development and greater economic stability.

## C. DETAILED OUTPUT SCORING

Output Title	Strategic and technical assistance that successfully supports and influences strategic direction of Government reforms, builds GoSL capability and supports delivery of key reforms.
Output number:		1	Output Score:	A
Impact weighting (%):		60%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 # Advisers reporting to GoSL and mutually agreed to be performing satisfactorily at break point	March 2020: 5 (minimum) / June 2020: 6 (minimum). Sept 2020: 1 (minimum)	Met. / March 2020: 7 / June 2020: 7 / Sept 2020: 5
1.2 % Advisers' workplans with concrete deliverables (including on capacity building) agreed within 6 weeks of mobilisation	March 2020: 80% / September 2020: 100% of advisers starting after March 2020 (or following contract extension beyond June 2020)	Not Met. / March 2020: 57% (although all advisers had workplans in place, only 4 out of the 7 work plans were in place within 6 weeks of mobilisation) / September 2020: 80% (it took longer than 6 weeks to secure an agreed workplan for the adviser starting in April 2020, however following the contract amendment in June 2020, all four updated work plans were submitted within 6 weeks)
1.3 % workplans delivered on schedule and with clear evidence of GoSL engagement / buy-in	March 2020: 80% / June 2020: 80%. / Sept 2020: 80%	Met. / March 2020: 86% / June 2020: 82% / Sept 2020: 85%

Briefly describe the output’s activities and provide supporting narrative for the score.

Strong progress has been made under all three thematic areas, and the output has therefore scored an A.

Public Financial Management

Activities under the PFM work stream have focused on strengthening the delivery of the PFM Reform Strategy and increasing the credibility and robustness of the budget process, including through improved payroll management. These areas are critical to improve public expenditure management and the efficient and effective utilisation of scarce resources. Measures to strengthen controls over expenditure have become even more important in the context of Covid-19, which has placed increased pressure on the Government’s fiscal position.

During the past year the project has had a heavy focus on improving the integrity of the payroll and increasing control over the public sector wage bill. In 2019 the payroll was around 48% of domestic revenue, equivalent to 6.9% of GDP, above the IMF target of 6%. This has increased in 2020 to 62% of domestic revenue or 8.1% of GDP in part reflecting the Covid-19 impacts on GDP and revenue, but also increases in the number of public sector workers and pay rises for certain groups. Under the project significant progress has been made in cleaning the payroll, ensuring integration with national insurance and national identification systems, and strengthening oversight and administration. For example:
- support to the National Civil Registration Agency (NCRA) payroll verification process resulted in the removal of 2,990 employees from the payroll – it is expected that about 50% of these employees are not in service. Monthly efficiency savings are expected to be between 2.5 billion – 3.5 billion Leones.
- support for data cleaning means over 99% of employees in the payroll system have a valid national insurance number, only 173 employees have an invalid social security number, and only 200 employees have bank account numbers not in the format specified by the Bank of Sierra Leone.
- the project identified 17,000 employees with incorrect DOBs, which has implications for the calculation of retirement benefits. 12,500 have been corrected and the remaining 4,500 will be corrected by the end of September 2020.
- the project has developed dashboards for the MoF internal audit department and Accountant General Department (AGD) payroll supervisors to monitor payroll integrity. These tools have already prevented petty corruption. For example, the AGD detected 21 teachers who left employment in January and February but continued to receive their salaries till May 2020. Around £7.5k was recovered from these employees.
- the project has supported reconciliation of employee contributions between Payroll and NASSIT systems, resulting in unreconciled records in 2020 averaging just 5,000 per month compared to an average of 32,000 per month in 2019.
- Strategic advisors worked closely with the Deputy Director Budget Bureau in developing a payroll report, analysing payroll costs for 2019 and 2020 and highlighting payroll related issues. The report was presented to the Economic Management Team (EMT), chaired by the President, and informed further meetings with the Financial Secretary to address payroll related matters. As a follow-up, the project developed a teacher recruitment and retirement policy to strengthen teacher workforce management, critical in the delivery of the Government’s flagship Free Quality School Education programme. We will continue to strengthen collaboration with Leh wi Lern on teacher workforce management.
- A payroll policy document has been developed to serve as a guide for those administering the GOSL payroll on daily basis.
In addition to strengthening payroll integrity, proper workforce planning is needed to control the wage bill, ensure human resources are well allocated, and support budget credibility through the avoidance of unplanned recruitments. The Government of Sierra Leone employs over 81,000 workers. Currently over 11,000 workers do not have their positions correctly recorded in the payroll. The project has begun strengthening data to support workforce planning, including by preparing workforce plans for the police and correctional services.

The project has also provided support to strengthen budget preparation, credibility, oversight and reporting. Key achievements include:
- Supporting the preparation of the 2020 Budget, including chart of account reforms, and preparing the enacted budget documentation for publication on the MoF website.
- Preparing consolidated FY18 public accounts (financial statements) for central government to include subvented agencies, as required by Section 89 of the PFM Act 2016. This was the first time consolidated public accounts were compiled.
- Assisting the AGD financial reporting team to prepare public debt data and analysis (domestic debt in particular) for the FY19 unaudited General Purpose Financial Statements (GPFS) of the Consolidated Fund.
- Supporting the Fiscal Risk Division by preparing a financial analysis reports for eight TSA Agencies and sixteen state owned enterprises (SOEs), for the period 2015-2018. The report on SOEs was presented by the Minister in the Presidential Seminar for Commissions/Parastatals/Agencies and SOEs (25th February 2020). The report findings have been used as a basis for discussion between the Minister of Finance and these entities on reforms to support solvency. Estimated SOE liabilities at the end of 2018, amounted to approximately Le 1.5 trillion (approx. £115m). The project has also provided support to strengthen the Ministry’s oversight of the state-owned banks.
Preparation of a Financial Procedures Manual for the Ministry of Health and Sanitation (MOHS) aimed at helping the MOHS staff and others understand the PFM systems, processes and procedures for managing public funds. Once finalised, it is expected to be replicated in other Ministries, Departments and Agencies (MDAs) to ensure compliance with Regulation 223 of the PFM Regulations 2018.
The project has worked to strengthen governance and coordination of PFM reforms through support to the PFM reform unit to review progress against the PFM reform strategy (2018 – 2021) and undertake preparatory actions for the planned PEFA 2021 and the new PFM Reform Strategy. A PFM retreat in February created new momentum around PFM reform monitoring and governance, however this was to some extent lost due to the onset of Covid-19 and related disruptions. This agenda will be picked up again under Phase 2.

Revenue Generation

Project activities undertaken in collaboration with the NRA have focussed on strengthening the strategic and operational reform process in the NRA. In the past year, particular areas of focus have been enhancing compliance and broadening two-way dialogue and engagement between the NRA and taxpayers.

Key achievements this year include:
- Development of a roadmap to pilot a block management system (BMS) to increase the tax base and promote compliance. The impacts of this pilot reform will be evaluated by the International Centre for Taxation and Development.
- Building NRA capacity around taxpayer education and communication. Following a functional review, a proposal has been developed for restructuring the taxpayer services and public affairs unit, outlining roles, responsibilities and staffing requirements. Key policies have been developed including: a communication strategy; guidelines for taxpayer engagement sessions; and a Taxpayers’ Charter outlining the rights and obligations of taxpayers and service delivery standards. The NRA Call Centre has been reactivated and two staff members appointed, with approval for the appointment of a further two staff members. Support was provided to organise 5 stakeholder engagements, targeting medium taxpayers, and 4 district level taxpayer sensitisation sessions.
- Project support to develop NRA Business Continuity and Business Recovery Plans around Covid-19. These plans institutionalise some of the key project reforms (e.g. the BMS) and support the adaptation of taxpayer education and communication initiatives in light of Covid-19. Strategic advisors have also developed a proposal for a simplified tax regime for SMEs as part of Business Recovery Plans.
- Supporting the NRA’s transition towards being a data led organisation. The advisers have provided continuous support to the Integrated Tax Administration System (ITAS) and Electronic Cash Register (ECR) reform processes. The project helped to clean 4000 taxpayer records for importation into ITAS and worked with the NCRA and AGD to prepare data of over 90,000 public sector employees for the ITAS system to support PAYE filing. A PAYE database was prepared to support compliance monitoring. This identified substantial challenges with data quality, which will be addressed in Phase 2. The project has also begun training the NRA data analytics team in data warehousing and analytics, which will be crucial for the NRA’s ability to draw insights from data provided by the new systems (ITAS, ASYCUDA World and the ECRs).
- Support for a review of NRA ICT assets (network, systems, applications) and current ICT security and support processes to identify risks and vulnerabilities (including internal and external threats) that might compromise NRA operations. The cyber security agenda will be picked up in Phase 2 in coordination with other development partners.
Anti-Corruption

The anti-corruption component is on target to meet its objective of a better functioning court and an Anti-Corruption Commission that is showing results in the fight against corruption. Project activities in the past year have been focussed on strengthening and institutionalising the institutional processes and systems of both the Anti-Corruption Commission and the Judiciary to increase the number of grand corruption cases that are investigated, prosecuted and completed and improve the public perception of government’s ability to fight corruption. Overall, 13 anti-corruption cases have been completed in 2020 compared to 4 in 2019. The value of assets recovered January – July 2020 was £0.3m, compared to £0.9m in 2019 and £0.7m in 2018. We expect asset recovery to increase in the second half of 2020, however it may remain below 2018 and 2019 levels given 2018 and 2019 saw a backlog of historical cases being reviewed.

Key achievements this year include:
- The establishment and launch of the Anti-Corruption Court / Anti-Corruption Division of the High Court (ACD) in December 2019. Five Judges were assigned to the adjudication of anti-corruption cases – two full-time High Court judges and three part-time judges (two Court of Appeal and one High Court Judges).
- A case file audit conducted by the TAs in October 2019 enabled reconciliation of the ACC and the judiciary case data. The subsequent recommendations informed administrative reforms at the ACD court.
- Capacity building of court administrative staff through support to recruitment processes, training, and facilitation of on-the-job learning.
- To strengthen records and case management at the judiciary, the TAs supported the introduction of administrative processes to ensure adherence to due process in case storage, court scheduling, fine/restitution payments, case research, internal case transfer and file movements.
- Support to business continuity plans, to enable court proceedings to continue safely despite the Covid-19 pandemic.
- Support to the National Anti-Corruption Strategy Secretariat (NACS) in its engagement with Ministries and Councils and the monitoring of Integrity Management Committee (IMC) programmes. IMCs play a key role in MDA’s role of combatting corruption within their mandated areas. At the request of the ACC Commissioner, the strategic advisors conducted an organisational audit to improve the effectiveness and efficiency of the NACS to coordinate the implementation of the National Anti-Corruption Strategy. The findings and implementation roadmap have been presented to the Commissioner for subsequent action.
- The project has strengthened planning, core-operational and M&E systems in the Anti-Corruption Commission (ACC). The new MEAL system has enabled the institution to perform integrated planning by aligning both strategic, departmental and individual staff plans and creating management information dashboards. The process of preparing and monitoring ACC departmental quarterly plans has been institutionalised. In the quarter April – June 70%-80% of all targets were completed on schedule. Staff performance management systems are now in place, including individual performance objectives. Project support to strengthen the IT system provided the institution with a platform for improving communication and increased administrative efficiency.
- Standard operating procedures (SOPs) have been developed for the Intelligence and Investigations and the Prosecution Departments of the ACC.
- The project has built the capacity of the ACC Asset Declaration Unit, resulting in increased compliance rates from 8% in January 2020 to 70% by June 2020.
Other workstreams
- The project supported the Office of the Chief Minister in conducting a study to determine the viability of a Presidential Executive Office (PEO) under the Office of the President to advice on issues and help the President focus on priorities while coordinating others to deliver effectively.
- Short term support was provided to the Directorate for Service Delivery and Performance Management in the Office of the Chief Minister. The project team recommended strengthening the service delivery mandate of the directorate and measures to enhance the performance management system, including Ministerial performance contracts.
- The project has provided a special adviser to the Minister of Finance to support him in the delivery of key reforms to promote broader macro-fiscal stability. The Adviser started work in April 2020 and was quickly brought in to support the Quick Action Economic Response Programme (QAERP) Secretariat that coordinates the government’s economic response to the Covid-19 pandemic. The QAERP Secretariat, with support from the special advisor has been collaborating with DFID’s Invest Salone programme on establishing a Private Sector Platform (PSP) that facilitates dialogue between the private sector and the government and undertaking a deep dive into challenges at the Freetown Port. The special adviser has also provided technical advice on key QAERP workstrands including: commodity price and stock monitoring and creating a credit facility for micro, small and medium enterprises (MSMEs).
- Audit of the Bank of Sierra Leone’s annual accounts by an international audit firm was a requirement by the IMF for them to proceed with disbursements under the ECF. DFID have supported this audit for the FY18 accounts, noting that under Sierra Leonean legal provisions the BSL audit had to be conducted by a local audit firm. BDO Germany and BDO Sierra Leone have worked in partnership on this.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Overall, the output has delivered good VFM and met VFM expectations set out in the Business Case.

Economy (cost and quality of inputs): The major cost under this output is personnel costs for the TA (74% of costs under the OPM contract). For the OPM contract, fee rates have been negotiated downwards for 60% of consultants from the maximum rate provided for under the DFID framework agreement. The average discount applied was 19%. Where possible we have used Sierra Leonean nationals, rather than more expensive international Advisers (30% of Advisory positions were filled by Sierra Leoneans). All of the live contracts under the output have been sourced through competitive procurement processes. Partners are required to ensure VFM in procurement and expenses. This is something we have challenged them on in their budgets and forecasts and are satisfied with their performance.

Efficiency (Productivity): Investments by DFID advisers to build relationships with Government institutions and key stakeholders have helped to ensure Advisers are able to integrate quickly. Ensuring we involve partner institutions in identifying their preferred Advisory candidates from a rage of CVs has also helped to develop ownership of the support. Where possible, Advisers have been selected who already have strong working relationships. This focus on relationships and ownership should be carried forward into Phase II.

Equity: Although there is limited direct link to equity under this output, project advisers are required to be gender-blind in their approach to engagement within MDAs, engaging equally with male and female colleagues.

A full VFM framework, including VFM metrics, will be worked up during Phase 2 inception.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The logframe has been updated twice in the past year, reflecting two major programme adaptations. Following the 2019 Annual Review, approval was sought and granted for Phase 2. Phase 1 was therefore extended from March 2020 to June 2020 to enable sufficient time to complete the Phase 2 procurement. The OPM contract amendment was completed in January 2020 and the logframe was updated in March 2020 to reflect this. The next logframe update took place in June 2020, alongside a further no-cost amendment moving money between expenses and fees. Covid-19 resulted in delays to the Phase 2 procurement. In response key TA positions (those working on PFM and anti-corruption) were extended from June 2020 to September 2020, and then again until March 2021, given the important support the TA were providing in helping the Government to manage expenditure in the context of a deteriorating macro-fiscal environment and ensuring the integrity of the fledgling anti-corruption court.

The logframe will be reviewed alongside the theory of change and programme workplan as part of Phase 2 inception. A monitoring and learning strategy will also be developed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Planning for Phase 2 has taken on board the lessons from the last Annual Review, and from Phase 1 more broadly.
- Procurement timelines have been challenged for realism, with substantial engagement with DFID’s Procurement and Commercial Department. Suppliers were required to demonstrate their ability to mobilise quickly in their bids.
- During Phase 2 inception, a focus will be put on finessing the monitoring and results frameworks to ensure these strike an appropriate balance between delivering reforms and building capacity, recognising that helping to facilitate others to achieve does more to build capacity and ownership but is less quantifiable and attributable.
- As in Phase 1, Phase 2 includes space for complementary inputs, for example critical equipment or event funding, to support technical assistants to deliver.
- There are a number of workstreams, which have been identified as priority areas to scope under phase 2, where work was not begun in phase 1 due to the short duration and the need to allow sufficient time for advisers to build relationships and support complex reforms over a longer time horizon.
The 2019 Annual Review highlighted the need to lobby for the appointment of the Anti-Corruption Advisory Board, as stipulated in the Anti-Corruption Act. Although the Board has still not been fully constituted, the ACC can fulfil its mandate without this Board in place and the return to lobbying efforts is likely to be low. It is therefore recommended that this isn’t prioritised in engagement as we move into Phase 2.

Key lessons identified this year:
- There are still silos between and within MDAs, which mean that sharing data and working collaboratively across institutions does not come automatically. During Phase 2, the project team will need to work hard to bridge these gaps at a technical and senior managerial level (for example in supporting the sharing of revenue data for tax policy analysis). This will be achieved in part by placing TA within downstream MDAs to act as counterparts to central reform efforts.
- In the absence of its own rules, the Anti-Corruption Court is currently managed under the hospice of the 1965 Criminal Procedure Act. This is proving to be problematic as the provisions do not adequately cover the complexities associated with anti-corruption adjudication. Phase 2 should engage with the Judiciary to develop ACD rules to enable the court to function effectively and independently.
- The Commissioner General of the NRA, in addition to officials in the ACC and MoF, has repeatedly flagged the need to keep under review the balance between technical assistance and support for complementary inputs (such as physical infrastructure and ICT hardware and software). There are challenges in taking forwards recommendations of donor TA (including that provided by other donors) due to these resourcing constraints. During phase 2 we will need to keep under review the key reform objectives and the appropriate balance of support to deliver these.
- The Phase 2 terms of reference outline priority areas for immediate engagement, which will build on work done under Phase 1, in addition a number of suggested intervention areas have been developed in partnership with Government which will be explored further, alongside emerging opportunities, during the Phase 2 inception.
Lessons identified in the 2019 annual review around the need to engage with Government and coordinate with other donors on wider public sector reform efforts, recognising challenges around staff incentives and performance management, remain valid.

Output Title	Civil society and accountability organisations supported to hold executive to account, including through generating critical data.
Output number:		2	Output Score:	A
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Availability and use (by GoSL and civil society) of data on citizens' understanding of the cost of corruption, perceptions of corruption, and on sector-specific corruption.	March 2020: Data used by GoSL and CSOs to inform future citizen engagement work. District level engagements continue. / September 2020: At least 2 TV and radio dissemination campaigns, at national and district levels done.	March 2020: Met. Two studies complete and report handed over to ACC which is leading the dissemination and citizens engagement with support from the consortium. / September 2020: Met. 2 TV broadcasts took place, with discussions led by the ACC, as well as nationwide radio broadcasts and an outreach campaign via text messages to 450,000 mobile network subscribers.
2.2 Availability and use (by NRA and other stakeholders) of data on taxpayer knowledge, attitudes and practices.	March 2020: KAP survey findings (incl. recommendations) disseminated to GoSL (NRA, MoF, state house) and development partners	Met (survey completed and report launched/ disseminated to GoSL and development partners)
2.3 # of informed dialogues on budget credibility and reach of public information products; availability and use of information from public expenditure tracking exercises in education, health and agriculture.	March 2020: 2 - based on robust analysis of FY19 full year outturn. Dissemination dialogues on all three PETS conducted. Evidence of Gov't and CSO follow up. / June 2020: By June 2020, evidence of at least 1 government action taken to respond to audit follow-up work. / September 2020: At least 15 multi-media (print, social and electronics) engagements with the public on revenue, the utilization of CoVID-19 resources, or other related information. / At least 2 reviewed statements of income, expenditure, procurement processes/procedures produced and shared with government focused on C19 response. / At least 3 revenue generation analysis updates produced. At least 6 media engagements held to update citizens on impact of Covid-19 on domestic revenue generation. / Evidence of Gov't and CSO follow up on PETS.	March 2020: Not met. Delays were experienced in finalising both the PETS and the budget credibility reports. / June 2020: Met. / Ministry of Finance developed and published actions plans to ensure implementation of the audit recommendations. Audit recommendations included in the ministerial performance contract (But information not made public). / September 2020: Met. / 23 radio engagements and 5 TV engagements completed. / One income and expenditure statement analysis done for COVID-19 and one on track to be completed by end-Sept. / One revenue analysis done and another one in the draft stage, which will be completed in September 2020. / PETS recommendations adopted by the Cabinet.
2.4 # of government actions to strengthen the transparency and legitimacy of duty waivers attributable to consortium influencing	March 2020: 2 substantive actions taken by government. / June 2020: 2 substantive actions taken by government (cumulative)	Met. The Government delayed the process for finalising the duty and waivers policy to allow time for adequate consultation and recommendations made by the CSO consortium have led to changes within the policy.
2.5 Availability of information to support C19 response procurement compliance to prevent fraud and corruption	September 2020: A copy of simplified laws relating to financial management transparency in emergencies produced and shared with NEOC. / Minutes of ACC Task Force deliberations indicate measures to address fraud in the Covid-19 response. / At least 4 media engagements to inform citizens on simplified financial management/procurement laws.	Partially met. / The simplified laws are in draft form and will be finalised in September 2020. / Although minutes from the ACC Task Force have not been shared, the Task Force has been monitoring the response, including at district level, and has identified instances of due process not being followed in recruitment, procurement and records management. Recommendations have been made to address this. / As the simplified laws have not been finalised no media engagement has taken place on these.

Briefly describe the output’s activities and provide supporting narrative for the score.

This year the CSO consortium, comprising Christian Aid, the Budget Advocacy Network (BAN), the Centre for Accountability and Rule of Law (CARL) and Restless Development, has focused on the production of a few flagship research / advocacy products, which have been used as a basis for influencing and awareness raising. Progress against key workstreams is outlined below. In April / May the activity plan was adapted to focus on oversight of the Covid-19 response and to avoid large events, which would not be compatible with social distancing.

A public expenditure tracking survey covering education, health and agriculture was co-financed with the Government and undertaken by a Sierra Leonean CSO, the Institute for Governance Reform (IGR). The recommendations from the PETS were adopted by the Cabinet in July 2020 and it was agreed that follow-up on these recommendations would form part of the performance contracts of the relevant MDAs.

The output is on-track to hit targets to be delivered by the end of the Phase-1 agreement and has therefore scored an A.

CSO Consortium achievements against key workstreams

Improving revenue generation
- Tax perception survey: This aimed to increase understanding of the factors influencing tax compliance to support actions to strengthen this over time. The survey of 2,755 businesses was produced in close collaboration with the National Revenue Authority’s Research Department and disseminated at national, regional and district level. The collaborative approach led to substantial take up of the recommendations by the NRA at a central and district level, informing their taxpayer education and services offer. The private sector also committed to actions to address identified knowledge gaps, for example in Tonkolili and Bombali the Traders’ Union is working with NRA to train its members on how to complete tax returns.
- Exemptions and waivers policy: Tax exemptions are a major source of revenue loss in Sierra Leone and are often granted through non-transparent processes and with little development rationale. On taking power in March 2018, the President’s first executive order abolished all exemptions and waivers and the Government committed to preparing a policy around their use. The consortium prepared a position paper, highlighting key issues which the new policy should address, and have been engaging with the Ministry of Finance and IMF since. The Ministry of Finance have taken on board recommendations from the consortium, although further work is needed to ensure the policy provides a clear, predictable and development friendly tax environment.
Strengthening public expenditure management systems
- Audit scorecards: Audit scorecards were produced as a simple way to communicate follow-up actions to the public for four MDAs (education, health, agriculture and the National Revenue Authority). These were used to influence the government to establish processes to support follow-up. As a result, the MoF required all MDAs to submit plans on how they will implement the audit recommendations and audit follow-up has been included as a performance measure in vote controllers’ contracts (although these have not been published). At least four Ministries have submitted plans for implementing recommendations from the auditor general’s report. These include Agriculture, Fisheries and Marine Resources, Lands, and Education.
- Budget credibility analysis: Weak budget credibility is a major challenge in Sierra Leone. The consortium has produced reports looking at FY19 outturn and the impacts of Covid-19 on the 2020 budget (highlighting revenue and expenditure impacts) and used these for dialogue with parliament and citizens on budget performance.
- Policy influencing: The consortium has effectively responded to emerging issues. For example, BAN engaged the Minister of Information, media and other CSOs to advocate successfully against the proposed Covid-19 Fund constitutional instrument, which exempted the Fund from the PFM Act and the Public Procurement Act.
- Building networks: The first budget credibility report was presented to various parliamentary committees, which resulted in the transparency and accountability committee of parliament requesting a memorandum of understanding (MOU) with BAN for continued engagement. BAN has also signed an MOU with the research department in the House of Parliament to enhance information sharing and support members of parliament during debates and in scrutinising legislative proposals.
Strengthening oversight and anti-corruption institutions in their abilities to deliver
- Cost of corruption and corruption perceptions reports: These two reports have been championed by the Anti-corruption Commission, which has proactively facilitated dissemination of the findings via the media (radio, TV and social media) and through text messages to 450,000 citizens. The ACC, in collaboration with CARL, held two meetings with MDAs mentioned in the reports to discuss the key findings and secure their commitment to implement the recommendations. The Corruption Perceptions Report has been widely picked up by local media and has triggered a public debate particularly focused on corruption within parliament.
- Court monitoring and “court watch” reports: In order to ensure the integrity of proceedings in the new anti-corruption court, established with support from this programme, the CSO consortium has monitored 30 court cases, with key observations being compiled into “court watch” reports. The reports have formed the basis for discussions with the Chief Justice and the ACC Commissioner on the efficiency of the courts and what improvements may be needed, for example the establishment of a witness management unit to reduce witness absenteeism and the need to recruit and provide additional training to prosecutors.
- Participation in the Covid-19 Transparency Taskforce: the consortium is a member of the ACC-led Transparency Taskforce, which is taking measures to ensure integrity in the Covid-19 response. For example, CARL and Restless Development have signed an MoU with the ACC task force to do joint radio programmes and outreach on Covid-19 transparency and accountability. In addition, the consortium has participated in Taskforce monitoring visits to the National and District C-19 Emergency Response Centres (NaCOVERC and DiCOVERCs) to raise awareness of laws and regulations and review their implementation.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year

Overall, the output has delivered good VFM and met VFM expectations set out in the Business Case.

Economy (cost and quality of inputs): Partners are required to ensure VFM in procurement and expenses, and this is something we have challenged them on in their budgets and forecasts. The CSO consortium has been able to demonstrate that they are maximising value in procurement. For example, the consortium negotiated fee rates for the consultant who produced the second budget credibility report that were 50% lower than the fees he charges on comparable multilateral contracts.

Efficiency (Productivity): The programme has been designed so that engagement and research produced by the CSO consortium complements the work of the Strategic and Technical Advisers. This explicit link helps to ensure that the government is able to respond to CSO findings and act on recommendations. A good example of this is the tax perceptions work undertaken by the CSO consortium, which will be directly picked up by the NRA and the Adviser embedded in the National Revenue Authority supporting taxpayer services and education.

The CSO consortium has sought to identify efficiencies in delivery. For example, linking RD’s interns and Regional Coordinators with CASL’s Regional Engagement Officers to work together at the regional/district level, is helping to ensure the efficient and nationwide delivery of planned activities at low cost.

Equity: The programme supported marginalised groups to conduct pre-budget meetings with Government ministries to ensure their needs were adequately represented in the FY20 budget. This work was deprioritised in light of Covid-19 and will not be repeated for the FY21 budget, however under Phase 2 there will be a focus on equity considerations in budget engagement and oversight. Outreach events organised under the project proactively engaged women and people living with disabilities.

A full VFM framework, including VFM metrics, will be worked up during Phase 2 inception.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The logframe has been updated twice in the past year, reflecting two major programme adaptations. Following the 2019 Annual Review, approval was sought and granted for Phase 2. Phase 1 was therefore extended from March 2020 to June 2020 to enable sufficient time to complete the Phase 2 procurement. The Accountable Grant Agreement amendment was completed in February 2020 and the logframe was updated in March 2020 to reflect this. The next logframe update took place in June 2020 to capture the impacts of Covid-19 which resulted in a pivot in the CSO consortium’s workplan to focus on Covid-19 response oversight. At this time the end date was also extended from June 2020 to October 2020 given delays to the Phase 2 procurement due to Covid-19 and the important oversight role the consortium could play during the early phases of the Government of Sierra Leone Covid-19 response.

The logframe will be reviewed alongside the theory of change and programme workplan as part of Phase 2 inception. A monitoring and learning strategy will also be developed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s annual review identified the need to be realistic about the timelines for procurement / mobilisation of Phase 2 and to continue close working between CSOs and Government in Phase 2. Suppliers’ ability to mobilise quickly was assessed as part of the bid process and we have consulted closely with PCD on procurement timelines. Phase 2 will continue to strengthen constructive engagement between the Government and CSOs. We hope to strengthen internal coordination within the project by bringing the CSO engagement and technical assistance together under one supplier.

There are two key lessons from this year of delivery:
- CSO influencing and engagement is difficult in the presence of social distancing requirements, which require a shift in delivery model away from local level, face-to-face engagements or large national level meetings. Over the next year, it will be important to build our understanding of the effectiveness of different forms of remote communication tools, both in terms of reaching citizens and communicating with Government stakeholders.
- Building effective partnerships amongst CSOs is challenging. Even within a consortium, proactive efforts are needed to create a sense of shared responsibility and accountability for delivery and performance. Phase 2 will need to actively seek to create coalitions for change and to support CSOs to work effectively together towards common objectives.
- Working with Sierra Leonean civil society organisations is crucial in order to develop effective oversight and accountability mechanisms as these organisations have a strong understanding of the political economy dynamics, have strong a strong voice in the public discourse and, in many cases, have productive relationships with Government to support a critical-friend relationship. However, there are a number of capacity challenges, including around technical report writing, data analysis and organisational management. Phase 2 will prioritise a structured engagement with domestic civil society to build longer term capabilities alongside active advocacy, oversight and influencing.
The consortium will present a detailed monitoring and lesson learning report as part of project closure, which will feed into the design of the Phase 2 CSO intervention during the Phase 2 inception phase.

D: RISK

Overview of risk management

As part of this annual review the programme risk appetite statement has been reviewed. The risk appetite has been left unchanged against each of the six categories, as summarised in Table 1. During the past year, risks have stayed comfortably within appetite except delivery and operational risks.

Table 1: Programme Risk Appetite
Risk Category	Risk Appetite
External context	Major
Delivery	Major
Fiduciary	Moderate
Safeguarding	Minor
Reputational	Moderate
Operational	Moderate

Although delivery risks at no point exceeded the “major” risk appetite, in March there was a risk that due to Covid-19 and the associated public health measures, programme activities would need to be cancelled, delayed or adapted and TA / CSOs would be unable to effectively engage with Government, undermining progress against workplans and delivery of outputs. Although the gross risk at the time was severe, the net risk remained within appetite due to mitigating measures including: revising workplans to align with new priorities emerging from Covid-19; adapting methods of engagement to reflect social distancing requirements; and communicating regularly with GoSL on the effectiveness of any remote TA delivery. As travel restrictions have eased, and Sierra Leone never entered full lockdown, the net risk has now been downgraded to moderate.

Throughout the year, operational risks have been at the upper end of the risk appetite due to the uncertainties created by the transition from phase 1 to phase 2 (requiring various levels of approval and amendments to agreements). There is currently one operational risk outside the programme risk appetite, which was escalated to the Country Director in May. This is the risk that delays in phase II procurement or delays in the supplier’s ability to mobilise due to Covid-19 travel restrictions, result in a gap in support provided, negatively impacting relationships with GoSL counterparts and creating a loss of momentum in programme delivery. Although this risk has fallen slightly due to greater certainty around the Phase 2 timelines and the approval from PCD to extend Phase 1 contracts, it remains major. We are taking steps to mitigate the risk through close engagement with PCD on the Phase 2 procurement and dialogue with the Government and hope to bring the risk back within appetite by the end of the year. We do not believe the risk appetite should be adjusted upwards to accommodate this risk, as it reflects short term dynamics rather than an underlying change in the operating environment.

All risk mitigations arising from the Due Diligence Assessment of Christian Aid have been implemented. This includes actions from the enhanced due diligence to strengthen safeguarding procedures including training for all staff and mapping of safeguarding services.

Update on Partnership Principles (delete this section if n/a)
The partnership principles do not form a formal part of monitoring arrangements for this programme. Given the programme’s central focus on a number of core partnership principles themes (especially PFM and anti-corruption), it is a source of information for our partnership principles assessments and also a mechanism to generate buy-in to crucial reforms and support the Government to take these forwards where the buy-in exists.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency.

Narrative and Financial Reporting
The quality and timeliness of narrative reporting from both OPM and Christian Aid has been strong over the period in question. Discussions on risk have taken place monthly between partners and DFID, in addition to ad hoc escalation where required. This has given a good shared understanding of the key risks. We note the IAD recommendation that we continue to strengthen our risk management procedures, including through better articulating fiduciary and safeguarding risks and strengthening the quality of risk matrices. This will be something we work on with the Phase 2 supplier.

Financial management, especially accurate forecasting, has been a challenge in the period under review. In the last 6 months (February – July) on average CASL has had a variance of 34% and OPM has had a 16% variance. There are three main reasons for this:
- Partner internal procedures and communications. This has particularly been a challenge for the CSO consortium, where Christian Aid have struggled to get timely and accurate information from partners. A more hands on approach from the CASL finance team to working with consortium partners’ finance team has improved the flow of financial information. On the OPM side, there was some confusion around DFID forecasting procedures (a view that overspends were seen more negatively than underspends) that led to consistent under-forecasting until this was clarified by DFID (in June 2020).
- Covid-19 impacts. This resulted in disruption to programme activities and created substantial amounts of uncertainty, including related to mobility restrictions, which created a number of challenges in accurate forecasting March – June. The programme has now adapted to be more resilient to Covid-19 impacts (e.g. improved ability to shift to remote delivery models when required).
- Multiple amendments to agreements and delays in agreeing revised workplans. Due to the need to secure approval for phase 2 and then extend support given the Covid-19 delays to Phase 2 procurement, there has been a need to revise agreements and workplans on several occasions. This necessarily creates uncertainty around forecasts and has made it harder for partners to plan effectively.
Up to date audited financial statements have not yet been received from all partners and this is something DFID are following up. To ensure good programme management practice is applied, we will ensure Phase 1 is fully closed out by March 2021 in line with closure procedures in the Smart Rules.

Assets have been well managed by CASL and OPM, with regular updates to asset registers and strong cooperation with DFID teams during asset checks.

The OPM contract sits under the EACDS framework agreement. There has only been one SRM scorecard assessment since the last Annual Review covering September – November. This scorecard showed a small improvement from Q1, although there were still challenges around communication (with DFID and TA) and programme management. The appointment of a new OPM programme manager in November led to a vast improvement in OPM’s responsiveness, financial management, and engagement with TA. The scorecard process was put on hold due to Covid-19.

Monitoring approaches
DFID Advisers have regular direct engagements with TA, OPM, Christian Aid and Government of Sierra Leone counterparts. These conversations provide a strong understanding of progress under different workstreams, risks and the political economy of reform. A political economy analysis was undertaken in October 2019 to inform Phase 2 design.

Phase 2 has been designed to have a more integrated approach to programme governance, across the TA and CSO elements, and will have a robust M&E framework. The programme has been designed to be adaptive, with active feedback loops that include mainstreaming political economy and conflict analysis across the programme.

The 2020 Internal Audit
The project was selected for a deep dive by IAD in May 2020. A summary of key findings and our planned follow-up actions is included below. We will track follow-up through the delivery plan.

Finding	Planned Follow-up
Severe operating risks stemming from the combination of coronavirus impacts, phase two contracting and continuity risks, and the impacts of the UK ODA prioritisation exercise responding to the fall in UK GNI.	We are engaging closely with the Procurement and Commercial Department on Phase 2 contracting, have put in place strong handovers to support staff transitions within FCDO, and have adapted the programme focus and, where relevant, delivery models to enable continued engagement in spite of Covid-19.
Risks surrounding delivery disruption as the programme moves from Phase 1 to Phase 2.	In addition to engagement with PCD noted above, we are working to ensure TA work under Phase 1 is accurately recorded and all documents are available for a smooth handover. We will minimise gaps in delivery as far as possible.
Decision capture under the programme should be strengthened to improve lesson learning and risk management.	We are working to develop more streamlined mechanisms to capture decisions and follow-up actions, including reviewing the use of decision log tools available on the Aid Management Platform.
There is scope to further strengthen programme risk management including through more nuanced assessments of contextual risk by component and better capture of safeguarding risks.	We will continue to refine the programme risk register and how we manage risk conversations with partners and internally.
The logframe could be strengthened to become a more useful tool for performance assessment and management.	This is something we will work on during Phase 2 inception in addition to revisiting the logframe after this review to accurately capture Phase 2 inception expectations.

Value for money
The 18-month Phase I, anticipated to promote VFM by enabling reform appetite and approaches to be tested, has in reality created a challenge to VFM. In particular, under Phase I Technical Advisers have accumulated context specific knowledge and built working relationships, which have added value to their work. The move to Phase II, which entails a new procurement process to select a supplier, risks losing this knowledge and relationships. This is significant as most reforms take longer than 18 months to deliver and embed. The design of Phase II takes this into account, with the contract running up until March 2024 with the option to extend for an additional 24 months.

The disruption caused by Covid-19, which impacted supplier markets, DFID budgets and needs on the ground, increased the complexity of managing the transition from Phase 1 to Phase 2. Delays to the Phase 2 contracting process, including a need to cancel and relaunch the tender to reflect Covid-19 impacts, meant that the programme had to be adapted both in terms of the workplans and also through amendments to formal agreements to extend end dates and move money between fees and expenses. Agreements with longer time horizons, which built in contingency windows to cover delays to Phase 2 contracting, could more easily have absorbed the impacts without requiring formal amendments. Delays to DFID internal processes, which meant these amendments could not be implemented as rapidly as usual also increased the levels of uncertainty. Both OPM and CASL worked constructively with DFID during this time period to minimise disruptions to delivery.

As noted above, these issues around the transition from Phase 1 to Phase 2 were highlighted as a severe risk in the DFID Internal Audit Department review of the programme, which took place in May 2020.

The absence of a robust value for money framework and unified results framework for the programme (at a more detailed level than the DFID logframe) has made it challenging to effectively assess the VFM of the programme. This is something that will be addressed during Phase 2. In preparation for this, and given the delays to the Phase 2 launch, we will seek to further develop the VFM narrative and an interim set of VFM indicators to more accurately capture both the VFM of Phase 1 overall, and that of delivery over the next 4-6 months.

Date of last narrative financial report	OPM: 17/08/20 / CASL: 21/08/20	Date of last audited annual statement	31st March 2017