Project Completion Review

Title: Strengthening prevention of gender-based violence in Rwanda
Final Programme Value £ (full life): £4.6m		Review Date: October 2018
Programme Code: 204142	Start Date: August 2014	Final End Date: August 2018

Summary of Programme Performance

Year	2014	2015	2016	2017	PCR
Programme Score	n/a	A	A	A	A+
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4574054.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4574329.xlsx

A. SUMMARY AND OVERVIEW

Acronyms

CA - Community Activist
CIUK - CARE International UK
CSO - Civil Society Organisation
DFIDR - DFID Rwanda
DPO - Disabled People’s Organisation
GBV - Gender Based Violence
GoR - Government of Rwanda
IPV - Intimate Partner Violence
IzU - Inshuti z’Umuryango
LSHTM - London School of Hygiene and Tropical Medicine
MIGEPROF - Ministry for Gender and Family Promotion
NCC - National Children’s Commission
NCPD - National Council for People with Disabilities
NISR - National Institute for Statistics Rwanda
OL - Opinion Leader
PAC - Programme Advisory Committee
PCR - Programme Completion Review
RCT - Randomised Control Trial
RWN - Rwanda Women’s Network
RWAMREC - Rwanda Men’s Resource Centre
UNICEF - United Nations Children’s Fund
VAC - Violence Against Children
WS - Women’s Space
WSF - Women’s Space Facilitator
WW - What Works

Description of the Programme

The UK provided £4.6m over 4 years (2014 - 2018) to prevent violence against women and children in Rwanda. The intended outcome of the programme was reduced prevalence of GBV and strengthened community-level mechanisms for the prevention of violence against women, girls and boys in programme sectors. The ‘Strengthening Prevention of Gender-Based Violence (GBV) in Rwanda’ programme had 3 components:

The Indashyikirwa - or ‘Agents of Change’ - programme was led by CARE International (£4,029,837), developing and rolling out community-level programming on GBV prevention. Indashyikirwa was implemented in 7 Districts in partnership with the Rwandan Men’s Resource Centre (RWAMREC) and Rwanda Women’s Network (RWN). It had 4 main components:
[note] The 7 districts reached are: Kayonza, Bugesera, Rwamagana, Rubavu, Nyabihu, Burera, Musanze. 14 Sectors within these districts were reached (not all villages per sector) – out of a total of 97 sectors. The total population of the intervention area is 2,425,204.
- Intensive 5-month participatory training with couples (Couple Curriculum);
- Community-based activism undertaken by a sub-set of individuals who completed the Couples Curriculum (Community Activists - CAs);
- Direct support to survivors of GBV through the Women’s Safe Spaces (WS) and training of Women’s Space Facilitators (WSFs); and
- Training and engagement of Opinion Leaders (OLs) - respected members of the community including elected officials, local government officials, religious leaders, and service providers (police, health, justice providers).

A separate impact evaluation was implemented alongside the programme as part of the wider What Works to Prevent Violence against Women and Girls Programme (WW). This was funded centrally by DFID’s policy and research division (203709) and is now completing the write up of findings of the randomised control trial (RCT) testing the impact of Indashyikirwa. It also included a cost-effectiveness study.

Inshuti z’Umuryango (IzU) - or ‘Friends of the Family’ - was led by the United Nations Children’s Fund (UNICEF) (£464,268). It supported the Government of Rwanda’s (GoR) new community-level child protection system in collaboration with the National Children’s Commission (NCC). IzU is a key component of the national Family Promotion Policy (2014) and includes:
- The mobilisation of 29,674 elected and trained volunteers (IzU - 50% men / 50% women) with responsibilities to assist in the prevention and protection of children from violence, exploitation, neglect at village level;
  [note] Training occurs in two stages: The pre-service training (29,674 so far) modules include child protection roles & responsibilities, positive parenting and how to conduct household visits. The in-service training (11,514 so far) modules includes: Rwanda legal framework, how to provide basic psychosocial support, conflict management, communication skills, asset inventory, referral pathways.
- Short-term, intensive, local support to the IzU system (to-date delivered by Save the Children)

Key Achievements and Limitations and Challenges

The ‘Strengthening Prevention of Gender-Based Violence in Rwanda’ programme has been a success. This is demonstrated by the A+ score at output level and, particularly, by the programme’s contribution to the central aim of reducing the prevalence of GBV. Table 1 below presents a selection of key achievements and limitations and challenges (see Section C for more details).

Achievements	Limitations and Challenges
The programme reduced experiences of violence (GBV and Children). The WW impact evaluation shows significant reductions in physical, sexual, emotional and economic Intimate Partner Violence (IPV) among the couples involved in the couple’s cohort. These results are amongst the best achieved by similar programmes in different contexts. The study also indicates significant decreases in: (i) men and women’s endorsement of corporal punishment or physical discipline in raising children; (ii) reported frequency of smacking or beating children in the home; (iii) mother’s reporting of children witnessing violence in the home; (iv) the reported number of reasons to justify wife-beating; (v) symptoms of depression; and (vi) household food insecurity. Increases are shown in levels of communication and trust in the home, community engagement among women participants, cash income and health scores. / Significant GoR buy-in. A driving factor behind the design of the programme was to complement GoR’s focus on responding to GBV through a prevention-focused approach – which GoR has demonstrated increasing support for. At national level, MIGEPROF’s Indashyikirwa II programme and the allocation of budget for IzU coordination by NCC are noteworthy. At implementation level, programme participants - CAs, WSFs and IzU - have been well-connected to, and involved in, formal local government structures and some Sector and/or District offices where Indashyikirwa was implemented have allocated finance and other resources to support the continuation of activities. / Indashyikirwa, through the WW evaluation, has generated (and will continue to generate) world-class evidence. This has the potential to influence future policy and programming on GBV in Rwanda and beyond, addressing a critical lack of robust evidence. Indashyikirwa has many aspects which will add value to the evidence base - including its scale, adaptation and the efficacy of working with couples. Important learning may also emerge from Indashyikirwa II. Implementing partners and the WW consortium have already had further discussions with interested organisations who would like to take up the Indashyikirwa model in other contexts.	The WW quantitative evaluation was unable to prove conclusively that the intervention reduced prevalence of GBV among the wider community (i.e. amongst indirect beneficiaries). There are a variety of possible reasons for this, including the duration of the intervention (only 18 months of activism). The test for community level change set up by the WW RCT was very stringent and may have under-reported some impact. The qualitative data suggests that community level change was in progress or beginning to emerge. / There were limits to the inclusiveness of Indashyikirwa. The programme, through both design decisions and oversights in implementation, could have been more inclusive. and targeted specific, vulnerable groups earlier. Efforts were made, particularly in the final 18 months, to address these gaps where possible. While this is identified as a limitation, it is also an example of the way the programme learned and adapted throughout its lifetime. / High turnover in DFID Rwanda staff over the life of the programme delayed the identification of capacity gaps among Indashyikirwa implementing partners. Capacity building needs were identified through the 2017 audit, with strategies and resources subsequently put in place to address these. While partners demonstrated strong commitment to capacity building in the final year, programme and financial management could have been improved earlier. / Only a limited amount of the evidence emerging from Indashyikirwa has been published, shared and disseminated to date. The specific findings of the impact evaluation and the cost-effectiveness study remain to be finalised and approved. As such, this PCR cannot, at the time of writing, include the numerical data to demonstrate findings. While this was expected, it has limited the ability of partners to build enthusiasm, momentum and lesson-learning beyond those directly involved. As a GoR programme, IzU will be fully evaluated in 2019.
[note] In 2016, MIGEPROF secured funding from the World Bank Great Lakes Sexual and Gender Based Violence (GLSGBV) programme to implement (a slightly revised version of) the Indashyikirwa couples curriculum and Women’s Spaces (WS) in four districts in Eastern province for one year, including an impact evaluation. This programme is known as Indashyikirwa II. MIGEPROF secured the same delivery partners as the DFID-funded Indashyikirwa I, however the programmes and evaluations have been implemented separately.
[note] NCC allocated nearly £150,000 for IzU system coordination in the 2017/18 financial year, and again allocated nearly £130,000 for the 2018/19 year.

Table 1: Summary of Achievements and Challenges/Limitations

Recommendations

Both DFIDR and DFID counterparts in the UK should pro-actively engage in evidence forthcoming from WW and Indashyikirwa II. DFID must ensure that as WW evidence becomes available throughout the remainder of 2018 and 2019 it is taken up internally and more widely. Where possible, this engagement should consider what support DFID can provide to increase in-country dissemination, for which there are currently no plans in place. DFID should also embrace the opportunity that Indashyikirwa II presents to build on the WW evidence. This may be more challenging for DFIDR due to staff turnover and the end of this programme – losing the GBV focal point - but should be anticipated in workflow planning.

As part of staying engaged with the evidence, DFIDR should continue to engage with partners, particularly GoR, to ensure future thinking about GBV programming in Rwanda draws appropriate conclusions from Indashyikirwa and Indashyikirwa II and their impact evaluations. This includes conclusions related to the cost-effectiveness of the intervention and considerations around reducing/streamlining components and roles, which has trade-offs and may reduce impact.

DFIDR and DFID UK should compile and share internally lessons learned in relation to:

- How best a joint centrally managed research programme and bilaterally-managed intervention can work together, recognising that this worked well for Indashyikirwa but improvements could be made in future - mitigating issues around timing, funding, research dissemination, and relationship building (this is particularly relevant for DFIDR’s IAG-R programme, GAGE more broadly, and any future iteration of WW).
- How we can more explicitly consider sustainability at the outset in pilot research interventions (which for various reasons may not be followed by a DFID-funded post-pilot stage), including the trade-offs between the higher costs of requirements for robust research vs. lowest cost programming options, and maintain a focus on sustainability throughout.

Future community-based programming, both in Rwanda and beyond, should consider:

- Whether sufficient time has been made available to realise community-level social norm change;
- Whether the programme design is likely to exclude some marginalised groups, and whether early targeted actions could mitigate that exclusion and increase impact;
- Whether sufficient time and resources have been allocated for the adaptation of a model from one context to another, not only at inception but throughout the programme;
- Whether greater engagement with media platforms could accelerate community-level change;
- Whether the use of, and burden on, volunteers has been appropriately planned for, supported and compensated, including expectations of high-turn over and associated costs;
- Whether local authorities and governance structures have been adequately consulted and included as key agents of influence and change, (particularly relevant to the Rwanda context);
- Whether the psycho-social role and training provided to agents working on GBV at community level is sufficiently robust and supported at various levels, to equip those agents to form a ‘front-line’ of counselling, psycho-social support and mental-healthcare in their communities (particularly relevant to the Rwanda context).

Output Scores and Overview

Output	Impact weight	Score	Risk
Output 1	35%	A+	Moderate
Output 2	20%	A+	Moderate
Output 3	25%	A+	Moderate
Output 4	20%	B	Low

Table 2: Summary of Output Delivery/Scoring

Table 2 above summarises the assessment of programme performance against scored outputs. Output 1, 2 and 3 scored A+. These outputs broadly cover the number of direct and indirect beneficiaries reached by both the Indashyikirwa and IzU programmes, targets which have routinely been exceeded (approximately 30% more beneficiaries have been reached than expected). While these are quantitative targets, the meaning behind each ‘beneficiary’ is significant – reduced violence against women and children. These outputs also represent significant resources and achievements that will outlast and reach beyond the programme (and logframe) – curricula to prevent violence against women and children (4 of which are open-access, 2 of which are owned by GoR), government commitments to prevent violence (including policy changes as a result of advocacy), and 14 sustained physical safe spaces. Output 4 scored B, in part due to the timing of the PCR. While WW has delivered a gold-standard RCT which we are confident will add to the global evidence base, at the time of writing it largely has yet to do so, as we wait for approval for it to be published. This is, mainly, due to circumstances outside of WW and implementing partner’s control.

Follow up Actions Required

On approval of this PCR, DFID will deliver the following close out actions: (i) the final programme audit will be completed by February 2019; (ii) final reports from WW will be published on Research for Development (R4D); (iii) all appropriate documents will be published on DevTracker; and (iv) all financial actions will be completed against Smart Rule requirements.

## B: DETAILED OUTPUT SCORING

Output Title	Best practice community-based GBV and Violence Against Children (VAC) prevention curriculum developed and implemented
Output number per LF		1	Output Score	A+
Impact weighting (%)?		35	Impact weighting % revised since last AR?	No

Indicator(s)	Targets (August 2018)	Progress
1.1. Community GBV prevention curriculum improved and agreed based on evidence, lessons learning and exchange between CSOs and the GoR	Indashyikirwa GBV curriculum prevention package is reviewed, tested and validated in Rwanda by MIGEPROF and other stakeholders	The GBV prevention package was validated by CARE, partners and MIGEPROF in a validation workshop in June 2018 A
1.2. Number of Indashyikirwa curriculum-trained couples actively promoting attitudes against GBV in target sectors	420 CAs continue to operate in communities and reach 585,553 community members, with strategy in place for their sustainability after the programme ends / Bi-annual catch up meetings for 1,180 non-activist trained individuals / Monthly catch up meetings for 420 CAs	500 CAs operating and 586,962 community members reached (344,918 women, 193 disabled); 242,044 men, 49 disabled). / On sustainability - see Outcome 1.5. / Bi-annual catch up meetings held with 1,180 non-activist couples / Monthly catch up meetings for 500 CAs collected activism reports, resolved challenges and planned for the coming month A+
1.3. Number, types and frequency of interventions taken by Community Activists and VAC Friends of the Family to promote gender equality and challenge GBV and VAC in Indashyikirwa target communities	21,317 activism actions taken in Year 4 by 420 activists (2 actions/activist/month) through training role plays, dialogues and other outreach activities / 115,140 household visits conducted to deliver positive parenting skills to reduce violent discipline practices / 46,056 children/families provided with basic psycho-social support	20,160 activism actions conducted / 150,418 household visits conducted to deliver child protection services / 85,104 children provided with direct basic psycho-social and counselling support / A+
1.4. Number of trained community based child protection IzU (volunteers) operating in Rwanda.	10,000 IzU receive in-service training by Sept 2018	10,186 IzU are now fully operational in 11 Districts. 11,514 IzU (all) in these Districts received refresher training - 1328 pending job aids to be fully operational A

Key Points

This Output scored an ‘A+’ (Outputs Exceed Expectations). This score reflects (i) the enormous value alone of the couples and CA curricula, which have been proven to be extremely effective and are now open-access to anyone around the globe, to meeting the output title; as well as the considerable over-achievement of IzU, who supported more than 80% more children than anticipated.

The Indashyikirwa and Inshuti z’Umuryango interventions only overlapped in 2 Districts (Rwamagana and Nyabihu). Where possible, the two components made efforts to coordinate on the ground, for instance by undertaking joint home visits (CAs and IzU), and joint messaging during community meetings on GBV and VAC and referral pathways. However, IzU is a GoR strategy while Indashyikirwa is a discrete intervention; opportunities to bring them closer together at a more strategic level were limited. All partners from both components participated in the GoR-led Programme Advisory Committee (PAC) meetings from the start, which supported information sharing.

Indashyikirwa has refined and produced a package of curricula used throughout the programme. These have been used to work with and train i) couples ii) CAs; iii) WSFs; and iv) OLs. This resource reflects the experience and learning from the programme. The curricula have been largely proven to be effective in reducing IPV by the impact evaluation and represent a valuable global public good. They will be published on the WW website, as well as on the CARE International website which targets peer agencies, donors and policy makers. The curricula will be open access and therefore available to GoR and other organisations working to prevent GBV in Rwanda.
[note] https://www.whatworks.co.za/resources/vawg-prevention-curricula
[note] https://insights.careinternational.org.uk/in-depth/life-free-from-violence

The total number of CAs was increased by 80 in November 2017 due to high demand from within the couple’s cohort to progress to activism - more than 25% of couples wanted to continue as activists - and to make sure that all villages were covered in each sector. ‘Actions’ undertaken by CAs included speaking at various community gatherings to promote gender equality and messages to prevent and respond to GBV. The number of activism actions did not meet the target (indicator 1.3) due to three periods in which activism was paused: (i) the presidential election campaign period (July/August 2017), (ii) the genocide commemoration period (April 2018), and (iii) (May and June 2018) when CAs participated in close-out meetings at sector and district levels, which took time away from other forms of activism. CAs have built strong reputations, interest in and appreciation of their work. As a result, CAs are now being called on to engage directly with couples where there are reports of violence and support local government officials in their broader GBV work. This is one of the newer elements of the programme and while the roots of community activism have been established, there is a significant risk that momentum will be lost as the programme ends.

The full roll-out of the IzU component (to all 30 Districts) is expected to be completed by 2023. DFIDR support has contributed to fully operationalising IzU in 11 Districts (training, CSO support, and job aids), and partly operationalising in an additional 2 districts (training and job aids) . Between the beginning of operationalisation (Jan 2017) and mid-June 2018, 65,094 child violence, abuse and exploitation cases have been reported and followed up, supported by testimonies from stakeholders of a significant increase in communities seeking child protection services. IzU reports to NCC during ‘follow-up’ (ongoing home visits) help to determine whether there is a need to reassess a child’s situation and care plan, or if further intervention from NCC is required.
[note] Additional funding (£32,268) was made available to UNICEF by DFID Rwanda in July 2018 to provide job aids for 1,476 IzU in an additional 2 Districts. This will be completed by the end of 2018,. Approximately 19,800 households and 5,904 children will be directly benefiting from IzU services and 79,200 children will be indirectly supported through the additional funding.
[note] Districts reached are: Gasabo, Gicumbi, Rwamagana, Nyabihu, Ruhango, Nyamagabe, Nyamasheke, Gekenke, Ngoma, Nyarugenge, Kirehe (additional funds to support Kamonyi and Kayonza districts).

UNICEF and NCC partnered with Save The Children to provide intense operationalisation support in 11 Districts. This led to a rapid scale-up of activity and has proven critical to the success of the programme. In the Districts where IzU are receiving support from Save the Children, each Izu conducts at least two visits to two different households every week (i.e. a total of 4 household visits), makes referrals or otherwise supports families to access appropriate services, follows up on referred cases, provides dedicated psycho-social support and counselling to both parents and children, and reports back on a monthly basis to NCC. However, in the other 19 districts, many IzU are not yet fully aware of their roles and responsibilities nor equipped to carry them out, and links to local government structures and other referral mechanisms much weaker. NCC and UNICEF are currently in discussions about the future of CSO support to the IzU system at the local level.

IzU have identified a number of challenges and opportunities, all of which have been collected by UNICEF for lesson learning and future adaptation. These include: (i) the need for further training modules (after in-service training or in addition to), e.g. working with children and carers with disabilities, and context-specific training, such as urban vs rural settings or areas close to refugee camps (with both refugees and host communities); (ii) improvements to standard reporting templates to improve data collection, monitoring and referral; and (iii) the absence of formal feedback after referring a case to relevant authorities (in accordance with privacy rules) - making follow-up action and future engagement with referred families more challenging.

Following the recommendation of the 2017 AR, 13,499 local leaders from 21 Districts who closely work with IzU benefited from Child Protection training as part of the programme to ensure they have the capacity to support the IzU system. Local leaders in the remaining districts will be reached by the end of 2018.

Lessons

The current Couples Curriculum takes 5 months to deliver and covers 20 sessions. The Indashyikirwa II curriculum is slightly revised, covering 22 sessions and may provide more evidence about the efficacy of the model. Inevitably, a shorter curriculum would be cheaper and there are questions around optimal cost effectiveness, particularly for government partners. (See Recommendation A).

The time, resources and cost of the adaptation of the SASA! model to the Rwandan context was underestimated. The two countries are significantly different, making the adaptation of the model nearly equivalent to the design of a new intervention (and a substantial start-up cost). Activism in the Rwandan context must take place in more formalized settings and requires extensive formal engagement with local leaders, a process which delayed the launch of activism activities. The WS provided a valuable place for more informal activism, and qualitative evidence suggests activists were starting to facilitate more informal meetings (e.g. at bars, churches, home visits), towards the end of the programme. This very context-specific reality should be anticipated and planned for in future community-level programming. (See Recommendation D).
[note] SASA! is a methodology and approach designed by the Uganda-based NGO Raising Voices, which works with women and children to explore the gender aspects of power and to address the link between violence against women and HIV/AIDS.

The time available for activism may have been insufficient to robustly demonstrate results. The activism component was, as noted above, adapted from SASA! – which was proven to be effective but operated in the field for 4 years, compared to the 18 months available in this programme. (See Recommendation D).

Volunteers enabled both Indashyikirwa and IzU components to be delivered at lower cost to all partners, but there are economic costs incurred by volunteers – including their time. To motivate and sustain volunteers, support is required to help coordinate, plan, prioritise and assess activities and pragmatically, to assist with costs and means to e.g. travel to different parts of a community and use mobile phones to communicate. There is also a cost – in impact and sustainability - associated with not or insufficiently providing this support. The economic costs of volunteers will be taken into account in the Indashyikirwa cost-effectiveness study, but must also be adequately considered in future programming from the outset. (See Recommendation D).

The recent GoR decision to reduce the number of state social workers/psychologists in each district from 68 to 30 will make it harder for IzU to have clear referral and support lines, and increase the workload for IzU. This also raises questions about the ongoing training, support and resourcing of various roles captured in this and other programmes - e.g. CAs, WSFs, IzU, as well as other proximity workers at community level, who have been trained in psychosocial support and may now form a ‘front-line’ of mental healthcare in communities, as violence and mental health concerns frequently co-occur. (See Recommendation D)

Output Title	Improved civil society coordination and partnerships: and increased responsibility of Government of Rwanda (GoR) in the GBV prevention and response space at national and local levels
Output number per LF		2	Output Score	A+
Impact weighting (%)?		20	Impact weighting % revised since last AR?	No

Indicator(s)	Targets (August 2018)	Progress
2.1 Opinion Leaders and Local Authorities engage, participate in and support GBV prevention messaging and activities at sector level	600 Opinion Leaders and Local Authorities continue to be engaged in supporting GBV prevention messaging at sector level (via training and meetings) beyond the end of the programme.	950 Opinion Leaders recruited (600 as planned; 350 additional Village leaders and representatives of People with Disabilities (PWD) in August 2018. This means there are 41-43 trained OL per intervention sector. A++
2.2 Number of sector level Imihigo GBV prevention and response indicators that are reviewed, quality assured and monitored by RWN and community members, disaggregated by sector	14 Imihigo performance contracts from 14 target sectors include GBV prevention and response related indicators that have been quality assured, reviewed and monitored by RWN and community members.	14 Imihigo performance contracts include GBV provisions that have been reviewed and monitored by RWN community members. / A
2.3 Number of information sharing and lesson learning interactions between CSOs and GoR at different levels on violence against women and children	4 Quarterly sharing and lesson learning interactions conducted between CSOs and GoR on GBV issues.	Over the life of the programme: / 12 quarterly meetings at sector level; / 9 quarterly meetings at district level; / 2 information sharing and lesson learning sessions at district level (June 2017 and 2018); / 2 dialogues at sector level (Nov 2017 and July 2018). / In the final year, 3 out of 4 quarterly meetings were held at district level. A
[note] Participants included implementing partners, District Leaders (education, social affairs), Police, Maison d’Accès a la Justice (MAJ), disability and youth associations, National Women’s Council, and representatives of the Joint Action Development Forum.

Key Points

This output scored an ‘A+’ (Outputs exceed expectations), particularly as a result of the over-achievement of indicator 2.1. OL are a critical element of the theory of change, in creating an enabling environment in which social norms may shift within local government and the wider community. Additional OL suggests that there is a higher chance that community–level change and behaviours will be sustained beyond the programme.

Engagement with leaders has been a critical element of Indashyikirwa to ensure community-based GBV prevention, particularly given the formal and structured nature of community life in Rwanda. A two week training curriculum was implemented to raise OL awareness on gender inequality and provide them with the necessary knowledge and skills to prevent and respond to cases of GBV more effectively. OLs initiated a number of formal and informal activities (discussions at community gatherings, home visits), engaged with programme advocates and made commitments, which were monitored and held to account by local stakeholders.

Regular monitoring, field consultations and the qualitative research indicates that engagement with OLs contributed to an “enabling environment” for better prevention of and response to GBV, consistent with the theory of change. Imihigo (performance contracts) are a critical facet of Rwanda’s governance system operating at all levels of the state. Put simply, what goes into an imihigo, is most likely planned for, measured, resourced, and held accountable. As a result of the interventions and support from CAs, WSFs and OLs, sector-level Imihigo in Indashyikirwa intervention sites have included more specific targets to prevent GBV. An assessment done by RWN showed that fiscal year 2016-17 imihigo in only 9 intervention sectors (out of 14) included GBV related actions as part of the Umugoroba w’Ababyeyi (Parents’ evening), but did not have clearly measurable indicators. For the 2017-18 imihigo, all 14 sectors included actions and 9 have allocated funds for GBV activities. Sector-controlled budgets are very small, so while this is a significant development, overall funding remains insufficient.
[note] Umugoroba w’Ababyeyi is a ‘homegrown initiative in Rwanda (pre-dating the programme). It is a community discussion for parents which takes place fortnightly, at which various issues and information related to the wellbeing of families are raised.

Lessons

Turn-over of volunteers (IzU), programme staff (DFIDR and partners), and elected and local government officials (OLs) should be expected and planned for, with a strategy in place to adapt and respond. Turn-over in OLs in particular drew on and diverted resources, however the wider impact was mitigated through refresher trainings. (See Recommendation D).

Diversification of OLs was beneficial, and could have been integrated earlier. Village leaders, youth representatives, and leaders among people with disabilities helped to reach more marginalised indirect beneficiaries, while greater engagement of religious leaders as OLs was possibly a gap, given their influence in Rwandan communities. (See Recommendation D).

Media and mass-communication mechanisms, with the exception of the radio dialogues, were not used as part of the programme for a number of reasons - including the formal nature of activism in Rwanda, limited monitoring scope, and changes in policy within DFID. However, Rwandans are well-accustomed to hearing public policy and behaviour change messaging through radio, television, news and loudspeakers, and there is evidence of their effectiveness in this context. Greater use of these platforms may have been a useful tool, particularly to engage younger people. (See Recommendation D).

Output Title	Women’s Spaces are established and provide information and support to community members and victims of GBV
Output number per LF		3	Output Score	A+
Impact weighting (%)?		25	Impact weighting % revised since last AR?	No

Indicator(s)	Targets (August 2018)	Progress
3.1 Establishment of functional and sustainable Women’s Spaces in target sectors	Implementation of 14 Women’s Space sustainability plans to provide sustainability of Safe Spaces beyond the lifetime of the programme.	14 WS sustainability plans were created, with varied implementation success. For example, only 5 out of 14 WS renovations progressed as planned. In spite of this, all WS remain operational at the time of writing. A
3.2 Number of Women’s Space Facilitators receiving training and ongoing support	300 Women’s Space Facilitators continue to be active in their work.	291 WSF were active at programme end. A
3.3 New cases received in the Women’s Spaces seeking GBV counselling or support; and use of Women’s Spaces to engage with community members and indirect beneficiaries (disaggregating by disability, age and location)	22,890 women in total participated in Women’s Space Activities, with 1200 individuals receiving counselling and support.	Cumulatively, 38,639 women attended community dialogues and 112,652 women received outreach over three years. / WSF reached 211 People With Disabilities (PWD) / New cases (individuals receiving support) at WSs from Aug 2017 to Aug 2018: 1,063 (854 Women & 209 men) A+
3.4 Proportion of counselling/support cases referred by the Women’s Spaces and receiving further support and WSF follow up; by: / # of referred cases / # of completed interventions	500 counselling and support cases referred and receive further support and follow-up	Cases received at WSs and referred to specialist services: 698 (572 women and 126 men) / 178 referred cases were fully resolved through these services/follow up. 227 cases were never ‘completed’ with WSF unable to access further information after referral. The vast majority of incomplete cases were women referred to local leaders (168). A+

Key Points

This Output scored an ‘A+’ (Outputs Exceed Expectations). WS provided more information and support to communities than anticipated, particularly through outreach. WSF have also played a critical role in off-logframe outputs, including advocacy, as a key source for identifying the barriers faced by survivors of GBV when accessing support.

WS were a tangible focal point for Indashyikirwa’s sector-level activities. Usually open 3 days a week, the WS provide a safe space for women and men to share information about violence and receive private and confidential support from trained WSFs. When necessary, cases/individuals were referred to other authorities or services, sometimes accompanied in person by WSF for support. Like IzU, WSF struggled to follow up on cases referred due to privacy regulations, but the voluntary use of referral feedback forms helped, and in some cases improved the timeliness and quality of services provided. This reflects a lesson/oversight in the logframe indicator. WS also hosted community dialogues (2 per week per space) and income generating activities. Relevant services and professionals (health workers, police etc.) were also brought to the WS to make engagement with authorities less intimidating for those involved.
[note] These include the Isange One-Stop Centres (a GoR GBV-response initiative), police, healthcare, local authorities, and legal service providers.
[note] Forms were initiated in the WS with a new case, added to by the referral service provider, and returned to WS.

By the end of the programme, WSF reported a decrease in cases coming to the Women’s Spaces (from over 10 per week to 2-3 per week). They attribute this reduction to an actual reduction of the prevalence of GBV and a general shift in perceptions of gender in their communities, as well as associated improvements in aspects of gender inequality, such as joint land titles, formalised marriages, etc. Often, women would engage in a WS first, before bringing their husband or partner along with them. The impact evaluation (community surveys) show that WS were generally well utilised (most attendees visit the WS more than once), and more than 90% of both men and women interviewed were willing to recommend the WS, speaking to a very strong reputation in the community: “The space is a place for women to come and record GBV. That wasn’t happening in the past. Women would get raped or sexually abused, but they wouldn’t talk about it. Ever since [WSFs] started being vocal about these issues, people are now more open to reporting GBV.” (Women Safe Space Facilitator)

Many women who attend the WS come to connect with other women, forming friendship and support networks which have contributed to building confidence, and led to economic cooperatives (e.g. for shared savings or making curtains, clothes, handicrafts, etc.).

WSF undertook home visits to marginalised households and villages further away from the WS, which while placing a strain on their time and resources, played a helpful role in reaching indirect beneficiaries. Interviews with WSFs indicate that some women were initially reluctant to come forward, participate in activities and particularly hesitant to talk about violence or abuse (with physical and sexual violence being the most taboo). Early on, some community members shared that they felt the spaces were only for married couples, which was keeping young people, divorced, widowed, and people in informal relationships away. WSF worked to spread the message that spaces were open to everyone, resulting in more diverse attendance. Following targeted outreach, the WS also welcomed young people to bespoke sessions, including young parents.

Lessons

More explicit links between participants in the Couples Curriculum, CAs, and WS could have better bridged the village level and sector level components of Indashyikirwa. Similarly, the training and outreach role of WSFs, the CAs and IzU could be more closely linked and/or streamlined. While IzU only overlapped with Indashyikirwa in 2 districts, the similarities between roles and the commonalities raised in reporting (particularly of the GBV issues occurring in communities and the challenges in delivering their roles) suggest that these responsibilities could also have been streamlined. However, the workload for all roles remained high throughout the life of the programme, and therefore there is a trade-off with fewer roles, which may lose some of the critical mass achieved. (See Recommendation A).

Ensuring the sustainability of the WS beyond the life of the programme was a major concern for implementing partners and required a lot of work in the final year. Sustainability plans were unique to each space and placed the onus on already-stretched volunteers to generate income. Some sector and district offices have contributed to support the continuation of Indashyikirwa activities, including by making existing state buildings available for use as WS. This is a significant step in demonstrating the value placed on WS and WSF by local authorities and communities. However, WSF will no longer receive the stipend to cover expenses they had under the programme, presenting a risk that they will move on to other income-generating activities. The sustainability of WS is likely to be more secure where the spaces are utilized for a wider range of activities. (See Recommendations C & D).

Output Title	Improved evidence base on ‘what works’ to prevent GBV in Rwanda
Output number per LF		4	Output Score	B
Impact weighting (%)?		20	Impact weighting % revised since last AR?	No

Indicator(s)	Targets (August 2018)	Progress
4.1 Independent impact evaluation for DFIDR programme delivers high quality research findings.	Endline study complete. Final impact evaluation report produced.	The draft What Works endline study was completed in June 2018. A national validation workshop was held on 2nd and 3rd October and findings discussed and accepted by the programme stakeholders and MIGEPROF. The report has yet to be submitted to NISR for final approval. A
4.2 Evidence from impact evaluation is disseminated to relevant policy, programme and academic stakeholders in Rwanda	Full impact evaluation findings published. Policy working paper disseminated with clear recommendations on future GBV prevention programming in Rwanda	This target should have been altered to reflect the endline schedule and knowledge of the NISR approval process (see point 32 below). / Publication of qualitative and process findings has been ongoing over the life of the programme, with 6 peer-reviewed journal articles to date, and 5 articles undergoing a review process. B

Key Points

Component	Details	Timing	Status/outputs
Qualitative – Beneficiary experience and Process Evaluation	Interviews with Couples, OL, CAs, WSF, WS Attendees, RWN staff, RWAMREC staff / 1 sector per province	Baseline, midline, endline	6 peer-reviewed journal articles to-date among other products (ongoing) / 4 practice briefs (couples, community activism, women’s safe spaces, opinion leaders)
Quantitative – couples cohort	N = 840 / Intervention villages	Baseline, midline (12 months), endline (24 months)	Pending NISR approval
Quantitative – Community surveys	N = 700 women, 700 men / 2 interview areas per intervention sector, each comprised of 2 adjacent villages; interviews with randomly selected married or cohabiting residents BUT excluding direct program beneficiaries	Baseline and Endline (24 months) only	Pending NISR approval
Control	Duplication of both quantitative components in non-intervention areas	Baseline, midline (for couples), endline	Pending NISR approval

Table 3: An Overview of the What Works Impact Evaluation Components

This Output scored a B (Outputs moderately did not meet expectation). The WW RCT is of exceptionally high quality and extremely rigorous and we believe it will improve the evidence base. However, at the time of writing, only the qualitative evidence has been published, and the quantitative is yet to be submitted to NISR for approval. This is not through fault of WW (which report to a different logframe), as outlined below.

The Output 4.2 target should have been altered in the January 2018 review of the logframe. In Rwanda, all quantitative data needs approval from the National Institute of Statistics (NISR) before it can be published and widely disseminated. Given the timing of the endline data collection (completed July 2018) and the need for analysis and the approval process, the target was unachievable. WW aims to complete the NISR approval process by the end of January 2019. MIGEPROF agreed at the Validation Workshop in October 2018 to facilitate submission of the final report to NISR. Once NISR approval is achieved, WW will publish and disseminate all quantitative data in accordance with their programme requirements.

An RCT with both quantitative and qualitative components has been extremely valuable in not only understanding what works but also why and for whom. Qualitative data has been analysed and published throughout the life of the programme and presented at a number of global conferences. Qualitative findings and recommendations from the beneficiaries and process evaluation were regularly considered during workshops with implementing partners, resulting in adaptations to address challenges and improve the Indashyikirwa intervention, including the curricula.

Integration with WW was seen by some to preference RCT evaluation findings over evidence coming out of regular programme monitoring. However, both aspects were complementary, and critical to the successful implementation of, assessment and future replicability of Indashyikirwa. Ongoing monitoring contributed to learning and adaptation in real time, was vital for annual reporting, and was less expensive. The RCT contributed to DFID’s aim of improving the global academic evidence base on GBV interventions (for which programme monitoring would be insufficient), and to which DFID (and other development partners) will turn when designing future interventions.

The validation workshop strongly recommended that a joint impact evaluation report (covering both quantitative and qualitative data) be produced for use by MIGEPROF and other stakeholders. WW has agreed to support this.

A separate impact evaluation of the Indashyikirwa II programme is ongoing. The WW team worked closely with the World Bank on the design of that evaluation, to build-in lessons already being learned through (our) original Indashyikirwa. The impact evaluations were designed to use different research protocols (and findings are therefore incomparable). There is both a risk and opportunity here: two evaluations may inadvertently lead to stakeholders drawing contradictory conclusions about the effectiveness of different versions of the intervention, while also presenting valuable learning opportunities for the field of GBV prevention. (See recommendation A, B)

Lessons

The strong relationship between WW and implementing partners was key to the adaptive, learning approach which strengthened the intervention and outcomes for beneficiaries during the life of the programme. Up-front time is required to bring implementing partners on board to work in parallel with an experimental impact evaluation. While partners were involved in design discussions, extra time was required to explain the sampling approach (randomised rather than targeted etc.), as well as how to understand/interpret findings. Capacity building from the WW team with implementing partners was substantial and critical - more than 30 workshops covering randomization, principles of qualitative and quantitative research, research analysis, research uptake and writing skills. Much of this was made possible by having a WW member residing in Rwanda for 2.5 years. Programme partners were invited to join the virtual community of practice meetings hosted by the WW Secretariat, and to attend the annual scientific meetings. Some partners co-authored papers; their first time publishing in peer reviewed journals. (See Recommendation C).

There is an opportunity for DFID to learn from Indashyikirwa as it continues to use this model (of a centrally-funded RCT and country-office led programme). Specific lessons include the need for: in-country capacity building, country-specific resources for building relationships and interest in the evidence with government stakeholders early on (not only research departments), and country-level dissemination and uptake strategy implementation. We should not assume that because DFID strongly values this type of evidence, national governments will also consider it important. Experience from Indashyikirwa can also inform thinking about the sustainability of pilot research interventions such as Indashyikirwa, which was designed as much to serve the purposes of WW as it was to deliver in practice.(See Recommendation C)

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall Assessment of Outcomes and Contribution to Impact

“…before I was a slave in my own home. My husband was always drunk and violent. Thanks to home visits by community activists many things have changed for good (…) Today, I enjoy life with my husband and our two children. Children go to school. We are like any other happy couple” (Kanama, 27 September, 2018).

The impact statement for the programme is: Women and children enjoy their human rights and live free of gender-based violence. This was to be judged by two indicators to be drawn from the Demographic and Health Survey (DHS) - (i) the prevalence of physical and sexual violence against women and (ii) women's decision-making power in the household (for intervention districts). The next DHS will take place in 2019/20 and there is therefore not any data available yet to speak to these indicators. This was missed in the logframe review in January 2018. As the assessment below indicates, evidence so far suggests that the programme Theory of Change remains valid and the outcome has been achieved for female and male direct beneficiaries. Whether this will make a significant contribution to the experience of violence and the enjoyment of rights by women and children on a larger, national scale remains in doubt.

While we are not able to report the numerical impact evaluation findings here to avoid pre-empting the official approval and dissemination process, we are confident that the outcome - reduced prevalence of GBV and strengthened community-level mechanisms for the prevention of violence against women, girls and boys in programme sectors - has been achieved. The full results of the evaluation will be accessible at https://www.whatworks.co.za/ once approved.

Outcome - Reduced prevalence of GBV and strengthened community-level mechanisms for the prevention of violence against women, girls and boys in programme sectors
Outcome Indicator	Target (Aug 2018)	Progress
Outcome 1.1 Indirect beneficiaries of the programme taking action to promote gender equality action and challenging harmful social norms of GBV.	Taking Action is: / #Spoken with someone about IPV = 93% / #Offered emotional support: 85% / # Attempted to intervene: 98% / #Encouraged victim to seek help: 85%	The WW quantitative evaluation did not demonstrate ‘diffusion’ - reduced prevalence of GBV resulting from social norm change among the wider community due to Indashyikirwa. / However, there is an enormous amount of qualitative testimony from both Indashyikirwa (see examples below) and IzU components which indicates that the programme has had a meaningful effect on indirect beneficiaries, particularly those that were closest to the programme participants. / 759,755 indirect beneficiaries were reached by Indashyikirwa. CAs reached 586,962 (344,918 women – including 193 with disabilities; 242,044 men - including 49 with disabilities); WSF reached 173,035.
Outcome 1.2 Reduction in prevalence in the past 12 months of women and men’s experiences of physical and/or sexual IPV with their current partner in intervention communities	Women from Couples’ Cohort – 30% / Women from Community Sample – 45%	The quantitative evaluation findings among the couples cohort point to significant reductions in physical, sexual, emotional and economic IPV among couples in the couple’s cohort. These reductions are among the best achieved by similar programmes in different contexts. / See below for qualitative information.
Outcome 1.3 Reduction in financial abuse, and strengthened economic rights among women in intervention communities	Women who have experienced financial abuse among: / Couples’ Cohort – 20% / Women from Community Sample – 30%	Among the couples cohort, economic abuse by male partners (defined as taking women’s money, preventing their partner from working, or squandering household money on alcohol or other non-essentials) also decreased. This is complemented by reduced food insecurity. Qualitative findings suggest that improved household economic status, in part due to improved/shared financial decision making, was one of the most significant spill-over effects for participants.
Outcome 1.4 Reduction in acceptability, and prevalence of violence against children in intervention communities	i) Importance of physical discipline in raising a well-behaved and moral child – 55.2% (baseline 65.2%) / ii) Parents who ‘sometimes’ punish children by smacking or beating them in the past 12 months – 59.8% (baseline 69.8%)	Among the couples cohort, both men and women reported significant decreases in their endorsement of corporal punishment or physical discipline in raising children, reduction of frequency of smacking or beating children in the home, and reduction in mother’s reporting of children witnessing violence in the home.
Outcome 1.5 Sustainability of programme activities and results maintained through Government and civil society taking increased responsibility in the GBV prevention and response space at national, local and community levels.	Government of Rwanda/MIGEPROF have a clear vision for further work on GBV in the medium term	See discussion below on / ‘Alignment and integration with GoR commitments and approach to GBV’ and / Sustainability concerns.

Table 4: Outcome Assessment

Programme Achievements and Outcomes

Preliminary findings from the WW impact evaluation of Indashyikirwa are exciting. They are considered by the experts involved in WW to represent the ‘gold standard’ among similar studies. They show a significant reduction in the experience of severe IPV among women and in the perpetration of severe IPV among men. Women who participated in the couple’s cohort also reported significant reductions in the experience of any physical IPV, economic abuse, and any emotional aggression. Male participants reported reductions in perpetration of any sexual IPV.

These findings have been reinforced and triangulated by various other sources - including the qualitative data, beneficiary and participant testimonials, individual stories of change, and regular programme monitoring and reporting, including through field visits. The findings also correlate to the self-reported reduction in cases received by WSs and CAs, as well as emerging similar trends in communities in which Izu are operating effectively.

The impact evaluation also identified helpful ‘risk and protective factors’ that can frame future programming decisions. These include:
- Food security, lack of debt, and improved household economic status are associated with less IPV; economic development is important to help prevent violence in families.
- Women’s economic empowerment is critical for preventing IPV, but needs to be accompanied by changing men’s attitudes towards women earning money. Encouraging a partnership model within couples can help both men and women recognize the value of women’s economic contributions, and joint economic decision-making.
- Men’s alcohol use is strongly associated with violence, particularly when men drink frequently and to excess. There is a need to encourage men to use alcohol responsibly, and challenge any idea that drunkenness is an excuse for violent behaviour.
- Women who experience violence in childhood or in the community are more vulnerable to IPV. All violence prevention is important, as preventing violence now and ensuring that survivors receive adequate support will help prevent additional violence later on.
- Witnessing IPV as a child leads to more IPV in adulthood, especially for boys. Preventing IPV now can help protect future generations.

Though yet to be evaluated, the awareness of GBV, legal rights and referral pathways has anecdotally improved as a result of the work done by IzU. IzU proximity to and familiarity with the people they support has significantly contributed to this increased awareness, both among adults and children themselves. As noted above, Indashyikirwa has also led to significant reductions in couples’ endorsement of physical discipline in raising children, frequency of smacking or beating children in the home, and mother’s reporting of children witnessing violence in the home. These results are particularly valuable given the risk factors identified above.

Other outcomes include:

- Significant improvements on all measures of relationship quality, including reduction in conflict and increase in trust;
  [note] Qualitative research indicates that the skills building sessions and the use of take-home exercises helped couples apply and practice new relationships skills. Participants reported improved dialogue and noticeable changes to how couples sit, eat and work together as well as improvements in sexual relationships including an increase in sexual pleasure for both women and men
- Increased cash income, decreased household food insecurity and decreased hunger. As a result of these changes, families gave examples of children being able to attend school, health insurance being covered, and increases in livestock and household equipment;
  [note] Couples reported changes in behaviour including increased joint decision-making around family income and assets, shared responsibilities for income-generation for the family, and a reduction of expenditure on alcohol. Women participants attest to now having the self-confidence and their partner’s backing to take up new income-generating activities.
- Qualitative evidence indicates an increase in participants engaging in public activities, including local-level decision-making and political processes, more formal responsibilities in their communities and roles in local government structures;
- Interviews with local officials suggest that imihigo rankings (and therefore local governance) have improved in sectors where Indashyikirwa is operating. For example, the Kanama Executive Secretary stated that “Kanama is now the best sector in Rubavu. Kanama and Nyamyumba used to be the worst sectors (out of 12). Today, all the other sectors come to learn from Kanama.”
  [note] Officials indicate that Indashyikirwa has reduced GBV cases and supported existing systems to perform better, allowing district and sector officials to concentrate on other development priorities; while the programme also helps the sector to meet family welfare and parent evening imihigo targets. It is impossible to prove any causal relationship, particularly as sector rankings are not publically shared each year.

Limitations and Challenges

While the WW quantitative community surveys were unable to prove conclusively that the intervention reduced prevalence of GBV among the wider community, the qualitative data indicates that community level change was in progress/emerging, for example in the (abridged) case studies below:

Person with disability - visited the WS

“People bullied me because of my arm. I used to think: ‘Why am I even living?’ I found comfort and solace at the women’s space, as it was a place that accepted everyone. The space is doing activities to incorporate people with disabilities. Every time I go to the space I learn something new. The women’s space opened up space for my husband and I to talk more, and I felt finally free to have more discussions with him. I spoke to another person with a disability in both legs, and she faced so many issues. One of them was rejection. We shared experiences, and I encouraged her to come with me to the women’s space.”
Couple A - reached through a CA home visit

Wife:
“He was an alcoholic at that time, I kept quiet to save my life. After they came to our house we decided to join the different activities, not just to learn, but to share our testimony with others. I want to teach (my children) about mutual respect so that when they are older, they can take these values to their own families.”

Husband:
“When I think about what my wife is saying, it’s a scary thought that I had gone that far. I also have a feeling of relief that I’m not in that kind of life anymore. Our children weren’t in school at that time, as I spent all of the money on alcohol. When I had a change of heart I decided to put them in school. From the little we get (money) from small things we are doing, we decide together what to do with it.”
We cannot conclusively say why the evaluation did not show a diffusion effect of indashyikirwa, however the three most likely justifications to consider are:

- The duration of the intervention (only 18 months of activism, and less than 6 months of concerted activism). In contrast, the SASA! model which Indashyikirwa was based on was implemented intensively over 4 years in 8 high-density neighbourhoods in Kampala. The Indashyikirwa design was therefore ambitious from the start. This premise would suggest that with more time, Indashyikirwa would have shown diffusion, and is supported by the qualitative evidence above.
- The test for community level change set up by the WW RCT was very stringent and may have under-reported some impact. This premise would suggest that with a different test, Indashyikirwa may have shown more impact at community level.
- Alternatively, the Indashyikirwa community-level intervention may have simply been ineffective and would therefore not have shown impact at community level with more time.

Unpacking the couple’s stipend - Improvements in living standards are undoubtedly affected by the stipend given to participants in the Indashyikirwa couples curriculum during the curricula period. Participants were given Rwfs 2,000 per session each (~Rwfs 32,000 per household per month). The stipend will have had a significant impact on household’s ability to engage in economic activities, save and buy new assets, effectively functioning as a cash transfer. As participants were targeted through Village Savings and Loan Associations (VSLAs), and therefore were in the two lowest national wealth quintiles, the stipend may have been in addition to other forms of social protection. Conversations with both partners and beneficiaries indicate that some couples made investments from these stipends, which were then used to address other family needs, such as small livestock, household equipment, and food and health insurance. Further analysis would be needed to be able to make any conclusions on the effects of these stipends - in comparison to the behaviour change elements of the programme - on improvements in living standards.
[note] In rural areas sources of income are very limited and the average monthly household income is Rwfs 29, 600

Sustainability - Indashyikirwa, in order to meet the requirements of an RCT, was designed to ensure the programme would be implemented exactly the same across intervention locations, and therefore created its own entry points which were within the control of implementing partners – for example using the VSLAs and WS. While this had obvious successes, the programme itself was complex, and for a Low Income Country Government, expensive. Rwanda is a particularly strong context for community interventions, and future programming could use existing (and more sustainable) mechanisms that are already functional in all villages, including the new Amasibo (sub-village cluster) or Ibimina (savings groups not facilitated by CSOs). Preliminary discussions on how best the model could be adapted by GoR have begun, however with DFID not currently committed to support a second phase of this pilot, the immediate sustainability of outcomes in Rwanda is in question, and DFIDR’s ability to influence is limited.

Inclusion opportunities missed - Indashyikirwa targeted marital/cohabiting households in the poorest two income quintiles in Rwanda (Ubudehe 1 and 2) and Districts with higher than average prevalence of GBV (DHS data). This inevitably excluded some younger people, particularly adolescents Implementing partners increased efforts to include young people and people with disabilities in the final year of implementation, including through staff training with the National Council for People with Disabilities (NCPD). However, opportunities had already been lost to more meaningfully include these groups. The WW qualitative evidence specifically included a small study on disabled beneficiaries. While this is identified as a limitation, it is also an example of the way Indashyikirwa learned and adapted throughout its lifetime. The national anti-GBV policy identifies (in addition to people living with disability) children living in child headed-households, and children born out of rape, among groups at high risk of GBV. While IzU work directly with vulnerable children, it is possible that more (sensitive) targeting could accelerate support for these children in line with the policy.
[note] 18-25 year olds represented a small proportion of enrolees in the couple’s cohort. There was no differential outcome based on age for younger participants compared to older participants in the WW data

Summarise the programme’s Theory of Change and Any Major Changes to it in the past year

The programme has two Theories of Change - one for the overall programme (ToC - found in the Business Case) and the Indashyikirwa ‘Pathways of Change’ (PoC) model. Both have remained the same for the majority of the programme. Points to note on the ToC include:

- It includes all the different components of both Indashyikirwa and Inshuti z’Umuryango and links are made between them but in reality the links were not easy to establish and the components remained quite distinct;
- It does not really locate the programme within the Rwandan political and policy context though this is evident from decisions made in design and inception phases. The decision to create Indashyikirwa-controlled entry points shaped the role for GoR as a stakeholder and the extent to which integration with GoR-led mechanisms was possible. As noted above, future iterations of Indashyikirwa could take advantage of existing state structures; and
- As discussed above, the timeframe for the programme was ambitious and while social norm change is part of the ToC in practice there was insufficient time for this to be realised.

Explain any Major Changes to the Log-frame in the Past Year

The programme substantially revised the logframe in May 2017 and some minor changes to 2018 targets were made in January 2018. As noted above, this PCR has noted minor issues in the logframe – especially around targets set for the end of programme which were missed in the January revision – but they have not impacted on the overall ability to report against the logframe.

## D: VALUE FOR MONEY

Assess VfM Compared to the Proposition in the Business Case

The original budget for the Indashyikirwa programme was £3,983,099. The budget was revised in the third quarter of 2017 and increased by £67,546. It was agreed during the inception phase of the programme that the budget would increase to cover additional costs related to complying with the WW RCT, to be disbursed if/when funding was required. The revised total budget was £4,050,645. Additional funding of £32,268 was made available to UNICEF by DFID Rwanda in July 2018, increasing the total budget for Inshuti z’Umuryango to £464,268.

Overall, the programme has performed well against logframe indicators, with targets achieved and in some cases exceeded, including numbers of beneficiaries (see below).Value for Money has been considered throughout the life of the programme, and achievements outlined throughout this report are of considerable value - both material and immaterial. Many outcomes are long-term and meaningful in a way that is difficult to capture quantitatively - such as a new lease on life free from violence, and future generations freed from violence.

Indashyikirwa was designed to be gold standard; putting all the best evidence into practice. This undeniably achieved very good results - and potentially could have achieved even more with more time to run. Anti-Gender-Based Violence programming is not, by nature, low-cost. However even among its WW peers and other similar interventions, the total costs of Indashyikirwa are considerably higher. This can be explained by the fact that Indashyikirwa was rolled out across a larger geographic scale, implementation activities lasted for longer, and activities delivered were multiple and complex. Collaboration with the WW programme enabled rigorous research findings at little to no cost to programme implementation.

As part of WW, an economic evaluation of Indashyikirwa was conducted by the London School of Hygiene & Tropical Medicine (LSHTM). The economic evaluation follows DFID’s VfM framework, as well as rigorous international costing standards, and is part of a five-country research project to determine cost-effectiveness of five different violence prevention strategies. Findings are yet to be completed. Measures of cost-effectiveness (e.g. cost per case of violence averted) that are comparable across interventions are being calculated and will be extremely valuable to DFID, programme partners, and for the global evidence base.

In contrast to Indashyikirwa, the Inshuti z’Umuryango, as a programme of volunteers, has so far been a (very) low-cost approach to providing a national child protection system/workforce. The model is similar to that of Community Health Workers, which is common in many low income countries, but is particularly effective here in Rwanda due to the cultural norm of volunteerism. However, there are economic – often hidden - costs associated with volunteering which should be adequately considered by donors or programme partners when assessing the financial ‘cost’ of an intervention. As a national programme, A costing and cost-effectiveness study of the Izu programme is planned as part of the formative evaluation in early 2019 (not using DFID Rwanda funding).

Economy

Both Indashyikirwa and IzU had spent over 99% of their allocated budget. Key cost drivers for Indashyikirwa were direct staff costs (42%) and training costs, job materials and capacity building (27%). For IzU, direct programme costs, including capacity development, training costs, and job aid materials accounted for more than 90% of the total cost.

Indashyikirwa’s financial management improved throughout the programme enabling budget execution and cost-savings. Examples include:

- Salary structures have remained benchmarked to similar programmes in Rwanda;
- Procurement has been undertaken economically with regular assessment of contracts, and pipeline proposals to ensure all procurement is delivering the good VfM. Planned procurements, including consultancies, which did not represent VfM, were cancelled;
- Management costs (7%) are below the expectation in the original Business Case for civil society support programmes (which average 16-18% regionally). The costs are within DFID’s policy and in line with similar programmes with CARE Rwanda, however less than CARE International UK (CIUK) policy (11.1%); and
- Proposed activities have been monitored and adapted to ensure better VfM. For example, the purchase of assets, including loudspeakers for activism in the final year of the programme was cancelled and the funds allocated instead to additional training and outreach activities.

Efficiency

Table 5 below reflects costs per Indashyikirwa beneficiary across different categories types of activity based on utilization of the DFID budget. However, preliminary alternatives have been shared by the LSHTM study: cost per couple trained was estimated at $84, the cost per community activism session delivered at $17 and the cost per person reached by at least one community activist session at $0.60. These figures are lower than those considered by DFID’s budget. They exclude all research costs and other costs not directly relevant to the development and delivery of the intervention. They also account for non-financial costs, namely volunteer time use as well as any donated of subsidised goods. Importantly, these costs also annuatise all start-up costs (i.e. costs incurred in developing, adapting and setting up the intervention) and apportion them across a number of expected useful years of the programme.

Costs/Types of Beneficiary	Opinion leaders	Women’s Space Facilitators	Community activists	Couples Cohorts	Community Members
Total beneficiaries reached	950	300	500	1680	759,755
Total cost (£) / Total costs include specific activities & associated partners’ costs (Staff and operational)	303,129.13	824,708.2	963,370.84	588,853.92	4,029,836.78
Cost per beneficiary reached (£)	319.08	2749.02	1924.74	350.51	5.30

Table 5: Indashyikirwa costs/beneficiary

Effectiveness

Beneficiaries/Numbers Reached	Expected Numbers to Reach	Actual Numbers Reached (August 2018)	Variance
Opinion leaders	600	950	+ 350
Women’s Space Facilitators	300	300	-
Individuals reached through WS and WSF outreach	22,890	173,035	+ 150,145
Girl Champions		280	+ 280
Women receiving counselling and support from Women’s Space	1,200	1,932	+ 732
Individuals in Couples Cohort (including Community Activists)	1680 / 420 CAs	1680 / 500 CAs	- / + 80
Community Members reached by CAs	585,553	586,720	+ 1,167
Operational IzU*	10,000	10,186 / (12,990 - Dec 2018)	+ 2,990
Children reached by IzU	46,056	85,104	+ 39,048
Local Leaders trained on child protection/IzU	0	13,499	+ 13,499
Total	668,279	876,490	+ 208,211

Table 6: Number of targeted beneficiaries reached (planned vs actual) from 2014-18
* In the original design, the IzU programme was planned to be a pilot reaching only 4,200 child protection volunteers. The decision to take the programme to scale immediately means that while not all fully operational, 29,674 child protection volunteers have been identified/reached. Using these figures, the total number of beneficiaries reached beyond target is 230,695.

Equity

This programme fundamentally works to improve equitable opportunities and outcomes through preventing violence and working towards gender equality. This foundation was built upon during the final year when Indashyikirwa stepped-up its work to ensure greater inclusion of vulnerable individuals, including youth and people with disabilities.

E: RISK

Overview of Programme Risk (risk rating MODERATE)

Key risks over the programme lifetime included:

Fiduciary - The 2017 audit identified that partners in some regards had insufficient capacity and systems to manage the risk of corruption and fraud in the programme, which were addressed through capacity building plans. This flags a wider concern about the ability of DFID’s internal due diligence processes conducted in advance of contracting organisations to effectively identify and/or document weaknesses in downstream partners’ ability to deliver the programme.

Delivery - throughout the programme, participants shared experience of regression (falling back into conflict), backlash, and resistance among the wider community. This, however, did not appear to have a detrimental or deterrent effect on participants (at 24 months/endline, retention among the couples cohort was more than 98%). The group dynamic of the curriculum appeared to be a mitigating factor, as did the very real benefits which participants saw sufficiently early on in the programme.

Operational - The programme experienced start up delays which had a knock-on effect on operational timelines. Indashyikirwa had an extended inception phase of one year due to the adaptation of the SASA! model. The IzU programme started after a 9 month delay due to a GoR decision to review the IzU Standard Operating Procedures. This then led to a seven-month delay in the roll-out of the programme. High turnover, especially in Local Government and other trained OL resulted in additional costs for Indashyikirwa. In addition, turnover in DFID Rwanda staff led to delays in approvals and gaps in consistency and oversight of the programme.

Reputational - Indashyikirwa II was at first seen as an opportunity to bring additional resources into Indashyikirwa and expand the original programme. However, in reality they became parallel programmes, albeit with the same implementing partners. This raised concerns over (i) the capacity of partners to deliver both adequately, (ii) the risk that the programmes would be seen as the same when, in effect, they were substantively different and (iii) the two separate impact evaluations would be compared, when they are by design incomparable. DFIDR invested a lot of time working with partners to raise and address these concerns. Further effort may be required as evidence emerges from both evaluations.

Safeguarding - Safeguarding to prevent harm, exploitation, abuse or increased violence against implementing staff and participants, but especially for vulnerable women, girls and children was a constant risk. This was of particular concern for the IzU programme which placed already vulnerable children into increased contact with volunteers. Discussions were held with all programme partners, particularly in the last 12 months of the programme as DFID’s expectations around safeguarding changed.

Context - Dissemination of the impact evaluation findings will occur outside of the Indashyikirwa programme life-span, reducing DFIDR’s ability to support evidence uptake.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of Partners and DFID (notably on Commercial and Financial Issues)

Quality of Programme Management

The programme was delivered by highly motivated and committed staff in all consortium organisations. A shared commitment to the objectives of the programme ensured potential programmatic issues were resolved to enable the programme to move forward. However, the quality of programme management was inconsistent, improving later in the programme. The extended inception phase (1 year) allowed for systems and procedures to be put in place but these did not always work effectively, particularly downstream partner internal finance and HR systems, policies and processes.

There was a significant delay in conducting an audit on the programme (in part as a result of DFID staff turn-over) but a thorough audit was commissioned in early 2017 (covering the first 3 years of the programme). Although the audit did not identify any fraud, it did highlight important weaknesses in programme management systems in all consortium partners. As a result of the audit findings, capacity building plans for all partners were put in place and closely monitored in the remaining 18 months (see below for details).

CIUK held overall responsibility for delivering the programme as the signatory and lead consortium partner in the Accountable Grant with DFID. CARE Rwanda was responsible for the day-to-day delivery and management of the programme, and was the intermediary between CIUK, DFID and downstream partners. Confidence in the intervention delivery was consistently high. DFID often facilitated communication around financial management and forecasting, and occasionally acted as an intermediary between consortium partners.

The main accountability mechanism established for the programme was the Programme Advisory Committee (PAC) which, brought together all partners in the programme including UNICEF and MIGEPROF. The World Bank joined PAC meetings when Indashyikirwa II commenced. These biannual meetings were a useful forum for information sharing, but largely operational, with limited strategic or policy discussion. DFID staff were highly engaged in the programme particularly in the last 18 months and were readily available to respond to amendments to activity planning and budget adjustments.

UNICEF provided consistently strong programme management. They worked closely with Save the Children and NCC to establish implementation procedures, monitored using UNICEF’s standard monitoring and reporting templates. UNICEF participated in the PAC and Indashyikirwa Quarterly meetings and welcomed opportunities to build synergies between the two components. As per the strategic partnership agreement, DFID does not audit UNICEF country programmes. UNICEF Rwanda was most recently audited by their Office of Internal Audit and Investigations in October 2016, for the period covering January 2015 – October 2016. The report was finalised in July 2017, identifying 8 actions for follow up, including some related to procurement and capacity building. All were completed as at March 2018.

Quality of Financial Management

CIUK used its established financial management systems to manage the programme. Annual Budgets were discussed with partners and DFIDR and were linked to work plans. Financial reports were included in quarterly and annual reporting requirements. A number of challenges in the financial management of the programme were flagged in the (unqualified) 2017 audit report. These related to financial management and accounting systems gaps in the consortium organisations and in relation to forecasting and managing variances between budget/expenditure across the programme. There were persistent issues with managing procurement timetables leading to payment delays. An ongoing challenge for DFIDR staff was the complex financial reports/budgets submitted by CIUK, which while thorough, did not easily communicate the information most needed. Inconsistency in DFIDR staff exacerbated programme and financial management issues, but improving financial management became a priority for the final 18 months of the programme when a consistent SRO and PM were in place. Assets were adequately managed throughout the programme. A final comprehensive asset register was submitted at the end of the programme and all assets have been disposed/returned as agreed.

Financing for the IzU component was channelled through DFID’s MoU with UNICEF. UNICEF received two payments per year of £54,000 each, with a costed amendment to the MoU in the final year of the programme adding £32,268 for procurement of additional materials and toolkits for operational Izu. UNICEF demonstrated reliable financial management based on their established processes and financial management principles, and submitted detailed narrative and financial reports as part of their regular reporting requirements.

Quality of Partnerships

A lack of clarity around roles and responsibilities and resource allocation for Indashyikirwa partners was an early challenge for the consortium, however, relationships between the consortium members strengthened throughout the programme. Much of this was the result of (and perhaps dependent on) trusted and highly motivated individuals. Issues have occasionally emerged between organisations but the consortium has worked to resolve these.

Partnership with the GoR has varied over the life of the programme. MIGEPROF has consistently engaged in PAC meetings, and built stronger relationships with consortium members through Indashyikirwa II. Partnership with Local Government authorities strengthened over the course of the programme.

Collaboration between the Indashyikirwa consortium and IzU partners has been good, including at the local level, even if not a natural fit. These components were developed separately and are largely distinct. The inclusion of both in one business case may have been a decision based on expediency rather than programme quality – but initial implementation delays did not help in establishing, from the beginning, coordination and collaboration mechanisms between both components.

All partners reported a good relationship with DFIDR. In particular, Indashyikirwa partners congratulated staff members who had facilitated early discussions and supported the design and preparatory work. Similarly, there was acknowledgement of the dedicated input and support over the past 18 months to drive forward strong programme management, capacity building and sustainability plans.

Capacity Development

Before the 2017 audit of the programme, there had been little attention given to capacity development within the consortium and CIUK, as an international NGO, had not provided the explicit and dedicated capacity support to the two downstream partners as expected. As a result of findings from the 2017 audit, capacity building plans were developed and implemented. Capacity building was funded through cost savings identified by partners from the programme, and included training for all partners (including field staff) on:

- financial management, accounting and fraud (including some conducted by DFID);
- procurement;
- programme and risk management;
- safeguarding and leave no one behind;
- exit planning training (conducted by DFID)

Date of last narrative financial report	12 October 2018
Date of last audited annual statement	Audit to be completed by January 2019

G: MONITORING, EVIDENCE & LEARNING

Monitoring
Over the course of the programme, monitoring has been conducted on a monthly and quarterly basis by the Senior Responsible Owner (SRO) and Programme Manager to track work plans, results and budgets. DFIDR and CARE Rwanda had monthly programme management meetings to discuss e.g. implementation issues, finances, changes to activities, etc. The Indashyikirwa consortium submitted quarterly reports that were discussed at quarterly review meetings, while UNICEF met quarterly with DFIDR and submitted biannual reports. DFIDR conducted field visits every four months and annual reviews, which built on the on-going monitoring meetings and partner engagement. PAC meetings provided an opportunity for monitoring and reporting oversight, though largely functioned as a mechanism to connect with MIGEPROF. although, as mentioned above, this forum did not thoroughly scrutinise the programme or challenge programme management or implementation decisions.

Indashyikirwa invested in the development of a Monitoring and Information System, which was never utilised, due to protracted issues with procurement, technical expertise, and a product that was not fit for purpose. After assessing VfM in the 2017 AR, DFIDR chose not to approve further investment in improving the system, and instead the basic paper and excel-based reporting tools were used for the life of the programme. IzU have reported that the standardised paper reporting tools they are using are not fit-for-purpose, and lead to the loss of valuable information. UNICEF and NCC have agreed to improve the templates.

Evidence and Learning

Lessons learned through the programme - for both Indashyikirwa and IzU - are spread through this report.

WW aims to complete data analysis and finalisation of research reports by January 2019, with plans to publish the evidence in line with the remaining timeframe of the WW programme, which ends in Sept 2019. To date, the qualitative evaluation research has been presented at over 7 national and international conferences including the Communities of Practice for Girls in Rwanda in March 2016, the Re-thinking Gender Conference in September 2016, the Global Status of Women and Girls Conference in Virginia in March 2017, the STRIVE learning lab in April 2017, the Men and Masculinities conference in Sweden in July 2017, the SVRI Forum in Brazil in September 2017, and the Savings Group Conference in Kigali in May 2018. These findings will next be shared at the International Domestic Violence and Health Conference in Melbourne in November 2018 and the 2019 SVRI conference in Cape Town, South Africa. Plans for dissemination of evidence in Rwanda are currently lacking, falling between the gaps (in planning, timing, and funding) of the centrally-managed and country programmes. (See Recommendation C).

A UNICEF-funded formative evaluation of the IzU programme will commence in 2019, generating more robust evidence including on the cost-effectiveness of the system. Plans for a national child protection database and case management system have been developed, though work on this has not yet begun.

Progress on Recommendations from Annual Reviews for this Programme

2017 Annual Review (AR) recommendations and updates included:

- Better coordination of the consortium partners, between components, and at the implementation level - the PCR noted more regular meetings, including the PAC, with on-the-ground outcomes. DFIDR played a key role to facilitate the strengthening of these partnerships.
- More systematic collection, analysis and sharing of evidence of policy and/or practice change by local authorities as a result of activism - the focus of this was on changes to Imihigo, however partners struggled to dedicate time to this and outcomes of advocacy/activism were often hard to pin down.
- Finalise and implement capacity building plans, and ensure programme management best practice standards are met for the remaining year - as mentioned above, this was prioritised; progress will be verified in the forthcoming programme completion audit.
- Expedite conversations with MIGEPROF and other government stakeholders to reach an agreement for the baseline data to be published. This issue is currently under consideration, but signs are positive - the baseline was combined with the endline impact evaluation findings and validated in a workshop held on October 02-03, 2018 with the support of MIGEPROF and MIGEPROF has agreed to facilitate the submission of the report to NISR for approval, before the findings can be published.
- Ensure the inclusion of participants and beneficiaries with disabilities, including by monitoring and more systematic disaggregation of data - significant efforts to include disabled beneficiaries were made, however data is incomplete.

This Programme Completion Review was led by two DFIDR Social Development Advisors, the DFIDR Programme Manager and in collaboration with two national consultants. The review process included meetings with the DFIDR programme team, all partners, two field visits to Rubavu and Kirehe districts (including meetings with beneficiaries and programme implementers), and a WW impact evaluation validation workshop with GoR.