Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Improving Security and Access to Justice in the Occupied Palestinian Territories
Programme Value: Up to £10.8m		Review Date: 15 April 2017
Programme Code: 204797	Start Date: 1/4/2015	End Date: 31/3/2018

Summary of Programme Performance
Year	2016	2017
Programme Score	A	A+
Risk Rating	Severe	Major

Summary of progress and lessons learnt since last review
The support to the Ministry of Interior has “been highly successful: it has achieved results which are widely seen as impressive. The most visible result is the official endorsement of (so far) five sets of Standard Operating Procedures for the Ministry of Interior and the related security agencies in the Palestinian Authority”.[1]
[1] January 2017 Mid-Term Strategic Review of Ministry of Interior component.

The support to the Rule of Law through UNDP/UNWomen “has notable strengths…as a combined UNDP/UNWomen programme…its mixed portfolio that is based on the logic of simultaneously strengthening supply of, and demand for justice…and its broad portfolio and joint UN ownership/expertise”.[2] The 2015 review of the programme, found that it has remained ‘highly relevant to the overall stated development goals of the PA and to the rights, safety and security of Palestinian citizens’, and its implementation is ‘well on track and making an impact’.[3]
[2] December 2016 independent paper produced by Clingendael Institute on the Joint Programme’s Theory of Change.
[3] May 2015 Mid-Term Strategic Review of Joint Programme component.

Summary of recommendations for the next year
	Recommendation
1	The overall Risk should rating be reduced from Severe to Major; this is to reflect the current positive direction of the Ministry of Interior (MOI) component and reduced level of activities within the overall programme. This also includes revising down the risk of the MOI component (output 1) from Severe to Major.
2	The programme officer to follow up on key recommendations made by the Mid-Term Strategic Review of the Ministry of Interior Component; through the implementation of the action plans developed for Year 3.
3	The programme officer and Senior Responsible Officer to consider adding training output indicator to reflect recommendation regarding increased focus on skills-oriented training made by Mid-Term Strategic Review [MTSR Quest ref: 5703127] by June 2017.
4	The programme officer and SRO to consider amending the weightings in the Logframe by June 2017 to place more emphasis on the Ministry of Interior (MOI) component that will continue until March 2018.
5	The programme officer should update results on indicator 2.2 to reflect progress against the anticorruption strategy once the independent review has been finalised.
6	Programme Officer to update results on indicator 4.3 once final results of surveys are completed.
7	As support to the Joint Programme ends in April 2017, it is recommended that follow up continue with Joint Programme partners on the final evaluation of the Joint Programme, reflecting relevant updates to the results within the next review.
8	The programme officer to explore outcome indicator 1.1 results implications ahead of the completion review.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204797/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204797/documents

The context: conflict and fragility
The development context in the OPTs is characterised by long-running conflict and fragility. Public trust in institutions and in the Palestinian political establishment risks being eroded by the ongoing Occupation and the lack of progress on the Middle East Peace Process (MEPP). Palestinians face the possibility of further fragmentation of territory, politics, power, government structures, business, economy, civil society and communities.

Why is UK support required?
This intervention is part of the UK Government’s ongoing investment in Palestinian state building, helping to contribute to the prospects for a negotiated two state solution to the Israeli-Palestinian conflict. It builds on DFID’s strong partnership with the PA and its experience in the justice and security sector, where DFID has been a lead donor. Eliminating Violence against Women and Girls and promoting gender equality is a DFID priority. This programme has directly supported this aim.

The PA has made encouraging progress on improving the effectiveness of security and justice in recent years. According to a UNDP survey (2015) of the Palestinian justice and security sector, there was a 12.3% increase in Palestinian men and women who had contact with at least one Palestinian institution mandated to uphold the rule of law accessed these services since the last survey (2012). In addition, the number of Palestinian households that regard Palestinian security and justice institutions as legitimate, independent and effective has increased at an average rate from 2.8 (on a five-point scale) in 2012 to 3.2 in 2015.[4]
[4] Statistics taken from UNDP Public Perceptions of Palestinian Justice and Security Institutions 2015.

What are the main programme activities?
The UK is providing up to £10.8 million over three financial years (2015/16, 2016/17, and 2017/18) to support the development of capable, accountable and responsive security and justice services for citizens in the Occupied Palestinian Territories (OPTs). The primary focus of the programme will be the West Bank with some support in East Jerusalem and Gaza. This intervention will target both the ‘supply’ and ‘demand’ sides of security and justice services. Citizens will be empowered to access services and to hold authorities to account while the capability, accountability and responsiveness of the two key ministries (Ministry of Interior and Justice) will be strengthened to enable them to deliver more effective and efficient services.

The intervention has two components:
£5m contribution through DFID to a multi-donor programme implemented by the UN Development Programme (UNDP) and UN Women. This focuses on improving service delivery and capacity building of key justice and security institutions, including the Ministry of Justice (MOJ), the High Judicial Council (HJC), Attorney General’s Office (AGO), the Palestinian Civil Police (PCP) and a number of civil society organisations (CSOs), with a strong focus on improving women’s security and access to justice. This component ends in April 2017.

£5.8m for UNOPS through the Conflict Stability and Security Fund to deliver technical assistance to the Ministry of Interior (MOI) to improve its capability to provide oversight and management of the security services. This component ends in March 2018.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome statement is: The PA provides more capable, accountable and responsive security and justice services to its people, with a specific emphasis on women and girls.

Outcome	Baseline	2017 Milestone	Actual	Progress
1.1 Percent of judgments enforced by the Executions Department	21.8%	55%	51%	The target was not met. Although there has been an upward trend in terms of judged cases arriving at the enforcement department, the absolute number of enforced judgements has declined slightly. The main reason being that with an increased workload within the enforcement department, there has not been a parallel increase in the capacity within the department to deal with the extra workload (approximately 5150 extra cases in 2016 compared to 2015). How the results are linked directly to the programme, and their implication, should be further elaborated by the next review.
1.2 Improved organisation, management, and skills and attitude in the security sector	All of the target functional areas being supported are currently rated "Poor" on OCA framework	Each function area is rated as “okay” in another OCA metric	Target met.	The target was met. The Organizational Capability Assessment (OCA) is a measurement tool, using surveys, developed by our implementing partners (UNOPS) to assess the institutional capability to undertake specific functions. The three organizational capability metrics concerned are: Mandate, Governance & Strategy; Roles & Management Structures, Knowledge, Resource, Understanding, Skills and Attitudes. / The latest surveys confirm that there is an average improvement across the six targeted functional areas. “Okay” signifies that the six functions have been rated between (40%-70%) in the specified metric across all security entities, which in turn signals that they have reached a level of development in the respective organizational attribute that enables them to effectively perform their duties, exercise their authorities and be accountable, transparent, and subject to civilian oversight.

Overall output score and description
The overall output score is A + (outputs exceeded expectation).
	Output	Score	Weighting %
1	The MOI has the institutional and organisational structures, processes and capabilities to exert clear civilian oversight of state security institutions	A+	40%
2	Institutional and technical capacity of the Ministry of Justice , High Judicial Council , Attorney General’s Office and Anti-Corruption Commission Strengthened	A	25%
3	Accountable justice and security services to prevent, protect and respond to violence against women and girls	A+	25%
4	Civil society contribution to rule of law and community access to justice enhanced in areas outside of the PA's jurisdiction	A++	10%

Key lessons
      1. Conducting a Mid-Term Strategic Review (MTSR) for the Ministry of Interior component has proved essential in focusing the programme for its final year. The review, conducted in December/January 2017, highlighted local ownership as a major factor in the successful implementation of the programme so far. The review also emphasized that the third year is crucial to embedding these processes. Consequently, taking forward recommendations made by the MTSR will be key to successfully implementing the final year of the programme. [5]
        [5] The main recommendations point to prioritising work around Human Resources, Complaints management and Planning in addition to, strengthening governance arrangements of the programme, and focussing efforts on embedding the processes that have been developed throughout the first two years of the programme.

      1. The preliminary findings of the evaluation of the Joint Programme found that targeting both the supply and demand side of access to justice has been essential in the effectiveness of the programme, concluding that civil society cannot be supported without building effective state institutions. The initial recommendations of the evaluation also suggested that strengthened partnerships between stakeholders is essential to affecting change; highlighting the importance of institutionalising change processes within targeted institutions, whilst streamlining support to Civil Society Organisations in any future phase of the programme.

Key actions
Senior Responsible Owner and Project Officer:
- To reduce overall risk rating from Severe to Major including for output 1.
- To follow up on key recommendations made by the Mid-Term Strategic Review of the Ministry of Interior Component.
- To consider adding training output indicator to output 1 by June 2017.
- To consider amending the weightings in the Logframe by June 2017 to place more emphasis on the Ministry of Interior (MOI) component that will continue until March 2018.
- To update results on indicator 2.2 to reflect progress against the anticorruption strategy.
- To follow up with Joint Programme partners on the final evaluation of the Joint Programme, reflecting relevant updates to the results within the next review.
- To update output indicator 4.3 when data collection is complete.
- To explore outcome 1.1 indicator results ahead of completion review.

Has the logframe been updated since the last review? Yes
Several indicators were modified as per recommendations from the previous Annual Review. These changes mostly reflect the project’s overachievement and increased ambition (see below) relative to the original business case with no additional funds.

Summary of changes
June 2016: Outcome Indicator 1.2 – modified from ‘% of executed judgments referred for enforcement’ to ‘% of judgements enforced by executions department’ / Target 1.2 changed from 30% to 55%.
In June 2016 several indicator were modified in response to Annual Review recommendations: / Output 1.3: Gender disaggregation was added. / Output 2.1: Gender disaggregation was added. / Output 3.4: New indicator was added “The Number of 'One Stop' Juvenile and Family protection centres established in OPTs” with a baseline of 0 and target of 1(70% completion). / Output 4.3: Indicator was modified (modification in red): Percentage of legal assistance service beneficiaries (disaggregated by sex) who feel at least satisfied (satisfied and very satisfied) with legal aid services provided (regardless of outcome of the case) / And target was modified: Target: At least 95% (was 80%) of legal assistance service beneficiaries (including women) feel at least satisfied with services provided
Output indicator 3.3 target was modified from 2 reports to 1 report in October 2016 to reflect the work UN Women are doing with ICHR, more specifically on the methodology and sustainability of processes developed within ICHR as a result of this work.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	The MOI has the institutional and organisational structures, processes and capabilities to exert clear civilian oversight of state security functions
Output number per LF		1	Output Score	A+
Risk:		Severe	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 The percentage of organisational, capacity and legal framework action plans completed	40% of actions completed	Target exceeded. 65% of actions completed.
1.2 Strategic planning units have a standardized, well-evidenced, and collaborative process for the development/updating of the sector and organisational strategic plans	One previously drafted SOP manual approved. Three SOP manuals drafted (4 drafted in total): / (1) M&E / (2) Operational and capacity-building for directorates/departments/units of MOI and security institutions / (3) Drafting the development plan for security institutions	Target exceeded. 6 SOP manuals for strategic planning drafted and approved: / (1)M&E / (2) Operational and capacity-building for directorates/departments/units of MOI and security institutions / (3) Drafting the development plan for security institutions / (4) Conduct Strategic Reviews / (5) Manage Projects / (6) Developing the Strategic Plan
1.3 Number of training sessions in key organisational areas where 80% of participants are satisfied (gender disaggregated): 1. M&E 2. Strategic Planning 3. Programme Management	1. M&E (12 sessions) 80% satisfaction (M,F) / 2. Strategic Planning (5 sessions) 80% satisfaction (M,F) / 3. Programme Management (10 sessions) 80% satisfaction (M.F)	Target met. / 1. 12 sessions in M&E (P22 M, 5 F) (86%) / 2. 5 sessions in Strategic Planning (22M, 5F) 95% satisfaction / 3. 10 sessions (22 M , 5F) 82% satisfaction

Key Points
Indicator 1.1: The 2017 target has been exceeded. The programme has been delivering effectively and with strong ownership by the MOI, this has enabled over achievement against action plans than the initial targets. For example: the MOI together with the services has developed and approved organisational restructuring of the planning units. There is overall approval on implementing the Complaints Handling operating procedures, with six security agencies establishing complaints units as a result. Proposals to restructure Human Resource units are currently going through the necessary approval processes.

Indicator 1.2: The 2017 target has been exceeded. With the support of the implementing partner, the MOI has developed Standard Operating Procedures (SOPs) for six areas under Strategic planning. These have been formally approved and endorsed by the Minister of Interior/Prime Minister. The Mid-Term Strategic Review found that the SOPs on planning have had a significant impact on the mandate and importance of planning within the sector. The programme has also developed standard operating procedures for another four priority areas including on Human Resources, Complaints Handling and Management and Legal Affairs. The Mid-Term Strategic Review found that in addition to the achievement of developing these SOPs, the process through which they were developed ensured ownership within the sector, and created a group of potential ‘agents of change’. The final year of the programme will work on embedding these processes and procedures.

Indicator 1.3: The target was met. Training on all three areas (M&E, Planning and Programme Management) was conducted during the past year, with a high level of satisfaction across all training programmes. The surveys found that participants were mostly satisfied with the knowledge they gained from the courses. The Mid Term Strategic Review (MTSR) found that the training was of a strong knowledge based character, and suggested that the final year of the programme should focus more on skills oriented training, to place more emphasis on change management (embedding processes that were developed over the first two years, as indicated in indicator 1.2).

Summary of responses to issues raised in previous annual reviews (where relevant)
Technical-level Steering Committees have continued on a regular basis, and special attention was given to progress against the logframe.

Recommendations
  1. The programme officer to make sure that recommendations of the Mid-Term Strategic Review of the programme are taken forward during the final year of the programme through the implementation of the action plans developed for Year 3 [MTSR Quest ref: 5703127, Action Plans Quest Ref: 5731294].
  2. The programme officer and Senior Responsible Officer to consider adding training output indicator to reflect recommendation regarding increased focus on skills-oriented training made by Mid-Term Strategic Review [MTSR Quest ref: 5703127] by June 2017.
  3. Given the positive trajectory of the component, it is recommended that the output risk be reduced from Severe to Major for the third year of the programme.

Output Title	Institutional and technical capacity of the MoJ, HJC, AGO and Anti-Corruption Commission strengthened
Output number per LF		2	Output Score	A
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of Ministry of Justice and High Judicial Council personnel trained in key legal and administrative skills	5 (2 men, 3 women) additional of MOJ staff to have completed Legal Skills Diploma 15 additional (7 men, 8 women ) HJC staff to have completed diploma	8 (7 women) additional MOJ staff attending legal skills diploma (second iteration) and 1 additional staff attended Organization Development Diploma (second iteration) / 10 (4 men, 6 women) additional HJC staff attended legal skills or organisational development diploma.
2.2 Implementation of National Anti-Corruption strategy (2015-17)	50% of the Palestinian Anti-Corruption Commission work plan implemented	At least 50% of work plan implemented.

Key Points
Indicator 2.1: The target was not fully met as originally planned. High Judicial Council (HJC) staff decided that this course was less relevant to their needs, and so the number of participants working on improving administrative skills did not reach the result that was as targeted for within the indicator. Out of a target of 15, only 10 (6 women) participated. To counter this however, there was an increase in interest by Ministry of Justice (MOJ) staff to participate in the diploma course, which the Joint Programme was able to accommodate for, thereby exceeding the target.

Indicator 2.2: The target was met. There has been tangible progress on the implementation of the National Anti-Corruption Strategy, and our partners’ initial assessment is that the strategy has been at least 50% implemented. For example, part of the strategy included the development of anti-corruption sectoral strategies; currently, strategies on anti-corruption and gender, and anti-corruption and youth are underway, in addition to the organizational strategy of the Palestinian Anti-Corruption Commission’s (PACC). Furthermore, and related to the work plan, the PACC has entered into 31 partnerships with Civil Society Organisations and institutions to implement activities under the strategy, and trained, in partnership with the General Personnel Council and Ministry of Higher Education, 45,000 civil servants on the civil service code of conduct. Our partners will assess progress against the Strategy later in 2017 as part of an independent review.

Summary of responses to issues raised in previous annual reviews (where relevant)
The target for indicator 2.1 was amended to reflect the expanded availability of the training to justice institutions in key legal and administrative skills.

Recommendations
2.1 The programme officer and SRO to consider amending the weightings in the Logframe by June 2017 to place more emphasis on the Ministry of Interior (MOI) component that will continue until March 2018.

2.2 The programme officer should update results on indicator 2.2 to reflect progress against the anticorruption strategy once the independent review has been finalised.

Output Title	Accountable justice and security services to prevent, protect and respond to violence against women and girls
Output number per LF		3	Output Score	A+
Risk:		Major	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Implementation of the Family and Juvenile Protection Units strategy and Standard Operating Procedures	At least 6 (over 50%) of Family and Juvenile Protection Units effectively implement the strategy and minimum standard guidelines.	All Family Protection Units (12) across the West Bank are implementing the strategic and standard guidelines.
3.2 Number of targeted Attorney General's Office prosecutors demonstrating increased level of gender sensitivity and understanding of gender equality, women's needs and rights	21 gender-sensitized prosecutors assigned to work on women's cases across the West Bank & SOPs finalised and piloted.	26 gender-sensitised prosecutors assigned to work on women’s cases across the West Bank. SoPs not finalised.
3.3 Level of access by Independent Commission on Human Rights Observatory to data and information generated within the justice and security sectors	1 Observatory annual reports on Women's Access to Justice published and disseminated	1 report issued by ICHR observatory on women’s access to justice
3.4 The Number of 'One Stop' Juvenile and Family protection centres established in OPTs	70% complete	Refurbishment 100% complete. The One Stop Centre was will be inaugurated on 26 April 2017.

Key Points
Indicator 3.1: The 2017 target has been exceeded. Family protection units in all districts are now implementing the family protection Standard Operating Procedures (SoPs) and implementing the strategy. However, it’s important to note that a decision was taken by the units to separate out the family protection SoPs from the Juvenile strategy and SoPs; although the latter have been developed, they will be disseminated later this year.

Indicator 3.2: The 2017 target has been met. The programme supported the development of an organisational structure to institutionalise the handling of Violence Against Women (VAW) cases within the Attorney General’s Office; since October 2016 there are 26 specialised Public Prosecutors who are receiving ongoing training on gender sensitivity and understanding of gender equality and women’s human rights; however, the Attorney General’s Office took the decision to delay finalisation of the SoPs until the trainings have been completed.

Indicator 3.3: The 2017 target was met. One report was produced. UN Women focused much effort into integrating the data collection and production of the report within ICHR’s processes; this has been achieved and during the upcoming period ICHR will no longer need financial support to produce its next report.

Indicator 3.4: The 2017 target has been exceeded. The pilot ‘One Stop’ centre in Ramallah, approved in 2015 by Palestinian Civil Police, has been completed and the official opening will take place on the 26th of April 2017. The centre that serves women, children and juvenile offenders provides all the needed services in one place, including health care, psychosocial assistance, critical referrals, specialised prosecution services for cases of VAW, gender responsive police officers, temporary shelter and forensic services.

Summary of responses to issues raised in previous annual reviews (where relevant)
An indicator was recommended to reflect the work conducted on the ‘One-Stop’ centre. This was taken forward and the indicator is being measured as part of this Annual Review.

Recommendations
3.1 The programme officer and SRO to consider amending the weightings of the outputs by June 2017 to place more emphasis on the Ministry of Interior (MOI) component that will continue until March 2018.

Output Title	Civil society contribution to rule of law and community access to justice enhanced in areas outside of the PA's jurisdiction
Output number per LF		4	Output Score	A++
Risk:		Major	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Number of legal assistance cases (legal representation, consultation or mediation) in West Bank (including Area C, East Jerusalem)	6259 beneficiaries of legal assistance (a further 10% increase), with 40% women minimum	West Bank (incl. area C and EJ): 15979 beneficiaries, of which 51% (8159) women.
4.2 Number of legal assistance cases (legal representation, consultation or mediation) in Gaza	6735 beneficiaries of legal assistance (a further 10% increase), maintaining a percentage of 70% of women beneficiaries	Total beneficiaries: 11776, of which 61% women (7185)
4.3 Percentage of legal assistance service beneficiaries (disaggregated by sex) who feel at least satisfied (satisfied and very satisfied) with legal aid services provided (regardless of outcome of the case)	At least 95% of legal assistance service beneficiaries (including women) feel at least satisfied with services provided	At least 96.8% of beneficiaries (96.1% M and 96.9% F) feel satisfied with services provided

Key Points
Indicator 4.1: The target was significantly exceeded. As in the previous year of the programme, the significant increase in number of legal aid beneficiaries is likely due to the fact that a large number of legal aid services supported in 2016 involved legal aid assistance to clients involving administrative bodies, which are typically less time and resource intensive than legal representation before judicial bodies. Also, the overall volume of financial support to legal aid providers was higher during the reporting period than for instance in 2014. In the West Bank, and due to an increase in investment for specialized legal aid services to women and girls within the Civil Society Organizations portfolio, the percentage of women beneficiaries significantly exceeded the target at 51%.

Indicator 4.2: The target was significantly exceeded. The significant increase in the number of beneficiaries is explained in indicator 4.1. In Gaza, in absolute terms, the number of women beneficiaries was more than was targeted for, however, the percentage of women beneficiaries constituted 61% in 2016, whilst this was 71% in 2015. Programme partners have explained that this is most likely due to a reconfiguration of the portfolio in 2016, with a more differentiated distribution of services across different target groups.

Indicator 4.3: The target is on track to be exceeded. Preliminary data captured by the initial surveys, that approximately represent 75% of questionnaires to date, suggest that at least 96.8% of beneficiaries are at least satisfied with the legal aid provided. This indicator will be updated once all data has been captured.

Summary of responses to issues raised in previous annual reviews (where relevant)
The Senior Responsible Officer and Project Officer have tracked implementation of the EU Steering Committee recommendations. In addition, the target for indicator 4.3 was amended to reflect a more realistic target.

Recommendations
4.1 Programme Officer to update results on indicator 4.3 once final results of surveys are completed.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers are administrative costs. Administrative costs were negotiated with UNDP/UN Women and UNOPS. In addition, both UNDP/UNWomen and UNOPS have developed Value for Money strategies for the duration of the programme. The below indicators are examples of how the programme is performing VfM throughout the first year of implementation.

VfM performance compared to the original VfM proposition in the business case
The indicators assessed below represent some of the VfM indicators monitored and assessed within the VfM strategies of the Ministry of Interior component and the UNDP/UNWomen Joint Programme component.
Type	Indicator	Progress
Economy	Overhead costs payable to UNDP as the implementing agency	As per the global UNDP guidelines, and agreed on in the agreement between DFID and the Multi-Partner Trust Fund Office (the MPTF Administrative Agent), 8% of the Programme budget amount is dedicated to overhead costs, of which 1% goes to the MPTF Office as the Administrative Agent of the funds, and 7% to UNDP and/or UN Women. DFID does not incur extra costs due to the involvement of MPTF Office, but rather the two Agencies hand in 1% of their overhead for services rendered by MPTF.
	Overall programme implementation costs	UNOPS continue to deliver the programme to the original proposal with reduced cost (£1.8m per year instead of £1.94m per year) over the first two years of the programme, without compromising the ability of UNOPS to provide support to the Ministry of Interior to implement the programme.
Efficiency	Cost per MOJ personnel trained in key legal and administrative skills;	Legal Skills Diploma (runs 1 academic year): USD 2,100 tuition fee per participant. (358 training + 80 coaching hours amounting to 43.8 accredited hours). These specialized trainings are tailor-made to the needs of, and were developed in consultation with, the institutions involved. The overall price of the Birzeit training is USD 600 more than the other option, due to the larger number of accredited hours. Considering the fact that the Birzeit University training has been tailored made to the needs of the participants and includes on the job coaching modalities, the Birzeit training provides good VfM.
	Cost of delivering outputs across work areas	The products developed for specific outputs have been used to serve other outputs thereby saving staff-time and cost. For example, under the Human Resources output, templates were developed for organizational restructuring that ultimately served the other 6 work areas of the programme.
Effectiveness	The independent Mid-Term Strategic Review of the MOI component found the effectiveness of the programme to be positive. This is due to the management of the programme, the national ownership, and the level of engagement by the security sector in the development of the processes delivered by the programme. A Mid-Term strategic Review was also carried out on the (UNDP/UNWomen )Joint Programme; in terms of effectiveness, the MTSR found that while governance structures and local ownership can be improved, there was effective collaboration between the main implementing agencies and other UN agencies involved in the sector.

Assessment of whether the programme continues to represent value for money
The implementing partners of the programme (UNDP/UNWomen and UNOPS) continued to follow their strategies to deliver Value for Money. For the Annual Review, they have provided updates on progress on these strategies. In addition, synergies developed between the UNDP/UNWomen Joint Programme and UNOPS MOI Maturity Programme have allowed for particular consultants/experts to work across both areas of intervention. For example, the gender expertise that was commissioned by the Joint Programme strand provided support on gender mainstreaming into the Maturity programme process engaged with technical committees (e.g. strategic planning, human resources, media) led by the MOI with participation from the security agencies.

Quality of financial management
All implementing partners (UNDP/UNWomen and UNOPS) of the programme have provided the financial and narrative reports in line with reporting requirements.

Type of Report	Partner	Date	Period
Date of last narrative financial report	UNDP/UNWomen	September 2016	2016
Date of last narrative financial report	UNOPS	February 2017	2016
Date of last audited annual statement	UNOPS	September 2016	Jan-Dec 2015

E: RISK (½ page)

Overall risk rating: Severe
The last Annual Review assessed the residual risk as severe. However, as the Joint Programme component comes to an end this April, and given the positive outcome of the Mid-Term Strategic Review of the MOI component, we recommend that the overall risk be reassessed as Major.

Overview of programme risk
This is a complex intervention in a fragile and highly politicised environment which therefore carries a number of risks. These include:

- Political or fiscal difficulties lead to the collapse of the PA;
- Changes in Palestinian leadership affect the PA’s commitment to reform and demand for this intervention;
- Suspension of security cooperation between the Government of Israel and the PA;
- The creation of gender-sensitive security forces and justice institutions is undermined by broader social attitudes to women and girls.
- Corruption within institutions hindering programme’s ability to affect meaningful and long-term change.

DFID has developed a thorough risk matrix for the business case of the programme. This is reviewed and updated on a quarterly basis; it is recommended that risks continue to be reviewed on a regular basis.

Outstanding actions from risk assessment
Risks continue to be treated in line with the Risk Matrix. There are no outstanding actions from risk assessments. Due Diligence Assessments of our partners took place prior to the start of the programme, and outstanding recommendations continue to be addressed.

F: COMMERCIAL CONSIDERATIONS (½ page)
Delivery against planned timeframe
Delivery against the original timeframe is on track.

Performance of partnership (s)
The UK’s relationship with UNDP/UNWomen is governed by a Standard Administrative Agreement and with UNOPS by a robust MoU. These agreements detail reporting and financial requirements. Partners have fulfilled obligations and commitments outlined therein.

Asset monitoring and control
Assets have been procured under the Ministry of Interior programme for the use of the programme office within the Ministry. UNOPS has registered these Assets; a list has been provided to DFID. An Annual spot check of these assets was carried in 2016 and another one will take place before June 2017.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The Partnership Principles are relevant to the management and monitoring of this programme given it works directly with the PA. Of particular importance to this programme is the second commitment on ‘Respecting human rights and other international obligations’.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
Both components of the programme have end-of-programme evaluations planned. The UNDP/UNWomen Joint Programme final evaluation is currently being conducted and is expected to be completed by April 2016. The objective of the evaluation is to assess the level of progress achieved by the programme against the output and outcome indicators set out in the programme document since the start of the programme.

The Ministry of Interior component has factored into its programme an end of programme independent impact evaluation to take place in the first quarter of 2018. The objective of the impact evaluation would be to provide an independent assessment of the performance of the project and whether the evidence base supports the underlying theory of change.

Annual review
This review was carried out by the Project Officer and Quality Assured by the Senior Responsible Owner (Conflict Adviser). Extensive reporting on progress, together with supporting documentation, was provided by the implementing partners. The annual review was quality assured by the OPTs Deputy Head of Office and the MENAD Results adviser.

Monitoring progress throughout the review period
To strengthen independent monitoring of the programme, the programme sought the support of the UK’s Stabilisation Unit to provide technical inputs to the programme at key stages of the implementation (e.g. in carrying out annual or mid-term/project completion reviews). An overall assessment was carried out in June 2015, followed by a Mid-Tem Strategic Review that was conducted for the UNDP/UNWomen Joint programme in January 2016, and another one for the UNOPS MOI Programme in December 2016.

The programme comes under the OPTs Governance and Security Pillar and is overseen by the Governance & Security Team Leader who is the SRO and managed by the Project officer. In line with DFID’s SMART Rules, a delivery plan was completed in January 2015 and continues to be updated on a rolling basis.

The team monitors progress through:
- Informal monthly meetings with partners.
- Quarterly progress and financial reports.
- Regular meetings with the Ministry of Interior
- Field visits

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process