Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: World Bank Trust Fund – International Comparison Programme
Programme Value: £4,900,000		Review Date: May 2017
Programme Code: 200806	Start Date: August 2010	End Date: December 2017

Summary of Programme Performance
Year	2013	2014	2015	2016	2017
Programme Score	A	A	A	A+	A
Risk Rating	Low	Low	Low	Minor	Minor

Summary of progress and lessons learnt since last review

The International Comparison Program (ICP) is a worldwide statistical initiative required to estimate purchasing power parities (PPPs) to be used as currency converters to enable comparison of the size of economies around the world.

ICP has made good progress against all outputs since the last Annual Review, and is delivering well. Preparation and implementation of the ICP 2017 cycle has begun, and interim activities were finalised. ICP has prepared the operational materials for the ICP 2017 cycle, and distributed these to countries. Capacity building workshops and technical assistance have been provided across 5 regions, and additional capacity building materials including a video tutorial and an introductory leaflet on PPPs have been launched. ICP has continued to work on improving extrapolated PPP estimates (for the period between ICP survey years 2011 and 2017), by implementing a third round of improvements to the methodology and calculating 2012-2013 estimates. In addition, key lessons have emerged from research on the feasibility of using price data collected in new and innovative ways, and there is ongoing work looking at how this data can practically be applied in urbanization and poverty analysis. Efforts to increase the use of PPPs have also progressed well, with 6 seminars on the uses of PPPs conducted over the last year and the launch of a new website for the permanent ICP programme.

ICP have implemented several key recommendations from the independent evaluation of ICP 2011, including establishment of a new governance structure, and producing a draft Research Agenda which will guide the future of ICP/PPPs. The Research Agenda will be further discussed and refined in May 2017, but will include a focus on: (i) building consistent PPP time series; (ii) improving PPP reliability and quality; (iii) addressing difficult to measure areas, such as housing; (iv) strengthening alignment between PPPs and national statistical programs; (v) advocating wider uses and applications of PPPs; and (vi) exploring innovations in technology and new sources.

Summary of recommendations for the next year

1. DFID and the World Bank should consider tracking the effectiveness and uptake of capacity building activities and materials, in the logframe.
2. The World Bank ICP team should consider how best to disseminate the findings and recommendations from the extended pilot study on alternative sources of price data more widely.
3. DFID and the World Bank should consider options for tracking use of PPP outreach materials in the logframe, and potentially also developing a metric for assessing actual use of PPPs as an outcome indicator.
4. DFID and the World Bank should ensure that, by end June 2017, realistic but ambitious logframe targets are set for December 2017.
5. DFID and the World Bank should continue to discuss options for future support to ICP, given that the current programme is due to end in December 2017.
A. Introduction and Context (1 page)

DevTracker Link to Intervention Summary:	Intervention Summary
DevTracker Link to Logframe:	Logframe

Outline of the programme

DFID currently provides £4.9 million over a 7 year period from August 2010 to December 2017 in support of the International Comparison Program (ICP) which is a worldwide statistical initiative required to estimate Purchasing Power Parities (PPPs) to be used as currency converters to enable comparison of the size of economies around the world. The indicator for the new Sustainable Development Goal (SDG) on poverty reduction explicitly uses PPP data to set a poverty line of $1.90 per person per day measured in constant purchasing power parities. DFID support will help ICP produce internationally comparable price and volume measures for gross domestic product (GDP) and its component expenditures. The measures are based on purchasing power parities (PPPs).

To calculate PPPs, the ICP has, until now, conducted surveys every six years to collect price and expenditure data for the goods and services that comprise GDP including consumer goods and services, government services and capital goods. At the 47th session of the United Nations Statistical Commission in March 2016, it was agreed that ICP should become a permanent element of the global statistical programme. ICP is now moving into a new phase, where surveys will instead be conducted over 3 years on a rolling basis. This will mean PPP data is available on a more frequent, timely basis, with the eventual aim of producing annual PPP data.

Additional funding was approved in September 2013 to strive ahead with the momentum gained and leverage on the 2011 ICP round investments, such as the trained human capital and established regional and national partnerships. A further, no-cost extension has recently (April 2017) been agreed to extend the end date of the project to 31 December 2017, and allow ICP to spend the small amount of funds remaining in the Multi-Donor Trust Fund. This follows an earlier, no-cost extension granted in April 2016; these were required as disbursement from the Trust Fund has been slower than originally expected, due to efficiency savings resulting from organising activities in a cost effective way. For example, use of new technologies has allowed some outreach activities to be conducted remotely, and holding activities back-to-back has reduced the overall cost. Implementation of activities, however, has generally not been slower than anticipated, and ICP has been able to carry out additional activities to utilise the funds.

As ICP moves into the 2017 benchmark round, it continues to build the capacity of countries in the areas of price statistics and national accounts, and to implement a technical research agenda to guide the future. Subject to further discussing and fine-tuning, the ICP Research Agenda will focus on: (i) building consistent PPP time series; (ii) improving PPP reliability and quality; (iii) addressing difficult to measure areas, such as housing; (iv) strengthening alignment between PPPs and national statistical programs; (v) advocating wider uses and applications of PPPs; and (vi) exploring innovations in technology and new sources.

Expected Results

The intended impact of this project is that data informs policies of donor agencies, government and civil society institutions.

The intended outcome of the project is timely and reliable statistical data on purchasing power parities for GDP and its main sub-aggregates for all major countries and regions are compiled and published.

The outputs attributable to DFIDs support are (this annual review only covers the 3 latter outputs):

- New methodological preparation developed for various components of the program (output completed by May 2014) .
- Accurate and timely collection of price survey data (output completed by May 2014).
- Improvements in statistical capacity in IDA countries (output removed from logframe in 2014. A similar indicator was added at outcome level instead).
- Increase the capacity of countries in national accounts and price statistics for the ICP.
- Improve non-benchmark PPP estimates.
- Increase the use of PPPs.

The 2011 round of the ICP support was leveraged on the successful implementation of the 2005 round and its scope was further extended. It was designed to enhance the robustness of PPP estimates through greater adherence to the System of National Accounts (SNA), the improvement of price survey methodologies, and to perform additional methodological research.

Context of UK support

There is a clear need for countries to have good quality statistics. They are essential not only to inform policy, but also to enhance the credibility of policies by enabling citizens to hold governments to account. Particularly crucial for the international community is reliable data on Sustainable Development Goal (SDG) indicators.

These play a key role in:
- holding the international community to account to ensure that global targets are being met
- encouraging sustained public support and funding for development;
- ensuring effective allocation of aid, and;
- comparing progress across countries.

DFIDs support for the ICP has played an important role in improving the quality and availability of poverty data, and enabling measurement of progress against the SDGs; PPPs produced by the ICP 2011 round informed the update of the International Poverty Line (IPL), which is the basis for measurement of progress against SDG target 1.1: “By 2030, eradicate extreme poverty for all people everywhere, currently measured as people living on less than $1.25 a day”. In addition, PPPs are required to facilitate global comparisons of Gross Domestic Product (GDP) and other economic data across countries. They can therefore play an important role in supporting policy and resource allocation decisions (e.g. by governments, international organisations and donors).

However, there have recently been some key changes to ICP and the context of DFID’s support. Firstly, an independent evaluation of ICP, completed in early 2016, highlighted many positive achievements of ICP and recommended a number of changes to the way in which the programme operates. As a result, UNSC agreed that ICP should become a permanent element of the global statistical programme, and that it should move from operating in discrete 6 year cycles, to a rolling survey basis which will produce benchmark PPPs on a more frequent basis (every 3 years). In light of ICP becoming a permanent programme, the World Bank are aiming to establish a viable and sustainable funding model, which aligns funding for ICP in 3-year segments. The global budget for the 2017 cycle is significantly less than that of the ICP 2011, and the aim is that the budget and resources needed for ICP will continue to decrease over time as countries integrate PPP surveys into their national statistical programmes. With increasing domestic contributions and declining donor funds devoted to governance activities, the World Bank is confident that it can meet its obligations to the program over the medium to long-term; however, a funding gap remains for the ICP 2017 cycle.

Secondly, in October 2016, the Report of the Commission on Global Poverty recommended that new PPPs should not be used to update the IPL again before 2030. While the World Bank accepted this recommendation, they kept open the option to use PPPs to update the IPL again before 2030, if the methodology had stabilised over at least 2 cycles of ICP. Therefore, any future support which DFID provides to ICP should be considered in the context of PPPs as a global public good, rather than focusing on their use in updating the international poverty line.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome of the program is to produce timely and reliable statistical data on purchasing power parities for GDP and its main sub-aggregates for all major countries and regions. All outcomes have been achieved and progress to date is as follows:
Outcome Indicator 1: Number of countries publishing PPP data for GDP
Progress is as follows:
The target was exceeded in December 2013 and there are no future milestones for this indicator. See logframe for futher details[1]
[1] Logframe (QUEST number 5755406)
Outcome Indicator 2: Number of regions publishing PPP data for GDP.
Progress is as follows:
The target was met in December 2013 and there are no future milestones for this indicator. See logframe for further details.
Outcome Indicator 3: Number of regions where up to date PPP Poverty estimates are available.
Progress is as follows:
The target was met in October 2015 and there are no future milestones for this indicator. See logframe for further details.
Outcome Indicator 4[2]: Overall Statistical Capacity Indicator (SCI) score for IDA countries (aggregate score for all IDA countries with a population of 1 million or more).
[2] This outcome indicator was added following revisions made to the logframe after the 2014 Annual Review. The logframe revisions were made to better reflect the increased support DFID gave in September 2013 to enable the World Bank to extend the ICP activities beyond the 2011 round and further strengthen the capacity-building activities in participating regions and countries.
The milestone for May 2017 = 63
Progress is as follows:

Milestone met. The most recent data, as of September 2016, shows that the overall statistical capacity score for IDA countries with a population of 1 million of more remains at 63, meeting the target for May 2017.

Overall output score and description

A – outputs met expectation.

OUTPUT	Weight	Score
4. Increase the capacity of countries in national accounts and price statistics for the ICP.	40%	A
5. Improve non-benchmark PPP estimates.	30%	A
6. Increase the use of PPPs.	30%	A+

Key lessons

The project is delivering well against the outputs. Two of the original outputs have been completed, and one original output was removed in September 2013 as it was felt that it was measuring an outcome rather than an output. Of the three current outputs, two are scoring A and one is scoring A+. All outcomes have been achieved. Given the recent no-cost extension to this project, additional ambitious but realistic (given the short time remaining until project completion) milestones should be set for December 2017 in the logframe; DFID and the World Bank should ensure this is done by end June 2017.
The 2011 round of the ICP has been independently evaluated by the Friends of the Chair (FOC) group established by the United Nations Statistical Commission (UNSC). In 2016, the final phase of evaluation was completed. This evaluation highlighted many positives of the ICP, such as an improvement in the availability, methodology, data and use of PPPs and increased capacity across countries on the knowledge of ICPs. Based on the evaluation findings, some key changes have been made to ICP as a programme, including: UNSC instituted ICP as a permanent element of the global statistical programme; ICP is moving towards a 3-year rolling survey approach, to provide more frequent PPP estimates and reduce the burden on countries; and a new governance structure has been established to oversee effective implementation of ICP. In addition, ICP is in the process of establishing a Research Agenda to inform future developments in ICP and PPPs.
Since the last annual review, ICP has completed research on the feasibility of collecting and using targeted crowdsourcing data in 15 countries, which has provided some useful lessons on what is required for this approach to work (see output 5 for more details).

Key actions

See the ‘Summary of recommendations for the next year’ section on the summary sheet

Has the logframe been updated since the last review?

Yes. The logframe was updated in January 2017, to set new milestones for May 2017 following the no-cost project extension to June 2017. A subsequent no-cost extension to December 2017 has been agreed, and the logframe will be updated following this annual review to set new targets for end 2017.

Summary of responses to issues raised in previous annual review

Recommendation: DFID extended its support to the ICP trust fund to June 2017, therefore the milestones for all outcomes and outputs need to be set for May 2017.
Response: DFID and the World Bank agreed milestones for May 2017, and the logframe was updated to include these.
Recommendation: DFID and World Bank should consider future support to ICP by November 2016. This will involve identifying priority areas of work and assessing value for money.
Response: DFID and the World Bank have had extensive discussions on future support to ICP; these discussions are still ongoing, in light of the recommendation of the Report of the Commission on Global Poverty that new PPPs should not be used in updates to the International Poverty Line before 2030.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increase the capacity of countries in national accounts and price statistics for the ICP
Output number per LF		4	Output Score	A
Risk:		Minor	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Conducting technical assistance missions to address gaps and difficulties in price and expenditure data identified during the 2011 ICP.	15 technical assistance missions are conducted between 2014 – 2017.	Milestone exceeded – 23 technical assistance missions conducted / See Key Point 1.
Organise regional/sub-regional workshops to address price statistics and national accounts gaps and challenges observed during the 2011 ICP.	15 workshops conducted between 2014 - 2017	Milestone exceeded - 20 capacity-building workshops conducted / See Key Point 2
Preparing capacity-building materials to help countries understand price and national accounts concepts and activities for the ICP.	May 2017 – E-learning modules and other training materials are launched and disseminated.	Milestone partially met / See Key Point 3

Key Points

Overall, ICP has made good progress against this output, and previous evidence from the ICP evaluation and regional reports on the 2011 round shows that ICP capacity building activities have had a positive effect on national and regional statistical capacity[3]. In the past 12 months, ICP has exceeded the targets for technical assistance missions and regional workshops (see key points 1 and 2 below).
[3] In early 2016, an independent evaluation of ICP concluded that “a large majority of ICP stakeholders confirmed that ICP 2011 had wide positive effects on the regional statistical programmes with regard to both price statistics and national accounts. The ICP exercises also brought considerable contributions in building national statistical capacities (institutional and technical)”. E.g. African regional report (AfDB): “The International Comparison Program has some important spin-offs: Chief among the spin-offs is statistical capacity-building in participating countries”; and the Western Asia regional report (UNESCWA): “Many countries employed the experiences gained and the tools acquired during the 2011 Round in order to enhance their national Consumer Price Index (CPI) production process”

1. Milestone exceeded. The ICP Global Unit has conducted 23 technical assistance (TA) missions in total since 2014; eleven of these were held during 2016-17, compared to 3 TA missions expected during this period. Of these 11 missions, 8 were associated with regional workshops (more details on the purpose of each of these workshops is included under key point 2 below). The ICP Global Unit supported the regional agencies to prepare for and deliver these workshops, and in some cases also provided TA and training directly to participants of the workshops. The workshops supported were:
- One TA mission to support AfDB with a regional workshop held in Africa (Zambia, early 2017).
- Three TA missions to support ADB with regional workshops in Asia (Bangkok, June 2016; Manila, September 2016; Bangkok, February 2017).
- One TA mission to support CIS-STAT with a regional meeting in Russia (Moscow, April 2017).
- Three TA missions to support UN-ESCWA with regional workshops for Western Asia (Egypt, September 2016, February 2017 & April 2017).

The remaining three TA missions delivered by the ICP Global Unit were:
- One TA mission to provide training to AfDB staff on the requirements of the ICP 2017 cycle (Nov 2016)
- One TA mission to support UN-ECLAC to prepare the regional item list for LAC, and discuss the requirements for the 2017 cycle (Nov 2016),
- One TA mission to conduct a training workshop of sub-national PPPs in Delhi, India (Feb 2017).
2. Milestone exceeded. The ICP has continued to support countries through regional workshops, with a total of 20 capacity building workshops conducted across 5 regions between 2014 – 2017; ten of these were held during 2016-17, compared to 5 workshops expected during this period. The focus of the regional/sub-regional capacity building workshops delivered during 2016-17 has mainly been on validation of 2016 price data, and preparations for the 2017 cycle:
- One workshop was conducted in the African region: African Development Bank (AfDB) and the Common Market for Eastern and Southern Africa (COMESA) held a regional technical workshop in Zambia in early 2017, with representatives from 49 African countries. The workshop assessed country readiness for ICP 2017; provided information and training to participants on the ICP 2017 approach and operational materials; and reviewed data sources for PPP time series.
- Three workshops were held in Asia: one in Bangkok in June 2016 to review methods for updating PPPs and conduct validation of prices for household consumption items; one in the Philippines in September 2016, to initiate operational preparations for the ICP 2017 cycle; and one in Bangkok in February 2017 to validate price data from the final quarter of 2016 and prepare for ICP 2017.
- Two workshops were held in the CIS region: one in Minsk, Belarus, in October 2016 on price statistics quality analysis, and one in Moscow in April 2017 to discuss publication of the 2014 regional results and the household consumption survey items list for ICP 2017.
- Four workshops were held in Egypt for the Western Asia and North Africa region. Three of these focused on price data validation (September 2016; February 2017; April 2017), and one focused on national accounts activities (April 2017).

3. Milestone partially met. The ICP has completed and disseminated some capacity building materials. These include operational and training materials for ICP 2017, which were disseminated directly to countries in regional workshops, as well as being posted on the ICP website and announced in the ICP Quarterly Update; a video tutorial explaining a multidimensional comparison between GDP, GDP per capita and price levels, based on ICP 2011 results, which was released on the ICP website and in the ICP Quarterly Update; and an introductory leaflet which outlines PPPs for a general audience, which was posted on the ICP website and distributed to regional agencies for onward dissemination. Another leaflet on ICP and its activities is currently being prepared, and planned to be released in June. The e-learning course contents have been finalised and professionally edited, and it is expected to be ready by the end of May 2017. The course is aimed at a wide audience, including both producers and users of PPPs. However, there has been a slight delay in the launch of the e-learning course; it is expected to be released by the end of June 2017. This delay was due to an iterative review conducted with the World Bank’s Open Learning Campus team taking slightly longer than expected. However, this review provided feedback on the narration style and graphics used and was instrumental in ensuring that the e-learning course is of high quality.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A.

Recommendations

DFID and the World Bank should consider tracking the effectiveness and uptake of capacity building activities and materials, in the logframe.

Output Title	Improve non-benchmark PPP estimates.
Output number per LF		5	Output Score	A
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
Introducing and applying an improved method for computing non-benchmark PPPs.	May 2017 - Third round of improvements of non-benchmark PPP estimates is implemented.	Milestone met. / See Key Point 1.
Introducing innovative technological advancements to improve data collection and compilation processes.	May 2017 - Research on the feasibility of utilizing price data from alternative sources (crowd-sourcing, billion price project etc.) to improve non-benchmark PPP estimates is completed and findings and recommendations from the extended pilot study are published.	Milestone partially met. / See Key Point 2.

Key Points

ICP has made good progress in calculating and improving non-benchmark PPP estimates, with the aim of publishing a complete PPP time series for 2012-2016 together with the 2017 PPPs.

Milestone met. A third round of improvements to the methodology for calculating non-benchmark PPP estimates has been implemented, and global PPP estimates for 2012-2013 were calculated and discussed with the ICP Inter-Agency Coordination Group. This third round of improvements focused on estimating global PPPs for 2012 and 2013, including utilising regional 2012 and 2013 interim PPPs for Eurostat and Western Asia. A fourth round of fine-tuning of the method and calculation of global 2014 PPP estimates by incorporating 2014 interim CIS results is underway, and is expected to be completed in June 2017. This will be followed by a fifth round of improvements to estimate 2015 and 2016 global PPPs, which should be completed by the end of 2018 (outside of the period covered by DFID’s current support to ICP).

Milestone partially met. An extended pilot study to collect and use targeted crowdsourcing data in 15 countries has been completed. Phase 1 of the study included 3 countries, and was completed during 2015, while phase 2 of the study included 15 countries and was completed in June 2016. The study investigated the feasibility of collecting price data through non-professional price collectors, using mobile phones and personal computers. A methodology and lessons learned paper has been published online, which discusses lessons learned from the first phase of the pilot study (which covered 3 countries) and sets out changes made to the methodology for the second phase of the pilot study, based on these lessons. The findings of the initial and extended pilot study were also presented and discussed at the PPP Research Agenda and Poverty PPPs meeting in May 2016, and the presentation has been released on the ICP website. However, the published materials mainly focus on lessons learned from the first phase of the pilot study, and the World Bank should consider how best to disseminate the findings of the full extended pilot study more widely.

Overall, the pilot study has shown that the approach for collecting price data using crowdsourcing and modern information and communications technology is feasible, and provided useful recommendations on what is required for this approach to succeed. These include lessons around: ensuring that the data collectors understand which items to price and their specification, and how to classify outlets; ensuring that data collected are representative and consistent, both spatially and temporally; and strengthening automated data verification processes. In addition, a key lesson learned is that mainstreaming this innovative approach would require identifying a long-standing organisation to partner with, rather than relying on start-up firms that do not necessarily provide the needed business continuity.

The World Bank are currently exploring the practical applications of the data in analysing urbanization and poverty – in particular, how they can be used in analysing spatial price differences and mapping poverty.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

The World Bank ICP team should consider how best to disseminate the findings and recommendations from the extended pilot study on alternative sources of price data more widely.

Output Title	Increase the use of PPPs
Output number per LF		6	Output Score	A+
Risk:		Minor	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Conducting outreach activities to promote the use of PPPs.	May 2017 – 10 seminars on the uses of PPPs are conducted. A revamped website for permanent ICP is launched and effectively promoting the use of PPPs.	Milestone exceeded – 14 seminars conducted in total. / See Key Point 1.
Number of hits on the ICP website, blogs and other online materials	May 2017 - 30,000 hits	Milestone exceeded – 35,641 hits between May 2016 – April 2017. / See Key Point 2.

Key Points

1. In order to promote awareness and use of PPPs, ICP have conducted a total of 14 seminars or courses since May 2014; 6 of these have been between June 2016 and May 2017, compared to 2 seminars expected during this period. These 6 seminars/courses include:
- Presentation of a paper on quality assurance procedures for estimating PPPs, at the 2016 European Conference on Quality and Official Statistics (May 2016).
- Discussion of a paper which used ICP data, titled “Is Living in African Cities Expensive?”, at the Annual Bank Conference on Development Economics (June 2016). This seminar promoted the use of PPPs beyond poverty measurement, and resulted in their use in a World Bank report on urbanization in Africa.
- A session at the World Bank hands-on poverty measurement training (July 2016).
- A seminar at Jiangxi University of Finance and Economics, China, on sub-national PPPs and the measurement of real GDP and living conditions comparisons (October 2016)
- A session on efforts to improve PPPs in the Gulf region to inform policy making, at the 15th International Association for Official Statistics Conference (December 2016). The session promoted the use and importance of PPPs in policy making to Chief Statisticians of participating countries, and included a presentation by UAE on their work on sub-national PPPs; other countries also indicated that they are interested in producing sub-national PPPs.
- A workshop on Global Poverty and ICP/PPPs (February 2017).

In addition, a new ICP website was launched in April 2017. The launch of the website was communicated via a World Bank blog post, promoted at various regional workshops, and included in the ICP Quarterly Update. The new website includes information on ICP and its history, the governance structure, results and their uses, PPP methodology, and the research agenda. A range of knowledge resources and training materials are available on the site.

2. The number of hits on the ICP website, infographics, blogs, videos and other online materials between May 2016 – April 2017 was 35,641. This exceeds the target of 30,000 for that period. The majority of these hits were on the ICP website (around 33,700), while ICP videos had roughly 2,400 hits and the blogs received 600 hits. The target, and number of hits, for May 2016 – April 2017 was substantially less than in the previous two years (>100,000 hits each year); however, this is to be expected since 2014-15 included the release of ICP 2011 results which attracted a high number of visits to the sites, and 2015-16 included the World Bank’s Future of Price Statistics seminar which was streamed live and had a large number of views.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

DFID and the World Bank should consider options for tracking use of PPP outreach materials in the logframe, and potentially also developing a metric for assessing actual use of PPPs as an outcome indicator.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers related to the delivery of the ICP programme are:

- Staff costs
- Consultants costs
- Seminars for outreach activities
- Technical assistance missions/workshops
- Costs for data collection
- Non-programme costs e.g. Admin/supervision costs.

VfM performance compared to the original VfM proposition in the business case
Preparation of the ICP project documents preceded the introduction and new requirements of the Business Case template, so no specific indicators or trigger points were established from the outset to monitor and measure VFM performance. However, since the 2014 annual review we have worked with the World Bank ICP team to develop appropriate vfm measures to measure economy, efficiency and effectiveness[4].
[4] See Quest document 5755791

Reporting on year 2016
The following measures demonstrate Value for Money. Please note that for some indicators, April 2016 VfM data relates data averaged across FY11 – FY16, whereas the April 2017 data relates only to the interim period (averaged across FY16 – FY17); this is stated in the notes column. Going forward, data will be averaged across the interim period and ICP 2017 cycle.
1. Economy (main cost drivers)	April 2016 (USD)	April 2017 (USD)	Notes
Non-program costs, annual average
Associated Overhead Costs	5,704	150	April 2016 figure is the average cost over FY11 FY16. April 2017 figure is the average of FY16 – FY17. The lower value is partly driven by low costs in the interim period, although overhead costs for ICP 2017 are expected to remain lower than ICP 2011 throughout.
Consultancy costs, annual average
Consultant Costs	449,953	118,050	April 2016 figure is the average cost over FY11 FY16. April 2017 figure is the average of FY16 – FY17. The lower value is partly driven by low costs in the interim period, although consultancy costs for ICP 2017 are expected to remain lower than ICP 2011 throughout.
Consultant Fee (average, net per day, per consultant)	445	444	Range (206-925 for April 2016; 250 – 610 for April 2017)). Per deciding the appropriate fee, ICP follows the World Bank guideline, which sets min/mid/max values depending on consultant's experience and qualification. US nationals are paid in gross, while all others are paid in net amount.
2.Efficiency (turning inputs into outputs)	April 2016 (USD)	April 2017 (USD)	Notes
Regional budget allocation, annual average
Total regional	5,100,000	2,625,000	FY11-FY16 average (April 2016); FY16 – FY17 average (April 2017). Excludes the contribution of national implementing agencies.
Per country, average	33,333	19,161	FY11-FY16 average (April 2016); FY16 – FY17 average (April 2017). Excludes the contribution of national implementing agencies.
Budget allocation per activity, average
Governance meeting	45,000	23,333	The substantial reduction in cost from the preivous year is driven by a decrease in the size of the new governance bodies
Outreach seminar	15,000	10,000	The cost of outreach seminars continues to decrease, as more outreach activities are conducted using remote technologies such as Webex and VC
Technical assistance mission (travel and staff/consultant time only)	15,000	15,000	The figure remains the same as last year.
Data collection
Per country, average	500,000 - 1,000,000	500,000 - 1,000,000	Relates to data collection for ICP 2011 cycle. Approximate range (100,000 - 10,000,000). Data collection cost vastly varies depending on the country size.
3.Effectiveness (in delivering outcomes)	April 2016 (USD)	April 2017 (USD)	Notes
Producing PPP data (annual average, per region)	850,000	525,000	FY11-FY16 average (April 2016); FY16 – FY17 average (April 2017). Excludes the contribution of national implementing agencies.
Global Coordination (annual average)	2,300,000	1,250,000	FY11-FY16 average (April 2016); FY16 – FY17 average (April 2017). Excludes the contribution of national implementing agencies.
ICP Mobile APP (contracting cost)	30,000	30,000	Total cost of app, live for 4 years (FY14 – FY17). Indicator to be removed for FY 17/18.
ICP Data Portal (contracting cost)	15,000	15,000	Annual maintenance cost. Indicator to be removed for FY 17/18.
ICP Data Dissemination Portal, App, Databank, etc. (annual average)	N/A	11,667	Includes all dissemination platforms FY14-FY17. From next year, this single indicator will replace the two VFM indicators on ICP Mobile App and Data Portal, since their functionalities are being migrated to the databank as the main dissemination platform.
ICP Website (staff and consultant time only)	10,000	10,000	Cost of upgrading and maintaining the ICP website, annual average
ICP Videos and Knowledge Material (staff and consultant time, printing costs)	25,000	25,000	Cost of producing outreach materials, annual average
E-learning course (staff time and contractual services), total charge (not average)	80,000	80,000	Cost of preparing and producing the E-learning course

Assessment of whether the programme continues to represent value for money

The costs presented are similar to those in the previous years, or in some cases have decreased due to efficiency/cost saving measures implemented by ICP – for example, moving to a new governance structure with fewer members of governing bodies has reduced the cost of ICP governance meetings, and use of technology such as Webex to allow outreach activities to be conducted remotely has also driven down costs. In addition, the total global and regional budget for the ICP 2017 cycle is expected to be substantially less than that of ICP 2011, as funding for the programme is beginning to shift from donor financing to domestic resources and ICP activities become more and more integrated into national statistical workplans.

Given the evidence provided throughout this annual review and through our monitoring of the project during the last 12 months, we are satisfied that the project is representing value for money.

Quality of financial management

There is no evidence to suggest that misuse of funds is a major risk or concern. The spending of all grants issued by the Bank is audited upon completion. For grants intended for the support of bank-executed activities, the Bank ensures that no ineligible expenses are charged to the trust funds and it reimburses the trust funds if there is a misuse of funds. For grants supporting recipient-executed activities, the Bank can seek reimbursement from recipients in the case of any misuse.

DFID funding is covered by a formal arrangement with the World Bank in the form of a multi donor trust fund. Under this established mechanism, DFID’s contribution is administered in accordance with the World Banks standard policies and procedures, including its framework to prevent and combat fraud and corruption.

World Bank projects and activities are governed by their Operational Policies & Bank Procedures (OPs & BPs) that are designed to be economically, financially, socially and environmentally sound. The Bank's Operational Manual spells them out, and provides guidance on how to comply with them ("Bank Procedures" and "Good Practices").

Date of last narrative financial report	31/12/2016
Date of last audited annual statement	30/6/2016

E: RISK (½ page)

Overall risk rating: Minor/Major/Moderate/Severe

Minor

Overview of programme risk

DFID and the World Bank have agreed a risk matrix[5], and regularly review and update it. It was last updated in April 2017, and now reflects new risks associated with the ICP 2017 cycle and shift to a permanent programme. A selection of some of the key risks and mitigating actions are as follows:
[5] See quest document 4974275.

Risk: The ICP institutional arrangements and partnerships are vulnerable in the long-run.

Mitigation action: Regional comparisons/updates are underway/planned: Africa 2017; Asia 2016; Commonwealth of Independent States 2014 and 2017; Latin America and the Caribbean 2017; and Western Asia 2012-2013 and 2016. In addition, the Eurostat-OECD region is conducting their frequent annual work programs. The ICP team is supporting regional partners in conducting workshops and technical assistance missions.

Risk: The international community decreases its interest in regional and global results.

Mitigation action: The 47th session of the UNSC endorsed the transformation of the ICP into a permanent exercise, and established a governance structure consisting of Governing Board, Global ICP Unit at the World Bank, Inter-Agency Coordination Group and Technical Advisory Group. The Governing Board and Inter-Agency Coordination Group have held their inaugural meetings in 2016 and are meeting on an annual/bi-annual basis, and the Technical Advisory Group inaugural meeting is planned for May 24, 2017.

Risk: The ICP 2017 results are of low quality.

Mitigating action: Ensuring the quality and completeness of data and metadata is crucial for the programme. The Global ICP Unit and Inter-Agency Coordination Group have put in place a three-stage data validation process (at national, regional, and global levels) to ensure the quality of the data. Also, following a recommendation from ICP Friends of Chair Group, more efforts will be devoted by the Technical Advisory Group to validating the resulting global PPPs from an economic point of view to ensure their consistency and plausibility.

Outstanding actions from risk assessment

The risk matrix and mitigating actions are regularly reviewed and updated by DFID and the World Bank. The risk matrix has been revised since the last review, to ensure that new risks associated with the ICP 2017 cycle and the move to a permanent programme are reflected. The risks are set out under DFID’s 6 risk categories:

- External context
- Delivery
- Operational
- Safeguards
- Fiduciary
- Reputational

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Project delivery is generally on track with agreed timescales. A small amount of uncommitted funds (around $250,000) are expected to remain in the MDTF by the planned end date of the project (30th June 2017). A no-cost extension to 31st December 2017 has therefore been agreed, to allow these funds to be used for interim activities and preparations for the 2017 cycle.

Performance of partnership (s)

The working relationship between DFID and the World Bank Global Office team has proved to be effective over the project term through regular meetings and dialogue. The Global Office has provided DFID with regular updates on project developments and timely responses to DFID requests for information, including the receipt of progress and financial reports.

A strong governance structure is in place for the management and implementation of the ICP; a new ICP Governance Framework was published in November 2016, which takes into account recommendations of the evaluation of ICP 2011 and the move to a permanent programme. The governing bodies include UNSC, an ICP Governing Board, the ICP Inter-Agency Coordination Group (IACG), a Technical Advisory Group and Task Forces, and the National Implementing Agencies. The IACG consists of the World Bank, who were selected by UNSC to act as the Global Implementing Agency, and the Regional Implementing Agencies.

The World bank continues to manage any Procurement activities under this project in accordance with their internal standard guidelines and procedures covering expenditures allocated to goods and services. It works to ensure that procurement in Bank-financed projects and programs is conducted in accordance with its Articles of Agreement, which require that loan proceeds are used only for the purposes for which the loan, grant, or credit was granted. The Procurement Policy and Services Group of the World Bank are charged with providing the Policy and Guidance necessary to carry out this mandate for the Bank’s operational clients.

Asset monitoring and control

The World Bank does not use this trust fund to purchase any assets or equipment. Any assets or equipment purchased for this project were funded from the World Bank’s regular budget.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

At its forty-fifth session (in March 2014), the United Nations Statistical Commission (UNSC) established the Friends of the Chair (FOC) group to carry out an independent evaluation of the 2011 round. The World Bank submits annual reports[6] on the ICP to the UNSC. The forty-sixth session of the UNSC in March 2015 discussed the initial FoC report on ICP[7]. In March 2016, the FoC group submitted its final evaluation report to the UNSC at its forty-seventh session. This report highlighted a number of positives about the 2011 ICP Round, including: (i) improved availability and use of PPPs; (ii) significant improvement in the methodology; (iii) increased capacity and knowledge of staff; (iv) improvements in quality of data and metadata
[6] http://web.worldbank.org/WBSITE/EXTERNAL/DATASTATISTICS/ICPEXT/0,,contentMDK:22388301~pagePK:60002244~piPK:62002388~theSitePK:270065,00.html
[7] http://unstats.un.org/unsd/statcom/doc15/2015-14-ICP-FOC-E.pdf

Following the evaluation, key decisions on the future of ICP were made at UNSC[8]. These include: instituting the ICP as a permanent element of the global statistical work program and conducting price collection more frequently; adopting a flexible approach for estimating PPPs with surveys spread over a three-year cycle to lower country burden, starting from the ICP 2017 comparison; exploring closer alignment of the ICP and CPI surveys to further reduce country burden and enhance the quality of price statistics; and linking ICP capacity building efforts to enhance statistical capacity for monitoring the SDGs. The UNSC also recommended establishing an efficient governance structure; this has now been established, as set out in the new ICP Governance Framework in November 2016.
[8] A full summary of these decisions can be found on Page 16 of the report of the 47th session of the UN Statistics Commision: http://unstats.un.org/unsd/statcom/47th-session/documents/Report-on-the-47th-session-of-the-statistical-commission-E.pdf

In October 2016, the use of PPPs in setting the International Poverty Line (IPL), and therefore the count of the global poor, was discussed in the report ‘Monitoring Global Poverty: Report of the Commission on Global Poverty’. One recommendation in the report was that new PPPs should not be used to update the IPL again before 2030. However the report also recognised the important of PPPs produced by ICP by stating that “There is little doubt that, come 2030 and the establishment of new global goals, the PPPs will have an important role to play in the setting of these goals”. In their covering note, the World Bank accepted this recommendation, but left open the possibility that future PPP rounds might be used again to inform the construction of the IPL, even before 2030, if they are satisfied that the ICP methods have substantially stabilized over at least two ICP rounds.

Gender

The ICP focuses on producing statistics which, due to their nature, cannot be disaggregated by gender. However, PPPs are a global public good and should be available for all to use. Additionally, new capacity building activities undertaken by ICP will be conducted in a gender-sensitive manner, ensuring that women have equal access to training activities.

Monitoring progress throughout the review period

Throughout 2016/17, DFID has monitored progress in ICP through a number of methods, including:

- Regular correspondence with the World Bank ICP Global Unit
- ICP Quarterly Newsletters
- ICP Report to UNSC, March 2017
- ICP Report to Donors, April 2017 (Quest number 5755808)

The review process was conducted by Lucy McDougall (Assistant Statistician in the Data for Development team) duiring April/May 2017.

Consultation during this process was conducted with the following people:

- Kenny Bambrick, Senior Statistician and Team Leader, Data for Development Team
- Nada Hamadeh & Grant Cameron, World Bank ICP Global Unit
- Andy Murray, DFID Statistics Advisor (Peer Review)

This Annual Review was informed by:

- Terms of Reference (Quest number: 5755409)
- Annual ICP Report to Donors (Quest number 5755808)
- ICP Value for Money framework (Quest number 5755791)
- ICP risk matrix (Quest number 5755807)
- ICP logframe (Quest number 5755406).
- Regular discussions with relevant World Bank staff throughout the last 12 months. Progress was also discussed at the annual meeting in Washington in December 2016.
- Other ICP documentation, such as the Governance Framework and other resources published on the ICP website.
Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process