## Annual Review Template – from April 2020

Title: Overseas Development Institute (ODI) Fellowship Scheme 2015-2020
Programme Value £ (full life): £19.7 million		Review date: September 2020
Programme Code: 300288	AMP start date: 01/04/2015	AMP end date: / 31/03/2021

Summary of Programme Performance
Year	2013	2014	2015	2016	2017	2018	2019	2020
Overall Output Score	A	A+	A+	A	A	A	A	A
Risk Rating	Moderate	Moderate	Minor	Minor	Minor	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.fcdo.gov.uk/iati_documents/5761575.odt
DevTracker Link to results framework:	http://iati.fcdo.gov.uk/iati_documents/25942304.xlsx

[Scoring your programme

Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Overseas Development Institute (ODI) Fellowship Scheme is a well-established programme addressing the need for staff with technical skills in developing country public institutions. It seeks to address this issue through the recruitment and posting of early career economists and statisticians of different nationalities to work as civil servants in developing country institutions on two-year postings. DFID’s/FCDO’s support has been predicated upon the principle set out in the Business Case that Fellows can both add to and build capacity and improve the effectiveness of governments in developing countries and the international development community. The Fellowship Scheme is a demand-led programme based on a model of costs shared between employing governments and ODI (funded by donors). It has developed a strong reputation within the field of international development.

The UK is a long-standing funder of the Scheme and DFID has worked closely with the ODI to continually improve the programme and drive value for money. In 2015, DFID began a new phase of support to the Scheme. Under the current agreement, DFID has funded up to 48 economists and statisticians a year. It has provided a five-year Accountable Grant (AG) to the ODI to support the Scheme with £17 million over the five financial years 2015/16 to 2019/20 inclusive. DFID agreed a one-year extension of £2.7 million with ODI for the financial year 2020/21, to allow time for a performance evaluation of the scheme to be undertaken and which will inform advice to Ministers on future funding. This is now underway. Funding for this financial year was lower than for previous years, to keep total funding within Directors’ delegated authority. ODI was also asked to make further savings for this financial year in response to an ODA prioritisation exercise and, in August 2020, agreed to find £150,000 of savings. As a consequence of these reductions in funding, no new FCDO-funded Fellows will be posted this year.

The Covid-19 pandemic has disrupted the Scheme over the review period. Most DFID-funded Fellows left their countries of posting in March 2020. ODI has reported that, on the whole, Fellows have succeeded in staying in touch with their supervisors and teams and have managed to work reasonably effectively, even if they were working from home in their country of posting or if they were back in a home or third country.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Overall, the programme has scored an ‘A’ as in the past years – but with some caveats. The first of these is that Output 1 has a weight of 70%. Therefore, that output, for which all but one of the indicator milestones were met, heavily determines the overall programme score, despite all but one of the indicators for the other two outputs being off track.

However, while the other two outputs scored ‘B’ and ‘C’ respectively, performance appears more positive than these scores suggest, indicating that the overall ‘A’ rating is reasonable. For the second output, on Fellows gaining and sharing practical experience through their Fellowship postings, both indicators are off track. For one of these (the proportion of Fellows rating their Fellowships as successful) the milestone was only narrowly missed. For the other (the proportion of Fellows going on to work in development), the measurement of the indicator is poor and does not reflect the high proportion of Fellows that do remain in development. For the third output, on the management of the Scheme, one of the indicators that was off track fell only slightly short of the milestone. For another indicator, on how well Fellows felt they had been supported by ODI, the questionnaire responses against which the indicator is measured are from Fellows who started their Fellowships in 2017. The experiences of these Fellows may not, therefore, reflect more recent improvements made by ODI.

The second caveat is that one of the indicators for the heavily weighted first output (the proportion of employers rating DFID-funded Fellowships as successful in increasing capacity of local staff) is not very challenging as currently defined, not all supervisors provided a response and those that did had an incentive to answer positively. The evidence that this indicator provides on the success of the programme in building capacity is therefore weak. Not only is the evidence weak on the programme’s effectiveness in this regard, the lack of clarity amongst stakeholders around expectations for capacity building gives cause for concern that the Scheme may not be meeting FCDO’s expectations in this area. This concern has been raised in previous Annual Reviews. Qualitative feedback from End of Fellowship Questionnaires completed by supervisors does give some assurance of some capacity building taking place, but more comprehensive and detailed evidence is needed. The ongoing evaluation should provide this. Furthermore, clear expectations against which to judge performance on capacity building are needed. FCDO should work collaboratively with ODI to define these before a decision on further funding for the Scheme is made.

This Annual Review was conducted by the consultancy firm contracted to carry out the ongoing independent evaluation of the Fellowship Scheme. In light of this evaluation, which will collect a large amount of qualitative and quantitative data from Scheme stakeholders, no primary data collection was conducted for this Annual Review. It is based on review and analysis of documentation and data provided by ODI and on discussion with ODI staff where clarification or further detail was required. ODI staff were very responsive to all requests for assistance. The review period for this Annual Review is April 2019 to June 2020. The Annual Review in previous years has covered financial years; this year’s has been delayed because of the pandemic and the timeline extended. This has the advantage of bringing the review period closer in line with the Scheme’s annual cycle, which approximates to academic years.

Major lessons and recommendations for the year ahead [1/2 page]

Last year’s Annual Review recommended that DFID should commission an independent evaluation of the Fellowship Scheme. This has now been commissioned. After some delays, resulting from a temporary freeze on new activity while an ODA resource prioritisation exercise was carried out, it began in August and is due to report by the end of January 2021. It was expected that the evaluation would have been completed earlier in the FY and would have informed the review of certain output indicators, in line with the previous AR’s recommendations. This has not yet taken place.

The evaluation will address the following objectives:
1. Impact: To evaluate how effectively the Fellowship Scheme contributes to sustainable capacity building
2. Theory of Change (ToC): To review and test the theory of change and log frame /assessment criteria
3. Delivery model: To assess how ODI’s delivery model compares to other similar capacity building Schemes funded by DFID (now FCDO) and other UK Government departments
4. Diversity and access: To assess how the Scheme’s approach to diversity and broadening access in recruitment compares with identified best practices
5. Safeguarding and duty of care: To assess whether the ODI Fellowship Scheme’s approach to and policies on safeguarding and duty of care of and on behalf of Fellows is sufficient
The evaluation will contribute to responses to some of the recommendations of this Annual Review.

The main recommendations for the year ahead are:

Evidence on capacity building needs to be strengthened.

Clear expectations against which to judge the success of Fellowships, including in terms of performance on capacity building, are needed. FCDO should work collaboratively with ODI to define these. FCDO also need to work with ODI to ensure that Fellows and supervisors share these expectations and can therefore work together to monitor and achieve them. The ongoing evaluation should contribute to this thinking and should consider how the success of Fellowships can be measured against expectations as part of ongoing monitoring. Clearer expectations should be embedded in performance metrics for any future funding arrangement.

The ToC and log frame/assessment criteria for further FCDO support for the Scheme should be revised and deepened. There are a number of weaknesses in the ToC that should be addressed as part of the ongoing evaluation. There are also inconsistencies between the ToC and the logframe which need to be addressed so that FCDO’s monitoring of the programme is consistent with the ToC. This Annual Review also highlights a number of weaknesses in the indicators and assessment criteria within the logframe which should be addressed and again, should be embedded in performance metrics for future funding.

The two previous Annual Reviews have both recommended increasing the size of the management team for the Scheme. This was in response to the increased demands placed on the ODI Fellowship Management team. However, in response to budget pressures, ODI has reduced the size of this team. This reduction represents a risk to the achievement of the programme’s aims and should be monitored. FCDO and ODI should make an assessment of the optimal size of the team and ensure that future FCDO funding reflects this.

The Business Case was based on the premise that the biggest impact would be made in LIC and FCAS countries whereas the 2018 Annual Review challenged this assumption. Last year’s Annual Review recommended further assessment of where and how fellows are likely to have the greatest impact in technical capacity building. FCDO and ODI need to consider this issue collaboratively and make a clear decision on the future direction for FCDO-funded Fellows before any further funding agreements are put in place. The recent creation of FCDO is a natural opportunity for such an assessment.

There has been a lack of clear positive movement in the indicator used to measure ODI’s performance in supporting Fellows. The evidence on which progress against this indicator is measured is based on the reported experiences of Fellows who started their Fellowships in 2017. The ongoing evaluation should provide a more current view of the support to Fellows around safeguarding and duty of care to enable FCDO and ODI to drive improvements.
Progress on most of these recommendations will be supported by the ongoing evaluation. The recommendations should all be acted upon before further funding for the Scheme is agreed.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

Figure 1: Theory of Change from Business Case

The ToC within the Business Case was set out in the above diagram. The text within the Business Case further described how Fellows would fill capacity gaps through providing technical skills and contribute to better decision making in developing country institutions and better economic management within developing countries, thereby leading to poverty reduction. The Business Case argued that the Scheme corresponds well with evaluation findings on effective Technical Cooperation because host institutions have ownership and control over the work of the Fellow. The Business Case envisaged that the Fellows would both provide immediate technical capacity and help to build staff capacity in their host institutions. How this capacity building should happen was not elaborated on within the Business Case.

The Business Case also described how the Scheme brings junior economists and statisticians into international development and gives them valuable experience. These benefits were not depicted in the graphical ToC.

The ToC has not been updated since the Business Case was written in 2015. However, the logframe was comprehensively revised during the second half of 2017, in line with previous Annual Review recommendations. Various changes to the original logframe outcome and impact indicators have been improvements, making the indicators more specific. There has also been some movement of indicators between outcomes and outputs. The most recent logframe puts more weight on the ‘sustainable capacity building’ goals of the Scheme than the original logframe did. The mechanisms for this should be better reflected in the ToC going forward.

There are a number of weaknesses in the ToC that should be addressed as part of the ongoing evaluation, which will revise and deepen both the ToC and log frame/assessment criteria and ensure that the two are consistent. The TORs for the performance evaluation acknowledge these weaknesses.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

Last year’s Annual Review concluded that “there is no clear and well evidenced demonstration of programme impact and results, particularly in terms of practical capacity building in countries where Fellows are placed.” This conclusion still largely holds true for this review period based on the logframe impact and outcome indicators and milestones against which the programme’s progress against expectations can be judged.

The intended impact of the programme, in the logframe, is “The ODI Fellowships Scheme makes a quantifiable contribution to improved capacity and effectiveness of developing countries and the international development community to deliver poverty reduction, in line with the UK's Aid Strategy.”

One impact indicator is a longer-term assessment of the Scheme’s impact, including sustainable capacity building. The available evidence on which to make a judgement on the achievement of this indicator is weak. ODI staff describe extremely positive verbal feedback from supervisors. Qualitative feedback from supervisors within their responses about the 2017-19 cohort in the supervisors’ End of Fellowship Questionnaire was similarly positive about Fellows’ contributions. However, this qualitative feedback does not provide a comprehensive picture of the performance of Fellows across the Scheme. The available evidence of impact from measures mentioned in the logframe is weak. The logframe impact indicators include the percentage of supervisors responding, in the End of Fellowship Questionnaire, that DFID-funded Fellows have contributed to sustainable capacity building “somewhat” or “a lot”. This is both an impact, outcome and output indicator. The strength of evidence it provides is weak because supervisors are unlikely to provide negative feedback for fear of not being allocated further Fellows and because not enough supervisors complete the questionnaire. Moreover, there seems to be inconsistency in levels of expectation around capacity building from DFID, ODI, Fellows and host governments, so it is likely that supervisors are not judging the Scheme’s impact on capacity building in the same way other programme stakeholders might. The logframe impact indicators also refer to ‘Country Strategy Notes’ which should include a longer-term assessment of Scheme impact. Some examples of these documents have been reviewed and it is clear that they do not serve this purpose.

There is reasonably strong evidence that the other impact indicator on Fellows staying in development has been met. The logframe also contains an impact indicator for “Proportion of ODI Fellows who go on to work in international development in the public or private sectors (broadly defined)”. The milestone for the 2019/20 financial year was that 80% of Fellows continue to work in development (broadly defined) immediately after placement and remain in development-related roles 3 and 5 years after completing their Fellowships. 47% of DFID-funded Fellows from the 2017-19 cohort who completed the End of Fellowship Questionnaire reported that they were going on to a development-related job immediately after the Fellowship, although this is a poor indicator and is likely to underestimate the proportion of Fellows going on to work in development after their Fellowship. Of Fellows from the 2014-16 cohort for whom information is available (not just the DFID-funded Fellows), 84% (36 of 43) remained in development roles 3 years after completing their Fellowships.

There are two outcome indicators. The first is the same as one of the impact indicators, i.e. the percentage of supervisors responding, in the End of Fellowship Questionnaire, that DFID-funded Fellows have contributed to sustainable capacity building “somewhat” or “a lot”. While the milestone has been met, as described above, the strength of evidence this indicator provides is weak and, as such, there is a risk that the Scheme might not be performing sufficiently well in achieving this outcome. The second outcome indicator is “Demand for and value of Scheme demonstrated by local contributions from host governments to Fellowship costs”. The milestone for the 2019/20 financial year is 90% in stable countries with established Fellowships and 80% in FCAS and new posts. In April 2020, this figure was 81% in stable countries with established Fellowships and 88% in FCAS and new countries. The scheme therefore over-achieved against the milestone for FCAS and new posts, but under-achieved for stable countries with established Fellowships.

The ongoing independent evaluation of the Fellowship Scheme will provide better evidence on the impact of the Scheme.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Available evidence on the programme’s impact is weak. The ongoing evaluation should address this lack of robust evidence, after which a more secure judgement can be made on whether the programme represents value for money.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Governments in low income, high poverty or FCAS countries are provided with high calibre junior professional economists and statisticians where gaps in local capacity exist
Output number:		1	Output Score:	A
Impact weighting (%):		70%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1. Number of DFID–funded placements each year. / Starters in each cohort year completed Fellowships (21 months min) at cohort end.	38-48 starters / 90% completion rate	On track: Of the 51 new Fellows being posted in the 2019-21 cohort, 42 are funded by DFID, of whom four (10%) were part of the statistics stream. / Broadly on track: For the 2017-19 cohort, 88% (36 out of 41) of DFID funded starters completed their Fellowships (at least 21 months). Three ended their placements between 21 and 24 months.
1.2. Proportion of employers rating DFID-funded Fellowships as successful; feedback provides evidence of capacity building.	85% satisfaction rate (somewhat, a lot) maintained or exceeded	On track: 100% of the employers that responded to the End of Fellowship Survey (42% “somewhat”, and 58% “a lot”) for the 2017-2019 cohort. / 76% of the employers (36 out of 41) hosting DFID funded Fellows responded to the survey in 2019. This is a significant improvement on previous years but is still too low.
1.3. Level of demand for Fellows increases, evidenced by new countries expressing interest in or joining Scheme.	Investigate at least one new country per year	On track: Several new countries have expressed interest in the Fellowship Scheme over the review period and the Fellowship Scheme team have investigated these, resulting in one reassignment to Sudan.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Indicator 1.1:

For the 2019-20 cohort, 42 of the 51 new Fellows posted were funded by DFID, of whom four (10%) were part of the statistics stream. This is in line with the logframe target. DFID is funding posts in 17 countries. Of these, all but three posts were made to low income or lower middle income countries (of the remaining three, two were to Guyana and one was to Sri Lanka).

ODI will not post any new FCDO-funded Fellows in 2020, i.e. in the 2020-22 cohort. This is because of the extension funding from DFID for the financial year of 2020/21 was lower than the annual funding for previous years. Also, DFID expressed concern that starting new placements would be inappropriate while existing Fellows were withdrawn from post as a result of the Covid-19 pandemic.

For the 2017-19 cohort, 88% (36 out of 41) of DFID-funded starters completed their Fellowships (at least 21 months). Three ended their placements between 21 and 24 months. This is slightly below the target of 90%. However, it is an improvement on the 2016-18 and 2015-17 cohorts, where 76% (37 out of 49) and 75% (38 out of 51) respectively completed their Fellowships. This high level of early terminations looks set to continue for the next cohort: for the 2018-20 cohort; five of the DFID-funded Fellows had, as of the end of 2019, terminated early and seven had already been reassigned.

Of the DFID-funded Fellows from the 2017-19 cohort who terminated early:
- four left because of frustration with their post
- two left for medical reasons
- one got a new job
- one left for personal reasons
- one left for studies
As in the previous two cohorts, the majority of those terminating early did so because of frustration with their post or because they chose to pursue another job or course of study. For the 2017-19 cohort, this was the case for six of nine of those who terminated early. For the 2016-18 cohort, this was the case for seven of 12. For the 2015-17 cohort, this was the case for 11 of 15.

An exit interview and a formal feedback survey especially for Fellows dissatisfied with their job or posting for all Fellows and supervisors where a placement is terminated early had been recommended by the March 2018 Annual Review. ODI have confirmed that no such exit interviews take place. However, all terminating Fellows are asked to fill in the End of Fellowship Questionnaire. Of those Fellows from the 2017-19 cohort who terminated early, four of nine Fellows completed an End of Fellowship Questionnaire. The questionnaire has been updated to include questions asking about reasons for early termination and what ODI could have done to prevent this. However, in practice very little detail was captured in these questionnaires on this point. A termination log is shared with FCDO – but lacks details on causes behind dissatisfaction with posts. Some very limited detail of the reasons behind terminations is included in quarterly reporting.

Of the 42 DFID-funded Fellows in the 2017-19 cohort, 8 were reassigned to another post. This figure is not unusual in comparison with other cohorts. Although reassignments show that ODI is responsive when a Fellowship is not working as expected, an increasing trend could pose opportunity costs, with value for money implications, and reputational risk. When considered together, the number of Fellows who either get reassigned or terminate early is high.

ODI staff have suggested that many early terminations involve the Fellow leaving only a short time before their Fellowship was due to end. If this is the case, the significance of the rate of early terminations would be less. Given the lack of adequate information on the reasons behind early terminations and reassignments, the ongoing evaluation should investigate the reasons behind early terminations and reassignments and the extent of the risk they pose to both delivering the programmes aims and value for money.

Indicator 1.2:

In the End of Fellowship Questionnaire for supervisors, for the DFID-funded Fellows from the 2017-19 cohort, 100% of supervisors reported evidence of sustainable capacity building. However, the indicator is not very challenging and not all supervisors provided a response. Supervisors were asked whether the ODI Fellow helped to increase capacity among local staff – this is the basis for this indicator. 42% of supervisors who completed the questionnaire responded ‘somewhat’ (13 out of 31 responses). 58% responded ‘a lot’ (18 out of 31 responses). However, the only other option for responses was ‘not at all’, which makes this 100% positive response unsurprising and a very low bar. A 100% ‘satisfaction rate’, defined in this way, has similarly been achieved for the previous three cohorts.

Out of the 31 respondents, 24 (77%) rated the performance of the Fellow as ‘very good’ and 6 rated it as ‘good’ (19%). One respondent (3%) rated a Fellow’s performance as ‘average’. 71% of respondents (22 out of 31) were ‘very satisfied’ with the arrangements with ODI, 26% were ‘satisfied’ (8 out of 31) and one was ‘neutral’ (3%).

The 2019 Annual Review noted that only 50% of the employers (23 out of 46) hosting DFID-funded Fellows in the 2016-18 cohort responded to the survey and concluded, therefore, that the survey wasn’t conclusive. For the 2017-19 cohort, this figure was 76% (31 out of 41). This is a big improvement on the previous year, but still leaves the results of the survey as inconclusive. ODI relate this increased response rate to having pushed supervisors harder to complete the questionnaire in 2019.

The qualitative feedback received from the supervisors on the same survey provides some evidence of capacity building, including through the Fellows running training sessions for colleagues and setting a good example in terms of work ethic. However, more comprehensive and detailed evidence is needed.

In addition to the End of Fellowship Questionnaire for the 2017-19 cohort, completed at the end of 2020, ODI also asked supervisors of Fellows from all cohorts to complete a ‘Fellowship Appraisal’ form in May and June 2020. This was done because no country visits were conducted this year due to the Covid-19 pandemic, so feedback was sought in this way instead. Responses were very positive. 100% of the supervisors of DFID-funded Fellows that completed the ‘Fellowship Appraisals’ in May and June 2020 thought that the current fellow has helped to increase capacity amongst local staff (68% “a lot”, 32% “somewhat”). Moreover, when asked to rate the performance of the current Fellow, 71% of supervisors rated their Fellow as “very good”, 25% as “good” and 4% as “average”. A total of 83 returns had been received for DFID-funded and other Fellows, out of 97 Fellows in post at the time (86%).

34 out of 41 (83%) of the DFID-funded Fellows from the 2017-19 cohort submitted End of Fellowship Questionnaires. Only 15% of the Fellows who completed the questionnaire responded that they had contributed ‘a lot’ to sustainable capacity building, in contrast to the more positive views of supervisors who completed the questionnaire (58% responded ‘a lot’). This disconnect between the views of Fellows and supervisors on the success of Fellows in capacity building has been noted in previous Annual Reviews. The previous Annual Review in March 2019 speculated that this disconnect might be caused by different expectations of supervisors and Fellows or the incentive for supervisors to give positive responses so as not to lose the low-cost, high-quality resource of an ODI Fellow. The DFID survey of ODI Fellows conducted as part of the 2018 Annual Review provides evidence to substantiate concerns about the extent of capacity building that fellows are contributing to. This survey found that most Fellows reported that the majority of their capacity building activities were limited to relatively basic tasks (sharing documents, word processing, English language and report writing). Few Fellows shared technical economics or statistical knowledge with their colleagues within host departments.

The last Annual Review from March 2019 reported that ODI would be identifying “realistic measurable capacity building expectations” with the 2018-2020 cohort which should minimize the disconnect in expectations between Fellows and supervisors. The reviewers urged that the effectiveness of these actions should be assessed in the next review cycle. We were told by ODI staff that ODI makes Fellows aware of its ‘capacity building statement’, which suggests ways that Fellows could build capacity, but has not attempted to measure progress against these expectations. ODI described ongoing discussion with DFID about what is meant by capacity building and the expectations for the Scheme. FCDO needs to ensure that any future funding agreements with ODI for the Fellowship Scheme are based on a shared understanding of expectations around capacity building. FCDO also need to work with ODI to ensure that Fellows and supervisors share these expectations around capacity building and can therefore work together to monitor and achieve them.

Indicator 1.3:

Several new countries have expressed interest in the Fellowship Scheme over the review period and the Fellowship Scheme team have investigated these, resulting in one reassignment to Sudan. Over the review period for this Annual Review (April 2019 to June 2020), various new countries expressed interest in the Fellowship Scheme. Members of the Fellowship Scheme team visited Cape Verde, Senegal, Lao PDR, Nepal and Angola as a result of interest expressed, but these visits did not result in any placements in new countries for the 2019-21 cohort. Following interest from a Minister in Sudan and the local DFID office, ODI planned to reassign one Fellow to Sudan in early 2020. The posting was to commence only after ODI’s Global Security team had visited Khartoum and the Fellow had completed Hostile Environment Awareness Training (HEAT) at the end of March. However, the HEAT training ended up being cancelled due to Covid-19. The Fellow has been working remotely. A second Fellow from the 2020-22 intake has accepted a second posting in Sudan. At this stage it is not clear when he will commence work. The Fellowship Scheme also plans to place two Fellows in Pakistan when conditions permit.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The Business Case for this programme emphasised capacity building by Fellows – their support to the learning of colleagues in the ministries they are working for, as well as the gap-filling capacity they directly provide – and how this would drive the most development impact possible from each placement. Before FCDO agrees further funding for the Scheme, FCDO needs, in collaboration with ODI, to clearly define its own expectations around capacity building. FCDO should consider what degree of capacity building would constitute sufficient value for money, i.e. what level of performance is good enough, against which performance in the future could be judged.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no changes to this output during the last year. Changes were recommended to indicator 1.2 in last year’s Annual Review. These have not been made yet, for the reasons set out in Section A. The ongoing evaluation should consider whether such revisions would be appropriate (see below). The ongoing evaluation will review and test the theory of change and log frame, with a view to revising and deepening both the theory of change and log frame/assessment criteria and ensuring that the two are consistent.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Last year’s Annual Review recommended revising indicator 1.2. The indicator requires assessment of ‘Proportion of employers rating DFID-funded Fellowships as successful; feedback provides evidence of capacity building’. The rate of returns on the end of Fellowship survey on which the assessment is based was only 50% in that review period. Thus, last year’s Annual Review recommended that the indicator should be revised to reflect that the responses may not be reflective of all the supervisors’ experiences. Last year’s Annual Review also suggested that consideration should be given to adding an indicator on increasing the proportion of employers that respond to the end of Fellowship survey. No such changes have been made yet. The ongoing evaluation should consider whether such revisions would be appropriate.

Looking forward, this Annual Review further notes that one of the milestones for indicator 1.2 is not, as currently measured, sufficiently challenging. Supervisors were asked in the End of Fellowship Questionnaire whether the ODI Fellow helped to increase capacity among local staff. 42% of supervisors who completed the questionnaire responded ‘somewhat’ (13 out of 31 responses). 58% responded ‘a lot’ (18 out of 31 responses). However, the only other option for responses was ‘not at all’, which makes this 100% positive response unsurprising and a very low bar. There is a disconnect between the feedback on this point from supervisors and Fellows and we suspect that there is an incentive for supervisors to give positive responses. We recommend that the End of Fellowship Questionnaire for supervisors is altered to allow for a greater range of responses to this question for supervisors, to include the option of ‘a little’ which is available in the questionnaire for Fellows. Furthermore, we recommend that the ongoing evaluation should consider how the success of Fellows in sustainably building capacity can be measured against expectations. ODI should also strive to further improve the response rate for feedback from supervisors.

FCDO needs to ensure that any future funding agreements with ODI for the Fellowship Scheme are based on a shared understanding of expectations around capacity building. FCDO also need to work with ODI to ensure that Fellows and supervisors share these expectations around capacity building and can therefore work together to monitor and achieve them.

Given the lack of adequate information on the reasons behind early terminations and reassignments, the ongoing evaluation should investigate the reasons behind these and the extent of the risk they pose to both delivering the programmes aims and value for money.

Output Title	Postgraduate economists and statisticians gain and share practical experience through their Fellowship postings.
Output number:		2	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Proportion of DFID-funded Fellows rating Fellowships as successful and feedback provides evidence of capacity building	Over 90% of Fellows completing their placements describe their Fellowships as "successful" or "very successful"	Off track: Less than 90% of DFID-funded Fellows from the 2017-19 cohort thought their Fellowship had been ‘successful’ or ‘very successful’, both for them and for their host organisation. / 85% of the DFID-funded Fellows from the 2017-19 cohort who completed an End of Fellowship Questionnaire rated the overall success of their Fellowship posting as ‘successful’ or ‘very successful;’ as far as the organisation they worked for is concerned. 82% rated it as ‘successful’ or ‘very successful’ as far as they personally were concerned.
2.2 Proportion of DFID-funded Fellows going on to work in development	At least 75% go on to development-related jobs immediately after Fellowship	Off track: 47% of DFID-funded Fellows from the 2017-19 cohort who completed the End of Fellowship Questionnaire reported that they were going on to a development-related job immediately after the Fellowship. / 82% of these Fellows planned to stay in development immediately after their Fellowship.

Indicator 2.1:

Less than 90% of DFID-funded Fellows from the 2017-19 cohort thought their Fellowship had been ‘successful’ or ‘very successful’, both for them and for their host organisation. 85% (29 out of 34) of the DFID-funded Fellows from the 2017-19 cohort who completed an End of Fellowship Questionnaire rated the overall success of their Fellowship posting as ‘successful’ or ‘very successful;’ as far as the organisation they worked for is concerned. Of these, 32% (11 out of 34) rated it as ‘very successful’ and 53% (18 out of 34) as ‘successful’. 82% rated it as ‘successful’ or ‘very successful’ as far as they personally were concerned. Of these, 35% (12 out of 34) rated it as ‘very successful’ and 47% (16 out of 34) as ‘successful’.

These figures are largely in-line with the two preceding cohorts. For the 2016-18 cohort, the figure was 90% rating their Fellowships as ‘successful’ or ‘very successful’. For the 2015-17 cohort, this figure was 82%. However, it is not clear from the previous Annual Review whether these figures concern the organisations these Fellows worked for or the Fellows personally.

However, Fellows were less positive about their contributions to capacity building than they were about the overall ‘success’ of their Fellowships. 15% of the same survey respondents from the 2017-19 cohort felt as though they had contributed ‘a lot’ to sustainable capacity building, 56% thought they had made ‘some’ contribution and 29% thought they had contributed ‘a little’. This is a high proportion of Fellows reporting only ‘a little’ contribution to capacity building. The proportion of Fellows who thought they had contributed ‘a lot’ to capacity building (15%) was very low relative to the same figure for supervisors (58%). This indicates that there is a mismatch between Fellows’ and supervisors’ expectations around what ‘a lot’ of capacity building is. There is a need to clarify expectations around what capacity building should be expected and to ensure that these expectations are shared.

Indicator 2.2:

47% of the DFID-funded Fellows from the 2017-19 cohort who completed the End of Fellowship Questionnaire reported that they were going on to a development-related job immediately after the Fellowship, which falls well short of the milestone of 75%. 38% reported that they ‘Did not know yet’ what they would be doing immediately after the Fellowship. However, 82% of these Fellows planned to stay in development immediately after their Fellowship. This latter indicator suggests that Fellows will go on to make further contributions to development. Nevertheless, the indicator milestone against which this Annual Review must make an assessment sets a clear expectation of movement by three quarters of Fellows straight into another development related job. This is far from being achieved, although the proportion may rise as those unsure of their destination secure their next employment. The previous Annual Review recommended that it would be helpful to ask these Fellows to update on their next destination. Then, the phrasing of the milestone might be adjusted (if, for example, the current reality is that development roles are largely being secured but often not ‘immediately’). This should be considered through the ongoing evaluation. Of Fellows from the 2014-16 cohort for whom information is available (not just the DFID-funded Fellows), 84% (36 of 43) remained in development roles 3 years after completing their Fellowships. This provides evidence that the current indicator is not adequately reflecting the high proportion of Fellows that do remain in development.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

On the basis of the evidence available to the review team, it is not possible to assess VFM with any accuracy.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no changes to this output during the last year. The ongoing evaluation will review and test the theory of change and log frame, with a view to revising and deepening both the theory of change and log frame/assessment criteria and ensuring that the two are consistent.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The previous Annual Review concluded that there is need for clarity on what a ‘successful’ Fellowship is and to have the same parameters for DFID, ODI, Fellows and the host organisations. This need has not yet been addressed. The ongoing evaluation should consider this issue.

The previous Annual Review recommended that the milestone for indicator 2.2 should be reconsidered. Until that point, this indicator seems to have been assessed in part through a proxy indicator of Fellows having an intention to work in the development sector. Yet the wording is specifically about immediate jobs. The previous Annual Review suggested that the indicator could be split into immediate plans and actual situation with a follow-up after, say, a year. This has not yet been done and should be considered through the ongoing evaluation.

Output Title	The Fellowships Scheme is managed efficiently and effectively and offers good value for money. The Fellowship Scheme provides high quality Duty of Care and medical and other emergencies are well managed.
Output number:		3	Output Score:	C
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Proportion of DFID-funded Fellows who feel they were well supported during their placements	At least 80% of Fellows' responses indicate they were well or very well supported	Off track: 68% of Fellows’ from the 2017-19 cohort who completed the End of Fellowship Questionnaire stated that they had been ‘well’ or ‘very well’ supported.
3.2 DFID-funded placements are increasingly aligned with UK Aid Strategy priorities and there is a shift over time to more LIC and FCAS placements	85% of postings in LIC or FCAS countries	Off track: 81% (64/79) of DFID-funded Fellows in post in April 2020 were in either LICs or FCAS. However, it should be noted that DFID has placed greater emphasis on the quality of placements in recent years, rather than the location.
3.3 Fellowship Scheme keeps tight control of costs.	Assessment of highest/lowest unit costs per year	On track: The average cost of Fellowship per year has gone up from £41,097 in FY 2018/19 to £43,221 in FY 2019/20. The average cost for FY2019/20 is the highest it has been over this phase of support to the Scheme. / The cheapest Fellowship was eSwatini and the most expensive was Ethiopia.
3.4 Scheme diversifies sources of funding over time so that DFID-funded posts account for two-thirds of Fellows posted	DFID funding is no more than 70% of total	Significantly off track: At the end of CY2019 DFID-funded posts accounted for 83 out of the 100 Fellows who were in posts (83%).

Indicator 3.1:

Of the 2017-19 cohort, only 68% of DFID-funded Fellows felt “very well” (18%) or “well” (50%) supported by the ODI. There is no evidence of an improvement in this indicator over the last four years, despite improvements to the level of support provided by ODI. (see graph below).

Figure 3: Percentage of Fellows in different cohorts who felt well supported by ODI

However, despite the lack of clear positive movement in this indicator, last year’s Annual Review described and welcomed ‘substantial’ progress made by DFID and ODI on Safeguarding. Since then, in this Annual Review period, ODI has taken further steps around Safeguarding improvements.

ODI has updated its Safeguarding policy. With assistance from DFID, ODI also included a session on Safeguarding in its last Briefing Week in the summer of 2019. The appointment of a new team member in September 2019, who took responsibility for financial management of the Scheme, allowed the Programme Manager to focus more on responsibilities for Safeguarding and general Duty of Care. This action responded to a recommendation from last year’s Annual Review to increase ODI’s management capacity. An immediate action taken as part of the Programme Manager’s new responsibility was to introduce new and better medical pre-screening, introduce screening for all Fellows at the start of their second year (which covers mental health), and ensure that Fellows who had experienced medical and other problems were issued with fit for work certificates by a qualified medical authority prior to returning to work. The screening at the start of Fellows’ second years threw up a number of issues which were followed up with the Fellows concerned by the Scheme’s Programme Manager/Safeguarding Officer. In June 2020, following ODI’s decision to start preparations to return Fellows to their countries of posting, ODI requested its medical screening provider to conduct medical and resilience profiles as part of ODI’s returns plan.

Moreover, Fellows have made considerable use of the CiC Confidential Counselling Service, introduced in 2018, during this Annual Review period. 41 calls were made, six emails sent and nine Fellows received counselling in the 2019/20 financial year. In the first quarter of the 2020/21 financial year, even more use was made of this service by Fellows, with 21 calls made, three emails sent and five Fellows receiving counselling. This is to be expected given the Covid-19 pandemic and should not be seen to reflect negatively on the Scheme.

Recently, the increase in the capacity of the ODI Fellowship Scheme team was reversed in response to budget pressures. ODI has reduced the capacity of the ODI Fellowship Scheme team through the loss of a Programme Administrator and a reduction in hours for a Programme Officer. The ongoing evaluation should consider the implications of this reduction in capacity for the Scheme’s approach to safeguarding and duty of care.

The apparent lack of progress on indicator 3.1 might reflect various aspects of Fellows’ experience on the Scheme, including Safeguarding issues discussed above, but also other areas such as support around maximising the success of their placement or the administrative efficiency of ODI. Some other data from the End of Fellowship Questionnaire reveals issues experienced by the 2017-19 cohort. For example, for DFID-funded Fellows in the 2017-19 cohort who completed this questionnaire:
- 29% felt that they needed more contact from the ODI, compared to 27% for the previous cohort.
- 21% claimed to have faced bullying and 15% harassment in their placements. 21% claimed to have faced sexual harassment at some point.
- Only 35% thought the briefing sessions prepared them well for the postings (29% ‘well’ and 6% ‘very well’). This is lower that for the previous cohort, for whom 48% thought the briefing sessions prepared them well.
Qualitative feedback in the submitted questionnaires included further recurrent issues. For example, some Fellows would have liked more focus from the ODI on setting up postings to ensure that they would be successful, i.e. ensuring employers are clear about what a Fellow ought to achieve and checking in with supervisors to ensure this is happening.

This cohort of Fellows started their Fellowships in 2017, so their experiences may not reflect more recent changes made by ODI in this review period. For example, these Fellows had their briefings some years ago, so their experience does not reflect the recent changes made.

Indicator 3.2:

81% (64/79) of DFID-funded Fellows in post in April 2020 were in either LICs or FCAS, which is lower than the milestone of 85% for 2019-20. Similarly, 80% (66 of 83) of DFID-funded Fellows in post on 31/12/19 were in either LICs or FCAS. This indicator has been judged to be on-track against the 85% milestone in the previous two annual reviews. It is worth noting however that DFID in recent years has placed greater emphasis on the quality of placements, rather than their location. The recent creation of FCDO is an opportunity to consider whether the capacity development objectives of the scheme might be better served by expanding into MICs.

DFID-funded Fellows in post in non LIC or FCAS countries on 31/12/19 were in Ghana, Vanuatu, Guyana, Thailand, eSwatini, Djibouti, South Africa and Sri Lanka. This was also the case in April 2020.

Indicator 3.3:

The average cost of Fellowship per year has gone up from £41,097 in FY 2018/19 to £43,221 in FY 2019/20. The average cost for FY2019/20 is the highest it has been over this phase of support to the Scheme. The cheapest Fellowship was eSwatini and the most expensive was Ethiopia. The average cost per Fellow to ODI varies according to the country of posting and the level of local salaries. As the Scheme has moved into lower income and more fragile environments, the average cost per Fellow can be expected to increase. This is taken into account when ODI determines how many Fellows can be posted to particular countries.

Figure 4: Average cost of a Fellow for a year over time

Financial year	Average cost of Fellowship
2015/16	£40,412.15
2016/17	£40,112.96
2017/18	£38,314.85
2018/19	£41,097.48
2019/20	£43,220.62

The Fellowship Scheme implements a number of measures to ensure costs are kept to a minimum and value for money is achieved. For example, housing allowances are reviewed annually based on information provided by an external provider ECA. Housing allowances can be lowered as well as raised as a result of this review. The insurance policy which covers Fellows is reviewed annually with ODI’s broker to ensure the policy is competitive and offers the greatest value for money.

The logframe includes a ‘target’ for this indicator of ‘Evidence of costs being managed well and offering good value for money, commensurate with Duty of Care requirements’. There is evidence that this is the case.

Indicator 3.4:

At the end of 2019, a total of 100 Fellows were distributed across 25 countries. 83 of these Fellows were DFID-funded (83%). By the end of March 2020, some further progress had been made, with 80 of 99 Fellows being funded by DFID (81%). However, this indicator is significantly off track against a target of 70%. The milestone for this indicator has become more challenging over time, to encourage diversification of sources of funding for the Scheme, but insufficient progress has been made to meet the milestone. At the end of CY2018, this percentage stood at 86%. At the end of CY2017 it stood at 82%. Similarly, when looked at by cohort, any downward trend is not fast enough.

Figure 5: Percentage of Fellows in each cohort funded by DFID

The previous Annual Review noted that, since 2013, there has been evidence of diversification of funders, but concluded that this has not attracted funding levels to lower progressively and sustainably the DFID share of all Fellowships. Over this current review period, further new additional funders have been brought on board; negotiations in 2019 led to further agreements with Comic Relief, EdTech, the World Bank and DFID Sudan, but the share of Fellows funded by DFID remains high.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The Business Case described ODI’s continuing attention to containing costs and ensuring value for money in management and recruitment, placements, and in-post support to Fellows. Evidence examined as part of this Annual Review confirms that this is still the case.

The Business Case compared the cost of a Fellow per year to the cost of providing Technical Assistance through consultancy for a year, which it estimated to be £127,500 per year. Last year’s Annual review made another comparison, with the cost of a junior consultant for a year, which would cost £78,750-90,000. The average cost of a Fellow still compares favourably against both of these figures.

The two previous Annual Reviews have both recommended increasing the size of the management team for the Scheme above 3.5 FTE. This was in response to the increased demands placed on the ODI Fellowship Management team (e.g. professional and pastoral support to Fellows and implementing capacity building initiatives). Since the last Annual Review, this increase in the team’s capacity was achieved. However, in response to budget pressures (described elsewhere in this document) ODI has again reduced the size of this team. At of September 2020, the Fellowship Scheme team consists of 3.2 FTE. This reduction represents a risk to the achievement of value for money and should be monitored.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There have been no changes to this output during the last year. The ongoing evaluation will review and test the theory of change and log frame, with a view to revising and deepening both the theory of change and log frame/assessment criteria and ensuring that the two are consistent.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

The previous Annual Review made various recommendations around the wellbeing of Fellows and those they are in contact with:
Recommendation - ODI should maintain the focus on regular, timely and clear communication with Fellows.
Progress - The ODI team report that they check in with Fellows every quarter by email and more often if circumstances warrant it. However, for DFID-funded Fellows in the 2017-19 cohort who completed the End of Fellowship Questionnaire, 29% felt that they needed more contact from the ODI, compared to 27% for the previous cohort, suggesting that further progress could be made on this recommendation.
Recommendation - ODI should provide more clarity in the briefing week about what constitutes harassment, reporting mechanisms and redressal from ODI’s end.
Progress – Examination of the presentations from the 2019 briefing week do not provide evidence that this recommendation has been addressed. The ODI Fellowship Code of Conduct does, however, provide information to Fellows about what they should do if they experience harassment.
Recommendation - New ODI/DFID policies with regard to safeguarding those in contact with Fellows during their placements – whether in their work settings or outside – need to be embraced. It is vital that Fellows understand and subscribe to ODI’s safeguarding policies and that this is demonstrably the case; FCDO must provide suitable supportive input to achieve this.
Progress – This was emphasised during the 2019 Briefing Session, including through a session about safeguarding which DFID actively participated in. ODI has also put more material on the shared online space for Fellows.
As described above, the two previous Annual Reviews have both recommended increasing the size of the management team for the Scheme. However, in response to budget pressures, ODI has reduced the size of this team. This reduction represents a risk to the achievement of the programme’s aims and should be monitored.

The Business Case was based on the premise that the biggest impact would be made in LIC and FCAS countries whereas the 2018 Annual Review challenged this assumption. Last year’s Annual Review recommended further assessment of where and how fellows are likely to have the greatest impact in technical capacity building. FCDO and ODI need to consider this issue collaboratively before any further funding agreements are put in place. The ongoing evaluation can contribute to this.

The evidence on which progress against indicator 3.1, on Fellows’ levels of satisfaction with the support they receive from ODI, is measured is based on the reported experiences of Fellows who started their Fellowships in 2017. The ongoing evaluation should provide a more current view of ODI’s support to Fellows around safeguarding and duty of care. ODI should continue to work to ensure that they provide sufficient clarity in the briefing week and in written guidance to Fellows about what constitutes harassment, reporting mechanisms and redressal from ODI’s end, and should review procedures to ensure they are robust.

D: RISK [½ to 1 page]

Overview of risk management [1/2 page]

Overall risk rating: Moderate

The overall risk rating remains the same as last year. While ODI has made progress in some areas to mitigate risks identified in last year’s Annual Review, there remain areas for improvement, particularly with regards to capacity building.

The Covid-19 pandemic has presented major risks which have been managed successfully to date by the Fellowship Scheme. ODI convened a special Covid-19 Crisis Management Team (CMT) which met for the first time on 5 March and which has met weekly since. The Head of the Fellowship Scheme reports weekly to CMT on the status of all Fellows everywhere. The Fellowship Scheme has stayed in close touch with all Fellows who remained in their host countries, initially on a daily basis and, after the situation stabilised, weekly. Since the end of April the Scheme has been updating DFID on the conditions of Fellows who remained in their countries of posting on a fortnightly basis. Throughout the first quarter of 2020/21, no serious incidents were recorded and no cases of Covid-19 were registered. At the time of this review, the fact that the majority of Fellows are in their home countries or in third countries with good health facilities significantly reduces safeguarding risks, but does pose delivery risks if fellows are unable to work as effectively remotely. Managing the risks around the pandemic, in particular as more Fellows return to their host countries, will clearly require significant effort from the ODI team going forward.

Delivery Risk - There is a risk, noted in previous Annual Reviews, that the programme is not meeting its expected outcomes in terms of capacity building in host organisations. This risk has been described in more detail elsewhere in this document. FCDO needs to ensure that any future funding agreements with ODI for the Fellowship Scheme are based on a shared understanding of expectations around capacity building. FCDO also needs to work with ODI to ensure that Fellows and supervisors share these expectations around capacity building and can therefore work together to monitor and achieve them. Other delivery risks are assessed to be low. The ODI Fellowships Scheme is long established; its systems and procedures are longstanding and well tested, and delivery risks are generally managed well.

Operational Risk – There is a risk that funding will not be available for all Fellows to complete their two-year Fellowships. At the present time, FCDO funding for the 2019-21 cohort is only guaranteed until the end of March 2021. Irrespective of Ministers’ decisions on future funding, FCDO expect to provide sufficient funding to enable the 2019-21 cohort to complete their placements.

Fiduciary Risk - Fiduciary risks are assessed to be moderate. The ODI Fellowships Scheme is long established; its systems and procedures are longstanding and well tested, and fiduciary risks are generally managed well. However, the Scheme continues to be highly dependent on FCDO funding. ODI should increase its efforts to diversify sources of funding.

Safeguarding Risk - ODI has taken further steps around Safeguarding improvements in this Annual Review period, in particular around welfare support for Fellows. Nonetheless, perceptions of bullying and harassment appear unacceptably high and must be addressed as a matter of urgency.

Reputational Risk - As highlighted in previous annual reviews, the number of early terminations for each cohort is high. Although early terminations do not pose a monetary cost to the ODI Fellowship programme, they are associated with a considerable opportunity and reputational cost. Levels of early terminations remained high over the review period. The ongoing evaluation should explore trends in and the reasons behind early terminations.

The programme risk register is regularly updated and the risks identified are also monitored quarterly when reporting to DFID. Last year’s Annual Review recommended ODI to provide more detailed and comprehensive information on risk assessment and mitigation in the quarterly reports. The level of detail within quarterly reporting in this review period is still low and we encourage ODI to improve this reporting.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and DFID, notably on commercial and financial issues, and including consideration of VfM measures of economy and efficiency. [max 1 page]

Monitoring activities throughout the review period have included:
- Quarterly check-ins by ODI with all Fellows
- Fellowship Scheme team and associates visited all current Fellows and supervisors to assess progress (March-June 2019).
- 2017-19 Fellows and supervisors completed End of Fellowship Questionnaires (September-October 2019).
- In place of country visits in 2020, the Scheme requested supervisors to complete and return Fellowship Appraisal Forms.
- The Scheme conducted a number of preliminary questionnaires of Fellows in March and April 2020 to obtain information on their situations and well-being. A regular weekly questionnaire was later initiated to get a better sense of how effectively Fellows were able to work remotely.
Financial management of the scheme by ODI appears to be strong. FCDO supports the Fellowship Scheme through an Accountable Grant Agreement with a budget of £17 million over five years. Agreement was reached in Q3 FY19/20 on a one-year £2.7 million extension until 31 March 2021. Actual spending to date (FY15/16, FY16/17, FY17/18, FY18/19 and FY19/20) has been in line with budgetary provision and totals £17 million. A reconciliation process conducted jointly by DFID and the Fellowship Scheme confirmed this last year. The Fellowship Scheme plans to come in within the £2.7 million extension for FY20/21.

The Fellowship Scheme implements a number of measures to ensure costs are kept to a minimum and value for money is achieved, including:
- The supplementation of local salaries paid to Fellows is reviewed annually but has not changed since 2009.
- Housing allowances are reviewed annually based on information provided by an external provider ECA. Housing allowances can be lowered as well as raised as a result of this review.
- The insurance policy which covers Fellows is reviewed annually with ODI’s broker to ensure the policy is competitive and offers the greatest value for money.
- Flights for Fellows and the ODI Fellowship Scheme and associates are booked through Diversity Travel which offers charity rates to the Scheme.
The two previous Annual Reviews have both recommended increasing the size of the management team for the Scheme above 3.5 FTE. This was in response to the increased demands placed on the ODI Fellowship Management team (e.g. professional and pastoral support to Fellows and implementing capacity building initiatives). Since the last Annual Review, this increase in the team’s capacity was achieved. However, in response to budget pressures (described elsewhere in this document) ODI has again reduced the size of this team. As at September 2020, the Fellowship Scheme team consisted of 3.2 FTE. This reduction represents a risk to the achievement of value for money and should be monitored.

Date of last narrative financial report	3rd July 2020 (Vault references 56400829, 56400830,56401708,56401380 56401707)	Date of last audited annual statement	FY 18-19 statement (Vault reference 57657928)