Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Access to Family Planning commodities
Programme Value: £18 million		Review Date: May 17th, 2017
Programme Code: 202668	Start Date: Oct 1st, 2011	End Date: June 30th, 2017

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017
Programme Score	N/A	N/A	B	A	A	A+
Risk Rating	N/A	N/A	Medium	Medium	Medium	Moderate

Summary of progress and lessons learnt since last review

The project continued its strong record of performance over the last year, providing 1.251 million couple years of contraceptive protection (CYP), compared to the annual target of 1 million CYPs. Cumulatively, the project has delivered 7.545 million CYPs (compared to target of 6 million CYPs) over the six year period of implementation. This is estimated to have averted 1.573 million unintended pregnancies (business case estimate 1,251,336 unintended pregnancies averted) and 9,613 maternal deaths averted (business case estimate 7,531 maternal deaths averted).
Recent surveys (2014 and 2015 smart surveys), as well as data showing increased throughput of contraceptive commodities through the health system, are indicating significant progress in modern contraceptive rates in the past few years since the last Demographic and Health Survey in 2013. However, this can only be confirmed when the results of the 2016 MICS survey are released in mid 2017.

The funding landscape for family planning in Nigeria continues to remain difficult. Fiscal constraints in Nigeria continue to limit the release of domestic financing, and the outlook for external financing is unclear given recent international political developments. However, the Nigerian Ministry of Health is looking to increase its annual contribution for FP commodity procurement, and UNFPA has commissioned some analytical work to develop a sustainable financing strategy for family planning.

Summary of recommendations for the next year

UNFPA and FMoH to finalise and ensure implementation of the Sustainability Plan for FP Program financing.

UNFPA to improve tracking of FP commodities at sub national levels and ensure end to end visibility of FP commodities data.

UNFPA to set clear targets for improvement in procurement lead times.

FP2020 co-conveners (DFID, UNFPA and Bill and Melinda Gates Foundation) to leverage the 2017 London Family Planning Summit to secure renewed commitments from the Nigerian Government and other stakeholders to improve the resourcing, management and delivery of family planning services.

UNFPA, with government and partner input, to develop a clear strategy, based on available evidence, to address both demand and supply side barriers that lead to discontinuation of contraception and hinder adolescent uptake of family planning.

DFID to continue to invest in family planning in Nigeria to support attainment of FP2020 and Government of Nigeria goals. This investment should include:
- Continued funding for FP commodity procurement alongside the development and implementation of the Sustainabiltiy Plan for FP Programme Financing, aiming to reduce and exit from FP commodity support over the coming 3-5 years;
- Evidence generation and strategies to reduce discontinuation rates, and increase contraceptive utilisation, particularly among adolescents. This could include programming to change societal expectations and practices around family planning, including the age of marriage and first child birth and desired family size;
- Provisions to engage with the private sector for FP scale up, and to support GoN to create and enabling environment for private sector provision; and
- Continued high level advocacy to mobilise domestic resources for family planning (including innovative financing mechanisms) and to improve the management and delivery of family planning services.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3716678.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5065041.xlsx

The Access to Family Planning Commodities in Nigeria project provides £3 million on an annual basis to centrally procure contraceptive commodities over a six year period (2011/12 – 2016/17). The expectation is that with this project at least 1 million Nigerian couples are provided with modern family planning each year. The project is funded by Department for International Development (DFID) and implemented by United Nations Population Fund (UNFPA).
UNFPA uses its own and pooled funds from the Government of Nigeria (GoN) and development partners for implementation of a coordinated approach to contraceptive commodity supply for the provision of family planning services in public health facilities. UNFPA is able to capitalise upon global pooled procurement and supply using pre-qualified vendors enabling access to pharmaceutical items and contraceptive commodities of the highest quality standards. This pooled procurement mechanism also enables price advantages through bulk purchases (economies of scale) and negotiated rates.

The project goal is to contribute to improved maternal and child health in Nigeria. As per the Business Case the intervention is expected to avert an estimated 1,251,336 unintended pregnancies and 7,531 maternal deaths by 2017.
Context
Nigeria with a projected population of 184 million (2015) and an annual population growth rate of 3.2% is set to double its population in 22 years. High population growth, and concurrent high levels of fertility (TFR of 5.5), are associated with high levels of maternal mortality, estimated at 576 per 100,000 live births[1]. This combination means that Nigeria contributes an estimated 14% of global maternal mortality. Behind these figures, lie a host of inter-related political, socio-cultural and systemic factors, which limit women’s access to voluntary family planning.
[1] National Population Commission (NPC) Nigeria and ICF International. Nigeria Demographic and Health Survey 2013. Abuja, Nigeria and Rockville, Maryland : NPC and ICF, 2014.
The GoN has identified population growth as a development challenge, allowing for greater political space for family planning, and, women’s and couples’ sexual and reproductive health rights (SRHR). The Federal Ministry of Health (FMoH) is increasingly stewarding family planning, through the development of the national FP BluePrint. This provides a road map for reaching Nigeria’s ambitious family planning goal of 36% CPR by 2018. This translates to more than 11.6 million women using contraceptives, an increase of approximately 7.9 million new users over and above the 3.65 million users existing in 2008. Nigeria needs to increase modern contraceptive prevalence by approximately four percentage points per year between 2013 and 2018 to reach this target.
Family planning, like other essential services, relies on a functional health system. While the Nigerian system is acknowledged to be weak and fractured, a number of policy initiatives have been put in place to address this. The FMoH has introduced the “primary health care under one roof” under the auspices of national and state Primary Health Care Development Agencies. Greater integration of the supply chain is also being addressed through the National Supply Chain Integration Project (NSCIP). Other policy initiatives highly relevant to family planning, include the free maternal and child health policy and the national task shifting and sharing policy. While, the free maternal health policy is well-known by its implementers, there is inconsistent understanding of what the policy covers, and, in some instances services under the policy are not totally free[2] (this affects the provision of LARC). The task shifting and sharing policy is also being operationalised in an ad hoc manner as it is left to individual states to implement and to prioritize aspects of the policy that best align with their situation (or the interests of respective development partners).
[2] EnCompass LLC, 2014. Population and Reproductive Health Accountability-related Grants in Nigeria Baseline Report, John D. and Catherine T. MacArthur Foundation, USA.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome indicator 1: % of married women currently using modern contraceptives (2017 Target – 16.7%) - Based on the National Nutrition and Health Survey 2015 and the PMA 2020 2016 Survey the national mCPR is estimated at 21% and 17% respectively. This is a significant increase from 9.8% from the 2013 NDHS. A Multiple Indicators Cluster Survey (MICS) was conducted in 2016 which will provide population-based survey data on CPR. Results are expected to be available by June 2017.

Outcome indicator 2: Number of states with a CPR of less than 15% (2017 target – 17) The last available state level data, the 2013 NDHS, shows 19 states with a CPR of less than 15%. However, it is likely that more recent data from the 2016 MICS (available in June 2017) will show an improvement. The highest increases in CPR have been observed among women aged 34 to 49 years with declining CPR observed among those aged 15 to 29 years. This is a concern and suggests that other factors are limiting access beyond availability, which may include persistent societal expectations and women’s choice for early childbirth, indicating the need for future family planning policy and programming to take a broader societal approach to change societal expectations and practices around age of marriage and first childbirth.

Outcome indicator 3: Adolescent birth rate (births – girls aged 15 to 19) per 1,000 births (2017 target – 90). The last available data (2013 NDHS) indicates 122 per 1,000, failing to reach the end of programme target. This correlates with the declining CPR observed among adolescents and as above, indicates a need to not only increase the supply of family planning services, but to promote behavioural change to increase utilisation.

Overall output score and description

A+ Outputs moderately exceeded expectation

Output	Description	Score	Weighting	A+
1	Adequate quantities of an appropriate mix of quality contraceptives procured and distributed.	A+	70%
2	Efficiently managed national contraceptive supplies and logistical management system.	A	30%

Key lessons

1. DFID investment in family planning commodities has made a significant contribution to increased CPR in Nigeria. Currently, DFID supplies 40% of FP commodities for the public sector. A withdrawal of DFID commodity support in the short term would impact drug availability, reversing recent CPR gains.
2. In order to ensure reproductive health commodity security, there is a need to develop more sustainable sources and modes of domestic financing for family planning commodities. Options for consideration include the Basic Health Care Provision Fund and ensuring coverage of family planning in emergent models for health financing reform, such as social health insurance.
3. Approximately 45% of family planning users access services through the private sector. There is a need for government and partners to engage more effectively with the private sector, to scale up service availability, while ensuring quality and access particularly for the poorest and adolescents.
4. The ongoing effort to improve supply chain efficiency and sustainability by fostering greater coordination and integration with other commodity supply chains is laudable and should be pursued. However this transition is not without its risks, which should be identified and actively managed to avoid disruption to the family planning commodity supply chain.
5. Recent evidence shows a declining trend in CPR among youth and adolescents, and suggests a high discontinuation rate of family planning among all age groups. The factors underlying these trends need to be investigated and understood, to inform appropriate strategies to increase and sustain CPR gains.

Key actions

This project is currently scheduled to close in June 2017. In order to ensure DFID’s contribution to family planning remains strategic and in line with UK priorities, an extension to this project is proposed to bridge to a proposed new family planning scale up programme planned for start in 2018.

Has the logframe been updated since the last review?

No
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Adequate quantities of an appropriate mix of quality contraceptives procured and distributed.
Output number per LF		1	Output Score	A+
Risk:		Moderate	Impact weighting (%):	70%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Couple years of protection of family planning commodities procured with DFID funds and distributed to public facilities	1 million CYP procured	1.251 million CYP procured (125.1%) / Target exceeded
1.2 CYP of commodities distributed/issued to states	1 million CYPs distributed/issued to states	1.350 million CYP issued to states (327.7%) / Target exceeded
1.3 Procurement lead time (average)	7 months (2014 baseline; no milestone in the logframe)	5.6 months

Key Points

The project provided 1.251 million CYPs, compared to the annual target of 1 million CYPs for the year (125% achievement). Cumulatively, the project has acheived 7.545 million CYPs compared to a target of 6 million for the six years period of implementation (125.75% achievement).

UNFPA supported FMoH to distribute contraceptives to the states stores in all 36 states + FCT; this was done during three review periods in 2016 (April, July and November) with a total of 1.35 mil CYP distributed. Through-put of greater stock to states than what was procured in the year was possible by utilisation of buffer stocks. This came at a cost however as current stock levels for some products are below minimum levels in the national warehouse[3].
[3] Min-max levels at national level are between 9-18 months; for states min-max levels are 3-4 months; while LGA min-max are 2-3 months.

The average procurement lead time has ranged from 222 days (7.4 months) in 2014 to 122 days (4.1 months) in 2015 and 168 days (5.6 months) in 2016. In addition, the clearing time reduced from 69 days in 2014 to 24 days in 2015 to 23 days in 2016. The clearing cost accounts for 2% of total shipment cost. This was possible through the use of multiple clearing agents as well as improved communication with PSB to enhance delivery time.

Summary of responses to issues raised in previous annual reviews (where relevant)

Output 1.1 Risk management and sustainability strategy: Continued prioritisation of commodity security and risk management is recommended given the volatile financing context. Specifically, it is recommended that a family planning sustainability strategy should be developed in 2016 that identifies a range of external and domestic financing opportunities and identifies risks and mitigation measures. – In 2016 UNFPA engaged Consultants to work with FMoH to draft a Sustainability Plan for the Family Planning Program including incremental funding from Government at national and sub-national levels as well as innovative financing mechanisms. Ongoing efforts are underway to finalise the plans in 2017. A risk assessment of the sustainability of the basket funds was conducted in 2016. In addition efforts were made to ensure FP funding was included in the Global Financing Facility (GFF) Investment case for funding through the World Bank.
Output 1.2 Contraceptive leakage and “added” costs: UNFPA, the federal and state ministries of health (MoH) and partners should continue to promote free access to public sector contraceptive services and address leakages of free commodities in the market. Measures including information campaigns, marking of products and packaging of consumables should continue as this remains a concern. – In 2016, UNFPA continued to use the opportunity of pooled procurement to mark the contraceptive commodities with inscription as follows; “Items not for sale. Donated by FMoH and donors”. In addition, tracking of contraceptives distributed to states are done using batch/lot numbers at Central Contraceptives Warehouse and efforts are made to encourage documentation of leakages in private sector.

Recommendations

FMoH and UNFPA to finalise and ensure adoption and implementation of the Sustainability Plan for FP Program financing.

UNFPA to improve tracking of FP commodities at sub national levels and ensure end to end visibility of FP commodities data.

UNFPA to set clear targets for improvement in procurement lead times.

FP2020 co-conveners (DFID, UNFPA and Bill and Melinda Gates Foundation) to leverage the 2017 London Family Planning Summit to secure renewed commitments from the Nigerian Government and other stakeholders to improve the resourcing, management and delivery of family planning services.

Output Title	Efficiently managed national contraceptive supplies and logistical management system
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	30%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 % of service delivery points reporting no stock outs of contraceptives in the last 3 or 6 months	95%	77% Target not met / However this still represents a substantial increase from 42% in 2011 / (Source: UNFPA Supplies survey, 2016)
2.2 % of CYP of States with requests for contraceptives resupplied (fill rate) within the reporting year	85%	79.78% / Target not met / (Routine data FMoH)
2.3 (a) % of primary health care public service delivery points currently providing FP services providing at least 3 modern contraceptive methods. (b) % of secondary and tertiary health care public service delivery points currently providing FP services providing at least 5 modern contraceptive methods	85% (both a and b)	Actual (PHC) – 92.6% Actual (secondary) – 91.7% Actual (tertiary) - 100% / Targets exceeded / (Source: UNFPA Supplies survey, 2016)
2.4 # of Health Facilities supported to provide LARC	300 (1,400 cumulative)	1,211 / (3,324 cumulative) / Target substantially exceeded / (Source: Marie Stopes Training Database/FP Dashboard)
2.5 Number of currently married women using FP services who are new acceptors of FP	1,500,000	2,419,914 / Target substantially exceeded / (Source NHMIS, 2016, UNFPA Supplies Survey 2016)

Key points
77% of service delivery points (SDPs) reported no stock out in the last three months (2016 UNFPA Supplies Survey). This is an improvement from 42% in 2011 and 69% in 2015. Review and resupply meetings were previously used as a commodity delivery model to health facilities and proved effective in reducing stock out by over 50% in the last five years[4]. However, this approach, while effective, proved to be expensive and difficult to sustain. The last mile distribution to health facilities using the Contraceptives Logistics Management System (CLMS) was implemented in the 36 states + FCT with support from UNFPA in 27 states + FCT, from USAID in 5 states and DfiD/MNCH2 in 3 states while Borno which is still in active insurgency is supported by several donors. The last mile distribution system was able to support states to distribute 1.471 million CYP worth of contraceptives to 9,500 health facilities providing FP services in 2016 compared to 1.21 mil CYP distributed to 8,400 health facilities in 2015. There is an ongoing transition to a new integrated supply chain system which will entail centralized distribution of all health commodities in the states with state ownership of the process. UNFPA is collaborating on this project with the Global Fund, bilateral donors such as USAID and DFID, as well as Federal and State governments.
[4] More information on review and resupply is available at: http://www.rhsupplies.org/fileadmin/uploads/rhsc/General_Membership_Meetings/Mexico_2014/Presentations/Day_4/PS_Equity_-_Achieving_equitable_access_-_Elizabeth_Obaje__USAID.pdf
There were variations in stock out rates across facility level, ranging from 17% of facilities reporting a stock out at the tertiary level to 25% at the primary and secondary levels. Supplies for male and female sterilization had the highest stock out rate among all contraceptive methods in the last three months at just 10% and 12%, respectively.
There were some variations in primary facilities that offered at least three contraceptive methods across geo-political zones. Over 90% of primary facilities in most regions offered at least three contraceptive methods, with the highest reports in South West (98%) and South South (96%). When examining the distribution of primary facilities offering at least three contraceptive methods by state level, it can be seen in the majority of states that 75% or more of primary facilities offer at least three methods. In four states (Kaduna, Katsina, Kogi and Yobe) between 50%- 75% of primary facilities reported they were able to offer at least three contraceptive methods. There were no states where less than 50% of primary facilities reported that they offered at least three contraceptive methods.
Overall, the majority of secondary and tertiary facilities reported offering at least five types of methods (Table 9). All tertiary facilities (42) surveyed reported offering at least five contraceptive methods while 92% (385) of secondary facilities reported the same, indicating a slight difference between levels of care. There were slight variations in the percentage of secondary and tertiary facilities that offered at least five contraceptive methods across geo-political zones. In the majority of geo-political zones, over 90% of secondary and tertiary facilities reported offering at least five contraceptive methods. The South West and South East zones reported slightly lower rates with 88% and 81% of secondary and tertiary facilities reporting that they offered at least five contraceptive methods.
In the majority of states, 75% or more of secondary and tertiary facilities offer at least five contraceptive methods (Figure 5). In Anambra, Enugu, and Oyo, 50-75% of secondary and tertiary facilities reported offering at least five contraceptive methods.
The National Health Management Information System (NHMIS) data indicates that current users of modern contraception are estimated at 8,722,113 (2015) and 5,549,913 (2016); the downward trend may be attributable to lower reporting rates in 2016. This includes new users; 3,846,226 (2015) and 2,419,914 (2016). However, discontinuation is not tracked in the NHMIS tools and estimates using the data from Demographic and Health Survey NDHS 2013 indicates that about 37% of women who initiated use of contraceptives discontinued within a year. The issue of discontinuation continues to be a challenge in tracking due to unavailbility of tools and indicators. The projected number of current users based on the mCPR from the National Nutrition and Health Survey (2015) and PMA2020 Survey (2016) is 10,060,516. The UNFPA Supplies Survey indicates that new users of family planning services was estimated at 2,126,750. These variations in estimation of new users and current users reinforces the need for improved tracking systems at state and national level.

Summary of responses to issues raised in previous annual reviews (where relevant)

Output 2.1 Last mile distribution: Sustained advocacy, guided by the risk and sustainability strategy and the window of opportunity offered by the National Health Act[5], should be used to develop guidelines through which states can draw funding from the PHC fund for last mile distribution of public health commodities (including contraceptives). – UNFPA has supported Government in implementation of activities to strengthen states to use integrated supply chain systems for last mile distribution of essential medicines including contraceptives, including coordinating structures and establishment of guidelines and protocols. Efforts are still ongoing to secure funding at state levels to support this. In 2016, a number of states agreed to include cost of last mile distribution in the SoML (Save One Million Lives Project) funds received from the World Bank. The integrated commodity distribution which has been adopted by states in Nigeria when fully functional will ensure that contraceptive and other health commodities are distributed to service delivery points. Continued advocacy to states on this new modality and assistance in capacity building is necessary to ensure states assume complete ownership of the process.
[5] Feedback from UNFPA indicates that the National Health Act implementation will start in 2016 (based on discussions with Honourable Minister of Health) and it would be one of the sources of funding for contraceptives for Government Counterpart Contribution.

Output 2.2. Standardised supply chain management (SCM): In line with decisions taken based on the National Supply Chain Integration Project (NSCIP), UNFPA has continued to strengthen supply chain management, particularly at State level. The State Government Logistics Management Coordination Units (LMCUs) have continued to receive on-going support with a range of functions including forecasting, warehousing, integrated last mile commodity distribution, reporting as well as data analysis.
Output 2.3 Sustain support for LARC: In 2015, UNFPA initiated bundling of consumables for long acting reversible contraception (LARC). This should reduce barriers to LARC, particularly for younger and poorer population segments. UNFPA is also addressing pre-service LARC orientation through the 98 midwifery training schools in Nigeria and the Nursing and Midwifery Council. UNFPA’s continued partnership with Marie Stopes Nigeria for sustained, supportive supervision and public-private collaboration in service delivery will facilitate positive client-centred experience and access to LARC.
Output 2.4 Adolescent access to contraception: Given existing challenges with adolescent access to contraception, as evidenced by reducing CPR amongst this age cohort (15 – 29 years of age), there has been concerted efforts to improve understanding on adolescent contraceptive seeking behaviour. Challenges for access including lack of privacy and confidentiality, and possible provider bias, limit adolescent patronage. UNFPA in collaboration with NGOs with expertise in adolescent sexual and reproductive health have introduced Sayana Press, a long acting contraceptive method that can be self-inected, to improve access to FP services using community distribution modalities in 9 states + FCT.
Output 2.5 Address contraceptive discontinuation: UNFPA continues to work with the FMoH and partners to gain a better sense of what factors responsible for discontinuation of contraceptive methods by users and strategies to combat this. However, it is not clear that there is now a clear strategy to address this based on the available evidence.

Recommendations

UNFPA, with government and partner input, to develop a clear strategy, based on available evidence, to address both demand and supply side barriers that lead to discontinuation of contraception and hinder adolescent uptake of family planning.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The bulk of DFID financing (93%) committed to UNFPA under this project is for contraceptive commodity procurement therefore, as in previous years, the main cost driver is the cost of commodities, which is determined by the mix of commodities procured together with the unit costs of the commodities. UNFPA uses the pooled procurement system through their Procurement Service Branch (PSB) in Copenhagen. Centralised UNFPA procurement procedures using pre-qualified vendors, ensure that manufacturers of pharmaceutical items and contraceptive commodities maintain the highest quality standards and lowest cost. This mechanism enables price advantages through bulk purchases internationally. UNFPA is consistently achieving equivalent or better prices for quality assured products[6] than the two internationally recognised price data sources: USAID’s listed prices and Management Sciences for Health’s International Drug Price Indicator Guide. UNFPA has also achieved reductions in the procurement lead time and in the port clearance time (refer to output 1.3).
[6] See e.g. Differential Pricing UNFPA’s Experience With Contraceptives Christian Saunders, Chief, Procurement Services, United Nations Population Fund. https://www.wto.org/ENGLISH/tratop_e/trips_e/.../17saunders_e.ppt; accessed 21 March 2015.

VfM performance compared to the original VfM proposition in the business case
This programme has delivered 7.5 million Couple Years of contraceptive Protection (CYPs) over the 6 years of the project, compared with the original VFM proposition of 6 million CYPs over the same period and at the same cost.

Assessment of whether the programme continues to represent value for money
Increasing modern family planning coverage is a highly cost effective intervention. It represents good value for money: The Guttmacher Institute in 2009 demonstrated that in Sub-Saharan Africa, providing modern contraceptives, would more than pay for itself, saving $1.30 in the cost of maternal and newborn care for each dollar invested[7] [8]. Application of Marie Stopes International’s Impact Calculator to contraceptives procured under this project estimate that for each £1 invested in family planning in Nigeria, the benefits are approximately £26 (total cost savings per CYP = 80.36 GBP; ecological footprint prevented (global hectares per person) = 0.54; carbon footprint prevented (global hectares per person) = 0.05)[9]. Researchers have estimated that a reduction in fertility of one child per woman in Nigeria would lead to a 13% increase in GD P per capita in 20 years, and 25% in 50 years. GDP per capita is increasing by 1.0% per year in China and 0.7% per year in India as a result of the effect of lower fertility on age structures[10].
[7] Singh S et al., Adding It Up: The Costs and Benefits of Investing in Family Planning and Maternal and Newborn Health, New York: Guttmacher Institute and United Nations Population Fund (UNFPA), 2009.
[8] Halperin, D. T., Stover, J., Reynolds, H. Benefits and costs of expanding access to family planning programs to women living with HIV. AIDS: November 2009. 23; 123–130.
[9] Corby N, Boler T and Hovig D. 2009. The MSI Impact Calculator: methodology and assumptions. London: Marie Stopes International.
[10] PMNCH Knowledge Summary #24. The Economic Benefits of Investing in Women’s and Chidren’s Health. PMNCH, 2013.

Quality of financial management
This project is managed using UNFPA’s financial management systems. UNFPA was assessed in the latest DFID Multilateral Aid Review (MAR), and key organisational components related to financial management (risk and assurance; results and value) were rated as Good. Details of the MAR for UNFPA are available on https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/573506/United-Nations-Population-Fund-Review.pdf

Date of last narrative financial report	December 2016
Date of last audited annual statement	June 2016

E: RISK (½ page)

Overall risk rating: Moderate

Overview of programme risk
Risks under the programme have generally been well managed. The following key risks are identified from this review for further attention:
1. Government of Nigeria commitments on Family Planning not met: The fall in oil prices, devaluation and fiscal crisis currently being experienced in Nigeria has meant the Nigerian Government has not fully met commitments to increase domestic financing of family planning. The fiscal situation is likely to remain difficult, possibly leading to widening gaps in commodity supply. UNFPA, working with other partners, should mitigate by completing the family planning sustainability plan and leverage the 2017 Family Planning Summit to secure greater domestic commitment and funding for family planning.
2. Transition to new integrated supply chain system leads to disruption in commodity supply: While the new system has potential to significantly improve supply chains for a number of health products, the greater leadership and coordination required between government, several donor and implementing partners and the private sector (and the less direct control UNFPA will have over the supply chain) mean there might be a higher risk of supply chain disruption if the system does not work as expected.

Outstanding actions from risk assessment

None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The project is delivering weel against its planned timeframe. The average procurement lead time has ranged from 222 days (7.4 months) in 2014 to 122 days (4.1 months) in 2015 and 168 days (5.6 months) in 2016. In addition, the clearing time reduced from 69 days in 2014 to 24 days in 2015 to 23 days in 2016.

Performance of partnership (s)
The Federal Ministry of Health (FMoH) remains UNFPA’s primary partner as it is the main recipient of technical support and contraceptives supply under the project. The project also leverages UNFPA partnerships in a range of areas: advocacy with Government; supply chain management and last mile distribution; contraceptive service capacity building; as well as contributions to the contraceptive basket. Other key partners include USAID and Canadian DFATD for contraceptive commodities; Marie Stopes, the Association for Reproductive and Family Health (ARFH) and Planned Parenthood for service delivery; and with the various partners (such as the Global Fund) involved in the National Supply Chain Integration Project (NSCIP).

Asset monitoring and control
Asset monitoring and control is undertaken by the FMoH, with technical support from UNFPA and JSI, as well as the broader Procurement and Supplies Management Technical Working Group.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The Partnership Principles were not considered within the project business case. In Sept 2014 DFID Nigeria conducted an assessment of the FGN commitment to the Partnership Principles which reconfirmed the UK’s declared policy that no UK aid money should go directly to the GoN: as an anti-corruption measure and to avoid substituting for the country’s own resources. The Access to Family Planning Commodities programme is consistent with this policy. DFID funding is provided directly to UNFPA for the procurement of family planning commodities. No funding is passed through government channels and as such the Partnership Principles are not relevant for the direct management and monitoring of this project.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The theory of change (ToC) presented in the project business case continues to remain relevant. In the last year there was no new evidence generated to demonstrate health impact or outcomes. However a Multiple Indicator Cluster Survey carried out in 2016, with results due by June 2017, is expected to provide updated data demonstrating progress at the outcome level.

Monitoring progress throughout the review period

Progress is monitored through FMoH and UNFPA systems. UNFPA provides DFID with semi-annual reports. UNFPA employs a dashboard for procurement monitoring which is shared with stakeholders during regular PSM meetings. Annually, the GPRHCS (now known as UNFPA Supplies) Survey is conducted with support from UNFPA and other partners. This provides data on the availability of essential medicines and commodities to analyse stock out and other service delivery bottlenecks.

This annual review was conducted by Ebere Anyachukwu, DFID SRO for the AFPC project, using a desk analysis of available data, reports, and information from a UNFPA annual review self assessment as well as the 2016 annual review.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
A: Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of financial management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Overall Risk Rating: Minor/Moderate/Major/Severe / Enter Minor, Moderate, Major or Severe, taken from the overall Output risk score entered in AMP
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Detail the key risks that affect the successful delivery of the expected results and mitigating actions. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix etc. / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process