## Annual Review Template – from April 2020

Title: Tackling Waste and Plastics Pollution Programme
Programme Value £ (full life): £16m		Review date: 11 September 2020
Programme Code: 300604	AMP start date: 1 June 2018	AMP end date: 31 May 2021

Summary of Programme Performance
Year	2019	2020	2021
Overall Output Score	B	B
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300604
DevTracker Link to results framework:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300604

Description of programme [1-2 paragraphs]

Plastics are polluting the oceans, harming marine life and posing a risk to the health of people. Tackling this problem requires finding ways to reduce plastics’ use by working with governments, innovators and businesses, and to improve the ways in which waste is managed, particularly in developing countries.

At the Commonwealth Heads of Government Meeting (CHOGM) in 2018, the UK Government committed to further its efforts to tackle plastic pollution. Following this, the £16 million Tackling Waste and Plastic Pollution programme was established to support developing countries to better manage their solid and plastic waste on land and to help tackle marine plastic pollution. The programme will run between 2018 to 2021 and its overall objective is to help reduce plastic waste reaching the ocean through programmes supporting developing countries by 2021, with consequent benefits for human health and marine life. It is implemented through two outputs:

1. CCOA Technical Assistance Facility: Up to £10m of technical assistance (TA) to developing countries who have signed up to the Commonwealth Clean Oceans Alliance (CCOA). This is delivered through the CCOA Technical Assistance Facility (TAF), and;
2. Waste Pilots: Up to £6m for pilot projects that aim to improve solid waste management approaches in up to 6 cities in developing countries.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

Overall, the programme continued to perform slower than expected. Despite some progress this year across both components Covid 19 has resulted in significant delays to activities. Output 1 and Output 2 have both been considered to have moderately not met expectations, scoring a B.

Under Output 1, Phase 1 was delivered by DAI and Common Seas and completed this year. Phase 1 involved a scoping exercise to understand technical assistance (TA) needs of eligible CCOA developing countries that commit to meet one or more of the CCOA ambitions. Overall, 24 countries and regional bodies in the Pacific were engaged with under Phase 1, resulting in 30 Terms of Reference (TOR) for TA being developed for 16 countries and 1 regional approach. Whilst the programme successfully scoped out work as planned, implementation in recipient countries was not feasible due to challenges in engaging with governments during phase 1 and then being unable to move to phase 2 of TA delivery due to Covid 19 implications. The programme has not achieved the outputs expected by this stage.
[note] 1. Taking steps to eliminate single use plastic waste; 2. Significantly reducing single use plastic carrier bags by 2021, and; banning the sale and manufacture of micro-beads in rinse-off personal care products by 2021.

Under Output 2, four pilot projects were planned to occur this year. Three were live, located in Ghana, Vanuatu and Uganda, and the first two successfully closed this year. A summary is provided in Box 1. The Uganda pilot has faced significant delays this year due to recruitment constraints, delayed approvals within the delivery partner, and Covid 19 restricting delivery and further recruitment. A fourth project in Bangladesh was planned however this was paused during the DFID-wide internal review of new commitments of aid spending in response to the expected fall in Gross National Income this year (and associated impact on the Government’s 0.7% GNI ODA target).

Box 1: Overview of pilot projects this year:

Ghana (Completed this year): This pilot raised awareness on waste handling and plastics use within communities, businesses and Ministries, including through data gap filling and hosting workshops. This has led to the Government of Ghana commitment through the Global Plastic Action Partnership to reduce reliance on plastics and implement a plastics bag levy from 2020. / Vanuatu (Completed this year): This pilot funded Vanuatu’s Plastics Strategy (2020-2025) proposal. It supported Vanuatu to develop and approve an evidence-based, country-wide strategy for practical and effective measures to eliminate avoidable single-use plastic waste. / Uganda (Ongoing): Supporting the Kampala Plastics Recycling Partnership. This pilot works with businesses and government, to improve the sustainable management of plastic waste in Greater Kampala.

Major lessons and recommendations for the year ahead [1/2 page]

Recommendations for the year ahead

Key lessons from the programme have been identified to support delivery in its final year and to inform future programme design.

Procuring Phase 2 of Output 1 earlier and whilst Phase 1 was live would have allowed for momentum to have continued, TORs to have been implemented quickly once finalised and relevant, and for lessons to have been drawn from their implementation to support the design and implementation of other TORs. This should be reflected on for other DFID programmes providing TA, especially in sectors requiring good political will to achieve action.

Programme management oversight of Phase 2 under Output 1 will be crucial in ensuring successful delivery. For example, regular monthly written updates on TA delivery status under Phase 1 were beneficial. This should be continued under Phase 2 to ensure DFID has clear oversight on delivery plans’ progress.

Additionally, Covid 19 demonstrates the importance of flexible programme management.

Based on these lessons, key recommendations for the programme have been identified:

Recommendation: The programme team should reconsider options for delivering Phase 2 of Output 1 given the remaining timeframe of the programme, with a decision reached by the end of September 2020. It is highly unlikely that procurement and TOR delivery can occur in the remaining timeframe. Options include extending this programme and reducing the number of TORs that will be supported as well as rolling this component into a new programme.

Recommendation: The Theory of Change (ToC) and log frame should be updated in Phase 2 of CCOA delivery if this component carries on under this project (by end of October 2020).

Recommendation: Due to the timeframe remaining reducing the likelihood of its success, the Bangladesh pilot is not recommended to continue.

Recommendation: The delays faced by the Uganda pilot project mean it is unlikely to deliver anticipated results by the project’s current end date of 31st December 2020; a decision should be taken by the end of September whether to extend the project.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The overall theory of change (ToC) for the programme at design was as follows:

1. TA to country governments who have committed to tackling plastic waste, and support for projects that increase waste plastic management and recycling, leads to:
2. Improved policies and approaches to deal with plastic waste and an increase in the number of people with access to proper waste management and a reduction in the mismanagement of plastic waste, which contributes to:
3. A reduction in the amount of floating plastic waste in the oceans (SDG indicator 14.1.1) and an increase in the proportion of urban solid waste collected and properly managed (SDG indicator 11.6.1).

The ToC’s major assumption is that most of the plastic waste in the ocean is derived from poor waste management practices on land. There have been no major changes to the ToC in the last year and the objectives remained the same. An update to the ToC should be made once a decision on how to progress Phase 2 of Output 1 is taken.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The UK Government remains committed to tackling plastic waste management issues in developing countries and plastic pollution in the Ocean. This programme has successfully delivered TORs to support these efforts under Phase 1 of Output 1 which are ready to be delivered under Phase 2. Delivering these TORs under Phase 2 should be continued, however the timeframe remaining under the programme is highly challenging to do so. A decision should be made whether to extend this programme to allow for the procurement and delivery of TORs or whether to continue this activity under another programme. Merits under the latter option include aligning monitoring and evaluation systems, allowing for better capturing and sharing of lessons learning, as well supporting greater value for money through the extension of this TA support beyond the current 30 TORs and CCOA geographic scope. Merits under the former option include a swifter delivery as the current programme is already established.

Only one pilot project remains ongoing under the programme and two successfully closed this year. The ongoing project in Uganda is due to close at the end of 2020 and has had limited success, however further time is required to ensure initial ambition is delivered. An extension to this within the current overarching programme timeframe should be considered if a clear delivery plan towards achieving the results targeted can be agreed.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Technical assistance provided to Commonwealth Clean Oceans Alliance countries
Output number:		1	Output Score:	B
Impact weighting (%):		70	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of Commonwealth Clean Oceans Alliance Countries provided with technical assistance	At least 15 CCOA countries to have been contacted and offered technical assistance. Terms of References drafted for all Technical Assistance concepts approved for support by UK government and CCOA partner country.	B - Moderately did not meet expectation / Despite the minimum target being met, TA delivery itself was not able to progress due to the first contracted milestone not being met and as a result of Covid 19 implications. / Progress includes: / Delivery partners engaging with 24 countries which resulted in 16 countries following through to receive Phase 1 assistance to develop TA ToRs. / A total of 30 ToRs were drafted covering 16 countries and 1 regional approach for the Pacific. These have been approved by HMG.
1.2 Number of new government policies (for example plastic bag bans or charging schemes) or measures making long term systemic improvements in plastic waste production or management supported by TA that is in line to support the delivery of 1 or more CCOA Ambitions.	ToR include clear activities and deliverables to support development of policies and / or measures that contribute to long term systemic improvements in plastic waste production of management	A – met expectations / All 30 drafted ToRs include clear activities and deliverables to support targeted CCOA ambitions.

Briefly describe the output’s activities, and provide supporting narrative for the score.

The CCOA TAF helps countries that sign up to CCOA to design and implement new policies to deliver on the CCOA’s three ambitions. There are 2 Phases to this Output: Phase 1 involves the development of TORs for activities and Phase 2 involves their implementation. There are two stages under Phase 1. Stage 1 involves discussions with the 24 CCOA member governments to establish their intended actions and what assistance they might need and the subsequent delivery of TOR to meet these. Stage 1 was completed this year and delivered by DAI and Common Seas. Stage 2 involves DFID, alongside Defra as the UK Government CCOA policy lead, agreeing which TORs should be taken forward under Phase 2. Stage 2 was also completed this year.

Output 1.1. Despite receiving a total 30 ToRs covering 16 developing countries and 1 regional proposal, summarised in Table 1, HMG was unable to procure TA delivery due to the first target milestone of at least 5 finalised ToRs not being met. All finalised ToRs received by March 2020 were put on hold from being procured due to Covid 19 restrictions. This output scored a B as the ambition of starting TA delivery this year was not met.

Table 1: Summary of countries that received support under Phase 1.
Country	Number of TORs	Country	Number of TORs
Bangladesh	1	10- St Lucia	3
Belize	3	11- Sierra Leone	1
Cameroon	1	12- Sri Lanka	3
The Gambia	1	13- Tonga	2
Ghana	1	14- Tuvalu	2
Mauritius	1	15- Uganda	1
Mozambique	3	16- Vanuatu	1
Namibia	1	17- Pacific regional	1
Rwanda	4

Output 1.2. The final TORs received were of high quality and exceeded the minimum requirements determined for a satisfactory TOR set within the delivery partners’ contracts. Each one was aligned to at least one of CCOA’s three objectives, and this indicator was considered to have been met in result.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The main costs of delivery under this Output were the contracting of the delivery partners for Phase 1. Delivery partners for Phase 1 were contracted through a competitive tendering process. VfM was a key element of the commercial assessment in the review of bids for all proposals. DFID ensured that an economic approach was taken when selecting implementing partners for the various components of the plastics programme. The total contract value was £443,925 and during the life of the contract £126,817.41 of savings were made mainly due to travel restrictions.

The VFM of this Output has been significantly impacted for various reasons. These include delays in intended recipient governments finalising their ToRs allowing Phase 2 and the procurement for a delivery partner to progress, with Covid 19 playing an additional factor, as well as DFID waiting to contract a delivery partner for Phase 2 until most TORs had been received and signed off by partner governments. Whilst TORs have been developed, it is likely that they will need to be reviewed and potentially revised given delays between their finalisation and implementation. Options to address this have been presented elsewhere in this Annual Review.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

In December 2019, and following the previous annual review, the original target of at least 19 countries to be consulted under Phase 1 and supported in scoping final TORs was amended to 15. This was due to the programme team becoming aware that not all 24 CCOA member countries were wishing to proceed with the TA due to capacity challenges or for other reasons, meaning a target of 19 was overly ambitious.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

During Phase 1, a significant amount of time was needed to engage with CCOA governments and keep the momentum going to finalise ToRs. This presents a key lesson to consider when considering delivery options and procuring for Phase 2.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Development of waste pilot projects in favour of plastic management improvement, including jobs created and people provided with waste collection services
Output number:		2	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of actions launched in Ghana by the Accra Plastics Management Pilot (APMP) project to tackle plastic pollution	2	A - met expectations / The APMP project has supported two actions: / Feasibility Study for developing Polyethylene terephthalate (PET) recycling in Ghana / 10 supermarkets signed an MoU to reduce sales of single use plastic bags.
2.2 Number of projects and / or initiative supported by the Accra Plastics Management Pilot to tackle plastic pollution	2	A - met expectations / The APMP project has supported and assisted three projects in Ghana: / Global Plastic Action Partnership / Plastic Punch / Plastic Revolution Foundation
2.3 Help increase local plastics recycling capacity, quality and use of locally produced recycled resins, setting out clear options backed by evidence and data on waste management in Dhaka.	TBC once contract can be issued. Workplan not agreed with successful bidder.	C - substantially did not meet expectation / Placed on hold due to Covid 19.
2.4 Improve livelihoods, local economy and reduction of plastic waste flowing in the Bay of Bengal.	TBC once contract can be issued. Workplan not agreed with successful bidder.	C - substantially did not meet expectation / Placed on hold due to Covid 19.
2.5 Number of sustainable new plastic waste recycling actions in Uganda.	Target 5	B - Moderately did not meet expectation / Pilot has delivered 2 of these actions with all others scheduled to be delivered later.
2.6 Partnerships for improved multi-stakeholder stewardship of natural resources effective in Uganda	Target 1	B - Moderately did not meet expectation / Pilot has created a governance structure, including a steering committee. The first meeting took place in 2019. / Two public sector bodies and three private sector organisations have joined the partnership. / Work is still on going to agree ambitions and experiencing delays due to staff recruitment and contractual factors.

Briefly describe the output’s activities, and provide supporting narrative for the score.

The overall B score for this output reflects the longer than anticipated time to fully mobilise for the Uganda pilot and the pause in contracting the pilot in Bangladesh due to Covid 19 implications despite the Ghana pilot scoring highly and completing in early 2020.

Ghana Waste Pilot (Outputs 2.1 and 2.2): This pilot continued to meet expectations and successfully closed this year. Both Output 2.1 and 2.2 indicators are considered to have been met. Highlights from the project include:

- Completing a PET recycling feasibility study and securing 10 supermarkets’ agreements to bring charges for single use plastic bags to reduce their use.
- Establishing a strong partnership between key stakeholders, including the Government of Ghana, relevant municipal authorities, industry, civil society and financiers.
- Developing a strategy and roadmap to establish support to implement regulatory reforms, development of waste collection and management systems, and related investment in waste management infrastructure.
- Capturing lessons to inform and support replication of approach in other countries and regions.

Bangladesh Waste Pilot (Outputs 2.3 and 2.4): Since the previous review the original pilot was terminated as the contracted delivery partner was not able to fulfil the intended contract. A new pilot was designed with DFID country office leads. However, this new pilot was paused during the DFID-wide internal review of new commitments of aid spending in response to the expected fall in Gross National Income this year (and associated impact on the Government’s 0.7% GNI ODA target). In result Output indicators 2.3 and 2.4 have scored a C.

Uganda Waste pilot (Outputs 2.5 and 2.6): The pilot was expected to launch in October 2019 however it has not been able to fully mobilise since the last annual review, largely due to recruitment delays experienced by GIZ. Further delays incurred due to GIZ requiring sign off between the German and Ugandan Ministries for the project to commence. This was received in early 2020 and GIZ began engaging stakeholders. The Covid 19 outbreak in March 2020 and subsequent lockdowns in Uganda resulted in further delays. Despite this, the project has successfully set up the partnership with 2 public sector and 3 private sector members (Output 2.6). With regards to Output 2.5, two actions were advanced including supporting the government to host a secretariat for the partnership to function (with a GIZ adviser planned to be seconded to the secretariat) and support to the government to enhance guidelines for private sector on implementation of extended producer responsibility under the 2020 Environmental Management Act (2019) and Waste Management Regulations (2020). Three further actions under this Output are currently being undertaken however these have been impacted by delays.

In addition to the three pilots above and recorded on the logframe, a fourth pilot was supported in Vanuatu to consider their CCOA ambitions. It has fallen between Output 1 and 2 and was not captured in the logframe. This pilot provided scientific and technical assistance to the government of Vanuatu to support the development of comprehensive strategic action on single use plastics use and waste flows to the sea. The pilot developed an evidence and consultation-based strategic plan for the management of plastics in Vanuatu, alongside a list of opportunities for funding or other assistance that could be supported through CCOA TAF.

Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year [1 paragraph]

The Expert Advisory Call Down Service (EACDS) framework has been used to procure and contract all pilots. This has provided access to a range of suppliers with strong development technical expertise throughout the projects. All projects have agreed workplans, milestones for delivery and payment plans that take into account measures needed for successful delivery. The Ghana and Vanuatu pilots were completed successfully and within contract budgets.

The Dhaka pilot had to be re-tendered due to issues with the original supplier. A new supplier has been selected but due to Covid 19 this contract has not yet started. This project will not be able to be delivered successfully in the remaining timeframe of the project and it is not recommended to continue.

Under the Ugandan pilot, results have been less than expected this year, in part due to Covid 19, which has negatively impacted the VFM performance of the project. A no cost extension should be considered by the programme team to allow for additional time to achieve the targeted results.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Changes were made to Outputs 2.5 and 2.6 to update the milestones for the Uganda pilot. Should the Uganda pilot be granted a no cost extension, DFID should revise the logframe.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Since the previous review, GIZ have provided DFID with monthly updates on the Uganda pilot’s performance, including meetings and regular reports. These have allowed DFID to understand the challenges and delays faced under the programme especially related to recruitment issues.

Lessons learnt from all pilots have been shared with programme teams across DFID and DEFRA to inform the development of new programming related to the marine environment and tackling plastic waste and support other ongoing plastics pollution projects.

D: RISK [½ to 1 page]

The overall risk rating of the programme is major, as plastics is a novel area of programming within DFID and as the programme works in countries through the CCOA TAF where there could be no DFID country presence.

DFID’s programme risk register was recently reviewed in August 2020. All risks in the register have mitigation measures in place and a named risk owner. All risks identified have been monitored regularly and where possible through application of scrutiny and diligence processes have been applied.

DFID met with all implementing partners on a regular basis to track progress, risks and ensure a mitigation plan was in place. This included weekly calls with the CCOA delivery partners between DFID and Defra colleagues to keep informed of progress and gain regular overview of challenges or issues and mitigation measures put in place.

Contextual Risk is major, largely due to the lack of in-country DFID presence in many of the CCOA countries and potential challenges in building good relationships with governments to drive buy in for the programme, particularly where UK posts have not had previous engagement with host governments on plastic issues. To mitigate this, DFID and Defra have sought to engage proactively with partner countries’ CCOA representatives and work alongside UK overseas posts in programme countries.

Delivery Risk is major given the novel area of programming for DFID and challenges in communicating with host governments Covid 19 and recruitment delays have affected full delivery of some pilots and in the delivery of Technical Assistance and are captured as major risks for the programme. The programme team will consider how Phase 2 of Output 1 could be contracted.

Safeguarding risks are considered major. Mitigations have included ensuring each of the directly funded partners has confirmed they have policies in place to understand their responsibility to take reasonable steps to prevent sexual exploitation, abuse and harassment by either their employees or a downstream partner.

Fiduciary Risk is major due to the risk of fraud within tier 1 and tier 2 delivery partners. Mitigations have included appropriate checks by DFID on delivery partners which are regularly updated, and close management of activities by framework managers.

Reputational Risk is major with the potential that DFID does not show enough leadership in the sector or with partner governments that helps achieve their buy in to the programme. Mitigation measures have included partnering with Defra, capturing lessons and ensuring delivery partners are sharing these with partner governments, and DFID sharing lessons internally. Extensive delivery network and range of partners can increase reputational risks, which can stem from actions such as failing to deliver, negative publicity, fraud or corruption. Mitigating actions include due diligence on implementing partners and setting clear expectations.

Operational Risk is major given the programme area is a new to DFID. Staffing changes within DFID have impacted continuity of the programme’s delivery and presented challenges to maintaining relationships with delivery partners. Partnering with Defra as policy leads for CCOA and with strong expertise in plastic waste management has helped mitigate this risk.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

All procurements included DFID standard terms and conditions, and where applicable, bespoke conditions to safeguard key risks and assumptions. VfM was a key element of the commercial assessment in the review of bids for all proposals. DFID ensured that an economic approach was taken when selecting implementing partners for the various components of the plastics programme. Suppliers under the programme have been paid against output milestones, ensuring value for money (VFM) as payments are based on clear deliverables and performance. Spend is fully compliant with the SMART rules. The fees and milestone payments forecast accuracy were affected by Covid 19 and recruitment delays were also a factor. Invoices were not submitted on time due to delays with sub-contractors and this also impacted on overall forecasting accuracy.

The Expert Advisory Call Down Service (EACDS) has provided access to suppliers able to deliver expert advisory services which has ensured strong technical development expertise is delivered throughout the programme. The EACDS has an agreed framework of costs, and the bidding under EACDS means that costs are of a competitive nature. For this programme, DFID is using a payment by results model for all elements that are commercially contracted so we only pay for results delivered.

Under Output 1, the partnership between DAI and Common Seas who coordinated the Technical Assistance Facility under Phase 1 continued to work well. Partners held weekly calls with DFID and Defra to receive updates on the TAF component. A payment by results contract was in place under this Output to ensure results were delivered efficiently. This Output was underbudget by 28%, predominantly due to travel restrictions reducing travel costs.

Under the Ghana pilot, IMC Worldwide were the delivery partner working with a consortium. DFID received regular reports from the implementing partner in Ghana, Seureca, and IMC Worldwide and held regular progress calls. Approvals for deliverables and for decision making were defined jointly with DFID, IMC and Seureca. IMC have delivered in a timely way against the agreed milestones and all payments were made. Under the Uganda pilot, GIZ and DFID held regular teleconferences to keep track of progress, particularly related to procurement delays. Quarterly progress reports are also sent to DFID.

Date of last narrative financial report	Component 1: / CCOA – 17 April 2020 / Component 2: / Ghana final report 24 March 2020 / Vanuatu final report 16 March / Uganda – 16 August 2020	Date of last audited annual statement	Component 1: / N/A / Component 2: / Ghana – / Vanuatu – reported centrally / Uganda – to be submitted by 30/09/2020
[note] Annual audited statements are not required for contracts which were used under Component 1.
[note] Reports are provided via EACDS.
[note] Given the timeframe remaining for the project, the DFID team will consider having one audited financial report for the whole project.