Annual Review

Title: Reducing poverty through Local Economic Development (LED) in the Commonwealth
Programme Value £ (full life): 3,900,000		Review date: / October 2020
Programme Code: [AMP ID#] / 204042	AMP start date: / August 2017	AMP end date: / March 2021

Summary of Programme Performance
Year	2018	2019	2020
Overall Output Score	A	A	A
Risk Rating	Minor	Minor	Minor

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-1-204042/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/projects/GB-1-204042/documents

A. SUMMARY AND OVERVIEW

Description of programme

The Commonwealth Local Government Forum (CLGF) was established in 1995 and is officially recognised by the Commonwealth Heads of Government. CLGF works to promote and strengthen effective democratic local government across the Commonwealth through local investment opportunities, job creation and improving the environment in which to do business. CLGF facilitate the exchange of good practice in local government through its extensive membership (more than 200 members in 47 Commonwealth countries) at national and local government level.

Under a previous £4.5 million programme funded by FCDO (2012–2016), CLGF successfully piloted a Local Economic Development (LED) approach, raised awareness for LED and demonstrated the potential impact of LED. This £3.9 million programme aims to further deepen and embed that approach by rolling out LED at scale with local government partners and by sharing the lessons learned with other Commonwealth countries. CLGF is an influential knowledge-sharing network and is focusing their efforts in this programme on six countries: Botswana, Ghana, Sri Lanka, South Africa, Eswatini (formerly Swaziland) and Zambia. The expected results are increased economic opportunities, job creation and improved skills. The programme is, in particular, targeting Sustainable Development Goals 8 (decent work and economic growth) and 11 (sustainable cities and communities) as well as contributing to Goal 16 (peace, justice and strong institutions).

Summary supporting narrative for the overall score in this review

The programme was due to conclude in July 2020 but was granted a ‘no cost’ extension to March 2021, with implementation of activities during this year impacted by the onset of the COVID-19 pandemic. With the Project Completion Review due in early 2021, this is a ‘light touch’ Annual Review.

The programme has continued to make good progress during the period covered by this review and is judged to be on track to achieve its expected outcome and output targets.
COVID-19 has had a significant impact with key project partners involved in delivery of frontline services to local communities. CLGF has worked hard to develop strategies to ensure that programme activities can continue, for example moving some activities on-line, but where this has not been possible alternative delivery plans have been prepared.

Major lessons and recommendations for the remaining period

Local economic development is likely to play a major part of the post COVID recovery in many Commonwealth countries. This project has developed approaches that can be adopted as part of that effort and CLGF should continue to capture and widely share lessons with Commonwealth members and more widely internationally.

The CLGF should continue to support its partners in attracting investment in ‘bankable’ projects and capture and disseminate lessons from doing so.

B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

CLGF’s Theory of Change

The theory of change builds on the lessons learned from FCDO’s earlier programme of support. The project aims to provide local government organisations with the skills, capabilities and support needed to design and deliver strategies that provide the environment needed for local economic development and create a series of bankable projects that will leverage additional investment. The project will focus on fewer countries but in greater depth, looking to demonstrate replicability by investing at scale.

The theory of change remains valid and there are no plans to make any changes to the expected outcomes or commitments to gender equality.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the remaining period?

The programme is broadly on track to achieve expected outcomes and contribute to the envisaged impact, within budget. The full effects of the COVID-19 pandemic are, however, still not fully known and in particular achievement of the target of 1,500 new jobs created by the end of the programme may be impacted by the ongoing pandemic and its after-effects though CLGF are confident it will be reached.

Outcome: Economic development, investment, and increased job opportunities in local communities in target countries.

Indicator 1: LED results in improved environment for doing business locally.

Target: Local business forums/associations (representing formal and informal traders) / chambers of commerce etc in four council areas report improved environment for doing business as a result of LED (March 2021)

Business forums and trade associations were a key constituency among the local organisations consulted in the development of the LED strategies in the focal countries. They highlighted three key areas:
- Improved communication with and from the local councils;
- Improved council processes for supporting businesses e.g. business registration and licencing, economic services and advice
- Improved infrastructure and basic service provision (e.g. rubbish collection, transport).

Follow-up consultations and surveys are being undertaken in the remaining period of the programme and will provide important evidence for the assessment for the Project Completion Review.

Indicator 2: Jobs created in local communities as a result of LED.

Target: At least 1,500 jobs created, positively impacting over 5,000 lives (March 2021)

To date, 612 jobs have been recorded as created, with an additional 10,865 individuals having profited from training and skills development programmes run as part of the programme. The CLGF is confident that the final target will be achieved as partner councils yet to report on job creation start to do so, and as investment fairs for bankable projects, postponed due to the COVID-19 pandemic, are held in all partner countries in the final quarter of 2020.
[note] CLGF is collecting data on job creation at three levels: (a) directly from ‘bankable’ projects supported within the project; (b) directly as outcomes of the pilot council implementation of their LED strategies; and (c) indirectly through the implementation of national LED strategies and LED rollout. The current figure is drawn from data collected from areas (a) & (b), which LCGF will be adding to in the final 6months of the project. CLGF is also working with its ministerial partners to collect data on area (c).

Impact: Improved livelihood for Commonwealth citizens as a result of local economic development.

Indicator 1: National SDG reporting on Goals 8 and 16.

Target: Progress in Commonwealth Countries towards achieving SDG 16 targets “ensuring responsive, inclusive, participatory decision making at all levels” and “develop effective accountable and transparent institutions at all levels” esp. Indicator 16.6.2 “percentage of population satisfied with their last experience of public service” (March 2021)

Despite being recognised as a key transformational and cross cutting goal, to date slow progress has been reported globally and within the Commonwealth against SDG16. The Synthesis of Voluntary National Reporting Review 2019 (page 66) recommended that: “To achieve SDG 16, accelerated action must be taken to strengthen the accountability and transparency of existing institutions, enhance public-private cooperation and trust, improve dissemination of information held by public institutions, reduce corruption among elected officials and combat terrorism.”

Of the fifty four Commonwealth Members, thirty four have submitted Voluntary National Reviews to the UN, with Bangladesh, Jamaica, Namibia, Rwanda, Samoa and Vanuatu providing data relevant to SDG 16, though much of the data provided is non-comparable with each country focusing on different aspects. While progress is slow, there are Commonwealth countries committing to take accelerated action, notably Sierra Leone which is co-chairing international working groups to promote SDG 16 in fragile and conflict-affected countries.
[note] Kenya (2020), India (2020), Eswatini (2019), Cameroon (2019), Ghana (2019), Lesotho (2019), Mauritius (2019), Nauru (2019) , New Zealand (2019), Pakistan (2019), Rwanda (2019), Saint Lucia (2019), South Africa (2019), United Kingdom (2019), Tanzania (2019), Vanuatu (2019), Australia (2018), Bahamas (2018), Sri Lanka (2018), Singapore (2018), Kiribati (2018), Canada (2018), Jamaica (2018), Malta (2018), Namibia (2018), Bangladesh (2017), Belize (2017),  Botswana (2017), Cyprus (2017), Nigeria (2017), Maldives (2017), Malaysia (2017), Sierra Leone (2016), and Samoa (2016,2020)
[note] Sierra Leone is co-chairing the Global Task Force on Justice of the G7+ group of countries leading the global agenda to address the problems faced by countries in fragile and conflict related contexts (see the Sierra Leone 2109 VNR).

Indicator 2: The relevance of LED in value chain development, sustainable consumption and production, and market development for trade across the Commonwealth is better understood.

Target: CLGF report/findings on relevance of LED to value chain, sustainable consumption and production and market development for trade across the Commonwealth is shared with the Commonwealth (for example via Trade Ministers) (March 2021)

CLGF has produced research on the linkage between trade (both national and international) and LED with a focus on value chains, sustainable and equitable consumption and market development. CLGF planned to highlight its findings at the CHOGM2020 Business Forum, however with the postponement of this meeting CLGF has revised and re-targeted activities for the remainder of the programme. A series of regional webinars are now planned with CLGF members; and a joint dialogue with the Commonwealth Secretariat is planned to discuss the intersection of LED and trade and the important impact local government and especially cities can have on supporting Commonwealth trade, with a view to this subject potentially featuring at the rescheduled CHOGM in 2021.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The project is helping to demonstrate the importance and relevance of LED to country, regional and local sustainable development and poverty reduction strategies. It is providing evidence of how LED can bring together a range of local actors , including the private sector, to work collectively to develop and implement strategies that enhance local economic opportunities, create jobs and strengthen and capitalise on local value chains, all relevant to Commonwealth and wider trade initiatives. The CLGF should continue to build on the experience gained through this programme and its predecessor highlighting the relevance of LED as part of Commonwealth members’ COVID19 economic recovery strategies.

C. DETAILED OUTPUT SCORING

Output Title	National/provincial local economic development (LED) strategies designed and rolled out (Botswana, Zambia and Sri Lanka)
Output number:		1	Output Score:	A (Met Expectation)
Impact weighting (%):		50%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of countries that have adopted the CLGF approach to LED and are rolling out national LED strategies which are designed to be (1) pro poor, (2) gender sensitive, (3) enable local participation, (4) locally responsive	On-going implementation of roll out [of strategies and M&E framework]. / Positive reporting of progress against agreed implementation plan and M&E framework (Oct 2019)	Target met: CLGF has continued to support the implementation of LED strategies which are (1) pro-poor; (2) gender sensitive; (3) enable local participation and (4) are locally responsive in the three target countries (Botswana, Sri Lanka and Zambia), with good progress reported. / In Zambia LED Guidelines have been included in the national integrated development planning process. All councils now develop LED plans as part of their national development planning responsibility. / In Botswana work is ongoing on guidelines for developing LED Strategies, Value Chains Maps and Bankable Business Plans in partnership with the Ministry of Local Government and Rural Development as part of the process to support the rollout of LED across the country. / In Sri Lanka CLGF continues to support the Provincial administrations with the development of LED pilots, although the terror attacks in April 2019, followed by political instability and the Covid-19 pandemic has impacted planned activities. Work is planned to resume following the August 2020 national election with a series of provincial dialogues on the potential of the LED approach in strengthening local economies. / Final target: National/ provincial LED strategies designed and rolled out in at least 2 countries (March 2021).
1.2 Percent of citizens surveyed in areas implementing LED report improvement with the council’s economic development services (disaggregated by gender)	Piloting KAP survey in three countries (Nov 2018) / Revise KAP survey method (Feb 2019) / Commission KAP survey (May 2019) / KAP survey completed (Feb 2020)	Target Met: Initial surveys were undertaken with stakeholders to inform the development of the LED strategies in 21 councils in the target countries, including identification of priority areas of work. / Follow up surveys to seek feedback on whether an improvement in services has resulted will be completed by the end of the project. / Final target: 75% percent of citizens surveyed in areas implementing LED report improvement in the council’s economic development services, disaggregated by gender (March 2021)

1.3 Target councils demonstrate increased capacity to develop bankable projects and successfully leverage investment	At least 8 (2/3rds) of target councils identify and start to develop business plans for at least one bankable project (Nov 2018) / At least 4 (1/3rd) are in dialogue with potential investors (July 2019)	Target Met: 20 participating councils have developed bankable project proposals. As of August 2020, over £1.1million of investment had been mobilised. / Final target: 8 (2/3) of target councils from OA 1 and/or OA2 develop bankable projects and successfully leverage funding of up to £1.5m for implementation of LED priorities (March 2021).

Briefly describe the output’s activities and provide supporting narrative for the score.

Throughout, the CLGF has worked to ensure LED strategies are (1) pro poor, (2) gender sensitive, (3) enable local participation, and (4) are locally responsive. Local participation and responding to local needs is at the core of CLGF’s LED methodology and integrated into national LED rollouts and LED strategy development and implementation at council level. These are locally driven processes, with local governments convening a broad cross section of the local population to input into the strategies.

Indicator 1.1: Targeted work plans for the development and implementation of National/Provincial LED Strategies (developed with national partners (Ministries of Local Government, Local Government Associations (LGAs) and key stakeholders including pilot councils) continue to be implemented in the three target countries (Sri Lanka, Botswana and Zambia), though the impact of the COVID-19 pandemic have slowed their implementation in 2020, especially in Sri Lanka . CLGF is working with its partners to review priorities to ensure gains in the National LED rollout are not lost due to the economic and social impact of Covid-19. For example:

In Botswana the LED rollout is aligned to the national agenda (11th National Development Plan and Visions 2036) and the Government’s Agenda 2030 plan, with poverty eradication as the core overarching priority. The national LED Framework and Action Plan are intended to guide and accelerate sustainable and inclusive economic growth and diversification at the sub-national level.

In Zambia the project is working with its partners to strengthen the local government sector to move beyond service provision and adopt a more developmental approach. This is reflected in the National Integrated Development Planning Process which, with support from this project, now includes LED (the LED guidelines developed through this project’s support).

Indicator 1.2: The KAP surveys, which are disaggregated by gender and in most cases by age, have informed the LED strategies and priorities at council level and are being revised to guide priorities and work plans in light of the social-economic impacts of the Covid-19 pandemic. For example:
[note] Knowledge, Attitude & Practices (KAP) survey consisting of predefined set of questions to provide access to quantitative and qualitative information.
- In Zambia the 4 pilot councils are prioritising services targeting women and youth through the strengthening of ward development committees.
- In Botswana the 11 pilot councils identified strengthened communication and dialogue between the local government and the business community, and have established LED Forums / Roundtables to serve as platforms to collectively address LED challenges and opportunities in the different localities.
- In Sri Lanka the 6 pilot councils are focusing on improving services that are most useful to supporting Small, Medium and Micro Enterprises (SMMEs), such as increasing the speed in processing of trade licences.

The results of the earlier surveys helped the councils better understand the issues being faced by the local business community, with a specific focus on ensuring the inclusion of women, youth and the informal sector. For example, in Zambia survey responses indicated that women and young people were disproportionately lacking in awareness of council activities and opportunities, hence the priority area identified of strengthening ward committees to better reach out to local communities.
Final surveys will be undertaken in the remaining period of the programme. The results will be disaggregated by gender and age, as well as against formal and informal employment. Some surveys are already underway. For example, in Kgalagadi (Botswana), 73% of respondents were female and 27% were male, 40% were between the ages of 20-29 years, 67% between 30-39 years and 8% between 40-48 years and with employment types including street vendors and informal shops. The data showed a satisfaction with the regulation of LED services including with the issuing of business licencing, which was rated at 93.3% positive. It also identified that the local council should work to improve the ease of doing business, with 60% of respondents requesting the local authority work towards attracting retail banks and property development.

Indicator 1.3: 20 participating councils have now developed bankable project proposals, as of August 2020 over £1.1m of investment had been mobilised. An example is a project aimed at enhancing the aquaculture industry in Kaoma, Zambia where the council has to date raised around £111,000 from a mix of government grants and private investment.

National and sub-national trade fairs in the three partner countries planned for 2nd and 3rd quarters of 2020 were postponed due to the Covid-19 lockdowns. Partners are revisiting proposals to ensure they remain economically viable in the new Covid-19 national and global environment. Investment fairs will be rescheduled during the remainder of the programme period and once the situation in national and sub-national economies stabilise. As of August 2020, CLGF remain confident that the target of £1.5m mobilised for projects will be achieved by the end of the programme.

Assess the VFM of this output compared to the proposition in the Business Case, based on performance over the past year

The relationships which CLGF has with local and national local government actors has seen the project able to test activities on the ground, but also influence local and national decision making, resulting in successful upscaling and roll out, with LED being integrated or mainstreamed into national development strategies.

The programme has built local partners’ capacity to better understand their local economies and the value chains that relate to them, helping them design and promote ‘bankable’ projects which have successfully attracted private sector or development funds.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The Covid-19 pandemic had a significant impact on this output area with the three focal countries experiencing significant periods of either full or partial lockdown. The economic impact of the pandemic has also impacted the potential viability of LED plans and bankable projects at council level, and diverted interest from LED at national/provincial level, though this is now reversing as governments begin to see LED as a potential strategy to support economic recovery. The extension of the programme will allow CLGF to support its partners to review and repurpose work undertaken to achieve the project targets and position their local and central government partners in the best possible position to use the tools, policies and methodologies developed in the project to support their post-Covid recovery plans.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the remaining period.

The 2018 Annual Review recommended that the CLGF ensure a cross section of staff and leaders were directly engaged in the projects to ensure wide engagement to mitigate the risks around staff turnover and their impact on project deliverables. The CLGF has responded to this by engaging with officials at national, local and provincial levels as well as local business communities and citizens.

Lessons: CLGF’s projects are helping demonstrate the value of inclusive approaches both at the national and local level. Local Economic Assessments (LEA) provide a key input to both LED strategies and the development of bankable projects ensuring that the work undertaken by councils is aligned with local realities and potential, as well as with citizens’ asks.

LED capacity building with local leaders and technical staff, remains a key priority to underpin the efforts for successful LED strategies at both the local and national levels.

Work on bankable projects requires a number of previous actions to be in place and for LED to be well understood and integrated into the council processes. Mainstreaming LED into the work of local councils makes the council more resilient to shocks such as the current pandemic and better able to respond to new stresses and community priorities.

A key lesson from the project has been the value of working at both a national and local level. The results of local LED approaches have been used by Ministries to inform the development of national policies/guidelines on LED. CLGF advise that there is also emerging evidence of LED approaches making the case for decentralisation, e.g. Botswana.
From a local government perspective, LED approaches have highlighted a positive aspect of the work of councils and is helping to build a more consultative and developmental relationship between the council and the community in many of the target councils, demonstrating how such engagement can be used to help address the concerns of disadvantaged groups such as women and youth entrepreneurs.

Recommendations for remainder of the programme:
The CLGF should ensure that the results of the final KAP surveys are available ahead of the project completion date as this will be a key source of evidence for the impact of the work undertaken. These should provide disaggregated data, by gender, age and employment status. CLGF to share the survey questionnaire with FCDO for review and input prior to commissioning responses.

The CLGF should continue to work with its partners to support them in attracting investment for ‘bankable’ projects.

Output Title	Increased capacity to roll out LED in selected countries (Ghana, South Africa and Eswatini (formerly Swaziland).
Output number:		2	Output Score:	A (Met Expectation)
Impact weighting (%):		20%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of countries embedding the CLGF approach to LED, where appropriate, in national policy, legal, regulatory and capacity development frameworks for LED	Policy review/amendments started where required, responding to assessment findings (July 2018) / Dialogue underway with stakeholders needed for ensuring buy-in for roll out (March 2019) / Positive progress reported against targets set out in implementation strategies for roll out (July 2019)	Targets Met: CLGF has strengthened its relationships with the key national actors in the three countries and supported them in the rollout of their national LED strategies. / Final target: Two countries have increased capacity and are rolling out their LED strategy (March 2021)
2.2 Capacity of technical staff and political leaders to deliver LED services increased (councils and ministries)	At least 80 technical staff and political leaders trained to deliver LED services (July 2018) / Evidence of increased capacity demonstrated via a sample of stakeholders participating in key practitioner tracking (March 2019) / 120 technical staff and political leaders are actively participating in the national roll out (July 2019)	Target exceeded: Over 200 technical staff and political leaders have been supported to increase their capacity in LED delivery (achieving the anticipated target for the programme). The project is continuing to build capacity with key practitioners including through online training so as to further embed LED capacity and respond to the new economic challenges arising from the Covid-19 pandemic. / Final target: Increased capacity of 200 technical staff and political leaders to deliver LED services demonstrated (March 2021).
2.3 Improved economic opportunities for citizens in areas implementing LED	KAP survey developed and piloted in three councils (July 2018) / Piloting KAP survey in three countries (Nov 2018) / Revise KAP survey methodology (Feb 2019) / Commission KAP survey (May 2019) / KAP survey completed (Feb 2020)	Targets Met: Surveys have been undertaken with stakeholders in the development process of the LED strategies. / In Ghana the four project councils gathered data on small businesses and council service uses, while local economic assessments (LEA) have been undertaken in the District of Bojanala in South Africa and 10 councils in Eswatini. These surveys informed priority areas of work over the course of the project. / Partner councils are currently reviewing their LED strategies to respond to the socio-economic impact of the COVID-19 pandemic. Final surveys to seek feedback on whether an improvement in services has resulted will be undertaken in the remaining period of the programme. / Final target: 60% of surveyed citizens who have used council LED services report improved economic opportunities (March 2021).

Briefly describe the output’s activities, and provide supporting narrative for the score.

Indicator 2.1: Over the period key achievements have been:

In South Africa, CLGF worked with the Ministry of Cooperative Governance and Traditional Affairs (COGTA) and South African Local Government Association (SALGA) to develop Regional Economic Development Guidelines which have now been finalised and circulated to all regional authorities. CLGF also worked with COGTA on the National LED Framework which provides the wider context for the targeted work CLGF has been supporting on regional economic cooperation.

In Ghana, CLGF worked with the Ministry of Local Government and Regional Development (MoLGRD) and National Association of Local Authorities of Ghana (NALAG) in the review of the National LED policy, supporting both the assessment of the 2013 policy, and the development of the revisions based on these recommendations. The revised policy was taken to a finalising workshop in August 2020, the validated Draft National LED Policy 2020 will now be submitted to the Minister for final approval. The revised LED Policy is expressly “built around the principles of gender equality, equity and inclusiveness in local economies and encourages effective and inclusive participation of different stakeholders without distinction based on status, gender or class”.

In Eswatini CLGF has worked with its partners on the national rollout of LED building capacity with councils and working with the Ministry of Housing and Urban Development (MoHUD) on developing the guideline for LED funding options, specifically around private finance initiatives for urban local government; however the COVID-19 pandemic did delay progress. The LED rollout is linked to the priorities of the National Development Strategy, which is expressly a pro-poor development strategy and has at its core improving the living standards in the country through poverty eradication, employment creation, gender equality, social integration and environmental protection.

Indicator 2.2 : While the numeric target of 200 technical staff and political leaders supported to increase capacity in LED delivery has been reached, CLGF’s work with key practitioners continues as part of the wider programme rolling out LED in the focal countries both with technical staff and political leaders. This ongoing capacity building has been targeted to key priority areas, such as for example in South Africa, where workshops on the application of the Regional Economic Development Guidelines and joint resource mobilisation were undertaken to further embed these policies into local systems.

CLGF has responded to the COVID-19 pandemic by moving training activities online, having worked with partners to assess whether they had the necessary tools to participate in virtual/online learning and what would need to be adapted and updated to allow a successful transfer of knowledge in an online format. CLGF report that to date this process has been successful in allowing the project to respond to the new and emerging needs of beneficiaries and support discussions on the revisions to LED strategies and bankable project proposals. The move to delivery of some activities online has also allowed CLGF to increase the project’s reach especially among technical staff at council level.

CLGF is tracking several key practitioners within each country who play integral roles either with the pilot councils, ministry or association. Their feedback on the support provided by CLGF has been positive. Currently the key practitioners being tracked are 34% women & 65% men, with a breakdown by role being 7% elected, 24% director level, 39% manager level and 29% officer level. A final survey of those supported through the programme will be undertaken in the remaining period of the programme. Data will be collected by gender, age and type of position (elected or technical; director; manager or officer) and will be reported in disaggregated form by these categories in the final reporting.

Indicator 2.3: Surveys have been undertaken with stakeholders in the three partner countries.

In Eswatini the surveys highlighted that local businesses in the pilot councils were experiencing skills shortages in the following disciplines: accounting, engineering, computer skills, catering, construction, and computing. In response a number of councils are supporting skills training in partnership with existing community groups (for example in Pigg’s Peak Town Council where a programme upskilling young entrepreneurs is underway). With regard to council service provision respondents highlighted communicating with local government and turnaround time in addressing complaints/issues as key concerns. In response, pilot councils are putting in place service charters that confirm turnaround times and complaint systems to address business sector concerns, thereby creating an enabling environment for business. They are also working to improve service delivery and reduce red tape.

In Ghana, the surveys highlighted a desire for improved communication and information on council services. In response, councils have increased their outreach LED activities. In Tema council district a follow up survey prior to COVID-19 provided preliminary data on citizen satisfaction, with 62% of respondents being satisfied with the council’s customer service and 72% satisfied with the council’s communication of its plans. 60% of respondents were women and 40% men, with 2% under 25, 58% between 25-44, 38% between 45-65, and 2% over 65. When asked to self-classify by type of employment, 40% were self-employed, 57% were formally employed, and 2% selected other.

In South Africa the surveys of businesses in Matlosana and Madibeng council areas outlined concerns linked primarily to delivery of essential services and economic infrastructure, such as electricity supply, sewage facilities, road infrastructure and refuse collection. The councils are investing additional resources to respond to these issues.

Final surveys will be undertaken in the remaining period of the programme. These will provide gender and age disaggregation, as well as disaggregation against formal and informal employment.

Assess the VFM of this output compared to the proposition in the Business Case, based on performance over the past year

This work has demonstrated value for money by drawing on CLGF’s wide technical expertise much of which can be accessed at low or no cost from within its network of members to support existing investment by governments in the LED rollout. It is matching the lack of technical expertise with national government funding and commitment for LED implementation.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No significant changes have been made – or are proposed to be made - to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the remaining period

The 2018 Annual Review identified two recommendations in regard to this output:
- CLGF should continue to prioritise and strengthen institutional relations and linkages with its existing project partners, as well as seek to build new linkages as appropriate with other key stakeholders;
- CLGF should continue to look for opportunities to support the informal sector and specific target groups (such as women and youth) in LED pilot work at the local level to ensure national LED rollouts are pro-poor and as inclusive as possible.

The CLGF has taken action in response to both recommendations. CLGF has worked to strengthen its partnerships with its core partners in the national Ministries and local government associations. These relationships proved valuable including during the COVID-19 lockdown ensuring the project work remained a priority. CLGF has also continued to reach out to civil society organisations where appropriate to reinforce project objectives at both the national and local level. An important focus of this work has been to provide additional support for LED initiatives around women and youth economic empowerment.

Lessons: The programme continues to demonstrate the value of participative and inclusive approaches, building on many of the partnerships established under the earlier project. Providing space for intergovernmental dialogue has been important in supporting LED rollout in the three countries, allowing different actors to come together to raise challenges, barriers and concerns impeding the national rollout of viable LED policies and processes. The institutional relationships and trust between partners built over multiple project years of joint work continues to ensure that CLGF is included in key strategic discussion and activities (such the update of the Ghana LED policy).

CLGF has a wealth of knowledge and good practice both in LED policy and practice as well as in the potential peer support that the network can draw on both in terms of individuals and institutions. Drawing on this technical and practitioner expertise is a key interest for the project partners at all levels.

Recommendations for the remainder of the programme:

The CLGF should ensure that the results of the final KAP surveys are available ahead of the project completion date as this will be a key source of evidence for the impact of the work undertaken. These should provide disaggregated data, by gender, age and employment status. CLGF to share the survey questionnaire with FCDO for review and input prior to commissioning responses.

Output Title	Increased awareness of LED potential in selected countries with some fragility (drawn from Bangladesh, Cameroon, Lesotho, India, Pakistan, Sierra Leone, Zimbabwe)
Output number:		3	Output Score:	A+ (moderately exceeded expectation)
Impact weighting (%):		15%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1 National actors (i.e. Ministry of LG, LGA, business fora) use lessons from demonstration projects and national/regional exchange to inform enabling policy and LED practice to empower local governments to deliver LED	National actors in at least four countries are working towards improving policy and practice in LED (July 2019) / At least two Local Government Associations (LGAs) have developed policy recommendations supporting LED adoption (July 2019)	Targets met: National actors in India, Sierra Leone, and Zimbabwe continue to work towards improved policy and practice on LED. / Work at council level (supported through the project) has significantly influenced and informed national actors in their work on LED. Zimbabwe and Madhya Pradesh (India) have used lessons from demonstration projects to integrate LED approaches into national/state policies and programmes. Local government associations in Zimbabwe and Madhya Pradesh, India have also developed and are implementing LED strategies. / Work remains ongoing in the three focal countries to further consolidate gains and inform national/state policies. / Final target: National actors in at least two countries use lessons from demonstration projects, national and regional exchange and learning, to inform policy development (March 2021)
3.2 LED demonstrated as an approach to integrated local development	LED strategies adopted and being implemented by 6 councils (March 2019) / At least 4 councils are undertaking LED activity (July 2019)	Target exceeded: 15 councils across the three target countries have developed and are implementing LED strategies. / Final target: 4 councils have demonstrated the LED approach through the development and implementation of LED strategies (March 2021).
3.3 Improved economic opportunities for citizens in areas implementing LED	Piloting KAP survey in three countries (Nov 2018) / Revise KAP survey method (Feb 2019) / Commission KAP survey (May 2019) / KAP survey completed (Feb 2020)	Targets Met: Surveys have been undertaken with stakeholders to inform the development of LED strategies, which have in turn informed priority areas of work. Final surveys to seek feedback on whether an improvement in services has resulted will be undertaken in the remaining period of the programme. / Final target: 50% percent of citizens surveyed in areas implementing LED report improvement in the council’s economic development services (disaggregated by gender) (March 2021).

Briefly describe the output’s activities, and provide supporting narrative for the score.

Indicator 3.1: National actors continue to draw on CLGF work to improve policy and practice for LED. Key achievements in the past year include:

In Zimbabwe, the Urban Councils Association of Zimbabwe (UCAZ) & Ministry of Local Government and Public Works (MLGPW) conducted their joint annual conference (with support from CLGF) under the theme “Urban Local Authorities, Embracing Devolution Towards Attaining Vision 2030” in November 2019. The conference created a platform for constructive engagements between local authorities, government and other stakeholders, and clarified the provisions of devolution and its implementation plan.
[note] While Zimbabwe is not currently a Commonwealth member, the CLGF has maintained its close relationship with local government in the country and has continued to work on a number of initiatives supporting local government and local communities’ access to services. In Zimbabwe, FCDO project funds are only used to support activities of local government associations and/or local councils.

In Sierra Leone a workshop on ‘LED and procurement’ led to pilot councils adopting guidelines for using local council procurement practise to strengthen LED. The Sierra Leone national Government participated in the meeting and committed to support and mainstream the guide through all local councils in the country. CLGF continues to advocate for the approaches detailed in the guidelines within government, local government and the donor community. For example, CLGF and its partner councils are currently helping the National Planning and Procurement Authority (NPPA) to apply the new regulations included in the 2019 budget speech.

In India, the Madhya Pradesh State Rural Livelihoods Mission (MPSRLM) has, with CLGF support, developed a tailored training module on LED which is being used with its all MPSRLM practitioners and professionals.

Indicator 3.2: In Zimbabwe, nine councils have developed and are implementing LED strategies. This is the first time that local councils in Zimbabwe have been asked to take an active developmental perspective on their local economies. A programme of capacity and support from CLGF helped them through the full - from undertaking local economic assessments, to developing their internal staff capacity to develop, implement and oversee the LED plan, through to the implementation of specific projects within the plan. For example, Mutoko council’s LED plan includes a focus on the vegetable and green product sector, with provision of market sheds and incentives for construction of and investment in processing plants.

In Madhya Pradesh, India the cities of Jabalpur and Ujjain have implemented initiatives supporting incubation centres and ‘start-ups’ (technology and non-technology). The pilot incubation centres provide advisory support, mentoring, office space and facilities to entrepreneurs in their first year of business start-up. Forty start-ups have now graduated from the incubator centre and are operating independently. One of these, “Hope for Faith Youth” has created an e-marketing platform which links rural artisans & self-help groups to online markets, creating and/or reinforcing 50 jobs.

Jabalpur has successfully taken its support to ‘start-ups’ online following the national Covid-19 lockdown. CLGF supported this move online through a monthly orientation and training series attended by over 10,000 participants. Focal areas included: understanding the basics of a start-up; moving from idea generation to shortlisting and validations: development funding proposals & business models; revenue model; government support programmes; pitching; mentoring, marketing and the basics of business finance etc. The publication of a compendium of government provisions for entrepreneurs and start-ups is currently being developed as part of the follow up to this programme.

In Sierra Leone the four pilot councils focused their LED strategies on helping SMEs in their local area to be able to potentially benefit from council procurement opportunities. They have also increased awareness and capacity within their staff to consider opportunities for local providers through production of guidelines and training. Up to August 2020, 289 SMEs/individuals had received training and support on Business Basic procurement and business management skills and/or specific thematic focal areas (such as agriculture or waste management/recycling). The CLGF is compiling data on contracts won by local providers.

Indicator 3.3: Consultation with stakeholders has been integral in developing the council LED plans and priority activities.

In Zimbabwe citizen feedback indicated job creation as a top priority. Councils have prioritised building good relations with existing businesses and supporting SME development. LED forums have been created in four local authorities, namely Mutare City Council, Rushinga RDC, Bindura and Kadoma City Council to interact in a coordinated way with the local business community. Across the nine council internal changes such as the creation of business departments, business unit focal persons, and LED forum have been put in place to improve service delivery to the local business community.

In Sierra Leone the survey identified a need for improved communication by councils on economic opportunities and on council services. The pilot councils have ensured this is a priority area of their interventions.

In the baseline survey in Madhya Pradesh, India, 53% of respondents were women and 47% men, whilst 30% were self-employed, 8% employed in the formal sector, 5% informal employment, 7% unemployed, 25% housewives, 25% chose other. A follow-up survey has been undertaken with initial results indicating an improvement in the council services and economic opportunities from its Smart City Incubation initiative will contribute to generating more livelihood/ employment opportunities, and to wider LED in the city. In a preliminary survey undertaken in Jabalpur, 93% of incubation centre users rated the service provided by the centre as ‘excellent’.

Final surveys will be undertaken in the remaining period of the programme. These will provide gender and age disaggregation, as well as disaggregated data against formal and informal employment.

Assess the VFM of this output compared to the proposition in the Business Case, based on performance over the past year

The use of the CLGF network has delivered VFM by ensuring that action is linked to national policy and priorities, and leverage of additional funds as a result of FCDO’s investment has seen the anticipated number of target councils implementing LED strategies significantly exceeded.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No significant changes have been made – or are proposed to be made - to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the remaining period

The 2018 Annual Review contained the following recommendations for this output:
CLGF should continue to involve project stakeholders in guiding the project over the course of implementation to ensure it remains tailored to the local context and it evolves in line with the changing political and social-economic priorities;

CLGF should continue to use LED practitioners from partner countries with experience of LED to share good practice and practitioner know-how.

The CLGF has taken action in response to both recommendations. In the three focal countries CLGF has taken tailored approaches to introducing LED into its partner countries, focusing interventions in areas where partners have identified either a need or an opportunity. Building on these opportunities and demonstrating the flexibility of the LED approach has helped convince political partners and ensure institutional buy in for ongoing project work while embedding LED methodologies. Working with and through local practitioners has allowed for the domestication of general principle and ensured that the core principles of LED are more easily transferred into general practice within partner institutions.

Lessons: CLGF continues to stress to its partners the importance of tailoring LED processes to each country’s national context. While CLGF can draw on experience from other country work to propose ideas and solutions to challenges, political will, support, and champions play a critical role, as does tailoring interventions to socio-economic and cultural appetites. Involving local, provincial and national stakeholders is a key driver of LED interventions and, while this process can slow down activities and interventions, it is essential for longer term sustainability and real system reform. An important lesson in building uptake for LED across government is framing local successes within the framework on national development policies so that all levels of government can easily see the benefits, and the programme has seen considerable successes with this approach.

Recommendations for the remainder of the programme:

The CLGF should ensure that the results of the final KAP surveys are available ahead of the project completion date as this will be a key source of evidence for the impact of the work undertaken. These should provide disaggregated data, by gender, age and employment status. CLGF to share the survey questionnaire with FCDO for review and input prior to commissioning responses.

The CLGF should also ensure data on contracts won by local providers in Sierra Leone is available ahead of project completion.

Output Title	CLGF acknowledged as a Commonwealth centre of LED learning and good practice.
Output number:		4	Output Score:	A+ (moderately exceeded expectation)
Impact weighting (%):		15%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Regional and global policy events highlight the effectiveness of LED as a means of achieving sustainable development	One regional and/or global policy event highlights the effectiveness of LED as a means of achieving sustainable development (Dec 2019)	Target met: CLGF’s strategic plan highlights LED as a core focal area for advocacy and policy influence. A targeted overview of key events was drawn up at the beginning of the project and has been periodically updated to ensure maximum impact. / Key priority forums that the CLGF has participated in over the past year include: / The annual UN High Level Panel Forum where local government is among the major groups making representations on SDG progress. Sept 2019; June 2020 (virtual) / The World Urban Forums (WUF) at which CLGF worked with other organisations such as Cities Alliance to ensure LED is on the agenda in multiple regional and global sessions. (Oct 2019; Feb 2020) / CLGF has also promoted LED through its regional meetings such as the Southern African Regional meeting which took place in Zambia in 2019 and brought together 130 participants from Ministries, Associations of local government and partner local councils from 10 countries of the SADC region. / Final target: Three regional and/or global policy events highlight the effectiveness of LED as a means of achieving sustainable development (March 2021).
4.2 National actors capitalise on the Commonwealth's shared systems, structures, language and governance to successfully implement LED	Knowledge management strategy on resources and good practice on LED being implemented (Dec 2018) / Number of quality materials and resources available through the CLGF knowledge hub increased (May 2019) / Member survey completed on impact of CLGF resources on understanding of LED among members (Dec 2019)	Targets moderately not met: CLGF has continued to implement its knowledge management strategy over the period. / CLGF has increased the number and variety of materials and resources held in its knowledge hub and additionally provided specific advisory support to some CLGF members. / A survey of Members on LED is underway and expected to be completed in November 2020. / Final target: CLGF members in three countries not participating in output areas 1,2 and 3 use CLGF resources and good practice on LED to inform policy and practice (March 2021).

4.3 CLGF’s knowledge hub has a sustained increase of quality LED-focused resources, reviewed on an annual basis with annual increases in the number of visitors to the knowledge hub on the CLGF website.	10% increase on the previous year's visitors to Knowledge Hub (March 2019) / Peer review of LED-focused resources in CLGF Knowledge Hub commissioned (July 2019) / 10% increase on the previous year's visitors to the Knowledge Hub (March 2020)	Targets exceeded: A peer review of the LED focused resources in the Knowledge hub was undertaken and confirmed their quality and relevance. / CLGF reports a 33.5% growth in users over the period Aug 2019-July 2020 compared to the previous year (Aug’18-July’19). This follows significant increases over the two years prior (96% for the 2018-19 period and 25% for 2017-18). / Final target: Peer review of LED-focused resources confirms good quality resources in the Knowledge Hub and number of visitors has increased by at least 10% per annum (March 2021).
4.4 % of funding leverage against FCDO contribution	25% of the FCDO contribution leveraged (March 2019) / 40% of the FCDO contribution leveraged (Dec 2019)	Targets exceeded: CLGF has successfully leveraged increasing contributions against the FCDO funding. As at August 2020, these leveraged contributions totalled over £3.5million for project work in the three focal regions of the project (Southern Africa, West Africa and South Asia). This has come from a mix of regional, national and sub-national sources, including the EU, CLGF member Local Government Associations, Ministries and councils. / Final target: 65% of the FCDO contribution leveraged (March 2021).

Briefly describe the output’s activities, and provide supporting narrative for the score

Indicator 4.1: CLGF has participated in several global and regional policy events over the course of the programme to actively promote the outcomes of the project and to highlight the important role of local government in local economic development and achieving global development targets. In the past year CLGF has made presentations to key global and regional events:
- The World Urban Forum 2020 & Asia Pacific Urban Forum 2019
- The World Assembly of Local and Regional Governments,
- The EU Policy Forum for Development - regional meetings
- UN HLPF annual events
- Side event on local government as part of the UN Commission on the Status of Women (CSW)
- COP26 preparatory meetings & Mayors and Ministers dialogue on Local and Regional Contributions to achieving the Paris Climate Agreement

CLGF has used its participation in these forums to disseminate learning and good practice emerging from the FCDO LED project, to strengthen the ability of local government to support local economic development within the framework of their existing mandates.

CLGF has also supported its members through the provision of policy advice. For example, as part of its role in the High Level Political Forum (HLPF) Global Taskforce (GTF), CLGF provided inputs to the local government statements on localising SDG 8 and 16 and mobilised members of its executive committee along with its Deputy Secretary General to speak during the 2nd Local and Regional Governments' Forum, on Tuesday, 24 September 2019 within the framework of United National General Assembly high-level week. The Forum saw the adoption of the constituency’s Statement to the SDG Summit.

Indicator 4.2: CLGF has actively sought to disseminate lessons and experience to the wider CLGF membership. Although the biennial conference of CW Local Government Ministers was postponed due to the Covid-19 pandemic, CLGF decided to develop a series of workshop and convene a number of online meetings to ensure information and experience sharing could continue.

CLGF continues to be responsive to its members’ requests for support. For example, during the past year CLGF has worked with both Uganda and Fiji to support development of their LED focused programmes for their local government sectors. In Uganda CLGF has worked with the Ugandan Local Government Association (ULGA) and drawn on work undertaken in South Africa to integrate a regional approach into its ongoing work on LED (funded through an EU grant). In Fiji CLGF has worked with the Ministry of Local Government to develop an action plan to encourage local councils to integrate the LED approach into their local planning.

Indicator 4.3 CLGF has continued to increase the number of high-quality resources on LED within its knowledge hub and its online resources and reported significant year-on-year increases in users. CLGF has also tracked the use of materials on the knowledge hub with journal articles being sighted in other publications 1294 times since 2015, an increase of 319 citations on the 2019 data. CLGF is promoting the knowledge hub through its communication with members and partners toward increasing recognition of it as a key source of information and good practice on local government and LED.

A dedicated knowledge management strategy on resources and good practice on LED has been developed and continues to be implemented. CLGF undertook a review of the materials available on the knowledge hub to assess the breadth and quality of these materials and commented favourably on available resources on equitable economic growth and the experience of Southern countries in the implementation of LED. CLGF is working with its research and university partners to increase the number of country specific resources available.

Indicator 4.4: CLGF has to date successfully leveraged over £3.5million, equivalent to 90% of the FCDO contribution, for work aligned with the programme plans at the global, regional, national and sub-national level. FCDO funding has helped CLGF and its partners to leverage partnerships with other organisations for example, international donors and partners supporting CLGF cross Commonwealth partnerships (Microsoft and the Commonwealth Secretariat), national donor programmes (e.g. €1.9million project contract with the EU Delegation in Zambia for targeted work with local government including LED activities), and CLGF members and partners directly involved in the national and local projects (including the State Government in Madhya Pradesh (India) providing 90% of the cost of the LED orientation activities, or the local councils in Ghana which have all made commitments from council budgets to pilot projects designed under the CLGF). This member co-funding of activities supports partner buy-in to the work and provides an important indicator of the long-term sustainability through institutionalisation of project work into wider LGA, Ministry and council practices.

Assess the VFM of this output compared to the proposition in the Business Case, based on performance over the past year

FCDO’s investment has helped CLGF to secure a significant investment in a larger portfolio of projects in support of LED. A modest budget to support CLGF’s advocacy has also ensured that CLGF has been able to champion LED as a strategy for poverty reduction and achieving SDGs across its Commonwealth membership and more widely in international debate and dialogue.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No significant changes have been made – or are proposed to be made - to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the remaining period

The 2018 Annual Review recommend:
CLGF should continue to ensure it is present and actively feeding into key Commonwealth and international policy discussions and events on LED, the SDGs and women in development to continue to influence these agendas and build knowledge and awareness of the role of local government in delivering development.

CLGF should continue to draw on the research outputs of its academic partners to feed into its programme of work both in projects and advocacy.

As detailed, the CLGF has proactively responded to these recommendations over the subsequent period.

Lessons: CLGF’s effectiveness as a Commonwealth organisation and in its wider global advocacy is significantly linked to the evidence base it draws from its project work at country and council level. A strong focus on evidence-based policy making has the potential for real impact with Commonwealth members. CLGF is recognised as a leader on LED and is called on by organisations to ensure that advocacy messages related to LED properly reflect the reality of local governments both in the challenges and potential result that LED can deliver (as of the case with the GTF submission to the UN HLPF).

CLGF continues to use the FCDO funds to help leverage additional funding for LED across its focal countries and support further work at both the local and national level.

Recommendations for the remainder of the programme:
The CLGF should continue to utilise evidence from its work in the target countries under outputs 1 – 3 and promote LED to other Commonwealth countries.

D: RISK

Overview of risk management:

The overall risk rating for this programme was MINOR. Based on reported progress, the risk assessment remains as MINOR.

The Business Case reflects that the main major risk to the success of this programme is political change in target countries, and the resulting potential for change of direction within national and/or local administrations. Other risks included: staff turnover and a lack of delivery capacity in LGAs and pilot councils.

Whilst there have been instances of political instability in some target countries, commitment to LED among the national, regional and local administrations has remained strong throughout the programme period, with progress achieved in line with anticipated milestones.

CLGF has worked consistently to build buy-in to the programme across the political spectrum in each country, as well as a wider more general cross-Commonwealth buy-in to LED as a methodology for delivering sustainable development. It has taking a flexible and adaptive approach to the development of workplans in close partnership with a range of stakeholders so as to ensure a wide base of support for objectives and activities. These have been effective and CLGF’s pro-active engagement and pragmatic approach to adaptive management mean the residual risk remains MINOR.

The Covid-19 Pandemic has introduced some additional risks; however the extension has sought to mitigate these with additional time to adjust and re-prioritise work with partners. However, new risks arising from the pandemic may impact on the full achievement of outcome and output targets:

RISK	MITIGATION
A second spike of infection in any of the partner countries	This will require CLGF to remain nimble in planning and responding quickly to changing contexts
Access to finance for the bankable projects may be more challenging, as resources are more limited or have been diverted into other urgent priorities	Working within the framework of a LED strategy means that the proposals for bankable projects have strong local relevance and local demand which should enhance their attractiveness to investors
Partner councils may be focused more on social and core services as a result of the need to provide urgent humanitarian support, with limited/reducing resources	CLGF will continue to work with its partners to promote LED as an important lever for local governments to help rebuild their income streams post COVID19

Whilst these risks are largely out of CLGF’s control, CLGF will continue to keep them new risks closely in view and take additional measures in response, where feasible.

E: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including consideration of VFM measures of economy and efficiency.

The programme builds on a previous pilot programme. CLGF has ensured that project delivering has progressed broadly in line with original expectations and within budget.

The CLGF has provided detailed quarterly narrative and financial reporting to the FCDO programme team, supplemented by regular meetings and communications to ensure FCDO is kept abreast of developments and day to day project management issues.

CLGF remains committed to good practice in the management and delivery of its programmes and projects and has a set of internal policies in place to ensure equal opportunities and safeguarding (gender strategy, safeguarding policy, whistleblowing, risk management, etc.) in line with FCDO’s due diligence process.

In regard to VFM, the CLGF has very little direct procurement of goods and services, however, procurement processes are in place throughout the project and include competitive bidding when specialist services are required for any purchases. As a membership organisation with an extensive network of members and partners, CLGF identifies and mobilises technical expertise and capacity at low or no-cost to the project. In addition to ensuring that the project can draw on experienced and skilled expertise with experience of working in the local government sector, this also helps to strengthen Commonwealth links and partnerships at the local level.

Date of last narrative financial report	August 2020	Date of last audited annual statement	For 2018/19 Financial Year (Dec 2019)