Annual Review – June 2018 to May 2019

Title: Responsible, Accountable and Transparent Enterprise (RATE)
Programme Value £ (full life): £30.3 million		Review Date: August 2019
Programme Code:	Start Date: / August 2014 / (with varying start dates for implementing partners)	End Date: / March 2020 / (implementation period 5 years, with shorter periods for individual components and partners)

Summary of Programme Performance
Year	2015	2016	2017	2018	2019
Programme Score	A	A	A	A	A
Risk Rating	Medium	Medium	Moderate	Moderate	Moderate
[note] Since the 2016 Annual Review was conducted, DFID has changed the programme risk rating system from a three-tiered system (Low/Medium/High) to a four-tiered system (Minor/Moderate/Major/Severe). The RATE programme risk rating has changed accordingly to moderate, where it was previously categorised as a medium.

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4547408.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4688140.xlsx

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The RATE programme aims to both ensure and improve the safety and well-being of poor women and men, where business activity affects their lives. It directly feeds into Sustainable Development Goal (SDG) 8: Decent Work and economic growth. It is managed by DFID’s Private Sector Department and will spend up to £30.3 million by March 2020 through giving grants to organisations that work to drive up responsible business standards.

The programme takes a multi-dimensional approach. It aims to affect change at both a systemic level, (for example through promoting greater transparency around issues like business and human rights, ranking company performance, and promoting better standards on public and private procurement) and at a local level (e.g. through looking to solve problems that exist in specific supply chains and geographies).
It combines providing support to some well-established techniques, such as encouraging supply chain businesses to become certified suppliers, with newer interventions, including new technologies to enable better dialogue with workers in global supply chains and testing company legal forms that include social and environmental considerations, as well as financial ones.

Across all its work RATE aims to:
- scale up the activities of organisations working within each of these spaces;
- grow the evidence bases around “what works” in terms of ensuring and improving the lives of poor people affected by business activity; and
- spread responsible business approaches more widely throughout DFID’s economic development programming.

Current grantees

Partner	Area of DFID support	Grant period
The ISEAL Alliance (ISEAL)	Collecting and sharing evidence on the impact and business case for credible sustainability standards. Identifying and piloting innovative approaches to the use of sustainability standards by business.	2014-18
Fairtrade Foundation	Piloting and promoting a suite of supply chain mapping tools - Fairsource - for use by companies to improve the sourcing of agricultural commodities such as cocoa, flowers and cotton.	2016-18
Global Reporting Initiative (GRI)	Advancing the impact of sustainability reporting by updating/developing the GRI reporting guidelines and supporting sustainability reporting in African priority countries.	2015-19
UK National Contact Point (NCP) for the OECD Guidelines for Multinational Enterprises	Co-funding the DIT unit responsible for raising awareness of the OECD guidelines with businesses, trade unions and NGOs and implementing the OECD guidelines complaints mechanism.	2014-19
British Academy	Funding innovative international research into the causes, consequences and solutions to child labour, human trafficking and modern slavery.	2017-19
UN Global Compact (UNGC)	Support to the world’s largest sustainability initiative to: increase UN agencies collaboration with the private sector; increase corporate action on gender equality, climate care and agricultural sustainability; and strengthen UNGC Local Networks capacity to implement corporate sustainability priorities relevant to SDGs. Also sponsoring the Decent Work Platform to build an alliance of companies committed to taking action on modern slavery and child labour.	2014-20
B Lab	Launch and support a regional B Lab hub for companies based in East Africa as part of a global network of Certified B Corporations who meet high standards of social and environmental performance. / Create and drive adoption at scale of an actionable management platform for businesses to assess, compare and improve their performance against the SDGs.	2016-20
Humanity United	Identifying and investing in early stage start-ups using new technology to identify and tackle forced labour in supply chains.	2017-19
Ethical Trading Initiative (ETI)	Support for ETI’s five year-strategy – ETI Perspective 2020 – to / improve worker’s rights in company members’ global supply chains.	2015-20
Shift	Improving companies’ human rights reporting through capacity building based on use of the UN Guiding Principles Reporting Framework and 2) Development of Reporting Maturity Methodology to analyse the maturity of existing company disclosure on human rights that is then uploaded to a Reporting Database.	2016-20
ShareAction	Launching and supporting the Workforce Disclosure Initiative (WDI). The WDI aims to harness institutional investor engagement in demanding better information and improved workforce policies and practices from multinational companies.	2016-20
World Benchmarking Alliance (WBA)	Preparatory work to build publicly available benchmarks, which show the progress – or lack - of the world’s top 2000 companies on the SDGs.	2017-20
Fourth Sector Group 2030 (FSG)	Creating tools for identifying, mapping, and analysing for-benefit companies and the fourth sector’s ecosystem. Creating guidance for business investors and government. Promoting knowledge transfer through outreach and consultation.	2019-20

Summary supporting narrative for the overall score in this review (1/2 page)

Overall, the assessment in this annual review is that the individual elements of RATE have performed well and are on track to deliver expected results. Five partners have now completed their part of the programme and have either finalised their close out reports. Outcome and output performance for the partners is generally positive (see summary table below).

The promotion of responsible business practices through the RATE programme has had an impact beyond the indicators in the logframe. Thousands of companies around the world have been positively impacted by the RATE partners, and those partners have built stronger delivery models with better means to assess performance. DFID’s focus on Monitoring, Evaluation and Learning (MEL) and structured reporting has built the competence and capacity of RATE partners. Several of the RATE partners have used the MEL approaches that they have developed with DFID to strengthen the management of other workstreams, even those supported by other donors. Another benefit of the RATE programme has been the outreach and networking opportunities provided. Policy audiences, stakeholders in the finance sector and international networks have all been engaged in a way that would not have happened otherwise.

Some highlights for this year include:
- Approximately 5000 companies around the world have engaged with RATE partner activities.
- 130 investors with $15 trillion Assets Under Management (AUM) are engaging with ShareAction on workforce policies (the target was 125 investors with $14 trillion).
- Research from the British Academy has generated more than 25 outputs, with 7 additional articles and reports, that have fed into parliamentary inquiries in the UK and overseas, has received extensive media coverage overseas and has been widely disseminated.
- 23 locally-headquartered business are part of B Corp Certification community in East Africa, including SolarNow – the largest in terms of revenue and employee size. 737 companies in the region have registered to use their Impact Assessment. Additionally, B-Labs recorded 69 gender-related improvements in the companies they work with.
- Since 2018, a total of 219 products have been published out of the RATE programme, which are being used to generate further understanding on responsible business.

Partner	Performance summary	Grant period
ISEAL	Grant period ended May 2018. All outcome indicators improved, but two of the three outcome targets under-achieved. All output targets were achieved or nearly achieved.	2014-18
Fairtrade Foundation	Grant period ended December 2018. Fairtrade Foundation met or exceeded all Phase II outcome and output targets.	2016-18
GRI	Grant period ended April 2019. Results were close to or exceeded the three outcome milestones.	2015-19
NCP	Grant period ended April 2019. While the output indicators set at the outset were not met, as no cases were concluded for reasons outside NCP’s control, there is evidence of NCP activity being regarded as good practice by external stakeholders.	2014-19
British Academy	Grant period ended June 2019. British Academy met expectations with 25 modern slavery, human trafficking and child labour research publications so far and more to come.	2017-19
B Lab	Performance against outcomes has been positive, with all having exceeded targets.	2016-19
UNGC	Indicators for the number of UNGC participants and those supporting Women’s Empowerment Principles are positive and above target.	2014-20
B Lab SDG	Good progress against majority of outputs.	2018-20
Humanity United	Good progress across the range of output indicators.	2017-19
ETI	Most outputs indicators are either meeting targets or are close to them.	2015-20
Shift	Most output indicators meet or exceed milestones with positive trends seen in external stakeholder reports.	2016-20
ShareAction	Indicators meet or exceed workforce disclosure and investor engagement targets. Behind schedule on final country-level case study.	2016-20
WBA	Logframe output indicators agreed with donors (DFID, NL and Denmark) as M&E framework developed.	2017-20
FSG	Project is on target for most indicators.	2019-20

Following the Mid-Term Evaluation (2018) and MEL workshop, M&E action plans were devised for RATE partners. Most of the partners updated their logframes in discussion with DFID as they gained a deeper understanding of the issues and markets in which they are working. Almost every RATE partner has acknowledged improvements in their M&E capability and capacity following the attention that the RATE programme team attached to this aspect of the relationship.

Regarding DFID’s own M&E systems, there have been changes to the overall strategy and approach. More focus has been to try and capture ‘on the ground data’, which has been relayed to partners with results to be shown in the final year of implementation. In addition, the programme logframe has been updated to take account of lessons learned over the grant period and to ensure that all new RATE partners were incorporated. However, there remain gaps in assessing the causal pathway links between these responsible business initiatives leading to long-term outcome and impact on local communities globally. As highlighted in the Mid-Term Evaluation, responsible business initiatives present an important, but limited set of tools to tackle poverty and address the significant negative impacts of irresponsible business practices. The full impact of the programme shall be seen over time as companies adopt these pilot initiatives in to their longer-term practises to ensure greater transparency and accountability going forward. In final year of implementation, it is important that the RATE programme team prioritise how best to capture results, draw out lessons learned and ensure evidence is generated where gaps remain ahead of any new future programming on responsible business.

Recommendations for the year ahead (1/2 page)

Impact measurement. Within the final year of implementation, the RATE programme team should place more efforts into measuring impact and improving MEL systems. Whilst they have developed MEL action points with partners, more work is required to translate the results from outputs into outcomes and assess impact.

Simplifying and standardising reporting systems. In the last year of the programme the focus for all partners should be on simplifying and aligning the reporting of results and achievements so that the considerable progress that has been made under the RATE programme can be easily communicated to the widest range of stakeholders.

Providing support for partners to attract potential investors and donors. RATE has been involved in providing seed-funding for a number of initiatives that will require additional funding from other sources to be sustainable. Where appropriate, the programme team should support partners in their efforts to identify future funding sources and there should be a clear communication exit strategy in place.

Development of RATE communication products and sharing lessons learned. Due to the complexity of the programme and the volume of partners, in order to reduce risk of fragmentation a clear narrative of results and outcomes should be developed. These products can draw out lessons learned to be shared between external partners and government stakeholders to increase awareness of the impact of RATE.

## B: DETAILED OUTPUT SCORING

Output Title	Increased business outreach and networks
Output number per LF		1	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of business leaders engaged with ISEAL (cumulative)	3,000 (Target)	2,692 (June 2018) / Project closed
1.2 Number of businesses involved with (a) GRI regional hub in Africa; (b) B Lab hub in East Africa.	880 / 600	1,524 (Mar 2019) / 737 (July 2019)
1.3 Number of country-based multi-stakeholder ethical trade platforms focused on increasing the rights of workers in supply chains (ETI)	3	3 platforms established

Provide supporting narrative for the score

Overall, these indicators show that nearly 5,000 companies have been engaged by RATE partners’ activities. There are four indicators in the programme logframe (representing four partners), three of which have been met or exceeded, and one was below target. However, six other partners also contribute to this output. Available data suggests that most of the partner outputs are on track.

GRI has significantly over-achieved on the number of businesses involved with the GRI regional hub in Africa, as it has with stakeholder outreach more generally. Events in the final programme year included:
6 peer-to-peer learning roundtables on sustainability reporting in Ghana, Kenya, South Africa and Nigeria, with 129 participants attending.
A workshop in March 2019 in collaboration with the Nigerian Stock Exchange (see Press release) which brought together C-level executives, Corporate Social Responsibility and Sustainability experts, non-governmental organisations and other stakeholders for an interactive session to share insights on the imperative of good sustainable practices and reporting.

Publications included an article on the GRI website in September 2018, which sought to engage further with businesses in Africa (Harnessing the power of sustainability reporting in Africa: on the road to sustainable development).

B Lab’s current B Corp Certification community in East Africa consists of 23 locally-headquartered businesses, and 9 that are headquartered abroad with presence in the region, less than anticipated but still a good result. The first quarter of 2019 saw the certification of the largest B Corp in the region in terms of both revenue and employee size, SolarNow​. B Corp Kenya was launched, serving as a launch pad to create awareness of the B Corp movement, celebrate the first adopters of the B Corp movement in Kenya, and stimulate conversation about the role of business as it links to sustainability in the market.
ETI: the work of initiating and formalising country platforms has taken longer than initially anticipated, in-part due to extenuated country registration processes. ETI has two active platforms in North and South India respectively, plus a nascent platform in Bangladesh. However, while the formalised structure of the platforms is still a work in progress, ETI’s regional representatives play a continuous, important networking role in bringing together key stakeholders to advocate for positive change and / or act on issues in need of joint solutions. This networking capacity was captured in an assessment carried out by Article 13, who reviewed evidence of outcomes relating to ETI’s programme of work over the past three years. It stated that there is direct evidence of the ETI enabling over 40 members between 2016-2018 to increase their dialogue with local stakeholders relating to improving working conditions and workers’ rights in supply chains.

ETI has also engaged increased business outreach and networks through various events and publications including a High-level Conference on Modern Slavery in Public Procurement on 25th March 2019 in partnership with the governments of the UK, USA, Canada, Australia & New Zealand, and the international organisations OSCE, ILO and OECD. The conference, attended by 170 participants and with 50 speakers, was designed to highlight examples of good practice, generate conversation amongst national and local governments, procurement specialists, supplier companies and civil society actors on how to translate principles into action, identify the policies, systems, skills and resources needed to make progress, and to build networks for greater collaboration.

In addition to these partners, six other partners contribute to this output. Examples of their contribution are given below. The progress of some of these partners is reflected in their own individual programme logframes.

Humanity United: Significantly more businesses are engaging with supply chain issues than anticipated, with 380 potential businesses looking at signing up and formally engaging, as against the initial target of 40. The overall strategy is being revised as a result.

ShareAction: The March 2019 milestone for investor engagement with companies on workforce policies and practices is above target - 130 investors with $15 trillion AUM against the target of 125 investors with $14 trillion AUM. The number of companies that have engaged with the Worker Disclosure Initiative- and thereby creating more publicly available information about their workforce practices- is 200, ahead of the target of 60. ShareAction ran a large Workforce Disclosure Initiative conference in June 2019. In addition to the 90 companies that disclosed, during the reporting period ShareAction established constructive engagement with a further 95 companies.

Shift: In total the project has delivered 19 capacity-building workshops to approx. 228 companies. Shift has been collaborating with CDC to strengthen the practice of human rights due diligence in high-risk investment contexts. The collaboration developed into two in-country capacity-building workshops with private equity fund managers and portfolio companies in several high-risk contexts (Ethiopia, North Africa), to test and apply approaches to incorporating a human rights lens into traditional Environmental Social and Governance (ESG) due diligence, and then leveraging lessons from these experiences into insights and tools for broader global application. This has potential to have a significant knock-on effect in how human rights is integrated into ESG measurement in emerging markets.

WBA: In September 2018, the WBA was launched at the UN General Assembly following extensive consultations in 10 cities over 10 months and an accompanying online consultation process. The WBA spoke at 12 conferences during the review period and convened three large-scale networking events. Ten new allies joined the Alliance between February and May 2019. The momentum and support behind the WBA is important in building the credibility of their initiative and strengthens the ability of WBA’s benchmarks to hold companies to account for their business practices.

UK NCP organised 10 meetings and events, as well as participating in 19 events, in which the NCP promoted the OECD Guidelines for Multinational Enterprises and/or the NCP. Events included speaking at the joint ETI and UN High Commissioner for Human Rights (OHCHR) Roundtable on access to remedy in February 2019. This advocacy is important in building awareness and uptake of the OECD Guidelines.

UNGC have continued to grow their network of business participants committed to business practices that will contribute to the Global Goals. During 2018, 1528 new business participants joined the UNGC, bringing their cumulative net number of businesses to 9998. They also convened a variety of high-profile events such as:
- SDG Business Platform in July 2018 as part of the High-level Political Forum on Sustainable Development at the UN in New York, which had 600 participants from 60 countries and various industries; and
- UNGC Leaders’ Summit in September 2018, which convened nearly 400 business leaders including 120 Chief Executives.

The focus was increasingly on ensuring the effectiveness of country level networks, with an emphasis on the Africa Strategy (draft presented in 2019). The RATE programme is also sponsoring the Decent Work Platform that supports companies in identifying opportunities to strengthen their commitments and actions on decent work. As of September 2019, 26 companies of different sizes and from various sectors and countries were active in the Action Platform, and 15 Global Compact Local Networks have been providing their local insight and support. In the AR period they convened three ‘Global Roundtables’. The third one was organised in March 2019 in London, with 16 companies in attendance.

Summary of responses to issues raised in previous annual review

The need for more effective monitoring and evaluation by most of the partners recommended in last year’s review was recognised and acted on by all partners and the DFID RATE team. Most partners were able to demonstrate improved M&E capacity and competence – several were able to show that these systems were being applied not only to the RATE work that they do, but also to other workstreams. For example, one recommendation in the Mid-Term Evaluation was that more mature RATE partners should commission robust independent organizational impact assessments, and this led to some detailed work at ShareAction. This consisted of detailed assessment from a consultant on the Theory of Change (ToC) in more detail and has then develop an internal set of indicators that ShareAction will continue to use in future across WDI workstreams.

Lessons identified this year, and recommendations for the year ahead linked to this output

Given the scale and reach of RATE partner outreach activities, it is important that the RATE programme team can capture and communicate how increased business networks have positively influenced company behaviour change. As part of this work, the RATE programme team have an opportunity to build a stronger communications strategy into the culmination of the programme. This strategy ought to focus on both sharing key messages as well as contributing to the larger evidence base on responsible business initiatives.

Output Title	Improved standards, guidance, tools, reporting systems and innovations generated and shared
Output number per LF		2	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of (a) updated and (b) new GRI Reporting Guidelines produced and disseminated (c) FSG: Taxonomy Framework, Census Instrument, data Comms and Cocoa Value Chain Report d) Number of methodologies (cumulative) developed. (WBA)	Milestone Dec. 2019: / 6 of existing 46 issue-level reporting guidance updated / 1 / n/a / 3	2 / 0 (but 1 planned by the end of 2019) / Assess at end of grant / 3
2.2 Number of database queries per year requested through the UNGP Reporting Database (SHIFT)	Milestone July 2019: / 1,485	1,670
2.3 B Lab standards for emerging markets reviewed and improved (B Lab)	Milestone July 2019: / 600 East African companies registered and using the (V6) business impact tool to measure impact (v5 and v6 considered together)	737 companies registered for V6 tool
2.4 A) Number of interventions that provide support for traceability, workers' voice, responsible recruitment, data analysis/risk assessment, and other responsible sourcing practices (Humanity United) B) Number of customised data dashboards created, populated and shared for tea, coffee and cocoa and c) increased use of Fairsource dashboards across supply chains (both Fairtrade)	Milestone July 2019 / a) 10 / b) n/a / c) 10	a) 27 / b) n/a / c) 11

Provide supporting narrative for the score
The milestones for these indicators were not all set for the period under review, but significant progress on standards and tools was made. Outputs from several of the RATE partners contribute to this programme output as demonstrated below. Indicators 2.1.c, d and 2.4 were added to the logframe over the period of this review, while 2.3 was successfully met in the previous review.

GRI is working on the continuous revision of the GRI Standards. The move from guidelines to standards over the period of the RATE programme, with an increased emphasis on clarity and simplicity, has changed priorities over time. Revisions to Water and Occupational Health and Safety standards were released in June 2018. New Standards have not been developed under the RATE program, the Standard on Tax and Payments to Government will be the first completely new Standard that will be released since program start. This is expected by the end of this year. A new standard on Tax and Payments to Governments, and revisions to the Human Rights-related Standards, the Universal Standards (Foundation, Disclosures and Management Approach), Waste, and a sector specific Standard for Oil, Gas and Coal are all in progress. These strengthened standards are based on evidence and create stronger tools with which companies can measure and report on their performance.

FSG has identified a pool of over 600 key experts and stakeholders from developed and developing countries across a wide range of diversity criteria, to recruit from for expansion of the Advisory Council and the development of a toolkit. Progress is being made on a technology platform for the data. On target for the completion of the cocoa sector ecosystem analysis. This work is creating buy in from across the public and private sector to identify tangible ways in which business procurement practices can strengthen social outcomes for poor people.

WBA: In November 2018, WBA convened a group of 15 close partners to work on maximising the impacts of efforts to create free, publicly available benchmarks. This meeting helped to begin the formation of a large-scale and inclusive global coalition reflecting the spirit of partnerships that lie at the heart of the SDG framework. Since then they have been working to finalise benchmark methodologies for Corporate Human Rights Benchmark (CHRB); Seafood Stewardship Index (SSI); and Corporate Climate Action Benchmark (CCAB). The technical methodologies for these evidence-based benchmarks are critical for their credibility as tools to change the way businesses operate.

Shift has started to analyse the data it receives from company disclosures into a “maturity” index, which allows not only a quick summary of company disclosure for Shift to discuss with that company, but also for companies to compare relative performance. Overall performance can be driven upwards – while this methodology also allows for self-financing work in longer term. As a result of the large volumes of data being assessed, Shift signed an agreement with Arabesque to create an AI database with their existing mappings. Number of instances reported by influential stakeholders (NGOs, Trade Unions, Academic Institutions) that they are using the Reporting Database to inform their decisions has increased rapidly, running at more than three times the anticipated target. Participant feedback and database enquiries are all much higher than anticipated.

B Lab East Africa Version 6 of the B Lab Impact Assessment was made live for global stakeholders in January 2019 based on around 900 pieces of feedback. More companies in East Africa than expected (737 against a target of 600) have registered to use this Impact Assessment. Targets for producing local case studies and best practice guides for key indicators have been exceeded (110 against the target of 100). A standard working group has been set up to create case studies and guides. The interest and uptake of the BIA in East Africa is compelling and has the potential to create a generation of companies committed to implementing better and more sustainable business practices.

Fairtrade Foundation has embedded its dashboards and platforms created under the RATE programme into its ongoing operations over the final months of the grant support, creating 11 dashboards against a target of 10. They recorded that Fairsource and dashboards are available to over 410 businesses and will continue to be available after the end of the grant. Fairsource dashboards have been used by over 13 businesses to support decision making about their supply chains, demonstrating not only uptake of the resources available but implementation that influenced business behaviour. Fairtrace has been used by over 545 producer groups and over 1,213 traders and businesses.

Humanity United is exceeding its targets in the number of interventions that provide support for traceability, workers' voice, responsible recruitment, data analysis/risk assessment, and other responsible sourcing practices. In addition, significantly more (11,615 as against the project target of 100) primary users (workers) are using Humanity United’s grantee products and services than anticipated.

In addition to these seven partners directly reflected in the programme logframe, other RATE partners contribute to this output. Examples of their contributions are given below:

B Lab also kicked off the SDG impact management platform project in February 2019 – in close collaboration with UNGC – aiming to allow companies around the globe to manage their impact by measuring performance against the SDGs. Progress to date has been on target – or better for some targets. While B Lab originally envisioned rolling out these metric sets in several tranches, the first versions of all 17 SDG metric sets were developed ahead of schedule. ​

ETI has met or exceeded its targets for the use and training on human rights due diligence and supporting local ethical trade platforms. Reporting frameworks to support human rights guidelines are now in place following beta testing and member feedback. The transparency road map has been published. A series of high-profile meetings with key stakeholders have been held to influence policies at national, EU or international level to the end of 2018 – for instance on the garment-specific aspects of the Rohingya issue.

ETI also published:
- A comprehensive research report titled Business Models and Labour Standards: Making the Connection together with a team of researchers from Kings College London and University of Warwick. The report aims to illustrate how flaws in prevailing business models create systemic downward pressures on workers’ rights and in turn identify opportunities for Business Model Innovations to improve the situation.
- A guidance on Responding to the Human Rights Crisis in Myanmar in January 2019. The guidance is aimed at helping businesses act responsibly in relation to the human rights crisis in Myanmar by providing decent work.

ShareAction: Some companies have provided specific evidence that the WDI is prompting changes in their approach to workforce data collection and/or disclosure. For example, the WDI was referenced by Landsec in a May 2018 Chartered Institute of Building (CIOB) report on tackling modern slavery (pages 75-76). The WDI is changing the capacity and approach in the companies it engages with, for example, SSE cited the WDI in its 2018 Sustainability Report (page 39).

UNGC: Under this output the Decent Work Platform has:
- Developed a Baseline Report with good practice examples and trends based on bilateral interviews with Action Platform participants. This was publicly launched at the Private Sector Forum during UN General Assembly week in September 2018.
- Gathered signatures from Chief Procurement Officers in support of the 6-tiered Commitment Framework.
- Consultations to develop an Engagement Toolkit on Decent Work to support sustainability and procurement professionals to translate human rights and decent work considerations into daily procurement decision making, including training material. Consultation workshops were held in March 2019 in London and Rome, in April 2019 in Texas, and in June 2019 in China.
- Development and launch of modernslaverymap.org in May 2018.

Summary of responses to issues raised in previous annual review

The partners have generally met or exceeded expectations indicating that the standards, guidance, tools, reporting systems and innovations are being effectively generated and shared. More effective monitoring and evaluation has been built into all the partners, with many using the skills that they have built on other non-RATE funded workstreams.

Lessons identified this year, and recommendations for the year ahead linked to this output

A theme coming from the partners’ work over the period of the review is that improving the quality of the data in the tools and guidelines is the priority rather than coming up with new ones. The RATE team should continue to focus on consolidation of existing tools and approaches, until the end of the programme.

Output Title	Impact evidence generated and shared
Output number per LF		3	Output Score	A+
Impact weighting (%):		15%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of new reports addressing sustainability impacts and performance of standards listed on ISEAL website (cumulative)	Milestone date: July 2018 / 135	190 / (NB ISEAL partnership came to an end in May 2018)
3.2 Number of academic and other outputs ready for publication addressing modern slavery, human trafficking and child labour issues (British Academy)	17	25 to date
3.3 Case studies published of company and investor awareness of working practices in target countries (ShareAction)	Milestone date: March 2019: / 5	4 (1 to be published in Q3 2019)

Provide supporting narrative for the score

On balance the programme has met expectations with 219 publications. Two of the milestones have been significantly exceeded; and one has not been fully achieved (but is on track to meet the target later in 2019).

ISEAL has identified 190 new reports that addressed sustainability impacts by the time the partnership finished against a target of 135, but no new activity was carried out over the period of the review as the partnership ended in May 2018. Since the end of this grant ISEAL have founded Evidensia in 2019 with Rainforest Alliance and WWF with support of the Global Environment Facility. Evidensia helps users access and interpret credible research on sustainability impacts and effectiveness of supply chain initiatives and tools. It provides a portal to information and evidence and supports shared learning through its insights and analysis.

British Academy has successfully ran the Tackling Slavery, Human Trafficking and Child Labour in Modern Business research programme. Eight research projects were funded through a competitive call. The British Academy has seen award holders produce approximately 25 academic and other outputs for publication based on the research conducted under the programme. A special supplement to the Journal of the British Academy was produced entitled Tackling Modern Slavery: Problems and Possibilities as well as a report synthesising the programme’s main findings and recommendations. The RATE programme enabled a wider range of stakeholder engagement than academics are normally able to access, and the researchers were able to talk about their work to UK and international policy audiences.

ShareAction commissioned Oxfam to produce 5 case studies (with 4 published on the WDI website) between November 2017 (Myanmar) and 2019 (Morocco), which were distributed to investor signatories of the WDI. These products have been distributed at events Oxfam has attended and at investor workshops. Links to all four case studies were shared in a March 2019 blog: 'Investors driving better quality jobs'. To accompany the case studies, 3 films have been created:
- WDI Myanmar: https://www.youtube.com/watch?v=frpMjrp4_2M&feature=youtu.be
- WDI Morocco film: https://shareaction.org/wdi/investor-resources/
- WDI India film: https://youtu.be/XodclkAC87Q

Two other partners have outputs that contribute to improved impact evidence through research and outreach:

B Lab East Africa has worked with 4 academic institutions to research, convene or teach on the topics covered by B Corporation or the B impact assessment platform, compared to a milestone of 2 for July 2018. For example, two B Corps in East Africa (Daproim Africa and Sustainable Business Consulting) took part in research work being done by Academia B on “The impact of B-Corps on Women and Youth Inclusion”.

GRI shared communications on peer-to-peer learning roundtables run by GRI Africa and the following newsletters and social media posts.

Summary of responses to issues raised in previous annual review

The RATE partners have produced a large portfolio of evidence, even though they are all very different organisations with very different target audiences and stakeholders. It is clearly challenging to create simply numeric targets, particularly when the aim is to change behaviour.

Lessons identified this year, and recommendations for the year ahead linked to this output

The RATE programme has invested significantly in the development of research, evidence and learning. Ensuring that this material is shared across the RATE partners and with the wider business and policy community is essential if the findings are to result in meaningful change to business practices that will have direct impacts on improving the lives of poor people.

Output Title	Government-led interventions demonstrate that they extend responsible business practices
Output number per LF		4	Output Score	B
Impact weighting (%):		5%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
4.1 Proportion of complaints concluding in agreement between parties or recommendation by the UK NCP	80%	No complaints were concluded for reasons outside NCP’s control
4.2 Peer assessment of performance of UK NCP compared with other NCPs	UK NCP maintains its leading position amongst all NCPs	Insufficient evidence until peer review published in September 2019

Provide supporting narrative for the score

The proportion of complaints concluding in agreement between parties or recommendations by the UK NCP has not been met, namely because the UK NCP is not wholly in control of the timeline for concluding cases. In the review period the UK NCP has not concluded any cases. Of the two cases that were in scope, one case concluded in April 2019. However, one of the parties to the case requested a procedural review and the publication of the complaint has been paused while this takes place. The Final Statement for the other case in scope is being drafted.

In the review period the UK NCP published three Initial Assessments, accepting all three cases for further examination. One further complaint which was received in March 2019 is awaiting an Initial Assessment. The UK NCP has also supported 5 other NCPs on cases which they are leading the handling of which relate to a UK company’s behaviour.

The OECD Peer Review was conducted in late 2018 and the site visit in November 2018 (including 19 organisations providing feedback and 30 organisations participating in the on-site visit). The final report has not yet been published. However, in the absence of published peer review report there is other evidence that suggests that the UK NCP is maintaining its leading position amongst all NCPs globally.
[note] In a progress report to the OECD Ministerial Council Meeting in May 2019, the OECD noted that UK NCP was one of only “six NCPs that have received nearly half (49%) of all cases filed since 2000” and “one of only seven NCPs that accounted for almost 50% of all organised/co-organised promotional activities” The UK NCP’s engagement with the finance sector in 2018 was used as a highlight in the OECD’s Annual Report for NCPs “The NCP of the United Kingdom (UK NCP) partnered with UK Finance, an industry association representing 300 firms in the UK providing credit, banking, markets and payment-related services, to organise an awareness raising event on the OECD work on responsible business conduct and due diligence in the financial sector. The UK NCP also facilitated coordination with UK Finance to host an expert working session with practitioners to feed into the OECD’s ongoing work on defining due diligence approaches for general corporate lending and underwriting securities transactions.” In an OECD report on NCPs issuing determinations and recommendations published in 2019 the OECD noted that the UK NCP is 1 of 4 NCPs to issue 3 or more determinations. OECD Watch – an NGO which represents civil society noted good practice of the UK NCP in making determinations in its cases.

Summary of responses to issues raised in previous annual review

The recommendations from the previous annual review were superseded by the peer review not yet having been published. Suggested improvements to the logframe were also challenging to implement, as the indicators were still out of the direct control of the NCP.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The main causal steps in the Theory of Change (TOC) are that RATE funding strengthens and scales up the responsible business initiatives (RBIs), which deploy a variety of influencing strategies to build corporate capacity. This leads to changes in corporate behaviours, particularly those that have positive impacts on poor workers, communities and the environment in developing and middle-income countries.

RATE funding strengthens and scales RBIs, including new and existing initiatives. These initiatives deploy a variety of influencing strategies to change corporate capacity (attitudes, knowledge, skills, plus opportunity/motivation) towards greater responsibility. In turn, this leads to changes in corporate commitments, policies, and practices, including those that have significant impacts upon poor workers (female, male), communities and the environment in emerging economies and developing countries. Pioneer or leading companies would act first, followed by a process of mainstreaming as competitor companies crowd in and public agencies respond (e.g. by changing procurement policies, by reforming policies) so that sector or industry becomes more sustainable. Multiple contextual factors shape will determine change in any specific context. RATE partners may also potentially influence that context by changing societal expectations or government policy.

Fig. 1 Programme Theory of Change

The operational components of RATE have all delivered their outputs effectively – some are still implementing their RATE grants and so it will only be possible to fully evaluate their individual effectiveness and contribution to the RATE programme at the final evaluation. The Mid-Term Evaluation found that the available evidence on business behaviour change (the longer-term outcome in the ToC) resulting from responsible business initiatives has been limited. The RATE programme team has been working with partners to ensure that such evidence (on the i.e. the impact initiatives) is generated in the final year of implementation.

Over the past year there has not been any major changes to the ToC, but rather increased efforts to enhance the MEL framework of partners discussed below.

Some partners did report that the emphasis on Theory of Change in the Mid-Term Evaluation and last year’s Annual Review did have positive outcomes. ShareAction for example commissioned a consultant to review their ToC and the indicators that arose from that review. This new way of working was successfully implemented and positively impacted not only on their RATE funded work, but also on other workstreams.

Current Programme Logframe
Outcome indicators	Milestone	Latest data
1. Number of chains of custody certificates issued by ISEAL members (a) globally, and (b) in Brazil, India and China.	June 2018 / 65,000; / 13,500	July 2018 data (end of grant) / 53,244 / 9,240
2. Number of annual sustainability reports registered globally (in the GRI Sustainability Disclosure Database and GRI internal back-end)	Dec 2018 / 6,740	June 2019 / 6,306
3. Number of UNGC signatories supporting the Women's Empowerment Principles CEO statement (UNGC)	July 2019 / 1,250	July 2019 data / 2,200
4. Level of progress in company's ethical trade performance reported by ETI corporate members (ETI)	December 2018 / Leader = 11 / Achiever = 16 / Improver = 34 / Foundation = 11	Dec 2018 data / Leader = 4 / Achiever = 14 / Improver = 36 / Foundation = 8
5. Percentage of reporting companies whose disclosure maturity reporting improves by more than one level (SHIFT)	2019 / 15%	Jan 2019 / 25%
[note] Expectations across Principles of Implementation (Commitment, Identifying Issues, Prevent, Mitigate, Remedy and Track and Communicate) have on average been raised in the new reporting framework with more precise requirements and with a far more stringent scoring criterion applied – i.e. different expectations are set for the number of criteria included in each of the four different achievement levels (Leader, Achiever, Improver and Foundation). Moreover, some POIs have changed. For example, the previous reporting system did not include a reporting point for FOA as a salient issue. It is therefore difficult to make a comparison on worker representation between reports using the former and new system.

Progress against the outcome indicators in the logical framework have been positive for two of the five indicators, while the ISEAL grant has ended and ETI changed the criteria for measurement. To note for indicator 2, the global number of sustainability reports registered has increased in reporting years 2015 through 2017. The final global milestone is below target, but GRI expects to measure an increase in reporting compared to the previous year retroactively. Active collection of reports has been slowed down because of the report registration requirement for GRI standards reports. There are signs of early and even medium-term outcomes either having been achieved or on track in the final year of implementation. Nonetheless, more work is required by the RATE programme team to capture progress and provide links between outputs and outcomes.

Likely impact achievement is rated as uncertain due to the limited evidence currently available. It would be unrealistic to expect impact at this stage in the programme, and arguably unrealistic to expect such impact to be easily identified and attributable even in the longer-term. While there are some improving trends in the impact indicators tracked in the logical framework (e.g. child labour), the scale of negative business-related impact remains substantial. Available data suggests that, globally, there has been no reduction in forced labour, and that labour rights have deteriorated. That said, certain contextual trends are positive (e.g. attitudes amongst some corporate leaders and consumers, and regulation), and there is a definite increase in the attention given by some businesses to social and environmental issues. However, the balance of the available evidence relevant to the ToC suggests that achieving positive impacts for poor women and men is likely to remain challenging. Likely impacts by gender and social group are uncertain.
[note] Global Estimates of Forced Labour (ILO, 2013) and Global Estimates of Modern Slavery (ILO, 2017); Global Rights Index annual reports (ITUC, 2014-2018)

Gender
The expected outcomes of the RATE programme on gender equality are different for each partner, some having more of a focus on gender issues than others. For example, B Lab and ETI have specific outputs related to gender equity within their individual RATE logframes whereas other partners, such as UNGC, have mainstreamed gender-related issues throughout their interventions. Examples of achievements towards improving gender equality within the workplace through the RATE programme are given below:

- B Lab has recorded 69 gender-related improvements to those businesses it works with in East Africa. These improvements include increase in female employees, increase in female managers and working with female entrepreneurs.
- ETI developed a new ETI Gender Strategy that outlines their approach to gender equality as an enabler of workers’ rights. They provided advisory support to 36 corporate members to underhand their ongoing gender work. They convened 4 Gender learning events for 28 participating member companies. They also established key partnerships with industry stakeholders to further the impact of their work on gender in supply chains.
- UNGC launched the Women’s Empowerment Principles Global Trends Report 2018 which examines the aggregate results of companies using the Women's Empowerment Principles Gender Gap Analysis Tool (WEPs Tool) with an aim to provide insights on corporate performance on gender equality and women's empowerment, demonstrate the value of using the tool, and showcase the efforts of partners and other stakeholders to drive gender equality around the world.
- ShareAction were able to demonstrate through a case study how Oxfam have supported women working as strawberry pickers in Morocco for the European market to both raise awareness of their rights and, through work with ETI, to persuade European retailers and importers to collaborate to apply gentle pressure to producers to improve working conditions.

Explain major changes to the logframe in the past year (1/2 page)

Changes to the logframe this year included some detailed improvements to the output indicators as progress became clearer and some partners changed their own systems. All partners are now covered by outcome or output indicators.

Describe any planned changes to the logframe as a result of this review (1/2 page)

The RATE programme team will focus ensuring the logframe is updated as final partner reports are submitted. The team will also focus on critically assessing the impact of RATE partner initiatives beyond just the logframe’s key indicators to ensure a holistic story on progress and impact is captured.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

The RATE programme has been implemented by all partners within the parameters of the 4Es to show efficient use of DFID resources and the best possible VfM.

Economy

Overall all partners have implemented mechanisms for reducing travel costs through planning field trips to coincide with other trips which are already paid for from outside sources. Partners have ensured they follow key procurement principles of ensuring three quotations are sourced and the supplier who demonstrated the best VfM (in terms of less cost and highest quality) was selected. Negotiating down fee rates and using consultants who were cheaper and located geographically closer to the intervention also ensured cost-savings. Other specific examples are as follows:

- FSG identified qualified contractors based outside the US whose rates were significantly lower than the initial budget model (which was based on US rates) which provided significant cost savings and allowed them to retain more of the contractors’ time and attention, which in turn enhanced quality and delivery. In addition, FSG identified non-profit technology providers whose costs were a fraction of that which for-profit providers charge, with strong mission alignment and without compromising quality.
- ISEAL has been working on reducing long-distance travel for meetings at the London Head Quarters. To achieve this, ISEAL used a range of in-house communication tools, and meeting attendance was done virtually. In addition, when travelling is necessary, efforts are made to cluster various internal and external in-person meetings within Europe.
- The WBA operational team which delivered the global stakeholder consultations in Phase II, were either pro bono or were a not-for-profit, thus cheaper than for profit consultants. Everyone involved was experienced in complex project delivery, corporate benchmarking and understanding of the wider contextual environment so were able to ensure they successfully delivered all aspects of the programme ensuring cost-efficiencies as well as better economy for the programme.

Efficiency

The RATE programme has shown efficiencies in its ability to leverage co-financing opportunities which contribute to the achievement of their RATE projects. In some instances, these additional resources are in the form of monetary co-funding agreements, in other instances they are human resources in the form of time spent on the programme which is not funded under DFID RATE. Where possible all partners ensure greater economies of scale to increase the efficiency in programme implementation.

- Fairtrade Foundation decided to move away from fully DFID-funded research-gathering trips to instead coordinating with other projects which also included research-gathering trips - leading to more research carried out over a wider range of producers - across more countries and commodities. This efficiency, together with other internal efficiencies of staff time resulted in DFID funding 372 days’ work and Fairtrade Foundation and Flocert contributing a further 2,679 days’ work to the programme from other co-funded opportunities.
- WBA ensured efficiency by building a coalition of impactful benchmarks and creating economies of scale across those benchmarks. In addition, WBA used an experienced delivery team and leadership from each of the different partners to ensure the most efficient programming possible in their implementation through tight work planning and creative resource management.

Effectiveness and Cost-Effectiveness

The RATE programme is having a significant impact on thousands of companies who have built stronger, more transparent and accountable delivery models with better means to assess performance. Aside from the logframe targets, there have been additional gains which have resulted from this programme such as ensuring a more just, equitable workplace for thousands of workers globally and improved business practises, both of which demonstrate the effectiveness of the programme.

- British Academy’s effective use of their Fellowship and reputation for excellence created an internationally-recognised and respected brand which enabled them to gain a higher profile for their new research programme, as demonstrated by the number of bids received, which was significantly higher than in the past when they were reliant on the Academy to fund this initiative.
- FSG worked with CARE Consulting to leverage an existing, separate trip to Cote d’Ivoire to conduct interviews and gain insights into the Cote d’Ivoire cocoa context. This ensured both cost saving and a more effective product which was informed by the beneficiaries of the intervention.
- ISEAL were able to leverage partners to co-fund activities which ensured the maximum effect at a reduced cost with respect to the delivery of the project’s outreach efforts through collaborations with various influencers, networks and platforms. With several of these, such as WWF, Business Fights Poverty, UNFSS and Sustainable Food Lab, ISEAL were able to co-develop effective products whilst ensuring direct cost savings in the process thus implementing a more cost-effective approach.

Equity

The RATE programme has ensured each partner considers the ‘leave no-one behind’ agenda through each partner integrating a focus on reducing gender inequalities and ensuring the inclusion of vulnerable and marginalised groups such as persons with disability.

- British Academy ensured equity in the research awards which were given whereby 50% of the award-holders were women, and the programme was designed and delivered to include active participation from researchers and institutions across the Global South.
- B Lab, through their work on reducing gender imbalances within the workplace and their work on inclusion of other key marginalised groups has demonstrated their commitment to improving equity through encouraging companies to change their policies and employ more marginalised peoples such as women and persons with disability.
- Through ETI’s Base Code Guidance on Gender, they were able to promote equity within the workplace through developing a business case to demonstrate the cost-benefits to inclusivity of women using the language through which most investors and business owners can relate.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

This programme is in its final stages and there are no reasons with respect to VfM why the programme should not continue until its natural completion date. As this is the final year of the programme, the RATE partners have demonstrated an increased emphasis on sustainability through sharing lessons and publishing papers which can increase the uptake of the initiatives and innovations implemented throughout the programme. Partners have also sought follow-on funding for key activities to ensure that the RATE programme continues even after DFID funding has finished thus further increasing the VfM of the RATE interventions.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The Risk Register for RATE identifies risks at portfolio level, with DFID responsible for monitoring and mitigating actions; and risks identified for each implementing partner, where responsibility for risk management lies mainly with the implementing partner. The Risk Register is based on risks identified in the Business Case, implementing partner proposals and due diligence assessments, as well as ongoing discussions with partners. It is reviewed and updated on a regular basis by the RATE programme manager. Since the 2018 Annual Review, new tabs have been added to the RATE risk register to reflect the partner-owned risks of new grantees but also extensions.

Portfolio Level

The main two risks relate to the delivery of the programme, namely that because the ToC is based on limited evidence, there is the risk that results will be mixed and it will be unclear what policy recommendations can be derived. This adds to the complexity of drawing out the results on the long-term impact. To mitigate this, in this last AR period the RATE programme team has built on last year’s recommendations of building the MEL capacity of implementing partners. Several of the grantees are now using methodologies developed in response to DFID’s attention, across their organisation. The RATE programme team has also worked with partners to capture impact through developing partnerships with 60 Decibels. In the final year of programme, the RATE programme team will organise a learning-workshop to draw out key lessons learned and map out further evidence gaps.

Another risk relates to the number of implementing partners and instruments used, ranging from grants, Memoranda of Understanding and commercial contracts. This makes RATE a complex programme to manage, requiring high level of human resource. To mitigate the risk of fragmentation, the RATE programme team have maintained a close working relationship with all partners and focused on MEL to ensure progress can be sufficiently monitored. It is noted that there have been some staffing changes (SRO and Programme Manager), which have led to a three-month staffing gap, which decreased the ability to speak to partners on a regular basis. Throughout this period, the Responsible and Inclusive Business Team split time between staff to ensure the programme was appropriately managed until all posts were filled. Clear communication was sent out to all partners about these changes during this period. The RATE programme team have resumed quarterly calls with each partner, update core documents (task matrix, delivery plan) and review quarterly financial and narrative reports as a means of monitoring partner progress. In this final year of implementation, the programme team will also seek to develop information products to better communicate the linkages between partners to internal and external parties.

Safeguarding and associated risks remain a top priority for DFID Ministers and the organisation. RATE is a low-risk programme in terms of safeguarding, given that most of the grantees are not working directly with beneficiaries. In line with the new Safeguarding requirements Enhanced Safeguarding Due Diligence assessments have been undertaken on all current grantees.

Project Level

Sustainability of activities funded through the RATE grants will come into increased focus for partners as many of them near the end of their funding period. Partners are considering how to integrate programme funded activities into the core delivery of their organisations or stopping them.

Risks, and mitigating actions, have been identified as part of the design and negotiation of each implementation agreement. The DFID team holds routine update meetings with the main implementing partners (monthly during at least the first six months of each contract), in which progress in risk management is discussed. In addition, audited financial accounts are submitted to DFID on an annual basis to ensure the risk of any misappropriation of funds is identified, mitigated and monitored.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Key developments in the financial and commercial space in year 5 include;

- End to grants with the Fairtrade Foundation in December 2018, GRI in April 2019 and the UK NCP in April 2019.
- Signed three new grants with FSG, B Lab SDG Platform and one with the WBA. Also putting into place several small cost and time extensions to grantees including the ETI, Shift, ShareAction and Humanity United.
- Closure to contract with the programme evaluator, Natural Resources Institute without fault, due to changes in MEL approach indicated below.
- In the 19/20 Financial Year, RATE had an approved budget of £9.73 million. The final programme spend for the year was £9.74 million, meaning a 99.97% forecasting accuracy on the overall budget.
- In this AR period, the programme team have tried to ensure the £5 million uncommitted funds from the previous year was fully allocated. At present the programme has approximately £700k uncommitted funds.

Performance of partnership (s)

The RATE programme supports a diverse range of partnerships (13 to date, 12 of which are assessed as part of this review). The RATE programme team have invested significant amounts of time building and maintain effective relationships across the portfolio, including intensively supporting the on-boarding of new programme partners, including those who are new to receiving government funding.

Key new partnerships to highlight since the 2018 Annual Review is with the FSG, which has the following outcomes:
- Increase the visibility and understanding of ‘for-benefit’s among policymakers and other key stakeholders in commercial value chains;
  [note] For-benefit businesses represent a fourth sector of the economy, which has been growing at the intersection of the three traditional sectors (public, private, and social). Two defining characteristics distinguish for-benefits from other organizational models: a primary commitment to social purpose, together with a predominantly earned-income business model. In addition to these, most for-benefits also have one or more secondary characteristics.
- Increase the demand in commercial value chains for ‘for-benefits’, with a focus of cocoa industry in West Africa;
- Mobilise stakeholders on market-building efforts directed at scaling ‘for-benefit’ enterprises in developing countries.

The FSG outcomes provide a roadmap for the cocoa industry to leverage buying power to create demand for for-benefits in their value chain. By instituting a for-benefit procurement preference, companies will incentivise for benefit suppliers, whose aim is to deliver equitable benefits to all stakeholders in a sustainable way. In the case of West Africa, it will keep more money at the farm gate, alleviate poverty and human rights abuses, and ensure sustainable farming practices that will halt deforestation before it is too late.

There are many instances where partners have worked with each other to increase harmonisation and collaboration. For example, Shift has worked with the ETI to align key elements of their members’ reporting framework with the UNGP Reporting Framework. Specifically, ETI members must now report to the ETI on their salient human rights, and the management thereof. Shift has engaged with the ShareAction team responsible for the development of the initial WDI survey to reflect the alignment with the UNGP Reporting Framework.

Partners are also engaged other initiatives across the rest of PSD and cross-government portfolio. For example:
- Shift continues to collaborate with CDC on the application of human rights due diligence in high-risk contexts, with a focus on the development of an investor briefing note for North Africa.
- ETI formally launched its Modern Slavery Statement Evaluation Framework in December 2018. During this reporting period, the Home Office Modern Slavery Unit has endorsed and promoted the Framework in its newsletter reaching approximately 2,500 UK businesses.
- Since April 2019, PSD mobilisation and climate team signed a grant to support the work of the UNGC Sustainable Finance Platform – workstream 2 in identifying mechanisms in financial intermediation, foreign direction investment and blended finance to mobilise capital towards the SDGs. Key deliverables of this grant include: new publications on the potential for corporates to finance SDG enabling investment in emerging and frontier markets; facilitation of case studies and pilot transactions; and creation of tolls and guidance for companies to transition their business and financing models to support SDG-aligned activities. In this AR period, they’ve conducted a Roundtable and written a first draft of their Scaling SDG Finance Report.

In addition to formal reporting, regular meetings are held between the programme manager and partners to discuss progress and raise challenges. The programme team regularly commission asset inventories and updates to delivery chain maps. The programme manager, SRO and Responsible and Inclusive Business Team also engage with partners through formal governance structures, for example observing the ETI board, participating in the UNGC Government Group meetings, participating in the NCP Steering Committee and attending World Benchmarking Alliance Donor meetings. In the last year of programming, it is important that DFID continue to provide additional support to grantees that do not have a history of working with DFID to ensure they are sustainable once the programme closes.

Audited Financial Statements 2018/19

Partner	Statement period	Publication date	Date of last narrative financial report	Status	Notes
World Benchmarking Alliance	Jan - Dec 2018	19/03/2019	11/07/2019	Unqualified	Significant increase in costs since 2017, justifications are provided on page 9.
B-Lab	Dec 31, 2018 and 2017	22/05/2019	12/07/2019	Unqualified	Nothing to note and no abnormal spends.
British Academy	April 2018 – March 2019	18/06/2019		Unqualified	Increase trend in expansion in line with strategy explained on page 19.
ETI	Apr 2017 – Mar 2018	18/08/2018	22/07/2019	Unqualified	Nothing to note
ShareAction	Feb 2017 – Jan 2018	31/01/2018	22/07/2019	Unqualified	Nothing to note
Humanity United	Dec 2017 – Dec 2018	26/06/2019	23/08/2019	Unqualified	Nothing to note
UN Foundation	Jan-Dec 2018	29/05/2019	23/09/2019 (FSG)	Unqualified	Nothing to note
Shift	June 2017- June 2018	30/10/2018	01/08/2019	Unqualified	Nothing to note
NRI / ISEAL / UKNCP / GRI / Fairtrade Foundation	N/A

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

The DFID RATE team have monitored the progress of partnerships through 6-weekly calls, regular updates via email, attending board and governance meetings of partners, reviewing quarterly/six-monthly progress and financial reports and commissioning updates to core documents such as log frames and risk registers.

Following the mid-term evaluation conducted by the Natural Resources Institute (NRI) in the last AR period, the RATE programme team have worked closely with partners to develop action plans to improve their logframes, Theories of Change and MEL practices. These action plans were the outcome of a 2-day learning event, which was held in October 2018 and facilitated by the NRI. At this event, partners captured and shared lessons on measuring impact and improving MEL systems. The workshop illustrated best practice approaches to MEL, taking partners on a progressive exploration of ToC, quantitative evidence and case studies, and the evaluation of capacity and behaviour change and impacts on poor people (workers and communities) and the environment. A key message from the event was that all RATE partners must evaluate their actual impact on poverty in line with DFID’s mandate.

Following the outcomes of the learning event, the RATE programme team reviewed their approach on programme evaluation and a strategic decision was made to collect more ‘on-the-ground’ data on the outcomes and impacts of the RATE programme. It was also decided that a final evaluation of the programme would not take place. The contract with NRI thus closed without fault in March 2019.

In February 2019, the RATE programme team conducted a meta-analysis to summarise the body of evidence around RATE’s achievements at outcome and impact level. This work helped the RATE programme team identify where there was a strong evidence of achievement and in which areas still have evidence gaps in the development logic as per programme’s Theory of Change.

In order to address the gap on measuring impact, four partners (ETI, Humanity United, ShareAction, B Lab East Africa) are working to generate case studies that capture where companies have been directly influenced to change their behaviour. Results from the case studies will be released in by November 2019. A provisional list of expected activities provided below.

B Lab will identify Business Impact Assessment (BIA) users where changes implemented following a BIA are likely to have been most significant to the lives of customers/employees/supply chain workers.

ETI will identify mills/factories/farms where they a) implement direct programmes and b) have company member’s supply chain likely to have benefited from actions resulting from ETI membership. This analysis will provide an assessment of ETI’s indirect attribution, which is an under-explored area that ETI is keen to try and understand.

ShareAction will conduct a study to better understand the perceived value of the WDI by its users, with the aim of this feeding into the effectiveness of ShareAction’s engagement and reach.

Humanity United will collect data from their workers or suppliers to better understand the effect of increased access to resources and services on worker quality life and productivity.

Shift have contracted an external evaluator to develop case studies that supplement evidence in support of the project outcomes.
In early 2020, the RATE programme team will organise a learning workshop to identify the key lessons learned from the RATE programme, identify gaps and provide recommendations to DFID Private Sector Department and implementing partners on future programming in responsible business. This workshop will include findings from the 60 Decibels surveys and studies.

Progress on recommendations from previous reviews (1/2 page)

Recommendation from Previous Annual Review	Progress and Actions Taken
RATE programme manager to update the programme level logframe with proposed changes based upon evolution of BEH strategy, programme funding decisions and the logframe review by the M&E team. The update to the log frame will include exploring how all 12 partners can be better measured under the outcome and output indicators, including the newer grants with Humanity United, World Benchmarking Alliance and British Academy.	The RATE programme team have worked to ensure all partners are measured under output indicators, including new grants with Humanity United, FSG, WBA and the British Academy.
DFID to ensure that partners take steps to improve their own M&E systems, and to support the M&E team in engaging with partners to develop partner action plans for generating evidence for the final evaluation themselves and collaborating with the NRI team in conducting additional M&E activities, including facilitating access to immediate beneficiaries (i.e. participating companies). All ongoing grants (except for British Academy) should have current logframes.	All partners put effort into improving their own M&E systems, some with such impact that they have adopted the methodologies across other non-DFID funded workstreams. Very detailed information behind each logframe and narrative report was provided by all partners. / DFID has revised M&E strategy and will work to capture results and lessons learned going forward.
The extent to which outreach and networking activities lead to changes in business policies and practices needs more effective monitoring and evaluation by most of the partners (and in turn this requires cooperation from participating companies).	Detailed narrative comments were provided by partners, but all have very different business models and targets so monitoring and evaluation is all undertaken by partners very differently. Comparison across the RATE programme is complex.
Now that it is fully staffed, the UK NCP needs to develop the evaluation metrics for both its promotional and complaint handling activities.	A Peer Review of the UKNCP has been carried out – to be published shortly – and this will assess their performance in relation to other NCPs. The NCP is no longer supported by the RATE programme.