## revised LF Sept 20 v2
Proposed revised and updated logframe | Centre of Excellence for Development Impact and Learning
Revised , Sept 20, revised version v2 | Previous | New | Rationale and notes | Comments/issues | Number
IMPACT | Impact Indicator 1 | Impact Indicator 1 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 | Rationale for 19/20 figure | 2019/20 | 2020/21 | 2021/22 | Target (cumulative - 2023) (1) | Notes
Strengthened evidence base and increased understanding and application of what works in international development built around more and better impact evaluations | Improved bodies of evaluation evidence in areas identified by CEDIL as evidence and synthesis gaps and addressed through the programmes of work |  |  | Proposed that we review this indicator after the 2019/20 annual review as it not easily quantifiied. | Planned |  | 0 | 0 | Too soon to assess systematically. Indicator also needs revision. | 0 | TBD | TBD | TBD
Achieved
Source
| Impact Indicator 2 | Impact Indicator 2 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (cumulative - 2023)
| Stories of Change' which provide plausible accounts of improvements to development interventions or policies arising from CEDIL's work |  |  |  | Planned | 0 | 0 | 0 |  | 0 | 2 | 4 | 10
|  |  |  | Numbers suggested but no clear basis for estimating them | Achieved
Source
CEDIL directorate, collection begins 2020/21
OUTCOME 1 | Outcome Indicator 1.1 | Outcome Indicator 1.1 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (2023) | Notes | Assumptions
Increased access, awareness and uptake of high quality evidence from impact evaluations and syntheses in key policy and programme areas | Number of evaluation findings and recommendations accepted by organisations conducting the interventions evaluated | [Placeholder indicator] Percentage of evaluation findings and recommendations accepted by organisations conducting or financing the interventions evaluated | Ongoing discussion within the team around this indicator |  | Planned | 0 | 0 | 0 |  | 0 | 0 | 0 | 70% |  | Political will and commitment to adopt and implement policy and practice. Favourable internal and external environment.
|  |  | Absolute numbers difficult to predict. But also difficult to be sure we can track % accurately, or to set a benchmark |  | Achieved
|  |  | Useful to discuss whether it should be replaced |  |  | Source
[6 empty] | Stakeholder responses to evaluation reports |  |  | Measured at end of project, given time required to develop, for programmes to respond and for CEDIL to follow up
| Outcome Indicator 1.2 | Outcome Indicator 1.2 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (2023)
| Number of DFID and other stakeholders who report in surveys that CEDIL outputs are useful or likely to be used | Percentage of stakeholders who report in surveys that CEDIL evidence outputs are useful or very useful | Focus explicitly on evidence (not methods) for this indicator |  | Planned | 0 | 0 | 0 |  | Too early to measure | TBD | TBD | TBD
|  |  | Absolute numbers very uncertain, depending on stakeholders surveyed and response rates | Use 19/20 user survey to set a benchmark | Achieved
|  |  | Need to agree on channel and process to reach stakeholders to minimise bias | Dissagregate DFID vs other in progress report |  | Source
End of year user survey, baseline measurement at end of 2019/20 to set future benchmarks.
| Outcome Indicator 1.3 | Outcome Indicator 1.3 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (cumulative - 2023) | Notes
| Number of downloads of working papers and evidence syntheses | Number of downloads of working papers, evidence syntheses and maps from CEDIL website |  |  | Planned | 0 | 0 | TBD | 100 downloads per paper per year (from current CEDIL data) | 500 | 700 | 1700 | 4200
|  |  | Difficult to compile from all sites. Use this as a proxy. | This includes inception phase and POW papers that are posted on the CEDIL website. It excludes methods guidance, captured under outcome indicator 2.4 | Achieved
Source
Web analytics
| Outcome Indicator 1.4 | Outcome Indicator 1.4 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (2023) | Notes
| Citations of peer-reviewed publications or other altmetrics indicating use. | Percentage of all stakeholders in CEDIL stakeholder survey / feedback who are non-academic users and who say that CEDIL evidence outputs are useful or very useful |  |  | Planned | 0 | 0 | 0 |  | Too early to measure | TBD | TBD | TBD
|  |  | Citations are an incomplete and highly lagging indicator. Altmetric not appropriate for CEDIL. Propose using direct feedback from users instead. | Use 19/20 user survey to set a benchmark | Achieved
Source
|  |  | Citations will still be tracked and reported in progress reports |  |  | End of year user survey, baseline measurement at end of 2019/20 to set future benchmarks.
INPUTS (£) | DFID | DFID |  |  |  | Govt (£) |  | Other (£) |  |  | Total (£) |  | DFID SHARE (%)
| £20m | £20m
INPUTS (HR) | DFID (FTEs) | DFID (FTEs)
| A2 Evaluation Adviser and A2 Programme Manager | A2 Evaluation Adviser and A2 Programme Manager
OUTCOME 2 | Outcome Indicator 2.1 | Outcome Indicator 2.1 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (2023) | Notes | Assumptions
Increased capacity in the development and evaluation communities to commission and conduct evaluation in previously hard to evaluate areas | Number of attendees at training events or CEDIL conference who report that they are likely or very likely to use methods learned from CEDIL in future evaluation activities | Percentage of attendees at CEDIL events who report that they are likely to consider using methods / approaches learned learned from CEDIL in future evaluation activities | Report absolute numbers attending in the progress report, but difficult to estimate values for logframe | Report for all relevant events ie with methods content & where CEDIL is able to obtain feedback | Planned | 0 | 0 | 0 |  | Too early to measure | TBD | TBD | TBD |  | Context in which CEDIL findings are presented in conducive to their uptake
|  |  | Recognises broader range of events used by CEDIL to reach stakeholders | Use 19/20 user survey to set a benchmark | Achieved
|  |  | Rephrased as indicator below, using 'consider' as this is probably more realistic | Disaggregate by stakeholder group in progress report |  | Source
Event feedback summaries, measured from start of 2020/21
| Outcome Indicator 2.2 | Outcome Indicator 2.2 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (2023) | Notes
| Number of online survey respondents who report they are likely to consider methods learned from CEDIL when conducting or commissioning future evaluations | Percentage of online survey respondents who report they are likely to consider methods learned from CEDIL when conducting or commissioning future evaluations |  |  | Planned | 0 | 0 | 0 |  | Too early to measure | TBD | TBD | TBD
|  |  | Absolute numbers uncertain | Source: end of year survey | Achieved
|  |  |  | Use 19/20 user survey to set a benchmark |  | Source
|  |  |  | Disaggregate by stakeholder group in progress report |  | End of year user survey, baseline measurement at end of 2019/20 to set future benchmarks.
| Outcome Indicator 2.3 | Outcome Indicator 2.3 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (cumulative - 2023) | Notes
| Number of downloads of CEDIL methods outputs (guidance notes and tools) |  |  |  | Planned | 0 | 0 | 0 | Current 3 guideline papers which were largely emailed to projects | Too early to measure | TBD | TBD | TBD
|  |  |  | Needs clarity on POW outputs to estimate for future years | Achieved
|  |  |  | Ensure we have a clear classifcation of outputs |  | Source
Web analytics
INPUTS (£) | DFID | DFID |  |  |  | Govt (£) |  | Other (£) |  |  | Total (£) |  | DFID SHARE (%)
| £20m | £20m
INPUTS (HR) | DFID (FTEs) | DFID (FTEs)
| A2 Evaluation Adviser and A2 Programme Manager | A2 Evaluation Adviser and A2 Programme Manager
OUTPUT 1 | Output Indicator 1.1 | Output Indicator 1.1 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (cumulative - 2023) | Notes | Assumption
Relevant, high quality evaluations and methodological papers / outputs produced |  |  |  |  | Planned | 0 | 0 | 0 |  | 32 | 32 | 32 | 32 | Previous total 12 | Sufficient response from research and evaluation community to commission high quality work
| Number of high quality evaluation, synthesis and methods development projects commissioned | Number of high quality evaluation, synthesis and methods development projects commissioned |  |  | Achieved
Source
CEDIL Directorate progress reports
| Output Indicator 1.2 | Output Indicator 1.2 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (cumulative - 2023)
[5 empty] | Planned | 0 | 4 | 12 | 1 working paper produced and uploaded per project, plus RD outputs | 5 | 7 | 17 | 58 | Previous total 40
| Number of working papers published on CEDIL website, including synthesis and lessons learned papers | Number of working papers published on CEDIL website, including evaluations, synthesis and lessons learned papers | Explicitly includes evaluations, removed from 2.1 |  | Achieved |  | 4 | 13
Source
CEDIL Directorate progress reports
IMPACT WEIGHTING (%) | Output Indicator 1.3 | Output Indicator 1.3 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (cumulative - 2023)
[5 empty] | Planned | 0 | 1 | 5 | 1 paper produced per project for those expected to have enough time to produce publishable paper | 0 | 0 | 7 | 20 | Previous total 39
50% | Number of peer reviewed academic papers produced by PoW and RD |  | Clarify definition, if this means drafted, accepted or published |  | Achieved |  |  | 5
[5 empty] | Source | [9 empty] | RISK RATING
[5 empty] | CEDIL Directorate progress reports | [9 empty] | Medium
INPUTS (£) | DFID (£) | DFID (£) |  |  |  | Govt (£) | Other (£) |  |  |  |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 | Output Indicator 2.1 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (cumulative - 2023) |  | Assumption
User-oriented outputs produced by Directorate or Programmes of Work which provide clear policy recommendations and enable broader take-up of methodological innovations |  |  |  |  | Planned | 0 | 0 | 0 | 1 per project plus RD outputs | 9 | 7 | 17 | 46 | Previous total 12 | Sufficient high quality project proposals funded with clear stakeholder relevance
| Number of evaluation reports, policy briefs and methodological guidance notes produced and published on CEDIL website | Number of user-oriented summary products produced and published on CEDIL website, including policy briefs, portals/maps and methodological guidance notes | Moves evaluation reports into 1.2 and provides more detail on relevant accessible products | Individual outputs are counted against 1.2 or 2.1 only, they cannot be counted against more than one of these two indicators. | Achieved
|  |  |  | Includes user oriented products from fast track studies | Source
CEDIL Directorate progress reports
IMPACT WEIGHTING (%) | Output Indicator 2.2 | Output Indicator 2.2 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (cumulative - 2023)
[5 empty] | Planned | 0 | 4 | 2 | 1 per project (including those within lecture series) plus others ad hoc | 17 | 16 | 16 | 65 | Previous total 12
30% | Number of dissemination and training events held with DFID or other users by the Directorate or individual projects within programmes of work |  | Number of dissemination and training events held with DFID or other users by the Directorate or individual projects within programmes of work and attended by at least 20 people |  | Achieved |  |  | 7
Source
CEDIL Directorate progress reports
INPUTS (£) | DFID (£) | DFID (£) |  |  |  | Govt (£) | Other (£) |  |  |  |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 | Output Indicator 3.1 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (2023) | Notes | Assumption
A range of communication products and activities to disseminate its objectives, activities and outputs effectively to generate broad interest in CEDIL among the research, evaluation and user community |  |  |  |  | Planned | 0 | 0 | 6 | One per month, starting from Feb 2020 | 8 | 12 | 12 | 53 | Previous total 42 | Wider community responds to CEDIL communications efforts
| Number of blog posts or other substantial comms reports published on the CEDIL website | Number of blog and vlog posts published on the CEDIL website | Single and most relevant indicator of engagement |  | Achieved |  |  | 4
Source
CEDIL Directorate progress reports
| Output Indicator 3.2 | Output Indicator 3.2 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (2023) | Notes
[5 empty] | Planned | 0 | TBD | TBD | 2019/20 data used to set baseline then 20% growth p.a. | 1250 | 1500 | 1800 | 1980
| Number of individuals signed up to CEDIL newsletters, social media followers and visits to CEDIL website | Total number of CEDIL Twitter account followers | Single measure of immediate engagement effects of outreach efforts, broken down by high income vs LIMC location. Engagement with content will be captured by downloads. | Other indicators to be included in the progress reports, with further information on diversity in line with data available for each source | Achieved
| Number and diversity of stakeholders represented by these |  |  |  | Source | [9 empty] | RISK RATING
[5 empty] | Twitter account data | [9 empty] | Medium
IMPACT WEIGHTING (%) | Output Indicator 3.3 | Output Indicator 3.3 |  |  |  | Baseline 2016/17 | 2017/18 | 2018/19 |  | 2019/20 | 2020/21 | 2021/22 | Target (2023) | Notes
[5 empty] | Planned | 0 | 0 | 0 | Uses 60 attendees per event | 1020 | 960 | 960 | 3900
20% | Number of attendees at annual conference not directly funded by CEDIL | Total number of 'attendees' at CEDIL events, including post-event online viewing | Reflects multiple channels for communicating CEDIL work. Includes virtual and physical attendance at conferences and side events, lectures and presentations, webinars. Breakdown by directorate vs project-led events (details in progress reports) | Diversity data collected through registration for online events (gender, stakeholder group, organisation type, country) | Achieved |  |  | 49
| Number and diversity of stakeholders represented by these | Number and diversity of stakeholders represented by these | Breakdown by key stakeholder groups using enrolment data (where collected) |  | Source:
CEDIL Directorate event registration data
INPUTS (£) | DFID (£) | DFID (£) |  |  |  | Govt (£) | Other (£) |  |  |  |  | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs) | DFID (FTEs)
(1) Note 2023 figures are cumulative totals that also include new outputs in that programme year (6 months).